## FUA MAKURDI
FEDERAL UNIVERSITY OF AGRICULTURE, MAKURDI
PROCUREMENT PLAN
BUDGET YEAR: 2018
|  |  | BASIC DATA | [10 empty] | DRAFT-BID DOCUMENT |  | TIMELINE
S/N | PROJECT DESCRIPTION | PLAN/ ACTUAL | PACKAGE NUMBER | LOT NUMBER | PROCUREMENT PLAN DATE | PROCUREMENT CATEGORY | CONTRACT TYPE | ESTIMATED CONTRACT AMOUNT(N) | PROCUREMENT METHOD | APPROVAL THRESHOLD | QUALILIFICATION(PRE/POST) | REVIEW(PRIOR/POST) | SELECTION METHOD | PREPARATION OF BIDDING DOCUMENT&ADVERT BY MDA'S | MDA'S APPROVAL FOR BIDDING DOCUMENT & ADVERT | ADVERTISEMENT FOR PRE-QUALIFICATION | PREQUALIFICATION EVALUATION | SUBMISSION OF PREQUALIFICATION EVALUATION REPORT | MDA APPROVAL | BID INVITATION/SUBMISSION DATE | BID CLOSING/OPENING DATE | SUBMISSION OF BID EVALUATION REPORT | MDA APPROVAL/BPP NO OBJECTION DATE | CERTIFIABLE AMOUNT | FEC APPROVAL | DATE OF CONTRACT OFFER | DATE OF CONTRACT SIGNATURE | MOBILIZATION/ADVANCE PAYMENT | SUBSTANTIAL COMPLETION | FINAL ACCEPTANCE | ACTION PARTY | CHAMPION
1 | CONSTRUCTION OF ROADS AND DRAINAGE SYSTEMS | PLAN | UAM/WK/01 | N/A | 3RD JAN 2018 | WORKS | BILL OF QUANTITIES | N135,274,384.00 | NATIONAL COMPETITIVE BIDDING | PARASTAL TENDER'S BOARD | POST QUALIFICATION | POST REVIEW | LEAST EVALUATED RESPONSIVE COST | 3RD JAN 2018 TO 22ND JAN 2018 | 23RD JAN 2018 TO 31ST JAN 2018 | N/A | N/A | N/A | N/A | 1ST FEB2018 TO 15TH MAR 2018 | 15TH MAR 2018 | 16TH MAR 2018 TO 30TH MAR 2018 | 2ND APR 2018 TO 6TH APR 2018 | N135,274,384.00 | N/A | 20 TH APR 2018 | 23RD APR 2018 TO 7TH MAY 2018 | 8TH MAY 2018 TO 8TH JUNE2018 | 30WEEKS | 2 WEEKS | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
ACTUAL
2 | CONSTRUCTION OF SENATE BUILDING | PLAN | UAM/WK/02 | N/A | 3RD JAN 2018 | WORKS | BILL OF QUANTITIES | N328,725,616.00 | NATIONAL COMPETITIVE BIDDING | MINISTERIAL TENDER'S BOARD | PRE QUALIFICATION | PRIOR REVIEW | LEAST EVALUATED RESPONSIVE COST | 3RD JAN 2018 TO 22ND JAN 2018 | 23RD JAN 2018 TO 31ST JAN 2018 | 1ST FEB 2018 TO 15TH FEB 2018 | 16TH FEB 2018 TO 2ND MAR 2018 | 5TH MAR 2018 TO 19T H MAR 2018 | 20TH MAR 2018 TO 27TH MAR 2018 | 28TH MAR 2018 TO 7TH MAY 2018 | 7TH MAY 2018 | 8TH MAY 2018 TO 21ST MAY 2018 | 22ND MAY 2018 TO 29TH MAY 2018 | N328,725,616.00 | N/A | 13 TH JUNE 2018 | 14TH JUNE 2018 TO 28TH JUNE 2018 | 29TH JUNE 2018 TO 31ST JULY 2018 | 52WEEKS | 2 WEEKS | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
ACTUAL
3 | FENCING OF UNIVERSITY LANDMASS | PLAN | UAM/WK/03 | N/A | 3RD JAN 2018 | WORKS | BILL OF QUANTITIES | N133,758,128.00 | NATIONAL COMPETITIVE BIDDING | PARASTAL TENDER'S BOARD | POST QUALIFICATION | POST REVIEW | LEAST EVALUATED RESPONSIVE COST | 3RD JAN 2018 TO 22ND JAN 2018 | 23RD JAN 2018 TO 31ST JAN 2018 | N/A | N/A | N/A | N/A | 1ST FEB2018 TO 15TH MAR 2018 | 15TH MAR 2018 | 16TH MAR 2018 TO 30TH MAR 2018 | 2ND APR 2018 TO 6TH APR 2018 | N133,758,128.00 | N/A | 20 TH APR 2018 | 23RD APR 2018 TO 7TH MAY 2018 | 8TH MAY 2018 TO 8TH JUNE2018 | 30WEEKS | 2 WEEKS | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
|  | ACTUAL | [28 empty] | AGBEDE S.G(SENIOR PROCUREMENT OFFICER)
4 | CONSTRUCTION OF NEW WATER TREATMENT PLANT AND RETICULATION SYSTEM | PLAN | UAM/WK/04 | N/A | 3RD JAN 2018 | WORKS | BILL OF QUANTITIES | N89,172,085.00 | NATIONAL COMPETITIVE BIDDING | PARASTAL TENDER'S BOARD | POST QUALIFICATION | POST REVIEW | LEAST EVALUATED RESPONSIVE COST | 3RD JAN 2018 TO 22ND JAN 2018 | 23RD JAN 2018 TO 31ST JAN 2018 | N/A | N/A | N/A | N/A | 1ST FEB2018 TO 15TH MAR 2018 | 15TH MAR 2018 | 16TH MAR 2018 TO 30TH MAR 2018 | 2ND APR 2018 TO 6TH APR 2018 | N89,172,085.00 | N/A | 20 TH APR 2018 | 23RD APR 2018 TO 7TH MAY 2018 | 8TH MAY 2018 TO 8TH JUNE2018 | 30WEEKS | 2 WEEKS | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
|  | ACTUAL | [28 empty] | AGBEDE S.G(SENIOR PROCUREMENT OFFICER)
5 | CONSTRUCTION OF HATCHERY BUILDING WITH EQUIPMENT | PLAN | UAM/WK/05 | N/A | 3RD JAN 2018 | WORKS | BILL OF QUANTITIES | N120,955,788.00 | NATIONAL COMPETITIVE BIDDING | PARASTAL TENDER'S BOARD | POST QUALIFICATION | POST REVIEW | LEAST EVALUATED RESPONSIVE COST | 3RD JAN 2018 TO 22ND JAN 2018 | 23RD JAN 2018 TO 31ST JAN 2018 | N/A | N/A | N/A | N/A | 1ST FEB2018 TO 15TH MAR 2018 | 15TH MAR 2018 | 16TH MAR 2018 TO 30TH MAR 2018 | 2ND APR 2018 TO 6TH APR 2018 | N120,955,788.00 | N/A | 20 TH APR 2018 | 23RD APR 2018 TO 7TH MAY 2018 | 8TH MAY 2018 TO 8TH JUNE2018 | 30WEEKS | 2 WEEKS | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
ACTUAL
6 | PURCHASE OF TRACTOR AND FARMING IMPLEMENTS | PLAN | UAM/WK/06 | N/A | 3RD JAN 2018 | GOODS | BILL OF QUANTITIES | N84,586,043.00 | NATIONAL COMPETITIVE BIDDING | MINISTERIAL TENDER'S BOARD | POST QUALIFICATION | POST REVIEW | LEAST EVALUATED RESPONSIVE COST | 3RD JAN 2018 TO 22ND JAN 2018 | 23RD JAN 2018 TO 31ST JAN 2018 | N/A | N/A | N/A | N/A | 1ST FEB2018 TO 15TH MAR 2018 | 15TH MAR 2018 | 16TH MAR 2018 TO 30TH MAR 2018 | 2ND APR 2018 TO 6TH APR 2018 | N84,586,043.00 | N/A | 20 TH APR 2018 | 23RD APR 2018 TO 7TH MAY 2018 | 8TH MAY 2018 TO 8TH JUNE2018 | 30WEEKS | 2 WEEKS | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
ACTUAL
7 | FARM DEVELOPMENT FOR STUDENTS | PLAN | UAM/WK/07 | N/A | 3RD JAN 2018 | WORKS | BILL OF QUANTITIES | N53,439,532.00 | NATIONAL COMPETITIVE BIDDING | PARASTAL TENDER'S BOARD | POST QUALIFICATION | POST REVIEW | LEAST EVALUATED RESPONSIVE COST | 3RD JAN 2018 TO 22ND JAN 2018 | 23RD JAN 2018 TO 31ST JAN 2018 | N/A | N/A | N/A | N/A | 1ST FEB2018 TO 15TH MAR 2018 | 15TH MAR 2018 | 16TH MAR 2018 TO 30TH MAR 2018 | 2ND APR 2018 TO 6TH APR 2018 | N53,439,532.00 | N/A | 20 TH APR 2018 | 23RD APR 2018 TO 7TH MAY 2018 | 8TH MAY 2018 TO 8TH JUNE2018 | 30WEEKS | 2 WEEKS | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
ACTUAL
8 | CONSTRUCTION OF SEED SORTING AND CERTIFICATION CENTRE | PLAN | UAM/WK/08 | N/A | 3RD JAN 2018 | WORKS | BILL OF QUANTITIES | N110,758,128.00 | NATIONAL COMPETITIVE BIDDING | PARASTAL TENDER'S BOARD | POST QUALIFICATION | POST REVIEW | LEAST EVALUATED RESPONSIVE COST | 3RD JAN 2018 TO 22ND JAN 2018 | 23RD JAN 2018 TO 31ST JAN 2018 | N/A | N/A | N/A | N/A | 1ST FEB2018 TO 15TH MAR 2018 | 15TH MAR 2018 | 16TH MAR 2018 TO 30TH MAR 2018 | 2ND APR 2018 TO 6TH APR 2018 | N110,758,128.00 | N/A | 20 TH APR 2018 | 23RD APR 2018 TO 7TH MAY 2018 | 8TH MAY 2018 TO 8TH JUNE2018 | 30WEEKS | 2 WEEKS | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
ACTUAL
9 | CONSTRUCTION,FURNISHING AND EQUIPPING OF FEEDMILL | PLAN | UAM/WK/GDS/09 | N/A | 3RD JAN 2018 | WORKS | BILL OF QUANTITIES | N140,465,542.00 | NATIONAL COMPETITIVE BIDDING | PARASTAL TENDER'S BOARD | POST QUALIFICATION | POST REVIEW | LEAST EVALUATED RESPONSIVE COST | 3RD JAN 2018 TO 22ND JAN 2018 | 23RD JAN 2018 TO 31ST JAN 2018 | N/A | N/A | N/A | N/A | 1ST FEB2018 TO 15TH MAR 2018 | 15TH MAR 2018 | 16TH MAR 2018 TO 30TH MAR 2018 | 2ND APR 2018 TO 6TH APR 2018 | N140,465,542.00 | N/A | 20 TH APR 2018 | 23RD APR 2018 TO 7TH MAY 2018 | 8TH MAY 2018 TO 8TH JUNE2018 | 30WEEKS | 2 WEEKS | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
ACTUAL
10 | CONSTRUCTION AND FURNISNING OF 3-STOREY BLOCK OF ACADEMIC OFFICES FOR COLLEGE OF SCIENCE | PLAN | UAM/WK/GDS/010 | N/A | 3RD JAN 2018 | WORKS | BILL OF QUANTITIES | N518,000,000.00 | NATIONAL COMPETITIVE BIDDING | MINISTERIAL TENDER'S BOARD | PRE QUALIFICATION | PRIOR REVIEW | LEAST EVALUATED RESPONSIVE COST | 3RD JAN 2018 TO 22ND JAN 2018 | 23RD JAN 2018 TO 31ST JAN 2018 | 1ST FEB 2018 TO 15TH FEB 2018 | 16TH FEB 2018 TO 2ND MAR 2018 | 5TH MAR 2018 TO 19T H MAR 2018 | 20TH MAR 2018 TO 27TH MAR 2018 | 28TH MAR 2018 TO 7TH MAY 2018 | 7TH MAY 2018 | 8TH MAY 2018 TO 21ST MAY 2018 | 22ND MAY 2018 TO 29TH MAY 2018 | N518,000,000.00 | N/A | 13 TH JUNE 2018 | 14TH JUNE 2018 TO 28TH JUNE 2018 | 29TH JUNE 2018 TO 31ST JULY 2018 | 52WEEKS | 2 WEEKS | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
ACTUAL
11 | CONSTRUCTION,FURNISHING/EQUIPPING OF ICT CENTRE | PLAN | UAM/WK/GDS/011 | N/A | 3RD JAN 2018 | WORKS | BILL OF QUANTITIES | N300,000,000.00 | NATIONAL COMPETITIVE BIDDING | MINISTERIAL TENDER'S BOARD | PRE QUALIFICATION | PRIOR REVIEW | LEAST EVALUATED RESPONSIVE COST | 3RD JAN 2018 TO 22ND JAN 2018 | 23RD JAN 2018 TO 31ST JAN 2018 | 1ST FEB 2018 TO 15TH FEB 2018 | 16TH FEB 2018 TO 2ND MAR 2018 | 5TH MAR 2018 TO 19T H MAR 2018 | 20TH MAR 2018 TO 27TH MAR 2018 | 28TH MAR 2018 TO 7TH MAY 2018 | 7TH MAY 2018 | 8TH MAY 2018 TO 21ST MAY 2018 | 22ND MAY 2018 TO 29TH MAY 2018 | N300,000,000.00 | N/A | 13 TH JUNE 2018 | 14TH JUNE 2018 TO 28TH JUNE 2018 | 29TH JUNE 2018 TO 31ST JULY 2018 | 52WEEKS | 2 WEEKS | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
ACTUAL
12 | CONSTRUCTION,FURNISHING/EQUIPPING OF 1NO. 3-STOREY BLOCK OF CLASSROOMS AND LABORATORIES FOR COLLEGE OF AGRICULTURAL SCIENCE AND SCIENCE EDUATION | PLAN | UAM/WK/GDS/012 | N/A | 3RD JAN 2018 | WORKS | BILL OF QUANTITIES | N200,000,000.00 | NATIONAL COMPETITIVE BIDDING | PARASTAL TENDER'S BOARD | POST QUALIFICATION | POST REVIEW | LEAST EVALUATED RESPONSIVE COST | 3RD JAN 2018 TO 18TH JAN 2018 | 18TH JAN 2018 TO 24TH JAN 2018 | N/A | N/A | N/A | N/A | 25TH JAN 2015 TO 26TH MAR 2018 | 26TH MAR 2018 | 27TH MAR 2018 TO 2ND APR 2018 | 3RD APR 2018 TO 18TH APR 2018 | N200,000,000.00 | N/A | 26 TH APR 2018 | 27TH APR 2018 TO 4TH MAY 2018 | 7TH MAY 2018 TO 11TH MAY2018 | 3 WEEKS | 2WEEKS | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
ACTUAL
13 | CONSTRUCTION AND UPGRADING OF TOILETS IN ACADEMIC AREAS | PLAN | UAM/WK/013 | N/A | 3RD JAN 2018 | WORKS | BILL OF QUANTITIES | N120,000,000.00 | NATIONAL COMPETITIVE BIDDING | PARASTAL TENDER'S BOARD | POST QUALIFICATION | POST REVIEW | LEAST EVALUATED RESPONSIVE COST | 3RD JAN 2018 TO 18TH JAN 2018 | 18TH JAN 2018 TO 24TH JAN 2018 | N/A | N/A | N/A | N/A | 25TH JAN 2015 TO 26TH MAR 2018 | 26TH MAR 2018 | 27TH MAR 2018 TO 2ND APR 2018 | 3RD APR 2018 TO 18TH APR 2018 | N120,000,000.00 | N/A | 26 TH APR 2018 | 27TH APR 2018 TO 4TH MAY 2018 | 7TH MAY 2018 TO 11TH MAY2018 | 3 WEEKS | 2WEEKS | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
ACTUAL
14 | PROCUREMENT OF LIBRARY BOOKS AND EQUIPMENT | PLAN | UAM/GDS/014 | N/A | 3RD JAN 2018 | GOODS | BILL OF QUANTITIES | N114,000.000.00 | NATIONAL COMPETITIVE BIDDING | FEC | PRE QUALIFICATION | PRIOR REVIEW | LEAST EVALUATED RESPONSIVE COST | 3RD JAN 2018 TO 22ND JAN 2018 | 23RD JAN 2018 TO 31ST JAN 2018 | 1ST FEB 2018 TO 15TH FEB 2018 | 16TH FEB 2018 TO 2ND MAR 2018 | 5TH MAR 2018 TO 19T H MAR 2018 | 20TH MAR 2018 TO 27TH MAR 2018 | 28TH MAR 2018 TO 7TH MAY 2018 | 7TH MAY 2018 | 8TH MAY 2018 TO 21ST MAY 2018 | 22ND MAY 2018 TO 22ND JUNE 2018 | N114,000.000.00 | 25TH JUNE 2018 TO 27TH JULY 2018 | 3RD AUG 2018 TO 17TH AUG 2018 | 20TH AUG 2018 TO 4TH SEPT 2018 | 5TH SEPT 2018 TO 4TH OCT 2018 | 4WEEKS | 2 WEEKS | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
ACTUAL
15 | SUPPLY / INSTALLATION OF FURNITURE FOR 5N0. LECTURE THEATRES AT COLLEGE OF FORESTRY AND FISHERIES | PLAN | UAM/GDS/015 | N/A | 3RD JAN 2018 | GOODS | BILL OF QUANTITIES | N100,000,000.00 | NATIONAL COMPETITIVE BIDDING | FEC | PRE QUALIFICATION | PRIOR REVIEW | LEAST EVALUATED RESPONSIVE COST | 3RD JAN 2018 TO 22ND JAN 2018 | 23RD JAN 2018 TO 31ST JAN 2018 | 1ST FEB 2018 TO 15TH FEB 2018 | 16TH FEB 2018 TO 2ND MAR 2018 | 5TH MAR 2018 TO 19T H MAR 2018 | 20TH MAR 2018 TO 27TH MAR 2018 | 28TH MAR 2018 TO 7TH MAY 2018 | 7TH MAY 2018 | 8TH MAY 2018 TO 21ST MAY 2018 | 22ND MAY 2018 TO 22ND JUNE 2018 | N100,000,000.00 | 25TH JUNE 2018 TO 27TH JULY 2018 | 3RD AUG 2018 TO 17TH AUG 2018 | 20TH AUG 2018 TO 4TH SEPT 2018 | 5TH SEPT 2018 TO 4TH OCT 2018 | 4WEEKS | 2 WEEKS | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
ACTUAL
16 | FURNISHING OF 1000-SEAT CAPACITY LECTURE THEATER AT COLLEGE OF AGRICULTURAL SCIENCE AND SCIENCE EDUCATION | PLAN | UAM/GDS/016 | N/A | 3RD JAN 2018 | GOODS | BILL OF QUANTITIES | N55,000,000.00 | NATIONAL COMPETITIVE BIDDING | PARASTAL TENDER'S BOARD | POST QUALIFICATION | POST REVIEW | LEAST EVALUATED RESPONSIVE COST | 3RD JAN 2018 TO 22ND JAN 2018 | 23RD JAN 2018 TO 31ST JAN 2018 | N/A | N/A | N/A | N/A | 1ST FEB2018 TO 15TH MAR 2018 | 15TH MAR 2018 | 16TH MAR 2018 TO 30TH MAR 2018 | 2ND APR 2018 TO 6TH APR 2018 | N55,000,000.00 | N/A | 20 TH APR 2018 | 23RD APR 2018 TO 7TH MAY 2018 | 8TH MAY 2018 TO 8TH JUNE2018 | 30WEEKS | 2 WEEKS | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
ACTUAL
17 | SUPPLY AND INSTALLATION OF TEACHING AND LEARNING EQUIPMENT TO 6N0. LECTURE THEATRES AT COLLEGE OF FISHERIES(5N0) AND COLLEGE OF AGRICULTURAL SCIENCE AND SCIENCE EDUCATION(1N0) | PLAN | UAM/GDS/017 | N/A | 3RD JAN 2018 | GOODS | BILL OF QUANTITIES | N175,000,000.00 | NATIONAL COMPETITIVE BIDDING | PARASTAL TENDER'S BOARD | POST QUALIFICATION | POST REVIEW | LEAST EVALUATED RESPONSIVE COST | 3RD JAN 2018 TO 22ND JAN 2018 | 23RD JAN 2018 TO 31ST JAN 2018 | N/A | N/A | N/A | N/A | 1ST FEB2018 TO 15TH MAR 2018 | 15TH MAR 2018 | 16TH MAR 2018 TO 30TH MAR 2018 | 2ND APR 2018 TO 6TH APR 2018 | N175,000,000.00 | N/A | 20 TH APR 2018 | 23RD APR 2018 TO 7TH MAY 2018 | 8TH MAY 2018 TO 8TH JUNE2018 | 30WEEKS | 2 WEEKS | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
ACTUAL
18 | FURNISHING/EQUIPPING OF 3-STOREY BLOCK OF LABORATORIES AT COLLEGE OF SCIENCE | PLAN | UAM/GDS/018 | N/A | 3RD JAN 2018 | GOODS | BILL OF QUANTITIES | N150,000,000.00 | NATIONAL COMPETITIVE BIDDING | PARASTAL TENDER'S BOARD | POST QUALIFICATION | POST REVIEW | LEAST EVALUATED RESPONSIVE COST | 3RD JAN 2018 TO 22ND JAN 2018 | 23RD JAN 2018 TO 31ST JAN 2018 | N/A | N/A | N/A | N/A | 1ST FEB2018 TO 15TH MAR 2018 | 15TH MAR 2018 | 16TH MAR 2018 TO 30TH MAR 2018 | 2ND APR 2018 TO 6TH APR 2018 | N150,000,000.00 | N/A | 20 TH APR 2018 | 23RD APR 2018 TO 7TH MAY 2018 | 8TH MAY 2018 TO 8TH JUNE2018 | 30WEEKS | 2 WEEKS | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
ACTUAL
19 | ELECTRICITY/WATER SUPPLY, FENCING AND LANDSCAPING OF 4NO. NEW STUDENTS HOSTELS AT NORTH CORE | PLAN | UAM/WK/019 | N/A | 3RD JAN 2018 | WORKS | BILL OF QUANTITIES | N250,000,000.00 | NATIONAL COMPETITIVE BIDDING | MINISTERIAL TENDER'S BOARD | POST QUALIFICATION | POST REVIEW | LEAST EVALUATED RESPONSIVE COST | 3RD JAN 2018 TO 22ND JAN 2018 | 23RD JAN 2018 TO 31ST JAN 2018 | N/A | N/A | N/A | N/A | 1ST FEB2018 TO 15TH MAR 2018 | 15TH MAR 2018 | 16TH MAR 2018 TO 30TH MAR 2018 | 2ND APR 2018 TO 6TH APR 2018 | N250,000,000.00 | N/A | 20 TH APR 2018 | 23RD APR 2018 TO 7TH MAY 2018 | 8TH MAY 2018 TO 8TH JUNE2018 | 30WEEKS | 2 WEEKS | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
ACTUAL
20 | FURNISHING,ELECTRICITY/WATER SUPPLY AND LANDSCAPING OF 2NO. NEW STUDENTS HOSTELS AT SOUTH CORE | PLAN | UAM/WK/020 | N/A | 3RD JAN 2018 | WORKS | BILL OF QUANTITIES | N200,000,000.00 | NATIONAL COMPETITIVE BIDDING | PARASTAL TENDER'S BOARD | POST QUALIFICATION | POST REVIEW | LEAST EVALUATED RESPONSIVE COST | 3RD JAN 2018 TO 18TH JAN 2018 | 18TH JAN 2018 TO 24TH JAN 2018 | N/A | N/A | N/A | N/A | 25TH JAN 2015 TO 26TH MAR 2018 | 26TH MAR 2018 | 27TH MAR 2018 TO 2ND APR 2018 | 3RD APR 2018 TO 18TH APR 2018 | N200,000,000.00 | N/A | 26 TH APR 2018 | 27TH APR 2018 TO 4TH MAY 2018 | 7TH MAY 2018 TO 11TH MAY2018 | 30WEEKS | 26WEEKS | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
ACTUAL
21 | LAND ACQUISITION | PLAN | UAM/WK/021 | N/A | 3RD JAN 2018 | WORKS | BILL OF QUANTITIES | N60,000,000.00 | NATIONAL COMPETITIVE BIDDING | PARASTAL TENDER'S BOARD | N/A | POST REVIEW | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 25TH JAN 2015 TO 26TH MAR 2018 | 26TH MAR 2018 | 27TH MAR 2018 TO 2ND APR 2018 | 6TH SEPT 2018 TO 13TH SEPT 2018 | N60,000,000.00 | N/A | 14TH SE PT2018 TO 28TH SEPT 2018 | 2ND OCT2018 TO 16TH OCT 2018 | N/A | N/A | 17TH OCT 2018 TO 31ST OCT 2018 | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
ACTUAL
22 | PRINTING & STATIONARY | PLAN | UAM/GDS/022 | N/A | 3RD JAN 2018 | GOODS | BILL OF QUANTITIES | N146,901,341.84 | NATIONAL COMPETITIVE BIDDING | FEC | PRE QUALIFICATION | PRIOR REVIEW | LEAST EVALUATED RESPONSIVE COST | 3RD JAN 2018 TO 22ND JAN 2018 | 23RD JAN 2018 TO 31ST JAN 2018 | 1ST FEB 2018 TO 15TH FEB 2018 | 16TH FEB 2018 TO 2ND MAR 2018 | 5TH MAR 2018 TO 19T H MAR 2018 | 20TH MAR 2018 TO 27TH MAR 2018 | 28TH MAR 2018 TO 7TH MAY 2018 | 7TH MAY 2018 | 8TH MAY 2018 TO 21ST MAY 2018 | 22ND MAY 2018 TO 22ND JUNE 2018 | N146,901,341.84 | 25TH JUNE 2018 TO 27TH JULY 2018 | 3RD AUG 2018 TO 17TH AUG 2018 | 20TH AUG 2018 TO 4TH SEPT 2018 | 5TH SEPT 2018 TO 4TH OCT 2018 | 4WEEKS | 2 WEEKS | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
ACTUAL
23 | LABORATORY & TEACHING | PLAN | UAM/GDS/023 | N/A | 3RD JAN 2018 | GOODS | BILL OF QUANTITIES | N16,875,739.99 | NATIONAL COMPETITIVE BIDDING | PARASTAL TENDER'S BOARD | POST QUALIFICATION | POST REVIEW | LEAST EVALUATED RESPONSIVE COST | 3RD JAN 2018 TO 22ND JAN 2018 | 23RD JAN 2018 TO 31ST JAN 2018 | N/A | N/A | N/A | N/A | 1ST FEB2018 TO 15TH MAR 2018 | 15TH MAR 2018 | 16TH MAR 2018 TO 30TH MAR 2018 | 2ND APR 2018 TO 6TH APR 2018 | N16,875,739.99 | N/A | 20 TH APR 2018 | 23RD APR 2018 TO 7TH MAY 2018 | 8TH MAY 2018 TO 8TH JUNE2018 | 4WEEKS | 2 WEEKS | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
ACTUAL
24 | MOTOR VEHICLES | PLAN | UAM/WK/024 | N/A | 3RD JAN 2018 | GOODS | BILL OF QUANTITIES | N204,000,000.00 | NATIONAL COMPETITIVE BIDDING | FEC | PRE QUALIFICATION | PRIOR REVIEW | LEAST EVALUATED RESPONSIVE COST | 3RD JAN 2018 TO 22ND JAN 2018 | 23RD JAN 2018 TO 31ST JAN 2018 | 1ST FEB 2018 TO 15TH FEB 2018 | 16TH FEB 2018 TO 2ND MAR 2018 | 5TH MAR 2018 TO 19T H MAR 2018 | 20TH MAR 2018 TO 27TH MAR 2018 | 28TH MAR 2018 TO 7TH MAY 2018 | 7TH MAY 2018 | 8TH MAY 2018 TO 21ST MAY 2018 | 22ND MAY 2018 TO 22ND JUNE 2018 | N204,000,000.00 | 25TH JUNE 2018 TO 27TH JULY 2018 | 3RD AUG 2018 TO 17TH AUG 2018 | 20TH AUG 2018 TO 4TH SEPT 2018 | 5TH SEPT 2018 TO 4TH OCT 2018 | 4WEEKS | 2 WEEKS | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
ACTUAL
25 | DRUGS & DRESSINGS | PLAN | UAM/WK/025 | N/A | 3RD JAN 2018 | GOODS | BILL OF QUANTITIES | N14,000,000.00 | NATIONAL COMPETITIVE BIDDING | PARASTAL TENDER'S BOARD | POST QUALIFICATION | POST REVIEW | LEAST EVALUATED RESPONSIVE COST | 3RD JAN 2018 TO 22ND JAN 2018 | 23RD JAN 2018 TO 31ST JAN 2018 | N/A | N/A | N/A | N/A | 1ST FEB2018 TO 15TH MAR 2018 | 15TH MAR 2018 | 16TH MAR 2018 TO 30TH MAR 2018 | 2ND APR 2018 TO 6TH APR 2018 | N14,000,000.00 | N/A | 20 TH APR 2018 | 23RD APR 2018 TO 7TH MAY 2018 | 8TH MAY 2018 TO 8TH JUNE2018 | 4WEEKS | 2 WEEKS | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
ACTUAL
26 | FURNITURE & FITTING | PLAN | UAM/GDS/026 | N/A | 3RD JAN 2018 | GOODS | BILL OF QUANTITIES | N124,577,400.00 | NATIONAL COMPETITIVE BIDDING | FEC | PRE QUALIFICATION | PRIOR REVIEW | LEAST EVALUATED RESPONSIVE COST | 3RD JAN 2018 TO 22ND JAN 2018 | 23RD JAN 2018 TO 31ST JAN 2018 | 1ST FEB 2018 TO 15TH FEB 2018 | 16TH FEB 2018 TO 2ND MAR 2018 | 5TH MAR 2018 TO 19T H MAR 2018 | 20TH MAR 2018 TO 27TH MAR 2018 | 28TH MAR 2018 TO 7TH MAY 2018 | 7TH MAY 2018 | 8TH MAY 2018 TO 21ST MAY 2018 | 22ND MAY 2018 TO 22ND JUNE 2018 | N124,577,400.00 | 25TH JUNE 2018 TO 27TH JULY 2018 | 3RD AUG 2018 TO 17TH AUG 2018 | 20TH AUG 2018 TO 4TH SEPT 2018 | 5TH SEPT 2018 TO 4TH OCT 2018 | 4WEEKS | 2 WEEKS | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
ACTUAL
27 | PLANT & EQUIPMENT | PLAN | UAM/GDS/027 | N/A | 3RD JAN 2018 | GOODS | BILL OF QUANTITIES | N266,305,000.00 | NATIONAL COMPETITIVE BIDDING | FEC | PRE QUALIFICATION | PRIOR REVIEW | LEAST EVALUATED RESPONSIVE COST | 3RD JAN 2018 TO 22ND JAN 2018 | 23RD JAN 2018 TO 31ST JAN 2018 | 1ST FEB 2018 TO 15TH FEB 2018 | 16TH FEB 2018 TO 2ND MAR 2018 | 5TH MAR 2018 TO 19T H MAR 2018 | 20TH MAR 2018 TO 27TH MAR 2018 | 28TH MAR 2018 TO 7TH MAY 2018 | 7TH MAY 2018 | 8TH MAY 2018 TO 21ST MAY 2018 | 22ND MAY 2018 TO 22ND JUNE 2018 | N266,305,000.00 | 25TH JUNE 2018 TO 27TH JULY 2018 | 3RD AUG 2018 TO 17TH AUG 2018 | 20TH AUG 2018 TO 4TH SEPT 2018 | 5TH SEPT 2018 TO 4TH OCT 2018 | 4WEEKS | 2 WEEKS | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
ACTUAL
28 | BOOKS & JOURNALS | PLAN | UAM/GDS/028 | N/A | 3RD JAN 2018 | GOODS | BILL OF QUANTITIES | N7,160,000.00 | NATIONAL COMPETITIVE BIDDING | PARASTAL TENDER'S BOARD | POST QUALIFICATION | POST REVIEW | LEAST EVALUATED RESPONSIVE COST | 3RD JAN 2018 TO 22ND JAN 2018 | 23RD JAN 2018 TO 31ST JAN 2018 | N/A | N/A | N/A | N/A | 1ST FEB2018 TO 15TH MAR 2018 | 15TH MAR 2018 | 16TH MAR 2018 TO 30TH MAR 2018 | 2ND APR 2018 TO 6TH APR 2018 | N7,160,000.00 | N/A | 20 TH APR 2018 | 23RD APR 2018 TO 7TH MAY 2018 | 8TH MAY 2018 TO 8TH JUNE2018 | 4WEEKS | 2 WEEKS | AGBEDE S.G(SENIOR PROCUREMENT OFFICER) | MR.CHRIS O.OLA(DIRECTOR PROCUREMENT)
ACTUAL

## SON
PROCUREMENT PLAN
PROCURING ENTITY |  | STANDARDS ORGANISATION OF NIGERIA (SON)
MINISTRY |  | FEDERAL MINISTRY OF INDUSTRY, TRADE AND INVESTMENT
FINANCIAL YEAR |  | 2018
WORKS (CONSTRUCTION)
S/NO | PROJECT DESCRIPTION | LOT NO | LUMP SUM OR BOQ | PROCUREMENT METHOD | BUDGETARY AMOUNT (₦) | APPROVAL THRESHOLD | ADVERT FOR PRE-QUALIFICATION | BID INVITATION DATE | BID CLOSING DATE | BID EVALUATION | APPROVAL/ | AWARD FEC APPROVAL | CONTRACT AMOUNT | CONTRACT SIGNING | CONTRACT DURATION
[11 empty] | “NO OBJECTION” |  | N
1 | Construction of Headquarters Office Complex (Phase II) & Perimeter Fencing | WK I (1) | BOQ | NCB | 296000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 295400000 | 2018-09-11 | 52 WEEKS
2 | Construction of Office Complex Gudu (Phase II) | WK I (2) | BOQ | NCB | 285000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 284900000 | 2018-09-11 | 52 WEEKS
3 | Construction of National Meterology Institute (Phase II) | WK I (3) | BOQ | NCB | 300000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 298350000 | 2018-09-11 | 52 WEEKS
4 | construction of tunnel, parking bay & basement for National Metrology Institute Emene, Enugu | WK I (4) | BOQ | NCB | 295000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 294550000 | 2018-09-11 | 52 WEEKS
5 | Construction of Administrative /Laboratory Office (Ogba Lagos) | WK I (5) | BOQ | NCB | 290000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 289750000 | 2018-09-11 | 52 WEEKS
6 | Construction of Administrative /Laboratory Office (Ado Ekiti) | WK I (6) | BOQ | NCB | 295000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 293340000 | 2018-09-11 | 52 WEEKS
7 | Construction of Administrative /Laboratory Office (Ilorin) | WK I (7) | BOQ | NCB | 300000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 299030000 | 2018-09-11 | 52 WEEKS
8 | Construction of Administrative /Laboratory Office (Portharcourt) | WK I (8) | BOQ | NCB | 298000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 297050000 | 2018-09-11 | 52 WEEKS
9 | Construction of Administrative /Laboratory Office (Bauchi) | WK I (9) | BOQ | NCB | 290000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 288950000 | 2018-09-11 | 52 WEEKS
10 | Construction of Administrative /Laboratory Office (Awka) | WK I (10) | BOQ | NCB | 290000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 288340000 | 2018-09-11 | 52 WEEKS
11 | Construction of Administrative /Laboratory Office (Lokoja) | WK I (11) | BOQ | NCB | 295000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 294940000 | 2018-09-11 | 52 WEEKS
WORKS (PROVISION & INSTALLATION OF LABORATORY EQUIPMENT)
12 | Provision & installation of Laboratory equipment (Food Laboratory)(Ogba Lagos) | WKII1 | BOQ | NCB | 300000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 299950000 | 2018-09-11 | 26 WEEKS
13 | Provision & installation of Laboratory equipment (Electrical Laboratory)(Ogba Lagos) | WKII2 | BOQ | NCB | 300000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 298490000 | 2018-09-11 | 26 WEEKS
WORKS (CONSTRUCTION)
14 | Construction of Perimeter Fencing, Sokoto | WKIII1 | BOQ | NCB | 35000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 34970000 | 2018-09-11 | 26 WEEKS
15 | Construction of Borehole | WKIII2 | BOQ | NCB | 10000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 9140000 | 2018-09-11 | 26 WEEKS
WORKS (RENOVATION OF LABORATORY & OFFICES)
16 | Renovation of Office Building Kaduna |  | BOQ | NCB | 30000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 29330000 | 2018-09-11 | 26 WEEKS
17 | Renovation of Office Building Oyo state office (Saki) | WKIV2 | BOQ | NCB | 35000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 34590000 | 2018-09-11 | 26 WEEKS
18 | Renovation of Office Building Akure | WKIV3 | BOQ | NCB | 30000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 28530000 | 2018-09-11 | 26 WEEKS
19 | Renovation of Office Building yobe | WKIV4 | BOQ | NCB | 30000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 29750000 | 2018-09-11 | 26 WEEKS
20 | Renovation of Office Building Lagos | WKIV5 | BOQ | NCB | 70000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 68250000 | 2018-09-11 | 26 WEEKS
CATEGORY B: GOODS (VEHICLES)
21 | Procurement & Supply of Vehicles, Abuja | GDI 1 | BOQ | NCB | 50000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 49950000 | 2018-09-11 | 13 WEEKS
22 | Procurement & Supply of Vehicles Enugu | GDI 2 | BOQ | NCB | 50000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 48750000 | 2018-09-11 | 13 WEEKS
23 | Procurement & Supply of Vehicles Owerri | GDI 3 | BOQ | NCB | 50000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 49950000 | 2018-09-11 | 13 WEEKS
24 | Procurement & Supply of Vehicles PortHarcourt | GDI 4 | BOQ | NCB | 50000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 47890000 | 2018-09-11 | 13 WEEKS
25 | Procurement & Supply of Vehicles Lagos | GDI 5 | BOQ | NCB | 50000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 49930000 | 2018-09-11 | 13 WEEKS
26 | Procurement & Supply of Vehicles Kaduna | GDI 6 | BOQ | NCB | 50000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 49980000 | 2018-09-11 | 13 WEEKS
27 | Procurement & Supply of Vehicles Bauchi | GDI 7 | BOQ | NCB | 50000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 47750000 | 2018-09-11 | 13 WEEKS
28 | Procurement & Supply of Vehicles Awka | GDI 8 | BOQ | NCB | 50000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 47630000 | 2018-09-11 | 13 WEEKS
CATEGORY B: GOODS (FURNITURE & OFFICE EQUIPMENT)
29 | Procurement & Supply of Laboratory Furniture Ogba Lagos | GDII 1 | BOQ | NCB | 50000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 48350000 | 2018-09-11 | 13 WEEKS
30 | Procurement & Supply of Office Furniture Ogba Lagos | GDII 2 | BOQ | NCB | 25000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 24990000 | 2018-09-11 | 13 WEEKS
31 | Procurement & Supply of Office Furniture Abuja | GDII 5 | BOQ | NCB | 25000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 24940000 | 2018-09-11 | 13 WEEKS
32 | Procurement & Supply of Office Furniture Enugu | GDII 6 | BOQ | NCB | 25000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 24350000 | 2018-09-11 | 13 WEEKS
33 | Procurement & Supply of Office Furniture PortHarcourt | GDII 7 | BOQ | NCB | 15000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 14980000 | 2018-09-11 | 13 WEEKS
34 | Procurement & Supply of Office Furniture Kaduna | GDII 8 | BOQ | NCB | 10000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 9450000 | 2018-09-11 | 13 WEEKS
35 | Procurement & Supply of Office Furniture Bauchi | GDII 9 | BOQ | NCB | 15000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 14780000 | 2018-09-11 | 13 WEEKS
36 | Procurement & Supply of Safes & Cabinets Abuja | GDII 10 | BOQ | NCB | 15000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 14980000 | 2018-09-11 | 13 WEEKS
CATEGORY B: GOODS (COMPUTERS)
37 | Procurement & Supply of Desktop Computers Abuja | GDIII 1 | BOQ | NCB | 30000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 29330000 | 2018-09-11 | 13 WEEKS
38 | Procurement & Supply of Desktop Computers Lagos | GDIII 2 | BOQ | NCB | 30000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 29450000 | 2018-09-11 | 13 WEEKS
39 | Procurement & Supply of Laptop Computers Abuja | GDIII 3 | BOQ | NCB | 30000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 29250000 | 2018-09-11 | 13 WEEKS
40 | Procurement & Supply of Laptop Computers Lagos | GDIII 4 | BOQ | NCB | 30000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 29730000 | 2018-09-11 | 13 WEEKS
41 | Procurement & Supply of Printers, UPS, Stabilizers, Toners, etc. Abuja | GDIII 5 | BOQ | NCB | 25000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 24340000 | 2018-09-11 | 13 WEEKS
42 | Procurement & Supply of Printers, UPS, Stabilizers, Toners, etc. Lagos | GDIII 6 | BOQ | NCB | 25000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 24550000 | 2018-09-11 | 13 WEEKS
43 | Procurement & Supply of Photocopiers Abuja | GDIII 7 | BOQ | NCB | 25000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 24350000 | 2018-09-11 | 13 WEEKS
44 | Procurement & Supply of Photocopiers Lagos | GDIII 8 | BOQ | NCB | 25000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 24390000 | 2018-09-11 | 13 WEEKS
45 | Procurement & Supply of Projector, Projector Screens, Digital Cameras, Public Address System, etc. Abuja | GDIII 9 | BOQ | NCB | 25000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 24650000 | 2018-09-11 | 13 WEEKS
46 | Procurement & Supply of Library Cabinet Enugu | GDIII 10 | BOQ | NCB | 20000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 19830000 | 2018-09-11 | 13 WEEKS
CATEGORY B: GOODS (TRUCKS)
47 | Procurement & Supply of heavy duty truck, Lagos. | GDIV1 | BOQ | NCB | 50000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 49870000 | 2018-09-11 | 13 WEEKS
48 | Procurement & Supply of crane, Lagos. | GDIV2 | BOQ | NCB | 50000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 49580000 | 2018-09-11 | 13 WEEKS
CATEGORY B: GOODS (GENERATORS)
49 | Procurement & supply of Generators (Abuja & Kaduna) | GDV1 | BOQ | NCB | 100000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 98490000 | 2018-09-11 | 13 WEEKS
CATEGORY B: GOODS (DIESEL)
50 | Procurement & Supply of Diesel Abuja | GDVI 1 | BOQ | NCB | 20000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 19950000 | 2018-09-11 | 13 WEEKS
51 | Procurement & Supply of Diesel Lagos | GDVI 2 | BOQ | NCB | 20000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 19780000 | 2018-09-11 | 13 WEEKS
52 | Procurement & Supply of Stationery Items Enugu | GDVI 3 | BOQ | NCB | 20000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 19250000 | 2018-09-11 | 13 WEEKS
CATEGORY B: GOODS (STATIONERY ITEMS)
53 | Procurement and supply of stationery items Abuja | GDVII 1 | BOQ | NCB | 25000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 24950000 | 2018-09-11 | 13 WEEKS
54 | Procurement and supply of stationery items Lagos | GDVII 2 | BOQ | NCB | 25000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 24960000 | 2018-09-11 | 13 WEEKS
CATEGORY B: GOODS (PRINTING)
55 | Printing & delivery of SON handbills, booklets etc (Nationwide) | PR 1 | BOQ | NCB | 50000000 | PTB/MTB | NA | 2018-03-09 | 15/10/2018 | 15/10/2018-29/10/2018 | 2018-06-11 | NA | 49940000 | 2018-09-11 | 13 WEEKS
S/N | PROJECT DESCRIPTION | LOT NO | LUMP SUM OR BOQ | PROCUREMENT METHOD | BUDGETARY AMOUNT IN MILLION (N) | APPROVAL THRESHOLD | ADVERT FOR EOI | EVALUATION OF EOI | BID INVITATION FOR RFP | BID CLOSING DATE | BID EVALUATION | APPROVAL/ | AWARD FEC APPROVAL | CONTRACT AMOUNT IN MILLION | CONTRACT SIGNING | CONTRACT DURATION
[12 empty] | “NO OBJECTION” |  | N
CONSULTANCY SERVICES
1 | Software Services in Wuse zone 7, Abuja | ICT 001 | LUMP SUM | QCBS | 100M | PTB/MTB | 03/9/2018-17/9/2018 | 17/9/2018-02/10/2018 | 03/10/2018-31/10/2018 | 31/10/2018 | 1/11/2018-5/11/2018 | 2018-06-11 | N/A | 98M | 2018-07-11 | 26 WEEKS
2 | Hardware & Software networking | ICT 002 | LUMP SUM | QCBS | 100M | PTB/MTB | 03/9/2018-17/9/2018 | 17/9/2018-02/10/2018 | 03/10/2018-31/10/2018 | 31/10/2018 | 1/11/2018-5/11/2018 | 2018-06-11 | N/A | 97.37M | 2018-07-11 | 26 WEEKS
3 | Production & Airing of SON Television Programme/Jingles, Nationwide | PB 001 | LUMP SUM | QCBS | 100M | PTB/MTB | 03/9/2018-17/9/2018 | 17/9/2018-02/10/2018 | 03/10/2018-31/10/2018 | 31/10/2018 | 1/11/2018-5/11/2018 | 2018-06-11 | N/A | 99.5M | 2018-07-11 | 26 WEEKS
4 | Production & Airing of SON Radio Programme/Jingles, Nationwide | PB 002 | LUMP SUM | QCBS | 100M | PTB/MTB | 03/9/2018-17/9/2018 | 17/9/2018-02/10/2018 | 03/10/2018-31/10/2018 | 31/10/2018 | 1/11/2018-5/11/2018 | 2018-06-11 | N/A | 99.5M | 2018-07-11 | 26 WEEKS
5 | General Sensitisation Programme Nationwide | GS 001 | LUMP SUM | QCBS | 300M | PTB/MTB | 03/9/2018-17/9/2018 | 17/9/2018-02/10/2018 | 03/10/2018-31/10/2018 | 31/10/2018 | 1/11/2018-5/11/2018 | 2018-06-11 | N/A | 99.5M | 2018-07-11 | 26 WEEKS
6 | Products Quality support, Nationwide | GS 002 | LUMP SUM | QCBS | 300M | PTB/MTB | 03/9/2018-17/9/2018 | 17/9/2018-02/10/2018 | 03/10/2018-31/10/2018 | 31/10/2018 | 1/11/2018-5/11/2018 | 2018-06-11 | N/A | 99.5M | 2018-07-11 | 26 WEEKS
7 | Environmental Management Awareness, Nationwide | GS 003 | LUMP SUM | QCBS | 300M | PTB/MTB | 03/9/2018-17/9/2018 | 17/9/2018-02/10/2018 | 03/10/2018-31/10/2018 | 31/10/2018 | 1/11/2018-5/11/2018 | 2018-06-11 | N/A | 99.25M | 2018-07-11 | 26 WEEKS
8 | Capacity Building, Nationwide | GS 004 | LUMP SUM | QCBS | 300M | PTB/MTB | 03/9/2018-17/9/2018 | 17/9/2018-02/10/2018 | 03/10/2018-31/10/2018 | 31/10/2018 | 1/11/2018-5/11/2018 | 2018-06-11 | N/A | 98.25M | 2018-07-11 | 26 WEEKS
9 | Best Practices on Standardisation, Nationwide | GS 005 | LUMP SUM | QCBS | 300M | PTB/MTB | 03/9/2018-17/9/2018 | 17/9/2018-02/10/2018 | 03/10/2018-31/10/2018 | 31/10/2018 | 1/11/2018-5/11/2018 | 2018-06-11 | N/A | 98.75M | 2018-07-11 | 26 WEEKS
10 | Training for Youths, Women & Vulnerable people on standard production of raw material, nationwide | GS 006 | LUMP SUM | QCBS | 120M | PTB/MTB | 03/9/2018-17/9/2018 | 17/9/2018-02/10/2018 | 03/10/2018-31/10/2018 | 31/10/2018 | 1/11/2018-5/11/2018 | 2018-06-11 | N/A | 99.65M | 2018-07-11 | 26 WEEKS
11 | Insurance services:Group Life for All SON staff | INS 001 | LUMP SUM | QCBS | 300M | PTB/MTB | 03/9/2018-17/9/2018 | 17/9/2018-02/10/2018 | 03/10/2018-31/10/2018 | 31/10/2018 | 1/11/2018-5/11/2018 | 2018-06-11 | N/A | 99.14M | 2018-07-11 | 26 WEEKS
12 | Insurance Services:Non - Life (Building & Assets) Nationwide | INS 002 | LUMP SUM | QCBS | 300M | PTB/MTB | 03/9/2018-17/9/2018 | 17/9/2018-02/10/2018 | 03/10/2018-31/10/2018 | 31/10/2018 | 1/11/2018-5/11/2018 | 2018-06-11 | N/A | 99.14M | 2018-07-11 | 26 WEEKS
13 | Auditing Consulting in Lagos & Abuja | AUD 001 | LUMP SUM | QCBS | 25M | PTB/MTB | 03/9/2018-17/9/2018 | 17/9/2018-02/10/2018 | 03/10/2018-31/10/2018 | 31/10/2018 | 1/11/2018-5/11/2018 | 2018-06-11 | N/A | 24.5M | 2018-07-11 | 26 WEEKS
14 | Supervision of Building construction Services works,Corporate Headquarters, Regional & state offices | GS 001 | LUMP SUM | QCBS | 200M | PTB/MTB | 03/9/2018-17/9/2018 | 17/9/2018-02/10/2018 | 03/10/2018-31/10/2018 | 31/10/2018 | 1/11/2018-5/11/2018 | 2018-06-11 | N/A | 99.45M | 2018-07-11 | 26 WEEKS
15 | Installation of Specialised Equipment, in Lagos | GS 002 | LUMP SUM | QCBS | 60M | PTB/MTB | 03/9/2018-17/9/2018 | 17/9/2018-02/10/2018 | 03/10/2018-31/10/2018 | 31/10/2018 | 1/11/2018-5/11/2018 | 2018-06-11 | N/A | 59.5M | 2018-07-11 | 26 WEEKS
16 | Maintenance of specialised Equipment, Abuja, Enugu, Kaduna & Lagos | GS 003 | LUMP SUM | QCBS | 60M | PTB/MTB | 03/9/2018-17/9/2018 | 17/9/2018-02/10/2018 | 03/10/2018-31/10/2018 | 31/10/2018 | 1/11/2018-5/11/2018 | 2018-06-11 | N/A | 59.5M | 2018-07-11 | 26 WEEKS
17 | Maintenance of Generators, Abuja, Lagos & Enugu | GS 004 | LUMP SUM | QCBS | 50M | PTB/MTB | 03/9/2018-17/9/2018 | 17/9/2018-02/10/2018 | 03/10/2018-31/10/2018 | 31/10/2018 | 1/11/2018-5/11/2018 | 2018-06-11 | N/A | 48.95M | 2018-07-11 | 26 WEEKS
18 | Cleaning & Fumigation, Abuja | GS 005 | LUMP SUM | QCBS | 20M | PTB/MTB | 03/9/2018-17/9/2018 | 17/9/2018-02/10/2018 | 03/10/2018-31/10/2018 | 31/10/2018 | 1/11/2018-5/11/2018 | 2018-06-11 | N/A | 19.25M | 2018-07-11 | 26 WEEKS
19 | Cleaning & Fumigation, Lagos | GS 006 | LUMP SUM | QCBS | 50M | PTB/MTB | 03/9/2018-17/9/2018 | 17/9/2018-02/10/2018 | 03/10/2018-31/10/2018 | 31/10/2018 | 1/11/2018-5/11/2018 | 2018-06-11 | N/A | 49.95M | 2018-07-11 | 26 WEEKS
20 | Cleaning & Fumigation, Enugu | GS 007 | LUMP SUM | QCBS | 25M | PTB/MTB | 03/9/2018-17/9/2018 | 17/9/2018-02/10/2018 | 03/10/2018-31/10/2018 | 31/10/2018 | 1/11/2018-5/11/2018 | 2018-06-11 | N/A | 24.25M | 2018-07-11 | 26 WEEKS
21 | Cleaning & Fumigation,Kaduna | GS 008 | LUMP SUM | QCBS | 20M | PTB/MTB | 03/9/2018-17/9/2018 | 17/9/2018-02/10/2018 | 03/10/2018-31/10/2018 | 31/10/2018 | 1/11/2018-5/11/2018 | 2018-06-11 | N/A | 19.29M | 2018-07-11 | 26 WEEKS

## NEPAD Consultancy Services
Ministry/Department/Agency: Test Department
Budget Year: 2018
|  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2.2 - 2 weeks | 3 weeks | 2 - 4 weeks | 2 weeks | 4 - 6 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
OTHER SERVICES - GENERAL | Plan | SERVICES/2018/3 | 1 | Lump-Sum | 125840000 | NCB | Parastatals Tenders Board | CQ-Consultant &qualification | NA | POST REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 125840000 | NA | 21/02/18-7/03/18 | 8/03/18-22/03/18 | NA | NA | NA | 125840000 | B.A ILEMORE (Designation; Director) | N.A. RAFFINDADI (Designation; Managing Director)
| Actual | 220206 | 1 | Lump-Sum | 53770383 | NCB | Ministerial Tenders Board | CQ-Consultant &qualification | NA | POST REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 53770383 | NA | 21/02/18-7/03/18 | 13/09/16 -20/09/16 | NA | NA | NA | 53770383 | B.A ILEMORE (Designation; Director) | N.A. RAFFINDADI (Designation; Managing Director)
CONSULTING & PROFESSIONAL SERVICES -GENERAL | Plan | SERVICES/2018/3 | 2 | Lump-Sum | 100000000 | NCB | Ministerial Tenders Board | CQ-Consultant &qualification | NA | POST REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 100000000 | NA | 21/02/18-7/03/18 | 8/03/18-22/03/18 | NA | NA | NA | 100000000 | B.A ILEMORE (Designation; Director) | N.A. RAFFINDADI (Designation; Managing Director)
| Actual | 220207 | 2 | Lump-Sum | 74820988 | NCB | Ministerial Tenders Board | CQ-Consultant &qualification | NA | POST REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 74820988 | NA | 21/02/18-7/03/18 | 13/09/16 -20/09/16 | NA | NA | NA | 74820988 | B.A ILEMORE (Designation; Director) | N.A. RAFFINDADI (Designation; Managing Director)
FINANCIAL CHARGES-GENERAL | Plan | SERVICES/2018/3 | 3 | Lump-Sum | 50000000 | NCB | Parastatals Tenders Board | CQ-Consultant &qualification | NA | POST REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 50000000 | NA | 21/02/18-7/03/18 | 8/03/18-22/03/18 | NA | NA | NA | 50000000 | B.A ILEMORE (Designation; Director) | N.A. RAFFINDADI (Designation; Managing Director)
| Actual | 220209 | 3 | Lump-Sum | 31815000 | NCB | Parastatals Tenders Board | CQ-Consultant &qualification | NA | POST REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 31815000 | NA | 21/02/18-7/03/18 | 13/09/16 -20/09/16 | NA | NA | NA | 31815000 | B.A ILEMORE (Designation; Director) | N.A. RAFFINDADI (Designation; Managing Director)
MISCELLANEOUS | Plan | SERVICES/2018/3 | 4 | Lump-Sum | 200000000 | NCB | Ministerial Tenders Board | CQ-Consultant &qualification | NA | POST REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 200000000 | NA | 21/02/18-7/03/18 | 8/03/18-22/03/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation; Director) | N.A. RAFFINDADI (Designation; Managing Director)
| Actual | 220210 | 4 | Lump-Sum | 101611132 | NCB | Ministerial Tenders Board | CQ-Consultant &qualification | NA | POST REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 101611132 | NA | 21/02/18-7/03/18 | 13/09/16 -20/09/16 | NA | NA | NA | 101611132 | B.A ILEMORE (Designation; Director) | N.A. RAFFINDADI (Designation; Managing Director)

## NEPAD Goods
Ministry/Department/Agency: Test Department
Budget Year: 2018
|  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Goods |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Arrival of Goods | Inspection/Final Acceptance | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
Plan vs Actual
MATERIALS ANDS SUPPLIES- GENERAL | Plan | GOODS/2018/2 | 1 | BILL OF QUANTITIES | 17000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST -REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | 21/02/18-21/03/18 | 22/03/18-5/04/18 | 9/04/18-7/05/18 | 2018-08-05 | 19/06/18 | 20/06/18-11/07/18 | 2018-12-07 | 17000000 | NA | 13/08/18-27/08/18 | 28/08/18-11/09/18 | NA | NA | NA | B.A ILEMORE (Designation: Director) | N.A RAFINDADI (Designation: Managing Director)
| Actual | 220203 | 1 | BILL OF QUANTITIES | 50595407 | NCB | Ministarial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST -REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | 21/02/18-21/03/18 | 22/03/18-5/04/18 | 9/04/18-7/05/18 | 2018-08-05 | 19/06/18 | 20/06/18-11/07/18 | 2018-12-07 | 50595407 | NA | 13/08/18-27/08/18 | 28/08/18-11/09/18 | NA | NA | NA | B.A ILEMORE (Designation: Director) | N.A RAFINDADI (Designation: Managing Director)
CAPITAL EXPENDITURE/FIXED ASSET PURCHASE -GENERAL | Plan | GOODS/2018/2 | 2 | BILL OF QUANTITIES | 35000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST -REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | 21/02/18-21/03/18 | 22/03/18-5/04/18 | 9/04/18-7/05/18 | 2018-08-05 | 19/06/18 | 20/06/18-11/07/18 | 2018-12-07 | 35000000 | NA | 13/08/18-27/08/18 | 28/08/18-11/09/18 | NA | NA | NA | B.A ILEMORE (Designation: Director) | N.A RAFINDADI (Designation: Managing Director)
| Actual | 230101 | 2 | BILL OF QUANTITIES | 32721059604 | NCB | Ministarial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST -REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | 21/02/18-21/03/18 | 22/03/18-5/04/18 | 9/04/18-7/05/18 | 2018-08-05 | 19/06/18 | 20/06/18-11/07/18 | 2018-12-07 | 32721059604 | NA | 13/08/18-27/08/18 | 28/08/18-11/09/18 | NA | NA | NA | B.A ILEMORE (Designation: Director) | N.A RAFINDADI (Designation: Managing Director)
CONSTRUCTION/PROVISION OF FIXED ASSETS/ OFFICE BULIDINGS- GENERAL | Plan | GOODS/2018/2 | 3 | BILL OF QUANTITIES | 17000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST -REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | 21/02/18-21/03/18 | 22/03/18-5/04/18 | 9/04/18-7/05/18 | 2018-08-05 | 19/06/18 | 20/06/18-11/07/18 | 2018-12-07 | 17000000 | NA | 13/08/18-27/08/18 | 28/08/18-11/09/18 | NA | NA | NA | B.A ILEMORE (Designation: Director) | N.A RAFINDADI (Designation: Managing Director)
| Actual | 23020101 | 3 | BILL OF QUANTITIES | 806907011 | NCB | Ministarial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST -REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | 21/02/18-21/03/18 | 22/03/18-5/04/18 | 9/04/18-7/05/18 | 2018-08-05 | 19/06/18 | 20/06/18-11/07/18 | 2018-12-07 | 806907011 | NA | 13/08/18-27/08/18 | 28/08/18-11/09/18 | NA | NA | NA | B.A ILEMORE (Designation: Director) | N.A RAFINDADI (Designation: Managing Director)
MAINTENANCE SERVICES- GENERAL | Plan | GOODS/2018/2 | 4 | BILL OF QUANTITIES | 35000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST -REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | 21/02/18-21/03/18 | 22/03/18-5/04/18 | 9/04/18-7/05/18 | 2018-08-05 | 19/06/18 | 20/06/18-11/07/18 | 2018-12-07 | 35000000 | NA | 13/08/18-27/08/18 | 28/08/18-11/09/18 | NA | NA | NA | B.A ILEMORE (Designation: Director) | N.A RAFINDADI (Designation: Managing Director)
| Actual | 220203 | 4 | BILL OF QUANTITIES | 12089659895 | NCB | Ministarial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST -REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | 21/02/18-21/03/18 | 22/03/18-5/04/18 | 9/04/18-7/05/18 | 2018-08-05 | 19/06/18 | 20/06/18-11/07/18 | 2018-12-07 | 12089659895 | NA | 13/08/18-27/08/18 | 28/08/18-11/09/18 | NA | NA | NA | B.A ILEMORE (Designation: Director) | N.A RAFINDADI (Designation: Managing Director)
FUEL AND LUBRICANTS- GENERAL | Plan | GOODS/2018/2 | 5 | BILL OF QUANTITIES | 20000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST -REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | 21/02/18-21/03/18 | 22/03/18-5/04/18 | 9/04/18-7/05/18 | 2018-08-05 | 19/06/18 | 20/06/18-11/07/18 | 2018-12-07 | 20000000 | NA | 13/08/18-27/08/18 | 28/08/18-11/09/18 | NA | NA | NA | B.A ILEMORE (Designation: Director) | N.A RAFINDADI (Designation: Managing Director)
| Actual | 220208 | 5 | BILL OF QUANTITIES | 11478311 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST -REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | 21/02/18-21/03/18 | 22/03/18-5/04/18 | 9/04/18-7/05/18 | 2018-08-05 | 19/06/18 | 20/06/18-11/07/18 | 2018-12-07 | 11478311 | NA | 13/08/18-27/08/18 | 28/08/18-11/09/18 | NA | NA | NA | B.A ILEMORE (Designation: Director) | N.A RAFINDADI (Designation: Managing Director)
Actual
Total Cost Plan |  |  |  |  | 124000000 | [14 empty] | 124000000
Total Cost Actual

## NEPAD Non-Consultancy Services
Ministry/Department/Agency: Test Department
Budget Year: 2018
|  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2.2 - 2 weeks | 3 weeks | 2 - 4 weeks | 2 weeks | 4 - 6 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
PRESERVATION OF THE ENVIRONMENT - GENERAL | Plan | SERVICES/2018/4 | 1 | Time- Based | 200000000 | NCB | Ministerial Tenders Board | QCBS-Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 200000000 | NA | 21/02/18-7/03/18 | 8/03/18-22/03/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation: Director) | N. A RAFFINDADI (Designation: Managing Director)
| Actual | 230401 | 1 | Time- Based | 212988883 | NCB | Ministerial Tenders Board | QCBS-Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 212988883 | NA | 21/02/18-7/03/18 | 8/03/18-22/03/18 | NA | NA | NA | 212988883 | B.A ILEMORE (Designation: Director) | N. A RAFFINDADI (Designation: Managing Director)
REHABILITATION/ REPAIRS OF FIXED ASSETS- GENERAL | Plan | SERVICES/2018/4 | 2 | Time- Based | 55000000 | NCB | Ministerial Tenders Board | QCBS-Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 55000000 | NA | 21/02/18-7/03/18 | 8/03/18-22/03/18 | NA | NA | NA | 55000000 | B.A ILEMORE (Designation: Director) | N. A RAFFINDADI (Designation: Managing Director)
| Actual | 230301 | 2 | Time- Based | 30869869137 | NCB | Ministerial Tenders Board | QCBS-Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 30869869137 | NA | 21/02/18-7/03/18 | 8/03/18-22/03/18 | NA | NA | NA | 30869869137 | B.A ILEMORE (Designation: Director) | N. A RAFFINDADI (Designation: Managing Director)
ACQUISATION OF NON TANGIBLE ASSETS | Plan | SERVICES/2018/4 | 3 | Bills of Quantity | 150000000 | NCB | parastatals Tenders Board | QCBS-Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 150000000 | NA | 21/02/18-7/03/18 | 8/03/18-22/03/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation: Director) | N. A RAFFINDADI (Designation: Managing Director)
| Actual | 230501 | 3 | Bills of Quantity | 482767312 | NCB | parastatals Tenders Board | QCBS-Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 482767312 | NA | 21/02/18-7/03/18 | 8/03/18-22/03/18 | NA | NA | NA | 482767312 | B.A ILEMORE (Designation: Director) | N. A RAFFINDADI (Designation: Managing Director)
TRAINING -GENERAL | Plan | SERVICES/2018/4 | 4 | Bills of Quantity | 20000000 | NCB | parastatals Tenders Board | QCBS-Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 20000000 | NA | 21/02/18-7/03/18 | 8/03/18-22/03/18 | NA | NA | NA | 20000000 | B.A ILEMORE (Designation: Director) | N. A RAFFINDADI (Designation: Managing Director)
| Actual | 220205 | 4 | Bills of Quantity | 15068790 | NCB | parastatals Tenders Board | QCBS-Quality and Cost Based Selection | POST REVIEW | POST REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 15068790 | NA | 21/02/18-7/03/18 | 8/03/18-22/03/18 | NA | NA | NA | 15068790 | B.A ILEMORE (Designation: Director) | N. A RAFFINDADI (Designation: Managing Director)
EXPENDITURE/PERSONAL COST | Plan | SERVICES/2018/4 | 5 | Bills of Quantity | 100000000 | NCB | Ministerial Tenders Board | QCBS-Quality and Cost Based Selection | POST REVIEW | POST REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 100000000 | NA | 21/02/18-7/03/18 | 8/03/18-22/03/18 | NA | NA | NA | 100000000 | B.A ILEMORE (Designation: Director) | N. A RAFFINDADI (Designation: Managing Director)
| Actual | 2101 | 5 | Bills of Quantity | 693136208 | NCB | Ministerial Tenders Board | QCBS-Quality and Cost Based Selection | POST REVIEW | POST REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 693136208 | NA | 21/02/18-7/03/18 | 8/03/18-22/03/18 | NA | NA | NA | 693136208 | B.A ILEMORE (Designation: Director) | N. A RAFFINDADI (Designation: Managing Director)
ALLOWANCES AND SOCAIL CONTRIBUTIONS | Plan | SERVICES/2018/4 | 6 | Bills of Quantity | 25000000 | NCB | parastatals Tenders Board | QCBS-Quality and Cost Based Selection | POST REVIEW | POST REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 25000000 | NA | 21/02/18-7/03/18 | 8/03/18-22/03/18 | NA | NA | NA | 25000000 | B.A ILEMORE (Designation: Director) | N. A RAFFINDADI (Designation: Managing Director)
| Actual | 2102 | 6 | Bills of Quantity | 21304742 | NCB | parastatals Tenders Board | QCBS-Quality and Cost Based Selection | POST REVIEW | POST REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 21304742 | NA | 21/02/18-7/03/18 | 8/03/18-22/03/18 | NA | NA | NA | 21304742 | B.A ILEMORE (Designation: Director) | N. A RAFFINDADI (Designation: Managing Director)
OVER HEAD COST/ TRAVEL AND TRANSPORT- GENERAL | Plan | SERVICES/2018/4 | 7 | Bills of Quantity | 25000000 | NCB | parastatals Tenders Board | QCBS-Quality and Cost Based Selection | POST REVIEW | POST REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 25000000 | NA | 21/02/18-7/03/18 | 8/03/18-22/03/18 | NA | NA | NA | 25000000 | B.A ILEMORE (Designation: Director) | N. A RAFFINDADI (Designation: Managing Director)
| Actual | 220201 | 7 | Bills of Quantity | 15603185 | NCB | parastatals Tenders Board | QCBS-Quality and Cost Based Selection | POST REVIEW | POST REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 15603185 | NA | 21/02/18-7/03/18 | 8/03/18-22/03/18 | NA | NA | NA | 15603185 | B.A ILEMORE (Designation: Director) | N. A RAFFINDADI (Designation: Managing Director)
UTILITIES-GENERAL | Plan | SERVICES/2018/4 | 8 | Bills of Quantity | 25000000 | NCB | parastatals Tenders Board | QCBS-Quality and Cost Based Selection | POST REVIEW | POST REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 25000000 | NA | 21/02/18-7/03/18 | 8/03/18-22/03/18 | NA | NA | NA | 25000000 | B.A ILEMORE (Designation: Director) | N. A RAFFINDADI (Designation: Managing Director)
| Actual | 220202 | 8 | Bills of Quantity | 24441799 | NCB | parastatals Tenders Board | QCBS-Quality and Cost Based Selection | POST REVIEW | POST REVIEW | 15/01/18-5/02/18 | 6/02/18-20/02/18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 24441799 | NA | 21/02/18-7/03/18 | 8/03/18-22/03/18 | NA | NA | NA | 24441799 | B.A ILEMORE (Designation: Director) | N. A RAFFINDADI (Designation: Managing Director)
Total Cost Plan |  |  |  |  | #REF! | [19 empty] | #REF! | [6 empty] | #REF!
Total Cost Actual

## NEPAD Works
Ministry/Department/Agency: Test Department
Budget Year: 2018
|  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Works |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Plan vs Actual
GENERAL MAINTENACE/PAYEMENT STRENGTHENING OF KEFFI- GITALA- KADUNA S/B ROAD ROUTE NO 346 IN NASARAWA STATE. | Plan | 1 | 1 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | NA | NA | 7/02/18 | 21/03/18 | 22/03/18 - 5/04/18 | 9/04/18 - 23/04/18 | 200000000 | NA | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107789 | Bills of Quantity | 97781260 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18-29/01/18 | 30/01/18-6/02/18 | NA | NA | NA | NA | NA | 2018-07-02 | 21/03/18 | 22/03/18-5/04/18 | 9/04/18-23/04/18 | 97781260 | NA | 24/04/18-8/05/18 | 9/05/18 - 23/05/18 | NA | NA | NA | 97781260 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE/PAVEMENT STRENGTHENING ALONG KEFFI- NASARAWA ROUTE NO 346 IN NASARAWA STATE | Plan | 1 | 2 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | BA ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual |  | ERGP12107803 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE/REPAIRS OF FAILED SECTION AND REINSTATEMENT OF EMBANKMENT WASHOUT ALONG LAFIA-MAKURDI ROAD ROUTE NO 70 IN NASSARAWA STATE | Plan | 1 | 3 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP121107823 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE AND REPAIRS OF CRITICALLY FAILED SECTION OF CARRIAGEWAY ALONG SHENDAM-NAMU NASSARAWA STATE BORDER ROAD IN PLATEAU STATE | Plan | 1 | 4 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107836 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL REPAIRS OF CARRIAGEWAY ISOLATED FAILED SECTIONS AND STRENGTHENING (OVDERLAY) OF WEAK SECTIONS ALONG JOS-SAMINAKA (KADUNA STATE BORDER) ROAD IN PLATEAU STATE | Plan | 1 | 5 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107845 | Bills of Quantity | 91972472 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 91972472 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 91972472 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE OF ABUJA-KEFFI ROAD IN FCT | Plan | 1 | 6 | Bills of Quantity | 220000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 2200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 2200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107868 | Bills of Quantity | 91972472 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 91972472 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 91972472 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
EMERGENCY MAINTENANCE REPAIRS OF DEIDEI-DAKWA-ABUJA-KADUNA JUNCTION ROAD FCT | Plan | 1 | 7 | Bills of Quantity | 110000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 110000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 110000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107883 | Bills of Quantity | 106494441 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 106494441 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 106494441 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE REPAIRS OF SHARE-PATIGI-EGGAN KOGI STATE BORDER ROAD INCLUDING PATIGI WITH SPUR IN KWARA STATE | Plan | 1 | 8 | Bills of Quantity | 170000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 170000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 170000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107891 | Bills of Quantity | 101653785 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 101653785 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 101653785 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
SPECIAL REPAIRS OF OKEOYI-OLOORU JUNCTION (NORTH LINK) IN KWARA STATE | Plan | 1 | 9 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107896 | Bills of Quantity | 87131816 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 87131816 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 87131816 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF FAILED SECTION OF OMU-ARAN-EKANMEJE -EKITI S/B ROAD IN KWARA STATE | Plan | 1 | 10 | Bills of Quantity | 100000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 100000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 100000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107915 | Bills of Quantity | 58087877 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 58087877 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 58087877 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF ILORIN- OMUARAN-KOGI STATE BORDER ROAD IN KWARA STATE | Plan | 1 | 11 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107921 | Bills of Quantity | 87131816 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 87131816 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 87131816 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE REPAIRS BETWEEN ALONG MINNA -ZUNGERU - TEGINA ROAD ROUTE NO 65 IN NIGER STATE | Plan | 1 | 12 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107935 | Bills of Quantity | 94011888 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 94011888 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 94011888 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
EMERGENCY REPAIRS BETWEEN ALONG TEGINA - BIRNIN GWARI ROAD ROUTE NO 20 IN NIGER STATE | Plan | 1 | 13 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107958 | Bills of Quantity | 87131816 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 87131816 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 87131816 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
CONSTRUCTION OF LINED DRAINS ALONG MINNA -TEGINA ROAD IN NIGER STATE | Plan | 1 | 14 | Bills of Quantity | 60000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 60000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 60000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107974 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF MOKWA - JEBBA (KWARA S\B) ROAD ROUTE NO.20 IN NIGER STATE | Plan | 1 | 15 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107982 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
EMERGENCY REPAIRS OF COLLAPSED EMBANKMENT AT CULVERT LOCATION IN MOKWA TOWN AND CONSTRUCTION OF REINFORCED CONCRETE LINED DRAIN BETWEEN ALONG MOKWA- JEBBA ROAD ROUTE NO 20 IN NIGER STATE | Plan | 1 | 16 | Bills of Quantity | 45000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 45000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 45000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107995 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
EMERGENCY CONSTRUCTION OF REINFORCED CONCRETE LINED DRAIN AT NEW BUSSA TOWN BETWEEN CH. 100 +200 - CH. 101+000 ALONG MOKWA - NEW BUSSA - WAWA ROAD ROUTE NO.55 IN NIGER STATE | Plan | 1 | 17 | Bills of Quantity | 65000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 65000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 65000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108004 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENACE REPAIRS OF MAKURDI-NASARAWA STATE BORDER ROAD IN BENUE STATE | Plan | 1 | 18 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108016 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF ALLADE-GBOKO-YANDEV ROAD IN BENUE STATE | Plan | 1 | 19 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108027 | Bills of Quantity | 87131816 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 87131816 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 87131816 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF OLUKPA-KOGI STATE BORDER ROAD IN BEN UE STATE | Plan | 1 | 20 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108055 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF MAKURDI-ALLADE ROAD IN BENUE STATE | Plan | 1 | 21 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108042 | Bills of Quantity | 87131816 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 87131816 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 87131816 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE OF MAKURDI - YANDEV - UGBEMA ROAD IN BENUE STATE | Plan | 1 | 22 | Bills of Quantity | 75000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 75000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 75000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108068 | Bills of Quantity | 46470302 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 46470302 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 46470302 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE OF KABBA-OMUO-EKITI STATE BORDER ROAD IN KOGI STATE | Plan | 1 | 23 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108078 | Bills of Quantity | 106494441 | NCB | parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 106494441 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 106494441 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINENENACE OF OF EGBE - OMUO ROAD R554 (SECTION 2,3,& 4) IN KOGI STATE | Plan | 1 | 24 | Bills of Quantity | 160000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 160000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 160000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108088 | Bills of Quantity | 96813128 | NCB | parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE OF KEBBA-AYERE ROAD IN KOGI STATE | Plan | 1 | 25 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108103 | Bills of Quantity | 107462573 | NCB | parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 107462573 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 107462573 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE OF ANYIGBA-ANKA-OTUKPA ROAD IN KOGI STATE | Plan | 1 | 26 | Bills of Quantity | 70000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 70000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 70000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108107 | Bills of Quantity | 43565908 | NCB | parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 43565908 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 43565908 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF KABBA-EGBE-KWARA S/B IN KOGI STATE | Plan | 1 | 27 | Bills of Quantity | 120000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 120000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 120000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108120 | Bills of Quantity | 72609846 | NCB | parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 72609846 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 72609846 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
COMPLETION OF PHASE IV FERMA FIELD OFFICE PLATEEAU STATE | Plan | 1 | 28 | Bills of Quantity | 120000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 120000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 120000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP27107860 | Bills of Quantity | 77450503 | NCB | parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 77450503 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 77450503 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
COMPLETION OF PHASE III ONGOING WORK FERMA STATE FIELD OFFICE TUNGA-MAJE , FCT ABUJA | Plan | 1 | 29 | Bills of Quantity | 12000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 12000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 12000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP27109051 | Bills of Quantity | 106494441 | NCB | parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 106494441 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 106494441 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
COMPLETION OF PHASE IV PLANNNED WORK FERMA STATE FIELD OFFICE KWARA STATE | Plan | 1 | 30 | Bills of Quantity | 120000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 120000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 120000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP27110205 | Bills of Quantity | 70354897 | NCB | parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 70354897 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 70354897 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
COMPLETION OF PHASE IV PLANNED WORK FERMA STATE FIELD OFFICE KOGI STATE | Plan | 1 | 31 | Bills of Quantity | 120000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 120000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 120000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP27110212 | Bills of Quantity | 80354897 | NCB | parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 80354897 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 80354897 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
OPERATION, MAINTENANCE AND REPAIR (OMR) OF STREET LIGHTING INSTALLATIONS ALONG ABUJA-KEFFI EXPRESSWAY ( FROM KUGBO-ADO BRIDGE) | Plan | 1 | 32 | Bills of Quantity | 40000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 40000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 40000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP10109922 | Bills of Quantity | 24203282 | NCB | parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
OPERATION, MAITENANCE AND REPAIR (OMR) OF SREET LIGHTING INSTALLATIONS ALONG ABUJA-KADUNA EXPRESSWAY (ZUBA FLYOVER & RAMPS) AND EXTENSION | Plan | 4 | 33 | Bills of Quantity | 15000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 15000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 15000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP10109927 | Bills of Quantity | 9681313 | NCB | parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 9681313 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 9681313 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
OPERATION, MAITENANCE AND REPAIR (OMR) OF STREET LIGHTING INSTALLATIONS ALONG INTERNATIONAL AIRPORT ROAD, ILORIN KWARA STATE. | Plan | 1 | 34 | Bills of Quantity | 10000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 10000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 10000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP10109938 | Bills of Quantity | 48406564 | NCB | parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 48406564 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 48406564 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
BRIDGEWORK INTERVENTION ON CONSTRUCTION OF IMPROVED MULTI-CELL BOX CULVERT ACROSS OMI DAM SPILLWAY (KM.17+000) WITH EROSION CONTROL AT APPROACHES ALONG EGBE-OMUO ROAD, ROUTE 554 IN KOGI STATE | Plan | 1 | 35 | Bills of Quantity | 63000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 630000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 630000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP19110057 | Bills of Quantity | 38725251 | NCB | parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL REPAIRS OF BILLIRI-FILIYA ROAD IN GOMBE STATE | Plan | 1 | 36 | Bills of Quantity | 160000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 160000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 160000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108120 | Bills of Quantity | 96813128 | NCB | parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL REPAIRS OF GOMBE - BAUCHI ROAD IN GOMBE STATE | Plan | 1 | 37 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108135 | Bills of Quantity | 91972472 | NCB | parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 91972472 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 91972472 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL REPAIRS OF GOMBE - DUKKU - DARAZO ROAD IN GOMBE STATE | Plan | 1 | 38 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108142 | Bills of Quantity | 106494441 | NCB | parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 106494441 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 106494441 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF MAYOBELWA -ZING ROAD IN ADAMAWA STATE | Plan | 1 | 39 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109392 | Bills of Quantity | 96813128 | NCB | parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
SPECIAL REPAIRS OF GANYE-SUGU-JAMTARI ROAD IN ADAMAWA STATE | Plan | 1 | 40 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109393 | Bills of Quantity | 91972472 | NCB | parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 91972472 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 91972472 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE OF KARI-YANA-JIGAWA STATE BORDER ROAD BAUCHI STATE | Plan | 1 | 41 | Bills of Quantity | 200000000 | NCB | parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109394 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE OF KARI-YOBE STATE BORDER ROAD IN BAUCHI STATE | Plan | 1 | 42 | Bills of Quantity | 180000000 | NCB | parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109395 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE OF BAUCHI -NINJI-JIGAWA STATE ROAD IN BAUCHI STATE | Plan | 1 | 43 | Bills of Quantity | 150000000 | NCB | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109397 | Bills of Quantity | 91972472 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 91972472 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 91972472 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE OF BAUCHI-JOS ROAD PLATEAU STATE BORDER ROAD IN BAUCHI STATE | Plan | 1 | 44 | Bills of Quantity | 120000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 120000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 120000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109398 | Bills of Quantity | 77450503 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 77450503 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 77450503 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF MAIDUGURI-DAMBOA-BIU ROAD IN BORNO STATE | Plan | 1 | 45 | Bills of Quantity | 200000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109399 | Bills of Quantity | 97781260 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 97781260 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 97781260 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF BIU -WUYO-GOMBE ROAD S/B ROAD IN BORNO STATE | Plan | 1 | 46 | Bills of Quantity | 180000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109400 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE REPAIRS BIU-SHAFFA-GARKIDA ADAMAWA ROAD S/B IN BORNO STATE | Plan | 1 | 47 | Bills of Quantity | 160000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 160000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 160000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109401 | Bills of Quantity | 91972472 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 91972472 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 91972472 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE AND REPAIRS OF JALINGO - MAYOLOPE- ADAMAWA STATE BORDER ROAD ROUTE 90 IN TARABA STATE | Plan | 1 | 48 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 |  |  |  | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108155 | Bills of Quantity | 101653785 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 101653785 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 101653785 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE AND REPAIRS OF FAILED SECTIONS ALONG JALINGO -MUTUMBIYU-WUKARI-BENUE STATE BORDER ROAD SECTION 1 FROM (JALINGO-TELLA) ROUTE 90 IN TARABA STATE | Plan | 1 | 49 | Bills of Quantity | 170000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 170000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 170000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108164 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE REPAIRS OF FAILED SECTION ALONG APAWA JUNCTION-ZING-ADAMAWA S/B ROAD ROUTE 477 IN TARABA STATE | Plan | 1 | 50 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108172 | Bills of Quantity | 101653785 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 101653785 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 101653785 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE REPAIRS OF SCETION II OF BIU-KWAYA KUSUR GOMBE STATE BORDER ROAD IN BORNO STATE | Plan | 1 | 51 | Bills of Quantity | 100000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 100000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 100000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109403 | Bills of Quantity | 62928534 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 62928534 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 62928534 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF POTISKUM -KARI -BAUCHI S/B ROAD IN YOBE STATE | Plan | 1 | 52 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108177 | Bills of Quantity | 106494441 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 106494441 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 106494441 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF POTISKUM-FIKA- NGALDA GOMBE S/B ROAD IN YOBE STATE | Plan | 1 | 53 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108184 | Bills of Quantity | 106494441 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 106494441 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 106494441 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF DAMATURU -DAPCHI-BAYAMART ROAD IN YOBE STATE | Plan | 1 | 54 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108193 | Bills of Quantity | 87131816 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 87131816 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 87131816 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF YOLA - FUFORE ROAD IN ADAMAWA STATE | Plan | 1 | 55 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108311 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE REPAIRS OF NUMAN - GUYUK ROAD IN ADAMAWA STATE | Plan | 1 | 56 | Bills of Quantity | 70000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 70000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 70000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108330 | Bills of Quantity | 43565908 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 43565908 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 43565908 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PREVENTIVE MAINTENANCE OF ABUTMENTS EMBANKMENT AND PROTETIONOF SCOURED PILED-CAPS OF BRIDGE AT ALONG GOMBE-POTISKUM ROAD IN GOMBE STATE | Plan | 1 | 57 | Bills of Quantity | 40000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 40000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 40000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108149 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
OPERATION , MAINTENANCE AND REPAIRS (OMR) OF SOLAR POWERED STREET LIGHTHING INSTALLATIONS ALONG DAMATURU -GASHUA ROAD, DAMATURU END YOBE STATE | Plan | 1 | 58 | Bills of Quantity | 15000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 15000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 15000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP10109943 | Bills of Quantity | 9681313 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 9681313 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 9681313 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
OPERATION, MAINTENANCE REPAIRS (OMR) OF STREET LIGHTHING INSTALLATION ON JIMETA BRIDGE AND YOLA-GOMBE ROAD YOLA , ADAMAWA STATE | Plan | 1 | 59 | Bills of Quantity | 10000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 10000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 10000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP10109947 | Bills of Quantity | 4840656 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 4840656 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 4840656 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
OPERATION,MAINTENANCE AND REPAIRS (OMR) OF STREET LIGHTHING INSTALLATION ALONG MAIDUGURI- MONGUNO ROAD BY MILITARY CONTOMENT (SOLAR) AND MAIDUGURI AND BIU-GOMBE ROAD BIU END BORNO STATE | Plan | 1 | 60 | Bills of Quantity | 12000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 12000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 12000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP10109953 | Bills of Quantity | 7262541 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 7262541 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 7262541 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE BETWEEN ALONG KATSINA -KANO (STATE BORDER) ROAD IN KATSINA STATE | Plan | 1 | 61 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107784 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE BETWEEN ALONG FUNTUA-ZARIA (KADUNA STATE BORDER) ROAD IN KATSINA STATE | Plan | 1 | 62 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107793 | Bills of Quantity | 97781260 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 97781260 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 97781260 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE BETWEEN ALONG BAKORI-DANJA-HUNKUYI (KADUNA STATE BORDER) ROAD IN KATSINA STATE | Plan | 1 | 63 | Bills of Quantity | 160000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 160000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 160000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107803 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF RIJAU-RIBAH-WASAGU ROAD IN KEBBI STATE | Plan | 1 | 64 | Bills of Quantity | 175000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 175000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 175000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107813 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
SPECIAL MAINTENANCE REPAIRS ALONG BIRNIN-KEBBI-ARGUNGU-SOKOTO STATE BORDER ROAD IN KEBBI STATE | Plan | 1 | 65 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 20000000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107826 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
SPECIAL MAINTENANCE REPAIRS ALONG BIRNIN-KEBBI-JEGA ROAD IN KEBBI STATE | Plan | 1 | 66 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107836 | Bills of Quantity | 91972472 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 91972472 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 91972472 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE OF SOKOTO -DANGE-ZAMFARA STATE BORDER ROAD IN SOKOTO STATE | Plan | 1 | 67 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107853 | Bills of Quantity | 106494441 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 106494441 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 106494441 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE OF SOKOTO-IIETA-NIGER REPUBLIC BORDER ROAD IN SOKOTO STATE IN SOKOTO STATE | Plan | 1 | 68 | Bills of Quantity | 160000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 160000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 160000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107862 | Bills of Quantity | 97781260 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 97781260 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 97781260 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL REPAIRS AND PAVEMENT STRENGHTENING OF KADUNA -ZARIA-KANO S/BORDER DUAL CARRIAGEWAY IN KADUNA STATE ROUTE NO 50 (A125) | Plan | 1 | 69 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107757 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE AND PAVEMENT STRENGTHNING OF KADUNA - BIRNIN GWARI (NIGER S/B) ROAD IN KADUNA STATE (ROUTE NO 20 (A. 125 ) ) | Plan | 1 | 70 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107768 | Bills of Quantity | 91972472 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 91972472 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 91972472 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE OF KATABU-PAMBEGUA-SAMINAKA-PLATEAU S/B ROAD IN KADUNA STATE ROUTE NO 317 (A.11) | Plan | 1 | 71 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP1210777 | Bills of Quantity | 91972472 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 91972472 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 91972472 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF JABO-KAJIJI-ZAMFARA STATE BORDER ROAD IN SOKOTO STATE | Plan | 1 | 72 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107872 | Bills of Quantity | 106494441 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 106494441 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 106494441 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF KANO-GWARZO-DAYI-KATSINA STATE BORDER ROAD IN KANO STATE | Plan | 1 | 73 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107881 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE REPAIRS OF KAFFIN MAIYAKI-TUDUNWADA - SAMINAKA-KADUNA S/B ROAD IN KANO STATE | Plan | 1 | 74 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107890 | Bills of Quantity | 110366966 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 110366966 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 110366966 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
SPECIAL MAINTENANCE REPAIRS OF KWANA HUGMA-DUTSE ROAD IN KANO STATE | Plan | 1 | 75 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107896 | Bills of Quantity | 106494441 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 106494441 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 106494441 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PREVENTIVE MAINTENANCE AND PROTECTION OF SCOURED PILE-CAPS AT BIRNIN KUDU BIDGES 1 (KM.26+900) AND 2 (KM.27+900) ALONG KANO-KARI ROAD IN JIGAWA STATE. | Plan | 1 | 76 | Bills of Quantity | 55000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 55000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 55000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107934 | Bills of Quantity | 33884595 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 33884595 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 33884595 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REPAIR OF FAILED SECTIONS AND PAVEMENT STRENGTHENING OF KANO S/B - BABURA - CH,A - NIGER REPUBLIC BORDER ROAD (CH.0+000 - CH.65+000) IN JIGAWA STATE (ROUTE NO. 306) | Plan | 1 | 77 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107945 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE OF GUMEL-MAIGATARI-NIGER REPUBLIC BORDER ROAD IN JIGAWA STATE | Plan | 1 | 78 | Bills of Quantity | 125000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 125000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 125000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107945 | Bills of Quantity | 77450503 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 77450503 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 77450503 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
SPECIAL REPAIR OF FAILED SECTIONS AND PAVEMENT STRENTHING OF HADEJIA- GAMAYIN ROAD IN JIGAWA STATE ROUTE NO. 70 | Plan | 1 | 79 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107965 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF GUSAU-TALATA-MARAFA ROAD SOKOTO S/B IN ZAMFARA STATE | Plan | 1 | 80 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108141 | Bills of Quantity | 106494441 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 106494441 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 106494441 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF GUSAU-KAURA -NAMODA SHINKAFI ROAD SOKOTO S/B IN ZAMFARA STATE | Plan | 1 | 81 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108149 | Bills of Quantity | 101653785 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 101653785 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 101653785 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PREVENTIVE MAINTENANCE AND PROTECTION OF SCOURED PILE-CAPS WITH RIVER TRAINING AT GALMA BRIDGE ALONG ZARIA PAMBEGUA ROAD IN KADUNA STATE | Plan | 1 | 82 | Bills of Quantity | 40000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 40000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 40000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12107779 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
EMBARKMENT PROTECTION AND CONSTRUCTION OF DRAINAGE ALONG KAURA-NAMODA ZURUMI KATSINA S/B ROAD IN ZAMFARA STATE | Plan | 1 | 83 | Bills of Quantity | 130000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 130000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 130000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108158 | Bills of Quantity | 77450503 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 77450503 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 77450503 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
SPECIAL REPAIRS AND EMBANKMENT PROTECTION OF BRIDGES AT DAN MARKEN BUNGUDU AND MARU ALONG GUSAU -SOKOTO S/B ROAD IN ZAMFARA STATE | Plan | 1 | 84 | Bills of Quantity | 65000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 65000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 65000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108165 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
OPERATION , MAINTENANCE AND REPAIRS (OMR) OF STREET LIGHTING INSTALLATION ALONG KADUNA - ABUJA EXPRESS WAY (GONIN GORA) AND EXTENTION, KADUNA STATE | Plan | 1 | 85 | Bills of Quantity | 15000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 15000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 15000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP10109960 | Bills of Quantity | 9681313 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 9681313 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 9681313 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
OPERATION, MAINTENANCE AND REPAIRS (OMR) OF STREET LIGHTING INSTALLATION ALONG KADUNA-ZARIA EXPRESSWAY (KAWO FLYOVER-RIGACHUKU) KADUNA STATE | Plan | 1 | 86 | Bills of Quantity | 12000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 12000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 12000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP10109969 | Bills of Quantity | 7262541 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 7262541 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 7262541 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
OPERATIVE, MAINTENANCE AND REPAIR (OMR) OF SOLAR POWERED STREET LIGHTHING INSTALLATIONS ALONG KATSINA-KANO ROAD ,KANKIA END AND KATSINA -BATSARI- DUTSINMA ROAD KATSINA STATE | Plan | 1 | 87 | Bills of Quantity | 12000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 12000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 12000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP10109975 | Bills of Quantity | 7260985 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 7260985 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 7260985 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
OPERATION, MAINTENANCE AND REPAIR (OMR) OF STREET LIGHTING INSTALLATION ALONG SOKOTO-GUSAU ROAD SOKOTO STATE | Plan | 1 | 88 | Bills of Quantity | 12000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 12000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 12000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP10109979 | Bills of Quantity | 7260985 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 7260985 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 7260985 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
OPERATION, MAINTENANCE AND REPAIRS (OMR) OF STREET LIGHTHING INSTALLATION ALONG SOKOTO WESTERN/BYE PASS/AIRPORT ROAD SOKOTO STATE | Plan | 1 | 89 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP10109984 | Bills of Quantity | 9681313 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 9681313 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 9681313 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REINSTAMENT OF WASHOUT ON BRIDGE ABUTMENT AND EMBANKMENT PROTECTION WORKS AT (WARWA KAZA BRIDGE ) ALONG KATSINA-DUTSINMA-KANKARA -KARFI ROAD IN KATSINA STATE | Plan | 1 | 90 | Bills of Quantity | 22000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 22000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 22000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP19110051 | Bills of Quantity | 14521969 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 14521969 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 14521969 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
EMERGENCY REPAIRS OF SCOURED PILE CAPS OF BRIDGE 3 IN THE FLOOD-PRONE FADAMA SECTION OF ARGUNGU-BUI ROAD IN KEBBI STATE | Plan | 1 | 91 | Bills of Quantity | 45000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 45000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 45000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP19110054 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE REPAIRS OF AGBANI-AKPUGO-AMAGUNZE -EBONYI STATE BORDER ROAD IN ENUGU STATE | Plan | 1 | 92 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109343 | Bills of Quantity | 77450503 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 77450503 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 77450503 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE OF OHAFIA -BIAKPAN ROAD ABIA STATE | Plan | 1 | 93 | Bills of Quantity | 80000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 80000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 80000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109348 | Bills of Quantity | 48406564 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 48406564 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 48406564 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE REPAIRS OF UMUAHIA-BENDA-OHAFIA ROAD IN ABIA STATE | Plan | 1 | 94 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109352 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE OF ENUGU S/B ISUIKWUATO UMUAHIA -RIVER STATE BORDER ROAD ABIA STATE | Plan | 1 | 95 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109412 | Bills of Quantity | 77450503 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 77450503 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 77450503 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE OF UMUAHIA - ARIAM - IKOT EKPENE ROAD ABIA STATE.. | Plan | 1 | 96 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109413 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PREVENTIVE MAINTENANCE OF NKANA BRIDGE ALONG AROCHUKWU-NKANA-AKWA- IBOM S/B ROAD IN ABIA STATE | Plan | 1 | 97 | Bills of Quantity | 45000000 | NS | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 45000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 45000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109414 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF IGWU BRIDGE ALONG UMUAHIA-BENDE-OHAFIA ROAD IN ABIA STATE | Plan | 1 | 98 | Bills of Quantity | 12000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 12000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 12000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109415 | Bills of Quantity | 9681313 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 9681313 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 9681313 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENARAL MAINTENANCE REPAIRS OF OWUTU-AMASIRI-OKPOSI-UBURU ROAD IN EBONYI STATE | Plan | 1 | 99 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109417 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE REPAIRS OF ABAKALIKI-OFEREKPE ROAD IN EBONYI STATE | Plan | 1 | 100 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109420 | Bills of Quantity | 77450503 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 77450503 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 77450503 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL REPAIRS OF AFIKPO-OKIGWE ROAD IN EBONYI STATE | Plan | 1 | 101 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 1500000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109422 | Bills of Quantity | 77450503 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 77450503 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 77450503 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE/REPAIRS OF AMANZE-MILE 71/2 -UMUELEMAI-UMUNA ROAD IN IMO STATE | Plan | 1 | 102 | Bills of Quantity | 210000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 210000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 210000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109428 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE/PAVEMENT STRENGTHING OF OWERRI-OBOWO-UMUAHIA ROAD IN IMO STATE | Plan | 1 | 103 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109621 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF OKIGWE -ARONDIZOUGU-UGA ROAD IN IMO STATE | Plan | 1 | 104 | Bills of Quantity | 100000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 100000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 100000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109624 | Bills of Quantity | 62928534 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 62928534 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 62928534 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PREVENTIVE MAINTENANCE ON TWO BRIDGES AT OJUJU RIVER AND AMAYI- EZIORSU ALONG EGBEMA-UGUTA-ULI ROAD IN IMO STATE | Plan | 1 | 105 | Bills of Quantity | 25000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 25000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 25000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109630 | Bills of Quantity | 15490101 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 15490101 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 15490101 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF ONITSHA-AGULERI-ADANI ROAD IN ANAMBRA STATE | Plan | 1 | 106 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108170 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
EMERGENCY REPAIRS OF OSEAKWA-IHIALA -ISSEKE ROAD IN ANAMBRA STATE | Plan | 1 | 107 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108175 | Bills of Quantity | 87131816 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 |  | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 87131816 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF AWKA-EKWULOBIA -UGA ROAD IN ANANBRA STATE | Plan | 1 | 108 | Bills of Quantity | 165000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 165000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 165000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108181 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PREVENTIVE MAINTENANCE OF NSUGBE BRIDGE AT ALONG ONITSHA -AGULERI-ADANI ROAD IN ANANBRA STATE | Plan | 1 | 109 | Bills of Quantity | 37000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 37000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 37000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108311 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE REPAIRS OF NSUKKA-ADANI ANAMBRA STATE BORDER ROAD IN ENUGU STATE | Plan | 1 | 110 | Bills of Quantity | 170000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 170000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 170000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108329 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF 9TH MILE -OJI RIVER (OLD ROAD ) IN ENUGU STATE | Plan | 1 | 111 | Bills of Quantity | 120000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 120000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 120000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108331 | Bills of Quantity | 72609846 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 72609846 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 72609846 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
EMERGENCY REPAIRS OF UDI-OZALIA-NARA-NKEREFFI EBONYI STATE BORDER ROAD IN ENUGU STATE | Plan | 1 | 112 | Bills of Quantity | 120000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 120000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 120000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109339 | Bills of Quantity | 67769190 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 67769190 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 67769190 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
RECONSTRUCTION OF DISTRESSED SLAB DECK/PIER SUPPORT OF 17M-SPAN SUBSTANDARD ACHARA/OKPOSI BRIDGE (KM. 4+100) AND APPROACH ROAD ALONG OMUTO - UBURU - OKPOSI AMASIRI ROAD IN EBONYI STATE | Plan | 1 | 113 | Bills of Quantity | 60000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 60000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 60000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109424 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PREVENTIVE MAINTENANCE ON FOUR BRIDGES AT AMURO(KM.15+900), ARO OFEIMO(KM.18+400), EFFURU(KM.23+700) AND ORJI-AMATTA (KM.56+100) ALONG IHUBE-OKIGWE-UMUNA-ANARA-OWERRI ROAD IN IMO STATE | Plan | 1 | 114 | Bills of Quantity | 60000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 60000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 60000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109426 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF WARRI BYE PASS EXTENSION (NPA-DSC) CH. 0+000 - CH. 15+350 DUAL CARRIAGEWAY IN DELTA STATE | Plan | 1 | 115 | Bills of Quantity | 120000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 120000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 120000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12108718 | Bills of Quantity | 67769190 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 67769190 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 67769190 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF RUMUOKWURUSHI-CHOKOCHO ROAD IN RIVER STATES | Plan | 1 | 116 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109719 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF ELEME JUNCTION -ONNE JUNCTION DUAL CARRIAGEWAY IN RIVER STATE | Plan | 1 | 117 | Bills of Quantity | 120000000 | NS | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 120000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 120000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109721 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
EMERGENCY REPAIRS OF EMOHUA-TEMA JUNCTION ROAD IN RIVER STATE | Plan | 1 | 118 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109726 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF ANOADA -ABUA-DEGEMA IN RIVER STATE | Plan | 1 | 119 | Bills of Quantity | 170000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 170000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 170000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109730 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE OF OGOJA (ABUOCHICHIE)-OBUDU (40KM) IN CROSS RIVER STATE | Plan | 1 | 120 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109733 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE OF A SECTION OF CALABAR -AKAMPA-IKOM IN CROSS RIVER STATE | Plan | 1 | 121 | Bills of Quantity | 65000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 65000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 65000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109735 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
SPECIAL REPAIRS OF OBUDU-OBUDU CATTLE RANCH (70M) IN CROSS RIVER STATE | Plan | 1 | 122 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 1800000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109738 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE OF CALABAR-ATIMBO-IKANG (CAMEROUN BORDER) (32KM) IN CROSS RIVER STATE | Plan | 1 | 123 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 1500000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 1500000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109741 | Bills of Quantity | 77450503 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 77450503 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 77450503 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE OF IKOT EKPENE-ARIAM ROAD IN AKWA IBOM STATE (434) | Plan | 1 | 124 | Bills of Quantity | 220000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 220000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 220000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109631 | Bills of Quantity | 106494441 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 106494441 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 106494441 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL REPAIRS OF EKPARAKWA -AZUMINI ROAD IN AKWA IBOM STATE (R409) | Plan | 1 | 125 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109632 | Bills of Quantity | 106494441 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 106494441 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 106494441 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE OF IKOT EKPENE-UYO-ORON- ENANG-IBAKA ROAD IN AKWA IBOM STATE | Plan | 1 | 126 | Bills of Quantity | 70000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 70000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 70000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109660 | Bills of Quantity | 43565908 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 43565908 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 43565908 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE AND REPAIRS OF FAILED SHOULDERS SECTION AND REINSTATEMENT OF EMBANKMENT WASHOUTS ALONG MBIAMA-YENAGOA ROAD IN BAYELSA STATE | Plan | 1 | 127 | Bills of Quantity | 220000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 220000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 220000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109662 | Bills of Quantity | 97781260 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 97781260 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 97781260 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE AND SPECIAL REPAIRS OF YENAGOA-IMIRINGI -OLOIBIRI ROAD IN BAYELSA STATE | Plan | 1 | 128 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109666 | Bills of Quantity | 97781260 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 97781260 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 97781260 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE AND EMERGENCY REPAIRS OF OPOLO-ELEBELE-EMAYAL ROAD IN BAYELSA STATE | Plan | 1 | 129 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109667 | Bills of Quantity | 77450503 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 77450503 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 77450503 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE FOR CARRIAGEWAY REPAIRS POTHOLES PATCHING AND PAVEMENT STRENGHTHING ALONG BENIN-WARRI DUAL CARRIAGEWAY IN EDO STATE | Plan | 1 | 130 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109673 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE FOR CARRIAGEWAY REPAIRS POTHOLE PATCHING AND PAVEMENT STRENGHTHING ALONG BENIN- UGO-ABROKA ROAD IN EDO STATE | Plan | 1 | 131 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109708 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF IRUEKPEN-UZEBBA-ONDO STATE BORDER ROAD IN EDO STATE | Plan | 1 | 132 | Bills of Quantity | 100000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 100000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 100000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109711 | Bills of Quantity | 58087877 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 58087877 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 58087877 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
EMERGENCY REPAIRS OF ASABA-LILAH -EBU ROAD IN DELTA STATE | Plan | 1 | 133 | Bills of Quantity | 165075000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 165075000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 165075000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109714 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE OF BENIN-ASABA DUAL CARRIAGEWAY IN DELTA STATE | Plan | 1 | 134 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109715 | Bills of Quantity | 106494441 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 106494441 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 106494441 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
EMERGENCY REINSTATEMENT AND PAVEMENT STRENTHING ALONG BENIN -WARRI DUAL CARRIAGEWAY IN DELTA STATE | Plan | 1 | 135 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109717 | Bills of Quantity | 77450503 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 77450503 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 77450503 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
SPECIAL REPAIRS OF BRIDGES AT OKUAHE , ADUHANHAN AND UGONOBA ON BENIN-BOUND ALONG BENIN-AGBOR-ASABA DUAL C/WAY IN EDO STATE | Plan | 1 | 136 | Bills of Quantity | 45000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 45000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 45000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109712 | Bills of Quantity | 28075807 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 28075807 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 28075807 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
FENCING OF ASPHALT PLANT AT IKOT-EKPENE IN AKWO-IBOM STATE | Plan | 1 | 137 | Bills of Quantity | 20000000 | ERGP | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 20000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 20000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP27110217 | Bills of Quantity | 14521969 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 14521969 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 14521969 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
COMPLETION OF PHASE IV PLANNED WORK FERMA STATE FIELD OFFICE EDO STATE | Plan | 1 | 138 | Bills of Quantity | 120000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 120000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 120000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP27110220 | Bills of Quantity | 77450503 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 77450503 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 77450503 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
OPERATION, MAINTENANCE AND REPAIR (OMR) OF STREET LIGHTING INSTALLATIONS ALONG ASABA-BENIN EXPRESSWAY AGBOR RHS AND ABRAKA SUBSTATIONS DELTA STATE | Plan | 1 | 139 | Bills of Quantity | 25000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 25000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 25000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP10109990 | Bills of Quantity | 14521969 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 14521969 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 14521969 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
OPERATION, MAINTENANCE AND REPAIR (OMR) OF STREET LIGHTING INSTALLATIONS ON NIGER BRIDGE DELTA STATE | Plan | 1 | 140 | Bills of Quantity | 12000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 12000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 12000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP10109992 | Bills of Quantity | 7745050 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 7745050 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 7745050 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS IKORODU-ITOIKIN ROAD IN LAGOS EAST SOUTH WEST II ZONE IN LAGOS STATE | Plan | 1 | 141 | Bills of Quantity | 210000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 210000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 210000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109757 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
SPECIAL REPAIRS OF OUTER MARINA IN LAGOS I (EAST), SOUTH WEST II ZONE IN LAGOS STATE | Plan | 1 | 142 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109757 | Bills of Quantity | 78418634 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 78418634 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 78418634 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE OF WESTERN AVENUE (NATIONAL STADIUM & JIBOWO FLYOVERS) IN LAGOS I (EAST) SOUTH WEST II ZONE IN LAGOS STATE | Plan | 1 | 143 | Bills of Quantity | 170000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 170000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 170000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109404 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE OF LAGOS-BADAGRY-SEMI DUAL CARRIAGEWAY IYANG IGBOLERIN -AGBARA IN LAGOS STATE | Plan | 1 | 144 | Bills of Quantity | 210000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 210000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 210000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109406 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE OF LAGOS -BADAGRY-SEME DUAL CARRIAGEWAY AGBARA-ARADAGUN IN LAGOS STATE | Plan | 1 | 145 | Bills of Quantity | 220000000 | NS | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 220000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 210000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109910 | Bills of Quantity | 4085514021 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 4085514021 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 4085514021 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE OF WESTERN AVENUE ROAD IN LAGOS STATE | Plan | 1 | 146 | Bills of Quantity | 120000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 120000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 120000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109916 | Bills of Quantity | 77450503 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 77450503 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 77450503 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE OF BAALE OLODI -KIRIKIRI ROAD IN LAGOS STATE | Plan | 1 | 147 | Bills of Quantity | 90000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 90000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 90000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109918 | Bills of Quantity | 58087877 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 58087877 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 58087877 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF SHAGAMU INTERCHANGE-OWODE-PAPALANTO ROAD IN OGUN STATE | Plan | 1 | 148 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109926 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF ITOIKI-IJEBU ODE-MAMU- OYO STATE BORDER ROAD IN OGUN STATE | Plan | 1 | 149 | Bills of Quantity | 50000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 50000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 50000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109930 | Bills of Quantity | 33884595 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 33884595 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 33884595 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAITENANCE REPAIRS OF SANGO OTA-IDIROKO ROAD (CH.0+000-CH.62+000) IN OGUN STATE. | Plan | 1 | 150 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109933 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF IJEBU IGBO-IFE-SEKONA ROAD IN OGUN STATE | Plan | 1 | 151 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109937 | Bills of Quantity | 82291159 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 82291159 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 82291159 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF KARIMU 1-2 STREET IN SURULERE 1, FEDERAL CONSTINTUENCY LAGOS, FERMA (POWER, WORKS AND HOUSING ) | Plan | 1 | 152 | Bills of Quantity | 250000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 250000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 250000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12115074 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
SPECIAL REPAIRS /PAVEMENT STRENGTHEING OF IBADAN-OYO NEW DUAL CARRIAGEWAY IN OYO STATE | Plan | 1 | 153 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109939 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
SPECIAL REPAIRS/PAVEMENT STRENGTHENING OF IBADAN-IFE DUAL C/W ROUTE 35, IN OYO STATE | Plan | 1 | 154 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12109942 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE OF OYO-OGBOMOSHO ROAD , ROUTE 20 IN OYO STATE | Plan | 1 | 155 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12110136 | Bills of Quantity | 77450503 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 77450503 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 77450503 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF IPELLE-IFIRA-AYERE-KOGI STATE BORDER ROAD ROUTE NO R40 (F220) IN ONDO STATE | Plan | 1 | 156 | Bills of Quantity | 100000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 100000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 100000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12110138 | Bills of Quantity | 62928534 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 62928534 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 62928534 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF OWO-IKORE ROAD ROUTE NO554 (F215) IN ONDO STATE | Plan | 1 | 157 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12110141 | Bills of Quantity | 77450503 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 77450503 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 77450503 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF AKURE-OWO-IFON EDO STATE BORDER ROAD ROUTE NOR35 (F22) IN ONDO STATE | Plan | 1 | 158 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12110143 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
SPECIAL REPAIRS OF ONDO-OKEIGBO-OSUN STATE BORDER ROAD ROUTE NO 553 (F207) IN ONDO STATE | Plan | 1 | 159 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12110147 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
EMERGENCY REPAIRS OF IBILO EDO STATE BORDER - ISUA-EPINMI ROAD ROUTE NO 553 (F117) IN ONDO STATE | Plan | 1 | 160 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12110149 | Bills of Quantity | 82291159 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 82291159 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 82291159 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE REPAIRS OF OMUO-IFE-OLUKOTUN-KOGI STATE BORDER ROAD R554 IN EKITI STATE | Plan | 1 | 161 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 19/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12110153 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
EMERGENCY REPAIRS OF OMUO-BYE PASS IN EKITI STATE | Plan | 1 | 162 | Bills of Quantity | 50000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 50000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 50000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12110157 | Bills of Quantity | 33884595 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 33884595 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 33884595 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE REPAIRS OF OMUO-OYIN-ONDO STATE BORDER ROAD R554 IN EKITI STATE | Plan | 1 | 163 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12110162 | Bills of Quantity | 86813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 86813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 86813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF ADO EKITI-ILUOMOBA-IMESI-ONDO STATE BORDER ROAD R554 IN EKITI STATE | Plan | 1 | 164 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12110167 | Bills of Quantity | 82291159 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 82291159 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 82291159 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE REPAIRS OF IBADAN -IFE DUAL CARRIAGEWAY ROAD, ROUTE 35 IN OSUN STATE | Plan | 1 | 165 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12110172 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAJOR MAINTENANCE REPAIRS OF IFE -ILESA DUAL CARRIAGEWAY ROAD, ROUTE 35 IN OSUN STATE | Plan | 1 | 166 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12110175 | Bills of Quantity | 82291159 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 82291159 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 82291159 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF IFE-SEKONA ROAD, ROUTE 530 IN OSUN STATE | Plan | 1 | 167 | Bills of Quantity | 150000000 | NCB | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12110176 | Bills of Quantity | 82291159 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 82291159 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 82291159 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE REPAIRS OF OSOGBO-IIOBU-OYO STATE BORDER ROAD, IN OSUN STATE | Plan | 1 | 168 | Bills of Quantity | 50250000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 50250000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 50250000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12110181 | Bills of Quantity | 33884595 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 33884595 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 33884595 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
SPECIAL REPAIRS OF OSOGBO-OKUKU-KWSB ROAD ROUTE 530 IN OSUN STATE | Plan | 1 | 169 | Bills of Quantity | 110000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 110000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 110000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12110188 | Bills of Quantity | 62928534 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 62928534 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 62928534 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
COMPLETION OF PHASE IV PLANNED WORK FERMA STATE FIELD OFFICE LAGOS STATE | Plan | 1 | 170 | Bills of Quantity | 120000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 120000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 120000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP27109048 | Bills of Quantity | 77450503 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 77450503 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 77450503 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
OPERATION, MAINTENANCE AND REPAIR (OMR) OF STREET LIGHTENING INSTALLATION ALONG LAGOS - IBADAN EXPRESSWAY OJOO & IBADAN- IFE ROAD , IBADAN OYO STATE | Plan | 1 | 171 | Bills of Quantity | 25000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 25000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 25000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP10109997 | Bills of Quantity | 14521969 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 14521969 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 14521969 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
OPERATION, MAINTENANCE AND REPAIRS (OMR) OF STREET LIGHTHENING INSTALLATION ALONG AKURE-OWO ROAD EKITI INTERCHANGE AKURE ONDO STATE | Plan | 1 | 172 | Bills of Quantity | 15000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 15000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 15000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP10110000 | Bills of Quantity | 9681313 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 9681313 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 9681313 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
COMPLETION OF PHASE 1 ON GOING WORKS FERMA STATE FIELD OFFICES , AWKA, LAFIA, ADO-EKITI, JALINGO, OWERRI,SOKOTO, DUTSE, AKURE | Plan | 1 | 173 | Bills of Quantity | 226907156 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 226907156 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 226907156 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP27109051 | Bills of Quantity | 106494441 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 106494441 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 106494441 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
COMPLETION OF PHASE II ONGOING WORKS FERMA STATE FIELD OFFICES, KADUNA, BAYELSA, DELTA | Plan | 1 | 174 | Bills of Quantity | 244026007 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 244026007 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 244026007 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP27109054 | Bills of Quantity | 106175754 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 106175754 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 106175754 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PROVISION AND INSTALLATION OF ROAD SIGNS NATIONWIDE 2 NOS. ROADS PER 36 STATES AND FCT | Plan | 1 | 175 | Bills of Quantity | 55560000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 55560000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 55560000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP30109834 | Bills of Quantity | 33884595 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 33884595 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 33884595 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF OCCUPIED OBSERVATION AND SERVICE CAMPS AT 45NOS LOCATION | Plan | 1 | 176 | Bills of Quantity | 30000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 30000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 30000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP27109063 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PRODUCTION OF 100 ROAD MATS PER STATE FOR 36 STATES AND FCT | Plan | 1 | 177 | Bills of Quantity | 36000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 36000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 36000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP30109073 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
CONSTRUCTION OF CORPORATE HEADQUARTERS OFFICE COMPLEX , ABUJA FERMA (ON GOING) | Plan | 1 | 178 | Bills of Quantity | 230000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 230000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 230000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP27109063 | Bills of Quantity | 106175754 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 106175754 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 106175754 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
ANNUAL ROAD CONDITION SURVEY USING STATE - OF- ART TECHNOLOGY | Plan | 1 | 179 | Bills of Quantity | 20000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 20000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 20000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP30109070 | Bills of Quantity | 14521969 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 14521969 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 14521969 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PRODUCTION OF RUBBERISED ASPHALT | Plan | 1 | 180 | Bills of Quantity | 21441000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 21441000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 21441000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP30109072 | Bills of Quantity | 9681313 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 9681313 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 9681313 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PROVISION FOR THE INTRODUCTION OF PERCENT WITHIN LIMIT (PWL) SPECIFICATION AS A QUALITY PARAMETER FOR THE PAYMENT OF INTERIM CERTIFICATION | Plan | 1 | 181 | Bills of Quantity | 15000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 15000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 15000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP30109830 | Bills of Quantity | 9681313 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 9681313 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 9681313 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
OPERATION, MAINTENANCE AND REPAIR (OMR) OF AGENCY'S GENERATORS (220,200,350 &400VA) AT HEADQUARTERS | Plan | 1 | 182 | Bills of Quantity | 35000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 35000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 35000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP10110003 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PROCUREMENT OF SPARE PARTS FOR POTHOLES PATCHERS FOR ROADS AND BRIDGES MAINTENANCE | Plan | 1 | 183 | Bills of Quantity | 40000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 40000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 40000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12110007 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PROCUREMENT OF LIGHT EQUIPMENT 4TON DOUBLE DRUM MOTORABLE ROLLER FOR ROADS & BRIDGES MAINTENANCE | Plan | 1 | 184 | Bills of Quantity | 90000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 90000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 90000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12110012 | Bills of Quantity | 58087877 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 58087877 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 58087877 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PROCUREMENT OF HEAVY OPERATION VEHICLES FOR ROADS, SUPERVISION & MONITORING | Plan | 1 | 185 | Bills of Quantity | 160000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 160000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 160000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12110014 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PROCUREMENT OF LIGHT OPERATION VEHICLES FOR SUPERVISION AND MONITORING | Plan | 1 | 186 | Bills of Quantity | 90000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 90000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 90000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12110016 | Bills of Quantity | 58087877 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 58087877 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 58087877 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PROCUREMENT OF OPERATIONAL DUMPER TRUCKS FOR ROADS & BRIDGES MAINTENANCE | Plan | 1 | 187 | Bills of Quantity | 100000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 100000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 10000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12110020 | Bills of Quantity | 33884595 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 33884595 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 33884595 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF THE ICT INFRASTRUCTURES, LOCAL AREA NETWORK AND WIRELESS LAN AT THE HEADQUARTERS , OFFICE ANNEX AND FIELD OFFICES (ON GOING) | Plan | 1 | 188 | Bills of Quantity | 30000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 30000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 30000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP29110038 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
CONSTRUCTION / PROVISION OF SOLAR ENERGY | Plan | 1 | 189 | Bills of Quantity | 30000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 30000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 30000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP10109294 | Bills of Quantity | 16458232 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 16458232 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 16458232 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
CONSTRUCTION / PROVISION OF LECTURE THEATRE | Plan | 1 | 190 | Bills of Quantity | 90000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 90000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 90000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP23109249 | Bills of Quantity | 48406564 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 48406564 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 48406564 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
CONSTRUCTION /PROVISION OF ROAD NETWORK, OFFICE FIXTURE & FITTINGS AND GUEST HOUSE | Plan | 1 | 191 | Bills of Quantity | 160000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 160000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 160000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP23109254 | Bills of Quantity | 135538380 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 135538380 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 135538380 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION / REPAIR OF CLASS ROOMS | Plan | 1 | 192 | Bills of Quantity | 230000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 230000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 230000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP23109260 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PURCHASE OF SURVEYING INSTRUMENT | Plan | 1 | 193 | Bills of Quantity | 230000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 230000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 230000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP23109270 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PURCHASE OF COMPUTER SOFTWARE FOR THE TEACHING OF STUDENTS | Plan | 1 | 194 | Bills of Quantity | 90000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 90000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 90000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP23109279 | Bills of Quantity | 9681313 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 9681313 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 9681313 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF STUDENTS HOSTEL | Plan | 1 | 195 | Bills of Quantity | 230000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 230000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 230000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP23109286 | Bills of Quantity | 9681313 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 9681313 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 9681313 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PROVISION OF VIRTUAL LIBRARY | Plan | 1 | 196 | Bills of Quantity | 160000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 160000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 160000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP23109312 | Bills of Quantity | 9681313 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 9681313 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 9681313 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PURCHASE OF MOTOR VEHICLES-TOYOTA HILUX JEEP (2 NOS) | Plan | 1 | 197 | Bills of Quantity | 90000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 90000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 90000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP23109316 | Bills of Quantity | 46470302 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 46470302 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 46470302 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION / REPAIRS - OFFICE BUILDING | Plan | 1 | 198 | Bills of Quantity | 230000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 230000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 230000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP27109302 | Bills of Quantity | 9681313 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 9681313 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 9681313 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
RESEARCH AND DEVELOPMENT - CAPACITY BUILDING | Plan | 1 | 199 | Bills of Quantity | 230000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 230000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 230000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP30109308 | Bills of Quantity | 14521969 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 14521969 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 14521969 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ORE-AGBABU ROAD IN ODIGBO LOCAL GOVERNMENT AREA, ONDO STATE | Plan | 1 | 200 | Bills of Quantity | 160000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 160000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 160000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP445002907 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
CONSTRUCTION OF ACCESS ROAD FROM ONICHUBOMA THROUGH AFOR UMEZE MARKETS SQUARE TO EZIMBA COMMUNITY IHITE UBOMA LGA, IMO STATE | Plan | 1 | 201 | Bills of Quantity | 90000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 90000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 90000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP445082870 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
CONSTRUCTION OF FIVE KILOMETRE ROAD (5KLM) FOR ABA NORTH/ SOUTH FEDERAL CONSTITUENCY OF ABIA STATE. | Plan | 1 | 202 | Bills of Quantity | 230000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 230000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 230000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP445002908 | Bills of Quantity | 9681313 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 9681313 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 9681313 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF 4KM YAMMAMA TO GWANAMARDE ROAD IN MALUMFASHI LOCAL GOVERNMENT AREA, MALUMFASHI/ KAFUR FEDERAL CONSTITUENCY, KATSINA STATE | Plan | 1 | 203 | Bills of Quantity | 160000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 160000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 160000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP445002909 | Bills of Quantity | 67769190 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 67769190 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 67769190 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF 3KM HAYIN GADA TO TORA ROAD IN MALUMFASHI LOCAL GOVERNMENT AREA, MALUMFASHI/ KAFUR FEDERAL CONSTITUENCY, KATSINA STATE | Plan | 1 | 204 | Bills of Quantity | 90000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 90000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 90000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP445002910 | Bills of Quantity | 50826892 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 50826892 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 50826892 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ORIE NGURU-UMUAGA- UMUKABIR ROAD, NGOR OKPALA IMO STATE | Plan | 1 | 205 | Bills of Quantity | 230000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 230000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 230000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP445003011 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
SOFTWARE MAINTENANCE/HOSTING (GIS SOFTWARE, NINE SOFTWARE, WEBSITE, HR SOFTWARE, ANTIVIRUS, EXCHANGE SERVERS, NETWORK MANAGEMENT AND STAFF TRAINING | Plan | 1 | 206 | Bills of Quantity | 160000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 160000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 160000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP29110031 | Bills of Quantity | 14521969 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 14521969 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 14521969 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
UPGRADE OF PROJECT DATA MANAGEMENT SYSTEM (PDMS) TO A FULL SCALE ENTERPRISE PROJECT MANAGEMENT SYSTEM (E MONITOR) MAINTENANCE AND STAFF TRAINING | Plan | 1 | 207 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP29110033 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PROCUREMEENT AND INSTALLATION OF CENTRALIZED IN VENTORY MANAGEMENT SYSTEM, MAINTENENACE AND STAFF TRAINING | Plan | 1 | 208 | Bills of Quantity | 250000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 250000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 250000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP29110034 | Bills of Quantity | 33884595 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 33884595 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 33884595 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE AND UPGRADE OF THE HP SAN STORAGE SYSTEM AND IMPLEMENTATION OF VIRTUALIZATION OF THE SERVERS AND STAFF TRAINING | Plan | 1 | 209 | Bills of Quantity | 250000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 250000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 250000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP29110035 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
INTERNET SUBSCRIPTION FOR THE HQTRS AND 12 ZONAL OFFICES BY GALAXY BACKBONE | Plan | 1 | 210 | Bills of Quantity | 160000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 160000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 160000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP110039 | Bills of Quantity | 9681313 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 9681313 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 9681313 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PROCUREMENT AND INSTALLATION OF AN ENTERPRISE NETWORK SECURITY AND MOBILITY SOLUTION WITH TRAINING AND ONE YEAR MAINTENANCE FOR THE AGENCY | Plan | 1 | 211 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP29110040 | Bills of Quantity | 15490101 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 15490101 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 15490101 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF DATA CENTER | Plan | 1 | 212 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP29110043 | Bills of Quantity | 6765407 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 6765407 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 6765407 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
UPGRADE AND MAINTENANCE OF OFFICE 365 AND MICROSOFT EMS | Plan | 1 | 213 | Bills of Quantity | 250000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 250000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 250000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP29110045 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PROCUREMENT AND INSTALLATION OF VIDEO SECURITY AND SURVEILLANCE SOLUTION FOR THE AGENCY'S HEADQUARTERS AND OFFICE ANNEX (INCLUSIVE OF STAFF TRAINING AND 1 YEAR MAINTENANCE ) | Plan | 1 | 214 | Bills of Quantity | 160000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 160000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 160000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP29110048 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
DEPLOYMENT OF ROAD ASSET MANAGEMENT SYSTEM | Plan | 1 | 215 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP30109068 | Bills of Quantity | 15490101 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 15490101 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 15490101 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PROVISION OF WORK ZONE SAFETY DEVICES FOR FIELD OFFICES AND HEADQUARTERS | Plan | 1 | 216 | Bills of Quantity | 250000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 250000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 250000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP30109836 | Bills of Quantity | 9681313 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 9681313 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 9681313 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
COSULTANCY FOR ROADS MAINTENANCE MANAGEMENT SERVICES | Plan | 1 | 217 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP30109837 | Bills of Quantity | 33884595 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 33884595 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 33884595 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MONITORING AND EVALUATION OF PROJECTS | Plan | 1 | 218 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP30109905 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
ADMINSTRATION AND COORDINATION | Plan | 1 | 219 | Bills of Quantity | 140000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 140000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 140000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP30109911 | Bills of Quantity | 62609846 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 62609846 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 62609846 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PROVISION OF STORAGE AND RECORDING EQUIPMENT FOR BOARD MEETINGS AND RECORDS | Plan | 1 | 220 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP30109914 | Bills of Quantity | 14521969 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 14521969 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 14521969 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF HADEJIA ROAD TO ZAKIRAI TO EASTERN BYE PASS KANO STATE | Plan | 1 | 221 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109502 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
EROSION CONTROL, PROVISION OF CONCRETE LINE AT WASIMI SANGO-ABEOKUTA DUAL CARRIAGEWAY OGUN STATE | Plan | 1 | 222 | Bills of Quantity | 160000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 160000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 160000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109503 | Bills of Quantity | 48406564 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 48406564 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 48406564 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
CONSTRUCTION OF DRAINAGE AND CULVERT AT TURAKU BY END FEDERAL ROAD KOKO-JEGA FEDERAL ROAD KEBBI STATE | Plan | 1 | 223 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109504 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF JAKUSKO/GASHU'A ROAD YOBE STATE | Plan | 1 | 224 | Bills of Quantity | 1750000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 1750000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 1750000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109505 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REPAIRS OF FEDERAL ROAD IN IKOT EKPENE/ESSIEN UDIM/OBOT AKARA FEDERAL CONSTITIUENCY, AKWA IBOM STATE | Plan | 1 | 225 | Bills of Quantity | 1450000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 1450000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 1450000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109506 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF BIRNIN-KUDU-ZANGA-DIKOKI ALONG MAIDUGURI ROAD, JIGAWA STATE | Plan | 1 | 226 | Bills of Quantity | 250000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 250000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 250000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109507 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REPAIRS OF FEDERAL ROAD FROM SAMINAKA TOWN (PHASE II) IN SHANGAL LGA OF KEBBI STATE | Plan | 1 | 227 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109508 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PROCUREMENT OF OPERATIONAL MONITORING VEHICLES FOR ROADS & SERVICES MAINTENANCE | Plan | 1 | 228 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12110023 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PROCUREMENT OF WORKING TOOLS AND SPARE PARTS FOR FERMA KUJE WORKSHOP | Plan | 1 | 229 | Bills of Quantity | 250000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 250000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 250000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12110024 | Bills of Quantity | 4840656 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 4840656 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 4840656 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PROCUREMENT OF 2NO. 15TONS HIAB (CRANE) | Plan | 1 | 230 | Bills of Quantity | 140000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 140000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 140000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12110026 | Bills of Quantity | 33884595 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 33884595 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 33884595 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PROCUREMENT OF 1NO. 200KVA SOUND PROOF (PERKIN ENGINE ) GENERATOR FOR FERMA ANNEX OFFCIE | Plan | 1 | 231 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP12110027 | Bills of Quantity | 14521969 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 14521969 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 14521969 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF BAKIN KASUWA-UNGUWAN GERIUNGUWAN HUDU - TASHAN TSAMIYA ROAD, KADUNA STATE | Plan | 1 | 232 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109509 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF FAILED PORTION WESTERN BYE PASS IN SOKOTO, SOKOTO STATE | Plan | 1 | 233 | Bills of Quantity | 140000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 140000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 140000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109510 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF OBA NNEWI ROAD SPUR TO ICHI TRIANGULAR ICHI INDUSTRIAL ROAD FOR CONVEYANCE OF AGRICULTURAL PRODUCE, ANAMBRA STATE | Plan | 1 | 234 | Bills of Quantity | 170000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 170000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 170000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109511 | Bills of Quantity | 135538380 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 135538380 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 135538380 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF FEDERAL ROADS IN IGBARA ODO EKITI TO IKOGOSI EKITI AND IKERE EKITI TO ISE EKITI | Plan | 1 | 235 | Bills of Quantity | 160000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 160000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 160000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109512 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PROVISION OFF ACEESS ROAD IN UMUOBA-ANAM WITH SPUR OTUOCHA-NZAM-ABAJI EXPRESSWAY , ANAMBRA STATE | Plan | 1 | 236 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109513 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REPAIRS OF ABAKALIKI/ISHIEKA EXPRESS ROAD, EBOYI STATE | Plan | 1 | 237 | Bills of Quantity | 160000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 160000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 160000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109514 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION AND ASHALTING OF 5KM OLD FEDERAL BENIN ROAD FROM AUCHI-BENIN FEDERAL HIGHWAY TO CAMPUS 2 ROAD, AUCHI FEDERAL POLYTECHNIC ROAD, AUCHI, EDO STATE. | Plan | 1 | 238 | Bills of Quantity | 1250000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 1250000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 1250000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109515 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF 8KM ROAD FROM AGENBODETO UNEUDEGOR, ETDAKOR EAST, FEDERAL CONSTITUENCY, EDO STATE | Plan | 1 | 239 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109516 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF OVADE/JESSE ROAD OFF SAPELE BENIN FEDERAL HIGHWAY, DELTA STATE | Plan | 1 | 240 | Bills of Quantity | 170000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 170000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 170000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109517 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF MUTUM BIYU-WUKARI ROAD - BENUE STATE BOARDER IN TARABA STATE | Plan | 1 | 241 | Bills of Quantity | 250000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 250000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 250000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109518 | Bills of Quantity | 24043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ENAGI-GBODOTI ROAD OFF BIDA-MOKWA FEDERAL HIGHWAY, NIGER STATE. | Plan | 1 | 242 | Bills of Quantity | 2400000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 2400000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 2400000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109519 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF OWENA CANTONMENT BARRACKS ROAD, AKURE, ONDO STATE | Plan | 1 | 243 | Bills of Quantity | 220000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 220000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 220000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109520 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF TORU EBENI-OKUMBIRI ROAD, OFF YENEGOA-MBIAMA ROAD OFF AMMASOMA ROAD, (PHASE II) BAYELSA STATE | Plan | 1 | 244 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109521 | Bills of Quantity | 48406564 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 48406564 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 48406564 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF BENIN/ABUDU (ASABA) ROAD IN EDO STATE | Plan | 1 | 245 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109522 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ASERI-APA ROAD IN BADAGRY, LAGOS STATE | Plan | 1 | 246 | Bills of Quantity | 170000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 170000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 170000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109523 | Bills of Quantity | 48406564 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 48406564 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 48406564 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION/ MODERNISATION OF THE ON-GOING ENUGU ONITSHA EXPRESSWAY WITH A SPUR AT OCHALLA-URUM ROAD, (PHASE II) IN ANAMBRA STATE | Plan | 1 | 247 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109524 | Bills of Quantity | 55183483 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 55183483 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 55183483 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF PAP FEDERAL ROAD SPUR AT DIRBI ROAD, BAGORO, BAUCHI STATE | Plan | 1 | 248 | Bills of Quantity | 170000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 170000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 170000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109525 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REPAIR OF DILAPIDATED PORTION OF IFON UZEBBA ROAD, OWON WEST EDO STATE | Plan | 1 | 249 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109526 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF YAKO-MADOBI-KAFIN MAIYAKI ROAD SPUR AT KWANAR DANGORA, OFF KANO-ZARIA ROAD ,KANO STATE. | Plan | 1 | 250 | Bills of Quantity | 250000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 250000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 250000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109527 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REINSTATEMENT OF SHOULDERS AT KADAURI MAYANCI, DANBALA AND STRENTHENING OVERLAY FROM GUSAU-TALATA MAFARA ROAD IN ZAMFARA STATE | Plan | 1 | 251 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109528 | Bills of Quantity | 67769190 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 67769190 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 67769190 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REINSTATEMENT OF SHOULDERS AND EMBARKMENT PROTECTION IN GUSAU-KAURA NAMODA ROAD IN ZAMFARA STATE | Plan | 1 | 252 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109529 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ORIE NGURU-UMUAGA- UMUKABIR ROAD, IMO STATE | Plan | 1 | 253 | Bills of Quantity | 220000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 220000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 220000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109530 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
RECONSTRUCTION OF OKEOLA-AKOLU ROAD,ERUWA, IBARAPA EAST LGA IN OYO STATE. | Plan | 1 | 254 | Bills of Quantity | 220000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 220000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 220000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109531 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
RENOVATION OF ISEYIN/IPAPO /OKOKA ROAD (PHASE II) IN OYO STATE | Plan | 1 | 255 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109532 | Bills of Quantity | 48406564 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 48406564 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 48406564 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION / REPAIRS OF FUNTUA-JABIRI ROAD, KATSINA STATE | Plan | 1 | 256 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109533 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF POTISKUM-FIKA- GOMBA ROAD (PHASE II) YOBE STATE | Plan | 1 | 257 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109534 | Bills of Quantity | 48406564 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 48406564 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 48406564 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF BIU -WANDALI ROAD (PHASE II) IN BORNO STATE | Plan | 1 | 258 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109535 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
RECONSTRUCTION OF MICHIKA - MODA BRIDGE ON KAMALE FEDERAL ROAD, ADAMAWA STATE. | Plan | 1 | 259 | Bills of Quantity | 250000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 250000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 250000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109536 | Bills of Quantity | 48406564 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 48406564 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 48406564 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF UKEHE-OHODO ROAD (PHASE II ) ENUGU STATE | Plan | 1 | 260 | Bills of Quantity | 20000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 20000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 20000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109537 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REPAIRS OF FEDERAL ROAD IN DAMBATTA BY -PASS, KANO STATE. | Plan | 1 | 261 | Bills of Quantity | 250000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 250000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 250000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109538 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF KANADAP (MARARABAN JAMAA JUNCTION) KURU, SPUR ALONG JOS-GIMI ROAD IN PLATEAU STATE | Plan | 1 | 262 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109539 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ZUNGERU-WUSHISHI-BIDA ROAD IN NIGER STATE | Plan | 1 | 263 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109540 | Bills of Quantity | 87131816 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 87131816 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 87131816 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF AMANGBU ROAD AND NDIA MKPACHARA AND AWA ROAD ALONG OZO ABAM-ARO CHUKWU-OHAFIA FEDERA HIGHWAY, ABIA STATE | Plan | 1 | 264 | Bills of Quantity | 1750000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 1750000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 1750000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109541 | Bills of Quantity | 14521969 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 14521969 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 14521969 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILATION OF ANIOCHA SOUTH-UBULU OKITI FEDERAL ROAD SPUR AT OGBE-OJI ROAD, DELTA STATE | Plan | 1 | 265 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109542 | Bills of Quantity | 14521969 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 14521969 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 14521969 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF DOGARAWA LINK ROAD (PHASE II) KADUNA-KANO EXPRESSWAY IN KADUNA STATE | Plan | 1 | 266 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109543 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE OF DILAPIDATED ROAD AT ILESHA OKUTA-KOSUBOSU-CHIKANDA ROAD (PHASE 2 IN KWARA STATE) | Plan | 1 | 267 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109544 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF IPELE--ISHUA ROAD, AFO/IDOAN JUNCTION ONDO STATE | Plan | 1 | 268 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109545 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE/REHABILITATION OF AIYEGUNJ EGBEDDE-ILLUKE FEDERAL ROAD, KOGI STATE | Plan | 1 | 269 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109546 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ANZE-NGALDA-GOMBE STATE BORDER ROAD IN YOBE STATE | Plan | 1 | 270 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109547 | Bills of Quantity | 67769190 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 67769190 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 67769190 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF ITOBE-OTUKPA ROAD, OTUKPA ANKPA SECTION OGBADIBO BENUE STATE | Plan | 1 | 271 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109548 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REPAIRS/REHABILITATION OFAKPABUYA-BAKASSI ROAD IN CROSS RIVER STATE | Plan | 1 | 272 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109549 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF JAMA'A RE-ITAS GADAU ROAD IN BAUCHI STATE | Plan | 1 | 273 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109550 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE OF OKENE-IBILLO ROAD IN KOGI STATE | Plan | 1 | 274 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109551 | Bills of Quantity | 67769190 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 67769190 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 67769190 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE OF SECTION 3 RIVERS BORDER-OWERRI ORLU WITH DRAINAGE AND BOX CULVERTS PHASE (2) STARTING FROM ORLU IN IMO STATE | Plan | 1 | 275 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109552 | Bills of Quantity | 116175754 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 116175754 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 116175754 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION/RECONSTRUCTION OF MAIDUGURI-MONGUNO BAGA ROAD, BORNO STATE | Plan | 1 | 276 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109553 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
LERE TAFAWA-BAUCHI-GINDIRI PLATEAU - MANGU , PHASE 3 PLATEAU STATE | Plan | 1 | 278 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109554 | Bills of Quantity | 164582318 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 164582318 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 164582318 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF IHIALA-UMUDURU FEDERAL ROAD SECTION 1 SPUR TO MANAOGU-MUZIKE-IMENYI ZURUIHITE ROAD WITH WORK CONSTRUCTION OF FAILED MULTIPLE BOX CULVERT ON OHIARA RIVER, ORSU IMO STATE | Plan | 1 | 279 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109555 | Bills of Quantity | 150060349 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150060349 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150060349 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF USMAN DANFODIO UNIVERSITY INTERNAL ROAD, SOKOTO STATE | Plan | 1 | 280 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109556 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF FEDERAL PSYCHIATRIC HOSPITAL , KWARE INTERNAL ROAD, SOKOTO STATE | Plan | 1 | 281 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109557 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF ALA URUMUDHU ROAD ISOKO SPUR TO BENIN - ONITSHA EXPRESS ROAD, DELTA STATE | Plan | 1 | 282 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109558 | Bills of Quantity | 67769190 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 67769190 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 67769190 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF WAMAKKO/BUNKARI ROAD SOKOTO STATE | Plan | 1 | 283 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109559 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GRADING, SPUR TO REPAIRS AND REHABILITATION ONITSHA-OWERRI EXPRESSWAY SPUR TO AKILIOGIDI-OMA ROAD | Plan | 1 | 284 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109560 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF ORAUKWU-ABATETE SPUR TO EZIOWERRI ROAD ONITSHA-ENUGU EXPRESSWAY | Plan | 1 | 285 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109561 | Bills of Quantity | 33884595 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 33884595 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 33884595 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION AND MAINTENANCE OF DARAZO-LANZAPAIDA BAUCHI STATE | Plan | 1 | 286 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109562 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF ONISHA-OWERRI EXPRESSWAY INTERCHANGE AT AMIRA -ATTA ROAD, ORU EAST IMO STATE | Plan | 1 | 287 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109563 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF KALAMBAINA ROAD, SOKOTO STATE | Plan | 1 | 289 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109564 | Bills of Quantity | 77450503 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 77450503 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 77450503 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF OWERRI -OKIGWE ROAD SPUR THROUGH CHUKWUMANWAOHA TO NGWA ROAD FOR ECONOMIC REASONS ,OWERRI IMO STATE | Plan | 1 | 290 | Bills of Quantity | 140000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 140000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 140000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109565 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF JALINGO -WUKARI ROAD SPUR TO COLLEGE OF AGRICULTURE JALINGO- TARABA STATE | Plan | 1 | 291 | Bills of Quantity | 140000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 140000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 140000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP09566 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILATATION IHIALA-ORLU-UMUDURU EXPRESS ROAD SPUR TO NANMA CUM BAMA ROAD IHIOMA IMO STATE | Plan | 1 | 292 | Bills of Quantity | 140000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 140000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 140000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109567 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ASABA-ONITSHA EXPRESS WAY (MAINTENANCE OF EBU-AHIA ROAD) DELTA STATE | Plan | 1 | 293 | Bills of Quantity | 250000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 250000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 250000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109568 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF KOROKORO/UGKEN ROAD IN TAI LGA ELEME/OYIBO/TAI FEDERAL CONSTITUENCY RIVER STATE | Plan | 1 | 294 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109569 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ROADS IN ONYEPA/AMULEMA AND OCHOBO IN OTUKPO/OHINIMI FEDERAL CONSTITUENCY BENUE STATE | Plan | 1 | 295 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109570 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ANYAFUIJIJI ROAD IN NRI ANAOCHA IN ANAMBRA STATE | Plan | 1 | 296 | Bills of Quantity | 170000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 170000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 170000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109571 | Bills of Quantity | 48406564 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 48406564 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 48406564 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE OF ONITSHA-OTUOCHA-ADANI FEDERAL ROAD SPUR TO AMADIE-OUT-IFITE-OGWARI ANANBRA STATE | Plan | 1 | 297 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109572 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF IHIALA-UMUDURU FEDERAL ROAD SECTION II IMO STATE | Plan | 1 | 298 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109573 | Bills of Quantity | 67769190 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 67769190 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 67769190 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OWERRI -UMUAHUA EXPRESS ROAD SPUR TO UMUEZERUGWU ROAD , OWERRI IMO STATE | Plan | 1 | 299 | Bills of Quantity | 220000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 220000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 220000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109574 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
CONSTRUCTION OF ROAD WITH DRAINAGE AT LINE NWOSU STREET RAYFIELD JOS PLATEAU STATE | Plan | 1 | 300 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109575 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION MPETE-IRUOBIELLI ROAD OFF ENUGU - ONISHA EXPRESS ROAD, ANAMBRA STATE | Plan | 1 | 301 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109576 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION IJEBU-ODE/IBADAN/OYO/ILORIN SPUR AT AWOYELU-BONOJO ROAD, IJEBU-QDE, OGUN STATE | Plan | 1 | 302 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109577 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION IHIALA-UMUDURU EXPRESSWAY SPUR TO UMUEZEALA -EZIORSUAKWALILU ROAD, ANANBRA STATE | Plan | 1 | 303 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109578 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION AND REPAIRS OF ROADS IN IMMIGRATION TRIANING SCHOOL, UMUOWA ORLU IMO STATE | Plan | 1 | 304 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109579 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF URASI RIVER BRIDGE FROM UMUDIALA NNEWI SOUTH TO LILUIHIALA LGA ANAMBRA STATE | Plan | 1 | 305 | Bills of Quantity | 400000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 400000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 400000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109580 | Bills of Quantity | 309802011 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 309802011 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 309802011 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION RIVER STATE BORDER-OWERRI-ORLU EXPRESS SECTION III, ROUTE 414 (F229) REHABILITATION OF A SPUR TO THE LINK BRIDGE/ROAD ON URASI RIVER BETWEEN ISI-IHITE OWERRI AND OBODOUKWU | Plan | 1 | 306 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109581 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ASSOCIATION AVENUE, IJESHATEDO AND OPELOYERU STREET BY BODE THOMAS ORILEIGANMUSURULERE II FED. CONSTITUENCY, LAGOS STATE | Plan | 1 | 307 | Bills of Quantity | 190000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 190000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 190000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109582 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
CONSTRUCTION OF URASI RIVER BRIDGE FROM AMARURU, IMO STATE TO EZINITITE ANAMBRA STATE, IMO STATE | Plan | 1 | 308 | Bills of Quantity | 400000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 400000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 400000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP3210983 | Bills of Quantity | 304961355 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 304961355 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 304961355 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF OLD ENUGU PORT-HARCOURT ROAD (IHIEAGBUDU ROAD) ENUGU STATE | Plan | 1 | 309 | Bills of Quantity | 160000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 160000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 160000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109584 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF OZUBULU-NNEWI-OKIGWE EXPRESS ROAD ORU-RINKO DRIVE NNEWI INDUSTRIAL LAYOUT (FOR TRANSPORTATION OF INDUSTRIAL PRODUCTS) ANAMBRA STATE | Plan | 1 | 310 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109585 | Bills of Quantity | 33884595 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 33884595 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 33884595 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF ROADS IN DUSTE AND KIYAWA LGA JIGAWA STATE | Plan | 1 | 311 | Bills of Quantity | 155000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 155000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 155000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109586 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF MGBEE-AMAIGBO ROAD ORLU IMO STATE | Plan | 1 | 312 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109587 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF ENUGU-PORT HARCOURT EXPRESS WAY SPUR TO AMUZUTA-UMUOVO-UMUECHEOKWU OLD UMUAHI ABIA STATE | Plan | 1 | 313 | Bills of Quantity | 1800000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 1800000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 1800000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109588 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF 3KM ROAD IN ANKPA, KOGI STATE | Plan | 1 | 314 | Bills of Quantity | 1250000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 1250000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 1250000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109589 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GRADING AND REHABILITATION OF IHIALA-ORLU-UMUDURU FEDERAL ROAD SECTION 1 SPUR TO MORNING STAR ROAD, ORLU IMO STATE | Plan | 1 | 315 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109590 | Bills of Quantity | 33884595 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 33884595 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 33884595 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
TRAINING OF YOUTHS ON ASHALT MACHINE OPERATION AND USE OF HEAVY DUTY CONSTRUCTION EQUIPMENTS IN ANAMBRA NORTH SENATORIAL DIST. | Plan | 1 | 316 | Bills of Quantity | 170000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 170000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 170000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109591 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF ONISHA-OKIGWE FEDERAL ROAD SPUR TO ASIANYA ROAD EKWUSIGO LGA ANAMBRA STATE | Plan | 1 | 317 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109592 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION AND MAINTENANCE OF ARONDIZUOGU-AKOKWA-UGA EXPRESSWAY SPUR TO UMUOPIA-OWERRI-OKAKWUE (PHASE2 DAVID'S ROAD) IMO STATE | Plan | 1 | 318 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109593 | Bills of Quantity | 33884595 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 33884595 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 33884595 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF ONISHA-OWERRI EXPRESS ANUNWA-UMUDIOKA ROAD OKIJA ANAMBRA STATE | Plan | 1 | 319 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109594 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF IFIRAAKOKO-ISUAAKOKO ROAD AT AKOKO SOUTH EAST LGA ONDO STATE | Plan | 1 | 320 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109595 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF OBA-NNEWI- OKIGWE EXPRESSWAY SPUR TO OSURUMENYI- ADENO- FIRE JUNCTION ANAMBRA STATE | Plan | 1 | 321 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109596 | Bills of Quantity | 58087877 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 58087877 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 58087877 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF OBA NNEWI -OKIGWE EXPRESSWAY SPUR TO DIMALAOSUMENYIAWOABANATO JUNCTION UMUDIALAIJRASI BRIDGE PHASE I OFF OBA-NNEWI OKIGWE ROAD ANAMBRA SATE | Plan | 1 | 322 | Bills of Quantity | 190000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 190000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 190000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109597 | Bills of Quantity | 48406564 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 48406564 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 48406564 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF OYO-ILORIN WITH INTERCHANGE AT IWOFIN ROAD | Plan | 1 | 323 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109598 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF AKANU -IHIE (UMUAPU ROAD) OWERRI PORTHARCOURT EXPRESSWAY UMUAPU-APANI ROAD/OWERRI EXPRESSWAY | Plan | 1 | 324 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109599 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ENUGU-NSUKKA-KOGI ROAD SPUR TO UMUAGAMA ENUGU STATE | Plan | 1 | 325 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109600 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF NWOOBINIGWU MARKET TO AKWAIHEDI ANANBRA STATE WITH INTERCHANGE AT OMAGONANSA ROAD ORLU IMO STATE | Plan | 1 | 326 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109601 | Bills of Quantity | 53247221 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 53247221 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 53247221 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF KABA-OMUO FED. ROAD SPUR AT OWO BODE-ODO ONA ROAD EKINRIN-ADDE KOGI STATE | Plan | 1 | 327 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109602 | Bills of Quantity | 33884595 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 33884595 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 33884595 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF MADUBUZ-JIKE ECO-ORIENTED ROAD UZOAKWU-IHIALA ANAMBRA STATE | Plan | 1 | 328 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109603 | Bills of Quantity | 67769190 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 67769190 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 67769190 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
RECONSTRUCTION OF BOTEM/KPITE/UEKEN ROAD IN ELEME/OYIGBO/TAI FED. CONSTITUENCY, RIVER STATE | Plan | 1 | 329 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109604 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF ROAD IN OGBOMOSHO SOUTH LOCAL GOVT. AREA OYO STATE | Plan | 1 | 330 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109605 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF DETERIORATED ROAD IN EJIGBO, OSHODI-ISOLO 2 FED. CONSTITUENCY, LAGOS STATE | Plan | 1 | 331 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109606 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF AKWOCHA-OLOSHI ROAD, ESAN SOUTH EAST LGA, EDO STATE | Plan | 1 | 332 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109607 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF EKWULOBIA/UGA/OKIGWE FEDERAL HIGHWAY AGUATA FED. CONSTITUENCY ANAMBRA STATE | Plan | 1 | 333 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109608 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF ENUGU-ABAKILIKI EXPRESSWAY SPUR AT UGWUMBA-OKPOKU-OKPOSI ROAD, DELTA STATE | Plan | 1 | 334 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109609 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF BENIN-ONISHA EXPRESS ROAD SPUR TO OWONTAALIOSIMIOWAALIZOMOR ROAD DELTA STATE | Plan | 1 | 335 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109610 | Bills of Quantity | 53247221 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 53247221 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 53247221 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF ONDO-AKURE EXPRESSWAY SPUR TO ASIN-LAGEGHE ROAD, ONDO STATE | Plan | 1 | 336 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109611 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE AND REPAIRS OF IDAH-ODOLU-IBAGWA-NSUKKA ROAD IN KOGI STATE | Plan | 1 | 337 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109612 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF PARK ONE UMUATIJOLUOGBU ROAD, UMUERI ANAMBRA LGA ANAMBRA STATE | Plan | 1 | 338 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109613 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ROAD FROM IGBO-ORA TO IGANGAN IN IBARAP CENTRAL/IBARAPA NORTH FED. CONSTITUENCY OYO STATE | Plan | 1 | 339 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109614 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF BUGUMA-ASARI TORU OFF EAST WEST- BAYELSA PORT HARCOURT, RIVER STATE | Plan | 1 | 340 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109615 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENACE OF REFINERY/OBIANIME ROAD OKRIKA LGA RIVER STATE | Plan | 1 | 341 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109616 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE/REPAIRS/COMPLETION ON IKANWEKE/AGULEZE ROAD 2KM AHIAZUMBAISE, IMO STATE | Plan | 1 | 342 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109617 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE AND SPECIAL REPAIRS ON OGUDU OJOTA ROAD , KOSOFE CONSTITUENCY LAGOS STATE | Plan | 1 | 343 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109618 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION/REPAIR OF STRRET LIGHT INSTALLATION ON CONSTITUENCY LAGOS STATE | Plan | 1 | 344 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109619 | Bills of Quantity | 9681313 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 9681313 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 9681313 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF NASARAWA EGGON-MADA STATION ACCESS ROAD NASARAWA STATE. | Plan | 1 | 345 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109620 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF KWARE GIDA NMADI-TANGAZA LGA SOKOTO STATE | Plan | 1 | 346 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109621 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION AND MAINTENANCE OF IKOT-EDOR, IKOT MBAT IKOT NDUAEMAN ROAD, ALONG EKET-IKOT BASI ROAD, AKWA IBOM STATE | Plan | 1 | 347 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109622 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GRADING MARARABA BASHIMO-BAISSA-ABONG FEDERAL ROAD IN GASHAKA/KURMI/SARDAUNA. FEDERAL CONSTITUENCY TARABA STATE | Plan | 1 | 348 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109623 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF ADOGO-OGANE IN AJAO KUTA FEDERAL CONSTITUENCY, KOGI STATE | Plan | 1 | 349 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109624 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
ROAD MAINTENANCE IN NGO-ILOTOMBIANDONI LGA RIVERS STATE | Plan | 1 | 350 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109625 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION AND RE-ENFORCEMENT OF THE ULASI-OKIJA BRIDGE ALONG ONITSHA-OWERRI ROAD IN IHIALA FED. CONSTITUENCY, ANAMBRA STATE | Plan | 1 | 351 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109626 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF PART OF OLD AGEGE MOTOR ROAD FROM MANGORO TO ABULEEGBA IN AGEGE FEDERAL CONSTITUENCY IN LAGOS STATE | Plan | 1 | 352 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109627 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF UMUDURUARO ROAD ABAJAHN WANGELE LGA CONNECTING ORIE ABAJAH IMO STATE | Plan | 1 | 353 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109628 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF MBAKITAM ROAD OFF CALABAR RITU EXPRESSWAY CROSS RIVER STATE | Plan | 1 | 354 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109629 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REPAIR/MAINTENANCE OF TAKUM-KATSINA ALA ROAD TARABA STATE | Plan | 1 | 355 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109630 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF KADUNA-ABUJA EXPRESSWAY ROAD SPUR TO BUNTU-IKU RIVER IN TAFA LGA NIGER STATE | Plan | 1 | 356 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109631 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
RENOVATION OF ROAD IN BENDE FED. CONSTITUENCY , ABIA STATE | Plan | 1 | 357 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109632 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
RENOVATION OF DAN LAWAN BRIDGE IN KATSINA STATE | Plan | 1 | 358 | Bills of Quantity | 225000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 225000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 225000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109633 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION/REPAIRS OF SOLAR POWERED STREET LIGHT AT MAILAFIYA AND GIDANWAYA, KADUNA STATE ALONG GIMI-KAGORO-KADUNA FEDERAL ROAD | Plan | 1 | 359 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109634 | Bills of Quantity | 14521969 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 14521969 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 14521969 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF EHINJOK-NWANGA ROAD, OGOJA LGA CROSS RIVER STATE | Plan | 1 | 360 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109635 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF OCHUBIUGAGA-IPUOLE-UGAGA ROAD YALA LGA CROSS RIVER STATE | Plan | 1 | 361 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109636 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION AND MAINTENANCE OF TRINITY ROAD, LAGOS STATE | Plan | 1 | 362 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109637 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF TUDUNBARIKI-SULEJA CLUB ROAD IN SULEJA LGA SULEJA/TAFA/GURARA FED. CONSTITUENCY, NIGER STATE | Plan | 1 | 363 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109638 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF FATHER WALSH-HOSPITAL ROAD, UMUAKURU, EMEKUKUOWERRI NORTH LGA, IMO STATE | Plan | 1 | 364 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109639 | Bills of Quantity | 33884595 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 33884595 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 33884595 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF OGBE-OGUME-IGBE ROAD IN NDOKWA/UKWUANI FEDERAL CONSTITUENCY, DELTA STATE | Plan | 1 | 365 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109640 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF OMUIYADUN-CENTRAL HOTEL BYE PASS ROAD IN IGBETI, OLORUNSOGO LGA UNDER IREPO/OORELOPE/OLORUNSOGO FED. CONSTITUENCY, OYO STATE | Plan | 1 | 366 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109641 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
CONSTRUCTION OF DRAINAGES AND ROADS AT BABURA/GARKI FEDERAL CONSTITUENCY, JIGAWA STATE. | Plan | 1 | 367 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109642 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ORIENGURUMUAGA/UMUKABIA ROAD IMO STATE | Plan | 1 | 368 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109643 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
CONSTRUCTION OF NTA ROAD IRUEKPEN ESAN WEST LGA EDO STATE | Plan | 1 | 369 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109644 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ROADS IN ILAJE/ESE-ODO FEDERAL CONSTITUENCY | Plan | 1 | 370 | Bills of Quantity | 225000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 225000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 225000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109645 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF AWAKAMBUTU-UMUOSHI ROAD, UVURU ROAD, ABO MBAISE IMO STATE | Plan | 1 | 371 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109646 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ACCESS ROAD FROM OKUKU, CROSS RIVER STATE TO BENUE STATE | Plan | 1 | 372 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109647 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
CONSULTANCY SERVICES FOR TRAFFIC MANAGEMENT SYSTEM IMPLEMENTATION PLAN FOR NNEWI INDUSTRIAL CLUSTER ERGP/SEZ FERMA | Plan | 1 | 373 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109648 | Bills of Quantity | 14521969 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 14521969 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 14521969 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF NNEWI POST OFFICE-TRAFFIC LIGHT 2KM FEDERAL ROAD IN NNEWI NORTH LGA ANAMBRA STATE | Plan | 1 | 374 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109649 | Bills of Quantity | 33884595 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 33884595 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 33884595 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF THE MAJOR ROAD FOR ECONOMIC REASONS (AGRIC PRODUCTS TRANSPORTATION) IN OPARANA DIM MBAISE IMO STATE OFF OWERRIUMAHIA EXPRESSWAY | Plan | 1 | 375 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109650 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF TSANYAWA TO GURUN ROAD IN KANO STATE | Plan | 1 | 376 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109652 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
RECONSTRUCTION AND RAHABILITATION OF UMUOGELE-ACHARA- UGWUEMEUMUNNEOCHI ON THE ENUGU PORT- HARCOURT EXPRESSWAY, ABIA STATE. | Plan | 1 | 377 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109653 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REPAIRS OF ROAD AT GIDAN SANI IN JABA LGA, KADUNA STATE | Plan | 1 | 378 | Bills of Quantity | 225000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 225000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 225000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109654 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ANYAFUIJIJI ROAD NRIANAOCHA ANAMBRA STATE | Plan | 1 | 379 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109655 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
RECONSTRUCTION OF OKPOSI TO ISU (11KM) PORTION OF NARA-ISU-OKPOSI FEDERAL HIGHWAY (F113) ENUGU/EBOYI STATE | Plan | 1 | 380 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109656 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
CONSTRUCTION OF ODO-ONA ELEWA-IDI-IROKO-OLUGBEMI- ADEWOLE ROAD IN OLUYOLE FEDERAL CONSTITUENCY, OYO STATE | Plan | 1 | 381 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109657 | Bills of Quantity | 23235151 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 23235151 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 23235151 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION APANI- OZUZU ROAD IN IKWERRE LGA RIVERS STATE EMOHUA-KALABARI ROAD IN EMUHUA LGA RIVER STATE | Plan | 1 | 382 | Bills of Quantity | 225000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 225000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 225000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109658 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF ILA - AGBAMU ROAD IN ILA LGA, OSUN STATE OFF OSOGBO-ILORIN FEDERAL HIGH WAY | Plan | 1 | 383 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109659 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REPAIRS AND MAINTENANCE OF IWO-OSOGBO ROAD IN AYEDIRE/IWO/OLA-OLUWA FED. CONSTITUENCY OSUN STATE | Plan | 1 | 384 | Bills of Quantity | 225000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 225000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 225000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109660 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ROADS IN GWARAM FEDERAL CONSTITUENCY, JIGAWA STATE | Plan | 1 | 385 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109661 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
CONSTRUCTION OF KOTO IRABA ROAD OFF AKOWONJO ROAD, ALIMOSHO FEDERAL CONSTITUENCY , LAGOS STATE | Plan | 1 | 386 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109662 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF OWERRI-OKIWE AT UMUEHIE INTEGRATED OIL PALM FACTORY, IKEDURU, OWERRI IMO STATE | Plan | 1 | 387 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109663 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
CONSTRUCTION OF DRAINAGE AND CULVERTS IN MWONA | Plan | 1 | 388 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109664 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
CONSTRUCTION OF TOWNSHIP 2KM ROAD AND DRAINAGE IN URUALLA, OBODOUKWU, IDEATO NORTH LGA, IMO STATE | Plan | 1 | 389 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109665 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
RESURFACING AND REHABILITATION OF OWODE-ILARO ROAD, EGBADO SOUTH LGA | Plan | 1 | 390 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109666 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF AGEGE MOTOR ROAD IN MUSHIN 1, LAGOS STATE (FEDERAL ROAD) | Plan | 1 | 391 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109667 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF OF EZIEBE ALFRED TO EZIBE RUFUS NNENANYA OF UMUEZEAKPUAKPU, ORUMBA SOUTH LGA, ANAMBRA STATE (2 1/2 KM) | Plan | 1 | 392 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109668 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF BENIN-ONISHA EXPRESS ROAD SPUR TO KWALE-EBEDE-UMUTU ROAD, DELTA STATE | Plan | 1 | 393 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109669 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
CONSTRUCTION OF KWATA-MANI ROAD, MANI- HAMCHETA ROAD SPUR TO MAGAMI AND BINDAWA-SHIFDAWA ROAD IN BINDAWA/MANI FEDERAL CONSTITUENCY, KATSINA STATE | Plan | 1 | 394 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109670 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF CYRIL CHAKA ROAD, OFF ENUGU PORT-HARCOURT EXPRESSWAY ,ENUGU STATE | Plan | 1 | 395 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109671 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF OWO-IKARE FEDERAL ROAD SPUR AT ADELOYE JUNCTION PHASE 2 ONDO STATE | Plan | 1 | 396 | Bills of Quantity | 225000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 225000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 225000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109672 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF ROAD IN LAGELU/AKINYELE FEDERAL CONSTITUENCY, OYO STATE. | Plan | 1 | 397 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109673 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF ABA- PORT HARCOURT EXPRESSWAY SPUR AT NGWA ROAD BY ASA ROAD PEOPLE ROAD JUNCTION ABIA STATE | Plan | 1 | 398 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109674 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REPAIR OF FEDERAL ROAD IN DAMBATTA BYEPASS KANO STATE | Plan | 1 | 399 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109675 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF KWARU ROAD BADARAWAMALANI | Plan | 1 | 400 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109676 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF BARKINLADI-MANGU ROADS IN PLATEAU STATE | Plan | 1 | 401 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109677 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF NNEWI-OZUBULU-STADIUM ROAD ANAMBRA STATE | Plan | 1 | 402 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109678 | Bills of Quantity | 33884595 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 33884595 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 33884595 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
CONSTRUCTION AND REHABILITATION OF EGBELU/ABAYI ROAD OSISIOMANGWA LGA ABIA STATE | Plan | 1 | 403 | Bills of Quantity | 225000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 225000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 225000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109679 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF OGURUGU-ADANI-NSUKKA ROAD (ENUGU STATE) | Plan | 1 | 404 | Bills of Quantity | 225000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 225000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 225000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109680 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE OF GAUTA/NIKE ROAD, KEFFI NASARAWA STATE | Plan | 1 | 405 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109681 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
COMPLETION OF DRAINAGES AND FORTIFIED CULVERT IN NTIGHA, NSULU, UMUOHA, NGWAUKWU ROAD, ISIALANGWA NORTH LGAA AND NVOSI, MBUTU, AMAOBI, OVIOVI ROAD IN ISIALANGWA SOUTH LGA, ABIA STATE | Plan | 1 | 406 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109682 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF SELECTED EKETE ROAD IN IGBO-EZE SOUTH LGA ENUGU STATE | Plan | 1 | 407 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109683 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION KANAM-GUYUK FEDERAL ROAD SPUR TO KURI TO LAMBAM ROAD, GOMBE STATE | Plan | 1 | 408 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109684 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
TRAINING AND EMPOWERMENT OF WOMEN AND YOUTH ON ASPHALT PRODUCTION IM MINNA CHACHANGA FEDERAL CONSTITUENCY OF NIGER STATE | Plan | 1 | 409 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109685 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF JALINGO -MARARRABA NAPAWA-MAYOLOPE ROAD IN ARDO-KOLA/KARIM-LAMIDO/LAU FEDERAL CONSTITUENCY , TARABA STATE | Plan | 1 | 410 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109686 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION, REPAIRS AND MAINTENANCE OF ONNE ROAD SPUR (PHASE 4) IN OBIO/AKPOR FEDRAL CONSTITUIENCY, RIVERS STATE | Plan | 1 | 411 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109687 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
CONSTRUCTION OF GADIYA-UDUBO-KAKIROMI-GAMAWA GOLOLO-JAKUSKO-ZINDIWA-TARMASUWA-KORE/KUBDIYA FEDERAL ROADS GAMAWA FEDERAL CONSTITUENCY, BAUCHI STATE | Plan | 1 | 412 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109688 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF DA CHOP BUSAH ROAD ,VOM (PHASE 3) SPUR TO SCHOOL OF NURSING PLATEAU STATE | Plan | 1 | 413 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109689 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF EAST WEST ROAD SPUR TO AHOADA-ABUA ROAD, RIVER STATE | Plan | 1 | 414 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109690 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ORU/AWA-IJEBU ROADS IN IJEBU NORTH/IJEBU EAST/OGUN WATERSIDE FEDERAL CONSTITUENCY | Plan | 1 | 415 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109691 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION KABBA- OMUO FEDERAL ROAD SPUR TO EBUNOLORUNDAMI ROAD EKINRIN ADDEIJOMU LGA KOGI STATE | Plan | 1 | 416 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109692 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF 60KM FEDERAL GOVERNMENT ROAD FROM KAGORO, MANCHOK (KADUNA STATE) TO GONAWURI.VOM ROAD ( PLATEAU STATE) | Plan | 1 | 417 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109693 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF OTUKPO-OJU ROAD, EARTH-SPOT, OGORE-ADUM WEST IKPONYIRE-OJIWO ROAD | Plan | 1 | 418 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109694 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REPAIR OF OZU-ABAM-OKAGWE-EBOYI FEDERAL ROAD IN AROCHUKWU/OHAFIA FEDERAL CONSTITUENCY | Plan | 1 | 419 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109695 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION AND MAINTENANCE OF FEANYI-OHIA ROAD OMOKU, RIVER STATE | Plan | 1 | 420 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109696 | Bills of Quantity | 19362626 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 19362626 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 19362626 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REPAIR/ RECONSTRUCTION OF POPOOLA STREET, OSHODI/ISOLO FEDERAL CONSTITUENCY, LAGOS STATE | Plan | 1 | 421 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109697 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF UMUAHIA -OWERRI EXPRESSWAY (UMULOGHA-AHAM-OKWUOHIA ROAD ) ABIA STATE | Plan | 1 | 422 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109698 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF BIDA-LEMU-ZUNGERU ROAD NIGER STATE | Plan | 1 | 423 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109699 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF BENIN-ASABA- ONITSHA EXPRESS ROAD OKPONTA JUNCTION ROAD SPUR TO UMUEZE-UZOROLU ROAD IBUSA DELTA STATE | Plan | 1 | 424 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109700 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF OWERRI-UMUAHIA HIGHWAY EGBELU-UMUHU ROAD ENYIOGU (PHASE 2) | Plan | 1 | 425 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109701 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF ROADS IN DAURAWA/HAUSA/DARMAWA IN KANO STATE | Plan | 1 | 426 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109702 | Bills of Quantity | 33884595 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 33884595 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 33884595 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ONITSHA-OWERRI FEDERAL EXPRESS ROAD SPUR TO UMUCHIMA-UMUBAZUULI ANAMBRA STATE | Plan | 1 | 427 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109703 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF POLICE ROAD ORSU OF IHIALA-UMUDURU ROAD INTERCHANGE AT UMUEZIKE, AMAOKPARA AND UMUEZENYI ROADS ORSU IMO STATE | Plan | 1 | 428 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109704 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF AGBANI-UGBAWKA-NARA-NKEREFI ROAD ENUGU STATE | Plan | 1 | 429 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109705 | Bills of Quantity | 24203282 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 24203282 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 24203282 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF AMBER FEDERAL ROAD SPUR TO KALASHI ROAD PLATEAU STATE | Plan | 1 | 430 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109706 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF OWERRI-OKIGWE EXPRESSWAY 'WUCHI - EBUBEDIKE ROAD, ORJI IMO STATE FOR TRANSPORTATION OF PRIMARYPRODUCTS | Plan | 1 | 431 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109707 | Bills of Quantity | 33884595 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 33884595 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 33884595 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ONISHA-OWERRI EXPRESS ROAD SPUR TO EDE-EZEMS-EZE-MOGAMBOORUMBA POLICE STATION-OBIBUENYI ANAMBRA STATE | Plan | 1 | 432 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109708 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE AND REHABILITATION OF IHITENANSA ROADS-AMADIABA-NWABIJO YEMA AND AKAMAORSU OFF IHIALA-UMUDURU SECTION 1 IMO STATE | Plan | 1 | 433 | Bills of Quantity | 1800000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 1800000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 1800000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109709 | Bills of Quantity | 48406564 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 48406564 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 48406564 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ROADS IN ONYEPA/AMULEMA AND OCHOBO IN OTUKPO/OHINIMI FEDERAL CONSTITUENCY BENUE STATE | Plan | 1 | 434 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109710 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF AKINTAN STREET, SURULERE 1 FEDERAL CONSTITUENCY, LAGOS STATE | Plan | 1 | 435 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109711 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF WASE-LANGTAN ROAD IN PLATEAU STATE | Plan | 1 | 436 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109712 | Bills of Quantity | 48406564 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 48406564 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 48406564 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF BAGA MOTOR PARK ABDU ONE MOHAMMAED TO SONGHAI ROAD JUNCTION IN MAIDUGURI BORNO STATE | Plan | 1 | 437 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109713 | Bills of Quantity | 67769190 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 67769190 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 67769190 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF SPECIAL SEGMENTS AT SABON PEGI NEW BUSSA TOWNSHIP AND KAINJI ROAD BYPASS ALONG MOKWA-NEW BUSSA-RAFIA-SWATE FEDERAL ROAD NIGER STATE | Plan | 1 | 438 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109714 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
COMPLETION OF PHASE II ON - GOING REPAIRS OF 15KM ROAD FROM NAFADA JUNCTION TO BARWO JUNCTION IN GOMBE STATE | Plan | 1 | 439 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109715 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REPAIRS OF EXISTING FEDERAL ROADS IN ANAMBRA NORTH SENATORIAL DISTRICT, ANAMBRA STATE | Plan | 1 | 440 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109716 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF DEIDEI DAKWA- MADALLA ROAD FCT ABUJA | Plan | 1 | 441 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109717 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF AWAJIN-ISE AGBERAAGRA- WUESE ROAD (SECTION) BENUE STATE | Plan | 1 | 442 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109718 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF OFOROLA PHASE II OLAUKWU ACCESS ROAD ALONG PORT HARCOURT EXPRESS ROAD OWERRI IMO STATE | Plan | 1 | 443 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109719 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
EMERGENCY REPAIRS OF CRITICAL FAILED SECTION ALONG GBAJI-OWODE ROAD IN BADAGARY IN LAGOS STATE | Plan | 1 | 445 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109720 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF MALUN FASHI/KAFUR/DABAI, KATSINA STATE | Plan | 1 | 446 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109721 | Bills of Quantity | 145219693 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 145219693 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 145219693 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF IRRUA TOWNSHIP ROAD, EDO STATE | Plan | 1 | 447 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109722 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF OSEGBO TO OKUKU ROAD, OSUN CENTRAL OSUN STATE | Plan | 1 | 448 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109723 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
SPECIAL PROTECTIVE MANAGEMENT REPAIRS ON BRIDGES 3,5 AND 6 ALONG ARGUNGU - BIU ROAD IN KEBBI NORTH SENATORIAL DISTRICT, KEBBI STATE | Plan | 1 | 449 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109724 | Bills of Quantity | 145219693 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 145219693 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 145219693 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ILLO-GIRIS ROAD IN KEBBI NORTH SENATORIAL DISTRICT, KEBBI STATE | Plan | 1 | 450 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109725 | Bills of Quantity | 145219693 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 145219693 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 145219693 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ARGUNGU-KAMBA ROAD (PHASE II) IN KEBBI NORTH SENATORIAL DISTRICT, KEBBI STATE | Plan | 1 | 451 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109726 | Bills of Quantity | 145219693 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 145219693 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 145219693 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ACCESS ROAD AND UPGRADE OF CONVOCATION/PAVILION AT ADAMU AUGIE COLLEGE OF EDUCATION, ARGUNGU, KEBBI NORTH SENATORIAL DISTRICT, KEBBI STATE | Plan | 1 | 452 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109727 | Bills of Quantity | 193626257 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 193626257 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 193626257 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REAHABILITATION OF ENUGU-PORT HARCOURT EXPRESS WAY , OGBAKU AMURI, INTERCHANGE AWGU LGA, ENUGU STATE | Plan | 1 | 453 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109728 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF OJI-ACHI-AWGU NDEGBOH-MPU-AKAETE FEDERAL ROAD, AMACHARA ODOEKPURO NZEREM INTERCHANGE, ANINRI LGA ENUGU STATE | Plan | 1 | 454 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109729 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF NGURU-GASHUA FEDERAL ROAD 64KM YOBE SOUTH SENATORIAL DISTRICT | Plan | 1 | 455 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109730 | Bills of Quantity | 242032821 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 242032821 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 242032821 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
COMPLETION OF THE REHABILITATION OF MARARABA-TUMU-PINDIGA-FUTUK-YALO ROAD | Plan | 1 | 456 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109731 | Bills of Quantity | 190439385 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 190439385 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 190439385 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF ORIE UMUEZU/UMUDINKA ROAD , ABOH MBAISE, IMO EAST SENATORIAL DISTRICT IMO STATE | Plan | 1 | 457 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109732 | Bills of Quantity | 101653785 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 101653785 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 101653785 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ITANNA-OGUNDELE-AGE OYO STATE BOUNDRY ROAD, KWARA STATE | Plan | 1 | 458 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109733 | Bills of Quantity | 145219693 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 145219693 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 145219693 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF GAMBARI-SOBI BARRACK-SHAO ROAD, KWARA STATE | Plan | 1 | 459 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109734 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF OKEOYI-OLOORU ROAD, KWARA STATE. | Plan | 1 | 460 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109735 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
COMLETION OF THE REHABILITATION OF DABA-KINAFA-GWARI WEST ROAD GOMBE STATE | Plan | 1 | 461 | Bills of Quantity | 500000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 500000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 500000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109736 | Bills of Quantity | 450439385 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 450439385 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 450439385 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF DABA-KINIFA GWARI WEST ROAD, GOMBE STATE | Plan | 1 | 462 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109737 | Bills of Quantity | 193626257 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 193626257 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 193626257 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ILLORIN-MARARABA-TUMU-FUTUK-YALO ROAD GOMBE STATE | Plan | 1 | 463 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP3210940 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF YOLA-FUFORE-GURIN ROAD, ADAMAWA STATE | Plan | 1 | 464 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109741 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ST.BRIGID BYPASS OF BODO BONNY ROAD, BODO CITY RIVER STATE | Plan | 1 | 465 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109742 | Bills of Quantity | 125857067 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 125857067 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 125857067 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE OF BORI BARRAKO LINK ROAD VIA YEGHE TOWN PORT HARCOURT RIVER STATE | Plan | 1 | 466 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109743 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENACE OF WAASE-LANGTANG ROAD, PLATAEU STATE | Plan | 1 | 467 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109744 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF OMERELU-OMUCHI ROAD OFF PORT HARCOURT -OWERRI ROAD RIVER STATE | Plan | 1 | 468 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109745 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF MGBOJI-VMUAGBAI-OYIGBO RIVER STATE | Plan | 1 | 469 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109746 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENACE AGENEBODE TOWNSHIP ETSAKA EAST LGA OF EDP NORTH IN EDO STATE | Plan | 1 | 470 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109747 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF MOGHO CENTRAL ROAD OF BODO-BONNY ROAD GOKANA RIVER STATE | Plan | 1 | 471 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109748 | Bills of Quantity | 116175754 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 116175754 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 116175754 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MENERAL MAINTENANCE OF AHOADA-OMOKU-OKWIZI ROAD RIVER STATE | Plan | 1 | 472 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109749 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE OF GOMBE DARAZO ROAD GOMBE STATE | Plan | 1 | 473 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109750 | Bills of Quantity | 116175754 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 116175754 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 116175754 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF KPITE-DEKEN-DEEYOUR- BIARA ROAD OFF EAST WEST ROAD RIVER STATE | Plan | 1 | 474 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109751 | Bills of Quantity | 193626257 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 193626257 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 193626257 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF APEGBON STREET TO ELEGBATA QUARTERS MARINA LAGOS ISLAND LAGOS STATE | Plan | 1 | 475 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109752 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF ZURU TO WASAGU ROAD, KEBBI STATE | Plan | 1 | 476 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109753 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF ALUU-EKPOREKA ROAD OFF EAST WEST ROAD, AKPAFO, ELEME RIVER STATE | Plan | 1 | 477 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109754 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
GENERAL MAINTENANCE OF EMOUHA-ABONEMA RIVER STATE | Plan | 1 | 478 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109755 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
MAINTENANCE OF BODO-BONNY EXPRESS SPUR TO BERA GOKANA FOR TRANSPORTATION OF PRIMARY PRODUCT IN RIVER STATE | Plan | 1 | 479 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109756 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF ONISHA ADANNI ROAD SPUR, FROM UMUARA OGBENDIDA-UMUIKPA -ABBAH-NNADI - NSUGBE ROAD IN ANAMBRA STATE | Plan | 1 | 480 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP32109757 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
CONSTRUCTION OF IKHIN-IDUMOGO ROAD LINKING THE FEDERAL HIGHWAY IRUEKPEN, ESAN WESAT/ESAN CENTRAL AND IGUEBEN FED. CONSTITUENCY EDO STATE | Plan | 1 | 481 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 180000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 180000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP445001256 | Bills of Quantity | 72609846 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 72609846 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 72609846 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
AGUMENTATION ON EZINIFITE - AMARURU BRIDGE (50M) AND EZINIFITE-LILU BRIDGE (50M) | Plan | 1 | 482 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP445001670 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATIONOF UDOJI ROAD FROM MICHAEL JUNCTION EKWUSIGO EXPRESS | Plan | 1 | 483 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP445001671 | Bills of Quantity | 106494441 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 106494441 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 106494441 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
CONSTRUCTION OF RURUM-YALWA ROAD | Plan | 1 | 484 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
wel;yu | Actual | 1 | ERGP445009218 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
0op[\ | Plan | 1 | 485 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP445009219 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
CONSTRUCTION OF KWANAR MARAKU-MARAKU ROAD | Plan | 1 | 486 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP445009220 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
CONSTRUCTION OF 5KM NDI-AGU-EDEMA ROAD IN NKALAGI ISHIELU LGA EBONYI STATE | Plan | 1 | 487 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP445001716 | Bills of Quantity | 96813128 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 96813128 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 96813128 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
CONSTRUCTION OF 20KM NEW BUSSA TOWNSHIP ROAD | Plan | 1 | 488 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP445001717 | Bills of Quantity | 193626257 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 193626257 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 193626257 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION AND RECONSTRUCTION OF UGA ROAD II SECTION IN ANAMBRA SOUTH SENATORIAL DISTRICT, ANAMBRA STATE | Plan | 1 | 489 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP445001718 | Bills of Quantity | 193626257 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 193626257 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 193626257 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
DESIGN AND DEVELOPMENT OF ROAD MAINTENANCE REPORTING SYSTEM | Plan | 1 | 490 | Bills of Quantity | 49163740 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 49163740 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 49163740 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP445001719 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
PAY FOR OUTSTANDING LIABILITY FOR PUBLIC WORKS (PIU/WORKS/15/1/16) 18 AND 15 FOR BAUCHI - GOMBE ROAD AND JOS-ABUJA ROAD 2015 | Plan | 1 | 491 | Bills of Quantity | 48406564 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 48406564 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 48406564 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP445001720 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF DANSARAI ROAD IN MALUM FASHI LGA MALUM FASHI/ KAFUR FEDERAL CONSTITUENCY , KATSINA STATE | Plan | 1 | 492 | Bills of Quantity | 43565908 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 43565908 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 43565908 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP445002900 | Bills of Quantity | 1550000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 1550000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 1550000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF UMUABAZU-ISI AHIA ORIE-UMUODA LINK ROAD AMUZU ABOH MBAISE LGA IMO STATE | Plan | 1 | 493 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP44903904 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION OF MAUTA-KAGARA ROAD IN MALUM FASHI LGA MALUMFASHI/KAFUR FEDERAL CONSTITUENCY, KATSINA STATE | Plan | 1 | 494 | Bills of Quantity | 43565908 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 43565908 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 43565908 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP445002901 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
COMPLETION AND EXTENSION OF AKILI OGIDI STREET ROAD (WITH DRAINAGES ) IN OGBARU ANAMBRA STATE | Plan | 1 | 495 | Bills of Quantity | 72609846 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 72609846 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 72609846 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP445002904 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 150000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 150000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
UMUATTUGBUOMA SIGNBOARD TO ENUGU, PH EXPRESSWAY/OBEAGHU OKWUO UGWUNANI AND AMIGBO RURAL ROAD CONSTRUCTION | Plan | 1 | 496 | Bills of Quantity | 38725251 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 38725251 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 38725251 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP445002905 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 200000000 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 200000000 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
REHABILITATION AND MAINTENANCE OF ODO-ORO EKITI TOWNSHIP ROAD ALONG IFAKI-IKOLE -OMUO ROAD IN EKITI STATE | Plan | 1 | 497 | Bills of Quantity | 29043939 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 | 29043939 | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA | 29043939 | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)
| Actual | 1 | ERGP445002906 | Bills of Quantity |  | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 15/01/18 - 29/01/18 | 30/01/18 - 6/02/18 | NA | NA | NA | 7/02/18 - 21/02/18 | 22/02/18 - 5/04/18 | 9/04/18 | 23/04/18 | 24/04/18 - 8/05/18 | 9/05/18 - 23/05/18 |  | NA | 24/05/18 - 7/06/18 | 11/06/18 - 25/06/18 | NA | NA | NA |  | B.A ILEMORE (Designation : Director) | N.A RAFINDADI (Managing Director)

## Works-NEMSA 2018
Ministry/Department/Agency: NIGERIAN ELECTRICITY MANAGEMENT SERVICES AGENCY (NEMSA) |  |  |  |  | PROCUREMENT PLAN - WORKS
Budgetary Year: 2018 |  | Draft Bid Documents including specs and quantities, draft SPN |  | If Post Review, No-objection Dates are not needed
Desk Officer/contact ≠: ERIKEN . 0805 616 4467 |  |  |  | Spec proc. Notice Advert | Bidding Period |  | Bid Evaluation |  |  | BASIC DATA | [5 empty] | Contract Finalization |  |  |  | Contract Implementation
Project Description | Plan vs. Actual | Prep. & Submission by MDAs | No-objection Date | Advertisement for Prequalification | Bid Invitation Date | Bid Closing - Opening | Submission Bid Eval. Report | No-objection Date | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or-Post Qualification | Prior or Post Review | Contract Amount Certified N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Remarks
Norm Duration of Proc Steps | Plan | 2 to 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | [5 empty] | If Prequalification |  |  | 2 wks | 1 - 2 wks | 3 wks
| Actual | [12 empty] | add 2 wks
List of Contracts
Purchase and installation of test equipment for the two Meter Test Stations, Oshodi and Port Harcourt | Plan | 5th - 23rd March | 26th March - 6th April | N/A | 23rd April | 1st June | 15th June | 22nd June | N/A | B/ Lot 1 | BOQ | NCB | 70000000 | Post | Post | To be determined | N/A | 5th July | 26th July | 15% | 20th March, 2019 | 25th March 2019 | To be determined
Actual
Opening of 2 new Meter Test Station in Enugu and Kano (Phase I/II) - Kano Phase II | Plan | 5th - 23rd March | 26th March - 6th April | N/A | 23rd April | 1st June | 15th June | 22nd June | N/A | B/ Lot 2 | BOQ | NCB |  | Post | Post | To be determined | N/A | 5th July | 26th July | 15% | 20th March, 2019 | 25th March 2019 | To be determined
Actual
Opening of new Inspectorate Field Offices in Bauchi, Uyo and Minna | Plan | 5th - 23rd March | 26th March - 6th April | N/A | 23rd April | 1st June | 15th June | 22nd June | N/A | B/ Lot 3 | BOQ | NCB | 20000000 | Post | Post | To be determined | N/A | 5th July | 26th July | 15% | 23rd Nov | 30th Nov. | To be determined
Actual
Renovation of 3 Inspectorate Field Offices in Ibadan, Ilorin and Sokoto (Inspectorate Field Office - Sokoto ) | Plan | 5th - 23rd March | 26th March - 6th April | N/A | 23rd April | 1st June | 15th June | 22nd June | N/A | B/Lot 4 | BOQ | NCB | 18500000 | Post | Post | To be determined | N/A | 5th July | 26th July | 15% | 23rd Nov | 30th Nov. | To be determined
Actual
Remodeling of National Meter Test Station Port Harcourt | Plan | 5th - 23rd March | 26th March - 6th April | N/A | 23rd April | 1st June | 15th June | 22nd June | N/A | B/ Lot 5 | BOQ | NCB | 100000000 | Post | Post | To be determined | N/A | 5th July | 26th July | 15% | 23rd Nov | 30th Nov. | To be determined
Actual
Total Cost | Plan
Actual
Fill gray cells only!

## Goods -NEMSA 2018
Ministry/Department/Agency: NIGERIAN ELECTRICITY MANAGEMENT SERVICES AGENCY (NEMSA) |  |  |  | PROCUREMENT PLAN - GOODS
Budgetary Year: 2018
Desk Officer/contact ≠: ERIKEN . 0805 616 4467 |  |  | BASIC DATA |  |  |  |  | Draft Bid Documents including specs and quantities, draft SPN |  | If Post Review, No-objection Dates are not needed
Project Description* | Plan vs. Actual | Package Number | Lot Number | Proposed Budget in Naira | Procurement Method | Pre or Post Qualification | Prior or Post Review |  |  | Spec proc. Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Norm Duration of Proc Steps | Plan |  |  |  |  | If Prequalification |  | Prep. & Submission by MDAs | No-objection Date | Advertisement for Prequalification | Bid Invitation Date | Bid Closing - Opening | Submission Bid Eval. Report | No-objection Date | Contract Amount Certified N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
| Actual |  |  |  |  | add 2 wks |  | 2 to 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 3 wks
List of Contracts
Procurement of computers servers, desktops, laptops, printers, scanners, ups, 2 nos. layer three switches. | Plan | N/A | A/Lot 1 | 12829050 | NCB | Post | Post | 5th - 23rd March | 26th March - 6th April | N/A | 23rd April | 4th May | 11th May | 25th May | To be determined | N/A | 15th June | 6th July | N/A | 20th July | 23rd July
Actual
Purchase of test equipment for 16 Area Offices under Technical Standard and Inspectorate Services Department | Plan | N/A | A/Lot 2 | 30000000 | NCB | Post | Post | 5th - 23rd March | 26th March - 6th April | N/A | 23rd April | 4th May | 11th May | 25th May | To be determined | N/A | 15th June | 6th July | 15% | 8th Oct | 15th Oct.
Actual
Total Cost
Fill gray cells only!

## Services - NEMSA 2018
| Ministry/Department/Agency: NIGERIAN ELECTRICITY MANAGEMENT SERVICES AGENCY (NEMSA) | [5 empty] | PROCUREMENT PLAN - CONSULTANCY SERVICES
| Budgetary Year: 2018 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest
| Desk Officer/contact ≠: ERIKEN . 0805 616 4467 |  | Contract Type |  |  |  | Preparation for Proposals |  |  |  | Short List |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [6 empty] | Contract Finalization |  |  |  | Contract Implementation
S/No | Project Description | Selection Method | Lumpsum or Time-Based | Proposed Budgetary Amount in Naira | Prior/Post Review | Plan vs. Actual | Prep. & Submission by MDAs | No objection Date | Advertisement | Lead-time before shortlist | Submission Date | No-objection Date | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Report | Submission Eval. Report (T) (F) | Negotiations (N) | Submission Date | No-objection Date | Contract Amount in Naira | Contract Award | Date of Contract Advert | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
| Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks |  | 4 wks |  | 3 wks
Actual
List of Contracts
1 | Legal services for the provision of electronic law library, review of NEMSA's acts dealing with enforcement and sanctions | LCS | Lumpsum | 25000000 | Post | Plan | 5th - 30th March | N/A | 16th - 27th April | 11th May | 14th May | 25th May | 4th June | 29th June | 20th July | 3rd Aug. | 17th Aug. | 31st Aug. | 3rd - 14th Sept | 17th - 28th Sept | 5th Oct | To be determined | 8th - 12th Oct | 15th Oct | 15th - 31st Oct | N/A | 30th Nov | 21st Dec. | To be determined
Actual
2 | Professional capacity building on government budgeting and financial systems and modelling and auditing | LCS | Lumpsum | 10753000 | Post | Plan | 5th - 30th March | N/A | 16th - 27th April | 11th May | 14th May | 25th May | 4th June | 29th June | 20th July | 3rd Aug. | 17th Aug. | 31st Aug. | 3rd - 14th Sept | 17th - 28th Sept | 5th Oct | To be determined | 8th - 12th Oct | 15th Oct | 15th - 31st Oct | N/A | 30th Nov | 21st Dec. | To be determined
Actual
3 | Consultancy for setting up of accounting system facilities and software upgrade for conversion and implementation of the International Public Sector Accounting Standard (IPSAS) | QBS | Lumpsum | 20000000 | Post | Plan | 5th - 30th March | N/A | 16th - 27th April | 11th May | 14th May | 25th May | 4th June | 29th June | 20th July | 3rd Aug. | 17th Aug. | 31st Aug. | 3rd - 14th Sept | 17th - 28th Sept | 5th Oct | To be determined | 8th - 12th Oct | 15th Oct | 15th - 31st Oct | N/A | 30th Nov | 21st Dec. | To be determined
Actual
4 | Consultancy Services for provision of technical drawing and BoQ for Opening of 2 New Meter Test Station in Enugu and Kano I/II, (Kano Phase 2). | LCS | Lumpsum | 2.5% of the proposed project cost | Post | Plan | 8th - 12th Jan | N/A | 15th - 26th Jan | 29th Jan | 31st Jan | 2nd Feb | 5th Feb | 2nd Mard | 6th March | 9th March | 14th March | 16th March | 19th March | 23rd March | 30th March | To be determined | 6th April | 9th April | 20th April | N/A | 18th May | 25th May | To be determined
Actual
5 | Consultancy Services for Supervision of Opening of 2 New Meter Test Station in Enugu and Kano I/II, (Kano Phase 2). | LCS | Lumpsum | 2.5% of the proposed project cost | Post | Plan | 5th - 28th Feb | N/A | 1st - 15th March | 23rd March | 26th March | 6th April | 9th April | 4th May | 25th May | 31st May | 7th June | 22nd June | 29th June | 6th July | 13th July | To be determined | 16th July | 17th July | 27th July | N/A | 2018-09-01 | 31st March 2019 | To be determined
Actual
6 | Consultancy Services for provision of technical drawing and BoQ for the Remodeling of National Meter Test Station Port Harcourt | LCS | Lumpsum | 2.5% of the proposed project cost | Post | Plan | 8th - 12th Jan | N/A | 15th - 26th Jan | 29th Jan | 31st Jan | 2nd Feb | 5th Feb | 2nd Mard | 6th March | 9th March | 14th March | 16th March | 19th March | 23rd March | 30th March | To be determined | 6th April | 9th April | 20th April | N/A | 18th May | 25th May | To be determined
Actual
7 | Consultancy Services for Supervision of the Remodeling of National Meter Test Station Port Harcourt | LCS | Lumpsum | 5% of the proposed project cost | Post | Plan | 5th - 28th Feb | N/A | 1st - 15th March | 23rd March | 26th March | 6th April | 9th April | 4th May | 25th May | 31st May | 7th June | 22nd June | 29th June | 6th July | 13th July | To be determined | 16th July | 17th July | 27th July | N/A | 2018-09-01 | 31st March 2019 | To be determined
Actual
8 | Consultancy Services for provision of technical drawing and BoQ for the Opening of new Inspectorate Field Offices in Bauchi, Uyo and Minna | LCS | Lumpsum | 5% of the proposed project cost | Post | Plan | 8th - 12th Jan | N/A | 15th - 26th Jan | 29th Jan | 31st Jan | 2nd Feb | 5th Feb | 2nd Mard | 6th March | 9th March | 14th March | 16th March | 19th March | 23rd March | 30th March | To be determined | 6th April | 9th April | 20th April | N/A | 18th May | 25th May | To be determined
Actual
9 | Consultancy Services for Supervision of the Opening of new Inspectorate Field Offices in Bauchi, Uyo and Minna | LCS | Lumpsum | 10% of the proposed project cost | Post | Plan | 5th - 28th Feb | N/A | 1st - 15th March | 23rd March | 26th March | 6th April | 9th April | 4th May | 25th May | 31st May | 7th June | 22nd June | 29th June | 6th July | 13th July | To be determined | 16th July | 17th July | 27th July | N/A | 2018-09-01 | 31st March 2019 | To be determined
Actual
| Total Cost |  |  |  | 0 | Plan | [15 empty] | 0 | [6 empty] | 0
[5 empty] | 0 | Actual | [15 empty] | 0 | [6 empty] | 0
Fill gray cells only!

## Gen. Info.
General Information
1 | Package Number is a number assigned to a procurement package made up of one or more Lots
2 | Lot Number is a unique number assigned to a particular lot in a package
3 | Budgetary Amount in Naira is the available fund duly approved or statutorily appropriated specifically for the project
4 | Procurement method is a process adopted in buying high quality goods and services as economically as possible through transparent and formal competitive bidding
5 | Pre - or Post-qualification is the qualification process which can be conducted prior to evaluating the Contractor's tender (pre-qualification or following the evaluation of the Contractor's tender (post-qualification)
6 | Prior-or-Post Review is the process where proposals are to be submitted for approval prior to taking the decision (prior-review) or Contracts are to be submitted to the Bureau prior to disbursement under the Contract for retroactive review even if the spending unit has already approved the awards and signed the Contracts (post-review)

## FEDERA MINISTRY OF PETROLEUM RE
NOCOPO DATA
PLANNING RECORD
MINISTRY OF PETROLEUM RESOURCES 2018
S/N | Project Code | Project Title | Project Rationale | Package Number | Lot Number | Development Partners | Budget Source | Budget Code | Budget Description | Budget Category | Budget Currency | Budget Amount | Project Estimated Currency | Project Estimated Amount | Project Category | Project Street | Project City | Nearest Landmark | Project LGA | Project State | Procurement Category | Contract type | Procurement Method | Selection Method | Appval Authority | Qualification | Review Type | Prep for Solicit Start date | Prep for Solicit End date | Is EoI applicable | Advert of EoI Start date | Advert of EoI End date | EoI Opening Event date | Eval of EoI Start Date | Eval of EoI End Date | EoI Eval Rpt Appval Start Date | EoI Eval Rpt Appval End Date | EoI Shortlist Publ Date | Invit Req Proposals Start Date | Invit Req Proposals End Date | Open of Tech Proposal Date | Tech Eval Rpt Approv Start Date | Tech Eval Rpt Approv End Date | Opening of Financial Proposal | Final Eval Rprt TF Start Date | Final Eval Rprt TF End Date | Negotiations Start Date | Negotiations End Date | Negotiations NotApplicable | Proc Entity Eval Rprt Appval Start Date | Proc Entity Eval Rprt Appval End Date | Iss of Cert of NO Eval Rprt Start Date | Iss of Cert of NO Eval Rprt End Date | Iss of Cert of NO Eval Rprt NotApplicable | Award Date | Submit of Final Rprt Start Date | Submit of Final Rprt End Date | Contract Period Start Date | Contract Period End Date | Contract Period Days | Prep of Bid Doc Advert Start Date | Prep of Bid Doc Advert End Date | Is PreQual applicable | Advert for PreQual Start Date | Advert for PreQual End Date | PreQual Opening Date | PreQual Eval Appval Start Date | PreQual Eval Appval End Date | PreQual Publish Date | Tendering Period Start Date | Tendering Period End Date | Bid Opening Date | Bid Evaluation Period Start Date | Bid Evaluation Period End Date | Proc Entity Eval Appval Start Date | Proc Entity Eval Appval End Date | Iss of Cert of NO Eval Rprt Start Date | Iss of Cert of NO Eval Rprt End Date | Contract Award Start Date | Contract Award End Date | Arrival of Goods Start Date | Arrival of Goods End Date | Substantial Completion Date | Final Acceptance Start Date | Final Acceptance End Date | Action Party Names | Action Party Designation | Action Party EMail | Action Party Phone | Champion Names | Champion Designation | Champion EMail | Champion Phone
1 | ERGP2100903 | OIL AND GAS SECTOR REFORM | OIL AND GAS SECTOR REFORM |  | N/A | N/A | 2018 APPROPRIATION BUDGET | ERGP2100903 | PROGRAMME | CAPITAL | NAIRA | 150000000 | NAIRA | 150000000 | CAPITAL | CBD ABUJA | FCT | NATIONAL MOSQUE | AMAC | FCT | CONSULTANCY | CAPITAL | NCB | QCBS | FEC | PRE-QUALIFICATION | PRE-REVIEW | 2018-10-09 | 24/09/2018 | YES | 2018-10-09 | 24/09/2018 | 24/09/2018 | 24/09/2018 | 2018-01-10 | 2018-01-10 | 2018-08-10 | 15/10/2018 | 15/10/2018 | 29/10/2018 | 29/10/2018 | 29/10/2018 | 2018-05-10 | 19/10/2018 | 19/10/2018 | 26/10/2018 | N/A | N/A | N/A | 26/10/2018 | 2018-03-12 | 2018-03-12 | 2018-10-12 | 2018-10-12 | 2018-10-12 | 2018-10-12 | 2019-04-02 | 2018-10-12 | 2019-04-02 | 60 Days | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Arc. O.I Agbe | Deputy Director (Proc)
2 | ERGP2100893 | IMPLEMENTATION OF NEW GAS POLICY | N/A |  | N/A | N/A | 2018 APPROPRIATION BUDGET | ERGP2100893 | PROGRAMME | CAPITAL | NAIRA | 100000000 | NAIRA | 100000000 | CAPITAL | CBD ABUJA | FCT | NATIONAL MOSQUE | AMAC | FCT | CONSULTANCY | CAPITAL | NCB | QCBS | MTB | PRE-QUALIFICATION | PRE-REVIEW | 2018-10-09 | 24/09/2018 | YES | 2018-10-09 | 24/09/2018 | 24/09/2018 | 24/09/2018 | 2018-01-10 | 2018-01-10 | 2018-08-10 | 15/10/2018 | 15/10/2018 | 29/10/2018 | 29/10/2018 | 29/10/2018 | 2018-05-10 | 19/10/2018 | 19/10/2018 | 26/10/2018 | N/A | N/A | N/A | 26/10/2018 | 2018-03-12 | 2018-03-12 | 2018-10-12 | 2018-10-12 | 2018-10-12 | 2018-10-12 | 2019-04-02 | 2018-10-12 | 2019-04-02 | 60 Days | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Arc. O.I Agbe | Deputy Director (Proc)
3 | ERGP2105025 | NATIONAL OIL AND GAS PRODUCTION ECONOMIC MODEL | N/A |  | N/A | N/A | 2018 APPROPRIATION BUDGET | ERGP2105025 | PROGRAMME | CAPITAL | NAIRA | 90000000 | NAIRA | 90000000 | CAPITAL | CBD ABUJA | FCT | NATIONAL MOSQUE | AMAC | FCT | CONSULTANCY | CAPITAL | NCB | QCBS | MTB | PRE-QUALIFICATION | PRE-REVIEW | 2018-10-09 | 24/09/2018 | YES | 2018-10-09 | 24/09/2018 | 24/09/2018 | 24/09/2018 | 2018-01-10 | 2018-01-10 | 2018-08-10 | 15/10/2018 | 15/10/2018 | 29/10/2018 | 29/10/2018 | 29/10/2018 | 2018-05-10 | 19/10/2018 | 19/10/2018 | 26/10/2018 | N/A | N/A | N/A | 26/10/2018 | 2018-03-12 | 2018-03-12 | 2018-10-12 | 2018-10-12 | 2018-10-12 | 2018-10-12 | 2019-04-02 | 2018-10-12 | 2019-04-02 | 60 Days | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Arc. O.I Agbe | Deputy Director (Proc)
4 | ERGP2100909 | IMPLEMENTATION OF SEVEN (7) BIG WINS | N/A |  | N/A | N/A | 2018 APPROPRIATION BUDGET | ERGP2100909 | PROGRAMME | CAPITAL | NAIRA | 110000000 | NAIRA | 110000000 | CAPITAL | CBD ABUJA | FCT | NATIONAL MOSQUE | AMAC | FCT | CONSULTANCY | CAPITAL | NCB | QCBS | MTB | PRE-QUALIFICATION | PRE-REVIEW | 2018-10-09 | 24/09/2018 | YES | 2018-10-09 | 24/09/2018 | 24/09/2018 | 24/09/2018 | 2018-01-10 | 2018-01-10 | 2018-08-10 | 15/10/2018 | 15/10/2018 | 29/10/2018 | 29/10/2018 | 29/10/2018 | 2018-05-10 | 19/10/2018 | 19/10/2018 | 26/10/2018 | N/A | N/A | N/A | 26/10/2018 | 2018-03-12 | 2018-03-12 | 2018-10-12 | 2018-10-12 | 2018-10-12 | 2018-10-12 | 2019-04-02 | 2018-10-12 | 2019-04-02 | 60 Days | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Arc. O.I Agbe | Deputy Director (Proc)
5 | ERGP17100934 | LEGAL SERVICES AND LITIGATION | N/A |  | N/A | N/A | 2018 APPROPRIATION BUDGET | ERGP17100934 | LITIGATIONS PAYMENTS | CAPITAL | NAIRA | 200000000 | NAIRA | 200000000 | CAPITAL | CBD ABUJA | FCT | NATIONAL MOSQUE | AMAC | FCT | CONSULTANCY | CAPITAL | NCB | QCBS | FEC | PRE-QUALIFICATION | PRE-REVIEW | 2018-10-09 | 24/09/2018 | YES | 2018-10-09 | 24/09/2018 | 24/09/2018 | 24/09/2018 | 2018-01-10 | 2018-01-10 | 2018-08-10 | 15/10/2018 | 15/10/2018 | 29/10/2018 | 29/10/2018 | 29/10/2018 | 2018-05-10 | 19/10/2018 | 19/10/2018 | 26/10/2018 | N/A | N/A | N/A | 26/10/2018 | 2018-03-12 | 2018-03-12 | 2018-10-12 | 2018-10-12 | 2018-10-12 | 2018-10-12 | 2019-04-02 | 2018-10-12 | 2019-04-02 | 60 Days | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Arc. O.I Agbe | Deputy Director (Proc)
6 | ERGP2104814 | DEVELOPMENT OF CRITICAL MANAGERIAL COMPETENCES INCLUDING INTERNATIONAL PUBLIC SECTOR ACCOUNTING STANDARDS IPSAS FOR OIL AND GAS SECTOR WITHIN THE RELEVANT MDAs, LEGISLATURE AND FAAC | N/A |  | N/A | N/A | 2018 APPROPRIATION BUDGET | ERGP2104814 | CONSULTANCY SERVICES FOR THE CAPACITY BUILDING ON MODERN TECHNIQUES IN THE OPERATIONS OF OIL AND GAS FOR SENIOR TECHNICAL/PROFESSIONAL STAFF OF THE MINISTRY |  | NAIRA | 25000000 | NAIRA | 25000000 | CAPITAL | CBD ABUJA | FCT | NATIONAL MOSQUE | AMAC | FCT | CONSULTANCY | CAPITAL | NCB | QCBS | MTB | PRE-QUALIFICATION | PRE-REVIEW | 30/07/2018 | 13/8/2018 | YES | 30/07/2018 | 13/8/2018 | 13/8/2018 | 13/8/2018 | 20/8/2018 | 20/8/2018 | 27/8/2018 | 2018-03-09 | 2018-03-09 | 17/9/2018 | 17/9/2018 | 17/9/2018 | 24/9/2018 | 2018-08-10 | 2018-08-10 | 15/10/2018 | N/A | N/A | N/A | 15/10/2018 | 22/10/2018 | 22/10/2018 | 29/10/2018 | 29/10/2018 | 29/10/2018 | 29/10/2018 | 28/12/2018 | 29/10/2018 | 28/12/2018 | 60 Days | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Arc. O.I Agbe | Deputy Director (Proc)
7 | ERGP2104814 | DEVELOPMENT OF CRITICAL MANAGERIAL COMPETENCES INCLUDING INTERNATIONAL PUBLIC SECTOR ACCOUNTING STANDARDS IPSAS FOR OIL AND GAS SECTOR WITHIN THE RELEVANT MDAs, LEGISLATURE AND FAAC | N/A |  | N/A | N/A | 2018 APPROPRIATION BUDGET | ERGP2104814 | CONSULTANCY SERVICES FOR THR DEVELOPMENT OF MANAGERIAL SKILLS ON GLOBAL BEST PRACTISES IN THE OIL AND GAS INDUSTRY FOR TOP MANAGEMENT AND SENIOR STAFF OF THE MINISTRY | CAPITAL | NAIRA | 25000000 | NAIRA | 25000000 | CAPITAL | CBD ABUJA | FCT | NATIONAL MOSQUE | AMAC | FCT | CONSULTANCY | CAPITAL | NCB | LERB | MTB | PRE-QUALIFICATION | PRE-REVIEW | 30/07/2018 | 13/8/2018 | YES | 30/07/2018 | 13/8/2018 | 13/8/2018 | 13/8/2018 | 20/8/2018 | 20/8/2018 | 27/8/2018 | 2018-03-09 | 2018-03-09 | 17/9/2018 | 17/9/2018 | 17/9/2018 | 24/9/2018 | 2018-08-10 | 2018-08-10 | 15/10/2018 | N/A | N/A | N/A | 15/10/2018 | 22/10/2018 | 22/10/2018 | 29/10/2018 | 29/10/2018 | 29/10/2018 | 29/10/2018 | 28/12/2018 | 29/10/2018 | 28/12/2018 | 60 Days | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Arc. O.I Agbe | Deputy Director (Proc)
8 | ERGP2104814 | DEVELOPMENT OF CRITICAL MANAGERIAL COMPETENCES INCLUDING INTERNATIONAL PUBLIC SECTOR ACCOUNTING STANDARDS IPSAS FOR OIL AND GAS SECTOR WITHIN THE RELEVANT MDAs, LEGISLATURE AND FAAC | N/A | MPR/PROC/S.30/1/T | N/A | N/A | 2018 APPROPRIATION BUDGET | ERGP2104814 | CONSULTANCY SERVICES FOR CAPACITY BUILDING FOR ACCOUNT OFFICERS IN THE MINISTRY ON THE OPERATIONS OF IPSAS ETC | CAPITAL | NAIRA | 32000000 | NAIRA | 32000000 | CAPITAL | CBD ABUJA | FCT | NATIONAL MOSQUE | AMAC | FCT | CONSULTANCY | CAPITAL | NCB | QCBS | MTB | PRE-QUALIFICATION | PRE-REVIEW | 30/07/2018 | 13/8/2018 | YES | 30/07/2018 | 13/8/2018 | 13/8/2018 | 13/8/2018 | 20/8/2018 | 20/8/2018 | 27/8/2018 | 2018-03-09 | 2018-03-09 | 17/9/2018 | 17/9/2018 | 17/9/2018 | 24/9/2018 | 2018-08-10 | 2018-08-10 | 15/10/2018 | N/A | N/A | N/A | 15/10/2018 | 22/10/2018 | 22/10/2018 | 29/10/2018 | 29/10/2018 | 29/10/2018 | 29/10/2018 | 28/12/2018 | 29/10/2018 | 28/12/2018 | 60 Days | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Arc. O.I Agbe | Deputy Director (Proc)
9 | ERGP2104814 | DEVELOPMENT OF CRITICAL MANAGERIAL COMPETENCES INCLUDING INTERNATIONAL PUBLIC SECTOR ACCOUNTING STANDARDS IPSAS FOR OIL AND GAS SECTOR WITHIN THE RELEVANT MDAs, LEGISLATURE AND FAAC | N/A | MPR/PROC/S.30/1/T | N/A | N/A | 2018 APPROPRIATION BUDGET | ERGP2104814 | CONSULTANCY SERVICES FOR CAPACITY BUILDING FOR BUDGET OFFICERS IN THE MINISTRY ON E-BUDGETING, GIFMIS ETC | CAPITAL | NAIRA | 18000000 | NAIRA | 18000000 | CAPITAL | CBD ABUJA | FCT | NATIONAL MOSQUE | AMAC | FCT | CONSULTANCY | CAPITAL | NCB | LERB | MTB | PRE-QUALIFICATION | PRE-REVIEW | 30/07/2018 | 13/8/2018 | YES | 30/07/2018 | 13/8/2018 | 13/8/2018 | 13/8/2018 | 20/8/2018 | 20/8/2018 | 27/8/2018 | 2018-03-09 | 2018-03-09 | 17/9/2018 | 17/9/2018 | 17/9/2018 | 24/9/2018 | 2018-08-10 | 2018-08-10 | 15/10/2018 | N/A | N/A | N/A | 15/10/2018 | 22/10/2018 | 22/10/2018 | 29/10/2018 | 29/10/2018 | 29/10/2018 | 29/10/2018 | 28/12/2018 | 29/10/2018 | 28/12/2018 | 60 Days | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Arc. O.I Agbe | Deputy Director (Proc)
10 | ERGP9100928 | STATUTORY CONTRIBUTION TO INTERNATIONAL ENERGY | N/A | MPR/PROC/S.30/1/T | N/A | N/A | 2018 APPROPRIATION BUDGET | ERGP9100928 | PROGRAMME | CAPITAL | NAIRA | 284000000 | NAIRA | 284000000 | CAPITAL | CBD ABUJA | FCT | NATIONAL MOSQUE | AMAC | FCT | CONSULTANCY | CAPITAL | NCB | LERB | FEC | PRE-QUALIFICATION | PRE-REVIEW | 30/07/2018 | 13/8/2018 | YES | 30/07/2018 | 13/8/2018 | 13/8/2018 | 13/8/2018 | 20/8/2018 | 20/8/2018 | 27/8/2018 | 2018-03-09 | 2018-03-09 | 17/9/2018 | 17/9/2018 | 17/9/2018 | 24/9/2018 | 2018-08-10 | 2018-08-10 | 15/10/2018 | N/A | N/A | N/A | 15/10/2018 | 22/10/2018 | 22/10/2018 | 29/10/2018 | 29/10/2018 | 29/10/2018 | 29/10/2018 | 28/12/2018 | 29/10/2018 | 28/12/2018 | 60 Days | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Arc. O.I Agbe | Deputy Director (Proc)
11 | ERGP2100913 | AUTOMATION OF MINISTRY OF PETROLEUM RESOURCES OPERATIONS E-LIBRARY ANNUAL SUBSCRIPTION | N/A | MPR/PROC/S.30/1/T | N/A | N/A | 2018 APPROPRIATION BUDGET | ERGP2100913 | CONSULTANCY SERVICES | CAPITAL | NAIRA | 115000000 | NAIRA | 115000000 | CAPITAL | CBD ABUJA | FCT | NATIONAL MOSQUE | AMAC | FCT | CONSULTANCY | CAPITAL | NCB | QCBS | MTB | PRE-QUALIFICATION | PRE-REVIEW | 30/07/2018 | 13/8/2018 | YES | 30/07/2018 | 13/8/2018 | 13/8/2018 | 13/8/2018 | 20/8/2018 | 20/8/2018 | 27/8/2018 | 2018-03-09 | 2018-03-09 | 17/9/2018 | 17/9/2018 | 17/9/2018 | 24/9/2018 | 2018-08-10 | 2018-08-10 | 15/10/2018 | N/A | N/A | N/A | 15/10/2018 | 22/10/2018 | 22/10/2018 | 29/10/2018 | 29/10/2018 | 29/10/2018 | 29/10/2018 | 28/12/2018 | 29/10/2018 | 28/12/2018 | 60 Days | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Arc. O.I Agbe | Deputy Director (Proc)
12 | 22020402 | MAINTENANCE OF OFFICE FURNITURE | N/A | MPR/PROC/S.30/1/T | MPR/PROC/S.30/1/T | N/A | 2018 APPROPRIATION BUDGET | 22020402 | PROCUREMENT OF OFFICE FURNITURE | RECURRENT | NAIRA | 25000000 | NAIRA | 25000000 | RECURRENT | CBD ABUJA | FCT | NATIONAL MOSQUE | AMAC | FCT | GOODS | RECURRENT | NCB | LERB | MTB | PRE-QUALIFICATION | PRE-REVIEW | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | YES | 2018-10-09 | 24/09/2018 | 24/09/2018 | 24/09/2018 | 2018-01-10 | 2018-08-10 | 2018-08-10 | 15/10/2018 | 15/10/2018 | 15/10/2018 | 22/10/2018 | 29/10/2018 | 2018-05-11 | N/A | N/A | 2018-05-11 | 2018-05-11 | [5 empty] | Arc. O.I Agbe | Deputy Director (Proc)
13 | 22020301 | OFFICE STATIONARIES | N/A | MPR/PROC/S.30/1/T | MPR/PROC/S.30/1/T | N/A | 2018 APPROPRIATION BUDGET | 22020301 | PROCUREMENT OF OFFICE STATIONARY | RECURRENT | NAIRA | 20000000 | NAIRA | 20000000 | RECURRENT | CBD ABUJA | FCT | NATIONAL MOSQUE | AMAC | FCT | GOODS | RECURRENT | NCB | LERB | MTB | PRE-QUALIFICATION | PRE-REVIEW | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | YES | 2018-10-09 | 24/09/2018 | 24/09/2018 | 24/09/2018 | 2018-01-10 | 2018-08-10 | 2018-08-10 | 15/10/2018 | 15/10/2018 | 15/10/2018 | 22/10/2018 | 29/10/2018 | 2018-05-11 | N/A | N/A | 2018-05-11 | 2018-05-11 | [5 empty] | Arc. O.I Agbe | Deputy Director (Proc)
14 |  | PROCUREMENT OF COMPUTER AND PERPHERALS | N/A | MPR/PROC/S.30/1/T | MPR/PROC/S.30/1/T | N/A | 2018 APPROPRIATION BUDGET |  | PROCUREMENT OF COMPUTER AND PERPHERALS | RECURRENT | NAIRA | 15000000 | NAIRA | 15000000 | RECURRENT | CBD ABUJA | FCT | NATIONAL MOSQUE | AMAC | FCT | GOODS | RECURRENT | NCB | LERB | MTB | PRE-QUALIFICATION | PRE-REVIEW | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | YES | 2018-10-09 | 24/09/2018 | 24/09/2018 | 24/09/2018 | 2018-01-10 | 2018-08-10 | 2018-08-10 | 15/10/2018 | 15/10/2018 | 15/10/2018 | 22/10/2018 | 29/10/2018 | 2018-05-11 | N/A | N/A | 2018-05-11 | 2018-05-11 | [5 empty] | Arc. O.I Agbe | Deputy Director (Proc)
15 | 22020401 | PROCUREMENT OF VEHICLES | N/A | MPR/PROC/S.30/1/T | MPR/PROC/S.30/1/T | N/A | 2018 APPROPRIATION BUDGET | 22020401 | PROCUREMENT OF VEHICLES | RECURRENT | NAIRA | 107250000 | NAIRA | 107250000 | RECURRENT | CBD ABUJA | FCT | NATIONAL MOSQUE | AMAC | FCT | GOODS | RECURRENT | NCB | LERB | MTB | PRE-QUALIFICATION | POST-REVIEW | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | YES | 2018-10-09 | 24/09/2018 | 24/09/2018 | 24/09/2018 | 2018-01-10 | 2018-08-10 | 2018-08-10 | 15/10/2018 | 15/10/2018 | 15/10/2018 | 22/10/2018 | 29/10/2018 | 2018-05-11 | N/A | N/A | 2018-05-11 | 2018-05-11 | [5 empty] | Arc. O.I Agbe | Deputy Director (Proc)

## FTH EKITI Works
Ministry/Department/Agency: Department Of Procurement | FEDERAL TEACHING HOSPITAL IDO EKITI, EKITI STATE
Budget Year: 2018
[9 empty] | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation - Works
Project Description |  | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | MDA Approval | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Cost
Normal duration of procurement Process | [7 empty] | 2 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
CONSTRUCTION OF RADIO-DIGNOSTIC BUILDING | Plan | 1 | Bills of Quantity | 160599737.68 | NCB | Parastatal Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 2014-08-13 | 2014-05-28 | 2014-07-16 | 2014-07-30 | 2014-08-13 | 34942453.31 | 2014-08-13 | 2014-08-24 | 2014-08-25 | Ongoing | 160599737.68
Actual
CONSTRUCTION OF HOUSE OFFICERS QUARTERS | Plan | 1 | Bills of Quantity | 135205960 | NCB | Parastatal Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 2017-10-17 | 2017-07-26 | 2017-08-31 | 2017-10-17 | 2017-10-17 | 100000000 | 2017-10-18 | 2017-10-22 | 2017-11-02 | Ongoing | 135205960
CONSTRUCTION OF MODERN ADULT ACCIDENT & EMERGENCY BUILDING | Plan | 1 | Bills of Quantity | 255000000 | NCB | Parastatal Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 2018-08-01 | 2018-06-04 | 2018-07-17 | 2018-07-31 | 2018-08-01 | 200000000 | 2018-08-03 | 2018-08-06 | 2018-08-15 | New Project | 255000000
Actual
RENOVATION OF MEDICAL REHABILITATION DEPARMENT BUILDING | Plan | 2 | Bills of Quantity | 85000000 | NCB | Parastatal Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 2018-08-01 | 2018-06-04 | 2018-07-17 | 2018-07-31 | 2018-08-01 | 85000000 | 2018-08-03 | 2018-08-06 | 2018-08-15 | New Project | 85000000
Actual
COMPLETE REHABILITAION AND UPGRADING OF OPERATING THEATRE BUILDING | Plan | 3 | Bills of Quantity | 150000000 | NCB | Parastatal Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 2018-08-01 | 2018-06-04 | 2018-07-17 | 2018-07-31 | 2018-08-01 | 100000000 | 2018-08-03 | 2018-08-06 | 2018-08-15 | New Project | 150000000
Actual
Total Cost Plan |  |  |  | 785805697.68 | [8 empty] | 519942453.31 |  |  |  |  | 785805697.68
Total Cost Actual

## FTH EKITI Goods
Ministry/Department/Agency: Department Of Procurement | FEDERAL TEACHING HOSPITAL, IDO-EKITI, EKITI STATE
Budget Year: 2018
[9 empty] | Specific Procurement Notice/Advert | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation - Goods
Project Description |  | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Arrival of Goods | Inspection/Final Acceptance
Normal duration of procurement Process | [7 empty] | 2 weeks | 2 - 4 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
Plan vs Actual
PROCUREMENT AND INSTALLATION OF MEDICAL EQUIPMENT | Plan | 3B | Bills of Quantity | 86466950 | NCB | Parastatal Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 2014-08-13 | NA | 2014-05-28 | 2014-07-16 | 2014-07-30 | 2014-08-13 | 38000000 | 2014-08-13 | 2014-08-24 | NA | 22/08/18 - 16/09/18 | 19/09/18 - 23/09/18
Actual
PROCUREMENT OF OFFICE EQUIPMENT FOR MULTIPURPOSE CLINICAL BUILDING | Plan | 4A | Bills of Quantity | 21746250 | NCB | Parastatal Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 2014-08-13 | NA | 2014-05-28 | 2014-07-16 | 2014-07-30 | 2014-08-13 | 21000000 | 2014-08-13 | 2014-08-24 | NA | 22/08/18 - 16/09/18 | 19/09/18 - 23/09/18
Actual
PROCUREMENT OF OFFICE EQUIPMENT FOR SPECIALIST CLINICAL BUILDING | Plan | 5A | Bills of Quantity | 26616500 | NCB | Parastatal Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 2014-08-13 | NA | 2014-05-28 | 2014-07-16 | 2014-07-30 | 2014-08-13 | 16000000 | 2014-08-13 | 2014-08-24 | NA | 22/08/18 - 16/09/18 | 19/09/18 - 23/09/18
Actual
PROCUREMENT AND INSTALLATION OF STATIONARY WASTE COMPACTOR | Plan | 2 | Bills of Quantity | 19350000 | NCB | Parastatal Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 2017-10-17 | N/A | 2017-07-26 | 2017-07-31 | 2017-10-17 | 2017-10-17 | 17000000 | 18/10/20017 | 22/10/20017 | N/A | 15/10/18 - 20/11/18 | 21/11/18 - 15/12/18
Actual
PROCUREMENT OF FURNITURE AND BEDDINGS FOR NEW 4-SUITE MODULAR THEATRE AND 4 SUB-SPECIALITY WARDS | Plan | 4 | Bills of Quantity | 27300000 | NCB | Parastatal Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 2018-08-01 | N/A | 2018-06-04 | 2018-07-17 | 2018-08-01 | 2018-08-01 | 18000000 | 2018-08-03 | 2018-08-06 | 2018-08-23 | 15/10/18 - 20/11/18 | 21/11/18 - 15/12/18
Actual
PROCUREMENT OF AIR CONDITIONERS, COMPUTERS ETC FOR NEW 4-SUITE MODULAR THEATRE AND 4 SUB-SPECIALITY WARDS | Plan | 5 | Bills of Quantity | 18000000 | NCB | Parastatal Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 2018-08-01 | N/A | 2018-06-04 | 2018-07-17 | 2018-08-01 | 2018-08-01 | 12700000 | 2018-08-03 | 2018-08-06 | 2018-08-23 | 15/10/18 - 20/11/18 | 21/11/18 - 15/12/18
Actual
PROCUREMENT AND INSTALLATION OF 6 SET OF DIALYSIS MACHINE | Plan | 6 | Bills of Quantity | 49000000 | NCB | Parastatal Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 2018-08-01 | N/A | 2018-06-04 | 2018-07-17 | 2018-08-01 | 2018-08-01 | 49000000 | 2018-08-03 | 2018-08-06 | 2018-08-23 | 15/10/18 - 20/11/18 | 21/11/18 - 15/12/18
Actual
PROCUREMENTMENSTRUAL CUP FOR WOMEN | Plan | 7 | Bills of Quantity | 15000000 | NCB | Parastatal Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 2018-08-01 | N/A | 2018-06-04 | 2018-07-17 | 2018-08-01 | 2018-08-01 | 15000000 | 2018-08-03 | 2018-08-06 | 2018-08-23 | 15/10/18 - 20/11/18 | 21/11/18 - 15/12/18
Actual
PROCUREMENT AND INSTALLATION OF 250KVA PERKINS GENERATORS | Plan | 8 | Bills of Quantity | 48000000 | NCB | Parastatal Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 2018-08-01 | N/A | 2018-06-04 | 2018-07-17 | 2018-08-01 | 2018-08-01 | 48000000 | 2018-08-03 | 2018-08-06 | 2018-08-23 | 15/10/18 - 20/11/18 | 21/11/18 - 15/12/18
Actual
PROCUREMENT AND INSTALLATION OF THEATRE AND LABORATORY EQUIPMENT | Plan | 9 | Bills of Quantity | 49000000 | NCB | Parastatal Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 2018-08-01 | N/A | 2018-06-04 | 2018-07-17 | 2018-08-01 | 2018-08-01 | 49000000 | 2018-08-03 | 2018-08-06 | 2018-08-23 | 15/10/18 - 20/11/18 | 21/11/18 - 15/12/18
Total Cost Plan |  |  |  | 360479700 | [9 empty] | 283700000
Total Cost Actual

## FTH EKITI Consultancy Services
Ministry/Department/Agency: Department Of Procurement | FEDERAL TEACHING HOSPITAL, IDO-EKITI, EKITI STATE
Budget Year: 2018
|  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 1 weeks | 2 - 4 weeks | 2 weeks | 2 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
TRAINING OF THEATRE AND LABORATORY STAFF | Plan | 1 | 10 | Lump Sum | 48500000 | NCB | Parastatal Tenders Board | QCBS - Quality and Cost Based Selection | NA | PST | 8/05/18 - 22/05/18 | 25/05/18 - 29/05/18 | 2/06/18 - 13/06/18 | 16/06/18 - 20/06/18 | 2018-06-20 | 23/06/18 - 27/06/18 | 27/06/18 - 10/07/18 | 10/07/18 - 10/07/18 | 13/07/18 - 20/07/18 | 21/07/18 - 24/07/18 | 27/07/18 - 27/07/18 | 1/08/18 - 8/08/18 | NA | 11/08/18 - 15/08/18 | 48500000 | NA | 15/08/18 - 22/08/18 | 25/08/18 - 29/08/18 | 29/08/18 - 12/09/18 | 2018-10-23 | 2018-11-07 | 48500000 | OLATIMILEHIN S.A [Designation: SPO] | DR. KUNLE AJAYI - [Designation: CMD/CEO]
Actual
MEDICAL OUTREACH (TO IGOGO EKITI & ISE EKITI) IN FEDERAL TEACHING HOSPITAL, IDO EKITI | Plan | 1 | 10 | Lump Sum | 25000000 | NCB | Parastatal Tenders Board | QCBS - Quality and Cost Based Selection | NA | PST | 8/05/18 - 22/05/18 | 25/05/18 - 29/05/18 | 2/06/18 - 13/06/18 | 16/06/18 - 20/06/18 | 2018-06-20 | 23/06/18 - 27/06/18 | 27/06/18 - 10/07/18 | 10/07/18 - 10/07/18 | 13/07/18 - 20/07/18 | 21/07/18 - 24/07/18 | 27/07/18 - 27/07/18 | 1/08/18 - 8/08/18 | NA | 11/08/18 - 15/08/18 | 25000000 | NA | 15/08/18 - 22/08/18 | 25/08/18 - 29/08/18 | 29/08/18 - 12/09/18 | 2018-10-23 | 2018-11-07 | 25000000 | OLATIMILEHIN S.A [Designation: SPO] | DR. KUNLE AJAYI - [Designation: CMD/CEO]
Actual
Total Cost Plan |  |  |  |  | 73500000 | [19 empty] | 73500000 | [6 empty] | 73500000
Total Cost Actual

## AIB GOODS
ACCIDENT INVESTIGATION BUREAU 2018 PROCUREMENT PLAN (GOODS)
| Ministry/Department/Agency: AIB | [6 empty] | THE TIME LINE IS TO BE COMPARED WITH THE COUNCILS APPROVAL
| Budgetary Year: 2017 |  |  | PROCUREMENT PLAN 2016 |  | FGN CAPITAL | PROJECTS |  | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
| Desk Officer/Contact #: ABDULLAHI, M. U. 08099665535 |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
| Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Plan vs. Actual | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
| Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 2 - 4 wks | Plan |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
1 | Installation of Electronic Surveillance (CCTV) System | NA | NA | 120000000 | KIV | No | FEC | Plan | 2018-04-09 | 2018-04-23 | 2018-05-02 | 2018-05-14 | 2018-06-11 | 2018-07-16 | 2018-07-30 | Plan | [8 empty] | Abdullahi, M. U. (GM, Procurement)
[6 empty] | No |  | Actual | [7 empty] | Actual
2 | Purchase of operational Vehicles Additional Vehicle Requirement in 2018, 5 Peugeot 508 Operational Vehicles , 4 Hiluxes& 3Toyota Hiace Buses (3) NO Objection for RESTRICTIVE Tendering Toyota Prado. (1) Lexus 570 | NA | NA | 1007657845.56 | Restrictive Tendering | No | FEC | Plan | 2018-05-07 | 2018-05-21 | 2018-06-04 | 2018-06-25 | 2018-07-23 | 2018-09-03 | 2018-09-24 | Plan | [8 empty] | Abdullahi, M. U. (GM, Procurement)
[6 empty] | No |  | Actual | [7 empty] | Actual
3 | Accident Investigative activities | NA | NA | 520000000 | In House | No | FEC | Plan | 2018-04-23 | 2018-05-07 | 2018-05-21 | 2018-06-04 | 2018-07-02 | 2018-08-06 | 2018-08-20 | Plan | [8 empty] | Abdullahi, M. U. (GM, Procurement)
[6 empty] | No |  | Actual | [7 empty] | Actual
4 | Power Generating plant (Enugu Regional office) purchase and Installation | NA | NA | 21000000 | Restrictive Tendering | No | PTB | Plan | 2018-04-09 | 2018-04-23 | 2018-05-02 | 2018-05-14 | 2018-06-11 | 2018-05-16 | 2018-07-30 | Plan | [8 empty] | Abdullahi, M. U. (GM, Procurement)
[6 empty] | No |  | Actual | [7 empty] | Actual
5 | ICT Equipment Hardware and Software | NA | NA | 345880000 | Recurrent | No | MTB | Plan | 2018-04-23 | 2018-05-07 | 2018-05-21 | 2018-06-04 | 2018-07-02 | 2018-08-06 | 2018-08-20 | Plan | [8 empty] | Abdullahi, M. U. (GM, Procurement)
[6 empty] | No |  | Actual | [7 empty] | Actual
6 | Purchase of Equipment and Training for Materials Analysis Laboratory. | NA | NA | 750000000 | Restrictive Tendering | No | FEC | Plan | 2018-04-09 | 2018-04-23 | 2018-05-02 | 2018-05-14 | 2018-06-11 | 2018-05-16 | 2018-07-30 | Plan | [8 empty] | Abdullahi, M. U. (GM, Procurement)
[6 empty] | No |  | Actual | [7 empty] | Actual
7 | Equipping of Wreckage Hangar | NA | NA | 250000000 | KIV | No | MTB | Plan | On going | [6 empty] | Plan | [8 empty] | Abdullahi, M. U. (GM, Procurement)
[6 empty] | No |  | Actual | [7 empty] | Actual
8 | Equipping of AIB Library. i. Establishment of Library management System ii. Procurement of Soft & hard copies of Library books | NA | NA | 150000000 | Restrictive Tendering | No | MTB | Plan | 2018-04-09 | 2018-04-23 | 2018-05-02 | 2018-05-14 | 2018-06-11 | 2018-05-16 | 2018-07-30 | Plan | [8 empty] | Abdullahi, M. U. (GM, Procurement)
[6 empty] | No |  | Actual | [7 empty] | Actual
9 | Provision of Emergency mobile Sate light for crash site operations mounted on all terrain 4 wheel drive SUV i. Procurement of SUV for emergency crash site. ii. Procurement of VSAT Ground Control satellite for crash site Operations. iii. Procurement of Air-Band Two-way Ground Tower Radio Comm. iv. Procurement of Technical Safety Equipment and accessories. v. Training and support on crash site operations. | NA | NA | 370960000 | Restrictive Tendering | No | MTB | Plan | 2018-05-07 | 2018-05-21 | 2018-06-04 | 2018-06-25 | 2018-07-23 | 2018-09-03 | 2018-09-24 | Plan | [8 empty] | Abdullahi, M. U. (GM, Procurement)
[6 empty] | No |  | Actual | [7 empty] | Actual
10 | Purchase of HI-Tech Unmanned Area Vehicle with Camera, Training and Support. | NA | NA | 47564000 | Restrictive Tendering | No | PTB | Plan | 2018-05-07 | 2018-05-21 | 2018-06-04 | 2018-06-25 | 2018-07-23 | 2018-09-03 | 2018-09-24 | Plan | [8 empty] | Abdullahi, M. U. (GM, Procurement)
[6 empty] | No |  | Actual | [7 empty] | Actual
11 | Safety Investigators Response Kit | NA | NA | 36000000 | Restrictive Tendering | No | PTB | Plan | 2018-04-23 | 2018-05-07 | 2018-05-21 | 2018-06-04 | 2018-07-02 | 2018-08-06 | 2018-08-20 | Plan | [8 empty] | Abdullahi, M. U. (GM, Procurement)
[6 empty] | No | [9 empty] | Actual
12 | Purchase of Memory Access Retrieval System, Training and Support on the Safety Laboratory. | NA | NA | 581440000 | Restrictive Tendering | No | FEC | Plan | 2018-04-09 | 2018-04-23 | 2018-05-02 | 2018-05-14 | 2018-06-11 | 2018-05-16 | 2018-07-30 | Plan | [8 empty] | Abdullahi, M. U. (GM, Procurement)
[6 empty] | No |  | Actual | [7 empty] | Actual

## AIB WORKS
ACCIDENT INVESTIGATION BUREAU 2018 PROCUREMENT PLAN (WORKS)
| Ministry/Department/Agency: AIB | [6 empty] | THE TIME LINE IS TO BE COMPARED WITH THE COUNCILS APPROVAL
| Budgetary Year: 2017 |  |  | PROCUREMENT PLAN 2016 |  | FGN CAPITAL | PROJECTS |  | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
| Desk Officer/Contact #: ABDULLAHI, M. U. 08099665535 |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
| Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Plan vs. Actual | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
| Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 2 - 4 wks | Plan |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
1 | Erosion Control/Landscaping of AIB Wreckage Hangar In Abuja. | NA | NA | 60000000 | Restrictive Tendering | No | MTB | Plan | 2018-04-23 | 2018-05-07 | 2018-05-21 | 2018-06-04 | 2018-07-02 | 2018-08-06 | 2018-08-20 | Plan | [8 empty] | Engr. Wali H
[6 empty] | No |  | Actual | [7 empty] | Actual
2 | Expansion and Equipping of new Abuja corporate office. | NA | NA | 58685000 | Restrictive Tendering | No | MTB | Plan | 2018-05-07 | 2018-05-21 | 2018-06-04 | 2018-06-25 | 2018-07-23 | 2018-09-03 | 2018-09-24 | Plan | [8 empty] | Engr. Wali H
[6 empty] | No |  | Actual | [7 empty] | Actual
3 | Construction and Equipping of Accident Investigation Training School | NA | NA | 700000000 | Restrictive Tendering | No | FEC | Plan | 2018-05-07 | 2018-05-21 | 2018-06-04 | 2018-06-25 | 2018-07-23 | 2018-09-03 | 2018-09-24 | Plan | [8 empty] | Engr. Wali H
[6 empty] | No |  | Actual | [7 empty] | Actual
4 | Demolition and clearing of Dilapidated Office Buildings at AIB's Lagos Office | NA | NA | 45000000 | KIV | No | PTB | Plan | [7 empty] | Plan | [8 empty] | Engr. Wali H
[6 empty] | No |  | Actual | [7 empty] | Actual
5 | Construction of Dilapidated Office Buildings and construction of AIB’s Lagos Office | NA | NA | 495670000 | KIV | No | MTB | Plan | [7 empty] | Plan | [8 empty] | Engr. Wali H
[6 empty] | No |  | Actual | [7 empty] | Actual
6 | Establishment of AIB Command and Communication Centre/Training and Support i. Procurement and Installation of Software for Command and Communication. ii. Procurement of Radio. iii. Equipping of the Command Centre. | NA | NA | 150000000 | Restrictive Tendering | No | MTB | Plan | 2018-04-09 | 2018-04-23 | 2018-05-02 | 2018-05-14 | 2018-06-11 | 2018-05-16 | 2018-07-30 | Plan | [8 empty] | Abdullahi, M. U. (GM, Procurement)
[6 empty] | No |  | Actual | [7 empty] | Actual
7 | Extension of AIB office in Abuja to incorporate Flight and Material Science Laboratory | NA | NA | 459879000 | Restrictive Tendering | No | MTB | Plan | 2018-04-23 | 2018-05-07 | 2018-05-21 | 2018-06-04 | 2018-07-02 | 2018-08-06 | 2018-08-20 | Plan | [8 empty] | Abdullahi, M. U. (GM, Procurement)
[6 empty] | No |  | Actual | [7 empty] | Actual

## AIB SERVICES
ACCIDENT INVESTIGATION BUREAU 2018 PROCUREMENT PLAN (SERVICES)
| Ministry/Department/Agency: AIB | [6 empty] | THE TIME LINE IS TO BE COMPARED WITH THE COUNCILS APPROVAL
| Budgetary Year: 2017 |  |  | PROCUREMENT PLAN 2016 |  | FGN CAPITAL | PROJECTS |  | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
| Desk Officer/Contact #: ABDULLAHI, M. U. 08099665535 |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
| Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Plan vs. Actual | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
| Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 2 - 4 wks | Plan |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
1 | Research Work/Study on Aviation Safety | NA | NA | 62000000 | Restrictive Tendering | No | MTB | Plan | 2018-04-23 | 2018-05-07 | 2018-05-21 | 2018-06-04 | 2018-07-02 | 2018-08-06 | 2018-08-20 | Plan | [8 empty] | Engr. Wali H
2 | Consultancy for Extension of AIB office in Abuja to incorporate Flight and Material Science Laboratory | NA | NA | 24000000 | Restrictive Tendering | No | PTB | Plan | 2018-04-09 | 2018-04-23 | 2018-05-02 | 2018-05-14 | 2018-06-11 | 2018-05-16 | 2018-07-30 | Plan | [8 empty] | Abdullahi, M. U. (GM, Procurement)
[6 empty] | No |  | Actual | [7 empty] | Actual

## NCE
NIGERIA COMMODITY EXCHANGE
2018 PROCUREMENT PLANNING PROJECT SUBMISSION TEMPLATE
S/NO. | PROJECT/SERVICES TITLE | PROJECT/SERVICES DESCRIPTION | SCOPE OF WORK | SPECIFIC REQUIREMENTS (GOODS AND SERVICES) | PROVISION UNDER 2018 APPROPRIATION |  | APPROVING AUTHORITY (PS/MTB/FEC) | REMARKS
1 | Development of Trading Application Software (Phase 2) | A moblie application with support for Andriod and Apple IOS platforms. This application will support both phones and tablets for Trading members of the NCX | The Mobile application will provide trading members of the Exchange: | SERVICES | 21000000 | 21000000 | Parastatal Tenders Board
1. Create a field where Brokers and other users can login, view order book and submit bids and offers.
2. Make it possible for Brokers to view their holdings and all accounts mapped to their firm and trade any on those accounts.
3.Make it possible for brokers to cancel or modify their Orders and also make it possible for all confirmed or executed orders to be displayed on the mobile application.
4. Create a field where applications for the opening or modification of accounts can be submitted via the mobile platform.
5. Make it possible for beneficiaries to view their warehouse receipts and also interact with the warehouses.
6. Beneficiaries/Accounts owners can also login and view their holdings.
7. Integration of this platform with the trading platform via FIX and the warehouse management system using web services.
2 | Development of Trading Application Software for Policy Auction (Phase 1) | Policy Auction | A Web and Stand-alone Software Application that will : 1. Enable Governmet Agencies to make bulk purchase from NCX Trading Members and Merchants on a Reverse Auction platform. 2. Make it possible for buyers on auction platform to individual give the price at which they want to buy a commodity on offer which is queued in a descending order so that the price that clears the market will be the prevailing market price. | SERVICES | 17800000 | 17800000 | Parastatal Tenders Board
3 |  | Upgrading and Enhancement of the Trading Application System of NCX | Interfacing the Phase 1 Trading Application System to integrate the web version and the moble version and any other identified issues. | SERVICES | 15440000 | 15440000 | Parastatal Tenders Board
4 |  | Software licence for Oracle 12g Database | Software licence for Oracle 12g Database and training of IT Staff on Oracle 12g Database | SERVICES | 14086092 | 14086092 | Parastatal Tenders Board
5 |  | Purchase of Microsoft Windows Server 2010 and Microsoft Licence for one year | Purchase of Microsoft Windows Server 2010 and Microsoft Office Licence for one year for 50 computer systems | SERVICES | 12000000 | 12000000 | Parastatal Tenders Board
6 |  | Procurement of Optic Fibre broadband solution/Annual Bandwidth subscription (2M/2M) | Procurement of Optic Fibre broadband solution/Annual Bandwidth subscription (2M/2M) | SERVICES | 12000000 | 12000000 | Parastatal Tenders Board
7 |  | Local Area Network Access including Network firewall, switches, LAN Cabling (Lump Sum) | Local Area Network Access including Network firewall, switches, LAN Cabling (Lump Sum) |  | 14800000 | 14800000 | Parastatal Tenders Board
8 |  | Application Access - Computers, Laptops, Scanners, Photocopiers, Printers, IT Consumers and Routers (Lump Sum) | Application Access - Computers, Laptops, Scanners, Photocopiers, Printers, IT Consumers and Routers (Lump Sum) |  | 22406888 | 22406888 | Parastatal Tenders Board
9 |  | Others- LED Screen, Projector, UPS, Stabilizers, VOIP, Alternative Power Solutions (Lump Sum) | Others- LED Screen, Projector, UPS, Stabilizers, VOIP, Alternative Power Solutions (Lump Sum) |  | 20356600 | 20356600 | Parastatal Tenders Board
10 |  | Purchase of Vsat Equipment for RAS | Purchase of Vsat Equipment for the 6 RAS Locations |  | 9000000 | 9000000 | Parastatal Tenders Board
11 | UPS | Purchase of UPS for the Six RAS Locations | Purchase of UPS for the Six RAS Locations |  | 11400000 | 11400000 | Parastatal Tenders Board
12 | HP 330 Computers | HP 330 computer | purchase of HP 330 Computer Systems |  | 1080000
13 |  | Stabilizer 3,000w | Stabilizer 3,000w |  | 720000
14 |  | Generator 20kva | Generator 20kva |  | 13200000
[6 empty] | 15000000 | Parastatal Tenders Board
16 | Annual bandwidth subscription 1m/1m | Purchase of Annual bandwidth for the six RAS |  |  | 8280000 | 8280000 | Parastatal Tenders Board
17 | Development of Market Information System (MIS). Phase 2 | Purchase and installation of Computer Assisted Personal Interview Devices (CAPI) Software | Purchase of CAPI Software |  | 16000000
18 |  |  | AMIS-CAPI Devices and smart phones 126GB |  | 5000000
19 |  |  | AMIS-CAPI Devices Storage: 16GB External Storage: 32GB |  | 10000000
[6 empty] | 31000000 | Parastatal Tenders Board
20 | Well equiped standard warehouses for effective storage of agro-commodities. | In the frist phase, 20 public and 3 private warehouses in the 6 geo-political zone will be leased , equiped and 10 of the leased public warehouses will be renovated to meet the approved standards for delivery warehouses. | [5 empty] | 224569580
21 |  |  | Consultancy for Warehouse Inspection, Monitoring and Evaluation of 5 warehouses |  | 21600000 | 21600000 | Parastatal Tenders Board
|  |  | Renovation of FMARD Warehouse on Ifaki-Onri Road, Ekiti State |  | 19000600 | 19000600 | Parastatal Tenders Board
|  |  | Renovation of FMARD Warehouse at Orlu Okuku Cross River State |  | 30000000 | 30000000 | Parastatal Tenders Board
|  |  | Renovation of FMARD Warehouse Adifun Echara Ikwo Ebonyi State |  | 17100000 | 17100000 | Parastatal Tenders Board
|  |  | Renovation of FMARD Warehouse at Ore Agundi LGA Enugu State |  | 18000500 | 18000500 | Parastatal Tenders Board
|  |  | Renovation of FMARD Warehouse in Ganye Adamawa State |  | 41000000 | 41000000 | Parastatal Tenders Board
22 |  |  | Digital weighing scales |  | 14500000 | 14500000 | Parastatal Tenders Board
23 |  |  | Pallets |  | 12859200 | 12859200 | Parastatal Tenders Board
24 |  |  | Fumigating sheets |  | 6500000 | 6500000 | Parastatal Tenders Board
180560300
|  |  | 2 Qty Elisa Test Mini Reader with stripes for total Aflatoxins (with barcode, Printer) |  | 6190000
26 | Improved clssification of agro- commodities into various grades for market participants. | Assaying equipments for use in the warehouses across the country will aid to ascertain the quality and grades of the agricultural commodities to be stored in the warehouses. | 5 Qty Moisture Meter and Moisture Probe (Each) |  | 5100000
27 |  |  | 2 Qty Elisa Reader (Table Top)Equipment |  | 5000000
28 |  |  | 2 Qty Accessories for Elisa Reader (PC, Printer, Micro pipettes and Multi Channel pipettes) |  | 1000000
|  |  | Consumable for 96 wells (Total Aflatoxins and Ochratoxins) |  | 600000
28 |  |  | 5 Qty Hectoliter Weight Equipment |  | 10800000
29 |  |  | 5 Qty Balance (0.01g sensitive) |  | 720000
30 |  |  | 5 Qty Blender/Grinder |  | 600000
31 |  |  | 5 Qty Generator set (3.5KVA) |  | 600000
32 |  |  | 5 Qty Uninterrupted Power Supply (UPS) |  | 900000
33 |  |  | 5 Qty horizontal glass Shakers(min 6 glasses) |  | 1200000
34
35 | Classification of commodities into grades | Enhancing the commodity assaying capacity of the Exchange to meet the quality required of market participants. | 6 Qty Work benches for Warehouses and Head office |  | 8110000
37 |  |  | 8 Air conditioners |  | 2000000
38 |  |  | 6 Qty Refrigerators |  | 1200000
39 |  |  | servicing/calibration of equipment |  | 1240000
40 |  |  | consumables(reagents, glasswares) |  | 1550000
41 | [5 empty] | 46810000 | Parastatal Tenders Board | 46810000
42 | Easy cordination of warehousing and other operational activities. | The Exchange shall purchase six(6) project vehicles to aid mobility and cordination of accredited warehouses and other operational activities. | Project vehicles (Hilux) |  | 45603458 | 45603458 | Parastatal Tenders Board | 45603458
[5 empty] | 497543338 | 497543338 |  | 497543338

## OHCSF Goods
Ministry/Department/Agency: OHCSF, ABUJA. | Package Number
Budgetary Year: 2018 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: Hussaini |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
PROVISION AND SERVICING OF FIRE FIGHTING EQUIPMENT | 23010123/ ERGP27113711 |  | 8110000 | NCB | POST | POST | Plan | 2nd - 16th July, 2018 | NA | NA | 16th July, 2018 | 27th August, 2018 | 27th August - 10th September, 2018 | NA | Plan | 8110000 | NA | 11th - 25th September, 2018 | 16th October, 2018 | NA | 23rd October, 2018 | 23rd October, 2018
[7 empty] | Actual | [7 empty] | Actual
PURCHASE OF BUSES | 23010108/ ERGP16113710 |  | 24330000 | NCB | POST | POST | Plan | 2nd - 16th July, 2018 | NA | NA | 16th July, 2018 | 27th August, 2018 | 27th August - 10th September, 2018 | NA | Plan | 24330000 | NA | 11th - 25th September, 2018 | 16th October, 2018 | NA | 23rd October, 2018 | 23rd October, 2018
[7 empty] | Actual | [7 empty] | Actual
OFFICE STATIONERIES/COMPUTER CONSUMABLES | 22020301 |  | 31,978,000.00 | NCB | POST | POST | Plan | 2nd - 16th July, 2018 | NA | NA | 16th July, 2018 | 27th August, 2018 | 27th August - 10th September, 2018 | NA | Plan | 31,978,000.00 | NA | 11th - 25th September, 2018 | 16th October, 2018 | NA | 23rd October, 2018 | 23rd October, 2018
[7 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF MEDIA EQUIPMENT/ADVOCACY | ERGP16113716 |  | 5,000,000.00 | NCB | POST | POST | Plan | 2nd - 16th July, 2018 | NA | NA | 16th July, 2018 | 27th August, 2018 | 27th August - 10th September, 2018 | NA | Plan | 5,000,000.00 | NA | 11th - 25th September, 2018 | 16th October, 2018 | NA | 23rd October, 2018 | 23rd October, 2018
[7 empty] | Actual | [7 empty] | Actual
PURCHASE OF OFFICIAL AND MONITORING VEHICLES FOR THE OHCSF | 23010105/ ERGP7113688 |  | 74,880,000 | NCB | POST | POST | Plan | 2nd - 16th July, 2018 | NA | NA | 16th July, 2018 | 27th August, 2018 | 27th August - 10th September, 2018 | NA | Plan | 74,880,000 | NA | 11th - 25th September, 2018 | 16th October, 2018 | NA | 23rd October, 2018 | 23rd October, 2018
[7 empty] | Actual | [7 empty] | Actual
PURCHASE OF LIBRARY BOOKS AND EQUIPMENT | 23010125 |  | 12,165,000.00 | NCB | POST | POST | Plan | 2nd - 16th July, 2018 | NA | NA | 16th July, 2018 | 27th August, 2018 | 27th August - 10th September, 2018 | NA | Plan | 12,165,000.00 | NA | 11th - 25th September, 2018 | 16th October, 2018 | NA | 23rd October, 2018 | 23rd October, 2018
[7 empty] | Actual | [7 empty] | Actual
GAZETTE PRODUCTION | ERGP16113693 |  | 8,110,000.00 | NCB | POST | POST | Plan | 2nd - 16th July, 2018 | NA | NA | 16th July, 2018 | 27th August, 2018 | 27th August - 10th September, 2018 | NA | Plan | 8,110,000.00 | NA | 11th - 25th September, 2018 | 16th October, 2018 | NA | 23rd October, 2018 | 23rd October, 2018
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Fill gray cells only!

## OHCSF Works
Ministry/Department/Agency: OHCSF, Abuja
Budgetary Year: 2018 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: Hussaini |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
REHABILITATION/RENOVATION OF FEDERAL SECRETARIAT COMPLEX PHASE II INCLUDING UPGRADING OF ELECTRICAL INSTALLATION | 23030121/ ERGP27113713 |  | LUMPSUM | NCB | 239016098 | POST | POST | Plan | 2nd - 16th July, 2018 | NA | NA | 16th July, 2018 | 27th August, 2018 | 27th August - 10th September, 2018 | NA | Plan | 239016098 | NA | 24th September, 2018 | 15th October, 2018 | NA | 29th October, 2018 | 30th October, 2018
[8 empty] | Actual | [7 empty] | Actual
MAINTENANCE OF OFFICE BUILDING / RESIDENTIAL QTRS | 22020403 |  | LUMPSUM | NCB | 50240000 | POST | POST | Plan | 2nd - 16th July, 2018 | NA | NA | 16th July, 2018 | 27th August, 2018 | 27th August - 10th September, 2018 | NA | Plan | 50240000 | NA | 24th September, 2018 | 15th October, 2018 | NA | 29th October, 2018 | 30th October, 2018
[8 empty] | Actual | [7 empty] | Actual
MAINTENANCE OF PLANTS/ GENERATORS | 22020405 |  |  | NCB | 15,000,000 | POST | POST | Plan | 2nd - 16th July, 2018 | NA | NA | 16th July, 2018 | 27th August, 2018 | 27th August - 10th September, 2018 | NA | Plan | 15,000,000 | NA | 24th September, 2018 | 15th October, 2018 | NA | 29th October, 2018 | 30th October, 2018
[8 empty] | Actual | [7 empty] | Actual
ESTABLISHMENT OF RESEARCH CENTRE FOR POLICY FORMULATION | ERGP30113708 |  |  | NCB | 18,110,000.00 | POST | POST | Plan | 2nd - 16th July, 2018 | NA | NA | 16th July, 2018 | 27th August, 2018 | 27th August - 10th September, 2018 | NA | Plan | 18,110,000.00 | NA | 24th September, 2018 | 15th October, 2018 | NA | 29th October, 2018 | 30th October, 2018
[8 empty] | Actual | [7 empty] | Actual
[6 empty] | POST | POST | Plan | [7 empty] | Plan |  | NA |  |  | NA
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | #REF! |  |  | Plan | [7 empty] | Plan | #REF! | [6 empty] | #REF!
[5 empty] | #REF! |  |  | Actual | [7 empty] | Actual | #REF! | [6 empty] | #REF!
Fill gray cells only!

## OHCSF Consultants
Ministry/Department/Agency: OHCSF, Abuja.
Budgetary Year: 2018 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: Hussaini |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Prior/Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
CLEANING AND FUMIGATION SERVICES | NCB |  | 9600000 | POST | Plan | 2nd - 30th July, 2018 | NA | 13th August, 2018 | - | 27th August, 2018 |  | Plan | 17th September, 2018 | 12th November, 2018 | 3rd December, 2018 | NA | 17th December, 2018 | 31st December, 2018 | 14th January, 2019 | Plan | 28th January, 2019 | NA | 9600000 | 25th February, 2018 | 25th February, 2018 | 18th March, 2018 | Plan | 1st April, 2018 | 15tth April, 2018 | 22nd April, 2018 | 29th April, 2018
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
INVENTORY AND VALUATION OF ASSETS NATIONWIDE | NCB |  | 16220000 | POST | Plan | 2nd - 30th July, 2018 | NA | 13th August, 2018 | - | 27th August, 2018 |  | Plan | 17th September, 2018 | 12th November, 2018 | 3rd December, 2018 | NA | 17th December, 2018 | 31st December, 2018 | 14th January, 2019 | Plan | 28th January, 2019 | NA | 16220000 | 25th February, 2018 | 25th February, 2018 | 18th March, 2018 | Plan | 1st April, 2018 | 15tth April, 2018 | 22nd April, 2018 | 29th April, 2018
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
CAPACITY BUILDING AND SKILL DEVELOPMENT | NCB |  | 28,385,000.00 | POST | Plan | 2nd - 30th July, 2018 | NA | 13th August, 2018 | - | 27th August, 2018 |  | Plan | 17th September, 2018 | 12th November, 2018 | 3rd December, 2018 | NA | 17th December, 2018 | 31st December, 2018 | 14th January, 2019 | Plan | 28th January, 2019 | NA | 28,385,000.00 | 25th February, 2018 | 25th February, 2018 | 18th March, 2018 | Plan | 1st April, 2018 | 15tth April, 2018 | 22nd April, 2018 | 29th April, 2018
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
ESTABLISHMENT OF ENTERPRISE CULTURE AND COMMERCIAL ORIENTATION FOR REVENUE GENERATION AND WEALTH CREATION | NCB |  | 20275000 | POST | Plan | 2nd - 30th July, 2018 | NA | 13th August, 2018 | - | 27th August, 2018 |  | Plan | 17th September, 2018 | 12th November, 2018 | 3rd December, 2018 | NA | 17th December, 2018 | 31st December, 2018 | 14th January, 2019 | Plan | 28th January, 2019 | NA | 20275000 | 25th February, 2018 | 25th February, 2018 | 18th March, 2018 | Plan | 1st April, 2018 | 15tth April, 2018 | 22nd April, 2018 | 29th April, 2018
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual
SUCCESSION PLANNING AND MENTORING | NCB |  | 12165000 | POST | Plan | 2nd - 30th July, 2018 | NA | 13th August, 2018 | - | 27th August, 2018 |  | Plan | 17th September, 2018 | 12th November, 2018 | 3rd December, 2018 | NA | 17th December, 2018 | 31st December, 2018 | 14th January, 2019 | Plan | 28th January, 2019 | NA | 12165000 | 25th February, 2018 | 25th February, 2018 | 18th March, 2018 | Plan | 1st April, 2018 | 15tth April, 2018 | 22nd April, 2018 | 29th April, 2018
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual
CONSULTANCY SERVICES TO MDAs (ODD, CST, LMSP AND L&D) | NCB |  | 20000000 | POST | Plan | 2nd - 30th July, 2018 | NA | 13th August, 2018 | - | 27th August, 2018 |  | Plan | 17th September, 2018 | 12th November, 2018 | 3rd December, 2018 | NA | 17th December, 2018 | 31st December, 2018 | 14th January, 2019 | Plan | 28th January, 2019 | NA | 20000000 | 25th February, 2018 | 25th February, 2018 | 18th March, 2018 | Plan | 1st April, 2018 | 15tth April, 2018 | 22nd April, 2018 | 29th April, 2018
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual
PROJECT TECHNICAL REPORTING AND SUPERVISION IN ALL THE SIX(6) FTCS | NCB |  | 16220000 | POST | Plan | 2nd - 30th July, 2018 | NA | 13th August, 2018 | - | 27th August, 2018 |  | Plan | 17th September, 2018 | 12th November, 2018 | 3rd December, 2018 | NA | 17th December, 2018 | 31st December, 2018 | 14th January, 2019 | Plan | 28th January, 2019 | NA | 16220000 | 25th February, 2018 | 25th February, 2018 | 18th March, 2018 | Plan | 1st April, 2018 | 15tth April, 2018 | 22nd April, 2018 | 29th April, 2018
[5 empty] | Actual |  |  |  |  | ` |  | Actual | [7 empty] | Actual | [6 empty] | Actual
NATIONWIDE STAFF IDENTIFICATION | NCB |  | 16220000 | POST | Plan | 2nd - 30th July, 2018 | NA | 13th August, 2018 | - | 27th August, 2018 |  | Plan | 17th September, 2018 | 12th November, 2018 | 3rd December, 2018 | NA | 17th December, 2018 | 31st December, 2018 | 14th January, 2019 | Plan | 28th January, 2019 | NA | 16220000 | 25th February, 2018 | 25th February, 2018 | 18th March, 2018 | Plan | 1st April, 2018 | 15tth April, 2018 | 22nd April, 2018 | 29th April, 2018
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
HUMAN RESOURCES ICT INFRASTRUCTURE | NCB |  | 40550000 | POST | Plan | 2nd - 30th July, 2018 | NA | 13th August, 2018 | - | 27th August, 2018 |  | Plan | 17th September, 2018 | 12th November, 2018 | 3rd December, 2018 | NA | 17th December, 2018 | 31st December, 2018 | 14th January, 2019 | Plan | 28th January, 2019 | NA | 40550000 | 25th February, 2018 | 25th February, 2018 | 18th March, 2018 | Plan | 1st April, 2018 | 15tth April, 2018 | 22nd April, 2018 | 29th April, 2018
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
RESEARCH AND DEVELOPMENT | NCB |  | 1022276250 | POST | Plan | 2nd - 30th July, 2018 | NA | 13th August, 2018 | - | 27th August, 2018 |  | Plan | 17th September, 2018 | 12th November, 2018 | 3rd December, 2018 | NA | 17th December, 2018 | 31st December, 2018 | 14th January, 2019 | Plan | 28th January, 2019 | NA | 1022276250 | 25th February, 2018 | 25th February, 2018 | 18th March, 2018 | Plan | 1st April, 2018 | 15tth April, 2018 | 22nd April, 2018 | 29th April, 2018
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
MONITORING AND EVALUATION | NCB |  | 80000000 | POST | Plan | 2nd - 30th July, 2018 | NA | 13th August, 2018 | - | 27th August, 2018 |  | Plan | 17th September, 2018 | 12th November, 2018 | 3rd December, 2018 | NA | 17th December, 2018 | 31st December, 2018 | 14th January, 2019 | Plan | 28th January, 2019 | NA | 80000000 | 25th February, 2018 | 25th February, 2018 | 18th March, 2018 | Plan | 1st April, 2018 | 15tth April, 2018 | 22nd April, 2018 | 29th April, 2018
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
UPGRADING OF PROCUREMENT DATABASE AND RECORD MANAGEMENT SYSTEM | NCB |  | 12165000 | POST | Plan | 2nd - 30th July, 2018 | NA | 13th August, 2018 | - | 27th August, 2018 |  | Plan | 17th September, 2018 | 12th November, 2018 | 3rd December, 2018 | NA | 17th December, 2018 | 31st December, 2018 | 14th January, 2019 | Plan | 28th January, 2019 | NA | 12165000 | 25th February, 2018 | 25th February, 2018 | 18th March, 2018 | Plan | 1st April, 2018 | 15tth April, 2018 | 22nd April, 2018 | 29th April, 2018
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
PROCUREMENT, CONFIGURATION AND TRAINING OF STAFF ON ARCHIVAL SYSTEMS | NCB |  | 14460500 | POST | Plan | 2nd - 30th July, 2018 | NA | 13th August, 2018 | - | 27th August, 2018 |  | Plan | 17th September, 2018 | 12th November, 2018 | 3rd December, 2018 | NA | 17th December, 2018 | 31st December, 2018 | 14th January, 2019 | Plan | 28th January, 2019 | NA | 14460500 | 25th February, 2018 | 25th February, 2018 | 18th March, 2018 | Plan | 1st April, 2018 | 15tth April, 2018 | 22nd April, 2018 | 29th April, 2018
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
AUTOMATION/DIGITALIZATION OF NATIONAL RECORDS CENTRE | NCB |  | 16220000 | POST | Plan | 2nd - 30th July, 2018 | NA | 13th August, 2018 | - | 27th August, 2018 |  | Plan | 17th September, 2018 | 12th November, 2018 | 3rd December, 2018 | NA | 17th December, 2018 | 31st December, 2018 | 14th January, 2019 | Plan | 28th January, 2019 | NA | 16220000 | 25th February, 2018 | 25th February, 2018 | 18th March, 2018 | Plan | 1st April, 2018 | 15tth April, 2018 | 22nd April, 2018 | 29th April, 2018
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
GROUP LIFE INSURANCE MONITORING & EVALUATION | NCB |  | 12165000 | POST | Plan | 2nd - 30th July, 2018 | NA | 13th August, 2018 | - | 27th August, 2018 |  | Plan | 17th September, 2018 | 12th November, 2018 | 3rd December, 2018 | NA | 17th December, 2018 | 31st December, 2018 | 14th January, 2019 | Plan | 28th January, 2019 | NA | 12165000 | 25th February, 2018 | 25th February, 2018 | 18th March, 2018 | Plan | 1st April, 2018 | 15tth April, 2018 | 22nd April, 2018 | 29th April, 2018
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
PRODUCTION OF AUTHORIZED ESTABLISHMENT OF MDAs | NCB |  | 8110000 | POST | Plan | 2nd - 30th July, 2018 | NA | 13th August, 2018 | - | 27th August, 2018 |  | Plan | 17th September, 2018 | 12th November, 2018 | 3rd December, 2018 | NA | 17th December, 2018 | 31st December, 2018 | 14th January, 2019 | Plan | 28th January, 2019 | NA | 8110000 | 25th February, 2018 | 25th February, 2018 | 18th March, 2018 | Plan | 1st April, 2018 | 15tth April, 2018 | 22nd April, 2018 | 29th April, 2018
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
PUBLISHING OF STATUTORY PUBLICATION/JOB CLASSIFICATION | NCB |  | 8110000 | POST | Plan | 2nd - 30th July, 2018 | NA | 13th August, 2018 | - | 27th August, 2018 |  | Plan | 17th September, 2018 | 12th November, 2018 | 3rd December, 2018 | NA | 17th December, 2018 | 31st December, 2018 | 14th January, 2019 | Plan | 28th January, 2019 | NA | 8110000 | 25th February, 2018 | 25th February, 2018 | 18th March, 2018 | Plan | 1st April, 2018 | 15tth April, 2018 | 22nd April, 2018 | 29th April, 2018
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
LOCAL TRAINING | NCB |  | 63348512 | POST | Plan | 2nd - 30th July, 2018 | NA | 13th August, 2018 | - | 27th August, 2018 |  | Plan | 17th September, 2018 | 12th November, 2018 | 3rd December, 2018 | NA | 17th December, 2018 | 31st December, 2018 | 14th January, 2019 | Plan | 28th January, 2019 | NA | 63348512 | 25th February, 2018 | 25th February, 2018 | 18th March, 2018 | Plan | 1st April, 2018 | 15tth April, 2018 | 22nd April, 2018 | 29th April, 2018
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
DIGITAL SERVICE INFRASTRUCTURE | NCB |  | 20275000 | POST | Plan | 2nd - 30th July, 2018 | NA | 13th August, 2018 | - | 27th August, 2018 |  | Plan | 17th September, 2018 | 12th November, 2018 | 3rd December, 2018 | NA | 17th December, 2018 | 31st December, 2018 | 14th January, 2019 | Plan | 28th January, 2019 | NA | 20275000 | 25th February, 2018 | 25th February, 2018 | 18th March, 2018 | Plan | 1st April, 2018 | 15tth April, 2018 | 22nd April, 2018 | 29th April, 2018
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
INSTALLATION AND CONFIGURATION OF E-LEARNING SOLUTION, TRAINING OF STAFF ON E-LEARNING CONTENT MANAGEMENT | NCB |  | 15000000 | POST | Plan | 2nd - 30th July, 2018 | NA | 13th August, 2018 | - | 27th August, 2018 |  | Plan | 17th September, 2018 | 12th November, 2018 | 3rd December, 2018 | NA | 17th December, 2018 | 31st December, 2018 | 14th January, 2019 | Plan | 28th January, 2019 | NA | 15000000 | 25th February, 2018 | 25th February, 2018 | 18th March, 2018 | Plan | 1st April, 2018 | 15tth April, 2018 | 22nd April, 2018 | 29th April, 2018
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
COMPUTER SOFTWARE ACQUISITION | NCB |  | 144,880,000.00 | POST | Plan | 2nd - 30th July, 2018 | NA | 13th August, 2018 | - | 27th August, 2018 |  | Plan | 17th September, 2018 | 12th November, 2018 | 3rd December, 2018 | NA | 17th December, 2018 | 31st December, 2018 | 14th January, 2019 | Plan | 28th January, 2019 | NA | 144,880,000.00 | 25th February, 2018 | 25th February, 2018 | 18th March, 2018 | Plan | 1st April, 2018 | 15tth April, 2018 | 22nd April, 2018 | 29th April, 2018
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
CAREER MANAGEMENT DEVELOPMENT | NCB |  | 16828250 | POST | Plan | 2nd - 30th July, 2018 | NA | 13th August, 2018 | - | 27th August, 2018 |  | Plan | 17th September, 2018 | 12th November, 2018 | 3rd December, 2018 | NA | 17th December, 2018 | 31st December, 2018 | 14th January, 2019 | Plan | 28th January, 2019 | NA | 16828250 | 25th February, 2018 | 25th February, 2018 | 18th March, 2018 | Plan | 1st April, 2018 | 15tth April, 2018 | 22nd April, 2018 | 29th April, 2018
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | #REF! |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan |  |  |  | #REF!
|  |  | #REF! |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | #REF! |  |  |  | Actual |  |  |  | #REF!
Fill gray cells only!

## Ministry of Foreign Affair
MINISTRY OF FOREIGN AFFAIRS,ABUJA
Budget Year: 2017
|  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Works |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Name/Designation | Name/Designation
PURCHASE OF COMP UTERS AND OTHER OFFICE EQUIPMENTS | Plan vs Actual | MFA/PRS/PROC/20/1 | LOT 1A | GOODS | N10,000,000.00 | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | N/A | 9-30/10/17 |  | N/A | Mrs A.I. Ogunyannwo, Mni Director(Procurement) | Mrs A.I. Ogunyannwo, Mni Director(Procurement)
OFFICE STATIONERIES AND COMPUTER CONSUMABLES | Plan vs Actual | MFA/PRS/PROC/20/2 | LOT 2A | GOODS | N20,716,980.00 | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | N/A | 9-30/10/17 |  | N/A | Mrs A.I. Ogunyannwo, Mni Director(Procurement) | Mrs A.I. Ogunyannwo, Mni Director(Procurement)
PURCHASE OF LAW BOOKS AND REPORT | Plan vs Actual | MFA/PRS/PROC/20/3 | LOT 3A | GOODS | N8,640,000.00 | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | N/A | 9-30/10/17 |  | N/A | Mrs A.I. Ogunyannwo, Mni Director(Procurement) | Mrs A.I. Ogunyannwo, Mni Director(Procurement)
PRINTING OF SECURITY DOCUMENTS | Plan vs Actual | MFA/PRS/PROC/20/4 | LOT 4A | GOODS | N24,768,000.00 | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | N/A | 9-30/10/17 |  | N/A | Mrs A.I. Ogunyannwo, Mni Director(Procurement) | Mrs A.I. Ogunyannwo, Mni Director(Procurement)
PRINTING OF NON-SECURITY DOCUMENTS | Plan vs Actual | MFA/PRS/PROC/20/5 | LOT 5A | GOODS | N13,176,000.00 | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | N/A | 9-30/10/17 |  | N/A | Mrs A.I. Ogunyannwo, Mni Director(Procurement) | Mrs A.I. Ogunyannwo, Mni Director(Procurement)
DRUGS & MEDICAL SUPPLIES | Plan vs Actual | MFA/PRS/PROC/20/6 | LOT 6A | GOODS | N8,640,000.00 | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | N/A | 9-30/10/17 |  | N/A | Mrs A.I. Ogunyannwo, Mni Director(Procurement) | Mrs A.I. Ogunyannwo, Mni Director(Procurement)
PROVISION AND INSTALLATION OF WORK STATION FOR MESSAGE PROCESSING , LAPTOPS FOR TROUBLE SHOOTING ON NETWORK AND 3 IN 1 PRINTERS | Plan vs Actual | MFA/PRS/PROC/20/7 | LOT 1B | WORKS | N18,000,000.00 | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | N/A | 9-30/10/17 |  | N/A | Mrs A.I. Ogunyannwo, Mni Director(Procurement) | Mrs A.I. Ogunyannwo, Mni Director(Procurement)
SERVICING AND MAINTENANCE OF 11NOS LIFTS AND PROVISION OF 3NOS LIFT ATTENDANTS | Plan vs Actual | MFA/PRS/PROC/20/8 | LOT 2B | WORKS | N14,000,000.00 | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | 9- 30/10/17 | 1/11/17-1/11/18 |  | N/A | Mrs A.I. Ogunyannwo, Mni Director(Procurement) | Mrs A.I. Ogunyannwo, Mni Director(Procurement)
REPAIRS OF OFFICE FURNITURE & EQUIPMENT IN THE MINISTRY | Plan vs Actual | MFA/PRS/PROC/20/9 | LOT 3B | WORKS | N16,781,000.00 | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | N/A | 9-30/10/17 |  | N/A | Mrs A.I. Ogunyannwo, Mni Director(Procurement) | Mrs A.I. Ogunyannwo, Mni Director(Procurement)
PROVISION AND INSTALLATION OF EMERGENCY LIGHTING STAIR WELLS | Plan vs Actual | MFA/PRS/PROC/20/10 | LOT 4B | WORKS | N6,729,600.00 | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | N/A | 9-30/10/17 |  | N/A | Mrs A.I. Ogunyannwo, Mni Director(Procurement) | Mrs A.I. Ogunyannwo, Mni Director(Procurement)
SYSTEM UPGRADE AT 4 NOS ELECTRICAL PANEL | Plan vs Actual | MFA/PRS/PROC/20/11 | LOT 5B | WORKS | N6,200,00.00 | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | N/A | 9-30/10/17 |  | N/A | Mrs A.I. Ogunyannwo, Mni Director(Procurement) | Mrs A.I. Ogunyannwo, Mni Director(Procurement)
MANAGEMENT AND MAINTENANCE OF ELECTRICAL, MECHANICAL,& WATER TREATMENT SERVICE | Plan vs Actual | MFA/PRS/PROC/20/12 | LOT 6B | WORKS | N25,000,000.OOK | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | 9- 30/10/17 | 1/12/17-1/12/18 |  | N/A | Mrs A.I. Ogunyannwo, Mni Director(Procurement) | Mrs A.I. Ogunyannwo, Mni Director(Procurement)
MISSIONS PROJECTS
BAMAKO, MALI
i,Renovation of HOC Staff QuarterS | Plan vs Actual | MFA/PRS | LOT 1 | WORKS | N2,092,562.00k | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | N/A | 3Months |  | N/A | HEAD OF CHANCERY | HEAD OF CHANCERY
ii,Purchase of Generator Set | Plan vs Actual | MFA/PRS | LOT 2 | WORKS | N3,426,669.00k | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | N/A | 3Weeks |  | N/A | HEAD OF CHANCERY | HEAD OF CHANCERY
iii,Purchase of Toyota Land Cruiser | Plan vs Actual | MFA/PRS | LOT 3 | WORKS | N12,727,629.00k | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | N/A | 3Weeks |  | N/A | HEAD OF CHANCERY | HEAD OF CHANCERY
TOTAL |  |  |  |  | N18,246,865.OOK
BANGUI,CENTRAL AFRICAN REPUBLIC
i,Renovation of Residence | Plan vs Actual | MFA/PRS | LOT 1 | WORKS | N 4,529,626.25 | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | N/A | 3Months |  | N/A | HEAD OF CHANCERY | HEAD OF CHANCERY
ii,Repair and Furniture of House No.36 Villa,Bangui | Plan vs Actual | MFA/PRS | LOT 2 | WORKS | N3,200,000.00K | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | N/A | 3Months |  | N/A | HEAD OF CHANCERY | HEAD OF CHANCERY
TOTAL APPROPRIATION |  |  |  |  | N18,246,865.00
BRAZZAVILLE, CONGO
i) Purchase of 1 Representional Car | Plan vs Actual | MFA/PRS | LOT 1 | WORKS | N19,500,000.00k | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | N/A | 3Weeks |  | N/A | HEAD OF CHANCERY | HEAD OF CHANCERY
ii) Purchase of Toyota Jeep | Plan vs Actual | MFA/PRS | LOT 2 | WORKS | N15, 000, 000.00k | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | N/A | 3Weeks |  | N/A | HEAD OF CHANCERY | HEAD OF CHANCERY
iii) Purchase of One Generator Set | Plan vs Actual | MFA/PRS | LOT 3 | WORKS | N15, 500, 000.00k | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | N/A | 3Weeks |  | N/A | HEAD OF CHANCERY | HEAD OF CHANCERY
TOTAL |  |  |  |  | N50, 000, 000.00k
BERNE, GENEVA
i)Purchase of 1 Rep. Car | Plan vs Actual | MFA/PRS | LOT 1 | WORKS | N36, 651, 020. 80 | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | N/A | 3Weeks |  | N/A | HEAD OF CHANCERY | HEAD OF CHANCERY
ii) Renovation of and Refurbishment of Chancery and Staff Quarters. | Plan vs Actual | MFA/PRS | LOT 2 | WORKS | N13,120,000.00k | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | N/A | 3Months |  | N/A | HEAD OF CHANCERY | HEAD OF CHANCERY
TOTAL |  |  |  |  | N49,771,020.80
PRETORIA,SOUTH AFRICA
i, Rehabilitation of Ambassadors Residence | Plan vs Actual | MFA/PRS | LOT 1 | WORKS | R1,009,450.00 | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | N/A | 3Months |  | N/A | HEAD OF CHANCERY | HEAD OF CHANCERY
ii, Renovation of 3nos Staff Quarters | Plan vs Actual | MFA/PRS | LOT 2 | WORKS | R2,377,995.00 | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | N/A | 3Months |  | N/A | HEAD OF CHANCERY | HEAD OF CHANCERY
iii, Purchase of 1 Rep.Car | Plan vs Actual | MFA/PRS | LOT 3 | WORKS | R 980,000.00 | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | N/A | 3Weeks |  | N/A | HEAD OF CHANCERY | HEAD OF CHANCERY
TOTAL |  |  |  |  | N79,989,835.15
ROME ITALY
i)Renovation of Chancery Building | Plan vs Actual | MFA/PRS | LOT 1 | WORKS | N50,000,000.00 | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | N/A | 3Months |  | N/A | HEAD OF CHANCERY | HEAD OF CHANCERY
ii)Furnishing of the Chancery. | Plan vs Actual | MFA/PRS | LOT 2 | WORKS | N20,000,000.00 | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | N/A | 3Months |  | N/A | HEAD OF CHANCERY | HEAD OF CHANCERY
TOTAL |  |  |  |  | N70,000,000.00
YAOUNDE, CAMEROON
i)Purchase of 3nos vehicles | Plan vs Actual | MFA/PRS | LOT 1 | WORKS | N28,500,000.00k | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | N/A | 3Weeks |  | N/A | HEAD OF CHANCERY | HEAD OF CHANCERY
AMMAN, JORDAN
Purchase of Rep. Car | Plan vs Actual | MFA/PRS | LOT 1 | WORKS | N18,246,865.00k (USD58,384.96) | NCB | MTB | LCS | N/A | N/A | 12- 26/6/17 | 26-10/7/17 | N/A | N/A | N/A | N/A | N/A | 10/7/17 - 21/8/17 | 2017-08-21 | 21-4/9/17 | 11-18/9/17 |  | N/A | 18- 25/9/17 | 25- 9/10/17 | N/A | 3Weeks |  | N/A | HEAD OF CHANCERY | HEAD OF CHANCERY

## National Eye Centre Kaduna
NATIONAL EYE CENTRE, KADUNA
S/N | 2017 PROJECT TITLE/LINE ITEM | 2017 ORIGINAL PROPOSAL TO FMoH | 2017 EXECUTIVE PROPOSAL (from BUDGET OFFICE) | 2017 ACTUAL COST OF PROJECT | VARIANCE/ DIFFERENCE | REMARKS
CAPITAL
1 | PURCHASE OF HEALTH/MEDICAL EQUIPMENT
| PROCUREMENT OF MEDICAL EQUIPMENT LIKE VITREO-RETINAL MACHINES, INSTALLATION OF EXCIMER LASER MACHINE, OPHTHALMIC SURGICAL INSTRUMENTS IN FORM OF CATARACT, PAEDIATRIC, GLAUCOMA, VIRECTOMY, OCULOPLASTIC AND CORNEA SETS AND ANAESTHETIC MACHINES. | 108750000 | 28793765.5 | 108750000 | 79956234.5 | Final envelope is grossly insufficient for the project
2 | REHABILITATION/REPAIRS - HOSPITAL FACILITIES
| REHABILITATION OF HOSPITAL BUILDING (BLOCKS A&B) | 82600000 | 15904308.5 | 82600000 | 66695691.5 | Final envelope is grossly insufficient for the project
3 | PROCUREMENT OF PROJECT VEHICLES
| PROCUREMENT OF PROJECT VEHICLES (TOYOTA HILUX, TOYOTA COROLLA, 18-SEATER BUS) | 35000000 | 13510000 | 35000000 | 21490000 | Final envelope is grossly insufficient for the project
4 | COMPUTER SOFTWARE ACQUISITION
| COMPLETION OF HOSPITAL COMPUTERIZATION (ELECTRONIC HEALTH RECORDS, PHARMCY, STORES, OPERATING THEATRE, HUMAN RESOURCES MANAGEMENT, ACCOUNTS AND AUDIT PLATFORMS) | 18000000 | 3474000 | 18000000 | 14526000 | Final envelope is grossly insufficient for the project
5 | TENDER MEETINGS/INTERNAL MONITORING OF CONTRACTORS | 0 | 1158000 | 2000000 | 842000 | Original proposal is not sufficient owing to inflation
6 | TRAINING OF PERSONNEL | 0 | 3860000 | 15000000 | 11140000 | Original proposal is not sufficient owing to inflation
7 | TRAINING OF 15 RESIDENT DOCTORS | 0 | 1930000 | 15000000 | 13070000 | Original proposal is not sufficient owing to inflation
8 | MONITORING AND EVALUATION | 0 | 1930000 | 2500000 | 570000 | Original proposal is not sufficient owing to inflation
| TOTAL | 244350000 | 70560074 | 278850000 | 208289926