## Planning
NOCOPO DATA
PLANNING RECORD
| MDA | 111010001 BUREAU OF PUBLIC PROCUREMENT (BPP)
| Budget Year | 2018
S/N | Project Code | Project Title | Project Rationale | Package Number | Lot Number | Development Partners | Budget Source | Budget Code | Budget Description | Budget Category | Budget Currency | Budget Amount | Project Estimated Currency | Project Estimated Amount | Project Category | Project Street | Project City | Nearest Landmark | Project LGA | Project State | Procurement Category | Contract type | Procurement Method | Selection Method | Appval Authority | Qualification | Review Type | Prep for Solicit Start date | Prep for Solicit End date | Is EoI applicable | Advert of EoI Start date | Advert of EoI End date | EoI Opening Event date | Eval of EoI Start Date | Eval of EoI End Date | EoI Eval Rpt Appval Start Date | EoI Eval Rpt Appval End Date | EoI Shortlist Publ Date | Invit Req Proposals Start Date | Invit Req Proposals End Date | Open of Tech Proposal Date | Tech Eval Rpt Approv Start Date | Tech Eval Rpt Approv End Date | Opening of Financial Proposal | Final Eval Rprt TF Start Date | Final Eval Rprt TF End Date | Negotiations Start Date | Negotiations End Date | Negotiations NotApplicable | Proc Entity Eval Rprt Appval Start Date | Proc Entity Eval Rprt Appval End Date | Iss of Cert of NO Eval Rprt Start Date | Iss of Cert of NO Eval Rprt End Date | Iss of Cert of NO Eval Rprt NotApplicable | Award Date | Submit of Final Rprt Start Date | Submit of Final Rprt End Date | Contract Period Start Date | Contract Period End Date | Contract Period Days | Prep of Bid Doc Advert Start Date | Prep of Bid Doc Advert End Date | Is PreQual applicable | Advert for PreQual Start Date | Advert for PreQual End Date | PreQual Opening Date | PreQual Eval Appval Start Date | PreQual Eval Appval End Date | PreQual Publish Date | Tendering Period Start Date | Tendering Period End Date | Bid Opening Date | Bid Evaluation Period Start Date | Bid Evaluation Period End Date | Proc Entity Eval Appval Start Date | Proc Entity Eval Appval End Date | Iss of Cert of NO Eval Rprt Start Date | Iss of Cert of NO Eval Rprt End Date | Contract Award Start Date | Contract Award End Date | Arrival of Goods Start Date | Arrival of Goods End Date | Substantial Completion Date | Final Acceptance Start Date | Final Acceptance End Date | Action Party Names | Action Party Designation | Action Party EMail | Action Party Phone | Champion Names | Champion Designation | Champion EMail | Champion Phone
1 | ocds-gyl66f-111010001-000001 | Office Stationeries/Computer Consumables | Restocking of Office Stationeries/Computer Consumables |  |  |  |  | 22020301 | Office Stationeries/Computer Consumables | Recurrent | NGN | 23,410,881.00 |  | 0.00 | [6 empty] | Goods | [6 empty] | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  |  |  | '' |  |  |  | ''
2 | ocds-gyl66f-111010001-000002 | Books | Provision of books in BPP's Library |  |  |  |  | 22020302 | Books | Recurrent | NGN | 1,213,801.00 |  | 0.00 | [6 empty] | Goods | [6 empty] | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  |  |  | '' |  |  |  | ''
3 | ocds-gyl66f-111010001-000003 | Printing of Non-Security Documents | Printing of Non-Security Documents |  |  |  |  | 22020305 | Printing of Non-Security Documents | Recurrent | NGN | 24,962,500.00 |  | 0.00 | [6 empty] | Goods | [6 empty] | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  |  |  | '' |  |  |  | ''
4 | ocds-gyl66f-111010001-000004 | Printing of Security Documents | Printing of Security Documents |  |  |  |  | 22020306 | Printing of Security Documents | Recurrent | NGN | 12,000,000.00 |  | 0.00 | [6 empty] | Goods | [6 empty] | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  |  |  | '' |  |  |  | ''
5 | ocds-gyl66f-111010001-000005 | Uniforms and other Clothing | Provision of Uniforms and other Clothing |  |  |  |  | 22020309 | Uniforms and other Clothing | Recurrent | NGN | 11,200,000.00 |  | 0.00 | [6 empty] | Goods | [6 empty] | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  |  |  | '' |  |  |  | ''
6 | ocds-gyl66f-111010001-000006 | Maintenance of Motor Vehicle/Transport Equipment | Routine Maintenance of Motor Vehicle/Transport Equipment |  |  |  |  | 22020401 | Maintenance of Motor Vehicle/Transport Equipment | Recurrent | NGN | 15,300,000.00 |  | 0.00 | [6 empty] | Non-Consultancy Services | [6 empty] | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  |  |  | '' |  |  |  | ''
7 | ocds-gyl66f-111010001-000007 | Maintenance of Office Furniture | Routine Maintenance of Office Furniture |  |  |  |  | 22020402 | Maintenance of Office Furniture | Recurrent | NGN | 5,515,482.00 |  | 0.00 | [6 empty] | Non-Consultancy Services | [6 empty] | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  |  |  | '' |  |  |  | ''
8 | ocds-gyl66f-111010001-000008 | Maintenance of Office Building/Residential Qtrs | Routine Maintenance of Office Building/Residential Qtrs |  |  |  |  | 22020404 | Maintenance of Office Building/Residential Qtrs | Recurrent | NGN | 9,864,020.00 |  | 0.00 | [6 empty] | Non-Consultancy Services | [6 empty] | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  |  |  | '' |  |  |  | ''
9 | ocds-gyl66f-111010001-000009 | Maintenance of Office/IT Equipment | Routine Maintenance of Office/IT Equipment |  |  |  |  | 22020404 | Maintenance of Office/IT Equipment | Recurrent | NGN | 7,744,343.00 |  | 0.00 | [6 empty] | Non-Consultancy Services | [6 empty] | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  |  |  | '' |  |  |  | ''
10 | ocds-gyl66f-111010001-000010 | Maintenance of Plants/ Generators | Routine Maintenance of Plants/ Generators |  |  |  |  | 22020405 | Maintenance of Plants/ Generators | Recurrent | NGN | 3,000,000.00 |  | 0.00 | [6 empty] | Non-Consultancy Services | [6 empty] | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  |  |  | '' |  |  |  | ''
11 | ocds-gyl66f-111010001-000011 | Provision of Office Furniture and Fittings | Replacement and Maintenance of Plants/ Generators | BPP/18/001 | Lot 1 |  | Appropriation | 15107497 | Maintenance of Plants/ Generators | Capital | NGN | 27,417,603.00 | NGN | 27,417,603.00 | [6 empty] | Goods | Lump Sum | Direct Procurement | Lowest Evaluated Responsive Bid | Parastatal Tenders Board | Post-Qualification | Post-Review | 1-01-01 | 1-01-01 | -1 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 2018-11-30 | 2018-12-30 | 0 | 2018-10-08 | 2018-10-14 |  | 2018-10-19 | 2018-11-01 | 2018-11-01 | 2018-11-16 | 2018-11-20 | 2018-11-22 | 2018-12-07 | 2019-01-17 | 2019-01-17 | 2019-01-19 | 2019-01-25 | 2019-01-31 | 2019-02-04 | 2019-02-10 | 2019-02-23 | 2018-11-20 | 2018-11-30 | 2018-08-31 | 2018-09-01 | 1-01-01 | 1-01-01 | 1-01-01 | Engr. Nasir Bello | Head, Procurement | nasir.bello@bpp.gov.ng | '' | Ilogbaka Ikenna | Procurement Officer I | ilogbaka.ikenna@bpp.gov.ng | ''
12 | ocds-gyl66f-111010001-000012 | Furnishing of BPP Library | Provision of Furniture for BPP Library | BPP/18/002 | Lot 2 |  | Appropriation | 15107504 | Furnishing of BPP Library | Capital | NGN | 20,000,000.00 | NGN | 16,000,000.00 | [6 empty] | Goods | Lump Sum | Direct Procurement | Lowest Evaluated Responsive Bid | Parastatal Tenders Board | Post-Qualification | Post-Review | 1-01-01 | 1-01-01 | -1 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 2018-04-02 | 2018-04-08 | No | 2018-04-13 | 2018-04-26 | 2018-04-26 | 2018-05-11 | 2018-05-15 | 2018-05-17 | 2018-06-01 | 2018-07-12 | 2018-07-12 | 2018-07-14 | 2018-07-20 | 2018-07-26 | 2018-07-30 | 2018-08-05 | 2018-08-18 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | Engr. Nasir Bello | Head, Procurement | nasir.bello@bpp.gov.ng | '' | Ilogbaka Ikenna | Procurement Officer I | ilogbaka.ikenna@bpp.gov.ng | ''
13 | ocds-gyl66f-111010001-000013 | Completion of Electronic Government Procurement System (E-GP) | Deployment of e-GP System in Nigeria | BPP/18/003 | Lot 3 |  | Appropriation | 15107515 | Completion of Electronic Government Procurement System (E-GP) | Capital | NGN | 100,000,000.00 | NGN | 100,000,000.00 | [6 empty] | Consultancy Services | Lump Sum | National Competitive Bidding | Quality & Cost Based Selection(QCBS) | BPP/FEC | Pre-Qualification | Prior-Review | 2018-09-24 | 2018-09-30 | -1 | 2018-10-05 | 2018-10-18 | 2018-10-18 | 2018-11-02 | 2018-11-06 | 2018-11-12 | 2018-11-14 | 2018-11-16 | 2018-12-01 | 2018-12-30 | 2018-12-30 | 2019-01-01 | 2019-01-07 | 2019-01-22 | 2019-01-24 | 2019-01-30 | 2019-02-07 | 2019-02-09 | No | 2019-02-20 | 2019-02-24 | 2019-03-02 | 2019-03-15 |  | 2019-02-11 | 2019-03-11 | 2019-04-15 | 2001-01-01 | 2001-01-01 | 100 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | Engr. Nasir | Head, Procurement | nasir.bello@bpp.gov.ng | '' | Aliyu | Head, Regulation & Database/ICT | aliyu.aliyu@bpp.gov.ng | ''
14 | ocds-gyl66f-111010001-000014 | Development of BPP Database Management System/Electronic Document Management and Archiving System | Development of BPP Database Management System/Electronic Document Management and Archiving System | BPP/18/004 | Lot 4 |  | Appropriation | 15107515 | EGP component modules: Development of BPP Database Management System/Electronic Document Management | Capital | NGN | 50,000,000.00 | NGN | 50,000,000.00 | [6 empty] | Consultancy Services | Lump Sum | Selective Tendering | Quality & Cost Based Selection(QCBS) | Parastatal Tenders Board | Post-Qualification | Post-Review | 2018-09-24 | 2018-09-30 | -1 | 2018-10-05 | 2018-10-18 | 2018-10-18 | 2018-11-02 | 2018-11-06 | 2018-11-12 | 2018-11-14 | 2018-11-16 | 2018-12-01 | 2018-12-30 | 2018-12-30 | 2019-01-01 | 2019-01-07 | 2019-01-22 | 2019-01-24 | 2019-01-30 | 2019-02-07 | 2019-02-09 | No | 2019-02-20 | 2019-02-24 | 2019-03-02 | 2019-03-15 |  | 2019-02-05 | 1-01-01 | 2019-02-24 | 2019-02-20 | 2019-02-24 | 100 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | Engr. Nasir Bello | Head, Procurement | nasir.bello@bpp.gov.ng | '' | Aliyu E. Aliyu | Head, Regulation & Database/ICT | aliyu.aliyu@bpp.gov.ng | ''
15 | ocds-gyl66f-111010001-000015 | Upgrade and Deployment of National Database of Contractors, Consultants and Service Providers | Upgrade of the CCSP Portal | BPP/18/005 | Lot 5 |  | Appropriation |  | Upgrade and Deployment of National Database of Contractors, Consultants and Service Providers | Capital | NGN | 50,000,000.00 | NGN | 49,000,000.00 | [6 empty] | Consultancy Services | Lump Sum | Repeat Procurement | Single Source Selection(SSS) | Parastatal Tenders Board | Post-Qualification | Post-Review | 2018-02-05 | 2018-02-11 | 2 | 2018-02-16 | 2018-03-01 | 2018-03-01 | 2018-03-16 | 2018-03-20 | 2018-03-26 | 2018-03-28 | 2018-03-30 | 2018-04-14 | 2018-05-13 | 2018-05-13 | 2018-05-15 | 2018-05-21 | 2018-06-05 | 2018-06-07 | 2018-06-13 | 2018-06-21 | 2018-06-23 | Yes | 2018-07-04 | 2018-07-08 | 2018-07-14 | 2018-07-27 |  | 2018-11-12 | 2018-12-12 | 2018-11-12 | 2018-11-12 | 2018-11-12 | 100 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | Engr. Nasir Bello | Head, Procurement | nasir.bello@bpp.gov.ng | '' | Aliyu E. Aliyu | Head, Regulation & Database/ICT | aliyu.aliyu@bpp.gov.ng | ''
16 | ocds-gyl66f-111010001-000016 | Upgrading of Accounting Software | Routine upgrade of Accounting Software | BPP/18/006 | Lot 6 |  | Appropriation |  | Upgrading of Accounting Software | Capital | NGN | 20,000,000.00 | NGN | 20,000,000.00 | [6 empty] | Goods | Lump Sum | Selective Tendering | Lowest Evaluated Responsive Bid | Parastatal Tenders Board | Post-Qualification | Post-Review | 1-01-01 | 1-01-01 | -1 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 2018-10-08 | 2018-10-14 |  | 2018-10-19 | 2018-11-01 | 2018-11-01 | 2018-11-16 | 2018-11-20 | 2018-11-22 | 2018-12-07 | 2019-01-17 | 2019-01-17 | 2019-01-19 | 2019-01-25 | 2019-01-31 | 2019-02-04 | 2019-02-10 | 2019-02-23 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | Engr. Nasir Bello | Head, Procurement | nasir.bello@bpp.gov.ng | '' | Aliyu E. Aliyu | Head, Regulation & Database/ICT | aliyu.aliyu@bpp.gov.ng | ''
17 | ocds-gyl66f-111010001-000017 | Purchase of Audio Visual Equipment | Replacement of BPP's Audio Visual Equipment | BPP/18/007 | Lot 7 |  | Appropriation |  | Purchase of Audio Visual Equipment | Capital | NGN | 20,000,000.00 | NGN | 12,000,000.00 | [6 empty] | Goods | Lump Sum | Selective Tendering | Lowest Evaluated Responsive Bid | Parastatal Tenders Board | Post-Qualification | Post-Review | 1-01-01 | 1-01-01 | -1 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 2018-09-10 | 2018-09-16 |  | 2018-09-21 | 2018-10-04 | 2018-10-04 | 2018-10-19 | 2018-10-23 | 2018-10-25 | 2018-11-09 | 2018-12-20 | 2018-12-20 | 2018-12-22 | 2018-12-28 | 2019-01-03 | 2019-01-07 | 2019-01-13 | 2019-01-26 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | Engr. Nasir Bello | Head, Procurement | nasir.bello@bpp.gov.ng | '' | Segun Imohiosen | Head, Media Unit | segun.imohiosen@bpp.gov.ng | ''
18 | ocds-gyl66f-111010001-000018 | Construction/Erection of Bill Boards in 10 Selected States in Nigeria and Automation of Media Operat | Construction/Erection of Bill Boards in 10 Selected States in Nigeria and Automation of Media Operat | BPP/18/008 | Lot 8 |  | Appropriation |  | Construction/Erection of Bill Boards in 10 Selected States in Nigeria and Automation of Media Operat | Capital | NGN | 16,000,000.00 | NGN | 16,000,000.00 | [6 empty] | Goods | Lump Sum | Selective Tendering | Lowest Evaluated Responsive Bid | Parastatal Tenders Board | Post-Qualification | Post-Review | 1-01-01 | 1-01-01 | -1 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 2018-10-08 | 2018-10-14 |  | 2018-10-19 | 2018-11-01 | 2018-11-01 | 2018-11-16 | 2018-11-20 | 2018-11-22 | 2018-12-07 | 2019-01-17 | 2019-01-17 | 2019-01-19 | 2019-01-25 | 2019-01-31 | 2019-02-04 | 2019-02-10 | 2019-02-23 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | Engr. Nasir Bello | Head, Procurement | nasir.bello@bpp.gov.ng | '' | Segun Imohiosen | Head, Media Unit | segun.imohiosen@bpp.gov.ng | ''
19 | ocds-gyl66f-111010001-000019 | Development of Market Survey Database | Development of Market Survey Database | BPP/18/009 | Lot 9 |  | Appropriation |  | Development of Market Survey Database | Capital | NGN | 20,000,000.00 | NGN | 20,000,000.00 | [6 empty] | Consultancy Services | Lump Sum | Selective Tendering | Quality & Cost Based Selection(QCBS) | Parastatal Tenders Board | Post-Qualification | Post-Review | 2018-09-24 | 2018-09-30 | -1 | 2018-10-05 | 2018-10-18 | 2018-10-18 | 2018-11-02 | 2018-11-06 | 2018-11-12 | 2018-11-14 | 2018-11-16 | 2018-12-01 | 2018-12-30 | 2018-12-30 | 2019-01-01 | 2019-01-07 | 2019-01-22 | 2019-01-24 | 2019-01-30 | 2019-02-07 | 2019-02-09 | No | 2019-02-20 | 2019-02-24 | 2019-03-02 | 2019-03-15 |  | 2018-12-17 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 100 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | Engr. Nasir Bello | Head, Procurement | nasir.bello@bpp.gov.ng | '' | Aliyu E. Aliyu | Head, Regulation & Database/ICT | aliyu.aliyu@bpp.gov.ng | ''
20 | ocds-gyl66f-111010001-000020 | Research and Development for Lawyers on Emerging Trends in Law and Procurement | Research and Development for Lawyers on Emerging Trends in Law and Procurement | BPP/18/010 | Lot 10 |  | Appropriation |  | Research and Development for Lawyers on Emerging Trends in Law and Procurement | Capital | NGN | 15,000,000.00 | NGN | 15,000,000.00 | [6 empty] | Consultancy Services | Lump Sum | Direct Procurement | Fixed Budget Selection (FBS) | Parastatal Tenders Board | Post-Qualification | Post-Review | 2018-09-24 | 2018-09-30 | -1 | 2018-10-05 | 2018-10-18 | 2018-10-18 | 2018-11-02 | 2018-11-06 | 2018-11-12 | 2018-11-14 | 2018-11-16 | 2018-12-01 | 2018-12-30 | 2018-12-30 | 2019-01-01 | 2019-01-07 | 2019-01-22 | 2019-01-24 | 2019-01-30 | 2019-02-07 | 2019-02-09 | No | 2019-02-20 | 2019-02-24 | 2019-03-02 | 2019-03-15 |  | 2019-01-10 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 50 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | Engr. Nasir Bello | Head, Procurement | nasir.bello@bpp.gov.ng | '' | Andrew Zibiri | Head, Legal Unit | andrew.zibiri@bpp.gov.ng | ''
21 | ocds-gyl66f-111010001-000021 | Research Work on Implementation of Public Procurement Process | Research Work on Implementation of Public Procurement Process | BPP/18/011 | Lot 11 |  | Appropriation |  | Research Work on Implementation of Public Procurement Process | Capital | NGN | 10,000,000.00 | NGN | 10,000,000.00 | [6 empty] | Consultancy Services | Lump Sum | Selective Tendering | Fixed Budget Selection (FBS) | Parastatal Tenders Board | Post-Qualification | Post-Review | 2018-09-24 | 2018-09-30 | -1 | 2018-10-05 | 2018-10-18 | 2018-10-18 | 2018-11-02 | 2018-11-06 | 2018-11-12 | 2018-11-14 | 2018-11-16 | 2018-12-01 | 2018-12-30 | 2018-12-30 | 2019-01-01 | 2019-01-07 | 2019-01-22 | 2019-01-24 | 2019-01-30 | 2019-02-07 | 2019-02-09 | No | 2019-02-20 | 2019-02-24 | 2019-03-02 | 2019-03-15 |  | 2019-02-11 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 100 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | Engr. Nasir Bello | Head, Procurement | nasir.bello@bpp.gov.ng | '' | Adebowale Adedokun | Head, TR&SP | adebowale.adedokun@bpp.gov.ng | ''
22 | ocds-gyl66f-111010001-000022 | Review of Socio-Economic Effect of Polices on Procurement/Guiding Government Strategy for Procuremen | Review of Socio-Economic Effect of Polices on Procurement/Guiding Government Strategy for Procuremen | BPP/18/012 | Lot 12 |  | Appropriation |  | Review of Socio-Economic Effect of Polices on Procurement/Guiding Government Strategy for Procuremen | Capital | NGN | 20,000,000.00 | NGN | 20,000,000.00 | [6 empty] | Consultancy Services | Lump Sum | Direct Procurement | Fixed Budget Selection (FBS) | Parastatal Tenders Board | Post-Qualification | Post-Review | 2018-09-24 | 2018-09-30 | 1 | 2018-10-05 | 2018-10-18 | 2018-10-18 | 2018-11-02 | 2018-11-06 | 2018-11-12 | 2018-11-14 | 2018-11-16 | 2018-12-01 | 2018-12-30 | 2018-12-30 | 2019-01-01 | 2019-01-07 | 2019-01-22 | 2019-01-24 | 2019-01-30 | 2019-02-07 | 2019-02-09 | Yes | 2019-02-20 | 2019-02-24 | 2019-03-02 | 2019-03-15 |  | 2019-02-05 | 1-01-01 | 1-01-01 | 2019-02-20 | 2019-02-24 | 50 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | Engr. Nasir Bello | Head, Procurement | nasir.bello@bpp.gov.ng | '' | Adebowale Adedokun | Head, TR&SP | adebowale.adedokun@bpp.gov.ng | ''
23 | ocds-gyl66f-111010001-000023 | Supply of Media Equipment | Replacement of Obsolete Media Equipment | BPP/18/0000 | NIL |  | Appropriation | ERGP15107542 | PURCHASE OF AUDIO-VISUAL AND CONSTRUCTION/ERECTION OF BILL BOARDS IN 10 SELECTED STATES IN NIGERIA A | Capital | NGN | 20,000,000.00 | NGN | 15,000,000.00 | [6 empty] | Goods | Lump Sum | Selective Tendering | Lowest Evaluated Responsive Bid | Parastatal Tenders Board | Post-Qualification | Post-Review | 1-01-01 | 1-01-01 | -1 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 2018-08-13 | 2018-08-24 | 0 | 2018-01-08 | 2018-01-14 |  | 2018-01-19 | 2018-02-01 | 2018-02-01 | 2018-02-16 | 2018-02-20 | 2018-02-22 | 2018-03-09 | 2018-04-19 | 2018-04-19 | 2018-04-21 | 2018-04-27 | 2018-05-03 | 2018-05-07 | 2018-05-13 | 2018-05-26 | 2018-08-06 | 2018-08-06 | 2018-08-24 | 2018-08-25 | 1-01-01 | 1-01-01 | 1-01-01 | Engr. Nasir Bello | Head, Procurement | nasir.bello@bpp.gov.ng | '08033500124 | Ilogbaka Ikenna | Procurement Officer I | ilogbaka.ikenna@bpp.gov.ng | '08133981593
24 | ocds-gyl66f-111010001-000024 | Office Stationeries/Computer Consumables | Restocking of Office Stationeries/Computer Consumables |  |  |  |  | 22020301 | Office Stationeries/Computer Consumables | Recurrent | NGN | 23,410,881.00 |  | 0.00 | [6 empty] | Goods | [6 empty] | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  |  |  | ' |  |  |  | '
25 | ocds-gyl66f-111010001-000025 | Books | Provision of Books |  |  |  |  | 22020302 | Books | Recurrent | NGN | 1,213,801.00 |  | 0.00 | [6 empty] | Goods | [6 empty] | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  |  |  | ' |  |  |  | '
26 | ocds-gyl66f-111010001-000026 | Newspapers | Procurement of Newspapers |  |  |  |  | 22020303 | Newspapers | Recurrent | NGN | 2,839,600.00 |  | 0.00 | [6 empty] | Goods | [6 empty] | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  |  |  | ' |  |  |  | '
27 | ocds-gyl66f-111010001-000027 | Magazines and Periodicals | Provision of Magazines and Periodicals |  |  |  |  | 22020304 | Provision of Magazines and Periodicals | Recurrent | NGN | 1,588,000.00 |  | 0.00 | [6 empty] | Goods | [6 empty] | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  |  |  | ' |  |  |  | '
28 | ocds-gyl66f-111010001-000028 | Printing of Non-Security Documents | Printing of Non-Security Documents |  |  |  |  | 22020304 | Printing of Non-Security Documents | Recurrent | NGN | 24,962,500.00 |  | 0.00 | [6 empty] | Goods | [6 empty] | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  |  |  | ' |  |  |  | '
29 | ocds-gyl66f-111010001-000029 | Printing of Security Documents | Printing of Security Documents |  |  |  |  | 22020306 | Printing of Security Documents | Recurrent | NGN | 12,000,000.00 |  | 0.00 | [6 empty] | Goods | [6 empty] | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  |  |  | ' |  |  |  | '
30 | ocds-gyl66f-111010001-000030 | Uniforms and other clothing | Provision of Uniforms and other Clothing |  |  |  |  | 22020309 | Printing of Security Document | Recurrent | NGN | 11,200,000.00 |  | 0.00 | [6 empty] | Goods | [6 empty] | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  |  |  | ' |  |  |  | '
31 | ocds-gyl66f-111010001-000031 | Maintenance of Motor Vehicle/Transport Equipment | Maintenance of Motor Vehicle/Transport Equipment |  |  |  |  | 22020401 | Maintenance of Motor Vehicle/Transport Equipment | Recurrent | NGN | 15,300,000.00 |  | 0.00 | [6 empty] | Non-Consultancy Services | [6 empty] | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  |  |  | ' |  |  |  | '
32 | ocds-gyl66f-111010001-000032 | Maintenance of Office Furniture | Maintenance of Office Furniture |  |  |  |  | 22020402 | Maintenance of Office Furniture | Recurrent | NGN | 5,515,482.00 |  | 0.00 | [6 empty] | Non-Consultancy Services | [6 empty] | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  |  |  | ' |  |  |  | '
33 | ocds-gyl66f-111010001-000033 | Maintenance of Office Building/Residential Qtrs | Maintenance of Office Building/Residential Qtrs |  |  |  |  | 22020403 | Maintenance of Office Building/Residential Qtrs | Recurrent | NGN | 9,864,020.00 |  | 0.00 | [6 empty] | Non-Consultancy Services | [6 empty] | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  |  |  | ' |  |  |  | '
34 | ocds-gyl66f-111010001-000034 | Maintenance of Office/IT Equipment | Maintenance of Office/IT Equipment |  |  |  |  | 22020404 | Maintenance of Office/IT Equipment | Recurrent | NGN | 3,000,000.00 |  | 0.00 | [6 empty] | Non-Consultancy Services | [6 empty] | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  |  |  | ' |  |  |  | '
35 | ocds-gyl66f-111010001-000035 | Maintenance of Plants/ Generators | Maintenance of Plants/ Generators |  |  |  |  | 22020405 | Maintenance of Plants/ Generators | Capital | NGN | 3,000,000.00 |  | 0.00 | [6 empty] | Non-Consultancy Services | [6 empty] | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  |  |  | ' |  |  |  | '
36 | ocds-gyl66f-111010001-000036 | Other Maintenance Services | Other Maintenance Services |  |  |  |  | 22020406 | Other Maintenance Services | Recurrent | NGN | 7,191,005.00 |  | 0.00 | [6 empty] | Non-Consultancy Services | [6 empty] | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  |  |  | ' |  |  |  | '
37 | ocds-gyl66f-111010001-000037 | Verification of Claims of Contractors, Consultants and Service Providers | Verification of Claims of Contractors, Consultants and Service Providers | [5 empty] | Verification of Claims of Contractors, Consultants and Service Providers | Capital | NGN | 25,000,000.00 |  | 0.00 | [6 empty] | Consultancy Services | [6 empty] | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  |  |  | ' |  |  |  | '
38 | ocds-gyl66f-111010001-000038 | Development of Call Center Management for Contractors, Consultants and Service Providers | Development of Call Center Management for Contractors, Consultants and Service Providers | [5 empty] | Development of Call Center Management for Contractors, Consultants and Service Providers | Capital | NGN | 25,000,000.00 |  | 0.00 | [6 empty] | Consultancy Services | [6 empty] | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 0 | 1-01-01 | 1-01-01 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  |  |  | ' |  |  |  | '