## Nig Elect Liabil Mgt Ltd
MINISTRY/ AGENCY: NIGERIA ELECTRICITY LIABILITY MANAGEMENT LTD/GTE
BUDGET YEAR : 2011 PROCUREMENT PLAN
|  |  | BASIC DATA | [5 empty] | SPEC PROC NOTICE ADVERT | BIDING PERIOD |  | BID EVALUATION | [5 empty] | CONTRACT IMPLEMENTATION
Project Description | Package number | Lot No | Estimated Amount in Naira | Procurement Method | Post or Pre-qualification | Approval Threshold | Preparation & submission by MDA'S | MDA Approval | Advert for Prequalification | Bid Inviatation Date | Bid Opening-Closing | Submission of Bid Evaluation Report | MDA Approval/ BPP "NO OBJECTION" | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of goods | Inspection/Final Acceptance | Action Party | Champion
OFFICE START - UP:
- FURNITURE | NELMCO/GDS/2011/01 | LOT 1 | 42000000 | NCB | Pre- qualification | PTB | 7/FEB/11- 18/FEB/11 | 21/FEB/11-25/FEB/11 | 28/FEB/11-11/MAR/11 | 14/MAR/11- 25/MAR/11 | 28/MAR/11 - 6/MAY/11 | 9/MAY/11 - 27/MAY/11 | N/A | N/A | 30/MAY/11 - 3/JUNE/11 | 6/JUNE/11 - 10/JUNE/11 | N/A | 13/JUNE/11- 24/JUNE/11 | 27/JUNE/11 - 1/JULY/11 | BOARD/ MANAGEMENT | FACILITY MNGR
- EQUIPMENT | NELMCO/GDS/2011/02 | LOT 2 | 35000000 | NCB | Pre- qualification | PTB | 7/FEB/11- 18/FEB/11 | 21/FEB/11-25/FEB/11 | 28/FEB/11-11/MAR/11 | 14/MAR/11- 25/MAR/11 | 28/MAR/11 - 6/MAY/11 | 9/MAY/11 - 27/MAY/11 | N/A | N/A | 30/MAY/11 - 3/JUNE/11 | 6/JUNE/11 - 10/JUNE/11 | N/A | 13/JUNE/11- 24/JUNE/11 | 27/JUNE/11 - 1/JULY/11 | BOARD/ MANAGEMENT | FACILITY MNGR
- VEHICHLE | NELMCO/GDS/2011/03 | LOT 3 | 88000000 | NCB | Pre- qualification | MTB | 7/FEB/11- 18/FEB/11 | 21/FEB/11-25/FEB/11 | 28/FEB/11-11/MAR/11 | 14/MAR/11- 25/MAR/11 | 28/MAR/11 - 6/MAY/11 | 9/MAY/11 - 27/MAY/11 | N/A | N/A | 30/MAY/11 - 3/JUNE/11 | 6/JUNE/11 - 10/JUNE/11 | N/A | 13/JUNE/11- 24/JUNE/11 | 27/JUNE/11 - 1/JULY/11 | BOARD/ MANAGEMENT | MAIATENANCE OFFICER
- GENERATOR | NELMCO/GDS/2011/04 | LOT 4 | 10000000 | NCB | Pre- qualification | PTB | 7/FEB/11- 18/FEB/11 | 21/FEB/11-25/FEB/11 | 28/FEB/11-11/MAR/11 | 14/MAR/11- 25/MAR/11 | 28/MAR/11 - 6/MAY/11 | 9/MAY/11 - 27/MAY/11 | N/A | N/A | 30/MAY/11 - 3/JUNE/11 | 6/JUNE/11 - 10/JUNE/11 | N/A | 13/JUNE/11- 24/JUNE/11 | 27/JUNE/11 - 1/JULY/11 | BOARD/ MANAGEMENT | FACILITY MNGR
- COMPUTER/SOFTWARE | NELMCO/GDS/2011/05 | LOT 5 | 20000000 | NCB | Pre- qualification | PTB | 7/FEB/11- 18/FEB/11 | 21/FEB/11-25/FEB/11 | 28/FEB/11-11/MAR/11 | 14/MAR/11- 25/MAR/11 | 28/MAR/11 - 6/MAY/11 | 9/MAY/11 - 27/MAY/11 | N/A | N/A | 30/MAY/11 - 3/JUNE/11 | 6/JUNE/11 - 10/JUNE/11 | N/A | 13/JUNE/11- 24/JUNE/11 | 27/JUNE/11 - 1/JULY/11 | BOARD/ MANAGEMENT | INFO TECH OFFICER
- WEB-SITE DEVELOPMENT | NELMCO/SER/2011/06 | LOT 6 | 25000000 | NCB | Pre- qualification | PTB | 7/FEB/11- 18/FEB/11 | 21/FEB/11-25/FEB/11 | 28/FEB/11-11/MAR/11 | 14/MAR/11- 25/MAR/11 | 28/MAR/11 - 6/MAY/11 | 9/MAY/11 - 27/MAY/11 | N/A | N/A | 30/MAY/11 - 3/JUNE/11 | 6/JUNE/11 - 10/JUNE/11 | N/A | 13/JUNE/11- 24/JUNE/11 | 27/JUNE/11 - 1/JULY/11 | BOARD/ MANAGEMENT | INFO TECH OFFICER
- OFFICE PARTITION | NELMCO/WRK/2011/07 | LOT 7 | 35000000 | NCB | Pre- qualification | PTB | 7/FEB/11- 18/FEB/11 | 21/FEB/11-25/FEB/11 | 28/FEB/11-11/MAR/11 | 14/MAR/11- 25/MAR/11 | 28/MAR/11 - 6/MAY/11 | 9/MAY/11 - 27/MAY/11 | N/A | N/A | 30/MAY/11 - 3/JUNE/11 | 6/JUNE/11 - 10/JUNE/11 | N/A | 13/JUNE/11- 24/JUNE/11 | 27/JUNE/11 - 1/JULY/11 | BOARD/ MANAGEMENT | FACILITY MNGR
Consultancy and due dilligence on Assets and Liabilities and Pensions Verification and Actuary Services | NELMCO/CNS/2011/08 | LOT 8 | 525000000 | NCB | Pre- qualification | FEC | 7/FEB/11- 18/FEB/11 | 21/FEB/11-25/FEB/11 | 28/FEB/11-11/MAR/11 | 14/MAR/11- 25/MAR/11 | 28/MAR/11 - 6/MAY/11 | 9/MAY/11 - 27/MAY/11 | N/A | 30/MAY/11 - 10/JUNE/11 | 13/JUNE/11 -17/JUNE/11 | 20/JUNE/11 - 24/JUNE/11 | 10% | 27/JUNE/11 - 8/JULY/11 | II/JULY/11 - 13/JULY/11 | BOARD/ MANAGEMENT | MD
Pension Buy-out of PHCN Pensioners | NELMCO/SER/2011/09 | LOT 9 | 39620000000 | DIRECT SOURCING | N/A | FEC | 7/FEB/11- 18/FEB/11 | 21/FEB/11-25/FEB/11 | N/A | N/A | N/A | N/A | N/A | 30/MAY/11 - 10/JUNE/11 | 13/JUNE/11 -17/JUNE/11 | 20/JUNE/11 - 24/JUNE/11 | N/A | N/A | N/A | BOARD/ MANAGEMENT | MD
Liquidation of Liabilities & Legacy Debts of PHCN | NELMCO/SER/2011/10 | LOT 10 | 35923000000 | DIRECT SOURCING | N/A | FEC | 7/FEB/11- 18/FEB/11 | 21/FEB/11-25/FEB/11 | N/A | N/A | N/A | N/A | N/A | 30/MAY/11 - 10/JUNE/11 | 13/JUNE/11 -17/JUNE/11 | 20/JUNE/11 - 24/JUNE/11 | N/A | N/A | N/A | BOARD/ MANAGEMENT | MD
TOTAL |  |  | 76323000000

## Nig. Hydrological serv agency
PROCUREMENT PLAN: CONSULTANCY SERVICES
Ministry/Department/Agency: Nigeria Hydrological Services Agency - NIHSA
Budgetary Year: 2011 Capital Budget |  | If Post-Review, No-objection Dates are not needed |  |  |  |  | Request for Expression of Interest (when required)
Desk Officer/Contact #: John A. Shamonda (DG) |  | Contract Type |  |  | Preparation Request for Proposals |  |  |  | Short List |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [6 empty] | Contract Finalization |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | No-objection Date | FEC Approval | Contract Amount in Naira | Contract Offer | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks |  | 1- 2 wk | 2 wks
List of Contracts
National Hydrometric Network: Establishment of Hydrological Stations equipped with OTT-Duosens and Nimbus equipment for surface water monitoring - LOTA (Hydrological Area1&8)- Sokoto, Kano & Borno States | NCB (LCS) | LS | 7100310 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | C. O. Nze (AD) | F. T. Oyeniyi (HOD)
17-19 Feb/11
National Hydrometric Network: Establishment of Hydrological Stations equipped with OTT-Duosens and Nimbus equipment for surface water monitoring - LOTB (Hydrological Area 2, 3, & 4)-Niger,Kaduna, Katsina, & Bauchi States | NCB (LCS) | LS | 7887810 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | C. O. Nze (AD) | F. T. Oyeniyi (HOD)
17-19 Feb/11
National Hydrometric Network: Establishment of Hydrological Stations equipped with OTT-Duosens and Nimbus equipment for surface water monitoring - LOTC (Hydrological Area 5,6 & 7)-Ogun, Oyo, Osun, Anambra & Cross River States | NCB (LCS) | LS | 7887810 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | C. O. Nze (AD) | F. T. Oyeniyi (HOD)
17-19 Feb/11
National Hydrometric Network: National Primary Hydrological Network Assessment in Hydrological Area VI (West Littoral) | NCB (LCS) | LS | 13000000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | S. L. Mustapha | M. O. Beckley (HOD)
17-19 Feb/11
National Hydrometric Network: Nationwide Data Retrieval and Compilation project in Hydrological Area III (Upper Benue) | NCB (LCS) | LS | 11300000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | S. L. Mustapha | M. O. Beckley (HOD)
17-19 Feb/11
National Hydrometric Network: Publication of Hydrological Year Book | NCB (LCS) | LS | 9500000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  |  | P. A. Nlekwa (HOD)
17-19 Feb/11
National Hydrometric Network: Publication of Newsletters | NCB (LCS) | LS | 4600000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  |  | P. A. Nlekwa (HOD)
17-19 Feb/11
National Hydrometric Network: Publication of Scientific Bulletin | NCB (LCS) | LS | 6700000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  |  | P. A. Nlekwa (HOD)
17-19 Feb/11
National Hydrometric Network: Publication of Borehole Data Inventory | NCB (LCS) | LS | 7800000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  |  | P. A. Nlekwa (HOD)
17-19 Feb/11
National Hydrometric Network: Periodic Information Bulletin | NCB (LCS) | LS | 4000000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  |  | P. A. Nlekwa (HOD)
17-19 Feb/11
Niger Basin Authority/World Meteorological Organisation-assisted Hydroniger Project: Rehabilitation and installation of enamel gauge plates at the Niger-HYCOS stations on river Niger and Benue system (7 DCP Stations) | NCB (LCS) | LS | 8760000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11
17-19 Feb/11
River Discharge Measurement: River Discharge Measurement programme in Hydrological Area VII (East Littoral) | NCB (LCS) | LS | 7500000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | D. A. Amodu | M. O. Beckley (HOD)
17-19 Feb/11
Nationwide Sediment Yield Studies: Sediment Yield measurement/study in Hydrological Area V (Niger South) | NCB (LCS) | LS | 5000000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | D. A. Amodu | M. O. Beckley (HOD)
17-19 Feb/11
Floodplain Investigation/Studies: Flood plain investigation studies in Hydrological Area IV and V | NCB (LCS) | LS | 6000000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | S. A. Ayuba (DD) | F. T. Oyeniyi (HOD)
17-19 Feb/11
River Flow Studies and Flood Forecasting: Instrumentation of Oshun River Basin in HA VI | NCB (LCS) | LS | 6540000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | S. A. Ayuba (DD) | F. T. Oyeniyi (HOD)
17-19 Feb/11
Study of Special Catchment Areas: Provision and Installation of Remote (Real-time) Data Communication System | NCB (LCS) | LS | 32000000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  |  | P. Nlekwa (HOD)
17-19 Feb/11
Study of Water Resources of FCT: Inventory and Mapping of surface water bodies in the FCT | NCB (LCS) | LS | 8000000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  |  | P. Nlekwa (HOD)
17-19 Feb/11
Global Environment Facility (GEF) Project: Procurement and Installation of Automatic Weather Equipment at Sokoto (HAI) and Ilorin (HAII) | NCB (LCS) | LS | 8700000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  |  | P. Nlekwa (HOD)
17-19 Feb/11
Application of Isotope Hydrology Techniques: Determination of Groundwater geochemistry of the Coastal Plains Sand in HA V, LOT A (Awka-Enugu Axis) | NCB (LCS) | LS | 9300000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | S. M. Babarinde (AD) | P. Oburo (HOD)
17-19 Feb/11
Application of Isotope Hydrology Techniques: Determination of Groundwater geochemistry of the Coastal Plain Sand in HA V, LOT B (Asaba-Port-Harcourt Axis) | NCB (LCS) | LS | 9000000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | S. M. Babarinde (AD) | P. Oburo (HOD)
17-19 Feb/11
Hydrogeological Mapping: Preliminary Hydrogeological Data Collection of Hydrological Area V (HA V) | NCB (LCS) | LS | 20000000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | E. N. Agbor (AD) | G. O. Usifoh (HOD)
17-19 Feb/11
Hydrogeological Mapping: Production of Stratisgraphic Profile of Hydrological Area V (HA V) | NCB (LCS) | LS | 30000000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | E. N. Agbor (AD) | G. O. Usifoh (HOD)
17-19 Feb/11
Hydrogeological Mapping: Production of Hydrogeological Maps of Hydrological Area I (HA I) | NCB (LCS) | LS | 39000000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | E. N. Agbor (AD) | G. O. Usifoh (HOD)
17-19 Feb/11
Groundwater Monitoring: Drilling of groundwater monitoring borehole equipped with data logger in Port-Harcourt, Rivers State | NCB (LCS) | LS | 8500000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | E. N. Agbor (AD) | G. O. Usifoh (HOD)
17-19 Feb/11
Groundwater Monitoring: Drilling of groundwater monitoring borehole equipped with data logger in Yola, Adamawa State | NCB (LCS) | LS | 8500000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | E. N. Agbor (AD) | G. O. Usifoh (HOD)
17-19 Feb/11
Groundwater Monitoring: Drilling of groundwater monitoring borehole equipped with data logger in Asaba, Delta State | NCB (LCS) | LS | 8500000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | E. N. Agbor (AD) | G. O. Usifoh (HOD)
17-19 Feb/11
Groundwater Monitoring: Drilling of groundwater monitoring borehole equipped with data logger in Bida, Niger State | NCB (LCS) | LS | 8500000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | E. N. Agbor (AD) | G. O. Usifoh (HOD)
17-19 Feb/11
Groundwater Monitoring: | NCB (LCS) | LS | 7800000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | E. N. Agbor (AD) | G. O. Usifoh (HOD)
17-19 Feb/11
Saline water Intrusion Studies: Saline water intrusion studies in Gombe State | NCB (LCS) | LS | 9000000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | L. Mberede (DD) | G. O. Usifoh (HOD)
17-19 Feb/11
Saline water Intrusion Studies: Saline water intrusion studies in Rivers State | NCB (LCS) | LS | 9800000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | L. Mberede (DD) | G. O. Usifoh (HOD)
17-19 Feb/11
Nationwide Geophysical Investigations: Preliminary Hydrogeophysical Investigation of the Upper Benue Trough | NCB (LCS) | LS | 10000000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | A. A. Adedeji (AD) | P. Oburo (HOD)
17-19 Feb/11
Nationwide Geophysical Investigations: Instrumentation of Tubewells in Katsina State with OTT Orphimedes Data Loggers | NCB (LCS) | LS | 10000000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | A. A. Adedeji (AD) | P. Oburo (HOD)
17-19 Feb/11
National Borehole Data Inventory: Borehole data inventory in Edo State | NCB (LCS) | LS | 6700000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | L. Mberede (AD) | G. O. Usifoh (HOD)
17-19 Feb/11
National Borehole Data Inventory: Borehole data inventory in Delta State | NCB (LCS) | LS | 6700000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | L. Mberede (AD) | G. O. Usifoh (HOD)
17-19 Feb/11
Data Rescue: Procurement of Hardware & Software and Ancillary facilities for data management | NCB (LCS) | LS | 9000000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  |  | P. Nlekwa (HOD)
17-19 Feb/11
Hydrological Information Systems Networking (HYDRONET): Maintenance of Internet and Website | NCB (LCS) | LS | 5000000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | M. I. Nwabufo (DD) | P. Nlekwa (HOD)
17-19 Feb/11
Hydrological Information Systems networking (HYDRONET): Provision and Installation of hardware and Software and Ancillary facilities for Data Management | NCB (LCS) | LS | 5250000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | M. I. Nwabufo (DD) | P. Nlekwa (HOD)
17-19 Feb/11
Hydrological Information Systems Networking (HYDRONET): ICT Training on Website Design and Data Management | NCB (LCS) | LS | 3500000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11 |  | M. I. Nwabufo (DD) | P. Nlekwa (HOD)
17-19 Feb/11
Establishment of Eight Zonal Offices and Building of the Headquarters: Provision of Office equipment both at Headquarters and the eight (8) Zonal Offices in the eight (8) Hydrological Areas | NCB (LCS) | LS | 6000000 | PTB | 22Jan - 5Feb/11 | 19 - 26 Feb/11 | NA | NA | 1 - 14 Mar/11 | 14 - 21 Mar/11 | 1 - 14 Mar/11 | 1 - 14 Mar/11 | 14 - 28 Mar/11 | 28Mar - 4Apr/11 | 4 - 11Apr/11 | 11 - 18 Apr/11 | 18 - 25 Apr/11 | 25Apr - 2May/11 | NA |  | 2 - 16 May/11 | 16 - 30 May/11 | On demand | 30 Aug/11 | 30 Sep/11
17-19 Feb/11
Total Cost |  |  | 392325930

## Min Tourisim & Cul
Ministry/Department/Agency: (Ministry of Tourism and Culture) PRD Department
Budgetary Year: 2011 --- GOODS | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: Mike Anyebe 07037707801 |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
Annual Procurement Audit/Review Publication | 001 | 1 | BOQ | NCB | 4000000 | N/A | Post | 7th - 21st March | 7th - 21st March | 22nd Mar. '11 | 11th - 25th April | 2nd - 16th May |  |  |  | N/A |  |  | On Request
4000000
Ministry/Department/Agency: Culture Department
Ministry/Department/Agency: National Orientation
Budgetary Year: 2011 | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed |  |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Desk Officer/Contact: |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 3 wks
Norm Duration of Proc Steps |  |  |  |  | If Pre-qualification |  | 2 - 3 wks | 1 - 2 wks | 6wks | 6 wks | 6 wks
add 2 wks
List of Contracts
Purchase of Generating set in Kano State Cultural Centre | FMTC. 001 | N/A | 7000000 | NCB | N/A | N/A |  |  | 7th - 21st March | 7th - 21st March | 22nd Mar. '11 | 11th - 25th April | 2nd - 16th May |  | N/A | 23rd - 27th May | 30th May - 3rd June | On Request
Purchase of Generating set in Akwa Ibom State Cultural Centre | FMTC. 002 | N/A | 7000000 | NCB | N/A | N/A |  |  | 7th - 21st March | 7th - 21st March | 22nd March | 11th - 25th April | 2nd - 16th May |  | N/A | 23rd - 27th May | 30th May - 3rd June | On Request
Implementation of Cultural Policy | FMTC. 003 | N/A | 4000000 | NCB | N/A | N/A |  |  | 7th - 21st March | 7th - 21st March | 22nd March | 11th - 25th April | 2nd - 16th May |  | N/A | 23rd - 27th May | 30th May - 3rd June | On Request
Abuja Carnival | FMTC. 004 |  | 10000000
Total Cost |  |  | 28000000
Ministry/Department/Agency: Tourism Department | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Budgetary Year: 2011
Desk Officer/Contact: |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Pre-qualification |  | 2 - 3 wks | 1 - 2 wks | 6wks | 6 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
Organization of an Int'l Investment Summit on the Master Plan and a National Workshop for Stakeholders in Abuja and Lagos | N/A | N/A | 25000000 | NCB | N/A | N/A |  |  | 7th - 21st March | 7th - 21st March | 22nd Mar. '11 | 11th - 25th April | 2nd - 16th May |  | N/A | 23rd - 27th May | 30th May - 3rd June | On Request
Liaison/Consultation with State Governments where the Flagship Projects are located. | N/A | N/A | 50000000 | NCB | N/A | N/A |  |  | 7th - 21st March | 7th - 21st March | 22nd March | 11th - 25th April | 2nd - 16th May |  | N/A | 23rd - 27th May | 30th May - 3rd June | On Request
Capacity Building for Staff at UNWTO Headquarters and other Releveant Institutions | N/A | N/A | 10000000 | NCB | N/A | N/A |  |  | 7th - 21st March | 7th - 21st March | 22nd March | 11th - 25th April | 2nd - 16th May |  | N/A | 23rd - 27th May | 30th May - 3rd June | On Request
Study Tours of South Africa, Jamaica and Egypt on Best practices in the Implementation of Masterplan |  |  | 14000000
Monitoring and Evaluation |  |  | 10000000
Production of High Quality Investment Brochures |  |  | 10000000
Total Cost |  |  | 119000000
Ministry/Department/Agency: National Orientation Agency | [8 empty] | If Post-Review, No-objection Dates are not needed
Budgetary Year: 2011 | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN
Desk Officer/Contact: Remi Afolabi (Mrs) - 08037042130 |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Pre-qualification |  | 2 - 3 wks | 1 - 2 wks | 6wks | 6 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
Purchase of Computers for Headquarters & State Offices | N/A | N/A | 10000000 | NCB | N/A | N/A |  |  | 7th - 21st March | 7th - 21st March | 22nd Mar. '11 | 11th - 25th April | 2nd - 16th May |  | N/A | 23rd - 27th May | 30th May - 3rd June | On Request
Purchase of Air-Conditional | N/A | N/A | 6500000 | NCB | N/A | N/A |  |  | 7th - 21st March | 7th - 21st March | 22nd March | 11th - 25th April | 2nd - 16th May |  | N/A | 23rd - 27th May | 30th May - 3rd June | On Request
Purchase of Office Furniture for Headquarters & State Offices | N/A | N/A | 10000000 | NCB | N/A | N/A |  |  | 7th - 21st March | 7th - 21st March | 22nd March | 11th - 25th April | 2nd - 16th May |  | N/A | 23rd - 27th May | 30th May - 3rd June | On Request
Total Cost |  |  | 26500000
Ministry/Department/Agency: National Commission for Museum and Monuments
Budgetary Year: 2011 | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN
Desk Officer/Contact: Owolabi (Mrs) - 08033154914 |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 6wks | 6 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
Documentation and Conservation of Collections | N/A | N/A | 5000000 | NCB | N/A | N/A |  |  | 15th - 29th March | 15th - 29th March | 29th March | 4th - 18th April | N/A |  | N/A | 6th - 20th June | 26 July-13th August | On Request
Acquisition and Protection of Antiquities | N/A | N/A | 5000000 | NCB | N/A | N/A |  |  | 15th - 29th March | 15th - 29th March | 29th March | 4th - 18th April | N/A |  | N/A | 6th - 20th June | 26 July-13th August | On Request
Computeriation of Payroll in Jos, Lagos, Ibadan and Enugu. | N/A | N/A | 10000000 | NCB | N/A | N/A |  |  | 15th - 29th March | 15th - 29th March | 29th March | 4th - 18th April | N/A |  | N/A | 6th - 20th June | 26 July-13th August | On Request
International Museun Day Celebration | N/A | N/A | 5000000 | NCB | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A
School Outreach Programme and Sensitization Programme | N/A | N/A | 5000000 | NCB | N/A | N/A |  |  | 15th - 29th March | 15th - 29th March | 29th March | 4th - 18th April | N/A |  | N/A | 6th - 20th June | 26 July-13th August | On Request
Total Cost |  |  | 30000000
Ministry/Department/Agency: National Council for Art and Culture
Budgetary Year: 2011 | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact: Mohammad Mas'ud - 07039600566 |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 6wks | 6 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 2 wks
add 2 wks
List of Contracts
Purchase of Office Furnitutre and Equipment | NCAC/085 | IV | 8000000 | NCB | N/A | N/A | 1st - 15th Feb |  | 3rd - 17th March | 3rd - 17th March | 18th March | 21st - 1st April | 4th - 15th April |  | N/A | 6th - 13th May | 6th - 13th May | On Request
Total Cost |  |  | 8000000
Ministry/Department/Agency: Centre for Black and African Arts and Civilization (CBAAC)
Budgetary Year: 2011 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact: - 08033354332 |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 1 - 2wks | 1 - 2 wks | 6 wks | 2 wks | 1 - 2 wks | Plan
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Equipment for Preserving Black and African Arts, Treasure, Culture and Transparencies | 065060510010000 | I | 10000000 | NCB | N/A | N/A | Plan |  |  | 5th - 19th April | 2nd - 16th May | 16th May | 26th May - 10th June | 13th - 27th June | Plan
[7 empty] | Actual | [7 empty] | Actual
Augumentation of the Centre's Collection (Artworks, Artefacts and Archival Materials) | 065060510020000 | II | 10000000 | NCB | N/A | N/A | Plan |  |  | 5th - 19th April | 2nd - 16th May | 16th May | 26th May - 10th June | 13th - 27th June | Plan
[7 empty] | Actual | [7 empty] | Actual
Purchase of Books, Journals and Periodicals | 065060510030000 | III | 10000000 | NCB | N/A | N/A | Plan |  |  | 5th - 19th April | 2nd - 16th May | 16th May | 26th May - 10th June | 13th - 27th June | Plan
Actual
Hall of Fame - Equipping and Documentation of Honorees | 065060510040000 | IV | 30000000 | NCB | N/A | N/A | Plan |  |  | 5th - 19th April | 2nd - 16th May | 16th May | 26th May - 10th June | 13th - 27th June | Plan
Actual
Restoration and Rehabilitation of CBAAC Museum | 065060510050000 | V | 30000000 | NCB | N/A | N/A | Plan |  |  | 5th - 19th April | 2nd - 16th May | 16th May | 26th May - 10th June | 13th - 27th June | Plan
Actual
Equpping and Upgrading of CBAAC Studio - Transfer of Tapes to Digital Formats. | 065060510060000 | VI | 40000000 | NCB | N/A | N/A | Plan |  |  | 5th - 19th April | 2nd - 16th May | 16th May | 26th May - 10th June | 13th - 27th June
Actual
Hosting of International Conference and Publication of proceedings on black and African Arts and Culture | 065060510070000 | VII | 50000000 |  |  |  | Plan |  |  | 5th - 19th April | 2nd - 16th May | 16th May | 26th May - 10th June | 13th - 27th June
Actual
Purchase of Project Vehicles - Hilux, Hiace Bus and Toyota Avensis for Ile-Ife, Igbo-Ukwu, Lafia Outreach Centres | 065060510080000 | VIII | 30000000 |  |  |  | Plan |  |  | 5th - 19th April | 2nd - 16th May | 16th May | 26th May - 10th June | 13th - 27th June
Actual
Establishment/Equipping of Outreach Centres in Lafia and Sokoto | 065060510090000 | IX | 20000000 |  |  |  | Plan |  |  | 5th - 19th April | 2nd - 16th May | 16th May | 26th May - 10th June | 13th - 27th June
Actual
Total Cost |  |  | 230000000
Ministry/Department/Agency: National institute for Cultural Orientation (NICO)
Budgetary Year: 2011 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact: |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 6wks | 6 wks | 6 wks | 2 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 2 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Office Stationeries & Computer Consumables |  |  | 10000000 | NCB | 23rd May | 3rd June | Plan | [7 empty] | Plan |  | N/A
[7 empty] | Actual | [7 empty] | Actual
Teachnical Aids/Instruction Materials |  |  | 5000000 | NCB |  |  | Plan
Actual
Total Cost |  |  | 15000000
Ministry/Department/Agency: Human Resources Department
Budgetary Year: 2011 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact: Mr Okorodudu Uruemu |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 6wks | 6 wks | 6 wks | 2 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Purchase of Sports Equipment | N/A | N/A | 5000000 | NCB | N/A | N/A | Plan |  |  | 15th - 29th March | 15th - 29th March | 29th March | 4th - 18th April | N/A | Plan |  | N/A | 6th - 20th June | 26 July-13th August | On Request
[7 empty] | Actual | [7 empty] | Actual
Drugs & Medical Supplies | N/A | N/A | 4113425 | NCB | N/A | N/A | Plan |  |  | 15th - 29th March | 15th - 29th March | 29th March | 4th - 18th April | N/A | Plan |  | N/A | 6th - 20th June | 26 July-13th August | On Request
[7 empty] | Actual | [7 empty] | Actual
Sporting Activities | N/A | N/A | 2500000 | NCB | N/A | N/A | Plan |  |  | 15th - 29th March | 15th - 29th March | 29th March | 4th - 18th April | N/A | Plan |  | N/A | 6th - 20th June | 26 July-13th August | On Request
Actual
Security Services | N/A | N/A | 4000000 | NCB | N/A | N/A | Plan |  |  | N/A | N/A | N/A | N/A | N/A | Plan |  | N/A | N/A | N/A | N/A
Actual
Total Cost |  |  | 15613425
Ministry/Department/Agency: National Gallery of Art
Budgetary Year: 2011 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact: Mr Bello 08059855769 |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 6wks | 6 wks | 6 wks | 2 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
PURCHASE/ACQUISITION OF ART WORKS | N/A | N/A | 30000000 | NCB | N/A | N/A | Plan |  |  | 15th - 29th March | 15th - 29th March | 29th March | 4th - 18th April | N/A | Plan |  | N/A | 6th - 20th June | 26 July-13th August | On Request
[7 empty] | Actual | [7 empty] | Actual
PURCHASE OF UTILITY VEHICLES. | N/A | N/A | 17000000 | NCB | N/A | N/A | Plan |  |  | 15th - 29th March | 15th - 29th March | 29th March | 4th - 18th April | N/A | Plan |  | N/A | 6th - 20th June | 26 July-13th August | On Request
[7 empty] | Actual | [7 empty] | Actual
PURCHASE OF EXHIBITION TRUCKS. | N/A | N/A | 13000000 | NCB | N/A | N/A | Plan |  |  | 15th - 29th March | 15th - 29th March | 29th March | 4th - 18th April | N/A | Plan |  | N/A | 6th - 20th June | 26 July-13th August | On Request
Actual
PURCHASE OF COMPUTERS AND COMPUTER ACCESSORIES | N/A | N/A | 5000000 | NCB | N/A | N/A | Plan |  |  | N/A | N/A | N/A | N/A | N/A | Plan |  | N/A | N/A | N/A | N/A
Actual
PURCHASE OF COMPUTER PRINTERS | N/A | N/A | 3000000 | NCB | N/A | N/A | Plan |  |  | 15th - 29th March | 15th - 29th March | 29th March | 4th - 18th April | N/A | Plan |  | N/A | 6th - 20th June | 26 July-13th August | On Request
[7 empty] | Actual | [7 empty] | Actual
PURCHASE OF PHOTOCOPYING MACHINES | N/A | N/A | 10000000 | NCB | N/A | N/A | Plan |  |  | 15th - 29th March | 15th - 29th March | 29th March | 4th - 18th April | N/A | Plan |  | N/A | 6th - 20th June | 26 July-13th August | On Request
[7 empty] | Actual | [7 empty] | Actual
PURCHASE OF SHREDDING MACHINES | N/A | N/A | 500000 | NCB | N/A | N/A | Plan |  |  | 15th - 29th March | 15th - 29th March | 29th March | 4th - 18th April | N/A | Plan |  | N/A | 6th - 20th June | 26 July-13th August | On Request
Actual
PURCHASE OF SCANNERS | N/A | N/A | 2000000 | NCB | N/A | N/A | Plan |  |  | 15th - 29th March | 15th - 29th March | 29th March | 4th - 18th April | N/A | Plan |  | N/A | 6th - 20th June | 26 July-13th August | On Request
[7 empty] | Actual | [7 empty] | Actual
PURCHASE OF OFFICE FURNITURE | N/A | N/A | 2000000 | NCB | N/A | N/A | Plan |  |  | 15th - 29th March | 15th - 29th March | 29th March | 4th - 18th April | N/A | Plan |  | N/A | 6th - 20th June | 26 July-13th August | On Request
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  |  | 82500000
Federal Ministry of Tourism, Culture and National Orientation 2011 Procurement Plan WORKS
Ministry/Department/Agency: PRD Department
Budgetary Year: 2011 --- Works | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: Mike Anyebe 07037707801 |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Equipping of ICT Unit | 001 | 2 Lots | BOQ | NCB | 3000000 | N/A | Post | Plan | 7th - 21st March | 7th - 21st March | 22nd Mar. '11 | 11th - 25th April | 2nd - 16th May |  |  | Plan |  | N/A |  |  | On Request
[8 empty] | Actual | [7 empty] | Actual
Consultancy/Equipping of E-Library | 002 | 2 Lots | BOQ | NCB | 3000000 | N/A | Post | Plan | 7th - 21st March | 7th - 21st March | 22nd Mar. '11 | 11th - 25th April | 2nd - 16th May |  |  | Plan |  | N/A |  |  | On Request
[8 empty] | Actual | [7 empty] | Actual
Purchase of Library Equipment, Books and Journals | 003 | 2 Lots | BOQ | NCB | 8000000 | N/A | Post | Plan | 7th - 21st March | 7th - 21st March | 22nd Mar. '11 | 11th - 25th April | 2nd - 16th May |  |  | Plan |  | N/A |  |  | On Request
[8 empty] | Actual | [7 empty] | Actual
Maintenance of Computers and ICT Equipment | 004 | 2 Lots | BOQ | NCB | 3000000 | N/A | Post | Plan | 7th - 21st March | 7th - 21st March | 22nd Mar. '11 | 11th - 25th April | 2nd - 16th May |  |  | Plan |  | N/A |  |  | On Request
[8 empty] | Actual | [7 empty] | Actual
Interconnectivity/Computerization of the Ministry | 005 | 2 Lots | BOQ | NCB | 5000000 | N/A | Post | Plan | 7th - 21st March | 7th - 21st March | 22nd Mar. '11 | 11th - 25th April | 2nd - 16th May |  |  | Plan |  | N/A |  |  | On Request
[8 empty] | Actual | [7 empty] | Actual
ICT Capacity Building for Staff | 006 |  |  | NCB | 3000000 | N/A | Post | Plan | 7th - 21st March | 7th - 21st March | 22nd Mar. '11 | 11th - 25th April | 2nd - 16th May |  |  | Plan |  | N/A |  |  | On Request
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 25000000 |  |  | Plan
Ministry/Department/Agency: Culture Department | [10 empty] | If Within MDAs Thresholds, No-objection Dates not required
Budgetary Year: 2011 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN
Desk Officer/Contact #: |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Cultural Industry Project in Kano | FMTC.001 |  | BOQ | NCB | 35,000,00.00 | N/A | Post | Plan | 15th - 29th Mar | N/A | N/A | 19th Apr - 17th May | 17th May | 24th May - 7th June | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
Cultural Industry Project in Akwa Ibom State | FMTC.002 |  | BOQ | NCB | 35000000 | N/A | Post | Plan | 15th - 29th Mar | N/A | N/A | 19th Apr - 17th May | 17th May | 24th May - 7th June | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 70000000 |  |  | Plan | [7 empty] | Plan
Budgetary Year: 2011 Tourism Department | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact: |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Procurement of Project Vehicles (1No. SUV, and 1 No. 16 Seater Bus) |  |  | BOQ | NCB | 50000000 | N/A | Post | Plan | March | N/A | N/A | 7th June - 19th July | 19th July | 26th July - 8th Aug | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
Provision of Additional Items/Information Management System (ICT) Equipment in the Project Secretariat. |  |  | Lumpsum | NCB | 9000000 | N/A | Post | Plan | March | N/A | N/A | 7th June - 19th July | 19th July | 26th July - 8th Aug | N/A | Plan
Actual
Actual
Total Cost |  |  |  |  | 59000000 |  |  | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Budgetary Year: 2011 National Orientation Agency (NOA) | [10 empty] | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact: Remi Afolabi (Mrs) - 08037042130 |  | Basic Data | [6 empty] | Draft Bid Documents |  | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Renovation of Accommodation (Selected State Directorate Offices) |  |  | Lumpsum | NCB | 20000000 | N/A | Post | Plan | Feb | N/A | March
Actual
Total Cost |  |  |  |  | 20000000 |  |  | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Ministry/Department/Agency: National Commission for Museums and Monuments
Budgetary Year: 2011 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: Owolabi 08033154914 |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Restoration and Rehabilitation of National Monuments, Heritage and Sites | 001 | 1 | BOQ | NCB | 40000000 | N/A | Post | Plan | Feb | N/A | 14th Mar. - 4th Apr. '11 | 14th Mar. - 4th Apr. '11 | 4th Apr. 2011 | 11th - 25th Apr | N/A |  |  | N/A | 30th May - 6th June | 7th - 14th June | On Request
Actual
Archiological, Ethnographic and Research Projects | 002 | 2 | Lumpsum | NCB | 20000000 | N/A | Post | Plan |  |  | 14th Mar. - 4th Apr. '11 | 14th Mar. - 4th Apr. '11 | 4th Apr. 2011 | 11th - 25th Apr | N/A |  |  | N/A | 30th May - 6th June | 7th - 14th June | On Request
Actual
Prospecting Development Site for Listing in World Heritage | 003 | 3 | Lumpsum | NCB | 20000000 | N/A | Post | Plan |  |  | 14th Mar. - 4th Apr. '11 | 14th Mar. - 4th Apr. '11 | 4th Apr. 2011 | 11th - 25th Apr | N/A |  |  | N/A | 30th May - 6th June | 7th - 14th June | On Request
Actual
Actualisation and Restoration Motna | 004 | 4 | Lumpsum | NCB | 20000000 | N/A | Post | Plan |  |  | 6th Apr - 20th Apr. '11 | 6th Apr - 20th Apr. '11 | 4th Apr. 2011 | 11th - 25th Apr | N/A |  |  | N/A | 30th May - 6th June | 7th - 14th June | On Request
Actual
Conservation and Restoration of Two World Heritage Sites | 005 | 5 | Lumpsum | NCB | 10000000 | N/A | Post | Plan |  |  | 26th Apr. - 10th May. 11 | 26th Apr. - 10th May. 11 | 10th May. 2011 | 16th May - 6th June | N/A |  |  | N/A | 4th - 11th July | 12th - 19th July | On request
Actual
Winning more Heritage sites for Nigeria | 006 | 6 | Lumpsum | NCB | 20000000 | N/A | Post | Plan |  |  | 26th Apr. - 10th May. 11 | 26th Apr. - 10th May. 11 | 10th May. 2011 | 16th May - 6th June | N/A |  |  | N/A | 4th - 11th July | 12th - 19th July | On request
Actual
Institute of Archiology and Museums Studies | 007 | 7 | Lumpsum | NCB | 5000000 | N/A | Post | Plan |  |  | 26th Apr. - 10th May | 26th Apr. - 10th May | 10th May. 2011 | 16th May - 6th June | N/A |  |  | N/A | 4th - 11th July | 12th - 19th July | On request
Actual
Total Cost |  |  |  |  | 135000000
Ministry/Department/Agency: National Council for Arts and Culture
Budgetary Year: 2011 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: Mohammad Mas'ud - 07039600566 |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual
List of Contracts
National Research Centre or Textiles Traditions at Osogbo, Osun State | NCAC/932 | 1 |  | NCB | 5000000 | N/A | Post | Plan | Feb | N/A | 14th Mar. - 4th Apr. '11 | 14th Mar. - 4th Apr. '11 | 4th Apr. 2011 | 11th - 25th Apr | N/A |  | N/A | 30th May - 6th June | 7th - 14th June | On Request
Actual
National Research Centre on Boat Regatta in Uyo | NCA/935 | 2 |  | NCB | 10000000 | N/A | Post | Plan | Feb | N/A | 14th Mar. - 4th Apr. '11 | 14th Mar. - 4th Apr. '11 | 4th Apr. 2011 | 11th - 25th Apr | N/A |  | N/A | 30th May - 6th June | 7th - 14th June | On Request
Actual
Development of Crafts Centres a) Akwa Ibom b) Ikare c) Kano d) Sokoto | NCAC/085 | 3 |  | NCB | 49000000 | N/A | Post | Plan | Feb | N/A | 14th Mar. - 4th Apr. '11 | 14th Mar. - 4th Apr. '11 | 4th Apr. 2011 | 11th - 25th Apr | N/A |  | N/A | 30th May - 6th June | 7th - 14th June | On Request
Actual
Establishment of Cultural Village in Abuja | NCAC/953 | 5 |  | NCB | 42000000 | N/A | Post | Plan | Feb | N/A | 14th Mar. - 4th Apr. '11 | 14th Mar. - 4th Apr. '11 | 4th Apr. 2011 | 11th - 25th Apr | N/A
Actual
Development of National Research Centre on Durbar Traditions | NCAC/928 | 6 |  | NCB | 15000000 | N/A | Post | Plan | Feb | N/A | 14th Mar. - 4th Apr. '11 | 14th Mar. - 4th Apr. '11 | 4th Apr. 2011 | 11th - 25th Apr | N/A
Actual
Development of National Research Centre on Masqurade Traditions | NCAC/934 | 7 |  | NCB | 10000000 | N/A | Post | Plan | Feb | N/A | 14th Mar. - 4th Apr. '11 | 14th Mar. - 4th Apr. '11 | 4th Apr. 2011 | 11th - 25th Apr | N/A
Actual
Maintenance/Improvement of Herbal Garden of Indigenous Plant Speeches | NCAC/931 | 8 |  |  | 5000000 | N/A | Post | Plan | Feb | N/A | 14th Mar. - 4th Apr. '11 | 14th Mar. - 4th Apr. '11 | 4th Apr. 2011 | 11th - 25th Apr | N/A
Actual
Maintenance/Improvement of Lagos Craft Centre | NCAC/975 | 9 |  |  | 10000000 | N/A | Post | Plan | Feb | N/A | 14th Mar. - 4th Apr. '11 | 14th Mar. - 4th Apr. '11 | 4th Apr. 2011 | 11th - 25th Apr | N/A
Actual
Establishment of Herbal Garden of Indigenous Plant Speecies Project (a) Taraba (b) Enugu | NCAC/928 | 10 |  |  | 15000000 | N/A | Post | Plan | Feb | N/A | 14th Mar. - 4th Apr. '11 | 14th Mar. - 4th Apr. '11 | 4th Apr. 2011 | 11th - 25th Apr | N/A
Actual
Purchase of Audio-Visual and Library Equipment for Five Special Cultural Libraries |  | 11 |  |  | 11000000 | N/A | Post | Plan | Feb | N/A | 14th Mar. - 4th Apr. '11 | 14th Mar. - 4th Apr. '11 | 4th Apr. 2011 | 11th - 25th Apr | N/A
Actual
Development of NCAC Permanent Site, Headquarters Abuja |  | 12 |  |  | 10000000 | N/A | Post | Plan | Feb | N/A | 14th Mar. - 4th Apr. '11 | 14th Mar. - 4th Apr. '11 | 4th Apr. 2011 | 11th - 25th Apr | N/A
Actual
Establishment of National Herbal Garden of Indigenous Plants Speecies in Gombe State |  | 13 |  |  | 10000000 | N/A | Post | Plan |  | N/A
Actual
Total Cost |  |  |  |  | 192000000
Ministry/Department/Agency: Centre for Black and African Arts and Civilization (CBAAC)
Budgetary Year: 2011 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Total Cost |  |  |  |  | 384000000 |  |  | Plan
Ministry/Department/Agency: Centre for Black and African Arts Civilization (CBAAC)
Budgetary Year: 2011 | [10 empty] | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: 08033354332 |  | Basic Data | [7 empty] | Spec Proc Notice Advert |  |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
Building of Igbo-Ukwu Outreach Centre Office | 0650605100100000 | 10 |  | NCB | 20000000 | N/A | Post | Feb | N/A | March
Total Cost |  |  |  |  | 20000000
Ministry/Department/Agency: National Theatre
Budgetary Year: 2011 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
Purchase of Electronics/ICT & Sound Equipment for Hall |  |  |  | NCB | 30000000 | N/A | Post | Feb | N/A | 14th Mar. - 4th Apr. '11 | 14th Mar. - 4th Apr. '11 | 4th Apr. 2011 | 11th - 25th Apr | N/A |  | N/A | 30th May - 6th June | 7th - 14th June | On Request
Purchase of Lighting Equipment for Halls |  |  |  | NCB | 30000000 | N/A | Post | Feb | N/A | 14th Mar. - 4th Apr. '11 | 14th Mar. - 4th Apr. '11 | 4th Apr. 2011 | 11th - 25th Apr | N/A |  | N/A | 30th May - 6th June | 7th - 14th June | On Request
Rehabilitation: Purchase of office Furniture and Equipments |  |  |  | NCB | 50000000 | N/A | Post | Apr | N/A | N/A | 12th Apr. - 17th May. '11 | 17th May. 2011 | 24th May- 6th June | N/A |  | N/A | 7th - 14th June | 14th - 28th June | On Request
Rehabilitation: Purchase & Replacement of electrical Parts |  |  |  | NCB | 30000000 | N/A | Post | Feb | N/A | N/A | 12th Apr. - 17th May. '11 | 17th May. 2011 | 24th May- 6th June | N/A |  | N/A | 7th - 14th June | 14th - 28th June
Rehabilitation: Purchase of Sound Equipment (Mixers) for Banquet Hall & Cinema Hall 1 & 2 |  |  |  | NCB | 30000000 | N/A | Post | Feb | N/A | N/A | 12th Apr. - 17th May. '11 | 17th May. 2011 | 24th May- 6th June | N/A |  | N/A | 7th - 14th June | 14th - 28th June
Purchase of Two (2Nos) Professional Cinema Projectors |  |  |  | NCB | 40000000 | N/A | Post | Feb | N/A | N/A | 12th Apr. - 17th May. '11 | 17th May. 2011 | 24th May- 6th June | N/A |  | N/A | 7th - 14th June | 14th - 28th June
Rehabilitation: Purchase of Banquet chairs for Halls |  |  |  |  | 40000000 | N/A | Post | Feb | N/A | N/A | 12th Apr. - 17th May. '11 | 17th May. 2011 | 24th May- 6th June | N/A |  | N/A | 7th - 14th June | 14th - 28th June
Total Cost |  |  |  |  | 250000000
Ministry/Department/Agency: Culture Department |  |  |  | PROCUREMENT PLAN: CONSULTANCT SERVICES
Budgetary Year: 2011 |  | If Post-Review, No-objection Dates are not needed |  |  |  |  | Request for Expression of Interest (when required)
Desk Officer/Contact |  | Contract Type |  |  | Preparation Request for Proposals |  |  |  | Short List |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [6 empty] | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Prior/Post Review | Prep & Submission by MDAs | MDA'S Approval | Advertisement | Lead-time before shortlist | Submission Date | No-objection Date | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks |  | 4 wk |  | 3 wks
List of Contracts
Maintenance of Airstrips Across the Country
Perimeter Fencing of Airstrips
Provision of Basic Navigational Aids
Organising Capacity Building and Skills Acquisition in Two (2) States ( Kano and Akwa Ibom) |  |  | 35000000 | N/A
Total Cost |  |  | 35000000 | [16 empty] | 21059467 | [6 empty] | 21059467

## Min Sci Tech
Ministry/Department/Agency: Federal Ministry of Sicence and Technology (FMST)
Budgetary Year: 2011 --- GOODS
Desk Officer/Contact #:P.O CHENDO | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
|  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks | B.C UDEH | P.O CHENDO
[5 empty] | add 2 wks |  | Actual | [14 empty] | A. MBIBI
List of Contracts
COMPUTERISATION OF FMST | 1 | 23020118 | 50000000 | NCB | 1- 15 March | MTB | Plan | 16 March -5 April | 6- 12 April | 13 - 26 April | 27 April - 26 May | 26 May | 27 May - 10 June | 11- 17 June | 50000000 | 18 June - 4 July | 5th - 15th July | 16th - 30th July | 1st - 15 August | 16 Aug. - 15 Oct | 16 - 30 Oct | B.C UDEH | P.O CHENDO
[7 empty] | Actual | [14 empty] | A. MBIBI
ESTABLISHMENT OF COMPREHENSIVE DATABANK FOR NIGERIAN CONTRIBUTION TO SCIENCE, ENGINEERING AND TECHNOLOGY | 2 | 23020118 | 95000000 | NCB | NA | MTB | Plan | 1 - 15 March | 16 - 30 March | NA | 1 Apr. - 15 May | 15th May | 16 - 30 May | 1 - 8 June | 95000000 | NA | 9 - 25 June | 26 June - 5 July | NA | 6 July - 5 Aug. | 6 - 20 Aug. | B.C UDEH | P.O CHENDO
[7 empty] | Actual | [14 empty] | A. MBIBI
ESTABLISHMENT OF CENTRAL E-LIBRARY | 3 | 23020119 | 110000000 | NCB | NA | MTB | Plan | 1 - 15 March | 16 - 30 March | NA | 1 Apr. - 15 May | 15th May | 16 - 30 May | 1 - 8 June | 110000000 | NA | 9 - 25 June | 26 June - 5 July | NA | 6 July - 5 Aug. | 6 - 20 Aug. | B.C UDEH | P.O CHENDO
[7 empty] | Actual | [14 empty] | A. MBIBI
ESTABLISHMENT OF IJSO LABORATORY | 4 | 23020119 | 29705500 | NCB | NA | MTB | Plan | 1 - 15 March | 16 - 30 March | NA | 1 Apr. - 15 May | 15th May | 16 - 30 May | 1 - 8 June | 29705500 | NA | 9 - 25 June | 26 June - 5 July | NA | 6 July - 5 Aug. | 6 - 20 Aug. | B.C UDEH | P.O CHENDO
[7 empty] | Actual | [14 empty] | A. MBIBI
PRESIDENTIAL STANDING COMMITEE ON INVENTIONS AND INNOVATIONS | 5 | 23020119 | 300000000 | NCB | NA | MTB | Plan | 1 - 15 March | 16 - 30 March | NA | 1 Apr. - 15 May | 15th May | 16 - 30 May | 1 - 8 June | 300000000 | NA | 9 - 25 June | 26 June - 5 July | NA | 6 July - 5 Aug. | 6 - 20 Aug. | B.C UDEH | P.O CHENDO
[7 empty] | Actual | [14 empty] | A. MBIBI
Ministry/Department/Agency:FMST
Budgetary Year: 2011 --- WORKS
Desk Officer/Contact #:P.O CHENDO
[8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
|  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months |  | B.C UDEH | P.O CHENDO
[6 empty] | add 2 wks | [16 empty] | A. MBIBI
List of Contracts
ESTABLISHMENT OF SCIENCE AND TECHNOLOGY MUSEUM | 1 | 23020118 | BOQ | NCB | 143,830,000.00 | NA | MTB | 1 - 21 March | 22 Mar- 7 Apr. | NA | 8 Apr. - 20 May | 21 May | 22 May - 15 June | 16th - 30th June | 143,830,000.00 | NA | 1st - 15th July | 16 - 22 July | 23July - 6 Aug. | 7Aug - 7 Oct | 8 Oct - 8 Mar. '11 | 54,010,000 | B.C UDEH | P.O CHENDO
A. MBIBI
ESTABLISHMENT OF SCIENCE AND TEECHNOLOGY PARKS IN NIGERIA | 2 | 23020118 | BOQ | NCB | 260,500,000.00 | NA | MTB | 1 - 21 March | 22 Mar- 7 Apr. | NA | 8 Apr. - 20 May | 21 May | 22 May - 15 June | 16th - 30th June | 260,500,000.00 | NA | 1st - 15th July | 16 - 22 July | 23July - 6 Aug. | 7Aug - 7 Oct | 8 Oct - 8 Mar. '11 | 5,401,000 | B.C UDEH | P.O CHENDO
A. MBIBI

## Nat Uni Comm
Ministry/Department/Agency: National University Commission
Budgetory year: 2011 -- Works | [6 empty] | Draft Bid Doccuments, including specs and qty, draft SPN |  | If within MDAs Thresholds, No-objection dates not required
DESK Officer/Contact #: |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding period |  | Bid Evaluation |  |  | Contract finalisation |  |  |  | Contract Implementation
Project Description | Package No. | Lot No. | Estimated Amount in N | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-qualification | Bid Invitation Date | Bid Closing/ Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No objection" | Certifiable Amount per contract | FEC Approval | Date Contract offer | Date contract signature | Mobilisation Advance payment | Arrival of Goods | Inspection /Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If pre-qualification |  | 2-3 wks | 1-2 wks | 2 wks | 4-6 wks |  | 2 wks | 2-4 wks |  | 2 wks | 1-2 wks | 2 weeks | 2-3 wks | T | 2 wks
add 2 wks
List of Contracts
Assessment of Marbles resources of Kwara state |  |  | 9900000 | Field work
Geophysical survey of anomalous magnetic areas in sheet 101, Maska, Katsina state |  |  | 7495000 | Field work
Radiometric survey for uranium mineralisation in sheet 216 Monki, Taraba state |  |  | 4505000 | Field work
Radiometric survey for uranium mineralisation in sheet 200 Igboho, Oyo state |  |  | 8000000 | Field work
Gravity network survey of Anambra state |  |  | 11000000 | Field work
Core drilling for cobalt in Bauchi state |  |  | 10730680 | Field work
Core drilling for lead/zinc in Zamfara state |  |  | 10626300 | Field work
Study of adverse effect of waste dumps on ground water in Makurdi and its environs |  |  | 10000000 | Field work
Study of adverse effect of waste dumps on ground water in Katsina and its environs |  |  | 9500000 | Field work
Geotechnical mapping of Minna, Niger state |  |  | 10000000 | Field work
Geotechnical mapping of Osogbo, Osun state |  |  | 9500000 | Field work
Production of three (3) geological maps from the North-West zone on the scale of 1:50,000 |  |  | 8179000 | Field work
Production of three (3) geological maps from the South-West zone on the scale of 1:50,000 |  |  | 8179000 | Field work
Production of three (3) geological maps from the North-Central zone on the scale of 1:50,000 |  |  | 8179000 | Field work
Production of two (2) geological maps from the South-South zone on the scale of 1:50,000 |  |  | 5708000 | Field work
Production of two (2) geological maps from the North-East zone on the scale of 1:50,000 |  |  | 5708000 | Field work
Production of two (2) geological maps from the South-East zone on the scale of 1:50,000 |  |  | 5708000 | Field work
Subsurface mapping of geochemical hot spots in the coastal region of Lagos, Ondo, Delta, Bayelsa, Rivers, Akwa Ibom and Cross river state |  |  | 17037000 | Field work
Tidal and potential sea level rise effects on coastal ground water and surface water bodies of Lagos and Cross river state |  |  | 4536200 | Field work
Pollutant flushing potentials of tidal rivers: Calabar, Rivers South East Nigeria |  |  | 3250000 | Field work
Longavity assesment of coastal ground water quality of some Niger Delta rigional communities (Igbokoda, Warri, Ogbia, Ibeno and Anantigha |  |  | 4613000 | Field work
Procurement of field-work equipment and water quality kits |  |  | 2362000 | Field work
Training on acquatic survey safety and Boat mishop survival strategy |  |  | 2851800 | Field work
Community enlightenment and monitoring of erosion sites in Anambra and Imo States |  |  | 8923850 | Field work
Gully eroshing studies in Edo state |  |  | 10650536 | Field work
Gully eroshing studies in Gombe state |  |  | 9569536 | Field work
Repairs, re-installation and recalibration of atomic absorption spectrometer (AAS) and UV-visible |  |  | 3202200 | Field work
Training on geotechnical sample preparation and laboratory analysis techniques for site investigation |  |  | 3203800 | Field work
Course on principles and application methods of chromatographic analysis |  |  | 5147900 | Field work
TOTAL COST |  |  | 218265802
Ministry/Department/Agency: NATIONAL UNIVERSITIES COMMISSION
Budgetory year: 2011 --- Goods | [6 empty] | Draft Bid Doccuments, including specs and qty, draft SPN |  | If within MDAs Thresholds, No-objection dates not required
DESK Officer/Contact #: Rita Kenny-Ogwu (Mrs.) |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding period |  | Bid Evaluation |  |  | Contract finalisation |  |  |  | Contract Implementation
Project Description | Package No. | Lot No. | Estimated Amount in N | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission of Bid Docs. by MDAs | MDA Approval | Advertisement for Pre-qualification | Bid Invitation Date | Bid Closing/opening | Submission Bid Eval Rpt | MDA Approval/BPP "No objection" | Certifiable Amount per contract | FEC Approval | Date Contract offer | Date contract signature | Mobilisation Advance payment | Arrival of Goods | Inspection/Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If pre-qualification |  | 2-3 wks | 1-2 wks | 2 wks | 4-6 wks |  | 2 wks | 2-4 wks |  | 2 wks | 1-2 wks | 2 weeks | 2-3 wks | T | 2 wks
add 2 wks
List of Contracts
Extension of Office Block | 001 | On-going | 44497747 | National Competitive Bidding |  | Tenders Board | 14/02/11 | 21/02/11 | 28/02/11 | 28/02/11 | 14/03/11 | 28/03/11 | 04/04/11 | N/A | N/A | 11/04/11 | 11/04/11 | N/A | N/A | N/A | PPC | G.S. Division
Sandtex External Painting/General Internal Painting of the Secretariat Building and the associated works. | 002/1 | Lot 1 A | 22000000 | National Competitive Bidding |  | Tenders Board | 14/02/11 | 21/02/11 | 28/02/11 | 28/02/11 | 14/03/11 | 28/03/11 | 04/04/11 | N/A | N/A | 11/04/11 | 11/04/11 | N/A | N/A | N/A | PPC | G.S. Division
Provision of Solar Street Lights (Phase II) | 002/2 | Lot 1B | 5500000 | National Competitive Bidding |  | Tenders Board | 14/02/11 | 21/02/11 | 28/02/11 | 28/02/11 | 14/03/11 | 28/03/11 | 04/04/11 | N/A | N/A | 11/04/11 | 11/04/11 | N/A | N/A | N/A | PPC | G.S. Division
Replacement of Curtain Walls. | 002/3 | Lot 1C | 13000000 | Direct Procurement |  | Tenders Board | 14/02/11 | 21/02/11 | 28/02/11 | 28/02/11 | 14/03/11 | 28/03/11 | 04/04/11 | N/A | N/A | 11/04/11 | 11/04/11 | N/A | N/A | N/A | PPC | G.S. Division
General Upgrading of Furniture and Fittings in the Secretariat. | 002/4 | Lot 1D | 12384800 | National Competitive Bidding |  | Tenders Board | 14/02/11 | 21/02/11 | 28/02/11 | 28/02/11 | 14/03/11 | 28/03/11 | 04/04/11 | N/A | N/A | 11/04/11 | 11/04/11 | N/A | N/A | N/A | PPC | G.S. Division
Procurement of Airtime for the Voyage of Discovery Programme and Production Cost. | 003 | On-going | 14039478 | National Competitive Bidding |  | Tenders Board | 14/02/11 | 21/02/11 | 28/02/11 | 28/02/11 | 14/03/11 | 28/03/11 | 04/04/11 | N/A | N/A | 11/04/11 | 11/04/11 | N/A | N/A | N/A | PPC | G.S. Division
Monitoring of Capital Grant | 004 | On-going | 17549348 |  |  | Tenders Board
Procurement of Office Furniture (Office Extension) | 005 | Lot 2 | 15019739 | National Competitive Bidding |  | Tenders Board | 14/02/11 | 21/02/11 | 28/02/11 | 28/02/11 | 14/03/11 | 28/03/11 | 04/04/11 | N/A | N/A | 11/04/11 | 11/04/11 | N/A | N/A | N/A | PPC | G.S. Division
Procurement of Electronic Books and Journals | 006 | Lot 3 | 14039478 | National Competitive Bidding |  |  | 14/02/11 | 21/02/11 | 28/02/11 | 28/02/11 | 14/03/11 | 28/03/11 | 04/04/11 | N/A | N/A | 11/04/11 | 11/04/11 | N/A | N/A | N/A | PPC | ICT Division
TOTAL COST |  |  | 158030590

## Min Agric_Rural Dev.
Federal Ministry of Agriculture
Procurement--- GOOD
MINISTRY/DEPT/AGENCY: Rural Access and Mobility Project (RAMP), Federal Ministry of Agriculture and Water Resources (FMAWR)
Budgetary Year: 2010 | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Nm | Procurement Method | Pre-or Post Qualification | Approval Threshold | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection(MTB Approval) Date | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
Procurement of 2No Project Vehicles | Package 1 | Lot 1 | 10.4 | NCB | Post qualification | MTB | Not Required | Not Required | Not Required | 1-June-10 | 30-June-10 | Not Required | 26-July-10 | 10.4 | Not Required | 29-July-10 | 5-Aug-10 | Not Required | 3-Sept-10 | 10-Sept-10
Total Cost |  |  | 10.40 | [10 empty] | 10.4
Total Cost | [13 empty] | 0.00
Ministry/Department/Agency: Federal Department of Agriculture - FDA
Budgetary Year: 2011 | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
Animal Traction and Hand tools technology. Procurement of 100 units and animal drawn plough
| 1 | A1 | 2000000 | National Competitive Bidding (NCB) |  |  | 21/2/2011 | 4/3/2011 |  | 15/3/2011 | 22/3/2011 | 30/3/2011 | 8/4/2011 | 2000000 | N/A | 30/4/2011 |  | `'' | 30/6/2011
(iI) Procurement of 100 units of animal drawn planter
| 2 | A2 | 2000000 | National Competitive Bidding (NCB) |  |  | 5/2/2011 | 28/2/2011 |  | 10/3/2011 | 21/3/2011 | 30/3/2011 | 5/4/2011 | 2000000 | N/A | 30/4/2011 |  |  | 29/6/2011
Development of Institutional Support for Agricultural Mechanization: (i) Procurement of assorted office equipment and training materials for AMMOTRAC Misau, Bauchi State
| 3 | B1 | 2000000 | National Competitive Bidding (NCB) |  |  | 5/2/2011 | 28/2/2011 |  | 10/3/2011 | 21/3/2011 | 30/3/2011 | 5/4/2011 | 2000000 | N/A | 30/4/2011 |  |  | 29/6/2011
(ii) Procurement of assorted office equipment and training materials for AMMOTRAC Akure, Ondo State
| 4 | B2 | 2000000 | National Competitive Bidding (NCB) |  |  | 5/2/2011 | 28/2/2011 |  | 7/3/2011 | 17/3/2011 | 30/3/2011 | 7/4/2010 | 2000000 | N/A | 30/4/2011 |  |  | 30/6/2011
(iii) Procurement of 2 No tractor mounted slasher for the 2 AMMOTRAC centres at Misau and Akure
| 5 | B3 | 2000000 | National Competitive Bidding (NCB) |  |  | 5/2/2011 | 28/2/2011 |  | 10/3/2011 | 21/3/2011 | 30/3/2011 | 5/4/2011 | 2000000 | N/A | 30/4/2011 |  |  | 29/6/2011
Procurement of Desktop /Laptops computers, computer Accessories, Printers, Fan, Scanner, Photocopiers Bookselve, External DVD Cdrom Drive,( 1, 2, 3) seater chairs for office of the project at the Headquarters
| 6 | B4 | 3000000 | National Competitive Bidding (NCB) |  |  | 5/2/2011 | 28/2/2011 |  | 7/3/2011 | 17/3/2011 | 30/3/2011 | 7/4/2010 | 3000000 | N/A | 30/4/2011 |  |  | 30/6/2011
Employment Generation in Mechanization Technology: Procurement of assorted equipment and materials for Blacksmiths and Artisans Training Centre (BATSU) Ilorin
| 7 | C5 | 2000000 | National Competitive Bidding (NCB) |  |  | 28/2/2010 | 28/2/2010 |  | 30/3/2010 | 30/3/2010 | 30/4/2010 | 30/4/2010 | 2000000 | N/A | 31/5/2010 |  |  | 31/5/2010
Procurement of treadle pumps for distribution to farmers for dry season vegetable production
| 7 | C6 | 6000000 | National Competitive Bidding (NCB) |  |  | 28/2/2010 | 28/2/2010 |  | 30/3/2010 | 30/3/2010 | 30/4/2010 | 30/4/2010 | 6000000 | N/A | 31/5/2010 |  |  | 31/5/2010
Post-Harvest loss prevention technology: (i) Procurement of assorted office equipment and training materials for crop storage unit
| 8 | D1 | 1000000 | National Competitive Bidding (NCB) |  |  | 3/3/2011 | 30/3/2011 |  | 3/4/2011 | 17/4/2011 | 31/5/2011 | 1/6/2010 | 1000000 | N/A | 30/6/2011 |  |  | 30/10/2011
(ii) Fabrication of improved fish smoking cabinet 20 No. in demand
| 9 | D2 | 2000000 | National Competitive Bidding (NCB) |  |  | 2/2/2010 | 28/2/2010 |  | 3/3/2010 | 17/3/2010 | 30/3/2010 | 1/4/2010 | 2000000 | N/A | 30/6/2010 |  |  | 30/10/2010
Total Cost
|  | =C9+C12+C15+C18+C21+CB3424+C27+C30+C33 | 24000000 | [10 empty] | 24000000
Tropical Fruits
i) Production and supply of 1,000Kg Hybrid (Premium) tomato seeds of rec. cvs by The Seed Project Company, Kano @ N25,000.00/Kg in collaboration with FDA to establish 2,000ha at 500gram/ha. |  | A1 | 25000000 | Reprocurement |  |  | 2011-02-05 | 14/5/2011 |  | 2011-03-06 | 14/6/2011 | 30/6/2011 | 30/6/2011 | 25000000 | NA | 14/7/2011 |  |  | 30/9/2011 | 30/9/2011
ii) Production and supply of 620Kg Hybrid (Elite) pepper seeds of rec. cvs by The Seed Project Company, Kano @ N25,000.00/Kg in collaboration with FDA to establish 1,240ha at 500gram/ha. |  | A2 | 15100000 | Reprocurement |  |  | 14/4/2011 | 28/4/2011 |  | 2011-02-05 | 14/5/2011 | 28/5/2011 | 28/5/2011 | 15100000 | NA | 2011-02-06 |  |  | 14/6/2011 | 14/6/2011
iii) Production and supply/distribution of 25,000 grafted elite mango seedlings @ N800.00/seedling by certified nursery operators (COA, Yandev & Ilikub Ventures, Zaria) in collaboration with FDA to establish 250ha at 100 seedlings/ha |  | A3 | 20000000 | Reprocurement |  |  | 14/4/2011 | 28/4/2011 |  | 2011-02-05 | 14/5/2011 | 28/5/2011 | 28/5/2011 | 20000000 | NA | 2011-02-06 |  |  | 14/6/2011 | 14/6/2011
iv) Production and supply/distribution of 40,000 budded citrus seedlings @ N600.00/seedling by certified nursery operators (COA, Yandev & Na'Allah Ferm, Lafia) in collaboration with FDA to establish 196ha at 204 seedlings/ha |  | A4 | 24000000 | Reprocurement |  |  | 14/4/2011 | 28/4/2011 |  | 2010-02-05 | 14/5/2011 | 28/5/2011 | 28/5/2011 | 24000000 | NA | 2011-02-06 |  |  | 14/6/2011 | 14/6/2011
v) Production and supply/distribution of 50,000 MD Series of pineapple suckers @ N400.00/sucker by certified nursery operators (ECU Ventures) in collaboration with FDA to establish 1.25ha at 40,000 suckers/ha |  | A5 | 2000000 | Reprocurement |  |  | 14/4/2010 | 28/4/2011 |  | 2011-02-05 | 14/5/2011 | 28/5/2011 | 28/5/2011 | 2000000 | NA | 2011-02-06 |  |  | 14/6/2011 | 14/6/2011
vi) Procurement and supply of 50tons of organic fertilizers for vagetable crops by Bonty Properties Limited, Suleja @ N120/Kg. |  | A6 | 6000000 | Procurement |  |  | 14/4/2011 | 28/4/2011 |  | 2011-02-05 | 14/5/2011 | 28/5/2011 | 28/5/2011 | 6000000 | NA | 2011-02-06 |  |  | 14/6/2011 | 14/6/2011
vii) Procurement and supply of 2,500litres of insecticides for vegetable production @ N2,500/litre |  | A7 | 6250000 | Procurement |  |  | 14/4/2011 | 28/4/2011 |  | 2011-02-05 | 14/5/2011 | 28/5/2011 | 28/5/2011 | 6250000 | NA | 2011-02-06 |  |  | 14/6/2011 | 14/6/2011
viii) Procurement and supply of 2,500Kg of fungicides for vegetable production @ N2,500/litre |  | A8 | 6250000 | Procurement |  |  | 14/4/2012 | 28/4/2012 |  | 2011-02-05 | 14/5/2011 | 28/5/2011 | 28/5/2011 | 6250000 | NA | 2011-02-06 |  |  | 14/6/2011 | 14/6/2011
ix) Procurement and supply of 2,500litres of nematicides for vegetable production @ N2,500/litre |  | A9 | 6250000 | Procurement |  |  | 14/4/2013 | 28/4/2013 |  | 2011-02-05 | 14/5/2011 | 28/5/2011 | 28/5/2011 | 6250000 | NA | 2011-02-06 |  |  | 14/6/2011 | 14/6/2011
Total |  |  | 110850000 | [10 empty] | 110850000
Oil Palm
i). Production of 100,000 improvedtenera oil palm seedlings @ N280.00 each to plant 666.67ha by public (NIFOR) and certified nursery operators for distribution to farmers in Edo, Imo and Benue Sttates. |  | A1 | 28.0m | Direct Implementation |  |  | 2011-05-02 | 19/2/2011 |  | 2011-03-06 | 14/6/2011 | 30/6/2011 | 30/6/2011 | 28.0m | NA | N/A |  |  | 30/9/2011 | 30/9/2011
Total |  |  | 28000000 | [10 empty] | 28000000
RUBBER
i). Production of 40,000 improved rubber budded stumps capable of planting 88ha at N140 each for distribution to Delta, Abia and Ondo States. |  | A1 | 5600000 | Direct Implementation |  |  | 2011-02-05 | 14/5/2011 |  | 2011-03-06 | 14/6/2011 | 30/6/2011 | 30/6/2011 | 5600000 | NA | 14/7/2011 |  |  | 30/9/2011 | 30/9/2011
ii) Procurement of 1000 litre of glyphosate at N3,000/litre |  | A2 | 3000000 | National Competitive Bidding (NCB) |  |  | 14/4/2011 | 28/4/2011 |  | 2011-02-05 | 14/5/2011 | 28/5/2011 | 28/5/2011 | 3000000 | NA | 2011-02-06 |  |  | 14/6/2011 | 14/6/2011
iii). Procurement of 1000litres of ethrel at N3,000/ltr. |  | A3 | 3000000 | National Competitive Bidding (NCB) |  |  | 14/4/2011 | 28/4/2011 |  | 2011-02-05 | 14/5/2011 | 28/5/2011 | 28/5/2011 | 3000000 | NA | 2011-02-06 |  |  | 14/6/2011 | 14/6/2011
Total |  |  | 11600000 | [10 empty] | 11600000
COCOA
i). Raising of 135,500 seedlings of cocoa at N100/seedling |  | A1 | 13550000 | Direct Implementation |  |  | 2011-02-05 | 14/5/2011 |  | 2011-03-06 | 14/6/2011 | 30/6/2011 | 30/6/2011 | 13550000 | NA | 14/7/2011 |  |  | 30/9/2011 | 30/9/2011
ii) Production of 200 fermentation boxes at N10,000/box. |  | A2 | 2000000 | National Competitive Bidding (NCB) |  |  | 14/4/2011 | 28/4/2011 |  | 2011-02-05 | 14/5/2011 | 28/5/2011 | 28/5/2011 | 2000000 | NA | 2011-02-06 |  |  | 14/6/2011 | 14/6/2011
iii). Fabrication of 44 solar dryers at N80,000/unit. |  | A3 | 3520000 | National Competitive Bidding (NCB) |  |  | 14/4/2011 | 28/4/2011 |  | 2011-02-05 | 14/5/2011 | 28/5/2011 | 28/5/2011 | 3520000 | NA | 2011-02-06 |  |  | 14/6/2011 | 14/6/2011
iv) Procurement of 1,428 sachets fungoran-OH @ N350/sachet |  | A4 | 5000000 |  |  |  | 2011-02-05 | 14/5/2011 |  |  | 14/6/2011 |  | 30/6/2011 | 5000000 |  | 14/7/2011 |  |  | 30/9/2011 | 30/9/2011
v) Procurement of 16,667 sachets Actara @ N150/sachet |  | A5 | 2500000 |  |  |  | 2011-02-06 | 14/5/2011 |  |  | 14/6/2011 |  | 30/6/2011 | 2500000 |  | 14/7/2011 |  |  | 30/9/2011 | 30/9/2011
Total |  |  | 26570000 | [10 empty] | 26570000
MEDICINAL PLANTS
i). Production and Supply of 31,160 Artemisia annua seedlings @ N300/seedling to plant 31.16ha at 1000seedlings/ha. |  | A1 | 9348000 | Direct Implementation |  |  | 2011-02-05 | 14/5/2011 |  | 2011-03-06 | 14/6/2011 | 30/6/2011 | 30/6/2011 | 9348000 | NA | 14/7/2011 |  |  | 30/9/2011 | 30/9/2011
ii) Production and Supply of 25,000 Moringa oleifera seedlings @ N300/seedling to plant 61.3ha at 408seedling/ha. |  | A2 | 7500000 | Direct Implementation
iii) Bush clearing and fencing of 18ha progeny/ nursery garden with Concrete pillers and barb wire loops on top in Katsina. |  | A3 | 3288035 | Procurement |  |  | 2011-02-05 | 14/5/2011 |  | 2011-03-06 | 14/6/2011 | 30/6/2011 | 30/6/2011 | 3288035 | NA | 14/7/2011 |  |  | 30/9/2011 | 30/9/2011
iv) Site clearing & perimeter fencing of 1ha company's land at FCT Permanent Site with concrete blocks and barb wire loops on top. |  | A4 | 3900000 | Procurement |  |  | 2011-02-05 | 14/5/2011 |  | 2011-03-06 | 14/6/2012 | 30/6/2011 | 30/6/2011 | 3900000 | NA | 14/7/2011 |  |  | 14/6/2010 | 14/6/2010
v) Sinking of 2nos. Boreholes, 2nos. 5,000ltr steel overhead tanks and water reticulation for irrigation during dry season farming in Katsina. |  | A5 | 4382500 | Construction |  |  | 2011-02-05 | 14/5/2011 |  | 2011-03-06 | 14/6/2013 | 30/6/2011 | 30/6/2011 | 4382500 | NA | 14/7/2011 |  |  | 14/6/2010 | 14/6/2010
vi) Construction of shed for drying, storage facilities and toilets for convinience of workers. |  | A6 | 2742607 | Construction |  |  | 2011-02-05 | 14/5/2011 |  | 2011-03-06 | 14/6/2014 | 30/6/2011 | 30/6/2011 | 2742607 | NA | 14/7/2011 |  |  | 14/6/2010 | 14/6/2010
Total |  |  | 31161142 | [10 empty] | 31161142
TROPICAL FRUITS VODEP
i). Production and Supply of 1,000Kg Hybrid (Premium) tomato seeds of rec. cvs by The Seed Project Company, Kano @ N25,000.00/Kg in collaboration with FDA to establishe 2,000ha at 500g/ha. |  | A1 | 25000000 | Reprocurement |  |  | 2011-02-05 | 14/5/2011 |  | 2011-03-06 | 14/6/2011 | 30/6/2011 | 30/6/2011 | 25000000 | NA | 14/7/2011 |  |  | 30/9/2011 | 30/9/2011
i). Production and Supply 620Kg Hybrid (Elite) Pepper seeds of rec. cvs by The Seed Project Company, Kano @ N25,000.00/Kg in collaboration with FDA to establish 1,240ha at 500g/ha. |  | A2 | 15100000 | Reprocurement |  |  | 2011-02-05 | 14/5/2011 |  | 2011-03-06 | 14/6/2011 | 30/6/2011 | 30/6/2011 | 15100000 | NA | 14/7/2011 |  |  | 30/9/2011 | 30/9/2011
iii). Production and Supply/Distribution of 25,000grafted elite mango seedlings @ N800/seedling by Certified nursery operator (COA, Yandev & Ilikub Ventures, Zaria) in collaboration with FDA to establish 250ha at 100seedlings/ha. |  | A3 | 20000000 | Reprocurement |  |  | 2011-02-05 | 14/5/2011 |  | 2011-03-06 | 14/6/2012 | 30/6/2011 | 30/6/2011 | 20000000 | NA | 14/7/2011 |  |  | 14/6/2010 | 14/6/2010
iv). Production and Supply/Distribution of 40,000 budded citrus seedlings @ N600/seedling by Certified nursery operator (COA, Yandev & Na'Allah Farm, Lafia) in collaboration with FDA to establish 196ha at 204seedlings/ha. |  | A4 | 24000000 | Reprocurement |  |  | 2011-02-05 | 14/5/2011 |  | 2011-03-06 | 14/6/2013 | 30/6/2011 | 30/6/2011 | 24000000 | NA | 14/7/2011 |  |  | 14/6/2010 | 14/6/2010
v) Production and Supply/Distribution of 50,000 MD Series pineapple suckers @ N400/sucker by Certified nursery operator (ECU Ventures) in collaboration with FDA to establish 1.25ha at 40,000 suckers/ha. |  | A5 | 2000000 | Reprocurement |  |  | 2011-02-05 | 14/5/2011 |  | 2011-03-06 | 14/6/2014 | 30/6/2011 | 30/6/2011 | 2000000 | NA | 14/7/2011 |  |  | 14/6/2010 | 14/6/2010
vi) Procurement and supply of 50 tons of organic fertilizers for vegetable crops by Bonty Properties Limited, Suleja @ N120/Kg |  | A6 | 6000000 | Procurement |  |  | 14/4/2010 | 28/4/2010 |  | 2010-02-05 | 14/5/2010 | 28/5/2010 | 28/5/2010 | 6000000 | NA | 2010-02-06 |  |  | 14/6/2010 | 14/6/2010
vii) Procurement and supply of 2,500ltrs of insecticides for vegetable production @ N2,500/ltr. |  | A7 | 6250000 | Procurement | [9 empty] | 6250000
viii) Procurement and supply of 2,500ltrs of fungicides for vegetable production @ N2,500/ltr. |  | A8 | 6250000 | Procurement
ix) Procurement and supply of 2,500ltrs of nematicides for vegetable production @ N2,500/ltr. |  | A9 | 6250000 | Procurement
Total |  |  | 110850000 | [10 empty] | 110850000
Community Mobilization
Production and Promotion of 1,184No. Briquette Stoves
|  |  | 5920000 |  |  |  | 14/3/2011 | 4/4/2011 | [5 empty] | 6750000 | NA |  | 9/05/2011 |  | 6/06/2011 | 6/06/2011
date
Establishment of National Rural Sector Data Bank and Strategic Reference Centre | [6 empty] | 14/3/2011 | 4/4/2011 | [5 empty] | 3000000 | NA |  | 3/05/2011 |  | 3/05/2011 | 3/05/2011
3000000
Total
|  |  | 8920000 | [10 empty] | 9750000
CEREALS
Medium Scale Cash Crop Development Pro -gramme (Cotton, Cassaca, Oilpalm, Rubber, Cocoa & Sesame): The programme is aimed at boosting the production of cash crops to a level of self sufficiency to achieve growth in the agro-industrial sector
i) Production and buyback 261tons of 4 classes of premium cotton seeds from IAR/Seed Companies | [6 empty] | 31/12/2011 | 15/2/2011 |  |  |  |  | 28/2/2011 | 11,650,000
| 1 | A1 | 11650000 | Direct | Post | Post | [7 empty] | 11,650,000 |  | 28/2/2011 | 21/3/2011 |  | 30/1/2012 | 15/2/2012
Production and buyback of 34,000bundles of cassava by RTEP | [12 empty] | 28/2/2011 | 19,000,000 |  | 28/2/2011 | 21/3/2011 |  | 28/2/2012 | 15/3/2012
| 2 | B1 | 19000000 | Direct | Post | Post | [7 empty] | 19,000,000
Procurement of 29,000 litres of pesticides and 18,095 sachets of seed dressing chemicals for cotton.. | [13 empty] | 27,500,000 |  | 28/2/2011 | 21/3/2011 |  | 20/5/2011 | 1/6/2011
| 6 | F | 27500000 | Advert | Post | Post |  | 15/2/2011 | 28/2/2011 | 1/3/2011 | 8/4/2011 | 22/4/2011 | 6/5/2011 | 27,500,000
FOOD CROPS DEVELOPMENT PROGRAMME (CEREALS, PULSES,FRUIT TREES, ROOTS/TUBER & VEGETABLES) :The programme is aimed at boosting the production of food crops to a level of self sufficiency to achieve growth in the agro-industrial sector, improve level of employment and generate surplus for export.
date
SEED PROCUREMENT (Certified) A. CEREALS: i) 144.65tons of OPV maize. ii) 47.32tons of millet seeds iii) 41.6tons of sorghum seeds iv) 38tons of wheat seed v) 183.6tons of rice seed | [13 empty] | 145060000 |  | 28/2/11 |  |  | 30/1/12 | 15/2/12
| 1.1 - 1.5 | A1 |  | DIRECT | POST | POST | 31/1/11 | 15/2/11 |  |  |  | 28/2/11
B. LEGUMES i) 47.67tons of groundnut seeds ii) 40.56tons of cowpea seeds iii) 50.31tons of soyabean seeds. | [13 empty] | 44.,060,000 |  | 28/2/11 |  |  | 30/1/12 | 15/2/12
| 1.6 - 1.8 | B1 |  | DIRECT | POST | POST
C. CUTTINGS: i) 1.3m yam minisetts ii) 30,000 bundles of sweet potato vines iii) 360tons of potato seeds | [13 empty] | 64500000 |  | 28/2/11 |  |  | 30/3/12 | 15/4/12
| 1.9 - 1.11 | C1 |  | DIRECT | POST | POST
INPUTS: A. PESTICIDES: i) 1,000 buckets of Aflasafe for maize ii) 23,500 litres of assorted agrochemicals for groundnut, soyabeans, cowpea, maize, millet, sorghum, wheat, potato, and 215tons of fungicides and 50tons of organic fertilizer. | [6 empty] | 15/2/11 | 28/2/11 |  |  |  | 28/2/11 |  | 64250000 |  | 28/2/11 | 21/3/11 |  | 30/1/12 | 15/2/12
| 2.1 - 2.2 | E1 |  | DIRECT | POST | POST
B. EQUIPMENT i) 40 units of water pumps ii) 36 units of groundnut motorized shellers iii) 10 units of groundnut oil extracting machines iv) 4 units of motorized cowpea shellers v) 5 units of soyabean threshing machines. | [6 empty] | 15/2/11 | 28/2/11 |  |  |  | 28/2/11 |  | 16900000 |  | 28/2/11 | 21/3/11 |  | 30/1/12 | 15/2/12
| 2.3 - 2.7 | F1 |  | DIRECT | POST | POST
Total Cost |  |  | 0 | [10 empty] | #VALUE!
#REF!
SOIL TESTING
ii. Procurement of Field,Office and Laboratory Equipment/ Materials |  | LOT 1 | 22500000 | Competitive Bidding |  |  | Feb 7 - Feb 28 | Feb 28 - Mar 14 | Mar 14 - Mar28 | Mar 28 | May 9 | May 9 - May 30 | May 30 - Jun 13 | 22500000 | N/A | Jun 13 - Jun 27 | July 18 | Aug 15 | Oct 10 | Oct 25
date
iv. Production of 1500 Extension manuals / maps of nutrient status of Kuje Area Council in FCT |  | LOT 2 | 3750000 | Competitive Bidding |  |  | Feb 7 - Feb 28 | Feb 28 - Mar 14 | Mar 14 - Mar28 | Mar 28 | May 9 | May 9 - May 30 | May 30 - Jun 13 | 3750000 | N/A | Jun 13 - Jun 27 | July 18 | Aug 15 | Oct 10 | Oct 25
Total Cost |  |  | 26250000 | [10 empty] | 26250000
|  |  | 0 | [10 empty] | 0
NSSP LAND MANAGEMENT
i. Procurement & installation of Remote Sensing Equipment to meet the Land Reform & NDGI standards |  | LOT 1 | 20000000 | Competitive Bidding |  |  | Feb 7 - Feb 28 | Feb 28 - Mar 14 | Mar 14 - Mar28 | Mar 28 | May 9 | May 9 - May 30 | May 30 - Jun 13 | 20000000 | N/A | Jun 13 - Jun 27 | July 18 | Aug 15 | Oct 10 | Oct 25
date
iii. Procurement & Installation of GIS and other data capture equipment, upgrade of server, design of data base |  | LOT 2 | 20000000 | Competitive Bidding |  |  | Feb 7 - Feb 28 | Feb 28 - Mar 14 | Mar 14 - Mar28 | Mar 28 | May 9 | May 9 - May 30 | May 30 - Jun 13 | 20000000 | N/A | Jun 13 - Jun 27 | July 18 | Aug 15 | Oct 10 | Oct 25
iv. Procurement of 5 meter resolution orthorectified spot imageries to 18 states |  | LOT 3 | 40000000 | Competitive Bidding |  |  | Feb 7 - Feb 28 | Feb 28 - Mar 14 | Mar 14 - Mar28 | Mar 28 | May 9 | May 9 - May 30 | May 30 - Jun 13 | 40000000 | N/A | Jun 13 - Jun 27 | July 18 | Aug 15 | Oct 10 | Oct 25
v. Production of base maps, 50,000 base maps of various thematic layers at scale 1:50,000 covered by the imageries |  | LOT 4 | 20000000 | Competitive Bidding |  |  | Feb 7 - Feb 28 | Feb 28 - Mar 14 | Mar 14 - Mar28 | Mar 28 | May 9 | May 9 - May 30 | May 30 - Jun 13 | 20000000 | N/A | Jun 13 - Jun 27 | July 18 | Aug 15 | Oct 10 | Oct 25
Total Cost |  |  | 100000000 | [10 empty] | 100000000
|  |  | 0 | [10 empty] | 0
CAT LAND MANAGEMENT
i) Procurement of CA Equipment/Materials. Target: Transfer of CAT technology to 3,600 framers |  | LOT 1 | 12000000 | Competitive Bidding |  |  | Feb 7 - Feb 28 | Feb 28 - Mar 14 | Mar 14 - Mar28 | Mar 28 | May 9 | May 9 - May 30 | May 30 - Jun 13 | 12000000 | N/A | Jun 13 - Jun 27 | July 18 | Aug 15 | Oct 10 | Oct 25
date
ii) Production of 2000 Extension Manuals on Conservation Agriculture Technology for farmers. |  | LOT 2 | 1500000 | Competitive Bidding |  |  | Feb 7 - Feb 28 | Feb 28 - Mar 14 | Mar 14 - Mar28 | Mar 28 | May 9 | May 9 - May 30 | May 30 - Jun 13 | 1500000 | N/A | Jun 13 - Jun 27 | July 18 | Aug 15 | Oct 10 | Oct 25
iv. Procurement of Ammeliorative materials (Lime, organic manure, Gypsum) |  | LOT 3 | 10000000 | Competitive Bidding |  |  | Feb 7 - Feb 28 | Feb 28 - Mar 14 | Mar 14 - Mar28 | Mar 28 | May 9 | May 9 - May 30 | May 30 - Jun 13 | 10000000 | N/A | Jun 13 - Jun 27 | July 18 | Aug 15 | Oct 10 | Oct 25
v. Production of 2,500 manuals on reclamation techniques of degraded soils |  | LOT 4 | 1500000 | Competitive Bidding |  |  | Feb 7 - Feb 28 | Feb 28 - Mar 14 | Mar 14 - Mar28 | Mar 28 | May 9 | May 9 - May 30 | May 30 - Jun 13 | 1500000 | N/A | Jun 13 - Jun 27 | July 18 | Aug 15 | Oct 10 | Oct 25
Total Cost |  |  | 25000000 | [10 empty] | 25000000
|  |  | 0 | [10 empty] | 0
Ministry/Department/Agency: | FEDERAL DEPARTMENT OF LIVESTOCK
Budgetary Year: 2011 | 2011 | [5 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: | DR. G.M. MSHELBWALA | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
add 2 wks
List of Contracts
 Provision of Laboratry Equipments and Reagents for the School of Pest Control Services, Kaduna | B.1 | B.1.2 | 7500000 | RP | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 7500000 | N/A | N/A | N/A | Late Jun.2011 | Late Aug.2011 | Late Sep.2011
 Procurement of Application tools and Personal Protective Equipment for Pest Control Operations in the 12 frontline states | B.1 | B.1.3 | 17250000 | RP | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 17250000 | N/A | N/A | N/A | Late Jun.2011 | Late Aug.2011 | Late Sep.2011
 Input support for Meat Hygiene and Inspection activities in the States through provision of modern of meat inspection tools (hooves and knives) | C.2 | C.2.1 | 19425435.75 | RP | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 19425435.75 | N/A | N/A | N/A | Late Jun.2011 | Late Aug.2011 | Late Sep.2011
 Provision of Vaccines and Vaccination of 10 m heads of Sheep and Goats against Peste des Petits Ruminants (PPR) | C.1 | A.1.3 | 63750000 | RP | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 63750000 | N/A | N/A | N/A | Late Jun.2011 | Late Aug.2011 | Late Sep.2011
 Provision of vaccines and Vaccination of 5m heads of cattle against Contagious Bovine Pleuropneumonia (CBPP) and Collection of 5m blood samples per quarter for Livestock Disease Surveillance and Sero-Monitoring and Animal Welfare Issues | C.1 | A.1.4 | 56250000 | RP | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 56250000 | N/A | N/A | N/A | Late Jun.2011 | Late Aug.2011 | Late Sep.2011
 Promotion of Bio-security through the provision of Equipments and Re-agents for Control of African Swine Fever (ASF) in Benue, Plateau, Ogun, Ondo, Cross-Rivers, Delta, Edo and Enugu States | C.1 | C.1.2 | 18750000 | RP | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 18750000 | N/A | N/A | N/A | Late Jun.2011 | Late Aug.2011 | Late Sep.2011
 Production of livestock extension and enterprise information guides | A.2 | A.2.2 | 7000000 | RP | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 7000000 | N/A | N/A | N/A | Late Jun.2011 | Late Aug.2011 | Late Sep.2011
Total Cost |  |  | 189925435.75 | [10 empty] | 189925435.75
|  |  | 0 | [10 empty] | 0
Ministry/Department/Agency: | FISHERIES
Budgetary Year: | 2011 | [5 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: | MR FF ADEYEMI /07032902444 | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
Procurement of Fish Laboratory Equipment for National Fisheries Laboratory, Victoria Island | [6 empty] | 24/03/11 | 24/03/11 | 07/04/11 | 21/04/11 | 02/06/11 | 23/06/11 | 30/06/11 | 45000000 | N/A | 07/07/11 | 28/07/11 | 09/08/11 | 19/08/11 | 31/08/11
| A | 1 | 45000000 | National Competitive Bidding | 10/03/11 | Post Review | 24/03/11 | 24/03/11 | 07/04/11 | 21/04/11 | 02/06/11 | 23/06/11 | 30/06/11 | 45000000 | N/A | 07/07/11 | 28/07/11 | 09/08/11 | 19/08/11 | 31/08/11
date
Ministry/Department/Agency: - Federal Fertilizer Department - FMARD
Budgetary Year: 2011 | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Fertilizer Market Stabilization Programme |  |  | 8768750000 |  |  |  | To be carried out | [6 empty] | to be obtained | to be obtained | March, 2011 | March, 2011 | 15% | Immediately | To be done later | To be decided | Completion
|  |  | 6573000000 | In line with BPP | Yes
Quality Control and Monitoring of Standard |  |  | 89760000
67330440
Organic Fertilizer Development and Promotion |  |  | 100066500
100081875
National Fertilizer Development Center |  |  | 45854250
61957091
Total Cost |  |  | 9004430750 | [10 empty] | #VALUE!
|  |  | 6802369406 | [10 empty] | #REF!
Ministry/Department/Agency: | NATIONAL FOOD RESERVE AGENCY
Budgetary Year: | 2011 | [5 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: | DR. M.I. Lawal/08073312154 | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Approval Threshold | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
Guaranteed Minimum Price Programme (GMP) Procurement of Assorted Grains (70,000 mts) | NFRA/Goods/GMP/01/2011 | 60 | 3600000000 | Repeat Procurement | N/A | FEC | 16/06/11 | 23/07/11 | N/A | 08/08/11 | 29/08/11 | 13/09/11 | 10/10/11 | 3600000000 | 19/10/11 | 07/11/11 | 28/11/11 | 05/12/11 | 26/12/11 | 13/02/12
Purchase of storage and environmental as well as grains management equipment (automatic pellet dispacer, mini oxygen tank, phostophine meter and safety jack | NFRA/Goods/GMP/02/2011 | 10 | 300000000 | National Competitive Bidding | N/A | MTB | 21/04/2011 | 15/05/11 | 11/05/11 | 18/05/11 | 29/06/2011 | 13/06/2011 | 5/7/2011 | 300000000 | N/A | 11/05/11 | 19/05/11 | 06/06/11 | 12/07/11 | 01/08/11
25% FGN Subsidy contribution for the provision of tractors and implements through Public Private Partnership (PPP) | NFRA/Goods/Tract/3/2011 | 3 | 711750000 | National Competitive Bidding | N/A | FEC | 31/01/11 | 21/03/11 |  | 05/04/11 | 26/04/11 | 03/05/11 | 22/06/11 | 711750000 | 18/05/11 | 26/05/11 | 15/06/11 | 15/06/11 | 30/08/11 | 30/12/11
Procurement of Equipment and Vheicles for Extension Services Delivery | NFRA/Goods/ICP/04/2011 | 2 | 20000000 | National Competitive Bidding | N/A | MTB | 21/04/2011 | 15/05/11 | 11/05/11 | 18/05/11 | 29/06/2011 | 13/06/2011 | 5/7/2011 | 20000000 | N/A | 11/05/11 | 19/05/11 | 06/06/11 | 12/07/11 | 01/08/11
Total Cost |  | 75 | 4631750000 | [10 empty] | 4631750000
Ministry/Department/Agency Cooperatives Dept. Federal Cooperative College, Kaduna.
Budgetary Year: 2011
Desk Officer/Contact# |  | BASIC DATA |  |  |  |  | Draft Bid Documents, including specs and quantities draft SPN |  | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description | Package Number | Lot Number | Budgetary Amt. in Nm | Procurement Method | Pre-Qualification | Prior or Post review | Prep. & Submission by MDAs | No. objection Date | Adveristment for Pre-Quantities | Bid Invitation Date | Bid Closing/Opening | Submission Bid Eval. Report | No objection Date | Contract Amt. Certified in Nm | EFC Approval | Date of Contract Offer | Date of Contract Signature | Opening of Letter of Credit | Arrival of Goods | Inspection final Acceptance.
Norm Duration of Proc. Steps | [6 empty] | 2-3wks | 1-2wks | 2wks | 2 to | 6wks | 2-3wks | 1-2wks |  | 2-4wks | 1-2wks | 3wks
List of Contracts
Furnishing of the newly completed College Theartre. | FCCK 2 | Lot 1 | 8.7m | PCB | Pre- Qualification | Post Review. | Jan. '11 | Feb. '11 | Mar. '11 | Mar. '11 | Apr. '11 | May. '11 | May. '11 | 8.7m | N/A | May-Jun.'11 | Jun. '11 | Jul. '11 | Jul. - Aug. '11 | Aug. '11
Furnishing of the newly completed College Hostel. | FCCK 2 | Lot 2 | 4.94m | PCB | Pre- Qualification | Post Review. | Jan. '11 | Feb. '11 | Mar. '11 | Mar. '11 | Apr. '11 | May. '11 | May. '11 | 4.94m | N/A | May-Jun.'11 | Jun. '11 | Jul. '11 | Jul. - Aug. '11 | Aug. '11
Purchase and installation of 150KVA College Generator. | FCCK 2 | Lot 3 | 8.53m | PCB | Pre- Qualification | Post Review. | Jan. '11 | Feb. '11 | Mar. '11 | Mar. '11 | Apr. '11 | May. '11 | May. '11 | 8.53m | N/A | May-Jun.'11 | Jun. '11 | Jul. '11 | Jul. - Aug. '11 | Aug. '11
Ministry/Department/Agency:NIGERIA AGRICULTURAL QUARANTINE SERVICE
Budgetary Year: 2010 | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #:DR KUKWI K.P. 08023775828 |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
add 2 wks
List of Contracts
procurement of 1no. Seed cold room,,1no. Incinerator | NAQS/01 | LOT 15 |  | NCB | Pre- Qualification | MTB | 1-14 Mar/10 | 15-20Mar/10 | 20-4Apr/10 | 20Ap-19May/10 | 19May/10 | 20May-4Jun/10 | 4-11Jun/10 |  | NA | 12-19Jun/10 | 20-27Jun/10 | NA | 30Aug/10 | 30Aug/10 | HOD/ADM | HOD/CP&P
Federal Ministry of Agriculture
Procurement--- WORKS
MINISTRY/DEPT/AGENCY: Rural Access and Mobility Project (RAMP), Federal Ministry of Agriculture and Rural Development
Budgetary Year: 2011(N1,491,281,125.00) | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Nm | Pre-or Post Qualification | Approval Threshold | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date(MTB Approval) | Contract Amount Certified in Nm | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost(Nm)
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
Construction/Rehabilitation of Xkm Rural Road | Package 1 | Lot 1 | BOQ | RT | 77,080,232.06 | Post qualification | MTB | 9-Feb-11 | 11-Feb-11 | Not Required | 14-Feb-11 | 28-Feb-11 | 31-Mar-11 | 15-Apr-11 | 77,080,232.06 | Not Required | 29-Apr-11 | 16-May-11 | 31-May-11 | 29-Jul-11 | 15-Aug-11 | 77,080,232.06
Total Cost |  |  |  |  | 77,080,232.06 | [9 empty] | 77,080,232.06 | [6 empty] | 77,080,232.06
Total Cost
MINISTRY/DEPT/AGENCY: Rural Access and Mobility Project (RAMP), Federal Ministry of Agriculture and Rural Development
Budgetary Year: 2011(N1,491,281,125.00) | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in N(Outstanding Payments) | Pre-or Post Qualification | Approval Threshold | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date(MTB Approval) | Contract Amount Certified in Nm | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost(Nm)
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 3 wks
add 2 wks
Outstanding Payments for Civil Works Contracts under the 2009 Constituency Rural Roads Projects
List of Contracts
Rehabilitation of Ogbaku Okwu Egbema Road in Imo State. | NA | NA | BOQ | NA | 1,309,927.50 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 1,309,927.50 | NA | NA | NA | NA | NA | 31-May-11 | 1,309,927.50
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Umuokpara Ibeku Umuhu Uvuru Road, Abo Mbaise in Imo State. | NA | NA | BOQ | NA | 2,857,561.84 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 2,857,561.84 | NA | NA | NA | NA | NA | 31-May-11 | 2,857,561.84
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Umuakagu Ezeoke Nsu Agbghara Nsu Road in Imo State. | NA | NA | BOQ | NA | 13,203,718.95 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 13,203,718.95 | NA | NA | NA | NA | NA | 31-May-11 | 13,203,718.95
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Isiekenesi Road Ideato LGA in Imo State. | NA | NA | BOQ | NA | 4,936,152.51 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 4,936,152.51 | NA | NA | NA | NA | NA | 31-May-11 | 4,936,152.51
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Oriegbaku-Amaegbu-Obidi-Agwa road in Imo state | NA | NA | BOQ | NA | 80,197,500.00 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 80,197,500.00 | NA | NA | NA | NA | NA | 31-May-11 | 80,197,500.00
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Umukuma Okposi Road. Ebonyi state | NA | NA | BOQ | NA | 29,014,617.46 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 29,014,617.46 | NA | NA | NA | NA | NA | 31-May-11 | 29,014,617.46
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitationof Amugu/ Ibii Road in the Afikpo North of Ebonyi state. | NA | NA | BOQ | NA | 20,988,635.12 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 20,988,635.12 | NA | NA | NA | NA | NA | 31-May-11 | 20,988,635.12
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Bnu Akpara Ezuku Uwaji Oda Ezuku Osu Road in Ebonyi state | NA | NA | BOQ | NA | 0.00 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 0.00 | NA | NA | NA | NA | NA | NA | 0.00
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA
Rehabilitation of Ndiagu Obuluchi Ndiaguazu Omuorie Ekadu Road in Ebonyi state | NA | NA | BOQ | NA | 13,009,720.38 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 13,009,720.38 | NA | NA | NA | NA | NA | 31-May-11 | 13,009,720.38
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Odomowo Oagbo road Ikon LGA of Ebonyi State. | NA | NA | BOQ | NA | 14,791,825.00 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 14,791,825.00 | NA | NA | NA | NA | NA | 31-May-11 | 14,791,825.00
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Azuiyaba Egu Out Road in Ebonyi state | NA | NA | BOQ | NA | 23,474,251.00 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 23,474,251.00 | NA | NA | NA | NA | NA | 31-May-11 | 23,474,251.00
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Nkwo ugwulangwu- obioha Uhuotaru-Ezuku Eze Iyioku- nwafor Aboeja Road in Ebonyi state. | NA | NA | BOQ | NA | 28,496,802.00 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 28,496,802.00 | NA | NA | NA | NA | NA | 31-May-11 | 28,496,802.00
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Umudioka Anam-Oroma Etiti-Aniasa in Anambra state | NA | NA | BOQ | NA | 9,256,695.00 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 9,256,695.00 | NA | NA | NA | NA | NA | 31-May-11 | 9,256,695.00
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Igbariam Afor Farm Settlement in Anambra state | NA | NA | BOQ | NA | 28,994,562.50 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 28,994,562.50 | NA | NA | NA | NA | NA | 31-May-11 | 28,994,562.50
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of College of Education Nsugbe Road in Anambra state. | NA | NA | BOQ | NA | 3,925,719.97 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 3,925,719.97 | NA | NA | NA | NA | NA | 31-May-11 | 3,925,719.97
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Ocuche Amiyi Road Ogbaru LGA of Anambra state. | NA | NA | BOQ | NA | 17,083,017.80 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 17,083,017.80 | NA | NA | NA | NA | NA | 31-May-11 | 17,083,017.80
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Ede Road Okpoko Ogbaru LGA in Anambra state | NA | NA | BOQ | NA | 16,451,282.50 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 16,451,282.50 | NA | NA | NA | NA | NA | 31-May-11 | 16,451,282.50
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Oyi Awkuzu Rural Road Oyi LGA, Anamabra State. | NA | NA | BOQ | NA | 7,163,200.00 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 7,163,200.00 | NA | NA | NA | NA | NA | 31-May-11 | 7,163,200.00
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Ugbene Village Omasi Agu Ayamelum LGA Rural road Oyi LGA, Anambra State. | NA | NA | BOQ | NA | 16,370,511.25 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 16,370,511.25 | NA | NA | NA | NA | NA | 31-May-11 | 16,370,511.25
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Agubu Umrumba Indiagu Road, Enugu State. | NA | NA | BOQ | NA | 1,897,062.80 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 1,897,062.80 | NA | NA | NA | NA | NA | 31-May-11 | 1,897,062.80
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Umudike Ring Road Ihiala in Anambra state. | NA | NA | BOQ | NA | 28,586,844.70 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 28,586,844.70 | NA | NA | NA | NA | NA | 31-May-11 | 28,586,844.70
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Enugwu Agidi Njikoka LGA in Anambra state. | NA | NA | BOQ | NA | 23,690,156.63 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 23,690,156.63 | NA | NA | NA | NA | NA | 31-May-11 | 23,690,156.63
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Umuala Umukwu Ohuhu Nsula Isiala Ngwa North in Abia state. | NA | NA | BOQ | NA | 15,055,410.00 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 15,055,410.00 | NA | NA | NA | NA | NA | 31-May-11 | 15,055,410.00
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Ohuhu Ekwu Amiyi Umuwaocha. Abia State. | NA | NA | BOQ | NA | 2,742,309.37 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 2,742,309.37 | NA | NA | NA | NA | NA | 31-May-11 | 2,742,309.37
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Mayo Chacha Timbo Rd in Tounga LGA in Adamawa state. | NA | NA | BOQ | NA | 4,858,654.12 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 4,858,654.12 | NA | NA | NA | NA | NA | 31-May-11 | 4,858,654.12
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Gwarangah PMSS Bongah Road Bogoro LGA in Bauchi state. | NA | NA | BOQ | NA | 2,356,385.40 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 2,356,385.40 | NA | NA | NA | NA | NA | 31-May-11 | 2,356,385.40
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Pulka Ngoshe Chikede Kwughum Road in Borno state. | NA | NA | BOQ | NA | 30,106,505.41 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 30,106,505.41 | NA | NA | NA | NA | NA | 31-May-11 | 30,106,505.41
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Gwoza-Dure road. Borno State. | NA | NA | BOQ | NA | 1,739,117.80 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 1,739,117.80 | NA | NA | NA | NA | NA | 31-May-11 | 1,739,117.80
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Yarima-Gassol Road in Gombe state. | NA | NA | BOQ | NA | 26,436,852.31 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 26,436,852.31 | NA | NA | NA | NA | NA | 31-May-11 | 26,436,852.31
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of 42km feeder road at mafa-Babaginda- tarmuwa LGA in Yobe state. | NA | NA | BOQ | NA | 25,647,328.75 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 25,647,328.75 | NA | NA | NA | NA | NA | 31-May-11 | 25,647,328.75
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Dohuwan Kura to garin Kauli Road in Yobe state. | NA | NA | BOQ | NA | 15,835,011.25 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 15,835,011.25 | NA | NA | NA | NA | NA | 31-May-11 | 15,835,011.25
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Namu Lankaku road, Quaan Pan LGA in Plateau state. | NA | NA | BOQ | NA | 28,428,393.96 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 28,428,393.96 | NA | NA | NA | NA | NA | 31-May-11 | 28,428,393.96
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Emitsogu magaji road Agaie LGA in Niger state. | NA | NA | BOQ | NA | 6,734,849.15 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 6,734,849.15 | NA | NA | NA | NA | NA | 31-May-11 | 6,734,849.15
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Federal housing Estate road ,Olomore Abeokuta in Ogun State. | NA | NA | BOQ | NA | 3,529,348.75 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 3,529,348.75 | NA | NA | NA | NA | NA | 31-May-11 | 3,529,348.75
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Sanyaolu Olobe Iporo Ojogun Village in Ogun state. | NA | NA | BOQ | NA | 28,881,028.00 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 28,881,028.00 | NA | NA | NA | NA | NA | 31-May-11 | 28,881,028.00
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of oke Odan-Isagbo Owo in Ogun state. | NA | NA | BOQ | NA | 3,965203.50 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 3,965203.50 | NA | NA | NA | NA | NA | 31-May-11 | 3,965203.50
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Ipokia- Maun Road. Ogun State. | NA | NA | BOQ | NA | 6,921,714.50 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 6,921,714.50 | NA | NA | NA | NA | NA | 31-May-11 | 6,921,714.50
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Ihunbo-Ita Egbe Road in Ogun state. | NA | NA | BOQ | NA | 27,817,393.68 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 27,817,393.68 | NA | NA | NA | NA | NA | 31-May-11 | 27,817,393.68
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Ijoun –Gbokofi road in ogun state. | NA | NA | BOQ | NA | 0.00 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 0.00 | NA | NA | NA | NA | NA | NA | 0.00
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA
Rehabilitation of Ijoun- Ijaka road in Ogun state. | NA | NA | BOQ | NA | 1,120,393.81 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 1,120,393.81 | NA | NA | NA | NA | NA | 31-May-11 | 1,120,393.81
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Olokoo-Iro- Idi-Araba in Ogun state. | NA | NA | BOQ | NA | 28,665,002.62 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 28,665,002.62 | NA | NA | NA | NA | NA | 31-May-11 | 28,665,002.62
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Odo Oba Aiyede Alabamete Opete, Ogo Oluwa LGA in Oyo state. | NA | NA | BOQ | NA | 29,082,750.00 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 29,082,750.00 | NA | NA | NA | NA | NA | 31-May-11 | 29,082,750.00
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Bareke Oloko Road Igboho in Oyo state. | NA | NA | BOQ | NA | 5,395,757.16 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 5,395,757.16 | NA | NA | NA | NA | NA | 31-May-11 | 5,395,757.16
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Igboko Soore Kisi Road in Oyo state. | NA | NA | BOQ | NA | 3,024,337.99 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 3,024,337.99 | NA | NA | NA | NA | NA | 31-May-11 | 3,024,337.99
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Iyaoje-Byiro-Iyelu-Egbeda-Abogunde road in Oyo state. | NA | NA | BOQ | NA | 4,441,955.17 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 4,441,955.17 | NA | NA | NA | NA | NA | 31-May-11 | 4,441,955.17
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Mafowoku Yaaye Village road in Oyo state. | NA | NA | BOQ | NA | 10,492,657.50 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 10,492,657.50 | NA | NA | NA | NA | NA | 31-May-11 | 10,492,657.50
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Araro Isale offa Oti River road, Okuku in Osun state. | NA | NA | BOQ | NA | 21,745,550.00 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 21,745,550.00 | NA | NA | NA | NA | NA | 31-May-11 | 21,745,550.00
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of igbaye- Imuleke-Oponda-Oda Otin LGA in Osun state. | NA | NA | BOQ | NA | 16,585,565.50 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 16,585,565.50 | NA | NA | NA | NA | NA | 31-May-11 | 16,585,565.50
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of orita-Odanbon- Ilogbo-Itemu road in Osun state. | NA | NA | BOQ | NA | 3,859,391.03 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 3,859,391.03 | NA | NA | NA | NA | NA | 31-May-11 | 3,859,391.03
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Babaegbe-Aladi-OKo in Osun state. | NA | NA | BOQ | NA | 81,453,447.92 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 81,453,447.92 | NA | NA | NA | NA | NA | 31-May-11 | 81,453,447.92
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Ijabe Central Mosque Ila Odo Oti, Osun state. | NA | NA | BOQ | NA | 12,285,500.00 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 12,285,500.00 | NA | NA | NA | NA | NA | 31-May-11 | 12,285,500.00
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of New Layout road AW LGA of Rivers state. | NA | NA | BOQ | NA | 9,443,415.51 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 9,443,415.51 | NA | NA | NA | NA | NA | 31-May-11 | 9,443,415.51
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Amamong Airport Ndon Ebom Farm Road in Akwa- Ibom state. | NA | NA | BOQ | NA | 2,019,644.96 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 2,019,644.96 | NA | NA | NA | NA | NA | 31-May-11 | 2,019,644.96
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Bridge linking Ikot Ntan Ide & Ikot Edem Udo Communities in Onna LGA of Akwa-Ibom state | NA | NA | BOQ | NA | 0.00 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 0.00 | NA | NA | NA | NA | NA | NA | 0.00
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA
Rehabilitation of access road to Ekugbe Grammar School from Aiyegunle, A/Ibom State. | NA | NA | BOQ | NA | 6,049,687.50 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 6,049,687.50 | NA | NA | NA | NA | NA | 31-May-11 | 6,049,687.50
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of 4km road in Otokon in Akwa Ibom state. | NA | NA | BOQ | NA | 1,612,607.86 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 1,612,607.86 | NA | NA | NA | NA | NA | 31-May-11 | 1,612,607.86
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Auchi Ibilo Aiyetoro Ogbe Ugugu Road, Edo State | NA | NA | BOQ | NA | 30,267,858.25 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 30,267,858.25 | NA | NA | NA | NA | NA | 31-May-11 | 30,267,858.25
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Tanbuwal yagawal Bashire road Tambuwal LGA in Sokoto state. | NA | NA | BOQ | NA | 35,069,302.55 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 35,069,302.55 | NA | NA | NA | NA | NA | 31-May-11 | 35,069,302.55
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Gidan Yarfara Labau S/Birni LGA in Sokoto state. | NA | NA | BOQ | NA | 19,550,000.00 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 19,550,000.00 | NA | NA | NA | NA | NA | 31-May-11 | 19,550,000.00
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Jabo Gabari- Shibara-Malama Gurgun Dabo Jaudadu Galadimawa Kafim Hausa LGA Express, Jigawa State. | NA | NA | BOQ | NA | 20,703,598.75 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 20,703,598.75 | NA | NA | NA | NA | NA | 31-May-11 | 20,703,598.75
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Kanya Babba Muku Babara-Garki LGA in Jigawa State. | NA | NA | BOQ | NA | 15,567,359.38 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 15,567,359.38 | NA | NA | NA | NA | NA | 31-May-11 | 15,567,359.38
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Danwaye Karasa road Doguwa LGA in Kano state. | NA | NA | BOQ | NA | 2,921,250.10 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 2,921,250.10 | NA | NA | NA | NA | NA | 31-May-11 | 2,921,250.10
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Kabo LGA road in Kano state. | NA | NA | BOQ | NA | 0.00 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 0.00 | NA | NA | NA | NA | NA | NA | 0.00
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA
Rehabilitation of Doka Jobe Tofa road in Kano state. | NA | NA | BOQ | NA | 21,212,628.45 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 21,212,628.45 | NA | NA | NA | NA | NA | 31-May-11 | 21,212,628.45
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Kadage Garmadi -Galadimawa Road, yadin Garu Binawa Road in Kaduna state. | NA | NA | BOQ | NA | 19,252,773.70 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 19,252,773.70 | NA | NA | NA | NA | NA | 31-May-11 | 19,252,773.70
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Markarfi Road in Kaduna state. | NA | NA | BOQ | NA | 101,220,403.37 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 101,220,403.37 | NA | NA | NA | NA | NA | 31-May-11 | 101,220,403.37
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Rehabilitation of Tashan Gade-Garu road in Kudanchi LGA in Kaduna state. | NA | NA | BOQ | NA | 78,283,640.00 | NA | MTB | NA | NA | NA | NA | NA | NA | NA | 78,283,640.00 | NA | NA | NA | NA | NA | 31-May-11 | 78,283,640.00
|  |  |  | NA |  | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
Total |  |  |  | 1,198,081,799.96 | 1,198,081,799.96 | [9 empty] | 1,198,081,799.96 | [6 empty] | 1,198,081,799.96
Ministry/Department/Agency: Federal Ministry of Agriculture and Water Resources (Federal Department of Agriculture - FDA)
Budgetary Year: 2011 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
Development of Institutional Support for Agricultural Mechanization: Construction of Office complex, Classroom and Administrative block at AMMOTRAC Akure, Ondo State
| 8 | B3 |  | National Competive Bidding (NCB) | 30000000 |  |  | 3/3/2011 | 30/3/2011 |  | 3/4/2011 | 17/4/2011 | 31/5/2011 | 1/6/2011 | 30000000 | N/A | 30/6/2011 |  |  |  | 30/10/2010 | 30000000
Construction of Office complex, Classroom and Administrative block at AMMOTRAC Misau, Bauchi State
| 9 | B4 |  | National Competive Bidding (NCB) | 30000000 |  |  | 3/3/2011 | 30/3/2011 |  | 3/4/2011 | 17/4/2011 | 30/5/2011 | 1/6/2011 | 30000000 | N/A | 30/6/2011 |  |  |  | 30/10/2010 | 30000000
External electrical works/ Construction of Sub-station at AMMOTRAC Misau, Bauchi State
| 10 | B5 |  | National Competive Bidding (NCB) | 10000000 |  |  | 30/6/2011 | 30/6/2010 |  | 30/7/2011 | 30/7/201 | 30/7/2011 | 30/8/2010 | 10000000 | N/A | 30/8/2011 |  |  |  | 30/11/2010 | 10000000
Employment Generation in Mechanization Technology: Renovation, Rehabilitation and Expansion of Hostels @ BATSU Ilorin
| 12 | C2 |  | National Competive Bidding (NCB) | 4000000 |  |  | 30/3/2010 | 30/3/2010 |  | 30/4/2011 | 30/4/2011 | 30/5/2011 | 30/5/2011 | 4000000 | N/A | 30/6/2011 |  |  |  | 30/10/2010 | 4000000
Reconstruction of water control structure and channelization at the site, BATSU, Ilorin
|  | C3 |  | National Competive Bidding (NCB) | 2000000 |  |  | 30/3/2010 | 30/3/2010 |  | 30/4/2011 | 30/4/2011 | 30/5/2011 | 30/5/2011 | 2000000 | N/A | 30/6/2011 |  |  |  | 30/10/2010 | 2000000
Procurement of treadle pumps for distribution to farmers for dry season vegetable production
| 13 | C4 |  | National Competive Bidding (NCB) | 6000000 |  |  | 30/3/2011 | 30/3/2011 |  | 30/4/2010 | 30/4/2010 | 30/5/2010 | 30/5/2010 | 6000000 | N/A | 30/6/2011 |  |  |  | 30/10/2010 | 6000000
Post-Harvest loss prevention technology: Construction and Installation of on-farm storage structures for demonstration, popularization and distribution to beneficiaries
| 14 | D3 |  | National Competive Bidding (NCB) | 3000000 |  |  | 30/3/2011 | 30/3/2011 |  | 30/4/2011 | 30/4/2011 | 30/5/2011 | 30/5/2011 | 3000000 | N/A | 30/6/2010 |  |  |  | 30/10/2010 | 3000000
Renovation of the equipment workshop at the Post Harvest Centre Ibadan
| 15 | D4 |  | National Competive Bidding (NCB) | 1500000 |  |  | 30/3/2011 | 30/3/2011 |  | 30/4/2011 | 30/4/2011 | 30/5/2011 | 30/5/2011 | 1500000 | N/A | 30/6/2011 |  |  |  | 30/10/2010 | 1500000
Total Cost
[5 empty] | 86500000 | [9 empty] | 86500000 | [6 empty] | 86500000
RURAL DEVELOPMENT
Rehabilitation of 30No. Farm wells at the Enclave Projects
|  | A1 |  | National Competetive Bidding | 12000000 |  |  | 21/02/2011 | 11/03/2011 | 25/03/2011 | 04/04/2011 | 13/05/2011 | 27/05/2011 | 6/06/2011 | 12000000 | NA | 10/06/2011 |  |  |  | 27/06/2011 | 12000000
Construction/Rehabilitation of 18No. Drying Slabs (3/Geo-Political Zone)
|  |  |  | National Competetive Bidding | 12600000 |  |  | 21/02/2011 | 11/03/2011 | 25/03/2011 | 04/04/2011 | 13/05/2011 | 28/05/2011 | 6/06/2011 | 9000000 | NA | 13/06/2011 |  |  |  | 2/06/2011 | 9000000
Construction/Rehabilitation of 12No. Farm shed |  | A2 | [5 empty] | 21/02/2011 | 11/03/2011 | 25/03/2011 | 04/04/2011 | 13/05/2011 | 27/05/2011 | 6/06/2011 | 37500000 | NA | 10/06/2011 |  |  |  | 27/06/2011 | 37500000
|  |  |  | National Competetive Bidding | 30000000
Total Cost
[5 empty] | 54600000 | [9 empty] | 58500000 | [6 empty] | 58500000
Ministry/Department/Agency: | FEDERAL DEPARTMENT OF LIVESTOCK
Budgetary Year: 2011 | 2011 | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: | DR. G.M. MSHELBWALA | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
add 2 wks
List of Contracts
 Maintenance of Pest control Laboratory, Kaduna | B.2 | B.2.1 | Bill of Quantities | OCB | 9000000 |  |  | 4th April. 2011 | 22nd April. 2011 | 2nd May.2011 | 20th May.2011 | 1st Jun.2011 | 15th July,2011 | 29th July,2011 | 9000000 |  | 1st August, 2011 | 12th Aug.2011 | 15th Aug.2011 | 31st Aug.2011 | 30th Sep.2011 | 9000000
 Maintenance and operation of 13no. Livestock Breeding centres in 1no. (Bauchi), 1no. (Niger), 1no. (Akwa-Ibiom), 1no. (Edo), 2no. (Enugu), 2no. (Oyo), 2no. (Katsina), 1no. (Ebonyi), 1no. (Zamfara) and 1no. (Adamawa) | A.3 | A.3.1 | Bill of Quantities | OCB | 52500000 |  |  | 4th April. 2011 | 22nd April. 2011 | 2nd May.2011 | 20th May.2011 | 1st Jun.2011 | 15th July,2011 | 29th July,2011 | 52500000 | N/A | 1st July,2011 | 12th Aug.2011 | 15th Aug.2011 | 31st Aug.2011 | 30th Sep.2011 | 52500000
Total Cost |  |  |  |  | 61500000 | [9 empty] | 61500000 | [6 empty] | 61500000
[5 empty] | 0 | [9 empty] | 0 | [6 empty] | 0
Ministry/Department/Agency: | NATIONAL LIVESTOCK DEVELOPMENT PROJECT/FMA&RD
Budgetary Year: 2011 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: | RUMA, BASHIR | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
add 2 wks
List of Contracts
Rehabilitation and Fencing of 50Ha out of Existing Developed Pasture in Bobi Grazing Reserve, Niger State |  | A1 | BOQ | Repeat | 35953000 |  | MTB | 1-14/4/2011 | 15-30/4/11 | N/A | N/A | N/A | N/A | N/A | 35953000 | N/A | 1-14/5/11 | 16-23/7/11 |  | 30/8/11 | 30/11/11 | 35953000
Rehabilitation and Fencing of 50Ha out of Existing Developed Pasture in Sankara Grazing Reserve, Jigawa State |  | A2 | BOQ | Repeat | 35753000 |  | MTB | 1-14/4/2011 | 15-30/4/11 | N/A | N/A | N/A | N/A | N/A | 35753000 | N/A | 1-14/5/11 | 16-23/7/11 |  | 30/8/11 | 30/11/11 | 35753000
Rehabilitation and Fencing of 50Ha out of Existing Developed Pasture in Zamfara Grazing Reserve, Zamfara State |  | A3 | BOQ | Repeat | 35653000 |  | MTB | 1-14/4/2011 | 15-30/4/11 | N/A | N/A | N/A | N/A | N/A | 35653000 | N/A | 1-14/5/11 | 16-23/7/11 |  | 30/8/11 | 30/11/11 | 35653000
Costruction of Handpump boreholes with Trough along Stock Routes |  | A4 | BOQ | Repeat | 88932000 |  | MTB | 1-14/4/2011 | 15-30/4/11 | N/A | N/A | N/A | N/A | N/A | 88932000 | N/A | 1-14/5/11 | 16-23/7/11 |  | 30/8/11 | 30/11/11 | 88932000
Maintenance of Heavy Duty Equipments |  | A5 | BOQ | Repeat | 20000000 |  | MTB | 1-14/4/2011 | 15-30/4/11 | N/A | N/A | N/A | N/A | N/A | 20000000 | N/A | 1-14/5/11 | 16-23/7/11 |  | 30/8/11 | 31/3/12 | 20000000
Maintenance and Operations of the Livestock Muultiplication and Breeding Centres |  | B1 | BOQ | Repeat | 15000000 |  | MTB | 1-14/4/2011 | 15-30/4/11 | N/A | N/A | N/A | N/A | N/A | 15000000 | N/A | 1-14/5/11 | 16-23/7/11 |  | 30/8/11 | 31/3/12 | 15000000
Rehabilitation of Some Field Offices |  | C1 | BOQ | OCB | 30000000 |  | MTB | 1-14/4/2011 | 15-30/4/11 | N/A | N/A | N/A | N/A | N/A | 30000000 | N/A | 1-14/5/11 | 16-23/7/11 |  | 30/8/11 | 30/11/11 | 30000000
Provision of Watering facilities(One earthdam and two handpump boreholes) in Bobi Grazing Reserve,Niger State |  | A6 | BOQ | Repeat | 16920000 |  | MTB | 1-14/4/2011 | 15-30/4/11 | N/A | N/A | N/A | N/A | N/A | 16920000 | N/A | 1-14/5/11 | 16-23/7/11 |  | 30/8/11 | 30/11/11 | 16920000
Provision of Watering facilities(One earthdam and two handpump boreholes) in Sankara Grazing Reserve, Jigawa State |  | A7 | BOQ | Repeat | 16860000 |  | MTB | 1-14/4/2011 | 15-30/4/11 | N/A | N/A | N/A | N/A | N/A | 16860000 | N/A | 1-14/5/11 | 16-23/7/11 |  | 30/8/11 | 30/11/11 | 16860000
Provision of Watering facilities(One earthdam and two handpump boreholes) in Zamfara Grazing Reserve, Zamfara State |  | A8 | BOQ | Repeat | 17070000 |  | MTB | 1-14/4/2011 | 15-30/4/11 | N/A | N/A | N/A | N/A | N/A | 17070000 | N/A | 1-14/5/11 | 16-23/7/11 |  | 30/8/11 | 30/11/11 | 17070000
Total Cost |  |  |  |  | 312141000 | [9 empty] | 312141000 | [6 empty] | 312141000
Ministry/Department/Agency: | FISHERIES
Budgetary Year: | 2011 | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: | MR FF ADEYEMI /07032902444 | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
Provision of Supporting infrastructure for The Lagos Fishery Harbour that will be developed on PPP Basis with Private Investors to boost Industrial Fisheries | B | 1 | Bill of Quantities | National Competitive Bidding | 550000000 | Prequalification | Post Review | 1/03/11 | 15/03/11 | 29/03/11 | 11/04/11 | 25/04/11 | 09/05/11 | 14/05/11 | 550000000 | 01/06/11 | 26/07/11 | 14/08/11 | 31/09/11 | 14/10/11 | 28/11/11 | 550000000
[8 empty] | 1/03/11 | 15/03/11 | 29/03/11 | 11/04/11 | 25/04/11 | 09/05/11 | 14/05/11 |  | 01/06/11 | 26/07/11 | 14/08/11 | 31/09/11 | 14/10/11 | 28/11/11
Fish Trade and Market Development Project in Conjunction with Cooperative Department and Registered Fishermen Cooperative Societies | B | 2 | Bill of Quantities | National Competitive Bidding | 40000000 | Post Qualification | Post Review | 1/03/11 | 15/03/11 | 29/03/11 | 11/04/11 | 25/04/11 | 09/05/11 | 14/05/11 | 40000000 | 01/06/11 | 26/07/11 | 14/08/11 | 31/09/11 | 14/10/11 | 28/11/11 | 40000000
[8 empty] | 1/03/11 | 15/03/11 | 29/03/11 | 11/04/11 | 25/04/11 | 09/05/11 | 14/05/11
Construction of Earthdam at National Aquaculture Centre Kuje and other Anxillary Facilities which will be an Aquaculture Technology Transfer Centre | B | 3 | Bill of Quantities | National Competitive Bidding | 80000000 | Post Qualification | Post Review | 1/03/11 | 15/03/11 | 29/03/11 | 11/04/11 | 25/04/11 | 09/05/11 | 14/05/11 | 80000000 | 01/06/11 | 26/07/11 | 14/08/11 | 31/09/11 | 14/10/11 | 28/11/11 | 80000000
[8 empty] | 1/03/11 | 15/03/11 | 29/03/11 | 11/04/11 | 25/04/11 | 09/05/11 | 14/05/11 |  | 01/06/11 | 26/07/11 | 14/08/11 | 31/09/11 | 14/10/11 | 28/11/11
Total Cost
NATIONL FOOD RESERVE AGENCY
Budgetary Year:2011 - PROJECTS | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: DR. M.I. LAWAL 08073312154 |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Threshold | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
On-going construction of one-stop 21 Agro Input Market Centre Phase II | NFRA/Works/APM/01/2011 | 21 | BOQ | NCB | 1470000000 | POST | MTB | 31/01/11 | 21/02/11 | 22/03/11 | 22/03/11 | 19/04/11 | 03/05/11 | 1/05/11 | 1470000000 | NA | 17/05/11 | 24/05/11 | 16/06/11 | 12/10/11 | 7/11/11 | 1470000000
Minor Refurblishment of 8 Silo Complexes | NFRA/Works/FRS/02/2011 | 8 | BOQ | NCB | 400000000 | Post | MTB | 31/01/11 | 21/02/11 | 22/03/11 | 22/03/11 | 19/04/11 | 03/05/11 | 1/05/11 | 400000000 | NA | 17/05/11 | 24/05/11 | 16/06/11 | 12/10/11 | 7/11/11 | 400000000
Total Cost |  |  |  |  | 1870000000 | [9 empty] | 1870000000 | [6 empty] | 1870000000
Ministry/Department/Agency: | NATIONL FOOD RESERVE AGENCY
Budgetary Year: 2010 - SIFA PROJECTS | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: DR. M.I. LAWAL 08073312154 |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Threshold | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
Integrated Livestock Market | NFRA/Works/SIFA/ 02/ 2010 | 5 | BOQ | Selective Tendering | 6500000000 |  | FEC | 15/4/10 | 20/04/10 | N/A | 04/05/10 | 02/06/10 | 15/06/10 | 22/06/10 | 6500000000 | 18/8/10 | 24/08/10 | 26/08/10 | 30/08/10 | 16/1/11 | 26/05/11 | 6500000000
Integrated Fish Estate | NFRA/Works/SIFA/ 03/2010 | 2 | BOQ | Selective Tendering | 2600000000 |  | FEC | 15/4/10 | 20/04/10 | N/A | 04/05/10 | 02/06/10 | 15/06/10 | 22/06/10 | 2600000000 | 18/8/10 | 24/08/10 | 26/08/10 | 30/08/10 | 16/1/11 | 26/05/11 | 2600000000
Farmers Markets | NFRA/Works/SIFA/ 04/2010 | 6 | BOQ | Selective Tendering | 1579620000 |  | MTB | 15/4/10 | 20/04/10 | N/A | 04/05/10 | 02/06/10 | 15/06/10 | 22/06/10 | 1579620000 | N/A | 24/08/10 | 26/08/10 | 30/08/10 | 16/1/11 | 18/3/11 | 1579620000
Food Courts | NFRA/Works/SIFA/ 05/2010 | 6 | BOQ | Selective Tendering | 1635000000 |  | MTB | 15/4/10 | 20/04/10 | N/A | 04/05/10 | 02/06/10 | 15/06/10 | 22/06/10 | 1635000000 | N/A | 24/08/10 | 26/08/10 | 30/08/10 | 16/1/11 | 18/2/11 | 1635000000
Exports Crop Handling, Preservation and Conditioning Centre | NFRA/Worls/SIFA/ 06/2010 | 4 | BOQ | Selective Tendering | 4800000000 |  | MTB | 15/4/10 | 20/04/10 | N/A | 04/05/10 | 02/06/10 | 15/06/10 | 22/06/10 | 4800000000 | 18/8/10 | 24/08/10 | 26/08/10 | 30/08/10 | 16/1/11 | 26/4/11 | 4800000000
Commodity Out-growers Development Centres (CODEC) | NFRA/Works/SIFA/ 07/2010 | 20 | BOQ | Selective Tendering | 78000000000 |  | FEC | 15/4/10 | 20/04/10 | N/A | 04/05/10 | 02/06/10 | 15/06/10 | 22/06/10 | 78000000000 | 18/8/10 | 24/08/10 | 26/08/10 | 30/08/10 | 16/1/11 | 26/05/11 | 78000000000
On-going construction of One-stop Agro Input Market Centre (86 Units) | NFRA/Works/SIFA/FA/ 01/2010 | 37 | BOQ | Selective Tendering | 4300000000 |  | FEC | 15/4/10 | 20/4/2010 | N/A | 4/5/2010 | 2/06/2010 | 15/06/2010 | 22/06/2010 | 4300000000 | 18/8/10 | 24/08/10 | 26/08/10 | 30/08/10 | 16/1/11 | 16/4/11 | 4300000000
Total Cost
Ministry/Department/Agency Cooperatives Dept.
Budgetary Year: 2011
Desk Officer/Contact |  | Basic Data | [5 empty] | Draft Bid Documents, including specs and quantities draft |  | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Draft Bid Documents, including specs and quantities draft |  | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation
Project Description | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgtary/Amt. in Nm | Pre-or Post Qualification | Prior or Post Review | Prep. & Submission by MDAs | No. objection Date | Adveristment for Proc. Quantities | Bid Invitation Date | Bid Closing/Opening | Submission Bid Eval. Report | No objection Date | Prep. & Submission by MDAs | No. objection Date | Adveristment for Proc. Quantities | Bid Invitation Date | Bid Closing/Opening | Submission Bid Eval. Report
List of Contracts | [7 empty] | 2-3 wks | 1-2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 -2 wks | 2-3 wks | 1-2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 -2 wks
Up-grading of National Cooperative Developnment Centre, (NCDC) Sheda. (i) Completion of Internal Road Network.
| FDC 1 | Lot 1 | BOQ | PCB | 25m | Pre Qualification | Post Review | Jan. - Feb. '11 | Feb. '11 | Feb. -Mar. '11 | Mar. '11 | Mar. - Apr. '11 | Apr. '11 | Apr. '11 | Jan. - Feb. '11 | Feb. '11 | Feb. -Mar. '11 | Mar. '11 | Mar. - Apr. '11 | Apr. '11 | Apr. '11
(ii) Completion of Landscaping / Car park | FDC 1 | Lot 2 | BOQ | PCB | 12m | Pre Qualification | Post Review | Jan. - Feb. '11 | Feb. '11 | Feb. -Mar. '11 | Mar. '11 | Mar. - Apr. '11 | Apr. '11 | Apr. '11 | Jan. - Feb. '11 | Feb. '11 | Feb. -Mar. '11 | Mar. '11 | Mar. - Apr. '11 | Apr. '11 | Apr. '11
(iii) Completion of senior staff quarters. | FDC 1 | Lot 3 | BOQ | PCB | 15m | Pre Qualification | Post Review | Jan. - Feb. '11 | Feb. '11 | Feb. -Mar. '11 | Mar. '11 | Mar. - Apr. '11 | Apr. '11 | Apr. '11 | Jan. - Feb. '11 | Feb. '11 | Feb. -Mar. '11 | Mar. '11 | Mar. - Apr. '11 | Apr. '11 | Apr. '11
(iv) Completion of drainage system | FDC 1 | Lot 4 | BOQ | PCB | 8m | Pre Qualification | Post Review | Jan. - Feb. '11 | Feb. '11 | Feb. -Mar. '11 | Mar. '11 | Mar. - Apr. '11 | Apr. '11 | Apr. '11 | Jan. - Feb. '11 | Feb. '11 | Feb. -Mar. '11 | Mar. '11 | Mar. - Apr. '11 | Apr. '11 | Apr. '11
(v) Staff training and development. | N/A | N/A | Lumpsum | In-house | 17m | N/A | N/A | In-house | N/A | N/A | N/A | N/A | N/A | N/A | In-house | N/A | N/A | N/A | N/A | N/A | N/A
Total Cost.
77m
Ministry/Department/Agency: Cooperatives Dept: Federal Cooperative College, Oji-River.
Budgetary Year: 2011 | [9 empty] | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact |  | Basic Data | [5 empty] | Draft Bid Documents, including specs and quantities draft |  | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgtary/Amt. in Nm | Pre-or Post Qualification | Prior or Post Review | Prep. & Submission by MDAs | No. objection Date | Adveristment for Proc. Quantities | Bid Invitation Date | Bid Closing/Opening | Submission Bid Eval. Report | No objection Date | Contract Amt. Certified in Nm | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization Advance Payment | Subtantial Completion | Final Acceptance | Final Cost
List of Contracts | [7 empty] | 2-3 wks | 1-2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 -2 wks
Completion of College Auditorium. | [7 empty] | Jan. - Feb. '11 | Feb. '11 | Feb. -Mar. '11 | Mar. '11 | Mar. - Apr. '11 | Apr. '11 | Apr. '11 | 25m | N/A | May '11 | May -Jun '11 | 15% | Sept. '11 | Oct. '11 | 25m
| FCCO 1 | Lot 1 | BOQ | PCB | 25m | Pre-Qualification | Post Review
Completion of College Erosion Control.
| FCCO 1 | Lot 2 | BOQ | Negotiation (On-going) | 9.23m | Post | Post Review | Jan. - Feb. '11 | Feb. '11 | Feb. -Mar. '11 | Mar. '11 | Mar. - Apr. '11 | Apr. '11 | Apr. '11 | 9.23m | N/A | May '11 | May -Jun '11 | 15% | Sept. '11 | Oct. '11 | 9.23m
[8 empty] | Jan. - Feb. '11 | Feb. '11 | Feb. -Mar. '11 | Mar. '11 | Mar. - Apr. '11 | Apr. '11 | Apr. '11
TOTAL | [14 empty] | 34.23M | [6 empty] | 34.23M
34.23M
Ministry/Department/Agency Cooperatives Dept: Federal Cooperative College, Kaduna
Budgetary Year: 2011
Desk Officer/Contact |  | Basic Data | [5 empty] | Draft Bid Documents, including specs and quantities draft |  | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgtary/Amt. in Nm | Pre-or Post Qualification | Prior or Post Review | Prep. & Submission by MDAs | No. objection Date | Adveristment for Proc. Quantities | Bid Invitation Date | Bid Closing/Opening | Submission Bid Eval. Report | No objection Date | Contract Amt. Certified in Nm | EFC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization Advance Payment | Subtantial Completion | Final Acceptance | Final Cost
List of Contracts | [7 empty] | 2-3 wks | 1-2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 -2 wks
Completion of the College Internal Road Network (Phase 1)
| FCCK | Lot 1 | BOQ | Negotiation (On-going) | 13.4m | Post | Post Review
Completion of the College Internal Road Network (Phase 11) | [7 empty] | Jan. - Feb. '11 | Feb. '11 | Feb. -Mar. '11 | Mar. '11 | Mar. - Apr. '11 | Apr. '11 | Apr. '11 | 13.4m | N/A | May '11 | May -Jun '11 | 15% | Sept. '11 | Oct. '11 | 13.4m
| FCCK | Lot 2 | BOQ | Negotiation (On-going) | 7.5m | Post | Post Review
Construction of College Store.
| FCCK | Lot 3 | BOQ | PCB | 26.5m | Pre Qualification | Post Review | Jan. - Feb. '11 | Feb. '11 | Feb. -Mar. '11 | Mar. '11 | Mar. - Apr. '11 | Apr. '11 | Apr. '11 | 7.5m | N/A | May '11 | May -Jun '11 | 15% | Sept. '11 | Oct. '11 | 7.5m
[8 empty] | Jan. - Feb. '11 | Feb. '11 | Feb. -Mar. '11 | Mar. '11 | Mar. - Apr. '11 | Apr. '11 | Apr. '11 | 26.5m | N/A | May '11 | May -Jun '11 | 15% | Sept. '11 | Oct. '11 | 26.5m
NIGERIA AGRICULTURAL QUARANTINE SERVICE | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
|  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
add 2 wks
List of Contracts
Construction of 120no. Rooms of Stables in the animal quarantine station sheda, Abuja for Horses | NAQS/01 | LOT 01 | BOQ | NCB | 54734221 |  | MTB | 1-14 Feb 2011 | 15-20 Feb 2011 | 20 -4 Mar 2011 | 20 Mar 15 Apr 11 | 19 Apr 2011 | 20/4-4 May/11 | 4-11 May/11 | 54734221 | NA | 12-19 May/11 | 20-27/5/11 | NA | NA | 30Aug/11 | 54734221 | HOD/ADM | HOD/CP&P
Construction of spray race facilities, holding yard and inspection gallery for 50 animals (large animals) sheda, Abuja. | NAQS/02 | LOT 02 | BOQ | NCB | 35000000 |  | MTB | 1-14 Feb/11 | 15-20 Feb/11 | 20-4 Mar/11 | 20 Mar-19Apr/11 | 19 Apr 2011 | 20/4-4/5/11 | 4-11May 11 | 35,000,000.00 | Plan | 12-19 May/11 | 20-27/5/11 | NA | NA | NA | 35,000,000.00 | HOD/ADM | HOD/ADM
Fencing of Port Harcourt Quarantine Station | NAQS/03 | LOT 03 | BOQ | NCB | 7500000 |  | MTB | 1-14 Feb/11 | 15-20 Feb/11 | 20-4 Mar/11 | 20 Mar-19Apr/11 | 19 Apr 2011 | 20/4-4/5/11 | 4-11May 11 | 7500000 | NA | 12-19 May/11 | 20-27/5/11 | NA | NA | 30Aug/10 | 7500000 | HOD/ADM | HOD/CP&P
Procurement of 2no. 100KVA generating sets for aquatic resources hostel NARCO shed Ikeja, Lagos and NAQS Headquarters | NAQS/04 | LOT 04 | BOQ | NCB | 8000000 |  | MTB | 1-14 Feb/11 | 15-20 Feb/11 | 20-4 Mar/11 | 20 Mar-19Apr/11 | 19 Apr 2011 | 20May-4Jun/10 | 4-11Jun/10 | 8000000 | NA | 12-19 May/11 | 20-27/5/11 | NA | NA | 30Aug/10 | 8000000 | HOD/ADM | HOD/CP&P
Construction of Cold Room Shed/ Gate House for aquatic resources hostel NARCO shed Ikeja, Lagos. | NAQS/05 | LOT5 | BOQ | NCB | 4234000 |  | MTB | 1-14 Feb/11 | 15-20 Feb/11 | 20-4 Mar/11 | 20 Mar-19Apr/11 | 19 Apr 2011 | 20May-4Jun/10 | 4-11Jun/10 | 4234000 | NA | 12-19 May/11 | 20-27/5/11 | NA | NA | 30Aug/10 | 4234000 | HOD/ADM | HOD/CP&P
Drawings and payment for Bill of Quantities to Archismith Associates | NAQS/06 | LOT6 | BOQ | NCB | 8533000 |  | MTB | 1-14 Feb/11 | 15-20 Feb/11 | 20-4 Mar/11 | 20 Mar-19Apr/11 | 19 Apr 2011 | 20May-4Jun/10 | 4-11Jun/10 | 8533000 | NA | 12-19 May/11 | 20-27/5/11 | NA | NA | 30Aug/10 | 8533000 | HOD/ADM | HOD/CP&P
Construction of 2no. Boreholes and Overhead Tanks for aquatic resources Hostel Ikeja, Lagos and Quarantine Station Sheda, Abuja | NAQS/07 | LOT 7 | BOQ | NCB | 18000000 |  | MTB | 1-14 Feb/11 | 15-20 Feb/11 | 20-4 Mar/11 | 20 Mar-19Apr/11 | 19 Apr 2011 | 20May-4Jun/10 | 4-11Jun/10 | 18000000 | NA | 12-19 May/11 | 20-27/5/11 | NA | NA | 30Aug/10 | 18000000 | HOD/ADM | HOD/CP&P
Construction of Office Block/Clinic / Store for Animal Quarantine Station Sheda, Abuja | NAQS/08 | LOT 8 | BOQ | NCB | 10.546,583.00 |  | MTB | 1-14 Feb/11 | 15-20 Feb/11 | 20-4 Mar/11 | 20 Mar-19Apr/11 | 19 Apr 2011 | 20May-4Jun/10 | 4-11Jun/10 | 10.546,583.00 | NA | 12-19 May/11 | 20-27/5/11 | NA | NA | 30Aug/10 | 10.546,583.00 | HOD/ADM | HOD/CP&P
Conduct of Pest Crop Survey for Cassava and Ginger Nationwide | NAQS/09 | LOT 9 | BOQ | NCB | 51000000 |  | MTB | 1-14 Feb/11 | 15-20 Feb/11 | 20-4 Mar/11 | 20 Mar-19Apr/11 | 19 Apr 2011 | 20May-4Jun/10 | 4-11Jun/10 | 51000000 | NA | 12-19 May/11 | 20-27/5/11 | NA | NA | 30Aug/10 | 51000000 | HOD/ADM | HOD/CP&P
Programme on the control of fruitfly in Nigeria | NAQS/10 | LOT 10 | BOQ | NCB | 23000000 |  | MTB | 1-14 Feb/11 | 15-20 Feb/11 | 20-4 Mar/11 | 20 Mar-19Apr/11 | 19 Apr 2011 | 20May-4Jun/10 | 4-11Jun/10 | 23000000 | NA | 12-19 May/11 | 20-27/5/11 | NA | NA | 30Aug/10 | 23000000 | HOD/ADM | HOD/CP&P
Aquaculture Pest and Disease Survey in Nigeria | NAQS/11 | LOT 11 | BOQ | NCB | 10000000 |  | MTB | 1-14 Feb/11 | 15-20 Feb/11 | 20-4 Mar/11 | 20 Mar-19Apr/11 | 19 Apr 2011 | 20May-4Jun/10 | 4-11Jun/10 | 10000000 | NA | 12-19 May/11 | 20-27/5/11 | NA | NA | 30Aug/10 | 10000000 | HOD/ADM | HOD/CP&P
Note on A324: USER:
Note on A764: USER:
Note on A789: USER:
Note on A809: USER:

## Jos Ele Dist Cmpy
Ministry/Department/Agency: JOS ELECTRICITY DISTRIBUTION COMPANY
Budgetary Year: 2011 --- WORKS | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
|  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks |  | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
add 2 wks
List of Contracts | [5 empty] | YES/NO
COMPLETION OF ONGOING PROJECTS:
1x7.5MVA 33/11KV Power Transformer for replacement of faulty ones at West of Mines injection substation in Jos | JSW | JSW-1 | BOQ | NCB | 8500000 | N/A | PTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
1x15MVA 33/11KV Power Transformer for replacement of faulty one at Bauchi road injection substation in Jos | JSW | JSW-2 | BOQ | NCB | 12500000 | N/A |  | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A
[17 empty] | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
1x7.5MVA 33/11KV Transformer to relief 1x 15MVA and 1x7.5MVA at Tasha-Duku Gombe/Substation Renovation | JSW | JSW-3 | BOQ | NCB | 29,500,.000.00 | N/A |  | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A
[17 empty] | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
1x7.5MVA to 2x 7.5MVA, 33/11KV Transformers at Fadanamade, Bauchi | JSW | JSW-4 | BOQ | NCB | 35000000 | N/A |  | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A
[17 empty] | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Construction of 2KM of 11KV Lines to relief existing GRA 11KV Feeders at GOMBE | JSW | JSW-5 | BOQ | NCB | 7000000 | N/A |  | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Constrution of 8KM of 33KV Lines from Transmission to separate 7.5MVA 33/11kv Transformers from Dass Nobodo 33kv Feeder | JSW | JSW-6 | BOQ | NCB | 15000000 | N/A |  | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Constrution of 10KM of 33KV Lines from Transmission to 1x15MVA & 1x7.5MVA 33/11kv Injection S/S at Bauchi Road to separate them from rural portion. | JSW | JSW-7 | BOQ | NCB | 29500000 | N/A |  | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Standardization of 11KV feeder, 19KM from Vom to Riyom | JSW | JSW-8 | BOQ | NCB | 35000000 | N/A |  | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Replacement of burnt 2.5MVA, 33/11KV Transformer at Nassarawa gate Bauchi Town | JSW | JSW-9 | BOQ | NCB | 7,500,00.00 | N/A |  | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Construction of 11KV feeder 3KM from Rayfield Injection Substation to Fwevei. | JSW | JSW-10 | BOQ | NCB | 10500000 | N/A |  | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Upgrading of Facilities ( Office Buildings ) | JSW | JSW-15 | BOQ | NCB | 30000000 | N/A |  | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
NEW PROJECTS:
Trace Clearing and Widening of 11KV and 33KV Lines. | JSW | JSW-17 | BOQ | NCB | 15000000 | N/A |  | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Reconductoring of 11KV and 33KV Overhead Lines. | JSW | JSW-18 | BOQ | NCB | 40000000 | N/A |  | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Uprating of 1x7.5MVA to 1x15MVA33/11KV at Jos 'C' Injection S/S. | JSW | JSW-19 | BOQ | NCB | 120000000 | N/A |  | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Relocation of the existing 1x7.5MVA Substation at Jos 'C' to Kafin Tafawacoplete with new Switchgears | JSW | JSW-20 | BOQ | NCB | 100000000 | N/A |  | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement & Installation of single Phase PPM & accessories for Jos, Gboko, Otukpo, Gombe, and Bauchi Business Units | JSW | JSW-23 | BOQ | NCB | 300000000 | N/A |  | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement & Installation of Three Phase PPM & accessories for Jos, Gboko, Otukpo, Gombe, and Bauchi Business Units | JSW | JSW-24 | BOQ | NCB | 300000000 | N/A |  | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurementof 32No. Vending Machines | JSW | JSW-25 | BOQ | NCB | 56, 000,000.00 | N/A |  | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement & Installation of 43,902 Single Phase Electronic Meters & accessories for Jos, Gboko, Otukpo, Gombe, and Bauchi Business Units | JSW | JSW-26 | BOQ | NCB | 300000000 | N/A |  | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement & Installation of 5,488 Three Phase Electronic Meters & accessories for Jos, Gboko, Otukpo, Gombe, and Bauchi Business Units | JSW | JSW-27 | BOQ | NCB | 192080000 | N/A |  | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement & Installation of 20No. 11KV Panel Meters. | JSW | JSW-28 | BOQ | NCB | 12000000 | N/A |  | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Radiating of 4No. 33KV Line from New Makeri Transmission SubStation | JSW | JSW-30 | BOQ | NCB |  | N/A |  | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Construction of 1No. 11KV Overhead Line from Rayfield 2x15MVA, 33/11KV Injection Substation | JSW | JSW-31 | BOQ | NCB |  | N/A |  | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Radiating of 3No. 33KV Feeder from Pankshin 33KV Transmission SubStation | JSW | JSW-32 | BOQ | NCB |  | N/A |  | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Construction of 33KV Line to take over Mango from NESCO (4KM ) | JSW | JSW-71 | BOQ | NCB |  |  |  | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Rrehabilitation of Control Room/ Civil Works at Makeri Injection S/S. | JSW | JSW-72 | BOQ | NCB |  |  |  | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Rrehabilitation of Control Room/ Civil Works at Dilimi Injection S/S. | JSW | JSW-73 | BOQ | NCB |  |  |  | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Rrehabilitation of Control Room/ Civil Works at Dogan Dutse Injection S/S. | JSW | JSW-74 | BOQ | NCB |  |  |  | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Total Cost
1562080000
Fill gray cells only!
Ministry/Department/Agency: JOS ELECTRICITY DISTRIBUTION COMPANY
Budgetary Year: 2011 --- GOODS | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: 08034747229 |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Buudgetary Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing/ Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection/ Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 4 -6 wks |  | 2 wks | 2 - 4 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
add 2 wks
List of Contracts
NEW PROJECTS:
Procurement of 500KVA, 11/0.415KV and 500KVA, 33/0.415KV Distribution for relief of Substations. Procurement of O/H Line Distribution Materials for Construction of relief Substations. | JSG | JSG-11 | 50000000 | NCB | N/A | MTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of Various Test Equipment | JSG | JSG-12 | 10000000 | NCB | N/A | PTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Manpower Development and Safety | JSG | JSG-13 | 15000000 | NCB | N/A | PTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 800A 4- Way Feeder Pillar | JSG | JSG-14 | 30000000 | NCB | N/A | PTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of Critical Materials for Maintenance of the Network | JSG | JSG-16 | 30000000 | NCB | N/A | PTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
HT & LT Cables & Termination Kits | JSG | JSG-21 | 30000000 | NCB | N/A | PTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
33KV Fibre Glass Cross Arms to rehabilitate weak 33KV Lines | JSG | JSG-22 | 22000000 | NCB | N/A | PTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Purchase of Vehicles( Hiab, Lorry, Hilux Pickup Van etc ) | JSG | JSG-33 | 300000000 | NCB | Pre-Qualification | FEC | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 |  |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Office Equipment (Computer System & acessories, Filling Cabinets, Photocopiers, Air conditioners etc.) | JSG | JSG-34 | 300000000 | NCB | Pre-Qualification | FEC | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | q4 |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Purchase of Office Furnitures ( Tables & Chairs of various sizes etc.) | JSG | JSG-35 | 15000000 | NCB | N/A | PTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of Stationery Items & Computer Stationeries & Consumables. | JSG | JSG-36 | 8500000 | NCB | N/A | PTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Projector and Screen for Elightenment/Seminars/Training | JSG | JSG-37 | 1000000 | NCB | N/A | PTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of ACL Infrastructure and Software & IS'Audit training of for Auditors on the use of ACL Software/Consulting. | JSG | JSG-38 | 13730000 | NCB | N/A | PTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Audit control of AVR Billing System and Metering System & Procurement of Computer Laptops. | JSG | JSG-39 | 10250000 | NCB | N/A | PTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
MATERIALS FOR NETWORK MAINTENANCE/REHABILITATION OF S/Ss:
Procurement of 3000No. 10.6M Reinforced Concrete Poles for Bauchi, Gombe and Benue Business Units. | JSG | JSG - 40 | 120000000 | NCB | Pre-Qualification | FEC | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 4000No. 8.53M Reinforced Concrete Poles for Bauchi, Gombe and Benue Business Units. | JSG | JSG-41 | 140000000 | NCB | Pre-Qualification | FEC | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 14,400Metres 150mm2 X 4Core Underground Cable (LT) | JSG | JSG-42 | 28800000 | NCB | N/A | PTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 10,800Metres 70mm2 X 4Core Underground Cable (LT) | JSG | JSG-43 | 98280000 | NCB | N/A | MTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 2,400Metres 500mm2 X 1Core Underground Cable (LT) | JSG | JSG-44 | 32760000 | NCB | N/A | PTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 3,600Metres 300mm2 X 1Core Underground Cable (LT) | JSG | JSG-45 | 35100000 | NCB | N/A | PTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 500Drums of Transformer Oil | JSG | JSG-46 | 48750000 | NCB | N/A | PTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 130 No. of H.T. Fibre Ladder | JSG | JSG-47 | 21970000 | NCB | N/A | PTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 240 No. L.T. Fibre Ladder | JSG | JSG-48 | 36000000 | NCB | N/A | PTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 6,000No. Of 9ft Fibre Cross Arm | JSG | JSG-49 | 120000000 | NCB |  | FEC | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Pre-Qualification
Procurement of 5,000No. Of 6ft Fibre Cross Arm | JSG | JSG-50 | 90000000 | NCB | N/A | MTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 14Sets of Phasing Sticks | JSG | JSG-51 | 16800000 | NCB | N/A | PTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 38Sets of Operating Rods | JSG | JSG-52 | 2371200 | M/S | N/A | A/C Officer | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 3,000No. Feeder Pillar Units | JSG | JSG-53 | 45000000 | NCB | N/A | PTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 35mm2 X 1XLPE cable for 11KV | JSG | JSG-54 | 72900000 | NCB | N/A | MTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 45,000Meters of 70mm2 Copper Wire | JSG | JSG-55 | 70200000 | NCB | N/A | MTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 35No. Transformer Control Panel | JSG | JSG-56 | 105140525 | NCB |  | FEC | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Pre-Qualification
Procurement of 18no. Transformer Circuit Breaker | JSG | JSG-57 | 78300000 | NCB | N/A | PTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 10Sets of Free Standing 33KV VT | JSG | JSG-58 | 1620000 | M/S | N/A | A/C Officer | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 10Sets of Free Standing 33KV CT | JSG | JSG-59 | 1120000 | M/S | N/A | A/C Officer | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 20Sets of 110VDC charger with 5KVA AC Stabilizer | JSG | JSG-60 | 34000000 | NCB | N/A | PTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 28Sets of 110Battery Bank | JSG | JSG-61 | 42000000 | NCB | N/A | PTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 23No. Relays for 11KV Panels | JSG | JSG-62 | 19550000 | NCB | N/A | PTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 15No. Of 100KVA, 33/0.415KV Station Service Transformer | JSG | JSG-63 | 16500000 | NCB | N/A | PTB | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 40Mtrs of Copper bars for battery bank link | JSG | JSG-64 | 280000 | NCB | N/A | FEC | 7/2-28/2/2011 | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 240No. 800AMP 4 Ways Feeder Pillar | JSG | JSG-65 | 84000000 | NCB | Pre-Qualification | MTB |  | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011
[16 empty] | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 120No. Of 33KV D-Fuse Assembly ( Complete ). | JSG | JSG-66 | 5400000 | NCB | N/A | PTB |  | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 360No. Of 11KV D-Fuse Assembly ( Complete ). | JSG | JSG-67 | 12600000 | NCB | N/A | PTB |  | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 12No. 7-Segment 11KV Panels. | JSG | JSG-68 | 576000000 | NCB | Pre-Qualification | FEC |  | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 |  |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 120No. 33/0.415KV Distribution Transformers. | JSG | JSG-69 | 300000000 | NCB | Pre-Qualification | FEC |  | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 |  |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Procurement of 24,000Mtrs of 150mm2 Aluminum Conductor ( AAC ). | JSG | JSG-70 | 6864000 | NCB | N/A | PTB |  | 28/2-7/3/2011 | 7/3/-14/4/2011 | 7/3/2011 | 14/4/2011 | 15/4-29/4/2011 | N/A |  |  | 9/5-13/5/2011 | 14/5-20/5/11 | N/A | 1/6-31/10/2011 | 1/11-25/11/2011
Total Cost |  |  | 3097785725
Note on K105: BPP:

## Code of Conduct Bur
Ministry/Department/Agency: Code of Conduct Bureau
Budgetary Year: 2011 --- GOODS | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact: N. U. Hussaini |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing/ Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection/ Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 3 wks |  | 4 - 6 wks |  | 2 wks | 2-4 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
add 2 wks
List of Contracts
Office Stationaries/Computer Consumeables | NA | NA | 61259509 | DP | NA | MTB | 14-28 Feb | 1-3 March | 5 - 19 Marh | 20th May | 19th May | 3rd June | NA | 61259509 | NA | 30th June | 13th July | 30th July | 2011-08-30 | 2011-08-22 | Usman Biu | Director, A. K. Omoyola
Books | NA | NA | 5611086 | DP | NA | MTB | 14-28 Feb | 1-7 March | NA | 8th March | 7th April | 21st April | NA | 5611086 | NA | 17th May | 30th May | 17th June | 2011-07-17 | 2011-08-05 | VictoriA A. | Director, A. K. Omoyola
+
Printing of Non Security Documents | NA | NA | 9763122 | ST | NA | MTB | 8-22 March | 22 March-5 Ap | 6th April | 6th April | 5th May | 19th May | NA | 9763122 | NA | 21st June | 5th June | 22nd June | 2011-07-22 | 2011-08-06 | Usman Biu | Director, A. K. Omoyola
Printing of Security Documents | NA | NA | 2440780 | NCB | NA | Chairman | 1-22 March | 22 - 5 April | NA | 6th April | 5th May | 19th May | NA | 2440780 | NA | 21st June | 5th June | 22nd June | 2011-07-22 | 2011-05-06 | Usman Biu | Director, A. K. Omoyola
Motor Vehicle Fuel Cost | NA | NA | 8780730 | DP | NA | MTB | NA | Recurent | NA | NA | NA | NA | NA | 8780730 | NA | 1st January | 1st January | NA | On Demand |  | Stephen P. | Director, A. K. Omoyola
Plant/Generator Fuel Cost | NA | NA | 4045143 | DP | NA | Chairman | NA | Recurrent | NA | NA | NA | NA | NA | 4045143 | NA | 1st January | 1st January | NA | On Demand |  | Amba, E | Director, A. K. Omoyola
Monitoring and Evaluation document and Equipment | NA | NA | 54038400 | NCB | NA | MTB | 15-30 March | 2-10 April | 12-26 April | 11th March | 10th May | 24th May | NA | 45038407 | NA | 25th June | 5th June | On Demand | 2011-07-06 | 2011-07-20 | A. K. | Secretary, Alhassan Ibrahim
Omoyola
Production of Assets Declaration Packages | NA | NA | 54038409 | NCB | NA | MTB | 15-30 March | 2 - 10 April | 12-26 April | 11th April | 10th May | 24th May | NA | 45038409 | NA | 21st June | 5th June | On Demand | 2011-07-06 | 2011-07-20 | S. G. Abubakar | Secretary, Alhassan Ibrahim
Total Cost |  |  | 199977188 | [10 empty] | 199977188
Note on K8: BPP:

## Min Labour
Ministry/Department/Agency: Ministry of Labour
Budgetary Year: 2011 --- Goods |  |  | PROCUREMENT PLAN- GOODS |  |  |  | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
[7 empty] | 2011 |  |  | 2011 | 2011 | 2011 |  |  |  | 2011 | 2011
OFFICE STATIONERIES/COMPUTER CONSUMABLES | ML/MTB/GOODS/ |  | 35943195 | NATIONAL SHOPPING | N/A | POST | 10TH -21ST JANUARY | N/A | N/A | 7TH MARCH | 7TH MARCH -18TH APRIL | 2ND - 13TH MAY | N/A |  | N/A | 23RD-31ST MAY | 1ST -17TH JUNE
PURCHASE OF LIBRARY BOOKS & PERIODICALS | ML/MTB/GOODS/ |  | 20000000 | NATIONAL SHOPPING | N/A | POST | 10TH -21ST JANUARY | N/A | N/A | 7TH MARCH | 7TH MARCH -18TH APRIL | 2ND - 13TH MAY | N/A |  | N/A | 23RD-31ST MAY | 1ST -17TH JUNE
PRINTING OF NON SECURITY DOCUMENTS | ML/MTB/GOODS/ |  | 7931585 | NATIONAL SHOPPING | N/A | POST | 10TH -21ST JANUARY | N/A | N/A | 7TH MARCH | 7TH MARCH -18TH APRIL | 2ND - 13TH MAY | N/A |  | N/A | 23RD-31ST MAY | 1ST -17TH JUNE
PRINTING OF SECURITY DOCUMENTS | ML/MTB/GOODS/ |  | 2432233 | NATIONAL SHOPPING | N/A | POST | 10TH -21ST JANUARY | N/A | N/A | 7TH MARCH | 7TH MARCH -18TH APRIL | 2ND - 13TH MAY | N/A |  | N/A | 23RD-31ST MAY | 1ST -17TH JUNE
FIELD AND CAMPING MATERIALS SUPPLIES | ML/MTB/GOODS/ |  | 1243349 | NATIONAL SHOPPING | N/A | POST | 10TH -21ST JANUARY | N/A | N/A | 7TH MARCH | 7TH MARCH -18TH APRIL | 2ND - 13TH MAY | N/A |  | N/A | 23RD-31ST MAY | 1ST -17TH JUNE
PRINTING OF ANNUAL REPORT. | ML/MTB/GOODS/ |  | 10000000 | NCB | N/A | POST | 10TH -21ST JANUARY | N/A | N/A | 7TH MARCH | 7TH MARCH -18TH APRIL | 2ND - 13TH MAY | N/A |  | N/A | 23RD-31ST MAY | 1ST -17TH JUNE
PURCHASE OF PROJECT VEHICLES | ML/MTB/GOODS/ |  | 40000000 | NATIONAL SHOPPING | N/A | POST | 10TH -21ST JANUARY | N/A | N/A | 7TH MARCH | 7TH MARCH -18TH APRIL | 2ND - 13TH MAY | N/A |  | N/A | 23RD-31ST MAY | 1ST -17TH JUNE
PURCHASE VEHICLES FOR MAIDUGURI STATE OFFICE | ML/MTB/GOODS/ |  | 20000000 | NATIONAL SHOPPING | N/A | POST | 10TH -21ST JANUARY | N/A | N/A | 7TH MARCH | 7TH MARCH -18TH APRIL | 2ND - 13TH MAY | N/A |  | N/A | 23RD-31ST MAY | 1ST -17TH JUNE
PURCHASE OF OFFICE FURNITURE AND FITTINGS | ML/MTB/GOODS/ |  | 55000000 | NCB | N/A | POST | 10TH -21ST JANUARY | N/A | N/A | 7TH MARCH | 7TH MARCH -18TH APRIL | 2ND - 13TH MAY | N/A |  | N/A | 23RD-31ST MAY | 1ST -17TH JUNE
PURCHASE OF OFFICE FURNITURE AND EQUIPMENTPROJECTS) | ML/MTB/GOODS/ |  | 24000000 | NATIONAL SHOPPING | N/A | POST | 10TH -21ST JANUARY | N/A | N/A | 7TH MARCH | 7TH MARCH -18TH APRIL | 2ND - 13TH MAY | N/A |  | N/A | 23RD-31ST MAY | 1ST -17TH JUNE
PURCHASE OF LIBRARY BOOKS AND EQUIPMENT | ML/MTB/GOODS/ |  | 20000000 | NCB | N/A | POST | 10TH -21ST JANUARY | N/A | N/A | 7TH MARCH | 7TH MARCH -18TH APRIL | 2ND - 13TH MAY | N/A |  | N/A | 23RD-31ST MAY | 1ST -17TH JUNE
PURCHASE OF CALCULATORS WITH CASTING ROLLS | ML/MTB/GOODS/ |  | 3000000 | NATIONAL SHOPPING | N/A | POST | 10TH -21ST JANUARY | N/A | N/A | 7TH MARCH | 7TH MARCH -18TH APRIL | 2ND - 13TH MAY | N/A |  | N/A | 23RD-31ST MAY | 1ST -17TH JUNE
PURCHASE OF SECURITY EQUIPMENT (SAVES AND PROCUREMENT EQUIPMENT) | ML/MTB/GOODS/ |  | 14000000 | NATIONAL SHOPPING | N/A | POST | 10TH -21ST JANUARY | N/A | N/A | 7TH MARCH | 7TH MARCH -18TH APRIL | 2ND - 13TH MAY | N/A |  | N/A | 23RD-31ST MAY | 1ST -17TH JUNE
COMPUTERIZATION OF 36 STATE LABOUR OFFICES/FCT AND OTHER SECTIONS OF THE MINISTRY |  |  | 700000000 | NCB | N/A | POST | 10TH -21ST JANUARY | N/A | N/A | 7TH MARCH | 7TH MARCH -18TH APRIL | 2ND - 13TH MAY | N/A |  | N/A | 23RD-31ST MAY | 1ST -17TH JUNE
COMPUTERIZATION OF FINANCE AND ACCOUNTS (NETWORKING OF FINAL ACCOUNTS, BANK RECONCILIATION, FUNDS AND BUDGET DIVISION) |  |  | 60000000 | NCB | N/A | POST | 10TH -21ST JANUARY | N/A | N/A | 7TH MARCH | 7TH MARCH -18TH APRIL | 2ND - 13TH MAY | N/A |  | N/A | 23RD-31ST MAY | 1ST -17TH JUNE
Total Cost
Fill gray cells only!
Ministry/Department/Agency: |  |  | PROCUREMENT PLAN: WORKS
Budgetary Year: | 2011 | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: | IBRAHIM IDRIS 08033156429 | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts | [7 empty] | 2011 |  |  | 2011 | 2011 |  | 2011 |  |  | 2011
REHABILITATION / REPAIRS - HOUSING | ML/MTB/WORKS/ | N/A | BILL OF QUANTITIES | NCB | 50000000 | POST | POST | 24TH JAN.-10TH FEB | N/A | N/A | 7TH MARCH | 7TH MARCH -18TH APRIL | N/A | 2ND - 13TH MAY |  | N/A | 23RD-31ST MAY | 1ST -17TH JUNE
EXPANSION OF TRADE TEST WORKSHOP AND PURCHASE OF TOOLS AND EQUIPMENT | ML/MTB/WORKS/ | N/A | BILL OF QUANTITIES | NCB | 120000000 | POST | POST | 24TH JAN.-10TH FEB | N/A | N/A | 7TH MARCH | 7TH MARCH -18TH APRIL | N/A | 2ND - 13TH MAY |  | N/A | 23RD-31ST MAY | 1ST -17TH JUNE
ESTABLISHMENT OF OCCUPATIONAL SAFETY AND HEALTH INSTITUTE/LABORATORY IN UMUAHIA | ML/MTB/WORKS/ | N/A | BILL OF QUANTITIES | NCB | 120000000 | POST | POST | 24TH JAN.-10TH FEB | N/A | N/A | 7TH MARCH | 7TH MARCH -18TH APRIL | N/A | 2ND - 13TH MAY |  | N/A | 23RD-31ST MAY | 1ST -17TH JUNE
Total Cost |  |  |  |  | 290000000
Fill gray cells only!
MINISTRY OF LABOUR |  |  | PROCUREMENT PLAN- CONSULTANCY
Ministry/Department/Agency:
Norm Duration of Proc Steps | 2011 | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: IBRAHIM IDRIS 08033156429 |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [6 empty] | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Prior/Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement | Lead-time before shortlist | Submission Date | No-objection Date | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks |  | 4 wk |  | 3 wks
Actual
List of Contracts
RESEARCH AND DEVELOPMENT |  |  |  |  | Plan
Actual
NATIONWIDE SURVEY ON THE ELIMINATION OF CHILD LABOUR HUMAN TRAFFICKING AND FORCED LABOUR | QCBS |  | 45000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A | YET TO BE DETERMINED | 6TH JULY | N/A | 15TH JULY
Actual
PUBLICATION OF ANNUAL SURVEY AND BULLETIN OF LABOUR STATISTICLE REPORTS | QCBS |  | 15000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A | YET TO BE DETERMINED | 6TH JULY | N/A | 15TH JULY
Actual
ESTABISHMENT E-LIBRARY | QCBS |  | 50000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A |  | 6TH JULY | N/A | 15TH JULY
[5 empty] | Actual | [15 empty] | YET TO BE DETERMINED
CONDUCT OF ILO OCTOBER ENQUIRY OF SELECTED FOOD ITERMSNATIONAL WIDE PLACE HIV / AIDS RESPONSE | QCBS |  | 10000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A | YET TO BE DETERMINED | 6TH JULY | N/A | 15TH JULY
Actual
NATIONAL WORK PLACE HIV/AIDS RESPONSE PROGRAMME | QCBS |  | 25000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A | YET TO BE DETERMINED | 6TH JULY | N/A | 15TH JULY
Actual
NATIONWIDE ESTABLISHMENT SAMPLE SURVEY ON EMPLOYMENT,WAGES,EARNINGS AND WORK HOURS OF WORK | QCBS |  | 60000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A | YET TO BE DETERMINED | 6TH JULY | N/A | 15TH JULY
Actual
NATIONAL ESTABLISHMENT SAMPLE SURVEY ON STRIKES AND LOCKOUTS | QCBS |  | 15000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A | YET TO BE DETERMINED | 6TH JULY | N/A | 15TH JULY
Actual
LABOUR AND FACTORIES INSPECTION OF WORK PLACES | QCBS |  | 50000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A | YET TO BE DETERMINED | 6TH JULY | N/A | 15TH JULY
Actual
NATIONAL PROGRAMME ON ELIMINATION OF THE WORST FORM OF CHILD LABOUR | QCBS |  | 25000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A | YET TO BE DETERMINED | 6TH JULY | N/A | 15TH JULY
Actual
NATIONAL RESPONSE ON HIV/AIDS |  |  | 25000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A | YET TO BE DETERMINED | 6TH JULY | N/A | 15TH JULY
Actual
NATIONAL COUNCIL ON OCCUPATIONAL SAFETY AND HEALTH |  |  | 20000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A | YET TO BE DETERMINED | 6TH JULY | N/A | 15TH JULY
Actual
CRISIS/EMERGENCY RESPONSE: INTERVENTION AND ENFORCEMENT ACTION ON RECALCITTRANTS |  |  | 25000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A | YET TO BE DETERMINED | 6TH JULY | N/A | 15TH JULY
Actual
EXTENTION OF LABOUR PROTECTION SERVICES TO INFORMAL SECTOR OF THE ECONOMY |  |  | 15000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A | YET TO BE DETERMINED | 6TH JULY | N/A | 15TH JULY
Actual
QUALITY ASSURANCE AND UNIVERSAL COVERAGE OF THE REGISTRATION INSPECTION AND CERTIFICATION OF PRESSURE VESSEL LIFFTING EQUIPMENT AND COMPETENT PERSONS | QCBS |  | 50000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A | YET TO BE DETERMINED | 6TH JULY | N/A | 15TH JULY
Actual
NATIONAL STAKEHOLDERS' CONFERENCE ON SAFETY |  |  | 15000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A | YET TO BE DETERMINED | 6TH JULY | N/A | 15TH JULY
Actual
NATIONAL PROGRAMME ON ELIMINATION OF UNFAIR LABOUR PRACTICES IN VARIOUS SECTOR OF THE ECONOMY |  |  | 10000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A | YET TO BE DETERMINED | 6TH JULY | N/A | 15TH JULY
Actual
SAFEGUARD PROGRAMME FOR STREET CLEANERS(MANAGER) AGAINST STREET AND JOB HARSARDS |  |  | 20000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A | YET TO BE DETERMINED | 6TH JULY | N/A | 15TH JULY
Actual
SPECIAL OCCUPATIONAL SAFETY AND HEALTH INTERVENTION IN CONSTRUCTION INDUSTRY |  |  | 20000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A | YET TO BE DETERMINED | 6TH JULY | N/A | 15TH JULY
Actual
DEVELOPMENT AND IMPLEMENTATION OF THE NATIONAL POLICY ON PRODUCTIVITY | QCBS |  | 139000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A | YET TO BE DETERMINED | 6TH JULY | N/A | 15TH JULY
Actual
NATIONAL SURVEY OF WAGES AND TRENDS IN PRODUCTIVITY | QCBS |  | 60000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A | YET TO BE DETERMINED | 6TH JULY | N/A | 15TH JULY
Actual
DEVELOPMENT OF SECTORAL PRODUCTIVITY STANDARDS | QCBS |  | 25000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A | YET TO BE DETERMINED | 6TH JULY | N/A | 15TH JULY
Actual
DEVELPOMENT OF NATIONAL INDUSTRIAL DIRECTORY | QCBS |  | 40000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A | YET TO BE DETERMINED | 6TH JULY | N/A | 15TH JULY
Actual
DEVELOPMENT AND IMPLEMENTATION OF INTERNATIONAL AND NATIONAL LABOUR STANDARDS AND PROTOCOLS | QCBS |  | 30000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A | YET TO BE DETERMINED | 6TH JULY | N/A | 15TH JULY
Actual
MONITORING AND EVELUATION OF CAPITAL PROJECTS, PROGRAMMES AND POLICIES OF THE MINISTRY AND ITS PARASTATALS. |  |  | 25000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A | YET TO BE DETERMINED | 6TH JULY | N/A | 15TH JULY
Actual
NATIONAL SURVEY ON LABOUR CONDITION IN THE MARITIME SECTOR | QCBS |  | 20000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A |  | 6TH JULY | N/A | 15TH JULY
[5 empty] | Actual | [15 empty] | YET TO BE DETERMINED
RESEARCH ON THE IMPACT OF LABOUR INSPECTIONS ON INDUSTRIAL PEACE IN NIGERIA. | QCBS |  | 40000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A |  | 6TH JULY | N/A | 15TH JULY
[5 empty] | Actual | [15 empty] | YET TO BE DETERMINED
DECENT WORK COUNTRY PROGRAMME (DWCP) | QCBS |  | 50000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A | YET TO BE DETERMINED | 6TH JULY | N/A | 15TH JULY
Actual
IMPLEMENTATION OF NATIONAL EMPOLYMENT | QCBS |  | 190000000 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A | YET TO BE DETERMINED | 6TH JULY | N/A | 15TH JULY
Actual
DEVELOPMENT OF UNEMPLOYMENT DATABASE | QCBS |  | 1333333334 | POST | Plan | 10TH -21ST JANUARY | N/A | 7TH -18TH MARCH | 22nd-31st MARCH | 4TH APRIL | N/A | 11TH TO | 29TH APRIL | 2ND -13TH MAY | N/A | 16TH MAY | 30TH MAY | 9TH JUNE | 20TH JUNE | N/A | YET TO BE DETERMINED | 6TH JULY | N/A | 15TH JULY
Actual
Total Cost |  |  |  |  | Plan

## EFCC
PROCUREMENT PLAN - GOODS - 2011
COUNTRY: NIGERIA
PROJECT: ECONOMIC AND FINANCIAL CRIMES COMMISSION (EFCC)
Description | Package No. | Basic Data | [5 empty] | Draft Bid Doc. Including Specs. & Quantities, draft SPN |  | If Post Review, NO datas are not needed |  |  | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation
|  | Lot No. | Est. amount Naira | Est. Amount US$'000 | Proc. Method | Pre/Post Qualif. | Prior or Post Review | Pre & Submission by Exec. Agent | NO Date | SPN Advert | Bidding period |  | Submission Bid Eval. Rpt. | NO Date | Contract Amount in NAIRA | Date of Contract Award | Date Contract Signature | Opening of Let. of Credit | Arrival of Goods | Inspection of Final Accpt
[10 empty] | On-line UNDB Gateway Nat. Press | Bid Invitation Date | Bid Closing & Opening Date
VEHICLES AND EQUIPMENT
1. Furniture for Zonal Offices | EFCC/NCB/11/01 | 1 | 60, 000,000.00 |  | NCB | Post | Post | 2011-04-03 |  | NA | 2011-01-04 | 15/4/11 | 14/4/11 | 29/4/11 | 60, 000,000.00 | 13/5/11 | 14/5/11 | NA | 2011-03-06
2. Supply of Arms and Ammunition | EFCC/NCB/11/02 | 2 | 200000000 |  | NCB | Post | Post | 2011-04-03 |  | NA | 2011-01-04 | 15/4/11 | 14/4/11 | 29/4/11 | 200000000 | 13/5/11 | 14/5/11 | NA | 2011-03-06
3. Supply of Bullet proof Vests | EFCC/NCB/11/03 | 3 | 30000000 |  | NCB | Post | Post | 2011-04-03 |  | NA | 2011-01-04 | 15/4/11 | 14/4/11 | 29/4/11 | 30000000 | 13/5/11 | 14/5/11 | NA | 2011-03-06
4. Purchase of ICT Equipment | EFCC/NCB/11/04 | 4 | 360000000 |  | NCB | Post | Post | 2011-04-03 |  |  | 2011-01-04 | 15/4/11 | 14/4/11 | 29/4/11 | 360000000 | 13/5/11 | 14/5/11 | NA | 2011-03-06
5. Purchase of Radio Communication Equipment | EFCC/NCB/11/05 | 5 | 25000000 |  | NCB | Post | Post | 2011-04-03 |  |  | 2011-01-04 | 15/4/11 | 14/4/11 | 29/4/11 | 25000000 | 13/5/11 | 14/5/11 | NA | 2011-03-06
6. Purchase of Of Office Vehicles | EFCC/NCB/11/06 | 6 | 175000000 |  | NCB | Post | Post | 2011-04-03 |  | NA | 2011-01-04 | 15/4/11 | 14/4/11 | 29/4/11 | 175000000 | 13/5/11 | 14/5/11 | NA | 2011-03-06
10000000
7. Purchase of Ambulance | EFCC/NCB/11/07 | 7 | 10000000 |  | NCB | Post | Post | 2011-04-03 |  | NA | 2011-01-04 | 15/4/11 | 14/4/11 | 29/4/11 |  | 13/5/11 | 14/5/11 | NA | 31/5/11
8. Purchase of Office Equipment | EFCC/NCB/11/08 | 8 | 100000000 |  | NCB | Post | Post | 2011-04-03 |  | NA | 2011-01-04 | 15/4/11 | 14/4/11 | 29/4/11 | 100000000 | 13/5/11 | 14/5/11 | NA | 2011-03-06
9.Office Furniture | EFCC/NCB/11/09 | 9 | 80000000 |  | NCB | Post | Post | 2011-04-03 |  | NA | 2011-01-04 | 15/4/11 | 14/4/11 | 29/4/11 | 80000000 | 13/5/11 | 14/5/11 | NA | 2011-03-06
TOTAL |  |  | 1,040,000,000.00
Procurement Plan - WORKS
Country/Organisation:Nigeria: Economic and Financial Crime Commission (EFCC)
[8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
IDA Credit No: ….. UNI |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation
Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Estimated Amount in US $ | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount in NAIRA | Date Contract Award | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks |  | 1 wk | 1.5-3 wks
add 7-13 wks
List of Contracts
Construction of additional Office buildings in zonal offices | EFCC/NCB/11 | 01 |  | NCB | 90000000 | [5 empty] | 3/03/11 | 17/03/11 | 7/4/11 |  |  | 21/4/11 | 22/4/11
Completion of zonal offices cells | EFCC/NCB/11 | 02 |  | NCB | 90000000 | [5 empty] | 3/03/11 | 17/03/11 | 7/4/11 |  |  | 21/4/11 | 22/4/11
Landscaping- Head Office Car Park | EFCC/NCB/11 | 03 |  | NCB | 20000000 | [5 empty] | 3/03/11 | 17/03/11 | 7/4/11 |  |  | 21/4/11 | 22/4/11
Landscaping- Zonal Offices- Gombe/P.Harcourt | EFCC/NCB/11 | 04 |  | NCB | 110000000 | [5 empty] | 3/03/11 | 17/03/11 | 7/4/11 |  |  | 21/4/11 | 22/4/11
Construction of Indoor Shooting Range at new HQ | EFCC/NCB/11 | 05 |  | NCB | 100000000 | [5 empty] | 3/03/11 | 17/03/11 | 7/4/11 |  |  | 21/4/11 | 22/4/11
Total Cost |  |  |  |  | 410000000 | [15 empty] | 0
0

## Fed Min Justice
Ministry/Department/Agency: Federal Ministry Of Justice
Budget Year: 2011 --- Consultancy Services
| Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
Project Description | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation /Submission Date | Closing /Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/ Financial | Negotiations | MDA Approval /No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/ Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/ Designation | Name/ Designation
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 1 weeks | 2 - 4 weeks | 2 weeks | 2 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Government Contract Data Base Management System | FMJ/PROC/11/1 | 3 | Lump Sum | 1215319 |  | Accounting Officer: Permanent Secretary |  | NA | PST
Total Cost Plan |  |  |  | 1215319
Total Cost Actual
Ministry/Department/Agency: Federal Ministry Of Justice
Budget Year: 2011 --- Goods
| Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Goods |  |  | Action Party | Champion
Project Description | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Arrival of Goods | Inspection /Final Acceptance | Name/ Designation | Name /Designation
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
PURCHASE OF COMPUTERS | FMJ/PROC/11/1 | 1 | Bills of Quantity | 19000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST
Establishment of Justice Data Bank | FMJ/PRS/11/2 | 2 | Bills of Quantity | 3780991 | NCB | Accounting Officer: Permanent Secretary | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST
PURCHASE OF LIBRARY BOOKS AND EQUIPMENT | FMJ/PRS/11/1 | 2 |  | 105000000 | NCB | BPP issues "No Objection" to award/FEC approves | LERB - LOWEST EVALUATED RESPONSIVE BID | PRE | PRIOR
Total Cost Plan |  |  |  | 127780991
Total Cost Actual
Ministry/Department/Agency: Federal Ministry Of Justice
Budget Year: 2011 --- Work
| Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Works |  |  |  | Action Party | Champion
Project Description | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing /Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Name /Designation | Name /Designation
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
CONSTRUCTION/PROVISION OFFICE BUILDING | FMJ/PRS/11/2 | 3 | Bills of Quantity | 21000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST
REHABILITATION/REPAIRS OF OFFICE BUILDINGS | FMJ/PRS/11/4 | 4 | Bills of Quantity | 12000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST
Total Cost Plan |  |  |  | 33000000
Total Cost Actual

## Fed Neuro-Psy hospital
Ministry/Department/Agency: Federal Neuro-Psychiatric Hospital, Yaba Lagos
Budget Year: 2011 --- Goods
|  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice /Advert | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Goods |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/ Advance Payment | Arrival of Goods | Inspection/Final Acceptance | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
Plan vs Actual
PROCUREMENT OF UTILITY VEHICLES (HILUX DOUBLE CABIN 4 UNITS, TOYOTA HIACE 2 UNITS, TOYOTA COASTER BUS 2 UNITS, TOYOTA AVENSIS 5 UNITS AND TOYOTA AMBULANCE 2 UNITS) | Plan | FNPHY/2011/YB/01 | 1 |  | 45628304 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/05/11 - 13/06/11 | 13/06/11 - 24/06/11 | NA | 24/06/11 | 5/08/11 | 5/08/11 - 26/08/11 | 26/08/11 - 23/09/11 | NA | NA | 23/09/11 - 30/09/11 | 30/09/11 - 14/10/11 | 17/10/11 - 28/10/11 | 31/10/11 - 11/11/11 | 11/11/11 - 18/11/11 | OLAGOKE BABATUNDE - [Designation: SENIOR PROCUREMENT OFFICER] | OYETOLA RAZAQ - [Designation: Director]
Actual
PROCUREMENT AND INSTALLATION OF ONE(1) DIGITAL TELEPHONE PABX EQUIPMENT WITH FOUR EXTERNAL LINES FOR THE HOSPITAL | Plan | FNPHY/2011/YB/02 | 2 | Sch of Del | 6598555 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/05/11 - 13/06/11 | 13/06/11 - 24/06/11 | NA | 24/06/11 | 5/08/11 | 5/08/11 - 26/08/11 | 26/08/11 - 23/09/11 | NA | NA | 23/09/11 - 30/09/11 | 30/09/11 - 14/10/11 | 17/10/11 - 28/10/11 | 31/10/11 - 11/11/11 | 11/11/11 - 18/11/11 | OLAGOKE BABATUNDE - [Designation: SENIOR PROCUREMENT OFFICER] | OYETOLA RAZAQ - [Designation: Director]
Actual
PROCUREMENT AND INSTALATION OF ONE (1) 350KVA GENERATING SET FOR THE HOSPITAL | Plan | FNPHY/2011/YB/03 | 3 |  | 10529609 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/05/11 - 13/06/11 | 13/06/11 - 24/06/11 | NA | 24/06/11 | 5/08/11 | 5/08/11 - 26/08/11 | 26/08/11 - 23/09/11 | NA | NA | 23/09/11 - 30/09/11 | 30/09/11 - 14/10/11 | 17/10/11 - 28/10/11 | 31/10/11 - 11/11/11 | 11/11/11 - 18/11/11 | OLAGOKE BABATUNDE - [Designation: SENIOR PROCUREMENT OFFICER] | OYETOLA RAZAQ - [Designation: Director]
Actual
PROCUREMENT AND INSTALATION OF ONE (1) E.E.G. MACHINE FOR THE HOSPITAL | Plan | FNPHY/2011/YB/04 | 4 |  | 7019739 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/05/11 - 13/06/11 | 13/06/11 - 24/06/11 | NA | 24/06/11 | 5/08/11 | 5/08/11 - 26/08/11 | 26/08/11 - 23/09/11 | NA | NA | 23/09/11 - 30/09/11 | 30/09/11 - 14/10/11 | 17/10/11 - 28/10/11 | 31/10/11 - 11/11/11 | 11/11/11 - 18/11/11 | OLAGOKE BABATUNDE - [Designation: SENIOR PROCUREMENT OFFICER] | OYETOLA RAZAQ - [Designation: Director]
Actual
PROCUREMENT AND INSTALATION OF TWENTY (20) EMERGENCY ALERT SYSTEM FOR THE HOSPITAL | Plan | FNPHY/2011/YB/05 | 5 |  | 7019739 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/05/11 - 13/06/11 | 13/06/11 - 24/06/11 | NA | 24/06/11 | 5/08/11 | 5/08/11 - 26/08/11 | 26/08/11 - 23/09/11 | NA | NA | 23/09/11 - 30/09/11 | 30/09/11 - 14/10/11 | 17/10/11 - 28/10/11 | 31/10/11 - 11/11/11 | 11/11/11 - 18/11/11 | OLAGOKE BABATUNDE - [Designation: SENIOR PROCUREMENT OFFICER] | OYETOLA RAZAQ - [Designation: Director]
Actual
PROCUREMENT AND INSTALATION OF TWENTY (20) ALTERNATIVE POWER SUPPLY (INVERTERS) TO THE HOSPITAL WARDS | Plan | FNPHY/2011/YB/010 | 10 |  | 7019739 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/05/11 - 13/06/11 | 13/06/11 - 24/06/11 | NA | 24/06/11 | 5/08/11 | 5/08/11 - 26/08/11 | 26/08/11 - 23/09/11 | NA | NA | 23/09/11 - 30/09/11 | 30/09/11 - 14/10/11 | 17/10/11 - 28/10/11 | 31/10/11 - 11/11/11 | 11/11/11 - 18/11/11 | OLAGOKE BABATUNDE - [Designation: SENIOR PROCUREMENT OFFICER] | OYETOLA RAZAQ - [Designation: Director]
Actual
PROCUREMENT OF UTILITY VEHICLE TWO (2) TOYOTA CORROLLA, ONE (1) TOYOTA COASTER BUS AND ONE (1) TOYOTA HIACE AMBULANCE | Plan | FSOT/2011/OSD/001 | 1 | Bills of Quantity | 14039478 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/05/11 - 13/06/11 | 13/06/11 - 24/06/11 | NA | 24/06/11 | 5/08/11 | 5/08/11 - 26/08/11 | 26/08/11 - 23/09/11 | NA | NA | 23/09/11 - 30/09/11 | 30/09/11 - 14/10/11 | 17/10/11 - 28/10/11 | 31/10/11 - 11/11/11 | 11/11/11 - 18/11/11 | OLAGOKE BABATUNDE - [Designation: SENIOR PROCUREMENT OFFICER] | OYETOLA RAZAQ - [Designation: Director]
Actual
PROCUREMENT AND INSTALLATION OF (1) 350KVA GENERATING SET FOR THE SCHOOL OF OCCUPATIONAL THERAPY OSHODI | Plan | FSOT/2011/OSD/02 | 2 |  | 10529609 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/05/11 - 13/06/11 | 13/06/11 - 24/06/11 | NA | 24/06/11 | 5/08/11 | 5/08/11 - 26/08/11 | 26/08/11 - 23/09/11 | NA | NA | 23/09/11 - 30/09/11 | 30/09/11 - 14/10/11 | 17/10/11 - 28/10/11 | 31/10/11 - 11/11/11 | 11/11/11 - 18/11/11 | OLAGOKE BABATUNDE - [Designation: SENIOR PROCUREMENT OFFICER] | OYETOLA RAZAQ - [Designation: Director]
Actual
FURNISHING OF A BUILDING CONTAINING TWO CLASSROOMS ONE LECTURE THEARTER, ONE LABORATORY AND ADJOURNING ADMINISTRATIVE OFFICES | Plan | FSOT/2011/OSD/04 | 4 | Sch of Del | 3509870 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/05/11 - 13/06/11 | 13/06/11 - 24/06/11 | NA | 24/06/11 | 5/08/11 | 5/08/11 - 26/08/11 | 26/08/11 - 23/09/11 | NA | NA | 23/09/11 - 30/09/11 | 30/09/11 - 14/10/11 | 17/10/11 - 28/10/11 | 31/10/11 - 11/11/11 | 11/11/11 - 18/11/11 | OLAGOKE BABATUNDE - [Designation: SENIOR PROCUREMENT OFFICER] | OYETOLA RAZAQ - [Designation: Director]
Actual
Total Cost Plan |  |  |  |  | 111894642
Total Cost Actual
Ministry/Department/Agency: Federal Neuro-Psychiatric Hospital, Yaba Lagos
Budget Year: 2011 --- Works
|  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Works |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing /Opening | Submission of Bid Evaluation Report | MDA Approval/ BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization /Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Plan vs Actual
CONSTRUCTION AND EQUIPPING OF A FIVE ROOM BUNGALOW BUILDING FOR THE SERVICOM/AUDIT UNIT | Plan | FNPHY/2011/YB/07 | 7 | Bills of Quantity | 14039478 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/05/11 - 13/06/11 | 13/06/11 - 24/06/11 | NA | NA | 24/06/11 - 5/08/11 | NA | NA | 5/08/11 - 26/08/11 | 26/08/11 - 23/09/11 | NA | NA | 23/09/11 - 30/09/11 | 30/09/11 - 14/10/11 | 17/10/11 - 28/10/11 | 10/02/12 | 29/02/12 | 14039478
Actual
COMPLETION OF ADMINISTRATIVE BUILDING | Plan | FNPHY/2011/YB/06 | 6 | Bills of Quantity | 14039478 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/05/11 - 13/06/11 | 13/06/11 - 24/06/11 | NA | NA | 24/06/11 - 5/08/11 | NA | NA | 5/08/11 - 26/08/11 | 26/08/11 - 23/09/11 | NA | NA | 23/09/11 - 30/09/11 | 30/09/11 - 14/10/11 | 17/10/11 - 28/10/11 | 10/02/12 | 29/02/12 | 14039478 | OLAGOKE BABATUNDE - [Designation: SENIOR PROCUREMENT OFFICER] | OYETOLA RAZAQ - [Designation: Director]
Actual
UPGRADING AND EQUIPPING OF THE STORE/PROCUREMENT UNIT TO ONE STOREY BUILDING | Plan | FNPHY/2011/YB/08 | 8 | Bills of Quantity | 17549348 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/05/11 - 13/06/11 | 13/06/11 - 24/06/11 | NA | NA | 24/06/11 - 5/08/11 | NA | NA | 5/08/11 - 26/08/11 | 26/08/11 - 23/09/11 | NA | NA | 23/09/11 - 30/09/11 | 30/09/11 - 14/10/11 | 17/10/11 - 28/10/11 | 10/02/12 | 29/02/12 | 17549348 | OLAGOKE BABATUNDE - [Designation: SENIOR PROCUREMENT OFFICER] | OYETOLA RAZAQ - [Designation: Director]
Actual
COMPLETION OF A DEDICATED HIGH TENSION 11KVA FEEDER WITH 750KVA TRANSFORMER AND RECABLING EXISTING CABLE NETWORKS OF THE HOSPITAL | Plan | FNPHY/2011/YB/09 | 9 |  | 10529609 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/05/11 - 13/06/11 | 13/06/11 - 24/06/11 | NA | NA | 24/06/11 - 5/08/11 | NA | NA | 5/08/11 - 26/08/11 | 26/08/11 - 23/09/11 | NA | NA | 23/09/11 - 30/09/11 | 30/09/11 - 14/10/11 | 17/10/11 - 28/10/11 | 10/02/12 | 29/02/12 | 10529609 | OLAGOKE BABATUNDE - [Designation: SENIOR PROCUREMENT OFFICER] | OYETOLA RAZAQ - [Designation: Director]
Actual
REHABILITATION OF HOSPITAL WARDS | Plan | FNPHY/2011/YB/011 | 11 | Bills of Quantity | 10529609 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/05/11 - 13/06/11 | 13/06/11 - 24/06/11 | NA | NA | 24/06/11 - 5/08/11 | NA | NA | 5/08/11 - 26/08/11 | 26/08/11 - 23/09/11 | NA | NA | 23/09/11 - 30/09/11 | 30/09/11 - 14/10/11 | 17/10/11 - 28/10/11 | 10/02/12 | 29/02/12 | 10529609 | OLAGOKE BABATUNDE - [Designation: SENIOR PROCUREMENT OFFICER] | OYETOLA RAZAQ - [Designation: Director]
Actual
REHABILITATION AND CONSTRUCTION OF 15KM ACCESS ROAD WITHIN THE THE HOSPITAL PREMISES YABA | Plan | FNPHY/2011/YB/012 | 12 | Bills of Quantity | 17549348 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/05/11 - 13/06/11 | 13/06/11 - 24/06/11 | NA | NA | 24/06/11 - 5/08/11 | NA | NA | 5/08/11 - 26/08/11 | 26/08/11 - 23/09/11 | NA | NA | 23/09/11 - 30/09/11 | 30/09/11 - 14/10/11 | 17/10/11 - 28/10/11 | 10/02/12 | 29/02/12 | 17549348 | OLAGOKE BABATUNDE - [Designation: SENIOR PROCUREMENT OFFICER] | OYETOLA RAZAQ - [Designation: Director]
Actual
CONSTRUCTION OF 15KM ROAD NETWORKS AND ACCESS DRAINAGE SYSTEM OF THE HOSPITAL OSHODI ANNEXE | Plan | FNPHY/2011/YB/013 | 13 | Bills of Quantity | 17549348 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/05/11 - 13/06/11 | 13/06/11 - 24/06/11 | NA | NA | 24/06/11 - 5/08/11 | NA | NA | 5/08/11 - 26/08/11 | 26/08/11 - 23/09/11 | NA | NA | 23/09/11 - 30/09/11 | 30/09/11 - 14/10/11 | 17/10/11 - 28/10/11 | 10/02/12 | 29/02/12 | 17549348 | OLAGOKE BABATUNDE - [Designation: SENIOR PROCUREMENT OFFICER] | OYETOLA RAZAQ - [Designation: Director]
Actual
CONSTRUCTION OF REFUSE DUMP FOR THE HOSPITAL ANNEXE OSHODI | Plan | FNPHY/2011/YB/014 | 14 | Bills of Quantity | 10529609 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/05/11 - 13/06/11 | 13/06/11 - 24/06/11 | NA | NA | 24/06/11 - 5/08/11 | NA | NA | 5/08/11 - 26/08/11 | 26/08/11 - 23/09/11 | NA | NA | 23/09/11 - 30/09/11 | 30/09/11 - 14/10/11 | 17/10/11 - 28/10/11 | 10/02/12 | 29/02/12 | 10529609 | OLAGOKE BABATUNDE - [Designation: SENIOR PROCUREMENT OFFICER] | OYETOLA RAZAQ - [Designation: Director]
Actual
CONSTRUCTION OF A MULTIPURPOSE INFORMATION TECHNOLOGY BUILDING | Plan | FSOT/2011/OSD/03 | 3 | Bills of Quantity | 11933557 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/05/11 - 13/06/11 | 13/06/11 - 24/06/11 | NA | NA | 24/06/11 - 5/08/11 | NA | NA | 5/08/11 - 26/08/11 | 26/08/11 - 23/09/11 | NA | NA | 23/09/11 - 30/09/11 | 30/09/11 - 14/10/11 | 17/10/11 - 28/10/11 | 10/11/11 | 29/02/12 | 11933557 | OLAGOKE BABATUNDE - [Designation: SENIOR PROCUREMENT OFFICER] | OYETOLA RAZAQ - [Designation: Director]
Actual
Total Cost Plan |  |  |  |  | 124249384 | [21 empty] | 124249384
Total Cost Actual

## NERC
Ministry/Department/Agency: Nigerian Electricity Regulatory Commission
Budget Year: 2011 --- Consulting Services
| Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
Project Description | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/ Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/ No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/ Designation | Name/ Designation
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 1 weeks | 2 - 4 weeks | 2 weeks | 2 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Consultancy Services on Adequate Monitoring of Licensees |  |  | Lump Sum | 250000000 |  |  | CQ - Consultant&#039;s Qualification | NA
Engagement of Financial Advisory Services Consultant | NERC/CONSULT/001 |  | Lump Sum | 40000000 |  | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | NA | PST | NA | 28/03/11 - 11/04/11 | 11/04/11 - 22/04/11 | 25/04/11 - 2/05/11 | 2/05/11 | 2/05/11 - 16/05/11 | 16/05/11 - 27/05/11 | 27/05/11 - 27/05/11 | 30/05/11 - 10/06/11 | 13/06/11 - 24/06/11 | NA | 27/06/11 - 8/07/11 | 11/07/11 - 22/07/11 | 25/07/11 - 12/08/11 | 40000000 | NA | 15/08/11 - 26/08/11 | 29/08/11 - 12/09/11 | 12/09/11 - 16/09/11 | 10/10/11 | 28/11/11 | 40000000
Engagement of External Auditor | NERC/CONSULT/2011/002 |  |  | 7500000 |  | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | NA | PST | NA | 28/03/11 - 11/04/11 | 11/04/11 - 25/04/11 | 2/05/11 - 9/05/11 | 9/05/11 | 9/05/11 - 20/05/11 | 23/05/11 - 6/06/11 | 6/06/11 - 6/06/11 | 6/06/11 - 17/06/11 | 20/06/11 - 1/07/11 | NA | 4/07/11 - 15/07/11 | 18/07/11 - 22/07/11 | 25/07/11 - 5/08/11 | 7500000 | NA | 8/08/11 - 12/08/11 | 15/08/11 - 26/08/11 | 29/08/11 - 2/09/11 | 3/10/11 | 31/10/11 | 7500000
Engagement of Independent Electricity Distribution/Transmission Network Consultant | NERC/CONSULT/2011/003 |  | Lump Sum | 15500000 |  | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | NA | PST | NA | 28/03/11 - 11/04/11 | 11/04/11 - 25/04/11 | 25/04/11 - 29/04/11 | 2/05/11 | 2/05/11 - 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 30/05/11 | 30/05/11 - 13/06/11 | 13/06/11 - 27/06/11 | 27/06/11 - 27/06/11 | 27/06/11 - 11/07/11 | 11/07/11 - 15/07/11 | 18/07/11 - 29/07/11 | 15500000 | NA | 1/08/11 - 5/08/11 | 8/08/11 - 19/08/11 | 22/08/11 - 2/09/11 | 5/09/11 | 10/10/11 | 15500000
Development of Electric Network Construction Standard | NERC/CONSULT/2011/004 |  | Lump Sum | 42000000 |  | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | NA | PST | NA | 28/03/11 - 11/04/11 | 11/04/11 - 25/04/11 | 25/04/11 - 2/05/11 | 2/05/11 | 9/05/11 - 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 30/05/11 | 1/06/11 - 10/06/11 | 13/06/11 - 27/06/11 | 4/07/11 - 4/07/11 | 4/07/11 - 18/07/11 | 18/07/11 - 29/07/11 | 29/07/11 - 8/08/11 | 42000000 | NA | 8/08/11 - 19/08/11 | 22/08/11 - 5/09/11 | 5/09/11 - 16/09/11 | 26/09/11 | 7/11/11 | 42000000
Consultancy Services on Vegetation Control/Right of Way | NERC/CONSULT/2011/00 |  | Lump Sum | 42000000 |  | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | NA | PST | NA | 28/03/11 - 11/04/11 | 11/04/11 - 25/04/11 | 2/05/11 - 9/05/11 | 9/05/11 | 30/05/11 - 13/06/11 | 13/06/11 - 27/06/11 | 27/06/11 - 27/06/11 | 27/06/11 - 11/07/11 | 11/07/11 - 22/07/11 | 28/07/11 - 2/08/11 | 9/08/11 - 19/08/11 | 24/08/11 - 29/08/11 | 30/08/11 - 12/09/11 | 42000000 | NA | 19/09/11 - 30/09/11 | 3/10/11 - 17/10/11 | 17/10/11 - 31/10/11 | 1/11/11 | 30/11/11 | 42000000
Consultancy Services for the Regulation on Smart Metering | NERC/CONSULT/2011/00 |  | Lump Sum | 42000000 |  | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | NA | PST | NA | 28/03/11 - 11/04/11 | 11/04/11 - 25/04/11 | 25/04/11 - 2/05/11 | 2/05/11 | 3/05/11 - 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 30/05/11 | 30/05/11 - 10/06/11 | 13/06/11 - 24/06/11 | 30/06/11 - 30/06/11 | 4/07/11 - 11/07/11 | 18/07/11 - 20/07/11 | 25/07/11 - 5/08/11 | 42000000 | NA | 8/08/11 - 12/08/11 | 15/08/11 - 29/08/11 | 29/08/11 - 12/09/11 | 19/09/11 | 26/09/11 | 42000000
Consultancy Services on Regulation of GIS | NERC/CONSULT/2011/007 |  | Lump Sum | 27000000 |  | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | NA | PST | NA | 28/03/11 - 11/04/11 | 11/04/11 - 25/04/11 | 25/04/11 - 2/05/11 | 2/05/11 | 2/05/11 - 13/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 30/05/11 | 30/05/11 - 13/06/11 | 13/06/11 - 27/06/11 | 29/06/11 - 29/06/11 | 29/06/11 - 13/07/11 | 18/07/11 - 20/07/11 | 25/07/11 - 8/08/11 | 27000000 | NA | 8/08/11 - 12/08/11 | 15/08/11 - 26/08/11 | 29/08/11 - 9/09/11 | 12/09/11 | 14/11/11 | 27000000
Consultancy Services on Regulation on Smart Grid | NERC/CONSULT/2011/008 |  | Lump Sum | 25000000 |  | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | NA | PST | NA | 28/03/11 - 11/04/11 | 11/04/11 - 25/04/11 | 25/04/11 - 29/04/11 | 2/05/11 | 4/05/11 - 13/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 30/05/11 | 1/06/11 - 10/06/11 | 13/06/11 - 24/06/11 | 27/06/11 - 27/06/11 | 4/07/11 - 15/07/11 | 18/07/11 - 22/07/11 | 25/07/11 - 5/08/11 | 270000000 | NA | 8/08/11 - 12/08/11 | 15/08/11 - 26/08/11 | 29/08/11 - 9/09/11 | 19/09/11 | 21/11/11 | 25000000
Development of 10 Years Generation Capacity Expansion Plan for the Power Indsutry | NERC/CONSULT/2011/0010 |  | Lump Sum | 35000000 |  | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | NA | PST | NA | 28/03/11 - 8/04/11 | 11/04/11 - 25/04/11 | 25/04/11 - 2/05/11 | 2/05/11 | 2/05/11 - 13/05/11 | 16/05/11 - 27/05/11 | 27/05/11 - 27/05/11 | 30/05/11 - 10/06/11 | 13/06/11 - 24/06/11 | 27/06/11 - 27/06/11 | 27/06/11 - 8/07/11 | 11/07/11 - 15/07/11 | 18/07/11 - 29/07/11 | 35000000 | NA | 1/08/11 - 12/08/11 | 15/08/11 - 29/08/11 | 29/08/11 - 9/09/11 | 19/09/11 | 7/11/11 | 35000000
Development of a Generation Resources (Hydro, Gas, Coal etc) Plan for the Power Industry | NERC/CONSULT/2011/0010 |  | Lump Sum | 115000000 |  | BPP issues "No Objection" to award/FEC approves | QCBS - Quality and Cost Based Selection | NA | PRIOR | 28/03/11 - 18/04/11 | 18/04/11 - 2/05/11 | 2/05/11 - 16/05/11 | 16/05/11 - 23/05/11 | 27/05/11 | 13/06/11 - 24/06/11 | 27/06/11 - 11/07/11 | 11/07/11 - 11/07/11 | 11/07/11 - 25/07/11 | 25/07/11 - 8/08/11 | 8/08/11 - 12/08/11 | 15/08/11 - 29/08/11 | 29/08/11 - 9/09/11 | 12/09/11 - 23/09/11 | 115000000 | 26/09/11 - 10/10/11 | 17/10/11 - 31/10/11 | 1/11/11 - 15/11/11 | 15/11/11 - 25/11/11 | 28/11/11 | 29/12/11 | 115000000
Consultancy Service on the Completion and Opertaionalising of Health and Safety Code | NERC/CONSULT/2011/0011 |  | Lump Sum | 20800000 |  | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | NA | PST | NA | 28/03/11 - 11/04/11 | 11/04/11 - 25/04/11 | 25/04/11 - 2/05/11 | 2/05/11 | 2/05/11 - 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 30/05/11 | 30/05/11 - 10/06/11 | 13/06/11 - 27/06/11 | 27/06/11 - 27/06/11 | 4/07/11 - 15/07/11 | 18/07/11 - 20/07/11 | 25/07/11 - 8/08/11 | 20800000 | NA | 8/08/11 - 12/08/11 | 15/08/11 - 26/08/11 | 29/08/11 - 9/09/11 | 26/09/11 | 31/10/11 | 20800000
Consultancy Service on Enforcement of Regulations | NERC/CONSULT/2011/0012 |  | Lump Sum | 22500000 |  | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | NA | PST | NA | 21/03/11 - 4/04/11 | 4/04/11 - 18/04/11 | 18/04/11 - 25/04/11 | 29/04/11 | 29/04/11 - 9/05/11 | 9/05/11 - 23/05/11 | 23/05/11 - 24/05/11 | 24/05/11 - 6/06/11 | 6/06/11 - 13/06/11 | 13/06/11 - 27/06/11 | 27/06/11 - 4/07/11 | 4/07/11 - 18/07/11 | 18/07/11 - 8/08/11 | 22500000 | NA | 8/08/11 - 15/08/11 | 15/08/11 - 29/08/11 | 29/08/11 - 19/09/11 | 21/11/11 | 19/12/11 | 22500000
Consultancy Services on Legal and Regulatory for Cross Border Trading in Electricity | NERC/CONSULT/2011/0013 |  | Lump Sum | 25000000 |  |  | QCBS - Quality and Cost Based Selection | NA | PST | 28/03/11 - 18/04/11 | 18/04/11 - 25/04/11 | 25/04/11 - 9/05/11 | 9/05/11 - 16/05/11 | 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 6/06/11 | 6/06/11 - 6/06/11 | 6/06/11 - 20/06/11 | 20/06/11 - 4/07/11 | 4/07/11 - 18/07/11 | 18/07/11 - 1/08/11 | 1/08/11 - 15/08/11 | 15/08/11 - 29/08/11 | 25000000 | NA | 29/08/11 - 5/09/11 | 5/09/11 - 19/09/11 | 19/09/11 - 10/10/11 | 28/11/11 | 12/12/11 | 25000000
Consultancy Services on Regulatory Framework on Embedded Generation | NERC/CONSULT/2011/0014 |  | Lump Sum | 14000000 |  | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | NA | PST | 7/03/11 - 28/03/11 | 28/03/11 - 11/04/11 | 11/04/11 - 25/04/11 | 25/04/11 - 2/05/11 | 9/05/11 | 9/05/11 - 23/05/11 | 23/05/11 - 6/06/11 | 6/06/11 - 7/06/11 | 7/06/11 - 21/06/11 | 21/06/11 - 5/07/11 | 5/07/11 - 19/07/11 | 19/07/11 - 2/08/11 | 2/08/11 - 16/08/11 | 16/08/11 - 13/09/11 | 14000000 | NA | 13/09/11 - 27/09/11 | 27/09/11 - 11/10/11 | 11/10/11 - 1/11/11 | 20/12/11 | 3/01/12 | 14000000
Consultancy Services on Legal and Regulatory Framework for Independent Network/Independent Electricity Transmission Network | NERC/CONSULT/2011/0015 |  | Lump Sum | 14000000 |  | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | NA | PST | 7/03/11 - 28/03/11 | 28/03/11 - 11/04/11 | 11/04/11 - 25/04/11 | 25/04/11 - 2/05/11 | 2/05/11 | 2/05/11 - 9/05/11 | 9/05/11 - 23/05/11 | 23/05/11 - 24/05/11 | 24/05/11 - 7/06/11 | 7/06/11 - 21/06/11 | 21/06/11 - 5/07/11 | 5/07/11 - 19/07/11 | 19/07/11 - 2/08/11 | 2/08/11 - 16/08/11 | 14000000 | NA | 16/08/11 - 30/08/11 | 30/08/11 - 13/09/11 | 13/09/11 - 4/10/11 | 22/11/11 | 6/12/11 | 14000000
Consultancy Service on Legal and Regulatory Framework on Health and Safety Guidelines for Constrcution Works in the Nigerian Electric Power Sector | NERc/CONSULT/2011/0016 |  | Lump Sum | 14000000 |  | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | NA | PST | 7/03/11 - 21/03/11 | 21/03/11 - 4/04/11 | 4/04/11 - 18/04/11 | 18/04/11 - 25/04/11 | 30/05/11 | 30/05/11 - 13/06/11 | 13/06/11 - 27/06/11 | 27/06/11 - 28/06/11 | 28/06/11 - 12/07/11 | 12/07/11 - 26/07/11 | 26/07/11 - 9/08/11 | 9/08/11 - 23/08/11 | 23/08/11 - 6/09/11 | 6/09/11 - 4/10/11 | 14000000 | NA | 4/10/11 - 18/10/11 | 18/10/11 - 1/11/11 | 1/11/11 - 22/11/11 | 17/01/12 | 7/02/12 | 14000000
Review of CAP 106 | NERC/CONSULT/2011/0017 |  | Lump Sum | 14000000 |  | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | NA | PST | 3/03/11 - 24/03/11 | 24/03/11 - 7/04/11 | 7/04/11 - 21/04/11 | 21/04/11 - 28/04/11 | 5/05/11 | 5/05/11 - 19/05/11 | 19/05/11 - 2/06/11 | 2/06/11 - 3/06/11 | 3/06/11 - 17/06/11 | 17/06/11 - 1/07/11 | 1/07/11 - 15/07/11 | 15/07/11 - 29/07/11 | 29/07/11 - 12/08/11 | 12/08/11 - 9/09/11 | 14000000 | NA | 9/09/11 - 23/09/11 | 23/09/11 - 7/10/11 | 7/10/11 - 28/10/11 | 16/12/11 | 30/12/11 | 14000000
Review of Health and Safety Code | NERC/CONSULT/2011/0018 |  | Lump Sum | 14000000 |  | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | NA | PST | NA | 28/03/11 - 11/04/11 | 11/04/11 - 25/04/11 | 25/04/11 - 2/05/11 | 2/05/11 | 2/05/11 - 13/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 30/05/11 | 30/05/11 - 10/06/11 | 13/06/11 - 24/06/11 | 29/06/11 - 29/06/11 | 29/06/11 - 13/07/11 | 18/07/11 - 22/07/11 | 25/07/11 - 12/08/11 | 14000000 | NA | 15/08/11 - 19/08/11 | 22/08/11 - 2/09/11 | 5/09/11 - 9/09/11 | 26/09/11 | 31/10/11 | 14000000
Engagement of Consultant to Audit the Physical Assets in the Industry | NERC/CONSULT/2011/0019 |  | Lump Sum | 170000000 |  | BPP issues "No Objection" to award/FEC approves | QCBS - Quality and Cost Based Selection | NA | PRIOR | NA | 28/03/11 - 8/04/11 | 11/04/11 - 22/04/11 | 25/04/11 - 2/05/11 | 2/05/11 | 2/05/11 - 13/05/11 | 16/05/11 - 27/05/11 | 30/05/11 - 30/05/11 | 30/05/11 - 10/06/11 | 13/06/11 - 24/06/11 | 24/06/11 - 24/06/11 | 27/06/11 - 8/07/11 | 11/07/11 - 22/07/11 | 25/07/11 - 12/08/11 | 170000000 | 15/08/11 - 29/08/11 | 29/08/11 - 12/09/11 | 12/09/11 - 26/09/11 | 26/09/11 - 7/10/11 | 7/11/11 | 19/12/11 | 170000000
Consultancy Services on Capacity Assesement of the Industry | NERC/CONSULT/2011/0020 |  | Lump Sum | 42300000 |  | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | NA | PST | NA | 28/03/11 - 8/04/11 | 11/04/11 - 22/04/11 | 25/04/11 - 2/05/11 | 2/05/11 | 2/05/11 - 13/05/11 | 16/05/11 - 27/05/11 | 27/05/11 - 27/05/11 | 30/05/11 - 10/06/11 | 13/06/11 - 24/06/11 | 27/06/11 - 8/07/11 | 11/07/11 - 22/07/11 | 25/07/11 - 29/07/11 | 1/08/11 - 12/08/11 | 42300000 | NA | 15/08/11 - 26/08/11 | 29/08/11 - 9/09/11 | 12/09/11 - 23/09/11 | 3/10/11 | 21/11/11 | 42300000
Consultancy Service on Implementation of Transitional Electricty Market | NERC/CONSULT/2011/0021 |  | Lump Sum | 13900000 |  | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | NA | PST | NA | 28/03/11 - 11/04/11 | 11/04/11 - 22/04/11 | 25/04/11 - 2/05/11 | 2/05/11 | 2/05/11 - 13/05/11 | 16/05/11 - 27/05/11 | 27/05/11 - 27/05/11 | 30/05/11 - 10/06/11 | 13/06/11 - 24/06/11 | NA | 27/06/11 - 8/07/11 | 11/07/11 - 13/07/11 | 18/07/11 - 29/07/11 | 13900000 | NA | 1/08/11 - 12/08/11 | 15/08/11 - 26/08/11 | 29/08/11 - 9/09/11 | 26/09/11 | 31/10/11 | 13900000
Consultancy Services on Market Surveillance Framework | NERC/CONSULT/2011/0022 |  | Lump Sum | 60300000 |  | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | NA | PST | NA | 28/03/11 - 11/04/11 | 11/04/11 - 25/04/11 | 25/04/11 - 2/05/11 | 2/05/11 | 2/05/11 - 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 30/05/11 | 30/05/11 - 10/06/11 | 13/06/11 - 24/06/11 | 24/06/11 - 24/06/11 | 27/06/11 - 8/07/11 | 11/07/11 - 15/07/11 | 18/07/11 - 29/07/11 | 60300000 | NA | 1/08/11 - 12/08/11 | 15/08/11 - 26/08/11 | 29/08/11 - 9/09/11 | 26/09/11 | 31/10/11 | 60300000
Engagement of Consultant for the Audit of TCN | NERC/CONSULT/2011/0023 |  | Lump Sum | 28700000 |  | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | NA | PST | NA | 28/03/11 - 8/04/11 | 11/04/11 - 22/04/11 | 25/04/11 - 2/05/11 | 2/05/11 | 2/05/11 - 13/05/11 | 16/05/11 - 27/05/11 | 27/05/11 - 27/05/11 | 30/05/11 - 10/06/11 | 13/06/11 - 24/06/11 | 24/06/11 - 24/06/11 | 27/06/11 - 8/07/11 | 11/07/11 - 15/07/11 | 18/07/11 - 29/07/11 | 2870000 | NA | 1/08/11 - 12/08/11 | 15/08/11 - 26/08/11 | 29/08/11 - 9/09/11 | 26/09/11 | 7/11/11 | 28700000
Consultancy Service on Development of Codes, Labelling and Standards for Energy Efficiency and Conservation | NERC/CONSULT/2001/0024 |  | Lump Sum | 20000000 |  | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | NA | PST | NA | 28/03/11 - 11/04/11 | 11/04/11 - 25/04/11 | 25/04/11 - 2/05/11 | 2/05/11 | 2/05/11 - 13/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 30/05/11 | 30/05/11 - 10/06/11 | 13/06/11 - 24/06/11 | 29/06/11 - 29/06/11 | 29/06/11 - 12/07/11 | 12/07/11 - 15/07/11 | 18/07/11 - 29/07/11 | 20000000 | NA | 1/08/11 - 12/08/11 | 15/08/11 - 26/08/11 | 29/08/11 - 2/09/11 | 12/09/11 | 24/10/11 | 20000000
Consultancy Service on the Development of Model Regulations on Energy Efficiency and Conservation | NERC/CONSULT/2011/0025 |  | Lump Sum | 40000000 |  | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | NA | PST | 28/03/11 - 18/04/11 | 18/04/11 - 2/05/11 | 2/05/11 - 16/05/11 | 16/05/11 - 23/05/11 | 23/05/11 | 23/05/11 - 31/05/11 | 31/05/11 - 14/06/11 | 14/06/11 - 14/06/11 | 14/06/11 - 28/06/11 | 28/06/11 - 12/07/11 | 12/07/11 - 12/07/11 | 12/07/11 - 25/07/11 | 25/07/11 - 29/07/11 | 29/07/11 - 12/08/11 | 40000000 | NA | 15/08/11 - 19/08/11 | 22/08/11 - 31/08/11 | 5/09/11 - 16/09/11 | 26/09/11 | 28/11/11 | 40000000
Consultancy Services for Nigerian Electric Power Information System | NERC/CONSULT/2011/0026 |  | Lump Sum | 46000000 |  | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection |  | PST | NA | 28/03/11 - 11/04/11 | 11/04/11 - 25/04/11 | 25/04/11 - 2/05/11 | 2/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 13/06/11 | 13/06/11 - 13/06/11 | 14/06/11 - 28/06/11 | 28/06/11 - 5/07/11 | 11/07/11 - 11/07/11 | 12/07/11 - 19/07/11 | 20/07/11 - 25/07/11 | 25/07/11 - 1/08/11 | 46000000 | NA | 1/08/11 - 8/08/11 | 8/08/11 - 22/08/11 | 22/08/11 - 29/08/11 | 1/09/11 | 1/11/11 | 46000000
Comparative Study of Rural Power Supply Options using Solar, Diesel Power and Grid Extension | NERC/CONSULT/2011/0027 |  | Lump Sum | 10000000 |  | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | NA | PST | NA | 28/03/11 - 11/04/11 | 11/04/11 - 25/04/11 | 25/04/11 - 2/05/11 | 2/05/11 | 2/05/11 - 13/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 30/05/11 | 30/05/11 - 10/06/11 | 13/06/11 - 24/06/11 | NA | 27/06/11 - 8/07/11 | 11/07/11 - 15/07/11 | 25/07/11 - 5/08/11 | 10000000 | NA | 1/08/11 - 5/08/11 | 8/08/11 - 19/08/11 | 22/08/11 - 26/08/11 | 12/09/11 | 24/10/11 | 10000000
Consultancy Services on Collection of Cost of Service Datafor Renewable Energy Based Power | NERC/CONSULT/2011/0028 |  | Lump Sum | 17000000 |  | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | NA | PST | NA | 28/03/11 - 11/04/11 | 11/04/11 - 25/04/11 | 25/04/11 - 2/05/11 | 2/05/11 | 2/05/11 - 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 30/05/11 | 30/05/11 - 13/06/11 | 13/06/11 - 27/06/11 | 27/06/11 - 27/06/11 | 27/06/11 - 11/07/11 | 11/07/11 - 15/07/11 | 18/07/11 - 29/07/11 | 15000000 | NA | 1/08/11 - 5/08/11 | 8/08/11 - 19/08/11 | 22/08/11 - 26/08/11 | 26/09/11 | 1/11/11 | 15000000
Consultancy Service on Development of Regulatory Framework for Renewable Energy based Power | NERC/CONSULT/2011/0029 |  | Lump Sum | 15000000 |  | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | NA | PST | NA | 28/03/11 - 11/04/11 | 11/04/11 - 25/04/11 | 25/04/11 - 2/05/11 | 2/05/11 | 9/05/11 - 20/05/11 | 23/05/11 - 3/06/11 | 6/06/11 - 6/06/11 | 6/06/11 - 17/06/11 | 20/06/11 - 1/07/11 | NA | 4/07/11 - 15/07/11 | 20/07/11 - 22/07/11 | 25/07/11 - 5/08/11 | 15000000 | NA | 8/08/11 - 19/08/11 | 22/08/11 - 2/09/11 | 5/09/11 - 16/09/11 | 10/10/11 | 28/11/11 | 15000000
Establishment of Computerized Central Registry | NERC/CONSULT/2011/0030 |  | Lump Sum | 30000000 |  | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | NA | PST
Engagement of Consultant for NERC Annual Retreat | NERC/CONSULT/2011/0031 |  | Lump Sum | 80000000 |  | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | NA | PST | 28/03/11 - 18/04/11 | 18/04/11 - 2/05/11 | 2/05/11 - 16/05/11 | 16/05/11 - 23/05/11 | 23/05/11 | 30/05/11 - 10/06/11 | 13/06/11 - 27/06/11 | 27/06/11 - 27/06/11 | 27/06/11 - 8/07/11 | 11/07/11 - 22/07/11 | 27/07/11 - 27/07/11 | 28/07/11 - 5/08/11 | 10/08/11 - 12/08/11 | 15/08/11 - 26/08/11 | 80000000 | 29/08/11 - 12/09/11 | 19/09/11 - 23/09/11 | 26/09/11 - 7/10/11 | 10/10/11 - 21/10/11 | 1/11/11 | 1/12/11 | 80000000
Consultancy Service on Team Building and Organisational Cohesion | NERC/CONSULT/2011/0032 |  | Lump Sum | 14500000 |  | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | NA | PST | NA | 28/03/11 - 11/04/11 | 11/04/11 - 25/04/11 | 25/04/11 - 2/05/11 | 2/05/11 | 2/05/11 - 16/05/11 | 16/05/11 - 27/05/11 | 27/05/11 - 27/05/11 | 30/05/11 - 13/06/11 | 13/06/11 - 24/06/11 | NA | NA | 27/06/11 - 30/06/11 | 4/07/11 - 15/07/11 | 145000000 | NA | 1/08/11 - 12/08/11 | 15/08/11 - 26/08/11 | 29/08/11 - 2/09/11 | 19/09/11 | 24/10/11 | 14500000
Media Consultancy | NERC/CONSULT/2011/0033 |  | Lump Sum | 50000000 |  | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | NA | PST | 7/03/11 - 28/03/11 | 28/03/11 - 11/04/11 | 11/04/11 - 25/04/11 | 25/04/11 - 2/05/11 | 23/05/11 | 23/05/11 - 6/06/11 | 6/06/11 - 20/06/11 | 20/06/11 - 21/06/11 | 21/06/11 - 5/07/11 | 5/07/11 - 19/07/11 | 19/07/11 - 2/08/11 | 2/08/11 - 16/08/11 | 16/08/11 - 30/08/11 | 30/08/11 - 27/09/11 | 50000000 | NA | 27/09/11 - 11/10/11 | 11/10/11 - 25/10/11 | 25/10/11 - 15/11/11 | 3/01/12 | 31/01/12 | 50000000
Consultancy Service on Induction Program for Commissioners | NERC/CONSULT/2011/0034 |  | Lump Sum | 16500000 |  | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | NA | PST | NA | 28/03/11 - 11/04/11 | 11/04/11 - 25/04/11 | 25/04/11 - 2/05/11 | 2/05/11 | 2/05/11 - 13/05/11 | 16/05/11 - 27/05/11 | 27/05/11 - 27/05/11 | 30/05/11 - 10/06/11 | 13/06/11 - 24/06/11 | NA | 27/06/11 - 8/07/11 | 11/07/11 - 15/07/11 | 18/07/11 - 29/07/11 | 16500000 | NA | 1/08/11 - 5/08/11 | 8/08/11 - 19/08/11 | 22/08/11 - 26/08/11 | 5/09/11 | 10/10/11 | 16500000
Architectural design for NERC Corporate Head office | NERC/CONSULT/2011/005 |  | Lump Sum | 800000000 |  | BPP issues "No Objection" to award/FEC approves | QCBS - Quality and Cost Based Selection | NA | PRIOR | 10/02/11 - 17/02/11 | 17/02/11 - 24/02/11 | 24/02/11 - 7/03/11 | 7/03/11 - 14/03/11 | 21/03/11 | 21/03/11 - 28/03/11 | 28/03/11 - 11/04/11 | 11/04/11 - 12/04/11 | 12/04/11 - 15/04/11 | 15/04/11 - 22/04/11 | 22/04/11 - 29/04/11 | 29/04/11 - 2/05/11 | 2/05/11 - 6/05/11 | 6/05/11 - 20/05/11 | 800000000 | NA | 20/05/11 - 27/05/11 | 27/05/11 - 10/06/11 | 10/06/11 - 24/06/11 | NA | NA | 800000000
REGULATION ON POWER CONSUMER ASSISSTANCE FUND | NERC/CONSULT/2011/ |  | Lump Sum | 50000000 | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | PST | PST | 28/03/11 - 11/04/11 | 11/04/11 - 25/04/11 | 25/04/11 - 9/05/11 | 9/05/11 - 16/05/11 | 23/05/11 | 23/05/11 - 30/05/11 | 30/05/11 - 13/06/11 | 13/06/11 - 14/06/11 | 14/06/11 - 27/06/11 | 27/06/11 - 11/07/11 | 11/07/11 - 25/07/11 | 25/07/11 - 8/08/11 | 8/08/11 - 22/08/11 | 22/08/11 - 12/09/11 | 50000000 | NA | 12/09/11 - 26/09/11 | 26/09/11 - 10/10/11 | 10/10/11 - 31/10/11 | 12/12/11 | 26/12/11 | 50000000
Legal drafting of 10 new rules and regulations |  |  | Lump Sum | 140000000 |  |  | QCBS - Quality and Cost Based Selection
HR Consultant to handle Recruitment | NERC/CONSULT/ |  | Lump Sum | 20000000 |  | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | NA | PST | NA | 28/03/11 - 11/04/11 | 11/04/11 - 25/04/11 | 25/04/11 - 2/05/11 | 2/05/11 | 2/05/11 - 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 30/05/11 | 30/05/11 - 10/06/11 | 13/06/11 - 24/06/11 | 27/06/11 - 27/06/11 | 27/06/11 - 8/07/11 | 11/07/11 - 15/07/11 | 18/07/11 - 29/07/11 | 40000000 | NA | 1/08/11 - 12/08/11 | 15/08/11 - 26/08/11 | 29/08/11 - 2/09/11 | 31/10/11 | 31/10/11 | 40000000
Retainership Mechanics for Vehicle Repairs | NERC/CONSULT/ |  | Lump Sum | 33400000 |  | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | NA | PST | NA | 28/03/11 - 11/04/11 | 11/04/11 - 25/04/11 | 25/04/11 - 2/05/11 | 2/05/11 | 2/05/11 - 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 30/05/11 | 30/05/11 - 10/06/11 | 13/06/11 - 27/06/11 | 27/06/11 - 27/06/11 | 27/06/11 - 8/07/11 | 11/07/11 - 15/07/11 | 18/07/11 - 29/07/11 | 33400000 | NA | 1/08/11 - 12/08/11 | 15/08/11 - 26/08/11 | 29/08/11 - 2/09/11 | 3/10/11 | 10/10/11 | 334000000
Engagemnent of Travel Agent | NERC/CONSULT/2011/074 |  | Lump Sum | 10000000 |  | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | NA | PST | 7/03/11 - 21/03/11 | 21/03/11 - 4/04/11 | 4/04/11 - 18/04/11 | 18/04/11 - 25/04/11 | 25/04/11 | 25/04/11 - 9/05/11 | 9/05/11 - 23/05/11 | 23/05/11 - 6/06/11 | 6/06/11 - 20/06/11 | 20/06/11 - 4/07/11 | 4/07/11 - 11/07/11 | 11/07/11 - 18/07/11 | 18/07/11 - 25/07/11 | 25/07/11 - 8/08/11 | 10000000 | NA | 8/08/11 - 15/08/11 | 15/08/11 - 29/08/11 | 29/08/11 - 19/09/11 | NA | NA | NA | BG Mohammed | Patrick Umeh
Total Cost Plan |  |  |  | 2486900000 | [19 empty] | 2434570000 | [6 empty] | 2375500000
Total Cost Actual
Ministry/Department/Agency: Nigerian Electricity Regulatory Commission
Budget Year: 2011 --- Goods
| Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Goods |  |  | Action Party | Champion
Project Description | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Arrival of Goods | Inspection/Final Acceptance | Name/Designation | Name/Designation
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
Procurement of office consumables and other materials | 01 | 2 | Bills of Quantity | 25000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | NA | 7/03/11 - 14/03/11 | NA | 21/03/11 | 18/04/11 | NA | 18/04/11 - 2/05/11 | 15000000 | NA | 2/05/11 - 9/05/11 | 9/05/11 - 16/05/11 | NA | 16/05/11 - 6/06/11 | 6/06/11 - 13/06/11 | NA | NA
Procurement of Library books and Periodicals | 002 |  |  | 48450000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | NA | 7/03/11 - 14/03/11 | NA | 21/03/11 | 18/04/11 | NA | 18/04/11 - 2/05/11 | 48450000 | NA | 2/05/11 - 9/05/11 | 9/05/11 - 16/05/11 | NA | 16/05/11 - 6/06/11 | 6/06/11 - 13/06/11
Procurement of Computer materials and supplies | 003 |  |  | 10000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | NA | 7/03/11 - 14/03/11 | NA | 21/03/11 | 18/04/11 | NA | 18/04/11 - 2/05/11 | 10000000 | NA | 2/05/11 - 9/05/11 | 9/05/11 - 16/05/11 | NA | 16/05/11 - 6/06/11 | 6/06/11 - 13/06/11
Printing of Non-Security Documents | GDS/2011/004 |  |  | 100175000 | INCB | BPP issues "No Objection" to award/FEC approves | LERB - LOWEST EVALUATED RESPONSIVE BID | PRE | PRIOR | 18/04/11 - 2/05/11 | 2/05/11 - 9/05/11 | 9/05/11 - 23/05/11 | 23/05/11 | 6/06/11 | 6/06/11 - 20/06/11 | 20/06/11 - 4/07/11 | 100175000 | NA | 4/07/11 - 11/07/11 | 11/07/11 - 18/07/11 | NA | 18/07/11 - 12/09/11 | 12/09/11 - 19/09/11
Production and Publication of Promotional items | GDS/2011/005 |  |  | 16790000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | NA | 14/02/11 - 28/02/11 | NA | 28/02/11 | 28/03/11 | NA | 28/03/11 - 11/04/11 | 16790000 | NA | 11/04/11 - 18/04/11 | 18/04/11 - 25/04/11 | NA | 25/04/11 - 23/05/11 | 23/05/11 - 30/05/11
Procurement of office equipment for the new Zonal and Forum offices | GDS/2011/006 | 5 |  | 100000000 | INCB | BPP issues "No Objection" to award/FEC approves | LERB - LOWEST EVALUATED RESPONSIVE BID | PRE | PRIOR | 21/03/11 - 4/04/11 | 4/04/11 - 18/04/11 | 18/04/11 - 16/05/11 | 16/05/11 | 13/06/11 | 13/06/11 - 27/06/11 | 27/06/11 - 11/07/11 | 41552500 | NA | 11/07/11 - 18/07/11 | 18/07/11 - 1/08/11 | 1/08/11 - 15/08/11 | 15/08/11 - 12/09/11 | 12/09/11 - 26/09/11
Procurement of IT Hardware & Software for the new Zonal and Forum offices | NERC/GDS/2011/007 | 2 |  | 50897500 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 28/03/11 - 11/04/11 | 11/04/11 - 18/04/11 | 18/04/11 - 2/05/11 | 2/05/11 | 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 6/06/11 | 19197500 | NA | 6/06/11 - 13/06/11 | 13/06/11 - 27/06/11 | 27/06/11 - 11/07/11 | 11/07/11 - 8/08/11 | 8/08/11 - 22/08/11
Procurement of Furniture for the Head office and the new Zonal & Forum offices | GDS/2011/008 | 5 |  | 100000000 | INCB | BPP issues "No Objection" to award/FEC approves | LERB - LOWEST EVALUATED RESPONSIVE BID | PRE | PRIOR | 21/03/11 - 4/04/11 | 4/04/11 - 18/04/11 | 18/04/11 - 16/05/11 | 16/05/11 | 13/06/11 | 13/06/11 - 27/06/11 | 27/06/11 - 11/07/11 | 41552500 | NA | 11/07/11 - 18/07/11 | 18/07/11 - 1/08/11 | 1/08/11 - 15/08/11 | 15/08/11 - 12/09/11 | 12/09/11 - 26/09/11
Procurement of 11no. Project Vehicles for zonal and forum offices - Forum offices pick-up van | NERC/GDS/2011/1 | 1 |  | 106500000 | NCB | BPP issues "No Objection" to award/FEC approves | LERB - LOWEST EVALUATED RESPONSIVE BID | PRE | PRIOR | 21/03/11 - 4/04/11 | 4/04/11 - 18/04/11 | 18/04/11 - 16/05/11 | 16/05/11 | 13/06/11 | 13/06/11 - 27/06/11 | 27/06/11 - 11/07/11 | 49500000 | NA | 11/07/11 - 18/07/11 | 18/07/11 - 1/08/11 | 1/08/11 - 15/08/11 | 15/08/11 - 12/09/11 | 12/09/11 - 26/09/11
Procurement of 6no. Project vehicles for zonal and forum offices - zonal offices saloon car | NERC/GDS/2011/2 | 2 |  | 30000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 21/03/11 - 4/04/11 | 4/04/11 - 18/04/11 | 18/04/11 - 9/05/11 | 16/05/11 | 13/06/11 | 13/06/11 - 27/06/11 | 27/06/11 - 11/07/11 | 30000000 | NA | 11/07/11 - 18/07/11 | 18/07/11 - 1/08/11 | 1/08/11 - 15/08/11 | 15/08/11 - 12/09/11 | 12/09/11 - 26/09/11
Procurement of 6no. project vehicles for zonal and forum offices- zonal offices 4WD drive pick-van | NERC/GDS/2011/3 | 3 |  | 27000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 21/03/11 - 4/04/11 | 4/04/11 - 18/04/11 | 18/04/11 - 9/05/11 | 16/05/11 | 13/06/11 | 13/06/11 - 27/06/11 | 27/06/11 - 11/07/11 | 30000000 | NA | 11/07/11 - 18/07/11 | 18/07/11 - 1/08/11 | 1/08/11 - 15/08/11 | 15/08/11 - 12/09/11 | 12/09/11 - 26/09/11
Procurement of furniture for head, Zonal & Forum offices- Zonal offices furniture | NERC/GDS/2011/2 | 2 |  | 22665000 | [5 empty] | 21/03/11 - 4/04/11 | 4/04/11 - 18/04/11 | 18/04/11 - 16/05/11 | 16/05/11 | 13/06/11 | 13/06/11 - 27/06/11 | 27/06/11 - 11/07/11 | 22665000 | NA | 11/07/11 - 18/07/11 | 18/07/11 - 1/08/11 | 1/08/11 - 15/08/11 | 15/08/11 - 12/09/11 | 12/09/11 - 26/09/11
Procurement of furniture for Head, Zonal & Forum offices- H/office furniture | NERC/GDS/2011/3 | 3 |  | 35782500 | [5 empty] | 21/03/11 - 4/04/11 | 4/04/11 - 18/04/11 | 18/04/11 - 16/05/11 | 16/05/11 | 13/06/11 | 13/06/11 - 27/06/11 | 27/06/11 - 11/07/11 | 35782000 | NA | 11/07/11 - 18/07/11 | 18/07/11 - 1/08/11 | 1/08/11 - 15/08/11 | 15/08/11 - 12/09/11 | 12/09/11 - 26/09/11
Procurement of office equipment for Head, Zonal & Forum offices-Zonal office equipment | NERC/GDS/2011/2 | 2 |  | 22665000 | [5 empty] | 21/03/11 - 4/04/11 | 4/04/11 - 18/04/11 | 18/04/11 - 2/05/11 | 2/05/11 | 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 6/06/11 | 22665000 | NA | 6/06/11 - 13/06/11 | 13/06/11 - 27/06/11 | 27/06/11 - 11/07/11 | 11/07/11 - 8/08/11 | 8/08/11 - 22/08/11
Procurement of IT facilities for Head, Zonal & Forum offices-Wireless LAN upgrade | NERC/GDS/2011/2 | 2 |  | 6000000 | [5 empty] | 28/03/11 - 11/04/11 | 11/04/11 - 18/04/11 | 18/04/11 - 2/05/11 | 2/05/11 | 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 6/06/11 | 6000000 | NA | 6/06/11 - 13/06/11 | 13/06/11 - 27/06/11 | 27/06/11 - 11/07/11 | 11/07/11 - 8/08/11 | 8/08/11 - 22/08/11
Procurement of It facilities for Head, Zonal & Forum offices-offsite data backup | NERC/GDS/2011/3 | 3 |  | 5000000 | [5 empty] | 28/03/11 - 11/04/11 | 11/04/11 - 18/04/11 | 18/04/11 - 2/05/11 | 2/05/11 | 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 6/06/11 | 5000000 | NA | 6/06/11 - 13/06/11 | 13/06/11 - 27/06/11 | 27/06/11 - 11/07/11 | 11/07/11 - 8/08/11 | 8/08/11 - 22/08/11
Procurement of IT facilities for Head, Zonal & Forum offices-Help desk software Windows7 | NERC/GDS/2011/004 | 4 |  | 10700000 | [5 empty] | 28/03/11 - 11/04/11 | 11/04/11 - 18/04/11 | 18/04/11 - 2/05/11 | 2/05/11 | 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 6/06/11 | 10700000 | NA | 6/06/11 - 13/06/11 | 13/06/11 - 27/06/11 | 27/06/11 - 11/07/11 | 11/07/11 - 8/08/11 | 8/08/11 - 22/08/11
Procurement of IT facilities for Head, Zonal & Forum offices-HR Mgt Software | NERC/GDS/2011/005 | 5 |  | 10000000 | [5 empty] | 28/03/11 - 11/04/11 | 11/04/11 - 18/04/11 | 18/04/11 - 2/05/11 | 2/05/11 | 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 6/06/11 | 10000000 | NA | 6/06/11 - 13/06/11 | 13/06/11 - 27/06/11 | 27/06/11 - 11/07/11 | 11/07/11 - 8/08/11 | 8/08/11 - 22/08/11
Procurement of office equipment for Head, Zonal & Forum offices- H/office furniture | NERC/GDS/2011/003 | 3 |  | 35782500 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 21/03/11 - 4/04/11 | 4/04/11 - 18/04/11 | 18/04/11 - 2/05/11 | 2/05/11 | 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 6/06/11 | 35782500 | NA | 6/06/11 - 13/06/11 | 13/06/11 - 27/06/11 | 27/06/11 - 11/07/11 | 11/07/11 - 18/07/11 | 18/07/11 - 1/08/11
Procurement of office equipment for head, Zonal & Forum offices-Forum ofices equipment | NERC/GDS/2011/001 | 1 |  | 41552500 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 21/03/11 - 4/04/11 | 4/04/11 - 18/04/11 | 18/04/11 - 2/05/11 | 2/05/11 | 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 6/06/11 | 41552500 | NA | 6/06/11 - 13/06/11 | 13/06/11 - 27/06/11 | 27/06/11 - 11/07/11 | 11/07/11 - 8/08/11 | 8/08/11 - 22/08/11
Total Cost Plan |  |  |  | 804960000 | [12 empty] | 592364500
Total Cost Actual
Ministry/Department/Agency: Nigerian Electricity Regulatory Commission
Budget Year: 2011 --- Works
| Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Works |  |  |  | Action Party | Champion
Project Description | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | First Stage Bidding | Second Stage Bidding - Technical /Financial | Bid Invitation Date | Bid Closing /Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Name/ Designation | Name/ Designation
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Construction of NERC Corporate Head office | NERC/WKS/2011/001 | 1 | Bills of Quantity | 3400000000 | INCB | BPP issues "No Objection" to award/FEC approves | LERB - LOWEST EVALUATED RESPONSIVE BID | PRE | PRIOR | 4/04/11 - 18/04/11 | 18/04/11 - 25/04/11 | 25/04/11 - 9/05/11 | NA | NA | 9/05/11 | 6/06/11 | 6/06/11 - 20/06/11 | 20/06/11 - 4/07/11 | 3400000000 | 4/07/11 - 18/07/11 | 18/07/11 - 1/08/11 | 1/08/11 - 15/08/11 | 15/08/11 - 5/09/11 | 27/08/12 | 24/12/12 | 3400000000
Establishment of five forum offices- Abuja forum office | NERC/WKS/2011/002/1 | 1 | Bills of Quantity | 44400000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | NA | 4/04/11 - 18/04/11 | NA | NA | NA | 18/04/11 | 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 13/06/11 | NA | NA | 13/06/11 - 27/06/11 | 27/06/11 - 11/07/11 | 11/07/11 - 25/07/11 | 26/09/11 | 17/10/11 | NA
[19 empty] | NA | NA | NA | NA
Establishment of six zonal offices - North-East Zone (M/guri/Gombe) | NERC/WKS/2011/003 | 1 | Bills of Quantity | 49000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | NA | 14/03/11 - 28/03/11 | NA | NA | NA | 28/03/11 | 25/04/11 | NA | 25/04/11 - 9/05/11 | 49000000 | NA | 9/05/11 - 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 13/06/11 | 15/10/12 | 12/11/12 | 49000000
Establishment of six zonal offices - North-Central (Makurdi/Minna) | NERC/WKS/2011/003/2 | 2 | Bills of Quantity | 49000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | NA | 14/03/11 - 28/03/11 | NA | NA | NA | 28/03/11 | 25/04/11 | NA | 25/04/11 - 9/05/11 | 49000000 | NA | 9/05/11 - 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 13/06/11 | 15/10/12 | 12/11/12 | 49000000
Establishment of six zonal offices - North-West (Birni Kebbi/Sokoto) | NERC/WKS/2011/03 | 3 | Bills of Quantity | 49000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | NA | 14/03/11 - 28/03/11 | NA | NA | NA | 28/03/11 | 25/04/11 | NA | 25/04/11 - 9/05/11 | 49000000 | NA | 9/05/11 - 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 13/06/11 | 17/10/11 | 14/11/11 | 49000000
Establishment of six zonal offices - South-West (Akure/Ondo) | NERC/WKS/2011/003/4 | 4 | Bills of Quantity | 49000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | NA | 14/03/11 - 28/03/11 | NA | NA | NA | 28/03/11 | 25/04/11 | NA | 25/04/11 - 9/05/11 | 49000000 | NA | 9/05/11 - 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 13/06/11 | 17/10/11 | 14/11/11 | 49000000
Establishment of six zonal offices - South-East (Owerri/Umuahia) | NERC/WKS/2011/003/5 | 5 | Bills of Quantity | 49000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | NA | 14/03/11 - 28/03/11 | NA | NA | NA | 28/03/11 | 25/04/11 | NA | 25/04/11 - 9/05/11 | 49000000 | NA | 9/05/11 - 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 13/06/11 | 17/10/11 | 14/11/11 | 49000000
Establishment of six zonal offices - South-South (Asaba/Calaba) | NERC/WKS/2011/003/6 | 6 | Bills of Quantity | 49000000 | NCB | Parastatals Tenders Board |  | PST | PST | NA | 14/03/11 - 28/03/11 | NA | NA | NA | 28/03/11 | 25/04/11 | NA | 25/04/11 - 9/05/11 | 49000000 | NA | 9/05/11 - 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 13/06/11 | 17/10/11 | 14/11/11 | 49000000
Estabishment of five forum offices - Benin forum office | NERC/WKS/2011/002/2 | 2 | Bills of Quantity | 22400000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | NA | 4/04/11 - 18/04/11 | NA | NA | NA | 18/04/11 | 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 13/06/11 | NA | NA | 13/06/11 - 27/06/11 | 27/06/11 - 11/07/11 | 11/07/11 - 25/07/11 | 26/09/11 | 17/10/11 | 22400000
Estabishment of five forum offices - Yola forum office | NERC/WKS/2011/002/3 | 3 | Bills of Quantity | 22400000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | NA | 4/04/11 - 18/04/11 | NA | NA | NA | 18/04/11 | 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 13/06/11 | NA | NA | 13/06/11 - 27/06/11 | 27/06/11 - 11/07/11 | 11/07/11 - 25/07/11 | 26/09/11 | 17/10/11 | 22400000
Establishment of five forum offices - Ibadan forum office | NERC/WKS/2011/002/4 | 4 | Bills of Quantity | 22400000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | NA | 4/04/11 - 18/04/11 | NA | NA | NA | 18/04/11 | 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 13/06/11 | NA | NA | 13/06/11 - 27/06/11 | 27/06/11 - 11/07/11 | 11/07/11 - 25/07/11 | 26/09/11 | 17/10/11 | 22400000
Establishment of five forum offices - Ikeja forum office | NERC/WKS/2011/002/5 | 5 | Bills of Quantity | 44400000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | NA | 4/04/11 - 18/04/11 | NA | NA | NA | 18/04/11 | 16/05/11 | 16/05/11 - 30/05/11 | 30/05/11 - 13/06/11 | NA | NA | 13/06/11 - 27/06/11 | 27/06/11 - 11/07/11 | 11/07/11 - 25/07/11 | 26/09/11 | 17/10/11 | 44400000
Acquisition of Land for NERC Corporate Head office | NERC/WKS/2011/001 | 1 | Bills of Quantity | 800000000 | NCB | Ministerial Tenders Board |  | PRE | PST | NA | NA | NA | NA | NA | NA | NA | 14/03/11 - 28/03/11 | 28/03/11 - 11/04/11 | 800000000 | NA | NA | 11/04/11 - 18/04/11 | NA | 18/04/11 | 18/04/11 | 800000000
Total Cost Plan |  |  |  | 4650000000 | [14 empty] | 4494000000 | [6 empty] | 4605600000
Total Cost Actual

## Ibadan_PHCN
Ministry/Department/Agency: Ibadan Electricity Distribution Company (PHCN)
Budget Year: 2011 -- Cosultancy Services
|  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/ Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/ Designation | Name/ Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 1 weeks | 2 - 4 weeks | 2 weeks | 2 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
Provision of Staff Training | Plan | IBEDC/2011/PP/068 | 68 | Lump Sum | 24500000 |  | Parastatals Tenders Board | LC - Least Cost | NA | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 13/05/11 | 13/05/11 - 20/05/11 | 20/05/11 | 20/05/11 - 31/05/11 | 1/06/11 - 15/06/11 | 15/06/11 - 30/06/11 | 1/07/11 - 15/07/11 | 15/07/11 - 29/07/11 | 1/08/11 - 15/08/11 | 15/08/11 - 29/08/11 | 1/09/11 - 15/09/11 | 15/09/11 - 30/09/11 | NA | NA | 3/10/11 - 17/10/11 | 17/10/11 - 31/10/11 | NA | 1/11/11 | 22/11/11 | NA | O Odunusi - [Designation: PM (Admin/Services)] | Mr. M. B. Obadimeji - [Designation: A.G.M. Admin. & Services]
Actual
Provision of Staff Foreign Training | Plan | IBEDC/2011/PP/069 | 69 | Lump Sum | 10000000 |  | Parastatals Tenders Board | LC - Least Cost | NA | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 2/05/11 - 16/05/11 | 16/05/11 - 23/05/11 | 23/05/11 | 20/06/11 - 30/06/11 | 1/07/11 - 15/07/11 | 15/07/11 - 5/08/11 | 5/08/11 - 19/08/11 | 19/08/11 - 31/08/11 | 1/09/11 - 15/09/11 | 15/09/11 - 29/09/11 | 3/10/11 - 17/10/11 | 17/10/11 - 31/10/11 | NA | NA | 1/11/11 - 15/11/11 | 15/11/11 - 29/11/11 | NA | NA | 6/12/11 | NA | O Odunusi - [Designation: PM (Admin/Services)] | Mr. M. B. Obadimeji - [Designation: A.G.M. Admin. & Services]
Actual
Maintenance of Office Equipment | Plan | IBEDC/2011/PP/070 | 70 | Lump Sum | 4000000 |  | Parastatals Tenders Board | LC - Least Cost | NA | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 2/05/11 - 16/05/11 | 16/05/11 - 23/05/11 | 23/05/11 | 23/05/11 - 31/05/11 | 1/06/11 - 15/06/11 | 15/06/11 - 30/06/11 | 1/07/11 - 15/07/11 | 15/07/11 - 29/07/11 | 1/08/11 - 15/08/11 | 15/08/11 - 29/08/11 | 1/09/11 - 15/09/11 | 15/09/11 - 30/09/11 | NA | NA | 3/10/11 - 17/10/11 | 17/10/11 - 31/10/11 | NA | NA | 16/11/11 | NA | O Odunusi - [Designation: PM (Admin/Services)] | Mr. M. B. Obadimeji - [Designation: A.G.M. Admin. & Services]
Actual
Maintenance of Vehicles | Plan | IBEDC/2011/PP/071 | 71 | Lump Sum | 4000000 |  | Parastatals Tenders Board | LC - Least Cost | NA | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 13/05/11 | 13/05/11 - 20/05/11 | 20/05/11 | 20/05/11 - 31/05/11 | 1/06/11 - 15/06/11 | 15/06/11 - 30/06/11 | 1/07/11 - 15/07/11 | 15/07/11 - 29/07/11 | 1/08/11 - 15/08/11 | 15/08/11 - 29/08/11 | 1/09/11 - 15/09/11 | 15/09/11 - 30/09/11 | NA | NA | 3/10/11 - 17/10/11 | 17/10/11 - 31/10/11 | NA | NA | 23/11/11 | NA | Mr. B Ajomo - [Designation: Zonal Transport Officer] | Mr. M. B. Obadimeji - [Designation: A.G.M. Admin. & Services]
Actual
Maintenance, Servicing and Refilling of existing Fire Extinguishers | Plan | IBEDC/2011/PP/072 | 72 | Lump Sum | 1500000 |  | Accounting Officer: Director General/CEO | LC - Least Cost | NA | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 2/05/11 - 16/05/11 | 16/05/11 - 23/05/11 | 23/05/11 | 23/05/11 - 31/05/11 | 1/06/11 - 15/06/11 | 15/06/11 - 30/06/11 | 1/07/11 - 15/07/11 | 15/07/11 - 29/07/11 | 1/08/11 - 15/08/11 | 15/08/11 - 29/08/11 | 1/09/11 - 15/09/11 | 15/09/11 - 15/09/11 | NA | NA | 15/09/11 - 29/09/11 | 3/10/11 - 17/10/11 | NA | NA | 30/11/11 | NA | Engr. C Ahonkhai - [Designation: PM Safety Stds & Work Methods] | Mr. M. B. Obadimeji - [Designation: A.G.M. Admin. & Services]
Actual
Architectural Design and Supervision of Construction of Standard Store Complex at Eleyele, Ibadan | Plan | IBEDC/2011/PP/073 | 73 | Lump Sum | 3000000 |  | Parastatals Tenders Board | LC - Least Cost | NA | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 2/05/11 - 16/05/11 | 16/05/11 - 23/05/11 | 23/05/11 | 23/05/11 - 31/05/11 | 1/06/11 - 15/06/11 | 15/06/11 - 30/06/11 | 1/07/11 - 15/07/11 | 15/07/11 - 29/07/11 | 1/08/11 - 15/08/11 | 15/08/11 - 29/08/11 | 1/09/11 - 15/09/11 | 15/09/11 - 30/09/11 | NA | NA | 3/10/11 - 17/10/11 | 17/10/11 - 31/10/11 | NA | NA | 1/11/11 | NA | Surv. Okey Ejehu - [Designation: P.M. (Works)] | Mr. M. B. Obadimeji - [Designation: A.G.M. Admin. & Services]
Actual
Total Cost Plan |  |  |  |  | 47000000
Total Cost Actual
Budget Year: 2011 --- Goods
|  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Goods |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Arrival of Goods | Inspection/Final Acceptance | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
Plan vs Actual
Supply of Underground High Voltage Cables and Kits for Netwoek Expansion | Plan | IBEDC/2011/PP/029 | 29 |  | 25000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 31/03/11 | 31/03/11 - 14/04/11 | 14/04/11 - 12/05/11 | 12/05/11 | 23/06/11 | 23/06/11 - 14/07/11 | 14/07/11 - 11/08/11 | NA | NA | 11/08/11 - 25/08/11 | 25/08/11 - 8/09/11 | 8/09/11 - 29/09/11 | 29/09/11 - 31/10/11 | 31/10/11 - 14/11/11 | Engr. A. F. Adedeji - [Designation: P.M. (O & M)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Supply of Underground Low Voltage Cables and Kits for Network Expansion | Plan | IBEDC/2011/PP/30 | 30 | Bills of Quantity | 25000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 30/06/11 | 30/06/11 - 21/07/11 | 21/07/11 - 18/08/11 | NA | NA | 18/08/11 - 31/08/11 | 31/08/11 - 14/09/11 | 14/09/11 - 5/10/11 | 5/10/11 - 31/10/11 | NA | Engr. A. F. Adedeji - [Designation: P.M. (O & M)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Supply of 33KV Overhead Line Materials for Network Extension | Plan | IBEDC/2011/PP/031 | 31 |  | 10000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 30/06/11 | 30/06/11 - 21/07/11 | 21/07/11 - 18/08/11 | NA | NA | 18/08/11 - 1/09/11 | 1/09/11 - 15/09/11 | 15/09/11 - 6/10/11 | 6/10/11 - 30/11/11 | 30/11/11 - 14/12/11 | Engr. A. F. Adedeji - [Designation: P.M. (O & M)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Supply of 11KV Overhead Line Materials for Network Extension | Plan | IBEDC/2011/PP/032 | 32 | Bills of Quantity | 10000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 30/05/11 | 11/07/11 | 11/07/11 - 1/08/11 | 1/08/11 - 29/08/11 | NA | NA | 29/08/11 - 12/09/11 | 12/09/11 - 26/09/11 | 26/09/11 - 17/10/11 | 17/10/11 - 30/11/11 | 30/11/11 - 14/12/11 | Engr. A. F. Adedeji - [Designation: P.M. (O & M)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Supply of Critical materials for Network maintenance | Plan | IBEDC/2011/PP/033 | 33 | Bills of Quantity | 30000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 17/10/11 - 9/11/11 | 9/11/11 - 23/11/11 | Engr. A. F. Adedeji - [Designation: P.M. (O & M)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Supply of 1No. 10Tons Fork Lift Truck | Plan | IBEDC/2011/PP/034 | 35 | Bills of Quantity | 20000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 20/10/11 | 20/10/11 - 3/11/11 | M. Fetuga - [Designation: Senior Manager (Stores)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Supply of 33KV Metering Panels | Plan | IBEDC/2011/PP/036 | 36 | Bills of Quantity | 60000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 28/10/11 | 28/10/11 - 11/11/11 | O Oyinloye - [Designation: P. M. Marketing] | H Onasile - [Designation: AGM Customer Services]
Actual
Supply of Low Voltage M.D./C.T. operated Meters | Plan | IBEDC/2011/PP/038 | 38 | Bills of Quantity | 50000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 20/10/11 | 20/10/11 - 3/11/11 | O Oyinloye - [Designation: P. M. Marketing] | H Onasile - [Designation: AGM Customer Services]
Actual
Supply of whole Current M.D. Meters | Plan | IBEDC/2011/PP/039 | 39 | Bills of Quantity | 50000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 19/10/11 | 19/10/11 - 2/11/11 | O Oyinloye - [Designation: P. M. Marketing] | H Onasile - [Designation: AGM Customer Services]
Actual
Supply of Single-phase Credit Electronic Meters | Plan | IBEDC/2011/PP/040 | 40 | Bills of Quantity | 45000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 19/10/11 | 19/10/11 - 28/10/11 | O Oyinloye - [Designation: P. M. Marketing] | H Onasile - [Designation: AGM Customer Services]
Actual
Supply of Three-phase Credit Electronic Meters | Plan | IBEDC/2011/PP/41 | 41 | Bills of Quantity | 35000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 28/10/11 | 28/10/11 - 11/11/11 | O Oyinloye - [Designation: P. M. Marketing] | H Onasile - [Designation: AGM Customer Services]
Actual
Supply of Single-phase Prepayment Meters | Plan | IBEDC/2011/PP/042 | 42 | Bills of Quantity | 120000000 | NCB | BPP issues "No Objection" to award/FEC approves | LERB - LOWEST EVALUATED RESPONSIVE BID | PRE | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | 23/09/11 - 7/10/11 | NA | 7/10/11 - 28/10/11 | 28/10/11 - 11/11/11 | O Oyinloye - [Designation: P. M. Marketing] | H Onasile - [Designation: AGM Customer Services]
Actual
Supply of Three-phase Prepayment Meters | Plan | IBEDC/2011/PP/043 | 43 | Bills of Quantity | 80000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 19/10/11 | 19/10/11 - 2/11/11 | O Oyinloye - [Designation: P. M. Marketing] | H Onasile - [Designation: AGM Customer Services]
Actual
Supply of LT Electronic Meters | Plan | IBEDC/2011/PP/044 | 44 | Bills of Quantity | 20000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 28/10/11 | 28/10/11 - 11/11/11 | O Oyinloye - [Designation: P. M. Marketing] | H Onasile - [Designation: AGM Customer Services]
Actual
Supply of Vending machines | Plan | IBEDC/2011/PP/045 | 45 | Bills of Quantity | 8000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 19/10/11 | 19/10/11 - 2/11/11 | O Oyinloye - [Designation: P. M. Marketing] | H Onasile - [Designation: AGM Customer Services]
Actual
Supply of Power Generators | Plan | IBEDC/2011/PP/046 | 46 | Bills of Quantity | 2000000 | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 23/08/11 | NA | NA | 23/08/11 - 6/09/11 | 6/09/11 - 20/09/11 | NA | 20/09/11 - 19/10/11 | 19/10/11 - 2/11/11 | MI Adams - [Designation: P. M. (F/A)] | Gbemi Soyemi-Beecroft - [Designation: AGM Finance/Accounts]
Actual
Supply of Power Inverters | Plan | IBEDC/2011/PP/047 | 47 | Bills of Quantity | 5000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 18/10/11 | 18/10/11 - 1/11/11 | MI Adams | Gbemi Soyemi-Beecroft - [Designation: AGM Finance/Accounts]
Actual
Supply of Cash Receipting and Cash Counting machines | Plan | IBEDC/2011/PP/048 | 48 | Bills of Quantity | 25000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 20/10/11 | 20/10/11 - 3/11/11 | MI Adams - [Designation: P. M. (F/A)] | Gbemi Soyemi-Beecroft - [Designation: AGM Finance/Accounts]
Actual
Supply of Vault-Safes and Fire-proof Cabinets | Plan | IBEDC/2011/PP/049 | 49 | Bills of Quantity | 15000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 18/10/11 | 18/10/11 - 1/11/11 | MI Adams | Gbemi Soyemi-Beecroft - [Designation: AGM Finance/Accounts]
Actual
Supply of Add-Listing and Franking machines | Plan | IBEDC/2011/PP/050 | 50 | Bills of Quantity | 1000000 | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 18/10/11 | 18/10/11 - 1/11/11 | MI Adams | Gbemi Soyemi-Beecroft - [Designation: AGM Finance/Accounts]
Actual
Supply of Line (Salary) Printers | Plan | IBEDC/2011/PP/051 | 51 | Bills of Quantity | 1000000 | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 7/10/11 | 7/10/11 - 21/10/11 | MI Adams - [Designation: P. M. (F/A)] | Gbemi Soyemi-Beecroft - [Designation: AGM Finance/Accounts]
Actual
Supply of Digital Cameras, Binoculars, Miniature Tape Recorders and Wheel Meters | Plan | IBEDC/2011/PP/052 | 52 | Bills of Quantity | 1000000 | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 21/10/11 | 21/10/11 - 4/11/11 | A Shittu - [Designation: P.M. (RE/SP)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Supply of Official Cars | Plan | IBEDC/2011/PP/053 | 53 | Bills of Quantity | 13500000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 14/10/11 | 14/10/11 - 28/10/11 | O Odunusi - [Designation: PM (Admin/Services)] | Mr. M. B. Obadimeji - [Designation: A.G.M. Admin. & Services]
Actual
Supply of Furniture for Training School | Plan | IBEDC/2011/PP/054 | 54 | Bills of Quantity | 1000000 | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 21/10/11 | 21/10/11 - 4/11/11 | O Odunusi - [Designation: PM (Admin/Services)] | Mr. M. B. Obadimeji - [Designation: A.G.M. Admin. & Services]
Actual
Supply of Desktop Computer sets | Plan | IBEDC/2011/PP/055 | 55 | Bills of Quantity | 1000000 | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 21/10/11 | 21/10/11 - 4/11/11 | O Odunusi - [Designation: PM (Admin/Services)] | Mr. M. B. Obadimeji - [Designation: A.G.M. Admin. & Services]
Actual
Supply of furniture for Computer and I.T. Equipment | Plan | IBEDC/2011/PP/056 | 56 | Bills of Quantity | 500000 | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 30/09/11 | 30/09/11 - 14/10/11 | O Odunusi - [Designation: PM (Admin/Services)] | Mr. M. B. Obadimeji - [Designation: A.G.M. Admin. & Services]
Actual
Supply of Laptop Computer Sets | Plan | IBEDC/2011/PP/057 | 57 | Bills of Quantity | 2500000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 14/10/11 | 14/10/11 - 28/10/11 | O Odunusi - [Designation: PM (Admin/Services)] | Mr. M. B. Obadimeji - [Designation: A.G.M. Admin. & Services]
Actual
Supply of Digital Photocopy machines | Plan | IBEDC/2011/PP/058 | 58 | Bills of Quantity | 5000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 21/10/11 | 21/10/11 - 4/11/11 | O Odunusi - [Designation: PM (Admin/Services)] | Mr. M. B. Obadimeji - [Designation: A.G.M. Admin. & Services]
Actual
Supply of Split Airconditioners and Refrigerators | Plan | IBEDC/2011/PP/059 | 59 | Bills of Quantity | 1500000 | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 21/10/11 | 21/10/11 - 4/11/11 | O Odunusi - [Designation: PM (Admin/Services)] | Mr. M. B. Obadimeji - [Designation: A.G.M. Admin. & Services]
Actual
Supply of Rugs and Window blinds; Water Dispensers, Electric kettles, Tea cups, etc. | Plan | IBEDC/2011/PP/060 | 60 | Bills of Quantity | 1000000 | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 21/10/11 | 21/10/11 - 4/11/11 | O Odunusi - [Designation: PM (Admin/Services)] | Mr. M. B. Obadimeji - [Designation: A.G.M. Admin. & Services]
Actual
Supply of Executive Furniture with Visitors' Chairs and other office furniture | Plan | IBEDC/2011/PP/061 | 61 | Bills of Quantity | 2000000 | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 28/10/11 | 28/10/11 - 11/11/11 | O Odunusi - [Designation: PM (Admin/Services)] | Mr. M. B. Obadimeji - [Designation: A.G.M. Admin. & Services]
Actual
Supply of modern filing cabinets and consumables for IT equipment, Computer accessories and Stationery | Plan | IBEDC/2011/PP/062 | 62 | Bills of Quantity | 1000000 | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 28/10/11 | 28/10/11 - 11/11/11 | O Odunusi - [Designation: PM (Admin/Services)] | Mr. M. B. Obadimeji - [Designation: A.G.M. Admin. & Services]
Actual
Printing and Supply of Official Forms and other documents | Plan | IBEDC/2011/PP/063 | 63 | Bills of Quantity | 1000000 | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 21/10/11 | 21/10/11 - 4/11/11 | O Odunusi - [Designation: PM (Admin/Services)] | Mr. M. B. Obadimeji - [Designation: A.G.M. Admin. & Services]
Actual
Supply of Medical facilities and Equipment | Plan | IBEDC/2011/PP/064 | 64 | Bills of Quantity | 2000000 | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 28/10/11 | 28/10/11 - 11/11/11 | O Odunusi - [Designation: PM (Admin/Services)] | Mr. M. B. Obadimeji - [Designation: A.G.M. Admin. & Services]
Actual
Supply of Fire Extinguishers for Injection Substations | Plan | IBEDC/2011/PP/065 | 65 | Bills of Quantity | 1000000 | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 21/10/11 | 21/10/11 - 4/11/11 | Sunday Akinlose - [Designation: Manager Safety] | Engr. C Ahonkhai - [Designation: PM Safety Stds & Work Methods]
Actual
Supply of Fire-proof Wares for Safety personnel | Plan | IBEDC/2011/PP/066 | 66 | Bills of Quantity | 1000000 | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 21/10/11 | 21/10/11 - 4/11/11 | Sunday Akinlose - [Designation: Manager Safety] | Engr. C Ahonkhai - [Designation: PM Safety Stds & Work Methods]
Actual
Supply of Law Books and other Legal materials and accessories | Plan | IBEDC/20011/PP/067 | 67 | Bills of Quantity | 500000 | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 23/09/11 - 21/10/11 | 21/10/11 - 4/11/11 | COK Iyanda - [Designation: Senior Manager] | Mr. M. B. Obadimeji - [Designation: A.G.M. Admin. & Services]
Actual
Supply of 11KV Metering Panels | Plan | IBEDC/2011/PP/037 | 37 | Bills of Quantity | 30000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | 27/05/11 | 30/06/11 | 30/06/11 - 21/07/11 | 21/07/11 - 18/08/11 | NA | NA | 18/08/11 - 31/08/11 | 31/08/11 - 14/09/11 | NA | 14/09/11 - 30/09/11 | 30/09/11 - 14/10/11 | O Oyinloye - [Designation: P. M. Marketing] | H Onasile - [Designation: AGM Customer Services]
Actual
Total Cost Plan |  |  |  |  | 702500000
Total Cost Actual
Budget Year: 2011 --- Works
|  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Works |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Second Stage Bidding - Technical/Financial | First Stage Bidding | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 4 - 6 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Plan vs Actual
Completion of Construction of 1x15MVA, 33/11KV Gaa Imam Inj. S/S. | Plan | IBEDC/2011/PP/001 | 1 | Bills of Quantity | 41000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/03/11 - 13/04/11 | 13/04/11 - 27/04/11 | 27/04/11 - 25/05/11 | NA | NA | 25/05/11 | 6/07/11 | 6/07/11 - 27/07/11 | 27/07/11 - 24/08/11 | NA | NA | 24/08/11 - 7/09/11 | 7/09/11 - 21/09/11 | NA | 5/12/11 | 21/12/11 | NA | Engr. A. F. Adedeji - [Designation: P.M. (O & M)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Completion of 2x15MVA, 33/11KV Budo Efo Injection S/Station | Plan | IBEDC/2011/PP/002 | 2 |  | 130000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/03/11 - 13/04/11 | 13/04/11 - 27/04/11 | 27/04/11 - 25/05/11 | NA | NA | 25/05/11 | 6/07/11 | 6/07/11 - 27/07/11 | 27/07/11 - 24/08/11 | NA | NA | 24/08/11 - 7/09/11 | 7/09/11 - 21/09/11 | NA | 30/11/11 | 14/12/11 | NA | A Shittu - [Designation: P.M. (RE/SP)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Construction of 1x15MVA, 33/11KV Obalufe Inj. Substation | Plan | IBEDC/2011/PP/003 | 3 | Bills of Quantity | 195000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/03/11 - 13/04/11 | 13/04/11 - 27/04/11 | 27/04/11 - 25/05/11 | NA | NA | 25/05/11 | 6/07/11 | 6/07/11 - 27/07/11 | 27/07/11 - 24/08/11 | NA | NA | 24/08/11 - 7/09/11 | 7/09/11 - 21/09/11 | NA | 21/11/11 | 6/12/11 | NA | Sehinde Onaleye - [Designation: P. M. P C M] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Construction of 1x15MVA, 33/11KV Eleweran Inj. Substation | Plan | IBEDC/2011/PP/004 | 4 |  | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/03/11 - 13/04/11 | 13/04/11 - 27/04/11 | 27/04/11 - 25/05/11 | NA | NA | 25/05/11 | 6/07/11 | 6/07/11 - 27/07/11 | 27/07/11 - 24/08/11 | NA | NA | 24/08/11 - 7/09/11 | 7/09/11 - 21/09/11 | NA | 14/11/11 | 19/12/11 | NA | Engr. A. F. Adedeji - [Designation: P.M. (O & M)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Completion of Construction of 2x15MVA, 33/11KV Ilesa Inj. Substation | Plan | IBEDC/2011/PP/005 | 5 | Bills of Quantity | 50000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/03/11 - 13/04/11 | 13/04/11 - 27/04/11 | 27/04/11 - 25/05/11 | NA | NA | 25/05/11 | 6/07/11 | 6/07/11 - 27/07/11 | 27/07/11 - 24/08/11 | NA | NA | 24/08/11 - 7/09/11 | 7/09/11 - 21/09/11 | NA | 15/11/11 | 14/12/11 | NA | Engr. A. F. Adedeji - [Designation: P.M. (O & M)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Construction of 1x15MVA, 33/11KV Aroje Inj. Substation | Plan | IBEDC/2011/PP/006 | 6 |  | 180000000 |  | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/03/11 - 13/04/11 | 13/04/11 - 27/04/11 | 27/04/11 - 25/05/11 | NA | NA | 25/05/11 | 6/07/11 | 6/07/11 - 27/07/11 | 27/07/11 - 24/08/11 | NA | NA | 24/08/11 - 7/09/11 | 7/09/11 - 21/09/11 | NA | 9/11/11 | 30/11/11 | NA | Engr. A. F. Adedeji - [Designation: P.M. (O & M)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Construction of 1x15MVA, 33/11KV Ifelodun Inj. Substation | Plan | IBEDC/2011/PP/007 | 7 | Bills of Quantity | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/03/11 - 13/04/11 | 13/04/11 - 27/04/11 | 27/04/11 - 25/05/11 | NA | NA | 25/05/11 | 6/07/11 | 6/07/11 - 27/07/11 | 27/07/11 - 24/08/11 | NA | NA | 24/08/11 - 7/09/11 | 7/09/11 - 21/09/11 | NA | 21/11/11 | 12/12/11 | NA | A Shittu - [Designation: P.M. (RE/SP)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Completion of Construction of 1x15MVA, 33/11KV Ota Inj. Substation | Plan | IBEDC/2011/PP/008 | 8 | Bills of Quantity | 70000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/03/11 - 13/04/11 | 13/04/11 - 27/04/11 | 27/04/11 - 25/05/11 | NA | NA | 25/05/11 | 6/07/11 | 6/07/11 - 27/07/11 | 27/07/11 - 24/08/11 | NA | NA | 24/08/11 - 7/09/11 | 7/09/11 - 21/09/11 | NA | 21/11/11 | 12/12/11 | NA | Engr. A. F. Adedeji - [Designation: P.M. (O & M)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Completion of Construction of 1x15MVA, 33/11KV Odi-Olowo Inj. Substation | Plan | IBEDC/2011/PP/009 | 9 | Bills of Quantity | 55000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/03/11 - 13/04/11 | 13/04/11 - 27/04/11 | 27/04/11 - 25/05/11 | NA | NA | 25/05/11 | 6/07/11 | 6/07/11 - 27/07/11 | 27/07/11 - 24/08/11 | NA | NA | 24/08/11 - 7/09/11 | 7/09/11 - 21/09/11 | NA | 14/11/11 | 12/12/11 | NA | Engr. A. F. Adedeji - [Designation: P.M. (O & M)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Construction of 1x15MVA, 33/11KV Isanlu-Isin Inj. S/S. in Kwara State | Plan | IBEDC/2011/PP/010 | 10 |  | 180000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/03/11 - 13/04/11 | 13/04/11 - 27/04/11 | 27/04/11 - 25/05/11 | NA | NA | 25/05/11 | 6/07/11 | 6/07/11 - 27/07/11 | 27/07/11 - 24/08/11 | NA | NA | 24/08/11 - 7/09/11 | 7/09/11 - 21/09/11 | NA | 15/11/11 | 12/12/11 | NA | Sehinde Onaleye - [Designation: P. M. P C M] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Rehabilitation of Distribution Transformer Substations | Plan | IBEDC/2011/PP/011 | 11 | Bills of Quantity | 8000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/03/11 - 13/04/11 | 13/04/11 - 27/04/11 | 27/04/11 - 25/05/11 | NA | NA | 25/05/11 | 6/07/11 | 6/07/11 - 27/07/11 | 27/07/11 - 24/08/11 | NA | NA | 24/08/11 - 7/09/11 | 7/09/11 - 21/09/11 | NA | 7/11/11 | 30/11/11 | NA | Engr. A. F. Adedeji - [Designation: P.M. (O & M)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Purchase & Installation of Distribution Transformers for Business Units in Oyo & Ogun States | Plan | IBEDC/2011/PP/012 | 12 |  | 100000000 |  | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/03/11 - 13/04/11 | 13/04/11 - 27/04/11 | 27/04/11 - 25/05/11 | NA | NA | 25/05/11 | 6/07/11 | 6/07/11 - 27/07/11 | 27/07/11 - 24/08/11 | NA | NA | 24/08/11 - 7/09/11 | 7/09/11 - 21/09/11 | NA | 14/11/11 | 12/12/11 | NA | Engr. A. F. Adedeji - [Designation: P.M. (O & M)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Purchase & Installation of Distribution Transformers for Business Units in Osun & Kwara States | Plan | IBEDC/2011/PP/013 | 13 | Bills of Quantity | 100000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/03/11 - 13/04/11 | 13/04/11 - 27/04/11 | 27/04/11 - 25/05/11 | NA | NA | 25/05/11 | 6/07/11 | 6/07/11 - 27/07/11 | 27/07/11 - 24/08/11 | NA | NA | 24/08/11 - 7/09/11 | 7/09/11 - 21/09/11 | NA | 7/11/11 | 29/11/11 | NA | Engr. A. F. Adedeji - [Designation: P.M. (O & M)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Rehabilitation of Overhead/HT Lines | Plan | IBEDC/2011/PP/014 | 14 | Bills of Quantity | 20000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/03/11 - 13/04/11 | 13/04/11 - 27/04/11 | 27/04/11 - 25/05/11 | NA | NA | 25/05/11 | 6/07/11 | 6/07/11 - 27/07/11 | 27/07/11 - 24/08/11 | NA | NA | 24/08/11 - 7/09/11 | 7/09/11 - 21/09/11 | NA | 17/10/11 | 12/12/11 | NA | Engr. A. F. Adedeji - [Designation: P.M. (O & M)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Rehabilitation of Overhead/LT Lines | Plan | IBEDC/2011/PP/015 | 15 | Bills of Quantity | 20000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/03/11 - 13/04/11 | 13/04/11 - 27/04/11 | 27/04/11 - 25/05/11 | NA | NA | 25/05/11 | 6/07/11 | 6/07/11 - 27/07/11 | 27/07/11 - 24/08/11 | NA | NA | 24/08/11 - 7/09/11 | 7/09/11 - 21/09/11 | 21/09/11 - 12/10/11 | 25/11/11 | 12/12/11 | NA | Engr. A. F. Adedeji - [Designation: P.M. (O & M)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Replacement of Matching CTs and Relays | Plan | IBEDC/2011/PP/016 | 16 |  | 31000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/03/11 - 13/04/11 | 13/04/11 - 27/04/11 | 27/04/11 - 25/05/11 | NA | NA | 25/05/11 | 6/07/11 | 6/07/11 - 27/07/11 | 27/07/11 - 24/08/11 | NA | NA | 24/08/11 - 7/09/11 | 7/09/11 - 21/09/11 | 21/09/11 - 12/10/11 | 30/11/11 | 14/12/11 |  | Engr. A. F. Adedeji - [Designation: P.M. (O & M)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Completion of Construction of office building in Ota, Ogun State | Plan | IBEDC/2011/PP/018 | 18 | Bills of Quantity | 23000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/03/11 - 13/04/11 | 13/04/11 - 27/04/11 | 27/04/11 - 25/05/11 | NA | NA | 25/05/11 | 6/07/11 | 6/07/11 - 27/07/11 | 27/07/11 - 24/08/11 | NA | NA | 24/08/11 - 7/09/11 | 7/09/11 - 21/09/11 | NA | 14/11/11 | 13/12/11 | NA | Surv. Okey Ejehu - [Designation: P.M. (Works)] | Mr. M. B. Obadimeji - [Designation: A.G.M. Admin. & Services]
Actual
Completion of Construction of Standard Store Complex with facilities in Eleyele, Ibadan | Plan | IBEDC/2011/PP/019 | 19 | Bills of Quantity | 10000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/03/11 - 13/04/11 | 13/04/11 - 27/04/11 | 27/04/11 - 25/05/11 | NA | NA | 25/05/11 | 6/07/11 | 6/07/11 - 27/07/11 | 27/07/11 - 24/08/11 | NA | NA | 24/08/11 - 7/09/11 | 7/09/11 - 21/09/11 | NA | 7/11/11 | 30/11/11 | NA | Surv. Okey Ejehu - [Designation: P.M. (Works)] | Mr. M. B. Obadimeji - [Designation: A.G.M. Admin. & Services]
Actual
Reconstruction of collapsed fence & Rehabilitation of 33KV Inj.S/S. Akarigbo | Plan | IBEDC/2011/PP/020 | 20 | Bills of Quantity | 2000000 | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/03/11 - 13/04/11 | 13/04/11 - 27/04/11 | 27/04/11 - 25/05/11 | NA | NA | 25/05/11 | 6/07/11 | 6/07/11 - 27/07/11 | 27/07/11 - 24/08/11 | NA | NA | 24/08/11 - 7/09/11 | 7/09/11 - 21/09/11 | NA | 25/10/11 | 22/11/11 | NA | Surv. Okey Ejehu - [Designation: P.M. (Works)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Rehabilitation of 33KV Injection Sub Station in New Bussa | Plan | IBEDC/2011/PP/021 | 21 | Bills of Quantity | 2200000 | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/03/11 - 13/04/11 | 13/04/11 - 27/04/11 | 27/04/11 - 25/05/11 | NA | NA | 25/05/11 | 6/07/11 | 6/07/11 - 27/07/11 | 27/07/11 - 12/08/11 | NA | NA | 12/08/11 - 26/08/11 | 26/08/11 - 9/09/11 | 9/09/11 - 30/09/11 | 18/11/11 | 30/11/11 | NA | Surv. Okey Ejehu - [Designation: P.M. (Works)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Rehabilitation of 33KV Injection Substation in Ajase-Ipo, Offa | Plan | IBEDC/2011/PP/023 | 23 | Bills of Quantity | 3000000 | NCB | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/03/11 - 13/04/11 | 13/04/11 - 27/04/11 | 27/04/11 - 25/05/11 | NA | NA | 25/05/11 | 6/07/11 | 6/07/11 - 27/07/11 | 27/07/11 - 24/08/11 | NA | NA | 24/08/11 - 7/09/11 | 7/09/11 - 21/09/11 | 21/09/11 - 12/10/11 | 25/11/11 | 8/12/11 | NA | Surv. Okey Ejehu - [Designation: P.M. (Works)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Rehabilitation and Re-roofing of Ilesa Service Centre | Plan | IBEDC/2011/PP/024 | 24 | Bills of Quantity | 3500000 | NCB | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/03/11 - 13/04/11 | 13/04/11 - 27/04/11 | 27/04/11 - 25/05/11 | NA | NA | 25/05/11 | 30/06/11 | 30/06/11 - 21/07/11 | 21/07/11 - 18/08/11 | NA | NA | 18/08/11 - 31/08/11 | 31/08/11 - 14/09/11 | 14/09/11 - 5/10/11 | 30/11/11 | 7/12/11 | NA | Surv. Okey Ejehu - [Designation: P.M. (Works)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Renovation of Mokola Service Centre Ibadan. | Plan | IBEDC/2011/PP/025 | 25 | Bills of Quantity | 3500000 | NCB | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/03/11 - 13/04/11 | 13/04/11 - 27/04/11 | 27/04/11 - 25/05/11 | NA | NA | 25/05/11 | 30/06/11 | 30/06/11 - 21/07/11 | 21/07/11 - 18/08/11 | NA | NA | 18/08/11 - 31/08/11 | 31/08/11 - 14/09/11 | 14/09/11 - 5/10/11 | 14/11/11 | 25/11/11 | NA | Surv. Okey Ejehu - [Designation: P.M. (Works)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Rehabilitation of Ago-Iwoye Injection Substation | Plan | IBEDC/2011/PP/026 | 26 |  | 3700000 | NCB | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/03/11 - 13/04/11 | 13/04/11 - 27/04/11 | 27/04/11 - 25/05/11 | NA | NA | 25/05/11 | 31/05/11 | 31/05/11 - 21/06/11 | 21/06/11 - 30/06/11 | NA | NA | 30/06/11 - 14/07/11 | 21/07/11 - 4/08/11 | 4/08/11 - 25/08/11 | 14/10/11 | 26/10/11 | NA | Surv. Okey Ejehu - [Designation: P.M. (Works)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Rehabilitation of Saki 33KV Injection Substation | Plan | IBEDC/2011/PP/027 | 27 | Bills of Quantity | 2800000 | NCB | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 23/03/11 - 13/04/11 | 13/04/11 - 27/04/11 | 27/04/11 - 25/05/11 | NA | NA | 25/05/11 | 31/05/11 | 31/05/11 - 21/06/11 | 21/06/11 - 19/07/11 | NA | NA | 19/07/11 - 2/08/11 | 2/08/11 - 16/08/11 | 16/08/11 - 31/08/11 | 31/10/11 | 11/11/11 | NA | Surv. Okey Ejehu - [Designation: P.M. (Works)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Installation of Back-up Server for Prepayment Metering | Plan | IBEDC/2011/PP/028 | 28 |  | 1500000000 | INCB | BPP issues "No Objection" to award/FEC approves | LERB - LOWEST EVALUATED RESPONSIVE BID | PRE | PRIOR | 23/03/11 - 13/04/11 | 13/04/11 - 27/04/11 | 27/04/11 - 25/05/11 | NA | NA | 25/05/11 | 31/05/11 | 31/05/11 - 21/06/11 | 21/06/11 - 30/06/11 | NA | 30/06/11 - 14/07/11 | 14/07/11 - 28/07/11 | 28/07/11 - 11/08/11 | 11/08/11 - 31/08/11 | 30/11/11 | 15/12/11 | NA | O Oyinloye - [Designation: P. M. Marketing] | H Onasile - [Designation: AGM Customer Services]
Actual
Rehabilitation of 33KV Injection Substation in Egbe | Plan | IBEDC/2011/PP/022 | 22 | Bills of Quantity | 4500000 |  | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 15/04/11 | 15/04/11 - 29/04/11 | 29/04/11 - 27/05/11 | NA | NA | 27/05/11 | 8/07/11 | 8/07/11 - 29/07/11 | 29/07/11 - 26/08/11 | NA | NA | 26/08/11 - 9/09/11 | 9/09/11 - 23/09/11 | NA | 18/10/11 | 25/11/11 | NA | Surv. Okey Ejehu - [Designation: P.M. (Works)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Total Cost Plan |  |  |  |  | 3118200000
Total Cost Actual
Budget Year: 2011 --- Non-Consultancy Services
|  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 1 weeks | 2 - 4 weeks | 2 weeks | 2 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
Trace Clearing of Distribution Network Lines | Plan | IBEDC/2011/PP/017 | 17 | Lump Sum | 26000000 | NCB | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | PST | PST | 23/03/11 - 13/04/11 | 13/04/11 - 27/04/11 | 27/04/11 - 11/05/11 | 11/05/11 - 18/05/11 | 31/05/11 | 31/05/11 - 14/06/11 | NA | NA | 14/06/11 - 28/06/11 | 28/06/11 - 12/07/11 | 12/07/11 - 26/07/11 | 26/07/11 - 9/08/11 | 9/08/11 - 23/08/11 | 23/08/11 - 20/09/11 | NA | NA | 20/09/11 - 4/10/11 | 4/10/11 - 18/10/11 | NA | 26/10/11 | 31/10/11 | NA | Engr. A. F. Adedeji - [Designation: P.M. (O & M)] | Engr. O Oyelade - [Designation: AGM Technical Services]
Actual
Total Cost Plan |  |  |  |  | 26000000
Total Cost Actual

## CIPB
Ministry/Department/Agency: Civil Defence, Immigration and Prison Service Board (CIPB)
Budget Year: 2011 --- Consultancy Service
| Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
Project Description | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing /Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/ Financial | Negotiations | MDA Approval/ No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/ Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/ Designation | Name/Designation
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 1 weeks | 2 - 4 weeks | 2 weeks | 2 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
PROJECT DESIGN OF DATABASE CAPTURING IN CDIPB OFFICE, ABUJA | CDIPB/CSULT/2011/PKG/001A | 1 | Lump Sum | 1250000 |  | Accounting Officer: Director General/CEO | LC - Least Cost | NA | PST | 22/12/10 - 5/01/11 | 5/01/11 - 6/01/11 | 6/01/11 - 20/01/11 | 20/01/11 - 21/01/11 | 21/01/11 | 21/01/11 - 24/01/11 | 24/01/11 - 7/02/11 | 7/02/11 - 8/02/11 | 8/02/11 - 11/02/11 | 11/02/11 - 14/02/11 | 14/02/11 - 16/02/11 | 16/02/11 - 18/02/11 | NA | 18/02/11 - 21/02/11 | 1250000 | NA | 21/02/11 - 23/02/11 | 23/02/11 - 25/02/11 | NA | 28/02/11 | 28/02/11 | 1250000 | ABDULKADRI AMUDA - [Designation: HEAD OF PROCUREMENT] | NANVEN NIMFEL - [Designation: DIRECTOR/SECRETARY]
DESIGN AND PRODUCTION OF MANUSCRIPT ON GUIDELINES FOR APPOINTMENT, PROMOTION AND DISCIPLINE; CONDITION AND SCHEME OF SERVICE FOR CDIPB OFFICE | CDIPB/CSULT/2011/PKG/002A | 2 |  | 2450000 |  | Accounting Officer: Director General/CEO | LC - Least Cost | NA | PST | 22/12/10 - 5/01/11 | 5/01/11 - 6/01/11 | 6/01/11 - 20/01/11 | 20/01/11 - 21/01/11 | 21/01/11 | 21/01/11 - 24/01/11 | 24/01/11 - 7/02/11 | 7/02/11 - 8/02/11 | 8/02/11 - 11/02/11 | 11/02/11 - 14/02/11 | 14/02/11 - 16/02/11 | 16/02/11 - 18/02/11 | NA | 18/02/11 - 21/02/11 | 2450000 | NA | 21/02/11 - 23/02/11 | 23/02/11 - 25/02/11 | NA | 25/02/11 | 2/03/11 | NA | ABDULKADRI AMUDA - [Designation: HEAD OF PROCUREMENT] | NANVEN NIMFEL - [Designation: DIRECTOR/SECRETARY]
TRINING OF THE END USERS (40 BOARD'S PERSONNEL) | CDIPB/CSULT/2011/PKG/003A | 3 | Lump Sum | 2100000 |  | Accounting Officer: Director General/CEO | LC - Least Cost | NA | PST | 15/06/11 - 21/06/11 | 21/06/11 - 22/06/11 | 22/06/11 - 6/07/11 | 6/07/11 - 8/07/11 | 8/07/11 | 8/07/11 - 12/07/11 | 12/07/11 - 26/07/11 | 26/07/11 - 27/07/11 | 27/07/11 - 29/07/11 | 29/07/11 - 2/08/11 | 2/08/11 - 4/08/11 | 4/08/11 - 8/08/11 | NA | 8/08/11 - 10/08/11 | 2100000 | NA | 10/08/11 - 12/08/11 | 12/08/11 - 16/08/11 | NA | 16/08/11 | 19/08/11 | 2100000 | ABDULKADRI AMUDA - [Designation: HEAD OF PROCUREMENT] | NANVEN NIMFEL - [Designation: DIRECTOR/SECRETARY]
CAPTURING OF 40,000 PERSONNELS FROM CIVIL DEFENCE, IMMIGRATION AND PRISONS SERVICES | CDIPB/CSULT/2011/PKG/004A | 4 | Lump Sum | 6077500 |  | Parastatals Tenders Board | LC - Least Cost | NA | PST | 5/07/11 - 18/07/11 | 18/07/11 - 20/07/11 | 20/07/11 - 3/08/11 | 3/08/11 - 5/08/11 | 5/08/11 | 5/08/11 - 9/08/11 | 9/08/11 - 23/08/11 | 23/08/11 - 24/08/11 | 24/08/11 - 30/08/11 | 30/08/11 - 2/09/11 | 2/09/11 - 8/09/11 | 8/09/11 - 14/09/11 | NA | 14/09/11 - 16/09/11 | 6077500 | NA | 16/09/11 - 20/09/11 | 20/09/11 - 22/09/11 | NA | 22/09/11 | 29/09/11 | NA | ABDULKADRI AMUDA - [Designation: HEAD OF PROCUREMENT] | NANVEN NIMFEL - [Designation: DIRECTOR/SECRETARY]
Total Cost Plan |  |  |  | 11877500 | [19 empty] | 11877500 | [6 empty] | 3350000
Total Cost Actual
Budget Year: 2011 --- Goods
| Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Goods |  |  | Action Party | Champion
Project Description | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing /Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/ Advance Payment | Arrival of Goods | Inspection/ Final Acceptance | Name/ Designation | Name/ Designation
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
SUPPLY AND INSTALLATION OF 3NOS SERVERS, 20NOS OF COMPUTER SETS, 20NOS UPS AND 6NOS OF PRINTERS INTO CDIPB OFFICE, ABUJA. | CDIPB/GOODS/2011/PKG/001 | 1 | Bills of Quantity | 7775000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 7/04/11 | 7/04/11 - 8/04/11 | 8/04/11 - 14/04/11 | 14/04/11 | 11/05/11 | 11/05/11 - 13/05/11 | 13/05/11 - 16/05/11 | 7775000 | NA | 16/05/11 - 18/05/11 | 18/05/11 - 20/05/11 | NA | 20/05/11 - 31/05/11 | 31/05/11 - 3/06/11 | ABDULKADRI AMUDA - [Designation: HEAD OF PROCUREMENT] | NANVEN NIMFEL - [Designation: DIRECTOR/SECRETARY]
SUPPLY AND INSTALLATION OF COMPUTER PROGRAMMS SOFTWARES INTO CDIPB OFFICE, ABUJA. | CDIPB/GOODS/2011/PKG/002A | 2 |  | 5315000 | NCB | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 7/04/11 | 7/04/11 - 8/04/11 | 8/04/11 - 14/04/11 | 14/04/11 | 11/05/11 | 11/05/11 - 13/05/11 | 13/05/11 - 16/05/11 | 5315000 | NA | 16/05/11 - 18/05/11 | 18/05/11 - 20/05/11 | NA | 20/05/11 - 2/06/11 | 2/06/11 - 6/06/11 | ABDULKADRI AMUDA - [Designation: HEAD OF PROCUREMENT] | NANVEN NIMFEL - [Designation: DIRECTOR/SECRETARY]
SUPPLY AND INSTALLATION OF 3NOS KVA UPS AND 5KVA INVERTER/BATTERIES INTO CDIPB OFFICE, ABUJA. | CDIPB/GOODS/2011/PKG/003A | 3 | Bills of Quantity | 2182500 | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 7/04/11 | 7/04/11 - 8/04/11 | 8/04/11 - 14/04/11 | 14/04/11 | 11/05/11 | 11/05/11 - 13/05/11 | 13/05/11 - 16/05/11 | 2182500 | NA | 16/05/11 - 18/05/11 | 18/05/11 - 20/05/11 | NA | 20/05/11 - 2/06/11 | 2/06/11 - 6/06/11 | ABDULKADRI AMUDA - [Designation: HEAD OF PROCUREMENT] | NANVEN NIMFEL - [Designation: DIRECTOR/SECRETARY]
SUPPLY AND INSTALLATION OF DISH AND LAYING OF NETWORK INTO CDIPB OFFICE, ABUJA. | CDIPB/GOODS/2011/PKG/004A | 4 |  | 9100000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/03/11 - 7/04/11 | 7/04/11 - 8/04/11 | 8/04/11 - 14/04/11 | 14/04/11 | 11/05/11 | 11/05/11 - 13/05/11 | 13/05/11 - 16/05/11 | 9100000 | NA | 16/05/11 - 18/05/11 | 18/05/11 - 20/05/11 | NA | 20/05/11 - 2/06/11 | 2/06/11 - 6/06/11 | ABDULKADRI AMUDA - [Designation: HEAD OF PROCUREMENT] | NANVEN NIMFEL - [Designation: DIRECTOR/SECRETARY]
PRINTING OF MANUSCRIPTS ON GUIDELINES FOR APPOINTMENT, PROMOTION & DISCIPLINE; CONDITION & SCHEME OF SERVICE OF 45,000 COPIES EACH FOR PARAMILITARY OFFICERS | CDIPB/GOODS/2011/PKG/005A | 5 | Bills of Quantity | 21870000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/05/11 - 31/05/11 | 31/05/11 - 2/06/11 | 2/06/11 - 15/06/11 | 15/06/11 | 13/07/11 | 13/07/11 - 19/07/11 | 19/07/11 - 21/07/11 | 21870000 | NA | 21/07/11 - 25/07/11 | 25/07/11 - 27/07/11 | NA | 27/07/11 - 26/08/11 | 26/08/11 - 1/09/11 | ABDULKADRI AMUDA - [Designation: HEAD OF PROCUREMENT] | NANVEN NIMFEL - [Designation: DIRECTOR/SECRETARY]
PRINTING OF THE BOARDS' HANDBOOK AND QUARTERLY REPORTS FROM THE THREE PARAMILITARY SERVICES | CDIPB/GOODS/2011/PKG/006A | 6 | Bills of Quantity | 8300000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PST | PST | 25/05/11 - 31/05/11 | 31/05/11 - 2/06/11 | 2/06/11 - 15/06/11 | 15/06/11 | 13/07/11 | 13/07/11 - 19/07/11 | 19/07/11 - 21/07/11 | 8300000 | NA | 21/07/11 - 25/07/11 | 25/07/11 - 27/07/11 | NA | 27/07/11 - 26/08/11 | 26/08/11 - 1/09/11 | ABDULKADRI AMUDA - [Designation: HEAD OF PROCUREMENT] | NANVEN NIMFEL - [Designation: DIRECTOR/SECRETARY]
Total Cost Plan |  |  |  | 54542500 | [12 empty] | 54542500
Total Cost Actual

## Immigration Serv
Ministry/Department/Agency: Ministry of Interior /Nigeria Immigration Service
Desk Officer/Contact #: M.S. GWANDU '08036239323
Budget Year: 2011 --- Goods
| Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Goods |  |  | Action Party |  | Champion
Project Description | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pro-Qualification | Bid Invitation Date | Bid Closing/ Opening | Submission of Bid Evaluation Report | MDA Approval/ BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/ Advance Payment | Arrival of Goods | Inspection/ Final Acceptance | Name | Designation | Name | Designation
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
Printing of Non- Security Documents | NIS/PCM/11 | 001 | BOQ | 45000000 | NCB | Immigration Service Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 9th Mar - 20th April 2011 |  | 01/03/11 - 21/03/11 | 22/03/11 - 04/04/11 | 05/04/11 - 18/04/11 | 27/04/11 - '01/06/11 | 01/06/11 - '01/06/11 | 09/06/11 - 30/06/11 | 04/07/11 - 11/07/11 | 45000000 |  | 18/07/11 - 25/07/11 | 26/07/11 - 11/08/11 | 12/08/11 -26/08/11 | 27/08/11 | 26/09/11 | M. S. Gwandu | CIS | U. A. Auna | ACI
Printing of Security Documents | NIS/PCM/11 | 002 | BOQ | 100000000 | DP | Immigration Service Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 9th Mar - 20th April 2011 |  | 01/03/11 - 21/03/11 | 22/03/11 - 04/04/11 | 05/04/11 - 18/04/11 | 27/04/11 - '01/06/11 | 01/06/11 - '01/06/11 | 09/06/11 - 30/06/11 | 04/07/11 - 11/07/11 | 100000000 |  | 18/07/11 - 25/07/11 | 26/07/11 - 11/08/11 | 12/08/11 -26/08/11 | 27/08/11 | 26/09/11 | " | " | " | "
Drugs & Medical Supplies | NIS/PCM/11 | 003 | BOQ | 22500000 | NCB | Immigration Service Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 9th Mar - 20th April 2011 |  | 01/03/11 - 21/03/11 | 22/03/11 - 04/04/11 | 05/04/11 - 18/04/11 | 27/04/11 - '01/06/11 | 01/06/11 - '01/06/11 | 09/06/11 - 30/06/11 | 04/07/11 - 11/07/11 | 22500000 |  | 18/07/11 - 25/07/11 | 26/07/11 - 11/08/11 | 12/08/11 -26/08/11 | 27/08/11 | 26/09/11 | " | " | " | "
Field & CampingMaterials Supplies | NIS/PCM/11 | 004 | BOQ | 99000000 | NCB | Immigration Service Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 9th Mar - 20th April 2011 |  | 01/03/11 - 21/03/11 | 22/03/11 - 04/04/11 | 05/04/11 - 18/04/11 | 27/04/11 - '01/06/11 | 01/06/11 - '01/06/11 | 09/06/11 - 30/06/11 | 04/07/11 - 11/07/11 | 99000000 |  | 18/07/11 - 25/07/11 | 26/07/11 - 11/08/11 | 12/08/11 -26/08/11 | 27/08/11 | 26/09/11 | " | " | " | "
Supply of Uniforms & other Clothing | NIS/PCM/11 | 005 | BOQ | 180000000 | NCB | Immigration Service Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 9th Mar - 20th April 2011 |  | 01/03/11 - 21/03/11 | 22/03/11 - 04/04/11 | 05/04/11 - 18/04/11 | 27/04/11 - '01/06/11 | 01/06/11 - '01/06/11 | 09/06/11 - 30/06/11 | 04/07/11 - 11/07/11 | 180000000 |  | 18/07/11 - 25/07/11 | 26/07/11 - 11/08/11 | 12/08/11 -26/08/11 | 27/08/11 | 26/09/11 | " | " | " | "
Maintenance of Motor Vehicle / Transport Equipment | NIS/PCM/11 | 006 | BOQ | 125000000 | DP/RT | Immigration Service Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 9th Mar - 20th April 2011 |  | 01/03/11 - 21/03/11 | 22/03/11 - 04/04/11 | 05/04/11 - 18/04/11 | 27/04/11 - '01/06/11 | 01/06/11 - '01/06/11 | 09/06/11 - 30/06/11 | 04/07/11 - 11/07/11 | 125000000 |  | 18/07/11 - 25/07/11 | 26/07/11 - 11/08/11 | 12/08/11 -26/08/11 | 27/08/11 | 26/09/11 | " | " | " | "
Purchase of Motorcycles | NIS/PCM/11 | 007 | BOQ | 31730750 | NCB | Immigration Service Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 9th Mar - 20th April 2011 |  | 01/03/11 - 21/03/11 | 22/03/11 - 04/04/11 | 05/04/11 - 18/04/11 | 27/04/11 - '01/06/11 | 01/06/11 - '01/06/11 | 09/06/11 - 30/06/11 | 04/07/11 - 11/07/11 | 31730750 |  | 18/07/11 - 25/07/11 | 26/07/11 - 11/08/11 | 12/08/11 -26/08/11 | 27/08/11 | 26/09/11 | " | " | " | "
Purchase of Motor Vehicles | NIS/PCM/11 | 008 | BOQ | 350000000 | DP/RT | Immigration Service Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 9th Mar - 20th April 2011 |  | 01/03/11 - 21/03/11 | 22/03/11 - 04/04/11 | 05/04/11 - 18/04/11 | 27/04/11 - '01/06/11 | 01/06/11 - '01/06/11 | 09/06/11 - 30/06/11 | 04/07/11 - 11/07/11 | 350000000 |  | 18/07/11 - 25/07/11 | 26/07/11 - 11/08/11 | 12/08/11 -26/08/11 | 27/08/11 | 26/09/11 | M. S. Gwandu | CIS | U. A. Auna | ACI
Purchase of Office Furniture and Fittings | NIS/PCM/11 | 009 | BOQ | 142596126 | NCB | Immigration Service Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 9th Mar - 20th April 2011 |  | 01/03/11 - 21/03/11 | 22/03/11 - 04/04/11 | 05/04/11 - 18/04/11 | 27/04/11 - '01/06/11 | 01/06/11 - '01/06/11 | 09/06/11 - 30/06/11 | 04/07/11 - 11/07/11 | 142596126 |  | 18/07/11 - 25/07/11 | 26/07/11 - 11/08/11 | 12/08/11 -26/08/11 | 27/08/11 | 26/09/11 | " | " | " | "
Purchase of Power Generating Set | NIS/PCM/11 | 010 | BOQ | 70000000 | NCB | Immigration Service Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 9th Mar - 20th April 2011 |  | 01/03/11 - 21/03/11 | 22/03/11 - 04/04/11 | 05/04/11 - 18/04/11 | 27/04/11 - '01/06/11 | 01/06/11 - '01/06/11 | 09/06/11 - 30/06/11 | 04/07/11 - 11/07/11 | 70000000 |  | 18/07/11 - 25/07/11 | 26/07/11 - 11/08/11 | 12/08/11 -26/08/11 | 27/08/11 | 26/09/11 | " | " | " | "
Purchase of Health / Medical Equipment | NIS/PCM/11 | 011 | BOQ | 5000000 | NCB | Immigration Service Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 9th Mar - 20th April 2011 |  | 01/03/11 - 21/03/11 | 22/03/11 - 04/04/11 | 05/04/11 - 18/04/11 | 27/04/11 - '01/06/11 | 01/06/11 - '01/06/11 | 09/06/11 - 30/06/11 | 04/07/11 - 11/07/11 | 5000000 |  | 18/07/11 - 25/07/11 | 26/07/11 - 11/08/11 | 12/08/11 -26/08/11 | 27/08/11 | 26/09/11 | " | " | " | "
Purchase of Security Equipment | NIS/PCM/11 | 012 | BOQ | 340269408 | DP/RT | Immigration Service Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 9th Mar - 20th April 2011 |  | 01/03/11 - 21/03/11 | 22/03/11 - 04/04/11 | 05/04/11 - 18/04/11 | 27/04/11 - '01/06/11 | 01/06/11 - '01/06/11 | 09/06/11 - 30/06/11 | 04/07/11 - 11/07/11 | 340269408 |  | 18/07/11 - 25/07/11 | 26/07/11 - 11/08/11 | 12/08/11 -26/08/11 | 27/08/11 | 26/09/11 | " | " | " | "
Purchase of Air Navigational Equipment | NIS/PCM/11 | 013 | BOQ | 250000000 | NCB | Immigration Service Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 9th Mar - 20th April 2011 |  | 01/03/11 - 21/03/11 | 22/03/11 - 04/04/11 | 05/04/11 - 18/04/11 | 27/04/11 - '01/06/11 | 01/06/11 - '01/06/11 | 09/06/11 - 30/06/11 | 04/07/11 - 11/07/11 | 250000000 |  | 18/07/11 - 25/07/11 | 26/07/11 - 11/08/11 | 12/08/11 -26/08/11 | 27/08/11 | 26/09/11 | " | " | " | "
Total Cost Plan |  |  |  | 1761096284 | [12 empty] | 1761096284
Total Cost Actual
Budget Year: 2011 -- Works
| Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/ Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Works |  |  |  | Action Party |  | Champion
Project Description | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pro-Qualification | Bid Invitation Date | Bid Closing/ Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/ Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Name | Designation | Name | Designation
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 24 weeks
Maintenance of Office Building / Residential QTRS | NIS/PCM/11 | 014 | BOQ | 80000000 | NCB | Immigration Service Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 9th Mar - 20th April 2011 |  | 01/03/11 - 21/03/11 | 22/03/11 - 04/04/11 | 05/04/11 - 18/04/11 | 27/04/11 - '01/06/11 | 01/06/11 - '01/06/11 | 09/06/11 - 30/06/11 | 04/07/11 - 11/07/11 | 80000000 |  | 18/07/11 - 25/07/11 | 26/07/11 - 11/08/11 | 12/08/11 -26/08/11 | 01/09/11 | 31/12/11 | Budgetary Provision | H. M. Maishanu | CIS | I. D. Musa | CII
Construction / Provision of Office Building | NIS/PCM/11 | 015 | BOQ | 340000000 | NCB | Immigration Service Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 9th Mar - 20th April 2011 |  | 01/03/11 - 21/03/11 | 22/03/11 - 04/04/11 | 05/04/11 - 18/04/11 | 27/04/11 - '01/06/11 | 01/06/11 - '01/06/11 | 09/06/11 - 30/06/11 | 04/07/11 - 11/07/11 | 340000000 |  | 18/07/11 - 25/07/11 | 26/07/11 - 11/08/11 | 12/08/11 -26/08/11 | 01/09/11 | 31/12/11 | Budgetary Provision | " | " | " | "
Purchase / Acquisition of Land |  |  |  | 16499990 | DP | [19 empty] | " | " | " | "
Construction / Provision of Water Facilities | NIS/PCM/11 | 017 | BOQ | 61731750 | NCB | Immigration Service Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 9th Mar - 20th April 2011 |  | 01/03/11 - 21/03/11 | 22/03/11 - 04/04/11 | 05/04/11 - 18/04/11 | 27/04/11 - '01/06/11 | 01/06/11 - '01/06/11 | 09/06/11 - 30/06/11 | 04/07/11 - 11/07/11 | 61731750 |  | 18/07/11 - 25/07/11 | 26/07/11 - 11/08/11 | 12/08/11 -26/08/11 | 01/09/11 | 31/12/11 | Budgetary Provision | " | " | " | "
Construction / Provision of Police Stations / Barracks | NIS/PCM/11 | 018 | BOQ | 483365326 | NCB | Immigration Service Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 9th Mar - 20th April 2011 |  | 01/03/11 - 21/03/11 | 22/03/11 - 04/04/11 | 05/04/11 - 18/04/11 | 27/04/11 - '01/06/11 | 01/06/11 - '01/06/11 | 09/06/11 - 30/06/11 | 04/07/11 - 11/07/11 | 483365326 |  | 18/07/11 - 25/07/11 | 26/07/11 - 11/08/11 | 12/08/11 -26/08/11 | 01/09/11 | 31/12/11 | Budgetary Provision | " | " | " | "
Construction / Provision of Libraries | NIS/PCM/11 | 019 | BOQ | 20038450 | NCB | Immigration Service Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 9th Mar - 20th April 2011 |  | 01/03/11 - 21/03/11 | 22/03/11 - 04/04/11 | 05/04/11 - 18/04/11 | 27/04/11 - '01/06/11 | 01/06/11 - '01/06/11 | 09/06/11 - 30/06/11 | 04/07/11 - 11/07/11 | 20038450 |  | 18/07/11 - 25/07/11 | 26/07/11 - 11/08/11 | 12/08/11 -26/08/11 | 01/09/11 | 31/12/11 | Budgetary Provision | " | " | " | "
Construction / Provision of Infrastructure | NIS/PCM/11 | 020 | BOQ | 76769200 | NCB | Immigration Service Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 9th Mar - 20th April 2011 |  | 01/03/11 - 21/03/11 | 22/03/11 - 04/04/11 | 05/04/11 - 18/04/11 | 27/04/11 - '01/06/11 | 01/06/11 - '01/06/11 | 09/06/11 - 30/06/11 | 04/07/11 - 11/07/11 | 76769200 |  | 18/07/11 - 25/07/11 | 26/07/11 - 11/08/11 | 12/08/11 -26/08/11 | 01/09/11 | 31/12/11 | Budgetary Provision | " | " | " | "
Rehabilitation / Repairs - Police Stations / Barracks | NIS/PCM/11 | 021 | BOQ | 100000000 | NCB | Immigration Service Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | 9th Mar - 20th April 2011 |  | 01/03/11 - 21/03/11 | 22/03/11 - 04/04/11 | 05/04/11 - 18/04/11 | 27/04/11 - '01/06/11 | 01/06/11 - '01/06/11 | 09/06/11 - 30/06/11 | 04/07/11 - 11/07/11 | 100000000 |  | 18/07/11 - 25/07/11 | 26/07/11 - 11/08/11 | 12/08/11 -26/08/11 | 01/09/11 | 31/12/11 | Budgetary Provision | H. M. Maishanu | CIS | I. D. Musa | CII
Total Cost Plan |  |  |  | 1178404716 | [12 empty] | 1161904726
Total Cost Actual

## INTERIOR
Ministry/Department/Agency: INTERIOR
Budgetary Year: 2011 -- Consultancy Services | [7 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: 08059691856 |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  | Consultancy Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [6 empty] | Contract Finalization |  |  | Contract Implementation
Project Description* CONSULTING AND PROFESSIONAL SERVICES - GENERAL | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/ Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | No-objection Date | FEC Approval | Contract Amount in Naira | Contract Offer | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks |  | 1- 2 wk | 2 wks
List of Contracts
Information Technology Consultancy | NCB | Lump Sum | 10301182 | MTB | 01.02.11-16.02.11 | 02.03.11-16.03.11 | 23.03.11-06.04.11 | 13.04.11 | 20.04.11 | 04.05.11 | 18.05.11 | 15.06.11 | 29.06,11 | 13.07.11 | 27.07.11 | 10.08.11 |  |  |  | 10301180 | 17.08.11 | 24.08.11 |  | 07.09.11 | 21.09.11 |  | Ofoegbu N. G. | F. O. Alaiyegbami
Legal Services | NCB | Lump Sum | 19342094 | MTB | 01.02.11-16.02.11 | 02.03.11-16.03.11 | 23.03.11-06.04.11 | 13.04.11 | 20.04.11 | 04.05.11 | 18.05.11 | 15.06.11 | 29.06,11 | 13.07.11 | 27.07.11 | 10.08.11 |  |  |  | 19342094 | 17.08.11 | 24.08.11 |  | 07.09.11 | 21.09.11 |  | Ofoegbu N. G. | F. O. Alaiyegbami
Total Cost |  |  | 29643276 | [16 empty] | 29643276
Budgetary Year: 2011 -- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN
Desk Officer/Contact #: 08059691856 |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
add 2 wks
List of Contracts
Office Stationaries/Computer Consumables | GDS.001 | Lot 1 | 61370861 | NCB | N/A | MTB | 1/02/11 | 2/03/11- 16/03/11 | N/A | 23/03/11- 6/03/11 | 6/05/11 | 20/05/11 | 10/06/11-24/06/11 | 61370861 | N/A | 24/06/11 | 30/06/11 | N/A | 14/07/11 | 31/07/11 | AFORKA, E.C. | ALAIYEGBAMI, F.O.
Books | GDS.001 | Lot 2 | 5186576 | NCB | N/A | MTB | 1/02/11 | 2/03/11- 16/03/11 | N/A | 23/03/11- 6/03/11 | 6/05/11 | 20/05/11 | 10/06/11-24/06/11 | 5186576 | N/A | 24/06/11 | 30/06/11 | N/A | 14/07/11 | 31/07/11 | AFORKA, E.C. | ALAIYEGBAMI, F.O.
News Papers | GDS.001 | Lot 3 | 2000000 | NCB | N/A | MTB | 1/02/11 | 2/03/11- 16/03/11 | N/A | 23/03/11- 6/03/11 | 6/05/11 | 20/05/11 | 10/06/11-24/06/11 | 2000000 | N/A | 24/06/11 | 30/06/11 | N/A | 14/07/11 | 31/07/11 | AFORKA, E.C. | ALAIYEGBAMI, F.O.
Magazines and Periodicals | GDS.001 | Lot 4 | 10318967 | NCB | N/A | MTB | 1/02/11 | 2/03/11- 16/03/11 | N/A | 23/03/11- 6/03/11 | 6/05/11 | 20/05/11 | 10/06/11-24/06/11 | 10318967 | N/A | 24/06/11 | 30/06/11 | N/A | 14/07/11 | 31/07/11 | AFORKA, E.C. | ALAIYEGBAMI, F.O.
Printing of Non Security Documents | GDS.001 | Lot 5 | 11750296 | NCB | N/A | MTB | 1/02/11 | 2/03/11- 16/03/11 | N/A | 23/03/11- 6/03/11 | 6/05/11 | 20/05/11 | 10/06/11-24/06/11 | 11750296 | N/A | 24/06/11 | 30/06/11 | N/A | 14/07/11 | 31/07/11 | AFORKA, E.C. | ALAIYEGBAMI, F.O.
Printing of Security Documents | GDS.001 | Lot 6 | 3527242 | NCB | N/A | MTB | 1/02/11 | 2/03/11- 16/03/11 | N/A | 23/03/11- 6/03/11 | 6/05/11 | 20/05/11 | 10/06/11-24/06/11 | 3527242 | N/A | 24/06/11 | 30/06/11 | N/A | 14/07/11 | 31/07/11 | AFORKA, E.C. | ALAIYEGBAMI, F.O.
Drugs and Medical Supplies | GDS.001 | Lot 7 | 5706765 | NCB | N/A | MTB | 1/02/11 | 2/03/11- 16/03/11 | N/A | 23/03/11- 6/03/11 | 6/05/11 | 20/05/11 | 10/06/11-24/06/11 | 5706765 | N/A | 24/06/11 | 30/06/11 | N/A | 14/07/11 | 31/07/11 | AFORKA, E.C. | ALAIYEGBAMI, F.O.
Computer Consumables | GDS.001 | Lot 8 | 50000000 | NCB | N/A | MTB | 1/02/11 | 2/03/11- 16/03/11 | N/A | 23/03/11- 6/03/11 | 6/05/11 | 20/05/11 | 10/06/11-24/06/11 | 50000000 | N/A | 24/06/11 | 30/06/11 | N/A | 14/07/11 | 31/07/11 | AFORKA, E.C. | ALAIYEGBAMI, F.O.
Motor Vehicle Fuel Cost | GDS.002 | Lot 1 | 9298193 | NCB | N/A | MTB | 1/02/11 | 2/03/11- 16/03/11 | N/A | 23/03/11- 6/03/11 | 6/05/11 | 20/05/11 | 10/06/11-24/06/11 | 9298193 | N/A | 24/06/11 | 30/06/11 | N/A | 14/07/11 | 31/07/11 | AFORKA, E.C. | ALAIYEGBAMI, F.O.
Plants/Generator Fuel Cost | GDS.002 | Lot 2 | 25242819 | NCB | N/A | MTB | 1/02/11 | 2/03/11- 16/03/11 | N/A | 23/03/11- 6/03/11 | 6/05/11 | 20/05/11 | 10/06/11-24/06/11 | 25242819 | N/A | 24/06/11 | 30/06/11 | N/A | 14/07/11 | 31/07/11 | AFORKA, E.C. | ALAIYEGBAMI, F.O.
Other Transport Equipment Fuel Cost | GDS.002 | Lot 3 | 2518570 | NCB | N/A | MTB | 1/02/11 | 2/03/11- 16/03/11 | N/A | 23/03/11- 6/03/11 | 6/05/11 | 20/05/11 | 10/06/11-24/06/11 | 2518570 | N/A | 24/06/11 | 30/06/11 | N/A | 14/07/11 | 31/07/11 | AFORKA, E.C. | ALAIYEGBAMI, F.O.
Purchase of Computers | GDS.003 | Lot 1 | 30000000 | NCB | N/A | MTB | 1/02/11 | 2/03/11- 16/03/11 | N/A | 23/03/11- 6/03/11 | 6/05/11 | 20/05/11 | 10/06/11-24/06/11 | 30000000 | N/A | 24/06/11 | 30/06/11 | N/A | 14/07/11 | 31/07/11 | AFORKA, E.C. | ALAIYEGBAMI, F.O.
Purchase of Library Books and Equipment | GDS.003 | Lot 2 | 15000000 | NCB | N/A | MTB | 1/02/11 | 2/03/11- 16/03/11 | N/A | 23/03/11- 6/03/11 | 6/05/11 | 20/05/11 | 10/06/11-24/06/11 | 15000000 | N/A | 24/06/11 | 30/06/11 | N/A | 14/07/11 | 31/07/11 | AFORKA, E.C. | ALAIYEGBAMI, F.O.
Purchase of Health/Medical Equipment | GDS.003 | Lot 3 | 10000000 | NCB | N/A | MTB | 1/02/11 | 2/03/11- 16/03/11 | N/A | 23/03/11- 6/03/11 | 6/05/11 | 20/05/11 | 10/06/11-24/06/11 | 10000000 | N/A | 24/06/11 | 30/06/11 | N/A | 14/07/11 | 31/07/11 | AFORKA, E.C. | ALAIYEGBAMI, F.O.
Total Cost |  |  | 55000000 | [10 empty] | 55000000
Fill gray cells only!
Budgetary Year: 2011 -- Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN
Desk Officer/Contact #: 08059691856 |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description*REHABILITATION/ REPAIRS OF FIXED ASSET GENERAL | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
add 2 wks
List of Contracts
Rehabilitation of Block A | WKS.002 | 2A | BOQ | NCB | 140m | N/A | MTB | 01.02.11-16.02.11 | 02.03.11-16.03.11 | N/A | 23.03.11-06.05.11 | 06.05.11 | 20.05.11 | 03.06.11 | 140m | N/A | 17.06.11 | 24.06.11 |  | 23.11.11 | 23.12.11 |  | Arc. S. A. Ejembi | Mr. F.O. Alaiyegbami
Rehabilitation of Annex | WKS.002 | 2B | BOQ | NCB | 25m | N/A | MTB | 01.02.11-16.02.11 | 02.03.11-16.03.11 | N/A | 23.03.11-06.05.11 | 06.05.11 | 20.05.11 | 03.06.11 | 25m | N/A | 17.06.11 | 24.06.11 |  | 23.11.11 | 23.12.11 |  | Arc. S. A. Ejembi | Mr. F. Alaiyegbami
Furnishing of Annex | WKS.002 | 2C | BOQ | NCB | 35m | N/A | MTB | 01.02.11-16.02.11 | 02.03.11-16.03.11 | N/A | 23.03.11-06.05.11 | 06.05.11 | 20.05.11 | 03.06.11 | 35m | N/A | 17.06.11 | 24.06.11 |  | 23.11.11 | 23.12.11 |  | Arc. S. A. Ejembi | Mr. F. Alaiyegbami
Rehabilitation of Warehouse/Store | WKS.001 | 1A | BOQ | NCB | 15m | N/A | MTB | 01.02.11-16.02.11 | 02.03.11-16.03.11 | N/A | 23.03.11-06.05.11 | 06.05.11 | 20.05.11 | 03.06.11 | 15m | N/A | 17.06.11 | 24.06.11 |  | 23.11.11 | 23.12.11 |  | Arc. S. A. Ejembi | Mr. F. O. Alaiyegbami
Rehabilitation of Mechanical Workshop | WKS.001 | 1B | BOQ | NCB | 15m | N/A | MTB | 01.02.11-16.02.11 | 02.03.11-16.03.11 | N/A | 23.03.11-06.05.11 | 06.05.11 | 20.05.11 | 03.06.11 | 15m | N/A | 17.06.11 | 24.06.11 |  | 23.11.11 | 23.12.11 |  | Arc. S. A. Ejembi | Mr. F. O. Alaiyegbami
Procurement of 250KVA Generator | WKS.001 | 1C | BOQ | NCB | 10m | N/A | MTB | 01.02.11-16.02.11 | 02.03.11-16.03.11 | N/A | 23.03.11-06.05.11 | 06.05.11 | 20.05.11 | 03.06.11 | 10m | N/A | 17.06.11 | 24.06.11 |  | 23.11.11 | 23.12.11 |  | Arc. S. A. Ejembi | Mr. F. O. Alaiyegbami
External Works | WKS.001 | 1D | BOQ | NCB | 5m | N/A | MTB | 01.02.11-16.02.11 | 02.03.11-16.03.11 | N/A | 23.03.11-06.05.11 | 06.05.11 | 20.05.11 | 03.06.11 | 5m | N/A | 17.06.11 | 24.06.11 |  | 23.11.11 | 23.12.11 |  | Arc. S. A. Ejembi | Mr. F. O. Alaiyegbami
0 | WKS.003 | Lot 1 | BOQ | NCB | 7369517 | N/A | MTB | 01/02/11-16/02/11 | 20/03/11-16/03/11 | N/A | 23/03/11-6/05/11 | 06/05/11 | 20/05/11 | 03/06/11 | 7369517 | N/A | 17/06/11 | 24/06/11 |  | 23/11/11 | 23/12/11 |  | Arc. S.A. EJEMBI | Mr. F.O. ALAIYEGBAMI
Maintenance of Office Building/Residential Qtrs | WKS.003 | Lot 2 | BOQ | NCB | 27357460 | N/A | MTB | 01/02/11-16/02/11 | 20/03/11-16/03/11 | N/A | 23/03/11-6/05/11 | 06/05/11 | 20/05/11 | 03/06/11 | 27357460 | N/A | 17/06/11 | 24/06/11 |  | 23/11/11 | 23/12/11 |  | Arc. S.A. EJEMBI | Mr. F.O. ALAIYEGBAMI
Maintenance of Office Furniture | WKS.003 | Lot 3 | BOQ | NCB | 7804248 | N/A | MTB | 01/02/11-16/02/11 | 20/03/11-16/03/11 | N/A | 23/03/11-6/05/11 | 06/05/11 | 20/05/11 | 03/06/11 | 7804248 | N/A | 17/06/11 | 24/06/11 |  | 23/11/11 | 23/12/11 |  | Arc. S.A. EJEMBI | Mr. F.O. ALAIYEGBAMI
Maintenance of Office/IT Equipments | WKS.003 | Lot 4 | BOQ | NCB | 16413099 | N/A | MTB | 01/02/11-16/02/11 | 20/03/11-16/03/11 | N/A | 23/03/11-6/05/11 | 06/05/11 | 20/05/11 | 03/06/11 | 16413099 | N/A | 17/06/11 | 24/06/11 |  | 23/11/11 | 23/12/11 |  | Arc. S.A. EJEMBI | Mr. F.O. ALAIYEGBAMI
Other Maintenance Services-I | WKS.003 | Lot5 | BOQ | NCB | 54018450 | N/A | MTB | 01/02/11-16/02/11 | 20/03/11-16/03/11 | N/A | 23/03/11-6/05/11 | 06/05/11 | 20/05/11 | 03/06/11 | 54018450 | N/A | 17/06/11 | 24/06/11 |  | 23/11/11 | 23/12/11 |  | Arc. S.A. EJEMBI | Mr. F.O. ALAIYEGBAMI
Other Maintenance Services II | WKS.003 | Lot 6 | BOQ | NCB | 60000000 | N/A | MTB | 01/02/11-16/02/11 | 20/03/11-16/03/11 | N/A | 23/03/11-6/05/11 | 06/05/11 | 20/05/11 | 03/06/11 | 60000000 | N/A | 17/06/11 | 24/06/11 |  | 23/11/11 | 23/12/11 |  | Arc. S.A. EJEMBI | Mr. F.O. ALAIGBAMI
Total Cost |  |  |  |  | 172962774 | [9 empty] | 172962774 | [6 empty] | #REF!
Fill gray cells only!

## Prison Serv
Ministry/Department/Agency: Nigerian Prison Service
Budget Year: 2011 -- Goods
| Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Goods |  |  | Action Party |  | Champion
Project Description | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pro-Qualification | Bid Invitation Date | Bid Closing /Opening | Submission of Bid Evaluation Report | MDA Approval /BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization /Advance Payment | Arrival of Goods | Inspection /Final Acceptance | Final Cost | Name | Designation | Name | Designation
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks | 1 weeks | 2 weeks
Purchase of Finger Prints/OCR Scanner/Biometrics | NPS/OPS/6/11 | Goods 1 | LUMP SUM | 14508354.29 | NCB | PTB | LERB | PST |  | 10/1/11 to 24/1/11 | 26/1/11 to 9/2/11 | 15/2/11 to 1/3/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/5/11 to 25/5/11 | 14508354.29 |  | 26/5/11 to 2/6/11 | 6/6/11 to 20/6/11 | NA | 18/7/11 | 2011-07-19 | 14508354.29 | Mr. Ayo | NA | Mr. Ayo | NA
Procurement of Kitchen and Cooking utensils/equipment | NPS/MSW/1/11 | Goods 1 | LUMP SUM | 32616599.97 | NCB | PTB | LERB | PST |  | 10/1/11 to 24/1/11 | 26/1/11 to 9/2/11 | 15/2/11 to 1/3/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/5/11 to 25/5/11 | 32616599.97 |  | 26/5/11 to 2/6/11 | 6/6/11 to 20/6/11 | NA | 18/7/11 | 2011-07-19 | 32616599.97 | Mr. Ayo | NA | Mr. Ayo | NA
Purchase of HIV/AIDS Control Programme | NPS/MSW/2/11 | Goods 2 | LUMP SUM | 11827564.62 | NCB | PTB | LERB | PST |  | 10/1/11 to 24/1/11 | 26/1/11 to 9/2/11 | 15/2/11 to 1/3/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/5/11 to 25/5/11 | 11827564.62 |  | 26/5/11 to 2/6/11 | 6/6/11 to 20/6/11 | NA | 18/7/11 | 2011-07-19 | 11827564.62 | Mr. Ayo | NA | Mr. Ayo | NA
procurement of Medical Equipment for Maintenance of Prison Clinics and Hospitals | NPS/MSW/3/11 | Goods 3 | LUMP SUM | 120709983.29 | NCB | PTB | LERB | PST |  | 10/1/11 to 24/1/11 | 26/1/11 to 9/2/11 | 15/2/11 to 1/3/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/5/11 to 25/5/11 | 120709983.29 |  | 26/5/11 to 2/6/11 | 6/6/11 to 20/6/11 | NA | 18/7/11 | 2011-07-19 | 120709983.29 | Mr. Ayo | NA | Mr. Ayo | NA
Procurement of fire prevention equipment | NPS/OPS/07/11 | GOODS | LUMP SUM | 10260334.25 | NCB | PTB | LERB | PST |  | 10/1/11 to 24/1/11 | 26/1/11 to 9/2/11 | 15/2/11 to 1/3/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/5/11 to 25/5/11 | 10260334.25 | NA | 26/5/11 to 2/6/11 | 6/6/11 to 20/6/11 | NA | 18/7/11 | 2011-07-19 | 10260334.25 | Mr. Ayo | NA | MR AYO | NA
Provision education facilities in Prison | NPS/OPS/08/11 | GOOGS5 | LUMP SUM | 15380024.58 | NCB | PTB | LERB | PST |  | 10/1/11 to 24/1/11 | 26/1/11 to 9/2/11 | 15/2/11 to 1/3/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/5/11 to 25/5/11 | 15380024.58 | NA | 26/5/11 to 2/6/11 | 6/6/11 to 20/6/11 | NA | 18/7/11 | 2011-07-19 | 15380024.58 | Mr. Ayo | NA | MR AYO | NA
Communication Equipment | NPS/OPS/10 | GOODS | LUMP SUM | 53129339.26 | NCB | PTB | LERB | PST |  |  | 26/1/11 to 9/2/11 | 15/2/11 to 1/3/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/5/11 to 25/5/11 | 53129339.26 |  | 26/5/11 to 2/6/11 | 6/6/11 to 20/6/11 | NA | 18/7/11 | 2011-07-19 | 53129339.26 | Mr. Ayo | NA | MR AYO | NA
Library Services Development | NPS/OPS/011/11 | GOODS | LUMP SUM | 18088604.23 | NCB | PTB | LERB | PST |  | 10/1/11 to 24/1/11 | 26/1/11 to 9/2/11 | 15/2/11 to 1/3/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/5/11 to 25/5/11 | 18088604.23 |  | 26/5/11 to 2/6/11 | 6/6/11 to 20/6/11 | NA | 18/7/11 | 2011-07-19 | 18088604.23 | Mr. Ayo | NA | MR AYO | NA
Law Books,journal of court vehicles | NPS/L/02/11/11 | GOOGDS | LUMP SUM | 10292835.17 | NCB | PTB | LERB | PST |  | 10/1/11 to 24/1/11 | 26/1/11 to 9/2/11 | 15/2/11 to 1/3/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/5/11 to 25/5/11 | 10292835.17 |  | 26/5/11 to 2/6/11 | 6/6/11 to 20/6/11 | NA | 18/7/11 | 2011-07-19 | 10292835.17 | Mr. Ayo | NA | MR AYO | NA
[7 empty] | LERB | PST |  |  |  |  | 14/3/11 | 13/04/2011 | [10 empty] | Mr. Ayo | NA | MR AYO | NA
PROVISION OF SPORTING FACILITIES AND EQUIPMENT | NPS/MSW/4/11 | GOODS | LUMP SUM | 20784118.04 | NCB | PTB | LERB | PST |  | 10/01/11 to 24/01/11 | 26/01/11 to 9/02/11 | 15/02/11 to 1/03/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/11 to 25/05/11 | 20784118.04 | GOODS | 26/05/11 to 02/06/11 | 06/06/11 to 24/06/11 | 22/06/11 to 05/07/11 | 18/7/11 | 2011-07-19 | 20784118.04 | Mr. Ayo | NA | Mr. Ayo | NA
JAMMING DEVICE FOR GSM/METAL DETECTOR AND DOOR METAL DETECTORS | NPS/OPS/12/2011 | GOODS | LUMP SUM | 3060441.48 | NCB | PTB | LERB | PST |  | 10/01/11 to 24/01/11 | 26/01/11 to 9/02/11 | 15/02/11 to 1/03/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/11 to 25/05/11 | 3060441.48 | NA | 26/05/11 to 02/06/11 | 26/05/11 to 02/06/11 | 26/05/11 to 02/06/11 | 18/7/11 | 2011-09-13 | 3060441.48 | MR AYO | NA | MR AYO | NA
PROVISION OF FIELD MATERIAL OF SUPPLIES | NPS/OPS/1/2011 | GOODS | LUMP SUM | 38439585.02 | NCB | PTB | LERB | PST |  | 10/01/11 to 24/01/11 | 26/01/11 to 09/02/11 | 15/02/11 to 01/03/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/11 to 25/05/11 | 38439585.02 | NIL | 26/05/11 to 02/06/11 | 06/06/11 to 24/06/11 | 22/06/11 to 05/07/11 | 18/7/11 | 2011-09-13 | 38439585.02 | Mr. Ayo | NA | Mr. Ayo | NA
SECURITY/ARMED SQUAD EQUIPMENT | NPS/OPS/2/2011 | GOODS | LUMP SUM | 87872689.22 | NCB | PTB | LERB | PST |  | 10/01/11 to24/01/11 | 26/01/11 to 09/02/11 | 15/02/11 to 01/03/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/5/11-25/5/11 | 87872689.22 | NIL | 26/05/11 to 02/06/11 | 6/6/11-24/6/11 | 22/06/11 to 05/07/11 | 18/7/11 | 2011-09-13 | 87872689.22 | Mr. Ayo | NA | Mr. Ayo | NA
PROVISION OF CCTV FOR SECURITY MONITORING IN PRISON YARDS | NPS. / / / | GOODS | LUMP SUM | 151571267.87 | NCB | PTB | LERB | PST |  | 10/1/11-24/1/11 | 26/01/11 to 09/02/11 | 15/02/11 to 01/03/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/11to 25/05/11 | 151571267.87 | NA | 26/5/11 to 2/6/11 | 6/6/11-24/6/11 | NA | 2011-07-18 | 2011-09-13 | 151571267.87 | Mr. Ayo | NA | Mr. Ayo | NA
BLACK MARIA | NPS/WL/2/11 | GOODS 3 | LUMP SUM | 124970491.33 | NCB | PTB | LERB | PST |  | 10/1/11-24/1/11 | 26/1/11-9/2/11 | 15/2/11-1/3/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/5/11-25/5/11 | 124970491.33 | NA- | 26/5/11-2/6/11 | 6/6/11-20/6/11 | NA | 18/7/11 | 2011-07-19 | 124970491.33 | MR AYO | NA | MR AYO | NA
AMBULANCE PROJECT | NPS/WL/3/11 | GOODS 4 | LUMP SUM | 20100781.37 | NCB | PTB | LERB | PST |  | 10/1/11-24/1/11 | 26/1/11-9/2/11 | 15/2/11-1/3/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/5/11-25/5/11 | 20100781.37 | NA | 26/5/11-2/6/11 | 6/6/11-20/6/11 | NA | 18/7/11 | 2011-07-19 | 20100781.37 | MR AYO | NA | MR AYO | NA
PURCHASE OF HEAVY DUTY VEHICLES AND TRUCKS FOR CONVEYING GOODS | NPS/WL/4/11 | GOOGS5 | LUMP SUM | 24989664.02 | NCB | PTB | LERB | PST |  | 10/1/11-24/1/11 | 26/1/11-9/2/11 | 15/2/11-1/3/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/5/11-25/5/11 | 24989664.02 | NA | 26/5/11-2/6/11 | 6/6/11-20/6/11 | NA | 18/7/11 | 2011-07-19 | 24989664.02 | MR AYO | NA | MR AYO | NA
[14 empty] | 13/04/2011 | 18/4/11-9/5/11 | [5 empty] | NA |  | 2011-07-19
PROVISION OFWATER TANKER AND SEWAGE TRUCKS | NPS/WL/5/2011 | GOODS6 | BOQ | 45187292.75 | NCB | PTB | LERB | PST |  | 10/1/11-24/1/11 | 26/1/11-9/2/11 | 15/2/11-1/3/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/5/11-25/5/11 | 45187292.75 | NA | 26/5/11-2/6/11 | 6/6/11-20/6/11 | NA | 18/7/11 | 2011-07-19 | 45187292.75 | MR AYO | NA | MR AYO | NA
[7 empty] | LERB | [6 empty] | 13/04/2011 | 18/4/11-9/5/11 | [5 empty] | NA |  | 2011-07-19
PURCHASE OF 1 NO.MB 1711 TRUCK MOBILE WORKSHOP | NPS/WL/6/11 | GOODS 7 | LUMP SUM | 12874984.18 | NCB | PTB | LERB | PST |  | 10/1/11-24/1/11 | 26/1/11-9/2/11 | 15/2/11-1/3/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/5/11-25/5/11 | 12874984.18 | NA | 26/5/11-2/6/11 | 6/6/11-20/6/11 | NA | 18/7/11 | 2011-07-19 | 12874984.18 | MR AYO | NA | MR AYO | NA
Budget Year: 2011 -- Works
| Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Works |  |  |  | Action Party |  | Champion
Project Description | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pro-Qualification | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Name | Designation | Name | Designation
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 1 weeks
PAYMENT OF COMPENSATION OF PROCESSING FEES FOR PRISONS LANDS | NPS/WL/1/2011 | WORKS 1 | LUMP SUM | 9597508.74 | NCB | PTB |  | PST |  | 10/1/11-24/1/11 | 26/1/11-9/2/11 | 15/2/11-1/3/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/5/11-25/5/11 | 9597508.74 | NA | 26/5/11-2/6/11 | 6/6/11-20/6/11 | 22/6/11-5/7/11 | 2011-09-12 | 2011-09-13 | 9597508.74 | MR AYO | NA | MR AYO | NA
KENNEL UNIT | NPS/OPS/4/2011 | WORKS | BOQ | 24522608.96 | NCB | PTB | LERB | PST |  | 10/1/11-24/1/11 | 26/01/11 to 09/02/11 | 15/02/11 to 01/03/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/11to 25/05/11 | 24522608.96 | NA | 26/5/11 to 2/6/11 | 6/6/11-24/6/11 | 22/6/11-5/7/11 | 2011-07-18 | 2011-09-13 | 24522608.96 | MR AYO | NA | MR AYO | NA
COMPLETION OF PRISONS HEADQUARTER, ABUJA AND HOUSING UNIT FOR CGP AND OTHERS SENIOR OFFICERS (ON GOING) | NPS/WL/11/2011 | WORKS | BOQ | 425523182.49 | NCB | PTB (ON GOING) | LERB | PST |  | 10/01/11 to 24/01/11 | 26/01/11 to 09/02/11 | 15/02/11 to 01/03/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/11to 25/05/11 | 425523182.49 | NA | 26/05/11 to 02/06/11 | 06/06/11 to 24/06/11 | 22/06/11 to 05/07/11 | 2011-09-12 | 2011-09-13 | 425523182.49 | Mr. Ayo | NA | Mr. Ayo | NA
CONSTRUCTION OF PHQ AT 37 STATES | NPS/WL/11/2011 | WORKS | BOQ | 26846012.21 | NCB | PTB | LERB | PST |  | 10/01/11 to 24/01/11 | 26/01/11 to 09/02/11 | 15/02/11 to 01/03/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/11 to 25/05/11 | 26846012.21 | NIL | 26/05/11 to 02/06/11 | 06/06/11 to 24/06/11 | 22/06/11 to 05/07/11 | 2011-09-12 | 2011-09-13 | 26846012.21 | Mr. Ayo | NA | Mr. Ayo | NA
CONSTRUCTION OF PRISONS VILLAGE ABUJA (ON GOING) | NPS/WL/11/2011 | W0RKS 5 | BOQ | 423110952.45 | NCB | PTB (ON GOING) | LOWEST COMP.BID | PST |  | 10/01/2011-24/01/2011 | 26/01/2011-09/02/2011 | 15/02/2011-01/03/2011 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/2011-25/05/2011 | 423110952.45 | N.A. | 26/05/2011-02/06/2011 | 06/06/2011-20/06/2011 | 22/06/2011-05/07/2011 | 2011-09-12 | 2011-09-13 | 423110952.45 | MR AYO | N.A | MR AYO | N.A.
PURCHASE OF SOLAR POWER ALTERNATIVES FOR PRISON YARDS | NPS/OPS/5/2011 | WORKS6 | BOQ | 177709823.75 | NCB | PTB | LOWEST COMP.BID | PST |  | 10/01/2011-24/01/2011 | 26/01/2011-09/02/2011 | 15/02/2011-01/03/2011 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/2011-25/05/2011 | 177709823.75 | N.A. | 26/05/2011-02/06/2011 | 06/06/2011-20/06/2011 | 22/06/2011-05/07/2011 | 2011-09-12 | 2011-09-13 | 177709823.75 | MR AYO | N.A | MR AYO | N.A.
PROVISION OF POTABLE WATER AND BOREHOLE IN PRISONS | NPS/WL/12/2011 | WORKS 7 | BOQ | 84413387.85 | NCB | PTB | LOWEST COMP.BID | PST |  | 10/01/2011-24/01/2011 | 26/01/2011-09/02/2011 | 15/02/2011-01/03/2011 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/2011-25/05/2011 | 84413387.85 | N.A. | 26/05/2011-02/06/2011 | 06/06/2011-20/06/2011 | 22/06/2011-05/07/2011 | 2011-09-12 | 2011-09-13 | 84413387.85 | MR AYO | N.A. | MR AYO | N.A.
CONSTRUCTION OF BORSTAL INSTITUTION AT OGBIA BAYELSA STATE | NPS/WL/13/2011 | WORKS | BOQ | 130694589.08 | NCB | PTB | LOWEST COMP. BID | PST |  | 10/01/11 TO 24/01/11 | 26/01/11 TO 09/02/11 | 15/02/11 TO 01/03/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/11 TO 25/05/11 | 130694589.08 | NA | 26/05/11 TO 02/06/11 | 06/06/11 TO 24/06/11 | 22/06/11 TO 05/07/11 | 2011-09-12 | 2011-09-13 | 130694589.08 | AYO | N.A. | MR AYO | N.A.
COMPLITION OF PRISON STAFF COLLEGE AND PRISON ACADEMY IJEBU IGBO ON GOING) | NPS/WL/14/2011 | WORKS | BOQ | 361958888.58 | NCB | PTB (ON GOING) | LOWEST COMP. BID | PST |  | 10/01/11 TO 24/01/11 | 26/01/11 TO 09/02/11 | 15/02/11 TO 01/03/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/11 TO 25/05/11 | 361958888.58 | NA | 26/05/11 TO 02/06/11 | 06/06/11 TO 24/06/11 | 22/06/11 TO 05/07/11 | 2011-09-12 | 2011-09-13 | 361958888.58 | AYO | N.A. | MR AYO | N.A.
COMPLETION OF 12 UNCOMPLETED PRISONS (ON GOING) | NPS/WL/15/2011 | WORKS | BOQ | 298012788.47 | NCB | PTB (ON GOING) | LOWEST COMP. BID | PST |  | 10/01/11 TO 24/01/11 | 26/01/11 TO 09/02/11 | 15/02/11 TO 01/03/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/11 TO 25/05/11 | 298012788.47 | NA | 26/05/11 TO 02/06/11 | 06/06/11 TO 24/06/11 | 22/06/11 TO 05/07/11 | 2011-09-12 | 2011-09-13 | 298012788.47 | AYO | N.A. | MR AYO | N.A.
COMPLETION OF A NEW PRISON AND STATE HEADQUARTERS OFFICE AT YENEGOA AND OMUARAN ( ON GOING) | NPS/WL/16/2011 | WORKS | BOQ | 385026132.87 | NCB | PTB (ON GOING) | LOWEST COMP. BID | PST |  | 10/01/11 TO 24/01/11 | 26/01/11 TO 09/02/11 | 15/02/11 TO 01/03/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/11 TO 25/05/11 | 385026132.87 | NA | 26/05/11 TO 02/06/11 | 06/06/11 TO 24/06/11 | 22/06/11 TO 05/07/11 | 2011-09-12 | 2011-09-13 | 385026132.87 | AYO | N.A. | MR AYO | N.A.
COMPLETION OF 160 BED MSP AT ILORIN ( ON GOING) | NPS/WL/17/2011 | WORKS | BOQ | 47347219.63 | NCB | PTB | LOWEST COMP. BID | PST |  | 10/01/11 TO 24/01/11 | 26/01/11 TO 09/02/11 | 15/02/11 TO 01/03/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/11 TO 25/05/11 | 47347219.63 | NA | 26/05/11 TO 02/06/11 | 06/06/11 TO 24/06/11 | 22/06/11 TO 05/07/11 | 2011-09-12 | 2011-09-13 | 47347219.63 | AYO | N.A. | MR AYO | N.A.
RELOCATION ADO-EKITI PRISON | NPS/WL/18/2011 | WORKS | BOQ | 70418274.16 | NCB | PTB | LOWEST COMP. BID | PST |  | 10/01/11 TO 24/01/11 | 26/01/11 TO 09/02/11 | 15/02/11 TO 01/03/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/11 TO 25/05/11 | 70418274.16 | NA | 26/05/11 TO 02/06/11 | 06/06/11 TO 24/06/11 | 22/06/11 TO 05/07/11 | 2011-09-12 | 2011-09-13 | 70418274.16 | AYO | N.A. | MR AYO | N.A.
RELOCATION IKOYI PRISON TO EPE | NPS/WL/8/2011 | WORKS | BOQ | 6460895.88 | NCB | PTB | LOWEST COMP. BID | PST |  | 10/01/11 TO 24/01/11 | 26/01/11 TO 09/02/11 | 15/02/11 TO 01/03/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/11 TO 25/05/11 | 6460895.88 | NA | 26/05/11 TO 02/06/11 | 06/06/11 TO 24/06/11 | 22/06/11 TO 05/07/11 | 2011-09-12 | 2011-09-13 | 6460895.88 | AYO | N.A. | MR AYO | N.A.
CONSTRUCTION OF FARM CENTRE AGO-IWOYE | NPS/ITP/1/2011 | WORKS | BOQ | 147844557.78 | NCB | PTB | LOWEST COMP. BID | PST |  | 10/01/11 TO 24/01/11 | 26/01/11 TO 09/02/11 | 15/02/11 TO 01/03/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/11 TO 25/05/11 | 147844557.78 | NA | 26/05/11 TO 02/06/11 | 06/06/11 TO 24/06/11 | 22/06/11 TO 05/07/11 | 2011-09-12 | 2011-09-13 | 147844557.78 | AYO | N.A. | MR AYO | N.A.
PROVISION OF SPORTING STRUCTURAL FACILITIES AT PRISON VILLAGE | NPS/H/WS/5/2011 | WORKS | BOQ | 15258444.84 | NCB | PTB | LOWEST COMP. BID | PST |  | 10/01/11 TO 24/01/11 | 26/01/11 TO 09/02/11 | 15/02/11 TO 01/03/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/11 TO 25/05/11 | 15258444.84 | NA | 26/05/11 TO 02/06/11 | 06/06/11 TO 24/06/11 | 22/06/11 TO 05/07/11 | 2011-09-12 | 2011-09-13 | 15258444.84 | AYO | N.A. | MR AYO | N.A.
CONSTRUCTION OF SHOOTING RANGE AT KADUNA, OWERRI AND FCT | NPS/OPS/12/11 | WORKS | BOQ | 38144569.49 | NCB | PTB | LERB | PST |  | 10/10/2011 TO 24/10/2011 | 26/01/2011 TO 09/02/2011 | 15/02/2011 TO 01/03/2011 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/2011 TO 25/05/2011 | 38144569.49 | NA | 26/05/2011 TO 2/06/2011 | 6/06/2011 TO 24/06/2011 | 25/06/2011 TO 5/07/2011 | 2011-09-12 | 2011-09-13 | 38144569.49 | MR. AYO | NA | MR. AYO | NA
|  |  | BOQ |  |  | PTB | [7 empty] | 13/04/2011 | 18/4/11-9/5/11 |  |  | NA |  |  |  | 2011-09-12 | 2011-09-13
PRISON HOSPITAL DEVELOPMENT | NPS/MSW/6 | WORKS | BOQ | 95241444.02 | NCB | PTB | LERB | PST |  | 10/10/2011 TO 24/10/2011 | 26/01/2011 TO 09/02/2011 | 15/02/2011 TO 01/03/2011 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/2011 TO 25/05/2011 | 95241444.02 | NA | 26/05/2011 TO 2/06/2011 | 6/06/2011 TO 24/06/2011 | 25/06/2011 TO 5/07/2011 | 2011-09-12 | 2011-09-13 | 95241444.02 | MR. AYO | NA | MR. AYO | NA
|  |  | BOQ |  |  | PTB | [7 empty] | 13/04/2011 | 18/4/11-9/5/11 |  |  | NA |  |  |  | 2011-09-12 | 2011-09-13
REHABILITATION AND EQUIPING OF BORSTAL INSTITUTION ABEOKUTA, KADUNA AND ILORIN | NPS/ADMIN/1 | WORKS | BOQ | 19377180.14 | NCB | PTB | LERB | PST |  | 10/10/2011 TO 24/10/2011 | 26/01/2011 TO 09/02/2011 | 15/02/2011 TO 01/03/2011 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/2011 TO 25/05/2011 | 19377180.14 | NA | 26/05/2011 TO 2/06/2011 | 6/06/2011 TO 24/06/2011 | 25/06/2011 TO 5/07/2011 | 2011-09-12 | 2011-09-13 | 15213086.72 | MR. AYO | NA | MR. AYO | NA
|  |  | BOQ |  |  | PTB | [7 empty] | 13/04/2011 | 18/4/11-9/5/11 |  |  | NA |  |  |  | 2011-09-12 | 2011-09-13
IMPROVEMENT/DEVELOPMENT OF TRAINING INSTITUTIONS | NPS/ADMIN/2 | WORKS | BOQ | 98035807.28 | NCB | PTB | LERB | PST |  | 10/10/2011 TO 24/10/2011 | 26/01/2011 TO 09/02/2011 | 15/02/2011 TO 01/03/2011 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/2011 TO 25/05/2011 | 98035807.28 | NA | 26/05/2011 TO 2/06/2011 | 6/06/2011 TO 24/06/2011 | 25/06/2011 TO 5/07/2011 | 2011-09-12 | 2011-09-13 | 98035807.28 | MR. AYO | NA | MR. AYO | NA
REHABILITATION OF PRISONS AND STAFF BARRACKS NATIONWIDE | NPS/WL/9/2011 | WORKS | BOQ | 902021528.01 | NCB | PTB (ON GOING) | LCB | PST |  | 10/01/2011-24/01/2011 | 26/01/2011-09/02/2011 | 15/02/2011-01/03/2011 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/2011-25/05/2011 | 902021528.01 | N.A | 26/05/2011-02/06/2011 | 06/06/2011-20/06/2011 | 22/06/2011-05/07/2011 | 2011-09-12 | 2011-09-13 | 902021528.01 | MR AYO | N.A. | MR.AYO | N.A.
|  | WORKS | BOQ | [10 empty] | 13/04/2011 | 18/4/11-9/5/11 | [6 empty] | 2011-09-12 | 2011-09-13
COTTAGE PRINTING INDUSTRY LAGOS | NPS/ITP/2/2011 | WORKS | BOQ | 16064422.99 | NCB | PTB | LCB | PST |  | 10/01/2011-24/01/2011 | 26/01/2011-09/02/2011 | 15/02/2011-01/03/2011 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/2011-25/05/2011 | 16064422.99 | N.A | 26/05/2011-02/06/2011 | 06/06/2011-20/06/2011 | 22/06/2011-05/07/2011 | 2011-09-12 | 2011-09-13 | 16064422.99 | MR AYO | N.A. | MR AYO | N.A.
COTTAGE FURNITURE INDUSTRY ILESHA | NPS/ITP/3/2011 | WORKS | BOQ | 15156581.71 | NCB | PTB | LCB | PST |  | 10/01/2011-24/01/2011 | 26/01/2011-09/02/2011 | 15/02/2011-01/03/2011 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/2011-25/05/2011 | 15156581.71 | N.A. | 26/05/2011-02/06/2011 | 06/06/2011-20/06/2011 | 22/06/2011-05/07/2011 | 2011-09-12 | 2011-09-13 | 15156581.71 | MR AYO | N.A. | MR.AYO | N.A.
ESTABLISHMENT OF 10 NOS.PRISONS INDUSTRY AND RE-EQUIPING OF7 EXISTING INDUSTRIES | NPS/ITP/4/2011 | WORKS | BOQ | 59448296.68 | NCB | PTB | LCB | PST |  | 10/01/2011-24/01/2011 | 26/01/2011-09/02/2011 | 15/02/2011-01/03/2011 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/2011-25/05/2011 | 59448296.68 | N.A. | 26/05/2011-02/06/2011 | 06/06/2011-20/06/2011 | 22/06/2011-05/07/2011 | 2011-09-12 | 2011-09-13 | 59448296.68 | MR AYO | N.A. | MR.AYO | N.A.
PRISONS FARM CENTRES | NPS/ITP/5/2011 | WORKS | BOQ | 214106375.14 | NCB | PTB | LCB | PST |  | 10/01/2011-24/01/2011 | 26/01/2011-09/02/2011 | 15/02/2011-01/03/2011 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/2011-25/05/2011 | 214106375.14 | N.A. | 26/05/2011-02/06/2011 | 06/06/2011-20/06/2011 | 22/06/2011-05/07/2011 | 2011-09-12 | 2011-09-13 | 214106375.14 | MR AYO | N.A. | MR.AYO | N.A.
REHABILITATION OR MAIDUGURI PRISON ( ON GOING) | NPS/WL/10/2011 | WORKS | BOQ | 176822091.1 | NCB | PTB (ON GOING) | LCB | PST |  | 10/01/2011-24/01/2011 | 26/01/2011-09/02/2011 | 15/02/2011-01/03/2011 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/05/2011-25/05/2011 | 176822091.1 | N.A. | 26/05/2011-02/06/2011 | 06/06/2011-20/06/2011 | 22/06/2011-05/07/2011 | 2011-09-12 | 2011-09-13 | 176822091.1 | MR AYO | N.A. | MR.AYO | N.A.
RENOVATION OF CENTRAL SEWAGE SYSTEM AND CONVERSION OF BUCKET TO WATER SYSTEM | NPS/WL/11/2011 | WORKS | BOQ | 29639980.43 | NCB | PTB | LCB | PST |  | 10/01/2011-24/01/2011 | 26/01/2011-09/02/2011 | 15/02/2011-01/03/2011 | 14/3/11 | 13/04/2011 | 18/04/2011-09/05/2011 | 11/05/2011-25/05/2011 | 29639980.43 | N.A. | 26/05/2011-02/06/2011 | 06/06/2011-20/06/2011 | 22/06/2011-05/07/2011 | 2011-09-12 | 2011-09-13 | 29639980.43 | MR AYO | N.A. | MR.AYO | N.A.
Budget Year: 2011 -- Non-Consultancy
| Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party |  | Champion
Project Description | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization /Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name | Designation | Name | Designation
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 1 weeks | 2 - 4 weeks | 2 weeks | 2 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
PAYMENT OF JUDGMENT DEPT | NPS/LEGAL/1/11 | NON-CONSULTANCY SERVICE | TIME BASED | 22265468.46 | NCB | PTB | QUALTY AND COST BASE | PST |  | 10/1/11-24/1/11 | 26/1/11-9/2/11 | 15/2/11-1/3/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/5/11-25/5/11 | 22265468.48 | NA | 26/5/11-2/6/11 | 6/6/11-20/6/11 | NA | 18/7/11 | 2011-07-19 | 22265468.46 | MR AYO | NA | MR AYO | NA
RESEARCH AND PUBLICATION | NPS/OPS/14/2011 | NO CONSULTANCY SERVICES | LUMP SUM | 15213086.72 | NCB | PTB | LERB | PST |  | 10/10/2011 TO 24/10/2011 | 26/01/2011 TO 09/02/2011 | 15/02/2011 TO 01/03/2011 | 14/3/11 | 13/04/2011 | 18/04/2011 TO 9/05/2011 | 11/05/2011 TO 25/05/2011 | 15213086.72 | N.A. | 26/05/2011 TO 2/06/2011 | 6/06/2011 TO 24/06/2011 | NA | 2011-07-18 | 19/09/2011 | 38144569.49 | MR. AYO | NA | MR. AYO | NA
PROCUREMENT MANAGEMENT, MONITORING AND ASSESS SERVICES BY PROCUREMENT UNIT | NPS/PROC/1/2011 | NO CONSULTANCY SERVICES | LUMP SUM | 60098638.87 | NCB | PTB | LERB | PST |  | 10/10/2011 TO 24/10/2011 | 26/01/2011 TO 09/02/2011 | 15/02/2011 TO 01/03/2011 | 14/3/11 | 13/04/2011 | 18/04/2011 TO 9/05/2011 | 11/05/2011 TO 25/05/2011 | 60098638.87 | N.A. | 26/05/2011 TO 2/06/2011 | 6/06/2011 TO 24/06/2011 | NA | 2011-07-18 | 19/09/2011 | 60098638.87 | MR. AYO | NA | MR. AYO | NA
Public Relation Equipment | NPS/OPS/09/11 | NON CONSULTANCY SERVICE | LUMP SUM | 16653292.04 | NCB | PTB | LERB | PST |  |  |  |  | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/5/11 to 25/5/11 | 16653292.04 |  |  |  | NA | 18/7/11 | 2011-07-19 | 16653292.04 | Mr. Ayo | NA | MR AYO | NA
REHABILITATION OF MOTOR VEHICLES | NPS/WL/7/11 | NON-CONSULTANCY SERVICE | LUMP SUM | 41296009.3 | NCB | PTB | LERB | PST |  | 10/1/11-24/1/11 | 26/1/11-9/2/11 | 15/2/11-1/3/11 | 14/3/11 | 13/04/2011 | 18/4/11-9/5/11 | 11/5/11-25/5/11 | 41296009.3 | NA | 26/5/11-2/6/11 | 6/6/11-20/6/11 | NA | 18/7/11 | 2011-07-19 | 41296009.3 | MR AYO | NA | MR AYO | NA

## Fire Serv
Procurement Plan-Goods
Ministry/Department/Agency: Ministry of Interior/Federal Fire Service
Budcgetry Year: 2011
Desk Officer/Contact #: O.A.Dada/08023617475 |  | BASIC DATA
Project Description | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Budgetry Amount in Naira | Pre or Post Quanlification | Prior or Post Review
Norm Duration of Procurement Steps | [5 empty] | If Prequalification
add 2 weeks
List of Contracts
PURCHASE OF FIREFIGHTING EQUIPMENT |  |  |  |  | 47500000
Purchase of Fire Training Fire Simulators | FFE11G1 |  | 10000000 | Open Competitive Bidding |  | 10/02/11
Purchase of Fire Protection Clothing & Hot Fire Gears for Training Purposes | FFE11G2 |  | 20000000 | Open Competitive Bidding |  | 10/02/11
Purchase, Installation and Training on Envirograph Perceive Fire Prevention Products Including FM 200 Fire Suppression System | FFE11G3 |  | 5000000 | Open Competitive Bidding |  | 10/02/11
Purchase of Communication Equipment | FFE11G4 |  | 5000000 | Open Competitive Bidding |  | 10/02/11
Purchase of Office Equipment | FFE11G5 |  | 7500000 | Open Competitive Bidding |  | 10/02/11
PURCHASE OF MOTOR VEHICLES |  |  |  |  | 9500000
Purchase of 1No. Vehicle for Monitoring to Ensure Compliance with the Provision of National Safety Code | FMV11G1 |  | 9500000 | Open Competitive Bidding |  | 10/02/11
PURCHASE OF RESIDENTIAL FURNITURE |  |  |  |  | 15000000
Furnishing of C.G's House | FRF11G1 |  | 5000000 | Open Competitive Bidding |  | 10/02/11
Furnishing of Senior Officers Quarters | FRF11G2 |  | 10000000 | Open Competitive Bidding |  | 10/02/11
Total Cost |  |  | 72000000 |  | 72000000
|  |  | 0 |  | 0

## Avitn_AIB
Ministry/Department/Agency: AIB (Ministry of Aviation)
Budgetary Year: 2011 --- Consultancy Services |  | Desk Officer/Contact #: JOSEPH P. SINEBE -08077090922 |  |  |  |  | Request for Expression of Interest (when required)
|  | Contract Type |  |  | Preparation Request for Proposals |  |  |  | Short List |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [6 empty] | Contract Finalization |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/ Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | No-objection Date | FEC Approval | Contract Amount in Naira | Contract Offer | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks |  | 1- 2 wk | 2 wks
List of Contracts
Conduct of Research study on Human Factor Element in Flight Operations (2) | NCB | Lumpsum. | 3240850 | ATB, | N.A. | NA. | NA | NA. | NA | NA | NA | NA | NA. | NA. | NA | NA | NA | NA | NA | 3,240,850.00 |  |  |  | Sept 2011 | Nov 2011 |  | Engr.AdedoyinT.A | Engr. Diala C.
|  |  | 9155900 | [16 empty] | 9155900 | Jan. 2011 | Jan 2011 | 9,155,900.00 |  |  | 12,396,750.00
Conduct of Research on windshear phenomenon in flight operations (2) | NCB | Lumpsum. | 3240850 | ATB | N.A. | NA. | NA | NA. | NA | NA | NA | NA | NA. | NA. | NA | NA | NA | NA | NA | 3,340,850.00 |  |  |  | Sept 2011 | Nov 2011 |  | Engr.AdedoyinT.A | Engr. Diala C.
|  |  | 9152976 | [16 empty] | 9152976 | Jan. 2011 | Jan 2011 | 9,152,976.00 |  |  | 12,393,816.00
Consultancy on Flight Safety Laboratory/Flight Data Monitoring System. | NCB | Lumpsum. | 5401416 | ATB | N.A. | NA. | NA | NA. | NA | NA | NA | NA | NA. | NA. | NA | NA | NA | NA | NA | 5,401,416.00 | Dec2011 |  |  | Nov 2011 | Jan 2012 |  | Engr.AdedoyinT.A | Engr. Diala C.
|  |  | 37125000 | [16 empty] | 37125000 |  |  | 339,634.00 |  |  | 42,526,416.00
Insurance on Flight Safety Laboratory/Flight Data Monitoring System. | NCB | Lumpsum. | 10802832 | ATB | N.A. | NA. | NA | NA. | NA | NA | NA | NA | NA. | NA. | NA | NA | NA | NA | NA | 10,802,832.00 | Nov 2011 |  |  | Nov 2011 |  |  | Engr.AdedoyinT.A | Engr. Diala C.
|  |  | 22815911 | [16 empty] | 22815911 | [5 empty] | 33,618,743.00
Total Cost |  |  | 78390911 | [16 empty] | 22785948
Fill gray cells only!
Draft Bid Documents, including specs and quantities, draft SPN
Budgetary Year: 2010 -- Goods |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 2 - 4 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
add 2 wks
List of Contracts
Construction of Flight Safety Laboratory(FDR/CVR)/Flight Data Monitoring system. | NA | NA | 215975621 | Direct procurement | No | Ministerial Tenders Board | N.A | N.A. | N.A | N.A. | N.A. | N.A. | N.A |  | N.A | N.A. | N.A | N.A | 16-27 AUG. 11 | 1-2 Sept. 11 | Engr. Adedoyin T.A. | Engr. Diala C. (D/Engr'ing)
|  |  | 509238225 | Direct procurement | No | MTB | [7 empty] | 155000000 |  | 11/01/11 | 11/02/11 | 155000000 |  |  | Engr. Adedoyin T.A. | Engr. Diala C. (D/Engr'ing)
Emergency management/Mock sensitization exercise | N.A | N.A | 3051800 | in-house activity | NO | AIB Tenders Boards | N.A | N.A. | N.A | N.A. | N.A. | N.A. | N.A |  | N.A | N.A. | N.A | N.A | N.A | 20 Dec. 2011 | Engr. Adedoyin T.A. | Engr. Diala C. (D/Engr'ing)
|  |  | 9521152 | DO |  | AIB Tenders Board | [7 empty] | 9521152 |  |  |  | 9521152
Provision for Difficult Terrainwreckage/Flight Data Recorder Recovery exercise.NA. | NA | NA | 540142 |  |  | AIB Tenders Board | N.A | N.A. | N.A | N.A. | N.A. | N.A. | N.A |  | N.A | N.A. | N.A | N.A | N.A | 20 Dec. 2011 | Engr. Adedoyin T.A. | Engr. Diala C. (D/Engr'ing)
|  |  | 2258778 | [14 empty] | 2258778
Provision for Helcopter Support services for crash site mapping. | N.A | N.A | 810212 | In house activity | NO | AIB Tenders Boards | N.A | N.A. | N.A | N.A. | N.A. | N.A. | N.A |  | N.A | N.A. | N.A | N.A | N.A | 20 Dec. 2011 | Engr. Adedoyin T.A. | Engr. Diala C. (D/Engr'ing)
|  |  | 2025000 | DO | [9 empty] | 2025000 |  |  |  | 2025000
Provision for hiring heavy and special equipment. | N.A | N.A | 540142 | In house activity | NO | AIB Tenders Boards | N.A. | N.A | N.A | N.A | N.A | N.A | N.A |  | N.A | N.A. | N.A. | N.A | N.A. | 20 Dec. 2011 | Bassey Ori | Kalejaiye O.A (Mrs) (DHR/F)
|  |  | 4410000 | [10 empty] | 4410000 |  |  |  | 4410000
Production of Accident reports. | N.A | N.A | 8102124 | In house activity | NO | AIB Tenders Boards | N.A | N.A. | N.A | N.A. | N.A. | N.A. | N.A |  | N.A | N.A. | N.A | N.A | N.A | 20 Dec. 2011 | Engr. Adedoyin T.A. | Engr. Diala C. (D/Engr'ing)
|  |  | 60075000 | [10 empty] | 60075000 |  |  |  | 60075000
Stakeholders /Safety Conference | N.A | N.A | 8372195 | In house activity | NO | AIB Tenders Boards | N.A | N.A. | N.A | N.A. | N.A. | N.A. | N.A |  | N.A | N.A. | N.A | N.A | N.A | 20 Dec. 2011 | Engr. Adedoyin T.A. | Engr. Diala C. (D/Engr'ing)
|  |  | 31833848 | [10 empty] | 31833848 |  |  |  | 31833848
Preventive monitoring of facilities and compliance to safety recommendations. | N.A | N.A | 8102124 | In house activity | NO | AIB Tenders Boards | N.A | N.A. | N.A | N.A. | N.A. | N.A. | N.A |  | N.A | N.A. | N.A | N.A | N.A | 20 Dec. 2011 | Engr. Adedoyin T.A. | Engr. Diala C. (D/Engr'ing)
|  |  | 17901222 | [10 empty] | 17901222 |  |  |  | 31833848
Major accident Investigation funds as required by ICAO/corrective plan for deficiences from the Audit. | N.A | N.A | 5401416 | In house activity | NO | AIB Tenders Boards | N.A | N.A. | N.A | N.A. | N.A. | N.A. | N.A |  | N.A | N.A. | N.A | N.A | N.A | 20 Dec. 2011 | Engr. Adedoyin T.A. | Engr. Diala C. (D/Engr'ing)
|  |  | 9450000 | [10 empty] | 9450000 |  |  |  | 9450000

## Avitn_NAMA
Ministry/Department/Agency: NIGERIAN AIRSPACE MANAGEMENT AGENCY
Budgetary Year: 2011---Goods
Desk Officer/Contact #: Humbe 08023508410 |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/ BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
add 2 wks
List of Contracts
Maintenance Agreement for the TRACON Project (Spare Parts) | NA | LOT 1 | 4070475540 | Selective Tender | N/A |  | N/A | 07/09/2009 | N/A | N/A | N/A
[6 empty] | FEC | [5 empty] | N/A | 08/10/2009 | 162042482 | 04/11/2009 | 20/11/2009 | 07/12/2009 | 22/12/2009 | periodically | 28/11/2014 | Engr. Egwu | Alh Auyo
Total Cost
|  |  | 0 | [10 empty] | 162042482
Fill gray cells only!
Budgetary Year: 2011 --- Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: Humbe 08023508410 |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 1 wks | 2-3 wks |  | 6 Months
add 2 wks
List of Contracts
Maintenance Agreement for the TRACON Project (Spare Parts) | NA | LOT 1 | BOQ | Selective Tender | 4070475540 | N/A |  | N/A | 07/09/2009 | N/A | N/A | N/A |  |  | 162042482 | 04/11/2009 | 20/11/2009 | 07/12/2009 | 22/12/2009 | periodically | 28/11/2014 | NA | Engr. Egwu | Alh Auyo
[7 empty] | FEC | [5 empty] | N/A | 08/10/2009
Navigational Aids Equipment (ILS/DME, DVOR, CVOR) |  |  |  |  | 1, 903,012,592.00 |  | FEC | NA | NA | NA | 01-15/02/2011 | 15/02/2011 | 15-22/02/2011 | 23-28/02/2011 | 809366492 | 01-11/03/2011 | 14-18/03/2011 | 21-23/03/2011 | 24-30/03/2011 | 30/09/2011 | 16/12/2011 | NA | Engr. Osoba | Alh Auyo
|  | LOT 2 | BOQ | ICB
Total VHF Radio Coverage of Nigeria |  | LOT 3 | BOQ | ICB | 375694683 |  | MTB | 01-22/02/2011 | 23/02-08/03/11 | 14-25/02/2011 | 14/03-04/04/11 | 04/04/2011 | 4-15/04/2011 | 18-29/04/2011 | 375694683 | N/A | 2-6/05/2011 | 9-13/05/2011 | 16/05-3/06/11 | 02/12/2011 | 16/12/2011 | N/A | Engr. Oreagba | Alh Auyo
AIS/AFTN Automation and AIP/Chart/MAP Production |  | LOT 4 | BOQ | ICB | 1093145332 |  |  | N/A |  | NA | N/A | N/A | N/A | N/A | 1093145332 |  |  |  |  | 22/12/2011 | 15/06/2012 | NA | Engr. Anasi | Alh Auyo
[7 empty] | FEC |  | 01/06/2009 | [6 empty] | 30/09/2009 | 02/11/2009 | 30/11/2009 | 11/12/2009
VCS Consoles for 13 Airports |  | LOT 5 | BOQ | ICB | 255255464 |  |  | N/A | N/A | NA | N/A | N/A | N/A | N/A | 255255464 |  |  |  |  | 24/06/2011 | 30/09/2011 |  | Engr. Anasi | Alh Auyo
[7 empty] | FEC | [8 empty] | 27/10/2010 | 04/11/2010 | 01/12/2010 | 23/12/2010
Solar Energy |  | LOT 6 | BOQ | NCB | 286365524 |  | MTB | 01-22/02/2011 | 23/02-08/03/11 | 14-25/02/2011 | 14/03-04/04/11 | 04/04/2011 | 4-15/04/2011 | 18-29/04/2011 | 286365524 | NA | 02-06/05/2011 | 09-13/05/2011 | 16-27/05/2011 | 25/11/2011 | 09/12/2011 | N/A | Engr. Agomoh | Alh Auyo
Terrestial Communication Facility (Lagos & Abuja) |  | LOT 7 | BOQ | ICB | 154627310 |  |  | NA | NA | NA | NA | NA | NA |  | 154627310 | NA |  | 01-08/02/2011 | 09-25/02/2011 | 26/08/2011 | 09/09/2011 | N/A | Engr. Oreagba | Alh Auyo
[7 empty] | PTB | [6 empty] | 22/12/2010 |  |  | 12/01/2011
SATCOM Communication (Lagos, Kano, Abj. & Phc.) |  | LOT 8 | BOQ | NCB | 99491069 |  | PTB | 01-22/02/2011 | 23/02-08/03/11 | 14-25/02/2011 | 14/03-04/04/11 | 04/04/2011 | 4-15/04/2011 | 18-29/04/2011 | 99491069 | NA | 02-06/05/2011 | 09-13/05/2011 | 16-27/05/2011 | 25/11/2011 | 09/12/2011 | N/A | Engr. Anasi | Alh. Auyo
Automatic Voltage Regulator |  | LOT 9 | BOQ | NCB | 5401416 |  |  | N/A | N/A | N/A | NA | NA | NA |  | 5401416 |  |  | 01-08/02/2011 | 09-25/02/2011 | 26/08/2011 | 09/09/2011 | N/A | Engr. Agomoh | Alh Auyo
[7 empty] | PTB | [6 empty] | 22/12/2010 |  | N/A | 12/01/2011
Total Cost |  |  |  |  | 8243468920 | [9 empty] | 3079347290
Fill gray cells only!

## Avitn_NAMA_IGR
Ministry/Department/Agency: NIGERIAN AIRSPACE MANAGEMENT AGENCY
Budgetary Year: 2011 --- Goods | IGR PROCUREMENT FOR GOODS | [5 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: Humbe 08023508410 |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
add 2 wks
List of Contracts
Procurement of Amoured cables and electrical materials | NA | LOT 1 | 250000000 | NCB |  | MTB | 07-25/03/2011 | 04-08/04/2011 | N/A | 01-29/06/2011 | 29/06/2011 | 04-22/07/2011 | 25-29/07/2011 | N/A | N/A | 08-12/08/2011 | 17-31/08/2011 | 12-23/09/2011 | 10-21/10/2011 | 24-28/10/2011 | Engr. Agomoh | Alh Auyo
Procurement of Refrigerators and Airconditioners | NA | LOT 2 | 150000000 | NCB |  | MTB | 07-25/03/2011 | 04-08/04/2011 | N/A | 01-29/06/2011 | 29/06/2011 | 04-22/07/2011 | 25-29/07/2011 | N/A | N/A | 08-12/08/2011 | 17-31/08/2011 | 12-23/09/2011 | 10-21/10/2011 | 24-28/10/2011 | Engr. Agomoh | Alh Auyo
Procurement of Office equipment | NA | LOT 3 | 70000000 | NCB |  | PTB | 07-25/03/2011 | 04-08/04/2011 | N/A | 01-29/06/2011 | 29/06/2011 | 04-22/07/2011 | 25-29/07/2011 | N/A | N/A | 08-12/08/2011 | 17-31/08/2011 | 12-23/09/2011 | 10-21/10/2011 | 24-28/10/2011 | Alh. Ozigi | Alh Auyo
Procurement of ILS/DME and CVOR/DME Spare Parts | N/A | LOT 4 | 400000000 | ICB |  | MTB | 07-25/03/2011 | 04-08/04/2011 | 18-29/04/2011 | 01-29/06/2011 | 29/06/2011 | 04-22/07/2011 | 25-29/07/2011 | N/A | N/A | 08-12/08/2011 | 17-31/08/2011 | 12-23/09/2011 | 10-21/10/2011 | 24-28/10/2011 | Engr. Osoba | Alh Auyo
Total Cost |  |  | 870000000
Budgetary Year: 2011 -- Works |  | IGR PROCUREMENT PLAN FOR WORKS | [5 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
|  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period | [7 empty] | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 1 wks | 2-3 wks |  | 6 Months
add 2 wks
List of Contracts
ICT project | NA | LOT 5 | BOQ | NCB | 100000000 |  | PTB | 07-25/03/2011 | 04-08/04/2011 |  | 01-29/06/2011 | 29/06/2011 | 04-22/07/2011 | 25-29/07/2011 | N/A | NA | 01-05/08/2011 | 08-12/08/2011 | 15-26/08/2011 | 02/12/2011 | 30/12/2011 | N/A | Mr. Ogochukwu | Alh Auyo
Procurement and Installation of Facility Generators | NA | LOT 6 | BOQ | NCB | 150000000 |  | PTB | 07-25/03/2011 | 04-08/04/2011 |  | 01-29/06/2011 | 29/06/2011 | 04-22/07/2011 | 25-29/07/2011 | N/A | NA | 01-05/08/2011 | 08-12/08/2011 | 15-26/08/2011 | 07/10/2011 | 21/10/2011 | N/A | Engr. Agomoh | Alh Auyo
Provision of Solar Energy System | NA | LOT 7 | BOQ | NCB | 120000000 |  | PTB | 07-25/03/2011 | 04-08/04/2011 |  | 01-29/06/2011 | 29/06/2011 | 04-22/07/2011 | 25-29/07/2011 | N/A | NA | 01-05/08/2011 | 08-12/08/2011 | 15-26/08/2011 | 02/12/2011 | 30/12/2011 | N/A | Engr. Agomoh | Alh Auyo
Total Cost |  |  |  |  | 370000000

## Avitn_NCAA
Ministry/Department/Agency: NIGERIAN CIVIL AVIATION AUTHORITY
Budgetary Year: 2011 -- GOODS | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #:Mr. A. Y Diyajo 08036002126 |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC /Board Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 8 wks | 3 weeks | 2 wks | 4 Weeks | 1 week | 3 Weeks | 3 Weks |  | 2 wks | 1 - 2 wks | 3 wks | 1 Week
add 2 wks
List of Contracts
Acquisition of office furniture and equipment. |  | Lot 11 | N96,000,000.00 | NCB | NA |  | Dec.15-31stJan |  | NA | 01 Feb,-Mar 10 | 10 Mar-Mar17 | 21st Mar-8 April | 11Apr-25 Apr | N96,000,000.00 | NA | 02 May-07 May | 07 May-14/5 | On Request | DEC.,2011 | DEC.,2011
Acquisition of Plant and Machinery |  | Lot 12 | N60,000,000.00 | NCB | NA |  | Dec.15-31stJan |  | NA | 01 Feb,-Mar 10 | 10 Mar-Mar17 | 21st Mar-8 April | 11Apr-25 Apr | N60,000,000.00 | NA | 02 May-07 May | 07 May-14/5 | On Request | DEC.,2011 | DEC.,2011
Acquisition of various operational Motor Vehicles |  | Lot 13 | N145,000,000.00 | NCB | NA |  | Dec.15-31stJan |  | NA | 01 Feb,-Mar 10 | 10 Mar-Mar17 | 21st Mar-8 April | 11Apr-25 Apr | N145,000,000.00 | NA | 02 May-07 May | 07 May-14/5 | On Request | DEC.,2011 | DEC.,2011
Acquisition of desktop and laptop computers |  | Lot 14 | N180,000,000.00 | NCB | NA |  | Dec.15-31stJan |  | NA | 01 Feb,-Mar 10 | 10 Mar-Mar17 | 21st Mar-8 April | 11Apr-25 Apr | N180,000,000.00 | NA | 02 May-07 May | 07 May-14/5 | On Request | DEC.,2011 | DEC.,2011
Flight safety Diagonstic Facilites & Cadiology Apparatus |  |  | N15,000,000.00 | NCB | NA |  | ON GOING |  |  | ON GOING |  |  | ON GOING | N15,000,000.00 |  | ON GOING |  |  |  | ON GOING
Flight Calibration Automatic Console |  |  | N300,000,000.00 | NCB | NA |  | ON GOING |  |  | ON GOING |  |  | ON GOING | N300,000,000.00 |  | ON GOING |  |  |  | ON GOING
Aircraft Tracking System (A GPS based flight watch program) |  |  | N47,000,000.00 | NCB | NA |  | ON GOING |  |  | ON GOING |  |  | ON GOING | N47,000,000.00 |  | ON GOING |  |  |  | ON GOING
Procurement of SMF/M Airfeild lighting equipment |  | Lot 15 | N28,000,000.00 | NCB | NA |  | Dec.15-31stJan |  | NA | 01 Feb,-Mar 10 | 10 Mar-Mar17 | 21st Mar-8 April | 11Apr-25 Apr | 28000000 | NA | 02 May-07 May | 07 May-14/5 | On Request | DEC.,2011 | DEC.,2011
Total Cost |  | #VALUE! | N871,000,000.00 | [10 empty] | N871,000,000.00
Budgetary Year: 2011 -- Works | [5 empty] | CAPITAL BUDGET |  | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: Mr. A. Y Diyajo |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Threshold | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | PTB Approval | Plan vs. Actual | Contract Amount Certified in N | FEC/MTB | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 4 Weeks | 1 - 2 weeks | 2 wks | 6 Weeks | 1 week | 3 Weeks | 2-wks | Plan |  | 2 Weeks | 1 Weeks | 2 wks | 1 Week
[6 empty] | add 2 wks | [8 empty] | Actual
List of Contracts
Completion of construction of abandoned projects at Portharcourt, and kano | NCAA/DFA/03 /2011/PP/01 |  |  |  | N260,000,000.00
Completion of construction of abandoned Regional office complex at Portharcourt |  | Lot 1 | BOQ | NCB | 40000000 | N/A | PTB | Dec.15-31stJan |  | NA | 01 Feb,-Mar 10 | 10 Mar-Mar17 | 21st Mar-8 April | 11Apr-25 Apr | Plan | 40000000 | NA | 02 May-07 May | 07 May-14/5 | On Request | DEC.,2011 | DEC.,2011 | 40000000
[8 empty] | Dec.15-31stJan | [6 empty] | Actual
Completion of construction of abandoned Regional office complex projects at Kano |  | Lot 2 | BOQ | NCB | 45000000 | N/A | PTB | Dec.15-31stJan |  | NA | 01 Feb,-Mar 10 | 10 Mar-Mar17 | 21st Mar-8 April | 11Apr-25 Apr | Plan | 45000000 | NA | 02 May-07 May | 07 May-14/5 | 14May-21/5 | DEC.,2011 | DEC.,2011 | 45000000
[8 empty] | Dec.15-31stJan | [6 empty] | Actual
Completion of construction of fencing,landscaping and borehole for Portharcourt Safety Inspectors staff quarters. |  | Lot 3 | BOQ | NCB | 175000000 | N/A | PTB | Dec.15-31stJan |  | NA | 01 Feb,-Mar 10 | 10 Mar-Mar17 | 21st Mar-8 April | 11Apr-25 Apr | Plan | 175000000 | NA | 02 May-07 May | 07 May-14/5 | 14May-21/5 | DEC.,2011 | DEC.,2011 | 175000000
[8 empty] | Dec.15-31stJan | [6 empty] | Actual
Construction of office Complex at operational Headquarters and Annex lagos | NCAA/DFA/03/2011/PP/02 |  |  | ' | [10 empty] | Plan
Actual
Construction of office Complex at Headquarters and Annex |  | Lot 4 | BOQ | NCB | 160000000 | N/A | PTB | Dec.15-31stJan |  | NA | 01 Feb,-Mar 10 | 10 Mar-Mar17 | 21st Mar-8 April | 11Apr-25 Apr | Plan | 160000000 | NA | 02 May-07 May | 07 May-14/5 | 14May-21/5 | DEC.,2011 | DEC.,2011 | 160000000
[8 empty] | Dec.15-31stJan | [6 empty] | Actual
Construction of staff Canteen at Headquarters Annex |  | Lot 5 | BOQ | NCB | 20000000 |  | PTB | Dec.15-31stJan |  | NA | 01 Feb,-Mar 10 | 10 Mar-Mar17 | 21st Mar-8 April | 11Apr-25 Apr | Plan | 20000000 | NA | 02 May-07 May | 07 May-14/5 | 14May-21/5 | DEC.,2011 | DEC.,2011 | 20000000
[8 empty] | Dec.15-31stJan | [6 empty] | Actual
Furnishing of office Complex at Headquarters and Annex Lagos |  | Lot 6 | BOQ | NCB | 8000000 |  | PTB | Dec.15-31stJan |  | NA | 01 Feb,-Mar 10 | 10 Mar-Mar17 | 21st Mar-8 April | 11Apr-25 Apr | Plan | 8000000 | NA | 02 May-07 May | 07 May-14/5 | 14May-21/5 | DEC.,2011 | DEC.,2011 | 8000000
[8 empty] | Dec.15-31stJan | [6 empty] | Actual
Fencing of Examination Hall at lagos |  | Lot 7 |  |  | 5000000 |  | PTB | Dec.15-31stJan |  | NA | 01 Feb,-Mar 10 | 10 Mar-Mar17 | 21st Mar-8 April | 11Apr-25 Apr | Plan | 5000000 | NA | 02 May-07 May | 07 May-14/5 | 14May-21/5 | DEC.,2011 | DEC.,2011 | 5000000
|  |  | BOQ | NCB |  |  |  | Dec.15-31stJan | [6 empty] | Actual
COMPUTARISATION:Integration of Sage line 500 with four Regional offices, Human Resoures,Procurement and Web based Video conferencing /Telepresence. |  | Lot 8 | BOQ | NCB | 200000000 |  | PTB | Dec.15-31stJan |  |  | ON GOING |  |  | ON GOING | Plan | 200000000 |  | ON GOING |  |  |  | ON GOING | 200000000
[8 empty] | Dec.15-31stJan | [6 empty] | Actual
Renovation and external works of Kaduna Regional office and Safety Inspectors duty room. |  | Lot 9 | BOQ | NCB | 38000000 |  | PTB | Dec.15-31stJan |  | NA | 01 Feb,-Mar 10 | 10 Mar-Mar17 | 21st Mar-8 April | 11Apr-25 Apr | Plan | 38000000 | NA | 02 May-07 May | 07 May-14/5 | 14May-21/5 | DEC.,2011 | DEC.,2011 | 38000000
Actual
Construction of twenty (20) Housing units of for BAGASSO in Abuja. |  | Lot 10 | BOQ | NCB | 800000000 |  | MTB | Dec.15-31stJan |  | NA | 01 Feb,-Mar 10 | 10 Mar-Mar17 | 21st Mar-8 April | 11Apr-25 Apr | Plan | 800000000 | NA | 02 May-07 May | 07 May-14/5 | 14May-21/5 | JUNE,2012 | JUNE,2012 | 800000000
Actual
N1,491,000,000.00

## Avitn_FAAN
Ministry/Department/Agency: FAAN
Budgetary Year: 2011 --- Consultancy Service |  | If Post-Review, No-objection Dates are not needed |  |  |  |  | Request for Expression of Interest (when required)
Desk Officer/Contact #: GM (PROCUREMENT)- FAAN |  | Contract Type |  |  | Preparation Request for Proposals |  |  |  | Short List |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [6 empty] | Contract Finalization |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/ Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | No-objection Date | FEC Approval | Contract Amount in Naira | Contract Offer | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion | Remarks.
Norm Duration of Proc Steps |  |  |  |  | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks |  | 1- 2 wk | 2 wks
List of Contracts
CONSULTING SERVICES
PHIA 03/21 asphalting/apron extension.(N10M | N/A | N/A | 18,270,290.00 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 10,000,000.00 | Engr. Agbo | Engr. Saleh | Awarded 2006. At 80% Completion stage
MMIA asphalting 18L/36R(N10M) | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 10,000,000.00 | Engr. Agbo | Engr. Saleh | Awarded 2006. At 80% Completion stage
MMIA Power supply improvement (N70M) | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 70,000,000.00 | Engr. Daula | Engr. Saleh | Awarded 2006. Upward review of consultancy being processed due to increas in scope.
MAKIA Power supply improvement (N50M) | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 50,000,000.00 | Engr.Daula | Engr. Saleh | 90% completed.
MMIA epanded Metal fence (N14M) | LC | TB |  | PTB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 14,000,000.00 | Engr.Abiola | Engr. Saleh | 100% completed
Bauchi airport access road (N10M) | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 10,000,000.00 | Engr. Abiola | Engr. Saleh | Not implemented
PHIA Power supply improvement (N50M) | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 50,000,000.00 | Engr.Daula | Engr. Saleh | 90% completed.
Bauchi blockwall perimeter fence ( (N14M) | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 14,000,000.00 | Engr.Abiola | Engr. Saleh | Not implemented
MMIA R. C. Fence (N14M) | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 13,000,000.00 | Engr. Abiola | Engr. Saleh | Not implemented
MMIA cargo apron expansion (N24M) | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 24,000,000.00 | Engr. Abiola | Engr. Saleh | Main contract Abandoned.
Budgetary Year: 2011 -- Works | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: FAMADEWA A.D / 08033063503 |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | MDA APPROVAL | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Inspection /Acceptance | Action party | Champion | REMARKS
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 4wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
MMIA Power Supply Improvement at Lagos |  |  | BOQ | NCB | 2414298792 | N/A |  | Plan | N/A | N/A | N/A | N/A | N/A |  |  | Plan | [5 empty] | 31/12/11 | 30/6/12 | 7719751577.07 | 30/6/12 |  |  | THE COMPLETION IS SUBJECT TO ADDITIONAL N3B
[7 empty] | FEC | Actual | [5 empty] | 7/6/10 | 28/9/09 | Actual | 2.250000,000.00 | 25/8/10 | 27/9/10 | 29/10/10 | [5 empty] | ENGR. DAURA | ENGR. SALEH
Power Supply Upgrade for Kano Airport. |  |  | BOQ | NCB | 72078879 | N/A |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 388,162,907.31 |  | 4/8/10 | 2/9/10 |  | 30/9/11 | 31/3/12 | 882363291.84 | 31/3/12 |  |  | THE COMPLETION IS SUBJECT TO ADDITIONAL N423M
[7 empty] | MTB | Actual | [7 empty] | Actual | [9 empty] | ENGR. DAURA | ENGR. SALEH
18Nos. Screening Equipment & Walk through Metal Detectors for MMIA, ABUJA, KANO& PHC @ N16,536,987.78 each. |  |  | BOQ | NCB | 81194745 | N/A |  | Plan | [6 empty] | N/A | Plan |  | N/A | 16/8/10 | 6/9/10 | 0.00 | 31/12/11 | 30/6/12 | 297665780 | 30/6/12 | MR, Obembe | Mr, Ridhard
|  | 4-FAAN/AVS/HQ/002 |  |  |  |  | MTB | Actual | 10/5/10 | 14/5/10 | 31/5/10 | 31/5/10 | 28/6/10 | 19/7/10 |  | Actual | 0 | N/A |  |  | 0.00
Replacement of carousel at MMIA, Lagos. |  |  | BOQ | NCB | 80676714 | N/A |  | Plan | [6 empty] | N/A | Plan |  |  | 11/1/11 | 1/2/11 |  | 31/12/11 | 30/6/12 |  | 30/6/12 |  |  | THE COMPLETION BY DEC. 2011 IS SUBJECT TO ADDITIONA FUND =N=70m
|  | 4-FAAN/CB/MMIA/003 |  |  |  |  | PTB | Actual | 10/5/10 | 14/5/10 | 31/5/10 | 31/5/10 | 28/6/10 | 28/11/10 |  | Actual | 0 | N/A |  |  | 0.00 |  |  | 297862153.63 |  | ENGR. NWODO | ENGR. SALEH
Installartion of 3nos. Melinnabar Bird strike avoidance radar MMIA, ABUJA & PHC@ N140m each. |  |  | BOQ | NCB | 96717756 | N/A |  | Plan | [6 empty] | N/A | Plan |  |  | 15/3/11 | 5/4/11 |  | 31/12/11 | 30/6/2012 | 252000000 | 30/6/12 |  |  | THE COMPLETION BY DEC. 2011 IS SUBJECT TO ADDITIONA FUND =N=156m
|  | 4/FAAN/EVR/HQ/001 |  |  |  |  | MTB | Actual | 10/5/10 | 14/5/10 | 31/5/10 | 31/5/10 | 28/6/10 | 19/7/10 |  | Actual | 0 | N/A |  |  | 0.00 |  |  |  |  | AYONIYI DEHINBO | Alh. Mohammed
Completion of AFL Systems at MMIA domestic runway including civil works at Lagos. |  |  | BOQ | NCB | 205888476 | N/A |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | [5 empty] | 31/12/11 | 30/6/12 | 960454843.02 | 30/6/12 | ENGR. DAURA | ENGR. SALEH | *
[7 empty] | PTB | Actual | [7 empty] | Actual |  |  |  |  | N/A | 31/12/11 | 30/6/12 | 960454843.02 | 30/6/12 | ENGR. DAURA | ENGR. SALEH
[16 empty] | Actual | 0 | N/A | 14/5/09 | 12/6/09 | 0.00
Construction of boundary fence at Port-harcourt Airport. |  |  | BOQ | NCB | 206976912 | N/A |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | [5 empty] | 31/12/11 | 30/6/12 | 1825789612.5 | 30/6/12 |  |  | THE COMPLETION BY DEC. 2011 IS SUBJECT TO ADDITIONA FUND =N=1.5B
[7 empty] | PTB | Actual | [7 empty] | Actual | 160,213,038.16 | N/A | 28/5/09 | 4/6/09 | 0.00 |  |  |  |  | ENGR. AGBO | ENGR. SALEH
Runway extension/expansion & resurfacing for Enugu Airport. |  |  | BOQ | NCB | 2160566421 | N/A |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A |  | Plan | [5 empty] | 31/10/11 | 30/4/12 |  | 30/4/12 |  |  | THE COMPLETION BY DEC. 2011 IS SUBJECT TO ADDITIONA FUND =N=5.4B
[7 empty] | FEC | Actual | [6 empty] | 1/12/08 | Actual | 2,788,429,063.00 | 27/8/09 | 7/9/09 | 24/9/09 |  |  |  | 10338078000.93 |  | ENGR. YEMI AYELETO | ENGR. SALEH
Construction of 6nos. Control towers(Maiduguri, Ilorin, Ibadan, Akure & Kaduna) @ N200m each. |  |  | BOQ | NCB | 245879924 | N/A |  | Plan | [7 empty] | Plan | [5 empty] | 31/12/11 | 30/6/12 |  | 30/6/12 |  |  | COMPLETION BY DEC. 2011 IS SUBJECT TO ADDITIONAL FUND =N=1.23B.
|  | 1/FAANCB /ILR/AK/BN/KD/IBD/001-005 |  |  |  |  | MTB | Actual | 10/5/10 | 14/5/10 | N/A | 31/5/10 | 28/6/10 | 19/7/10 | N/A | Actual | 259,252,062.15 | N/A | 9/11/10, 22/7/10 | 13/12/10, 2/9/10 | 0.00 |  |  | 1732823897.31 |  | ENGR. YEMI AYELETO | ENGR. SALEH
6Nos. (15km) BI-Metal operational perimeter fence at Owerri (10.25km) , Maaiduguri(11.85km), Yola (11.85km), Kaduna ,Benin & Minna (12.65km) |  |  | BOQ | NCB | 275515286 | N/A |  | Plan | [7 empty] | Plan | [5 empty] | 31/12/11 | 30/6/12 |  | 30/6/12 |  |  | COMPLETION BY DEC. 2011 IS SUBJECT TO AVAILABILTY OF ADDITIONAL FUND OF =N=222M. ENUGU AND ILORIN ARE ON-GOING BUT OMMITED IN THE 2011 BDGT. KANUNA & BENIN ARE INADCERTENTLY INCLUDED.
|  | 2/FAN/CB/IMO/MIU/YOL/MN/ILR/ENU/NAIA/001-007 |  |  |  |  | MTB | Actual | 10/5/10 | 14/5/10 | N/A | 31/5/10 | 28/6/10 | 10/9/10 | N/A | Actual | 127,510,518.89 | N/A | 9/11/10 | 6/12/10 | 0.00 |  |  | 1,712,353,699.52 |  | ENGR. AGBO | ENGR. SALEH
Blockwall perimeter fencing for Akure & Ibadan Airports |  |  | BOQ | NCB | 118831153 | N/A |  | Plan | [7 empty] | Plan | [5 empty] | 31/12/11 | 3/6/12 |  | 30/6/12 |  |  | CONPLETION BY DEC. 2011 SUBJECT TO ADDITIONAL FUND OF N216M.
[7 empty] | PTB | Actual | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Actual | 77,275922.19 | N/A | 9//11/10&22/10/10 | 29/11/10&24/11/10 | 0.00 |  |  | 515172815.33 |  | ENGR. AGBO | ENGR. SALEH
Portharcourt apron expansion. |  |  | BOQ | NCB | 32408496 | N/A | MTB | Plan | [7 empty] | Plan | [5 empty] | 31/12/11 | 30/6/12 |  | 30/6/12
[8 empty] | Actual | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Actual | 0 | N/A | 3/2/09 | 22/6/10 | 0.00 |  |  | 506020058.75 |  | ENGR. AGBO | ENGR. SALEH
Completion/Equipping of Akure Airport terminal building. |  |  | BOQ | NCB | 36579785 | N/A |  | Plan | [7 empty] | Plan |  |  |  | 14/11/10 |  | 31/12/11 | 30/6/12 |  | 30/6/12 |  |  | CONPLETION BY DEC. 2011 SUBJECT TO ADDITIONAL FUND OF N31M.
[7 empty] | PTB | Actual | 10/5/10 | 14/5/10 | N/A | 31/5/10 | 28/6/10 | 19/7/10 | N/A | Actual | 0 | N/A | 22/10/10 |  | 0.00 |  |  | 166722584.13 |  | ENGR. AGBO | ENGR. SALEH
AFL lighting CAT I for Akure Airport. |  |  | BOQ | NCB | 96070671 | N/A |  | Plan | [7 empty] | Plan | [5 empty] | 31/12/11 | 30/6/12 |  | 30/6/12 |  |  | CONPLETION BY DEC. 2011 SUBJECT TO ADDITIONAL FUND OF N82M.
|  | 4/FAAN/EE/AKR/OO4 |  |  |  |  | PTB | Actual | 10/5/10 | 14/5/10 | N/A | 31/5/10 | 28/6/10 | 19/7/10 | N/A | Actual | 0 | N/A | 9/11/10 | 13/12/10 | 0.00 |  |  | 375862008.06 |  | ENGR. DAURA | ENGR. SALEH
Refurbishment/remodelling of Kano terminal building. |  |  | BOQ. | NCB | 270070803 | N/A |  | Plan | [7 empty] | Plan |  |  | 15/3/11 | 15/4/11 |  | 30/4/12 | 31/10/12 | 13000000000 | 31/10/12 |  |  | BPP ADVISED THATCERTIFICATE OF NO OBJECTION WOULD BE ISSUED ONLY IF THERE IS ENOUGH FUND AVAILABLE TO PAY 15% MOBILIZATION. MOREOVER, THE BUDGET TITLE IS REFURBISHMENT/REMODELLING OF KANO TERMINAL BUILDING, HOWEVER WHAT IS BEEN PROCESSED IS CONSTRUCTION OF NEW TERMINAL BUILDING.
[7 empty] | FEC. | Actual | 10/5/10 | 14/5/10 | 31/5/10 | 14/6/10 | 28/6/10 | 19/7/10 | NOT APPROVED | Actual | 0 | N/A |  |  | 0.00 |  |  |  |  | ENGR. ABIOLA | ENGR. SALEH
Refurbishment of Abuja international terminal building. |  |  | BOQ | NCB | 71996091 | N/A |  | Plan | [7 empty] | Plan |  |  | 15/3/11 | 5/4/11 |  | 30/6/11 | 31/12/11 |  | 31/12/11 |  |  | PROJECT COMPLETED 2010. FUND PROVIDED IN 2011 BDGT. NOT ADEQUATE TO PAY OUTSTANDING BALANCE OF N263MILLION.
|  | 8/FAAN/CB/NAIA/003 |  |  |  |  | MTB | Actual | N/A | 14/5/10 | N/A | 31/5/10 | 28/6/10 | 19/7/10 | N/A | Actual | 892,575,571.79 | N/A |  |  | 0.00 |  |  | 960551510.81 |  | ENGR. AGBO | ENGR. SALEH
Completion of SMIA Airfield lighting system at Owerri |  |  | BOQ | NCB | 5137092 | N/A |  | Plan | [7 empty] | Plan |  |  | N/A | N/A |  | 31/12/11 | 30/6/12 |  | 30/6/12 |  |  | PROJECT AWARDED 2009. 75% PAID, BALANCE REMAINING =N189M. N180M PROVIDED IN 2010. FUND PROVIDED IN 2011 ADEQUATE.
[7 empty] | MTB | Actual | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Actual | 0 | N/A |  |  | 0.00 |  |  | 596000000 |  | ENGR. DAURA | ENGR. SALEH
Abuja Airport power upgrade, AFL & apron lighting, water supply & sewage systems and construction of MTCE building- urgent repairs needed. |  |  | BOQ | NCB | 1080283210 | N/A |  | Plan | [7 empty] | Plan | [5 empty] | 31/12/11 | 30/6/12 | 1080283210 | 30/6/12
[7 empty] | FEC | Actual | [6 empty] | 11/5/10 | Actual | 518,367,935.45 | 28/7/10 | 4/8/10 | 15/10/10 | 0.00 |  |  |  |  | ENGR. DAURA | ENGR. SALEH
Resurfacing of 20m width central area of runway total length of Benin Airport. |  |  | BOQ | NCB | 249839956 | N/A |  | Plan | [7 empty] | Plan | [5 empty] | 31/12/11 | 30/6/12 |  | 30/6/12 |  |  | THE BID WINNER HAS DECLINED THE OFFER, THE NEXT RESPONSIVE BIDDER MAY BE READVERTISED OR THE PROJECT BE PROCURED.
[7 empty] | MTB | Actual | 10/5/10 | 14/5/10 | N/A | 31/5/10 | 28/6/10 | 19/7/10 | N/A | Actual | 0 | N/A | 20/11/10 | 29/11/2010 | 0.00 |  |  | 777545291.25 |  | ENGR. AGBO | ENGR. SALEH
Rehabilitation of Calabar CAT II AFL |  |  | BOQ | NCB | 8562117 | N/A |  | Plan | [7 empty] | Plan | [5 empty] | 31/12/11 | 30/6/12 |  | 30/6/12
|  | 3/FAAN/EE/CAL/003 |  |  |  |  | PTB | Actual | 10/5/10 | 14/5/10 | N/A | 31/5/10 | 28/6/10 | 19/7/10 | N/A | Actual | 0 | N/A | 22/10/10 | 13/12/10 | 0.00 |  |  | 150851615.28 |  | ENGR. DAURA | ENGR. SALEH
Rehabilitation of CAT I Airfield lighting at Minna airport. |  |  | BOQ | NCB | 8102124 | N/A |  | Plan | [7 empty] | Plan |  |  | N/A | N/A |  | 31/12/11 | 30/6/12 |  | 30/6/12 |  |  | TERMINATION OF SUBSISTING CONTRACT IS BEING PROCESSED
[7 empty] | MTB | Actual | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Actual | 0 | N/A |  |  | 0.00 |  |  | N/A |  | ENGR. DAURA | ENGR. SALEH
Upgrade of AFL to CAT II Katsina Airport. |  |  | BOQ | NCB | 50582739 | N/A |  | Plan | [7 empty] | Plan | [5 empty] | 31/12/11 | 30/6/12 |  | 30/6/12
[7 empty] | PTB | Actual | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Actual | 28,897,077.13 | N/A | 11/6/10 | 2/9/10 | 0.00 |  |  | 192647180.88 |  | ENGR. DAURA | ENGR. SALEH
Rehabilitation of CAT I Airfield lighting at Ilorin Airport. |  |  | BOQ | NCB | 46327695 | N/A |  | Plan | [7 empty] | Plan | [5 empty] | 31/12/11 | 30/6/12 |  | 30/6/12
[7 empty] | PTB | Actual | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Actual | 29,170,070.97 | N/A | 11/6/10 | 2/9/10 | 0.00 |  |  | 194467139.79 |  | ENGR. DAURA | ENGR. SALEH
Calabar Airport runway resurfacing. |  |  | BOQ | NCB | 206796488 | N/A |  | Plan | [6 empty] | N/A | Plan | [5 empty] | 30/11/11 | 31/5/12 |  | 31/5/12 |  |  | ADDITIONAL FUND OF N166M REQUIRED TO COMPLETE THE PROJECT IN 2011.
|  | 7/FAAN/CB/CAL/002 |  |  |  |  | MTB |  | 10/5/10 | 14/5/10 | N/A | 31/5/10 | 28/6/10 |  | N/A | Actual | 124,928,409.38 | N/A | 29/11/10 | 2/12/10 | 0.00 |  |  | 832856062.5 |  | ENGR. AGBO | ENGR. SALEH
Maiduguri Airport runway resurfacing |  |  | BOQ | NCB | 69452980 | N/A |  | Plan | [7 empty] | Plan | [5 empty] | 30/9/11 | 31/3/12 |  | 31/3/12 |  |  | ADDITIONAL FUND OF N607M REQUIRED TO COMPLETE THE PROJECT IN 2011.
[7 empty] | MTB | Actual | N/A | N/A | N/A | N/A | N/A |  | N/A | Actual | 74,974936.55 | N/A | 5/1/10 | 23/2/10 | 0.00 |  |  | 750000000 |  | ENGR. YEMI AYELETO | ENGR. SALEH
Airconditioning systems for MMIA, Lagos. |  |  | BOQ | NCB | 99230562 | N/A |  | Plan | [7 empty] | Plan | [5 empty] | 31/12/11 | 30/6/12 |  | 30/6/12 |  |  | ADDITIONAL FUND OF N84M REQUIRED TO COMPLETE THE PROJECT IN 2011.
[7 empty] | MTB | Actual | 10/5/10 | 14/5/10 | N/A | 31/5/10 | 28/6/10 |  | N/A | Actual | 74,806,818.68 | N/A | 9/11/10 | 2/11/12/10 | 0.00 |  |  | 498712124.56 |  | ENGR. NWODO | ENGR. SALEH
Rehabilitation of Benin , Ibadan & Kaduna AFL lighting. |  |  | BOQ | NCB | 177301482 | N/A |  | Plan | [7 empty] | Plan |  |  |  | 14/11/10 |  | 31/12/11 | 30/6/12 |  | 30/6/12
[7 empty] | PTB | Actual | 10/5/10 | 14/5/10 | N/A | 31/5/10 | 28/6/10 |  | N/A | Actual | 0 | N/A | 22/10/10 |  | 0.00 |  |  | 650000000 |  | ENGR. DAURA | ENGR. SALEH
2nd Runway Construction at Abuja |  |  | BOQ | ICB | 270070803 | N/A |  | Plan | [7 empty] | Plan |  |  |  | 14/11/10 |  | 31/12/11 | 30/6/12 | 4500000000 | 30/6/12
[7 empty] | FEC | Actual | 10/5/10 | 14/5/10 | N/A | 31/5/10 | 28/6/10 |  | N/A | Actual | * | N/A | 22/10/10 |  | * |  |  |  |  | ENGR. DAURA | ENGR. SALEH
MMIA Power Supply Improvement. | WG01 |  | BOQ | NCB | 2414298792 | N/A |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 7719751577.07 | N/A | N/A |  |  |  | DEC. 2012 | 7719751577.07 | DEC. 2012
[7 empty] | FEC | Actual | [7 empty] | Actual |  |  |  | 27/9/2010 |  | DEC, 2010 (35%) |  |  |  | ENGR. DAULA | ENGR. SALEH
Power Supply Upgrade for Kano Airport. | WQ02 |  | BOQ | NCB | 72078879 | N/A |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 882363291.84 | N/A | N/A | 4/8/2010 |  |  | SEPT2011 | 882363291.84 | SEPT. 2011
[7 empty] | MTB | Actual | [7 empty] | Actual | [5 empty] | DEC, 2010 (95%) |  |  |  | ENGR. DAULA | ENGR. SALEH
Replacement of carousel at MMIA. | WG03 |  | BOQ | NCB | 80676714 | N/A |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 297862153.63 | N/A | N/A | N/A | [7 empty] | THE COMPLETION BY DEC. 2011 IS SUBJECT TO ADDITIONA FUND =N=70m
[7 empty] | PTB | Actual | [7 empty] | Actual |  |  |  |  | On demand | DEC, 2010 (0%) | DEC 2011 | 297862153.63 | DEC. 2011 | ENGR. NWODO | ENGR. SALEH
Installartion of 3nos. Melinnabar Bird strike avoidance radar @ N140m each. | WG04 |  | BOQ | NCB | 96717756 | N/A |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan |  | N/A | 15/3/11 | 5/4/11 | [7 empty] | THE COMPLETION BY DEC. 2011 IS SUBJECT TO ADDITIONA FUND =N=224m
[7 empty] | MTB | Actual | [7 empty] | Actual |  |  |  |  | On demand | DEC,2010 (0%) | DEC 2011 |  | DEC, 2011 | AYONIYI DEHINBO | DES
Completion of AFL Systems at MMIA domestic runway including civil works. | WG05 |  | BOQ | NCB | 205888476 | N/A |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 960454843.02 | N/A | N/A | N/A
[7 empty] | PTB | Actual | [7 empty] | Actual |  |  |  |  | N/A | DEC,2010 (45%) | DEC. 2011 | 960454843.02 | DEC. 2011 | ENGR. DAULA | ENGR. SALEH
Construction of boundary fence at Port-harcourt Airport. | WG06 |  | BOQ | NCB | 206976912 | N/A |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan |  | N/A | N/A | N/A |  |  | DEC. 2011 | 1825789612.5 | DEC. 2011
[7 empty] | PTB | Actual | [7 empty] | Actual | 1825789612.5 |  |  |  | N/A | DEC,2010 (35%) |  |  |  | ENGR. AGBO | ENGR. SALEH
Runway extension/expansion & resurfacing for Enugu Airport. | WG07 |  | BOQ | NCB | 2160566421 | N/A |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 10338078000.93 | N/A | N/A | N/A
[7 empty] | FEC | Actual | [7 empty] | Actual |  |  |  |  | N/A | DEC, 2010 (60%) | OCT.2012 | 10338078000.93 | OCT. 2012 | ENGR. YEMI AYELETO | ENGR. SALEH
Construction of 6nos. Control towers(Maiduguri, Ilorin, Ibadan, Akure & Kaduna) @ N200m each. | WG08 |  | BOQ | NCB | 245879924 | N/A |  | Plan | [7 empty] | Plan | [11 empty] | THE COMPLETION BY DEC. 2011 IS SUBJECT TO ADDITIONAL FUND =N=1.04B.
[7 empty] | MTB | Actual | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Actual | 1732823897.31 |  | N/A | 29/11/10 | N/A | DEC, 2010 (15%) | DEC. 2012 | 1732823897.31 | DEC. 2012 | ENGR. YEMI AYELETO | ENGR. SALEH
6Nos. (15km) BI-Metal operational perimeter fence at Owerri (10.25km) , Maaiduguri(11.85km), Yola (11.85km), Kaduna ,Benin & Minna (12.65km) | WG09 |  | BOQ | NCB | 275515286 | N/A |  | Plan | [7 empty] | Plan | [11 empty] | THE COMPLETION BY DEC. 2011 IS SUBJECT TO AVAILABILTY OF ADDITIONAL FUND OF =N=222M. ENUGU AND ILORIN ARE ON-GOING BUT OMMITED IN THE 2011 BDGT. KANUNA & BENIN ARE INADCERTENTLY INCLUDED.
[7 empty] | MTB | Actual | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Actual | 1712353699.52 |  | N/A | 9/11/2010 | N/A | DEC, 2010 (15%) | DEC, 2011 | 1,712,353,699.52 | DEC, 2011 | ENGR. AGBO | ENGR. SALEH
Blockwall perimeter fencing for Akure & Ibadan Airports | WG10 |  | BOQ | NCB | 118831153 | N/A |  | Plan | [7 empty] | Plan | [11 empty] | CONPLETION BY DEC. 2011 SUBJECT TO ADDITIONAL FUND OF N216M.
[7 empty] | PTB | Actual | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Actual | 515172815.33 | NA | N/A | 9/11/2010 | N/A | DEC,2010 (15%) | DEC. 2011 | 515172815.33 | DEC. 2011 | ENGR. AGBO | ENGR. SALEH
Portharcourt apron expansion. | WG11 |  | BOQ | NCB | 32408496 | N/A | MTB | Plan | [7 empty] | Plan
[8 empty] | Actual | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Actual | 506020058.75 | N/A | N/A | N/A | N/A | DEC, 2010 (20%) | DEC. 2011 | 506020058.75 | DEC. 2011 | ENGR. AGBO | ENGR. SALEH
Completion/Equipping of Akure Airport terminal building. | WG12 |  | BOQ | NCB | 36579785 | N/A |  | Plan | NA | N/A | N/A | N/A | N/A | N/A | N/A | Plan |  | N/A | 22/10/2010 | N/A | [7 empty] | CONPLETION BY DEC. 2011 SUBJECT TO ADDITIONAL FUND OF N31M.
[7 empty] | PTB | Actual | [7 empty] | Actual | 166722584.13 |  |  |  | N/A | DEC, 2010 (15%) | DEC. 2011 | 166722584.13 | DEC. 2011 | ENGR. AGBO | ENGR. SALEH
AFL lighting CAT I for Akure Airport. | WG13 |  | BOQ | NCB | 96070671 | N/A |  | Plan | NA | N/A | N/A | N/A | N/A | N/A | N/A | Plan | [11 empty] | CONPLETION BY DEC. 2011 SUBJECT TO ADDITIONAL FUND OF N82M.
[7 empty] | PTB | Actual | [7 empty] | Actual | 375862008.06 | N/A | N/A | 9/11/2010 | N/A | DEC, 2010 (15%) | DEC. 2011 | 375862008.06 | DEC. 2011 | ENGR. DAULA | ENGR. SALEH
Refurbishment/remodelling of Kano terminal building. | WG14 |  | BOQ. | NCB | 270070803 | N/A |  | Plan | [7 empty] | Plan | 13000000000 | [6 empty] | 13000000000 |  |  |  | BPP ADVISED THATCERTIFICATE OF NO OBJECTION WOULD BE ISSUED ONLY IF THERE IS ENOUGH FUND AVAILABLE TO PAY 15% MOBILIZATION. MOREOVER, THE BUDGET TITLE IS REFURBISHMENT/REMODELLING OF KANO TERMINAL BUILDING, HOWEVER WHAT IS BEEN PROCESSED IS CONSTRUCTION OF NEW TERMINAL BUILDING.
[7 empty] | FEC. | Actual | N/A | N/A | N/A | N/A | N/A | N/A | NOT APPROVED | Actual | [9 empty] | ENGR. ABIOLA | ENGR. SALEH
Refurbishment of Abuja international terminal building. | WG15 |  | BOQ | NCB | 71996091 | N/A |  | Plan | [7 empty] | Plan |  | N/A | 15/3/11 | 5/4/11 | [7 empty] | PROJECT COMPLETED 2010. FUND PROVIDED IN 2011 BDGT. NOT ADEQUATE TO PAY OUTSTANDING BALANCE OF N263MILLION.
[7 empty] | MTB | Actual | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Actual | 960551510.81 |  |  | 4/8/2010 | N/A | DEC, 2010 (100%) | JUNE, 2011 | 960551510.81 | JUNE 2011 | ENGR. AGBO | ENGR. SALEH
Completion of SMIA Airfield lighting system | WG16 |  | BOQ | NCB | 5137092 | N/A |  | Plan | [7 empty] | Plan |  | N/A | N/A | N/A | [7 empty] | PROJECT AWARDED 2009. 75% PAID, BALANCE REMAINING =N189M. N180M PROVIDED IN 2010. FUND PROVIDED IN 2011 ADEQUATE.
[7 empty] | MTB | Actual | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Actual | 596000000 |  |  |  | N/A | DEC, 2010 (43%) | DEC,2011 | 596000000 | DEC. 2011 | ENGR. NWODO | ENGR. SALEH
Abuja Airport power upgrade, AFL & apron lighting, water supply & sewage systems and construction of MTCE building- urgent repairs needed. | WG17 |  | BOQ | NCB | 1080283210 | N/A |  | Plan | [7 empty] | Plan
[7 empty] | FEC | Actual | [7 empty] | Actual | [9 empty] | ENGR. DAULA | ENGR. SALEH
Resurfacing of 20m width central area of runway total length of Benin Airport. | WG18 |  | BOQ | NCB | 249839956 | N/A |  | Plan | [7 empty] | Plan | [11 empty] | THE BID WINNER HAS DECLINED THE OFFER, THE NEXT RESPONSIVE BIDDER MAY BE READVERTISED OR THE PROJECT BE PROCURED.
[7 empty] | MTB | Actual | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Actual | 777545291.25 | N/A | N/A | 29/11/2010 |  | DEC, 2010 (0%) | DEC, 2011 | 777545291.25 | DEC, 2011 | ENGR. AGBO | ENGR. SALEH
Rehabilitation of Calabar CAT II AFL | WG19 |  | BOQ | NCB | 8562117 | N/A |  | Plan | [7 empty] | Plan
[7 empty] | PTB | Actual | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Actual | 150851615.28 | N/A | N/A | N/A | N/A | DEC, 2010 (15%) | DEC. 2011 | 150851615.28 | DEC. 2011 | ENGR. DAULA | ENGR. SALEH
Rehabilitation of CAT I Airfield lighting at Minna airport. | WG20 |  | BOQ | NCB | 8102124 | N/A |  | Plan | [7 empty] | Plan | [11 empty] | TERMINATION OF SUBSISTING CONTRACT IS BEING PROCESSED
[7 empty] | MTB | Actual | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Actual |  | N/A | N/A | N/A | N/A | (DEC,2010 (0%) |  | N/A |  | ENGR. DAULA | ENGR. SALEH
Upgrade of AFL to CAT II Katsina Airport. | WG21 |  | BOQ | NCB | 50582739 | N/A |  | Plan | [7 empty] | Plan
[7 empty] | PTB | Actual | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Actual | 192647180.88 | N/A | N/A | 21/5/2010 | N/A | (DEC,2010 (15%) | DEC. 2011 | 192647180.88 | DEC. 2011 | ENGR. DAULA | ENGR. SALEH
Rehabilitation of CAT I Airfield lighting at Ilorin Airport. | WG22 |  | BOQ | NCB | 46327695 | N/A |  | Plan | [7 empty] | Plan
[7 empty] | PTB | Actual | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Actual | 194467139.79 | N/A | N/A | 21/5/2010 | N/A | DEC, 2010 (15%) | DEC. 2011 | 194467139.79 | DEC. 2011 | ENGR. DAULA | ENGR. SALEH
Calabar Airport runway resurfacing. | WG23 |  | BOQ | NCB | 206796488 | N/A |  | Plan |  |  |  |  | N/A | N/A | N/A | Plan | [11 empty] | ADDITIONAL FUND OF N166M REQUIRED TO COMPLETE THE PROJECT IN 2011.
[7 empty] | MTB | Actual | N/A | N/A | N/A | N/A |  |  |  | Actual | 832856062.5 | N/A | N/A | 29/11/2010 | N/A | DEC, 2010 (15%) | NOV. 2011 | 832856062.5 | NOV, 2011 | ENGR. AGBO | ENGR. SALEH
Maiduguri Airport runway resurfacing | WG24 |  | BOQ | NCB | 69452980 | N/A |  | Plan | [7 empty] | Plan
[7 empty] | MTB | Actual | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Actual | 750000000 | N/A | N/A | N/A | N/A | DEC, 2010 (15%) | SEPT. 2011 | 750000000 | SEPT. 2011 | ENGR. YEMI AYELETO | ENGR. SALEH
Airconditioning systems for MMIA. | WG25 |  | BOQ | NCB | 99230562 | N/A |  | Plan | [7 empty] | Plan | [11 empty] | ADDITIONAL FUND OF N84M REQUIRED TO COMPLETE THE PROJECT IN 2011.
[7 empty] | MTB | Actual | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Actual | 498712124.56 | N/A | N/A | 9/11/2010 | N/A | DEC, 2010 (0%) | DEC. 2011 | 498712124.56 | DEC. 2011 | ENGR. NWODO | ENGR. SALEH
Rehabilitation of Benin , Ibadan & Kaduna AFL lighting. | WG26 |  | BOQ | NCB |  | N/A |  | Plan | [7 empty] | Plan
[7 empty] | PTB | Actual | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Actual | 650000000 | N/A | N/A | 22/10/2010 | N/A | DEC,2010 (15%) | DEC. 2011 | 650000000 | DEC. 2011 | ENGR. DAULA | ENGR. SALEH
Fire Alarm systems for MMIA | W001 | 1 | BOQ | NCB | 18416006.5 | N/A |  | Plan | 14-21/2/11 | 21/02-7/3/2011 | N/A | 7/3/11-7/4/2011 | 7/4/2011 | 7/4/11-21/4/2011 | N/A | Plan | N/A | N/A | 5-12/5/2011 | 12/5/11- 2/6/2011 |  | 31/12/2011 | 30/6/2012 | N/A | Dec, 2011 | Engr.Daula | Engr Saleh
[7 empty] | PTB | Actual | [7 empty] | Actual
Fire Alarm systems for PHC | W002 | 2 | BOQ | NCB | 18416006.5 | N/A |  | Plan | 14-21/2/11 | 21/02-7/3/2011 | N/A | 7/3/11-7/4/2011 | 7/4/2011 | 7/4/11-21/4/2011 | N/A | Plan | N/A | N/A | 5-12/5/2011 | 12/5/11- 2/6/2011 |  | 31/12/2011 | 30/6/2012 | N/A | Dec, 2011 | Engr.Daula | Engr Saleh
[7 empty] | PTB | Actual | [7 empty] | Actual
Water hydrant Restoration Projects at MMIA | W003 | 3 | BOQ | NCB | 40250000 | N/A |  | Plan | 14-21/2/11 | 21/02-7/3/2011 | N/A | 7/3/11-7/4/2011 | 7/4/2011 | 7/4/11-21/4/2011 | N/A | Plan | N/A | N/A | 5-12/5/2011 | 12/5/11- 2/6/2011 |  | 31/12/2011 | 30/6/2012 | N/A |  | Surv. Obi | Engr Saleh
[7 empty] | PTB | Actual | [7 empty] | Actual
Water hydrant Restoration Projects at Abuja Airport | W004 | 4 | BOQ | NCB | 40250000 | N/A |  | Plan | 14-21/2/11 | 21/02-7/3/2011 | N/A | 7/3/11-7/4/2011 | 7/4/2011 | 7/4/11-21/4/2011 | N/A | Plan | N/A | N/A | 5-12/5/2011 | 12/5/11- 2/6/2011 |  | 31/12/2011 | 30/6/2012 | N/A | Dec, 2011 | Surv. Obi | Engr. Saleh
[7 empty] | PTB | Actual | [7 empty] | Actual
Water hydrant Restoration Projects at Benin Airport | W005 | 5 | BOQ | NCB | 25250000 | N/A |  | Plan | 14-21/2/11 | 21/02-7/3/2011 | N/A | 7/3/11-7/4/2011 | 7/4/2011 | 7/4/11-21/4/2011 | N/A | Plan | N/A | N/A | 5-12/5/2011 | 12/5/11- 2/6/2011 |  | 31/12/2011 | 30/6/2012 | N/A | Dec, 2011 | Surv. Obi | Engr. Saleh
[7 empty] | PTB | Actual | [7 empty] | Actual
Water hydrant Restoration Projects at Enugu Airport | W006 | 6 | BOQ | NCB | 25250000 | N/A |  | Plan | 14-21/2/11 | 21/02-7/3/2011 | N/A | 7/3/11-7/4/2011 | 7/4/2011 | 7/4/11-21/4/2011 | N/A | Plan | N/A | N/A | 5-12/5/2011 | 12/5/11- 2/6/2011 |  | 31/12/2011 | 30/6/2012 | N/A | Dec, 2011 | Surv. Obi | Engr. Saleh | *
[7 empty] | PTB | Actual | [7 empty] | Actual
Reactivation and Rehabilitation of Abandoned Sewage Treatment Plant at MMIA | W007 | 7 | BOQ | NCB | 44561682 | N/A | PTB | Plan | 14-21/2/11 | 21/02-7/3/2011 | N/A | 7/3/11-7/4/2011 | 7/4/2011 | 7/4/11-21/4/2011 | N/A | Plan | N/A | N/A | 5-12/5/2011 | 12/5/11- 2/6/2011 |  | 31/12/2011 | 30/6/2012 | N/A | Dec, 2011 | Surv. Obi | Engr. Saleh | *
Actual
Construction of Bayesa Airport, Yenagoa | W008 | 8 | BOQ | NCB | 2889757588 |  |  | Plan | 14-21/2/11 | 21/02-7/3/2011 | N/A | 7/3/11-7/4/2011 | 7/4/2011 | 7/4/11-21/4/2011 | N/A | Plan | N/A | N/A | 5-12/5/2011 | 12/5/11- 2/6/2011 |  | 31/12/2011 | 30/6/2012 | N/A | Dec, 2011 |  |  | PROJECT YET TO BE HANDED OVER TO FAAN.
[7 empty] | FEC | Actual | [7 empty] | Actual | [9 empty] | FMA/FAAN | FMA
Completion of Module D at International Airport, Abuja. | W009 | 9 | BOQ | NCB | 432113325 | N/A |  | Plan | 14-21/2/11 | 21/02-7/3/2011 | N/A | 7/3/11-7/4/2011 | 7/4/2011 | 7/4/11-21/4/2011 | N/A | Plan | N/A | N/A | 5-12/5/2011 | 12/5/11- 2/6/2011 |  | 31/12/2011 | 30/6/2012 | N/A | Dec, 2011 | Engr. Agbo | Engr Saleh
[7 empty] | MTB | Actual | [7 empty] | Actual
Construction of control Tower at Enugu Airport. | W010 | 10 | BOQ | NCB | 178131325 | N/A |  | Plan | 14-21/2/11 | 21/02-7/3/2011 | N/A | 7/3/11-7/4/2011 | 7/4/2011 | 7/4/11-21/4/2011 | N/A | Plan | N/A | N/A | 5-12/5/2011 | 12/5/11- 2/6/2011 |  | 31/12/2011 | 30/6/2012 | N/A | Dec, 2011 | Engr. Agbo | Engr Saleh
[7 empty] | MTB | Actual | [7 empty] | Actual

## Avitn_NCAT
Ministry/Department/Agency: Nigerian College of Aviation Technology
Budgetary Year: 2011 --- Consultancy Service | [6 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: Engr. Audu Ali/08035872238 |  | Contract Type |  |  | Preparation Request for Proposals |  |  |  | Short List |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [6 empty] | Contract Finalization |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/ Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | No-objection Date | FEC Approval | Contract Amount in Naira | Contract Offer | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks |  | 1- 2 wk | 2 wks
List of Contracts
Consultancy Services for the Design and Supervision of the Rehabiltation/Construction of College Road Network and Drainages | QCBS | LUMP SUM | 6000000 | PTB | 24 JAN - 7 FEB 2011 | 7 FEB-11 FEB 2011 | 7 FEB-2 1FEB 2011 | 21FEB- 28 FEB 2011 | 28 FEB 2011 | 28 FEB - 7 MAR 2011 | 7 MAR-21 MAR 2011 | 21 MAR -4 APR 2011 | 4APR - 18 APR 2011 | 18 APR - 2 MAY 2011 | 2 MAY- 16 MAY 2011 | 16 MAY-30 MAY 2011 | 30MAY - 15 JUN 2011 | 15 JUN - 27 JUN 2011 | N/A | 45000000 | 27 JUN - 11 JUL 2011 | 11 JUL - 26 JUL 2011 |  | 11 AUG 2011 | 11 SEP 2011 |  | Engr. Abdullahi | Mr. C.ONUGHA
Consultancy Services for the Supervision of Construction/Up-gading of Aeromedical Centre Main Building and Perimeter Fence | QCBS | LUMP SUM | 38000000 | PTB | 24 JAN- 7 FEB 2011 | 7 FEB-11 FEB 2011 | 7FEB-21 FEB 2011 | 21FEB-28 FEB 2011 | 28 FEB 2011 | 28 FEB -7 MAR 2011 | 7 MAR- 21 MAR 2011 | 21 MAR- 4 APR 2011 | 4 APR - 18 APR 2011 | 18 APR- 2 MAY 2011 | 2 MAY- 16 MAY 2011 | 16 MAY- 30 MAY 2011 | 30 MAY- 15 JUN 2011 | 15 JUN- 27 JUN 2011 | N/A | 21000000 | 27 JUN - 11 JUL 2011 | 11 JUL-26 JUL 2011 |  | 11 AUG 2011 | 11 SEPT 2011 |  | Engr. Abdullahi | Dr. E.Shittu
Consultancy Services for the Supervision of Construction Flying School First Floor Classroom Block | QCBS | LUMP SUM | 41000000 | PTB | 24 JAN- 7 FEB 2011 | 7 FEB-11 FEB 2011 | 7FEB-21 FEB 2011 | 21FEB-28 FEB 2011 | 28 FEB 2011 | 28 FEB -7 MAR 2011 | 7 MAR- 21 MAR 2011 | 21 MAR- 4 APR 2011 | 21 MAR - 4 APR 2011 | 18 APR- 2 MAY 2011 | 2 MAY- 16 MAY 2011 | 16 MAY- 30 MAY 2011 | 30 MAY- 15 JUN 2011 | 15 JUN- 27 JUN 2011 | N/A |  | 27 JUN - 11 JUL 2011 | 11 JUL-26 JUL 2011 |  | 11 AUG 2011 | 11 SEPT 2011 |  | Engr. Abdullahi | Capt. Caulcrick
Consultancy Services for the Design and Supervision of the Resurfacing and Extension of Runway and Taxiway | QCBS | LUMP SUM | 45000000 | PTB | 24 JAN- 7 FEB 2011 | 7 FEB-11 FEB 2011 | 7 FEB-2 1FEB 2011 | 21FEB-28 FEB 2011 | 28 FEB 2011 | 28 FEB - 7 MAR 2011 | 7 MAR-21 MAR 2011 | 21 MAR- 4 APR 2011 | 4APR-18 APR 2011 | 18 APR- 2 MAY 2011 | 2 MAY- 16 MAY 2011 | 16 MAY-30 MAY 2011 | 30MAY - 15 JUN 2011 | 15 JUN - 27 JUN 2011 | N/A | 45000000 | 27 JUN - 11 JUL 2011 | 11 JUL - 26 JUL 2011 |  | 11 AUG 2011 | 11 SEP 2011 |  | Engr. Abdullahi | Capt. Caulcrick
Consultancy Services for the Supervision of Rehabilitation of 3rd Hangar | QCBS | LUMP SUM | 21000000 | PTB | 24 JAN- 7 FEB 2011 | 7 FEB-11 FEB 2011 | 7FEB-21 FEB 2011 | 21FEB-28 FEB 2011 | 28 FEB 2011 | 28 FEB -7 MAR 2011 | 7 MAR- 21 MAR 2011 | 21 MAR- 4 APR 2011 | 4 APR-18 APR 2011 | 18 APR- 2 MAY 2011 | 2 MAY- 16 MAY 2011 | 16 MAY-30 MAY 2011 | 30 MAY- 15 JUN 2011 | 15 JUN- 27 JUN 2011 | N/A | 21000000 | 27 JUN - 11 JUL 2011 | 11 JUL-26 JUL 2011 |  | 11 AUG 2011 | 11 SEPT 2011 |  | Engr. Abdullahi | C. Manshop
Consultancy Services for the Design and Supervision of the Construction of Students Hostel Block B | QCBS | LUMP SUM | 25000000 | PTB | 24 JAN- 7 FEB 2011 | 7 FEB-11 FEB 2011 | 7FEB-21 FEB 2011 | 21FEB-28 FEB 2011 | 28 FEB 2011 | 28 FEB -7 MAR 2011 | 7 MAR- 21 MAR 2011 | 21 MAR -4 APR 2011 | 4 APR-18 APR 2011 | 18 APR- 2 MAY 2011 | 2 MAY- 16 MAY 2011 | 16 MAY-30 MAY 2011 | 30 MAY- 15 JUN 2011 | 15 JUN- 27 JUN 2011 | N/A | 25000000 |  |  |  | 11 AUG 2011 | 11 SEPT 2011 |  | Engr. Abdullahi | C.Onugha
Provision of Insurance Cover for the College Assets | QCBS | LUMP SUM | 750000000 | FEC | 24 JAN- 7 FEB 2011 | 7 FEB-11 FEB 2011 | 7FEB-21 FEB 2011 | 21FEB-28 FEB 2011 | 28 FEB 2011 | 28 FEB -7 MAR 2011 | 7 MAR- 21 MAR 2011 | 21 MAR- 4 APR 2011 | 4 APR-18 APR 2011 | 18 APR- 2 MAY 2011 | 2 MAY- 16 MAY 2011 | 16 MAY-30 MAY 2011 | 30 MAY- 15 JUN 2011 | 15 JUN- 27 JUN 2011 | 27JUN-10JUL2011 | 750000000 | 11JUL- 25JUL2011 | 26JUL-10AUG2011 |  | 11 AUG 2011 | 11 SEPT 2011 |  | Abubakar Aliyu | Capt. Caulcrick
Total Cost |  |  | 841000000 | [16 empty] | 907000000
Budgetary Year: 2011 -- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN
Desk Officer/Contact #: Engr. Audu Ali/08034872238 |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/ BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
add 2 wks
List of Contracts
Purchase of Aerobatic Aircraft (On Going) | NCAT/GDS/DC/2010/003 | LOT 11 | 140000000 | DC | Post-Qualification | MTB | 22 FEB- 8 MAR-2010 | 8 MAR- 18 MAR 2010 | N/A | 22 MAR- 19 APR 2010 | 19 APR 2010 | 19 APR-3 MAY2010 | 3 -17MAY 2010 | 140000000 | 18 MAY- 2JUN 2010 | 2JUN- 16JUN 2010 | 16JUN- 30JUL 2010 | 1AUG - 14 AUG 2010 | 14 SEP 2010 | 15 SEP- 29SEP 2010 | Engr. Ibrahim Hirse/ Manshop | Capt. Caulcrick
Purchase of Aircraft Spare Parts | NCAT/GDS/DC/2010/005 | N/A | 146835847 | DP | N/A | PTB | N/A | N/A | N/A | 5-APR-2011 | 17-MAY-2011 | 7-JUN-2011 | 21-JUN-2011 | 146835847 | N/A | 5-JUL-2011 | 18-JUL-2011 | 2-AUG-2011 | 01-NOV-2011 | 8-NOV-2011 | Engtr. Audu Ali | Capt. Caulcrick
Purchase of Operational Vehicles(on-going) | NCAT/GDS/NCB/2011/005 | LOT 12 | 60000000 | NCB | Post-Qualification | MTB | 22 FEB- 8 MAR-2011 | 8 MAR- 18 MAR 2011 | N/A | 22 MAR- 19 APR 2011 | 19 APR 2011 | 19 APR- 3MAY 2011 | 3-17 MAY 2011 | 60000000 | 4 MAY- 18 MAY 2011 | 19 MAY- 2 JUN 2011 | 3 JUN- 17 JUN 2011 | 18 JUN - 4 JULY 2011 | 30 JUL 2011 | 30 JUL 2011 | Transport Officer | Registrar
Purchase of Two (2) Trainer Helicopter (On-Going) | NCAT/GDS/DC/2010/003 | LOT 11 | 1177566525.66 | DC | N/A | FEC | 22 FEB- 8 MAR-2010 | 8 MAR- 18 MAR 2010 | N/A | 22 MAR- 19 APR 2010 | 19 APR 2010 | N/A | 20 APR- 3 MAY 2010 | 1177566525.66 | 4 MAY- 18 MAY 2010 | 19 MAY- 2 JUN 2010 | 3 JUN- 17 JUN 2010 | 18 JUN- 4 JULY 2010 | 4 JAN 2011 | 5 JAN- 18 JAN 2011 | Engr. Ibrahim Hirse/ Manshop | Capt. Caulcrick
[10 empty] | 1-JUN-2010 | 1-JUL-2010 | N/A | 26-NOV-2010 |  | 8-DEC-2010 | 29-DEC-2010 | N/A | N/A | N/A | N/A
Purchase of Aircraft Spare Parts | NCAT/GDS/DC/2010/005 | N/A | 146835847 | DP | N/A | PTB | N/A | N/A | N/A | 5-APR-2011 | 17-MAY-2011 | 7-JUN-2011 | 21-JUN-2011 | 146835847 | N/A | 5-JUL-2011 | 18-JUL-2011 | 2-AUG-2011 | 01-NOV-2011 | 8-NOV-2011 | Engtr. Audu Ali | Capt. Caulcrick
Purchase of Aircraft Spare Parts | NCAT/GDS/DC/2011/005 | LOT 11 | 71675055 | DP | N/A | PTB | 22 FEB- 8 MAR-2011 | 8 MAR- 18 MAR 2011 | N/A | 22 MAR- 19 APR 2011 | 19 APR 2011 | 1 JUL- 18 JUL 2011 | 20 APR- 3 MAY 2011 | 71675055 | 4 MAY- 18 MAY 2011 | 19 MAY- 2 JUN 2011 | 3 JUN- 17 JUN 2011 | 18 JUN- 4 JULY 2011 | 4 JAN 2012 | 5 JAN- 18 JAN 2012 | Japhet Yalson | C. Manshop
Purchase of Aircraft Fuel(Avgas 100LL,Jet A-1 & Lubricants) | NCAT/GSD/NCB/2011/0015 | LOT 9 | 150000000 | DC | N/A | MTB | 22 FEB- 8 MAR-2011 | 8 MAR- 18 MAR 2011 | N/A | 22 MAR- 19 APR 2011 | 19 APR 2011 | 1 JUL- 18 JUL 2011 | 20 APR- 3 MAY 2011 | 150000000 | 4 MAY- 18 MAY 2011 | 19 MAY- 2 JUN 2011 | 3 JUN- 17 JUN 2011 | 18 JUN- 4 JULY 2011 | 4 JAN 2012 | 5 JAN- 18 JAN 2012 | C.Manshop | Capt. Caulcrick
Supply of ONE(1) Mechtronic Ascent Simulator(6 MOUV Flight Simulator) | NCAT/GDS/DC/2011/008 | LOT 14 | 140000000 | DC | N/A | FEC | 24 MAR- 5 APR 2011 | 06 APR- 17 APR 2011 | N/A | 18 MAY- 29 JUN 2011 | 29-JUN-2011 | 1 JUL- 18 JUL 2011 | 19 JUL- 30 JUL 2011 | 140000000 | N/A | 1 AUG- 13 AUG 2011 | 14 AUG- 20 AUG 2011 | 11 JUN- 11 JUL 2012 | 12 DEC 2012- 12 JAN 2013 |  | Capt. Abbas/ Aba | Capt S. Caulcrick
Purchase of Visual Tower Simulator(on-going) | NCAT/GDS/DC/2010/001 | LOT 13 | 381365027 | DC | N/A | FEC | 22 FEB - 10 MAR 2010 | N/A | N/A | 25 MAR- 7 MAY 2010 | 7 MAY 2010 | 8 MAY- 30 MAY 2010 |  | 381365027 | 1 JUN- 1 JUL 2010 | 2 JUL- 16 JUL 2010 | 17 JUL - 24 JUL 2010 | 23-DEC-2010 | 22-MAY-2010 |  | Engr. Tijjani | Engr. S.T. Yahaya
[7 empty] | 22-FEB-2010 | N/A |  | 3-AUG-2010 | 24-AUG-2010 | 19-NOV-2010 | 24 DEC 2010 | 371992299.44 | 8-DEC-2010 | 29-DEC-2010 | 10-FEB-2011
Total Cost |  |  | 2414278301.66 | [10 empty] | 2414278301.66
Budgetary Year: 2011 --- Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: Engr. Audu Ali/08035872238 |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
add 2 wks
List of Contracts
Construction/Upgrading of Aeromedical Centre Main Building & Perimetrer Fence | NCAT/WKS/NCB/2010/001 | LOT 1 | 140,000,000.00 | NCB |  | Post Qualification | PTB | 2-16FEB2010 | 16FEB-1MAR2010 | N/A | 1 - 14 MAR2011 | 12 APR 2011 | 12-26APR 2011 | 26 APR- 10 May 2011 | 140000000 |  | 12-26AUG 2011 | 26 AUG -2SEP 2011 |  | 20/03/2012 | 31 MARCH 2012 | 140000000 | Engr. Abdullahi | Dr. E.Shittu
N/A
Purchase and Installation of Aerodynamic Trainer System (On-Going) | NCAT/WKS/DC/2010/002 | LOT 2 | 43,450,000.00 | DC | 38750000 | Post Qualification | PTB | 17JAN-2FEB2010 | 2 - 16FEB2010 | N/A | 1 - 14 MAR2010 | 12 APR 2010 | 12-26APR 2010 | 26 Apr- 10 May 2010 |  |  | 12 -26-AUG-2010 | [5 empty] | Engr.Abdullahi/SA | Engr. L.Tachio
[8 empty] | 31 MAR 2010 | 11 MAY 2010 |  | 08 JUN- 13 JUL 2010 | 13-JUL-2010 | 13-27 JUL-2010 |  | 43450000 | N/A | 6 OCT 2010 | 6-13OCT2010 | 30 OCT 2010 | 15 APR 2011 | 15MAY 2011 | 43450000
Purchase and Installation of Gas Turbine Engine Trainer (On-Going) | NCAT/WKS/DC/2010/007 | LOT 3 | 70,140,000.00 | DC | 64560000 | Post Qualification | PTB | 17JAN-2FEB2010 | 06 APR- 17 APR 2010 | N/A | 18 MAY- 29 JUN 2010 | 29-JUN-2010 | 1 JUL- 18 JUL 2010 | 19 JUL- 30 JUL 2010 |  | N/A | 12-26-AUG-2010 | 14 AUG- 20 AUG 2010 |  |  | 31 MARCH 2011 |  | Engr. Abdullahi/SA | Engr. L.Tachio
[8 empty] | 31-MAR-2010 | 11-MAY-2010 | N/A | 08 JUN- 13 JUL 2010 | 13-JUL-2010 | 13-27 JUL-2010 | 27JUL -11AUG2010 | 70140000 |  | 6 OCT 2010 | 6 -13 OCT 2010 | 30-OCT-2010 | 15 APR 2011 | 15 MAY 2011 | 70140000
Purchase and Installation of Avionuics System Trainer (On-Going) | NCAT/WKS/DC/2010/008 | LOT 4 | 39,550,000.00 | DC | 34056000 | Post Qualification | PTB | 17JAN-2FEB2010 | 06 APR- 17 APR 2010 | N/A | 18 MAY- 29 JUN 2010 | 29-JUN-2010 | 1 JUL- 18 JUL 2010 | 19 JUL- 30 JUL 2010 |  | N/A | 12-26-AUG-2009 | 14 AUG- 20 AUG 2009 |  |  | 31 MARCH 2011 |  | Engr. Abdullahi | Engr. L.Tachio
[8 empty] | 31MAR2010 | 1-14 APR 2010 |  | 08 JUN- 13 JUL 2010 | 13-JUL-2010 | 13-27 JUL-2010 | 27JUL -11AUG2010 | 39550000 |  | 6 OCT 2010 | 6 - 13 OCT 2010 | 30 OCT 2010 | 15 APR 2011 | 15 MAY 2011 | 39550000
Construction of perimeter fence for Aircraft Navigational Station,Layin Zomo - Zaria | NCAT/WKS/NCB/2011/011 | LOT 1 | 20,000,000.00 | NCB |  | POST-Qualification | PTB | 17JAN-2FEB2011 | 06 APR - 17 APR 2011 | N/A | 18 MAY - 29 JUN 2011 | 29 JUN 2011 | 1JUN -18JUL2011 | 19JUL-30JUL2011 | 20000000 | N/A | 1 - 14 AUG 2011 | 14 -30 AUG 2011 | 19 SEP 2011 | 15 MAR 2012 | 31 APR2012 | 20000000 | Engr. Abdullahi | Aih. S.T.Yahaya
Rehabilitation/Construction of College Road Network & Drainages | NCAT/WKS/NCB/2011/002 | LOT 2 | 275,992,880.50 | NCB | 30000000 | Post Qualification | MTB | 24 MAR- 5 APR 2010 | 06 APR- 17 APR 2011 | N/A | 18 MAY- 29 JUN 2011 | 29-JUN-2011 | 1 JUL- 18 JUL 2011 | 19 JUL- 30 JUL 2011 | 275,992,880.50 | N/A | 1 AUG- 13 AUG 2011 | 14 AUG- 20 AUG 2011 | 13 SEP 2011 | 13 APR 2012 | 13 JUN 2012 | 275992880.5 | Engr. Abdullahi | G.C Onugha
Construction of Flying School First Floor Classroom Block | NCAT/WKS/NCB/2011/003 | LOT 3 | 90,000,000.00 | NCB |  | Post Qualification | PTB | 24 MAR- 5 APR 2011 | 06 APR- 17 APR 2011 | N/A | 18 MAY- 29 JUN 2011 | 29-JUN-2011 | 1 JUL- 18 JUL 2011 | 19 JUL- 30 JUL 2011 | 90000000 | N/A | 1 AUG- 13 AUG 2011 | 14 AUG- 20 AUG 2011 | 27 AUG 2011 | 13 OCT 2011 | 13 NOV 2011 | 90000000 | Engr. Abdullahi | Capt. S.Caulcrick
Supply and Installation of ADS-B Base Station and Airborne Equipment(on-going) | NCAT/WKS/DC/2010/004 | LOT 4 | 59,803,322.00 | DC | 55638400 | Post Qualification | PTB | 17JAN-2FEB2010 | 06 APR- 17 APR 2010 | N/A | 18 MAY- 29 JUN 2010 | 29-JUN-2010 | 1 JUL- 18 JUL 2010 | 19 JUL- 30 JUL 2010 |  | N/A | 1 AUG- 13 AUG 2011 | 14 AUG- 20 AUG 2011 | 27 AUG 2011 | 13 OCT 2011 | 13 NOV 2011 |  | Engr. Tijani | Alh. S.T.Yahaya
[8 empty] | 31MAR2010 | 1-14 APR 2010 |  | 8JUN-13JUL 2010 | 13 JUL 2010 | 13-27 JUL-2010 | 27JUL -11AUG2010 | 59803322 |  | 6 OCT 2010 | 6 -13 OCT 2010 | 30 OCT 2010 | 15 APR 2011 | 15 MAY 2011 | 59803322
Completion of Construction of Library Complex (On-Going) | NCAT/WKS/NCB/2009/001 | LOT 1 | 231,420,781.23 | NCB | 44460501 | Post Qualification | PTB | 2-16FEB2009 | 16FEB-1MAR2009 | N/A | 1 - 14 MAR2009 | 12 APR 2009 | 12-26APR 2009 | 26 APR- 10 May 2009 | 231420781.23 |  |  |  |  | 20/03/2011 | 31 MARCH 2011 | 231420781.23 | Engr. Abdullahi | E. Gandu
[11 empty] | 18JUL-29AU2009 | 29 AUG 2009 | 1- 18 SEP 2009 | 8 OCT 2009 |  | 6 APRIL 2002 | 8-OCT-2009 (Re-awarded) | 8/02/2010 | 4/05/2010
Completion of Construction of College Auditorium (On-Going) | NCAT/WKS/NCB/2009/002 | LOT 2 | 328,644,078.00 | NCB | 83262735 | Post Qualification | PTB | 17JAN-2FEB2009 | 2 - 16FEB20009 | 16FEB-1MAR2009 | 1 - 14 MAR2009 | 12 APR 2009 | 12-26APR 2009 | 26 Apr- 10 May 2009 | 328644078 |  |  |  |  | 05/12/2011 | 31 JAN 2012 | 328644078 | Engr.Abdullahi/SA | G.C Onugha
[14 empty] | 14 DEC 2009 |  | 6 /4/2002 | 14 DEC2009(Re-awarded) | 4 MAR 2010 | 8 JUN 2010
Construction and Furnishing of Students Hostel BLOCK A (On-Going) | NCAT/WKS/NCB/2009/007 | LOT 3 | 225,943,799.81 | NCB | 27574198 | Post Qualification | PTB | 24 MAR- 5 APR 2009 | 06 APR- 17 APR 2009 | N/A | 18 MAY- 29 JUN 2009 | 29-JUN-2009 | 1 JUL- 18 JUL 2009 | 19 JUL- 30 JUL 2009 | 225943799.81 | N/A | 1 AUG- 13 AUG 2009 | 14 AUG- 20 AUG 2009 |  | 10/03/2011 | 31 MARCH 2011 | 225943799.81 | Engr. Abdullahi/SA | G.C Onugha
[8 empty] | 31-MAR-2009 | 11-MAY-2009 | N/A | 08 JUN- 13 JUL 2009 | 13-JUL-2009 | 13-JUL-2009 | 27-JUL-2009 | 225943799.81 |  | 26-AUG-2009 | 2-SEP-2009 | 07-OCT-2009
Construction and Furnishing of Classroom (On-Going) | NCAT/WKS/NCB/2009/008 | LOT 4 | 92,306,731.31 | NCB | 44128007 | Post Qualification | PTB | 24 MAR- 5 APR 2009 | 06 APR- 17 APR 2009 | N/A | 18 MAY- 29 JUN 2009 | 29-JUN-2009 | 1 JUL- 18 JUL 2009 | 19 JUL- 30 JUL 2009 | 92306731.31 | N/A | 1 AUG- 13 AUG 2009 | 14 AUG- 20 AUG 2009 |  | 22/02/2011 | 31 MARCH 2011 | 92306731.31 | Engr. Abdullahi | H.O Toluhi
[11 empty] | 21 APR- 01 JUN 2009 | 01-JUN-2009 | 01-JUN-2009 | 01-JUL-2009 | 92306731.31 |  | 26-AUG-2009 | 05-SEP-2009 | 12-OCT-2009
Resurfacing and Extension of Runway and Taxi way | NCAT/WKS/NCB/2011/001 | LOT 1 | 2,200,000,000.00 | NCB | 217787382 | Pre-Qualification | MTB | 8 - 22 AUG 2011 | 22 AUG - 5 SEP 2011 | 8 - 22 AUG 2011 | 5 SEP - 3 OCT 2011 | 3 OCT 2011 | 3 - 17 OCT 2011 | 17 - 30 OCT 2011 | 2200000000 | 7 - 21 NOV 2011 | 21 - 28 NOV 2011 | 5 DEC 2011 | 19 DEC 2011 | 15 DEC 2012 | 31 DEC 2012 | 2200000000 | Engr. Abdullahi | Capt S. Caulcrick
Construction and Furnishing of Student Hostel BLOCK B | NCAT/WKS/NCB/2011/002 | LOT 2 | 275,992,880.50 | NCB | 27574198 | Post Qualification | PTB | 24 MAR- 5 APR 2011 | 06 APR- 17 APR 2011 | N/A | 18 MAY- 29 JUN 2011 | 29-JUN-2011 | 1 JUL- 18 JUL 2011 | 19 JUL- 30 JUL 2011 | 45,150,786.00 | N/A | 1 AUG- 13 AUG 2011 | 14 AUG- 20 AUG 2011 | 13 SEP 2011 | 13 APR 2012 | 13 JUN 2012 | 275992880.5 | Engr. Abdullahi/SA | G.C Onugha
Purchase and Installation of Programmable Controller Laboratory | NCAT/WKS/NCB/2011/003 | LOT 3 | 23,004,230.00 | NCB | 16204230 | Post Qualification | FEC | 24 MAR- 5 APR 2011 | 06 APR- 17 APR 2011 | N/A | 18 MAY- 29 JUN 2011 | 29-JUN-2011 | 1 JUL- 18 JUL 2011 | 19 JUL- 30 JUL 2011 | 23004230 | N/A | 1 AUG- 13 AUG 2011 | 14 AUG- 20 AUG 2011 | 27 AUG 2011 | 13 OCT 2011 | 13 NOV 2011 | 23004230 | Engr. Isa Danjuma | W.B Disu
Completion of AVNET project | NCAT/WKS/NCB/2011/004 | LOT 4 | 25,000,000.00 | NCB | 13503525 | Post Qualification | FEC | 24 MAR- 5 APR 2011 | 06 APR- 17 APR 2011 | N/A | 18 MAY- 29 JUN 2011 | 29-JUN-2011 | 1 JUL- 18 JUL 2011 | 19 JUL- 30 JUL 2011 | 16000000 | N/A | 1 AUG- 13 AUG 2011 | 14 AUG- 20 AUG 2011 | 27 AUG 2011 | 13 OCT 2011 | 13 NOV 2011 | 25000000 | Engr. Bassey | H.O. Toluhi
Rehabilitation of 3rd Hangar | NCAT/WKS/NCB/2011/005 | LOT 5 | 479,080,980.00 | NCB | 49844678 | Pre-Qualification | MTB | 24 OCT- 5 NOV 2011 | 06 NOV- 17 NOV 2011 | N/A | 18 NOV- 29 DEC 2011 | 29-DEC-2011 | 1 JAN- 18 JAN 2012 | 19 JAN- 30 JAN 2012 | 479080980 | N/A | 1 FEB- 13 FEB 2012 | 14 FEB- 20 FEB 2012 | 20 MAR 2012 | 31 JUL. 2012 | 31 AUG. 2012 | 479080980 | Engr. Abdullahi | C. Manshop
Total Cost | [14 empty] | 3374220406.35 | [6 empty] | 3614062500.85
Supply and Installation of Airfield Lighting- CAT1 | NCAT/WKS/NCB/2011/006 | LOT 4 | 211,750,000.00 | NCB | 108204230 | Post Qualification | PTB | 24 MAR- 5 APR 2011 | 06 APR- 17 APR 2011 | N/A | 18 MAY- 29 JUN 2011 | 29-JUN-2011 | 1 JUL- 18 JUL 2011 | 19 JUL- 30 JUL 2011 | 211750000 | N/A | 1 AUG- 13 AUG 2011 | 14 AUG- 20 AUG 2011 | 20 SEP 2011 | 13 MAR 2012 | 13 NOV 2012 | 211750000 | Engr. John Ali | W.B. Disu
Purchase and Installation of AS Trainer for AME School | NCAT/WKS/DC/2011/002 | LOT 5 | 53196889 | NCB | 53,196,589.00 | Post Qualification | PTB | 24 MAR- 5 APR 2011 | 06 APR- 17 APR 2011 | N/A | 18 MAY- 29 JUN 2011 | 29-JUN-2011 | 1 JUL- 18 JUL 2011 | 19 JUL- 30 JUL 2011 |  | N/A | 1 AUG- 13 AUG 2011 | 14 AUG- 20 AUG 2011 | 13 SEP 2011 | 13 OCT 2011 | 13 NOV 2011 | 53198889 | Engr. M.A.Yusuf | Engr. L. Tachio
Automation of AIS Simulator | NCAT/WKS/DC/2011/004 | LOT 6 | 33005000 | NCB | 29,707,755.00 | Post Qualification | PTB | 24 MAR- 5 APR 2011 | 06 APR- 17 APR 2011 | N/A | 18 MAY- 29 JUN 2011 | 29-JUN-2011 | 1 JUL- 18 JUL 2011 | 19 JUL- 30 JUL 2011 |  | N/A | 1 AUG- 13 AUG 2011 | 14 AUG- 20 AUG 2011 | 13 SEP 2011 | 13 OCT 2011 | 13 NOV 2011 | 33005000 | Mrs. Adekola | Alh. S.T. Yahaya
Completion of Construction of College Perimeter Fence(on-going) | NCAT/WKS/NCB/2010/009 | LOT 5 | 976,492,527.29 | NCB |  | Pre-Qualification | MTB | 22 FEB - 10 MAR 2010 | N/A | N/A | 25 MAR- 7 MAY 2010 | 7 MAY 2010 | 8 MAY- 30 MAY 2010 |  | 976,492,527.29 | N/A | 7 - 14 FEB2011 | 14 - 21 FEB 2011 | 7 MAR 2011 | 6 JUL 2012 | 5 AUG 2012 | 976492527.29 | Engr. Audu Ali | Engr. Abdullahi
[10 empty] | 29 OCT-12 NOV 2010 | 29 OCT- 26 NOV 2010 | 26 NOV 2010 | 10- DEC- 2010 | 12 JAN 2011

## Avitn_NIMET
NIGERIAN METEOROLOGICAL AGENCY
Procurement Plan - Consultancy
Ministry/Department/Agency: Nigerian Meteorological Agency
Budgetary Year: 2011 -- Consultancy Service | [8 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: H.O. Abdulkareem |  | Contract Type |  |  | Preparation Request for Proposals |  |  |  | Short List |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [6 empty] | Contract Finalization |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | No-objection Date | FEC Approval | Contract Amount in Naira | Contract Offer | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks |  | 1- 2 wk | 2 wks
List of Contracts
PROCUREMENT AND INSTALLATION OF LIDAR BASED WINDSHEAR ALERT SYSTEM FOR ABUJA, KANO, LAGOS & PH (in 3 years) | QBS | Man Month Rate | 10000000 | PTB | 6 - 27 Apr,11 | 27Apr - 4May, 11 | 11-15May, 11 | 16-29 May, 11 | 29 May, 11 | 30 May, 11 | 2 Jun, 2011 | 30 Jun, 11 | 8 Aug, 11 | 15 Aug, 11 | NA | NA | 22 Aug, 11 | NA | NA | 10000000 | 25 Aug, 11 | 1 Sept, 11 | ON DEMAND | Monthly | 1 Dec, 11 | 10000000 | Engr C.E. Ummunnakwe | Mr. I.D. Nnodu
Total Cost |  |  | 10000000 | [16 empty] | 10000000 | [5 empty] | 10000000
Procurement Plan - Consultancy Service (IGR)
Budgetary Year: 2010 |  |  |  |  | Budgetary Year: 2010 |  |  |  | Request for Expression of Interest (when required)
Desk Officer/Contact #: Haleed S. Dass |  | Contract Type |  |  | Preparation Request for Proposals |  |  |  | Short List |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [6 empty] | Contract Finalization |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | No-objection Date | FEC Approval | Contract Amount in Naira | Contract Offer | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks |  | 1- 2 wk | 2 wks
List of Contracts
Capital Training Program (Local) | QBS | Time Base | 129754290 | PTB | 6 - 27 Apr,10 | 27 Apr - 4 May, 10 | 11-15May, 10 | 16-29 May, 10 | 29 May, 10 | 30 May, 10 | 2 Jun, 2010 | 30 Jun, 10 | 8 Aug, 10 | 15 Aug, 10 | NA | NA | 22 Aug, 10 | NA | NA | 129754290 | 25 Aug, 10 | 1 Sept, 10 | ON DEMAND | Monthly | 1 Dec, 10 | 129754290 | Procurement Dept. | Director Admin & Supply
Capital Training Program (Foreign) | QBS | Time Base | 161,776,616 | PTB | 6 - 27 Apr,10 | 27 Apr - 4 May, 10 | 11-15May, 10 | 16-29 May, 10 | 29 May, 10 | 30 May, 10 | 2 Jun, 2010 | 30 Jun, 10 | 8 Aug, 10 | 15 Aug, 10 | NA | NA | 22 Aug, 10 | NA | NA | 161,776,616 | 25 Aug, 10 | 1 Sept, 10 | ON DEMAND | Monthly | 1 Dec, 10 | 161,776,616 | Procurement Dept. | Director Admin & Supply
Consultancy for ICT master plan. | QBS | Time Base | 35000000 | PTB | 6 - 27 Apr,10 | 27 Apr - 4 May, 10 | 11-15May, 10 | 16-29 May, 10 | 29 May, 10 | 30 May, 10 | 2 Jun, 2010 | 30 Jun, 10 | 8 Aug, 10 | 15 Aug, 10 | NA | NA | 22 Aug, 10 | NA | NA | 35000000 | 25 Aug, 10 | 1 Sept, 10 | ON DEMAND | Monthly | 1 Dec, 10 | 35000000 |  | Director Engineering and Technical Services
Equipment, Building and Motor Vehicle Insurance | QBS | Time Base/Value | 35000000 | PTB | 6 - 27 Apr,10 | 27 Apr - 4 May, 10 | 11-15May, 10 | 16-29 May, 10 | 29 May, 10 | 30 May, 10 | 2 Jun, 2010 | 30 Jun, 10 | 8 Aug, 10 | 15 Aug, 10 | NA | NA | 22 Aug, 10 | NA | NA | 35000000 | 25 Aug, 10 | 1 Sept, 10 | ON DEMAND | Monthly | 1 Dec, 10 | 35000000 |  | Director Legal services
International Obligations; | Fees | Lumpsum | 15400000 | PTB | 6 - 27 Apr,10 | 27 Apr - 4 May, 10 | 11-15May, 10 | 16-29 May, 10 | 29 May, 10 | 30 May, 10 | 2 Jun, 2010 | 30 Jun, 10 | 8 Aug, 10 | 15 Aug, 10 | NA | NA | 22 Aug, 10 | NA | NA | 15400000 | 25 Aug, 10 | 1 Sept, 10 | ON DEMAND | Monthly | 1 Dec, 10 | 15400000 |  | Director Weather Forecasting Services
Consultancy for production of Aviation Weather Guide | QBS | Time Base | 45, 000, 000 | PTB | 6 - 27 Apr,10 | 27 Apr - 4 May, 10 | 11-15May, 10 | 16-29 May, 10 | 29 May, 10 | 30 May, 10 | 2 Jun, 2010 | 30 Jun, 10 | 8 Aug, 10 | 15 Aug, 10 | NA | NA | 22 Aug, 10 | NA | NA | 45, 000, 000 | 25 Aug, 10 | 1 Sept, 10 | ON DEMAND | Monthly | 1 Dec, 10 | 45, 000, 000 |  | Director Weather Forecasting Services
Total Cost |  |  | 129754290 | [16 empty] | 129754290 | [5 empty] | 129754290
#REF!
Budgetary Year: 2011 --- Goods | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN
Desk Officer/Contact #: H.O. Abdulkareem |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
add 2 wks
List of Contracts
PROCUREMENT OF CONVENTIONAL EQUIPMENT FOR MET STATIONS NATIONWIDE | 13 | 4 | 170307500 | National Competitive Bidding | N/A | Parastatal | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 152990500 | N/A | N/A | N/A | N/A | 4tht - 30th Oct | 4th - 15th Nov. | Engr. S.A. Aderinto | Mr. I.D.Nnodu
Total Cost |  |  | 170307500 | [10 empty] | 152990500
#REF!
Procurement Plan - Goods (IGR) | [8 empty] | Procurement Plan - Goods
Budgetary Year: 2010 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN
Desk Officer/Contact #: Halled S. Dass |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
add 2 wks
List of Contracts
Procurement of Teaching Aids/Equipment for RTC | 2 | 2 | 10000000 | National Competative Bidding | N/A | Parstatal Tendar Board | N/A | N/A | N/A | 1st March -26th March. | 1st - March -9th April | 13th - 19st April | 20th - 27th April | 10000000 | N/A | 25th April - 15th May | 19th - 23 May | On Request | 4tht - 30th Oct | 4th - 15th Oct. | Procurement Department | Director of Research and Training
Procurement of Conventional Instrument for 54 Met-stations nation-wide | 12 | 12 | 81000000 | National Competative Bidding | N/A | Parstatal Tendar Board | N/A | N/A | N/A | 1st March -26th March. | 1st - March -9th April | 13th - 19st April | 20th - 27th April | 81000000 | N/A | 25th April - 15th May | 19th - 23 May | On Request | 4tht - 30th Oct | 4th - 15th Oct. | Procurement Department | Director Weather Forecasting Services
Procurement of 15Nos. Operational Vehicles: | 5 | 5 | 122000000 | National Competative Bidding | N/A | Parstatal Tendar Board | N/A | N/A | N/A | 1st March -26th March. | 1st - March -9th April | 13th - 19st April | 20th - 27th April | 122000000 | N/A | 25th April - 15th May | 19th - 23 May | On Request | 4tht - 30th Oct | 4th - 15th Oct. | Procurement Department | Director Admin and Supply
Procurement of Office Equipment for NIMET stations nation-wide | 12 | 12 | 90000000 | National Competative Bidding | N/A | Parstatal Tendar Board | N/A | N/A | N/A | 1st March -26th March. | 1st - March -9th April | 13th - 19st April | 20th - 27th April | 90000000 | N/A | 25th April - 15th May | 19th - 23 May | On Request | 4tht - 30th Oct | 4th - 15th Oct. | Procurement Department | Director Admin and Supply
Procurement of Furniture and Fittings | 15 | 15 | 70000000 | National Competative Bidding | N/A | Parstatal Tendar Board | N/A | N/A | N/A | 1st March -26th March. | 1st - March -9th April | 13th - 19st April | 20th - 27th April | 70000000 | N/A | 25th April - 15th May | 19th - 23 May | On Request | 4tht - 30th Oct | 4th - 15th Oct. | Procurement Department | Director Admin and Supply
Total Cost |  |  | 373000000 | [10 empty] | 373000000
#REF!
Procurement Plan - Works
Budgetary Year: 2011 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: Engr. H.O. Abdulkareem, 08035029300 |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation |  |  |  | 08035029300
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | Contract Amount Certified in N | FEC/ MTB Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
[6 empty] | add 2 wks | [8 empty] | Actual
List of Contracts
National Weather Forecasting and Climate Research Centre, Abuja (under the National Weather Observation and Forecasting Infrastructure initiative) -Infrastructure and Equipment | 1 | 1 | BOQ | National Competative Bidding | 282,315,566.00 | Post Qualification | Ministerial Tender Board | N/A | N/A | N/A | 7th Feb -7th March. | 7th March | 8-15th March | 16th - 23rd March | Plan | 282,315,566.00 | 24th March - 21st April | 22nd April - 29th April | 2nd May -9th May | 10th - 17th May | 31st Oct. | 1st - 30th Nov. | 282,315,566.00 | Engr. H.O. Abdulkareem | Mr I.D. Nnodu
Actual
PROCUREMENT AND INSTALLATIONS OF 4NOS. UPPER AIR SOUNDING EQUIPMENT & 7NOS. CONSUMMABLES. (on-going) | 2 | 11 | BOQ | National Competative Bidding | 46011921 | N/A | Parastatal Tender Board | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 180267500 | N/A | N/A | N/A | N/A | 28 Feb. | 14th March |  | Engr. C. E. Ummunnakwe | Mr I.D. Nnodu
[15 empty] | Actual | 167411920.75 | [6 empty] | 167411920.75
PROCUREMENT AND INSTALLATION OF 8NOS. INTERGRATED WEATHER OBSERVING DISPLAY SYSTEMS (AWODS) | 3 | 2 | BOQ | National Competative Bidding | 261108709 | N/A | Parastatal Tender Board | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 480535679.43 | N/A | N/A | N/A | N/A | 28 Feb. | 14th March |  | Engr. S.A. Aderinto | Mr I.D. Nnodu
[16 empty] | 474108703.76 | [6 empty] | 474108703.76
PROCUREMENT AND INSTALLATION OF WINDSHEAR ALERT SYSTEM (New) | 4 | 3 | BOQ | National Competative Bidding | 506720399.2 | Post Qualification | Parastatal Tender Board | N/A | N/A | N/A | 7th Feb -7th March. | 7th March | 8-15th March | 16th - 23rd March | Plan | 504900000 | N/A | 24th March - 31st March | 1st April-8th April | 11th - 18th April | 30 Sept | 1st - 31stOct. | 504900000 | Engr. S.A. Aderinto | Mr I.D. Nnodu
PROCUREMENT AND INSTALLATION OF SADIS (SATELLITE DIST SYSTEM AND ACCESSORIES) (On-going) | 5 | 6 | BOQ | National Competative Bidding | 72720000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 108720000 | N/A | N/A | N/A | N/A | 28 Feb. | 14th March |  | Engr. C. E. Ummunnakwe | Mr I.D. Nnodu
[16 empty] | 108590000 | [6 empty] | 108590000
CONSTRUCTION OF MARINE/ PORT MET STATIONS & ENCLOSURES. (On-going) | 6 | 3 | BOQ | National Competative Bidding | 30000673 | N/A | Parastatal Tender Board | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 50555850 | N/A | N/A | N/A | N/A | 28 Feb. | 14th March |  | Engr. H.O. Abdulkareem | Mr I.D. Nnodu
[15 empty] | Actual | 42246300 | [6 empty] | 42246300
CONSTRUCTION OF 7Nos. NEW SYNOPTIC STATIONS (New) | 7 | 7 | BOQ | National Competative Bidding | 114657553 | Post Qualification | Parastatal Tender Board | N/A | N/A | N/A | 7th Feb -7th March. | 7th March | 8-15th March | 16th - 23rd March | Plan | 114657553 | N/A | 24th March - 31st March | 1st April-8th April | 11th - 18th April | 30 Sept | 1st - 31st Oct. | 114657553 | Engr. H.O. Abdulkareem | Alhaji Garba Adamu
[15 empty] | Actual | [9 empty] | 0
PROCUREMENT OF 6NO. THUNDERSTORM/ LIGHTING DETECTORS (2per lot) (On-going) | 8 | 6 | BOQ | National Competative Bidding | 56400000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 53100000 | N/A | N/A | N/A | N/A | 28 Feb. | 14th March |  | Engr. C. E. Ummunnakwe | Mr I.D. Nnodu
[15 empty] | Actual | 53100000 | [6 empty] | 53100000
CONSTRUCTION AND EQUIPPING CENTRAL INSTRUMENT MAINTAINANCE WORKSHOP AT ABUJA. | 9 | 2 | BOQ | National Competative Bidding | 134477270 | N/A | Parastatal Tender Board | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 275552269.5 | N/A | N/A | N/A | N/A | 28 Feb. | 14th March |  | Engr. H.O. Abdulkareem | Engr. S.A. Aderinto
[15 empty] | Actual | 257491700 | [6 empty] | 257491700
PROCUREMENT & INSTALLATION OF METEOFACTORY SYSTEM | 10 | 1 | BOQ | National Competative Bidding | 350212500 | Post Qualification | Parastatal Tender Board | N/A | N/A | N/A | 7th Feb -7th March. | 7th March | 8-15th March | 16th - 23rd March | Plan | 350212500 | N/A | 24th March - 31st March | 1st April-8th April | 11th - 18th April | 30 Sept | 1st - 31st Oct.z | 350212500 | Engr. C. E. Ummunnakwe | Mr I.D. Nnodu
Actual
Total Cost | [14 empty] | Plan
Actual
Budgetary Year: 2011 --- Works | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: Engr. H.O. Abdulkareem, 08035029300 |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation |  |  |  | 08035029300
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
PROCUREMENT OF AUTOMATIC WEATHER OBSERVATION SYSTEM FOR 5Nos. MET STATIONS NATIONWIDE (On-going) | 11 | 5 | BOQ | National Competative Bidding | 75120000 | N/A | Parastatal Tender Board | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 48890000 | N/A | N/A | N/A | N/A | 28 Feb. | 14th March |  | Engr. S.A. Aderinto | Mr I.D. Nnodu
[8 empty] | Actual | [8 empty] | 48890000 | [6 empty] | 48890000
PROCUREMENT OF AUTOMATIC WEATHER OBSERVATION SYSTEM FOR 2Nos. MET STATIONS NATIONWIDE (New) | 11 | 3 | BOQ | National Competative Bidding | 75120000 | Post Qualification | Parastatal Tender Board | Plan | N/A | N/A | N/A | 7th Feb -7th March. | 7th March | 8-15th March | 16th - 23rd March | Plan | 29334000 | N/A | 24th March - 31st March | 1st April-8th April | 11th - 18th April | 30 Sept | 1st - 31st Nov | 29334000 | Engr. S.A. Aderinto | Mr I.D. Nnodu
Actual
PROCUREMENT AND INSTALLATION OF 3NO AIR QUALITY & OZONE MONITORING EQUIPMENT FOR THREE ZONES (New) | 12 | 3 | BOQ | National Competative Bidding | 373621684 | Post Qualification | Parastatal Tender Board | Plan | N/A | N/A | N/A | 7th Feb -7th March. | 7th March | 8-15th March | 16th - 23rd March | Plan | 168768750 | N/A | 24th March - 31st March | 1st April-8th April | 11th - 18th April | 30 Sept | 1st - 31st Oct | 168768750 | Engr. S.A. Aderinto | Mr I.D. Nnodu
[8 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF SOLAR POWER SYSTEMS FOR 25 SYNOPTIC STATIONS | 13 | 1 | BOQ | National Competative Bidding | 105073320 | Post Qualification | Parastatal Tender Board | Plan | N/A | N/A | N/A | 7th Feb -7th March. | 7th March | 8-15th March | 16th - 23rd March | Plan | 105073320 | N/A | 24th March - 31st March | 1st April-8th April | 11th - 18th April | 30 Sept | 1st - 31st Oct. | 105073320 | Engr J. Ibekwe | Engr. S.A. Aderinto
[8 empty] | Actual | [7 empty] | Actual
PROCUREMENT AND INSTALLATION OF NUMERICAL WEATHER PREDICTION EQUIPMENT (CLUSTERS FOR MODELLING) (On - going) | 14 | 1 | BOQ | National Competative Bidding | 4329900 | N/A | Parastatal Tender Board | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 42129900 | N/A | N/A | N/A | N/A | 28 Feb. | 14th March |  | Dr EAfiesimama | Mr I.D. Nnodu
[8 empty] | Actual | [7 empty] | Actual | 38920400 | [6 empty] | 38920400
CONSTRUCTION OF 2 MARINE MET FORECAST OFFICE & ENCLOSURES (On - going) | 15 | 1 | BOQ | National Competative Bidding | 30000000 | N/A | Parastatal Tender Board | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 14290060 | N/A | N/A | N/A | N/A | 28 Feb. | 14th March |  | Engr. H.O. Abdulkareem | Mrs J.E Ukeje
[8 empty] | Actual | [7 empty] | Actual | 10773400 | [6 empty] | 10773400
CONSTRUCTION OF 2 MARINE MET FORECAST OFFICE & ENCLOSURES (New) | 15 | 1 | BOQ | National Competative Bidding | 30000000 | Post Qualification | Parastatal Tender Board | Plan | N/A | N/A | N/A | 7th Feb -7th March. | 7th March | 8-15th March | 16th - 23rd March | Plan | 14290060 | N/A | 24th March - 31st March | 1st April-8th April | 11th - 18th April | 30 Sept | 1st - 31st Oct. |  | Engr. H.O. Abdulkareem | Mrs J.E Ukeje
[8 empty] | Actual | [7 empty] | Actual
2NOS. VOLMET EQUIPMENT FOR 2 AREA CONTROLLERS (IKEJA & KANO) (On - going) | 16 | 6 | BOQ | National Competative Bidding | 63736709 | N/A | Parastatal Tender Board | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 59005988 | N/A | 24th March - 31st March | 1st April-8th April | 11th - 18th April | 30 Sept | 1st - 31st Oct. |  | Engr. C. E. Ummunnakwe | Mr I.D. Nnodu
[8 empty] | Actual | [7 empty] | Actual | 56133180 | N/A | N/A | N/A | N/A | 28 Feb. | 14th March | 56133180
PROCUREMENT AND INSTALLATION OF ATIS BROADCAST EQUIPMENTS FOR 1No AIRPORT: (New) | 16 | 1 | BOQ | National Competative Bidding | 63736709 | N/A | Parastatal Tender Board | Plan | N/A | N/A | N/A | 7th Feb -7th March. | 7th March | 8-15th March | 16th - 23rd March | Plan | 7584000 | N/A | 24th March - 31st March | 1st April-8th April | 11th - 18th April | 30 Sept | 1st - 31st Oct. | 7584000 | Engr. C. E. Ummunnakwe | Mr I.D. Nnodu
[8 empty] | Actual | [7 empty] | Actual
PROCUREMNT AND INSTALLATION OF 4NOS. WEATHER MONITORING SYSTEMS AND CONSUMABLES (DOPPLER WEATHER RADAR) (2NOS in 2011 and 2Nos in 2012) (New) | 17 | 1 | BOQ | International impetative Bidding | 97019543 | Pre Qualification | FEC | Plan | N/A | N/A | 7th Feb -21st Feb. | 21st Feb -21st March. | 21st March | 22nd March -1st April | 4th - 11th April | Plan | 1351000526 | 18th April - 16th May | 17th May - 24th May | 25th May- 1st June | 2nd June - 16th June | 31st May | 1st - 29th June | 1351000526 | Engr. S.A. Aderinto | Mr I.D. Nnodu
[8 empty] | Actual | [7 empty] | Actual
Total Cost | [7 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Procurement Plan - Works
Budgetary Year: 2010 --- Works (IGR) | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: Haleed S. Dass |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
add 2 wks
List of Contracts
Construction of New WMO-RTC Class Room /Library Blocks | 1 | 1 | BOQ | National Competative Bidding | 150000000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | 26th April to 4th June | 26th April to 4th June | 7th - 18st June | 21th - 30th June | 150000000 | N/A | 1st - 8th July | 9th -16th July | On Request | 30 November | 1st - 10th Dec. | 150000000 | Procurement Dept. | Director Research and Training
Renovation of Oshodi Operational Headquarters Complex | 1 | 1 | BOQ | National Competative Bidding | 50000000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | 26th April to 4th June | 26th April to 4th June | 7th - 18st June | 21th - 30th June | 50000000 | N/A | 1st - 8th July | 9th -16th July | On Request | 30 November | 1st - 10th Dec. | 50000000 | Procurement Dept. | Director Research and Training
Equipping and furnishing the newly renovated RTC Blocks, Conference Centre and RTC Classrooms | 3 | 3 | BOQ | National Competative Bidding | 35000000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | 26th April to 4th June | 26th April to 4th June | 7th - 18st June | 21th - 30th June | 35000000 | N/A | 1st - 8th July | 9th -16th July | On Request | 30 November | 1st - 10th Dec. | 35000000 | Procurement Dept. | Director Research and Training
Construction of National Weather Forecast and Research Centre Complex at Abuja (for augmenting the actual total contract sum) | 1 | 1 | BOQ | National Competative Bidding | 55000000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | 26th April to 4th June | 26th April to 4th June | 7th - 18st June | 21th - 30th June | 55000000 | N/A | 1st - 8th July | 9th -16th July | On Request | 30 November | 1st - 10th Dec. | 55000000 | Procurement Dept. | Director Weather Forecasting Services
Construction of 2Nos. Of New 33m Tower for Doppler Weather Radar Domes at Oshodi and Kano | 2 | 2 | BOQ | National Competative Bidding | 35000000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | 26th April to 4th June | 26th April to 4th June | 7th - 18st June | 21th - 30th June | 35000000 | N/A | 1st - 8th July | 9th -16th July | On Request | 30 November | 1st - 10th Dec. | 35000000 | Procurement Dept. | Director Weather Forecasting Services
Procurement and Installation of 3Nos. new RETIM 2000 System for Ikeja, Portharcourt, Kano and upgrading of Abuja type RT 2000. | 4 | 4 | BOQ | National Competative Bidding | 140000000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | 26th April to 4th June | 26th April to 4th June | 7th - 18st June | 21th - 30th June | 140000000 | N/A | 1st - 8th July | 9th -16th July | On Request | 30 November | 1st - 10th Dec. | 140000000 | Procurement Dept. | Director Weather Forecasting Services
Automation of NIMET Accounting System (General Ledger, Payroll and stores) | 1 | 1 | BOQ | National Competative Bidding | 30000000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | 26th April to 4th June | 26th April to 4th June | 7th - 18st June | 21th - 30th June | 30000000 | N/A | 1st - 8th July | 9th -16th July | On Request | 30 November | 1st - 10th Dec. | 30000000 | Procurement Dept. | Director Finance and Accounts
Procurement and Installation of Cli-data (WMO Prescribed Software and other software for weather data processing). | 3 | 3 | BOQ | National Competative Bidding | 34000000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | 26th April to 4th June | 26th April to 4th June | 7th - 18st June | 21th - 30th June | 34000000 | N/A | 1st - 8th July | 9th -16th July | On Request | 30 November | 1st - 10th Dec. | 34000000 | Procurement Dept. | Director Weather Forecasting Services
Upgrade of IT infrastructure at computer Centre and Migration to WMO new Dbase management System at Oshodi-Lagos & Abuja | 2 | 2 | BOQ | National Competative Bidding | 15000000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | 26th April to 4th June | 26th April to 4th June | 7th - 18st June | 21th - 30th June | 15000000 | N/A | 1st - 8th July | 9th -16th July | On Request | 30 November | 1st - 10th Dec. | 15000000 | Procurement Dept. | Director Engineering and Tech Serv.
Rehabilitation of NIMET Complx at Stracham Street , Race Course, Lagos. | 2 | 2 | BOQ | National Competative Bidding | 60000000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | 26th April to 4th June | 26th April to 4th June | 7th - 18st June | 21th - 30th June | 60000000 | N/A | 1st - 8th July | 9th -16th July | On Request | 30 November | 1st - 10th Dec. | 60000000 | Procurement Dept. | Director Engineering and Tech Serv.
Procurement and Installation of Automated Data transfer and achieving system (e-Met) for 12Nos. New Stations | 1 | 1 | BOQ | National Competative Bidding | 45000000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | 26th April to 4th June | 26th April to 4th June | 7th - 18st June | 21th - 30th June | 45000000 | N/A | 1st - 8th July | 9th -16th July | On Request | 30 November | 1st - 10th Dec. | 45000000 | Procurement Dept. | Director Weather Forecasting Services
Procurement and Installation of Data transfer link system for linking Operational HQTR with MMIA and MM2 Pilot briefing room. | 1 | 1 | BOQ | National Competative Bidding | 5000000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | 26th April to 4th June | 26th April to 4th June | 7th - 18st June | 21th - 30th June | 5000000 | N/A | 1st - 8th July | 9th -16th July | On Request | 30 November | 1st - 10th Dec. | 5000000 | Procurement Dept. | Director Weather Forecasting Services
Establishment of 4Nos. Solar Radiation Monitoring Centres at Sokoto, Port-Harcourt, Enugu and Kano | 4 | 4 | BOQ | National Competative Bidding | 40000000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | 26th April to 4th June | 26th April to 4th June | 7th - 18st June | 21th - 30th June | 40000000 | N/A | 1st - 8th July | 9th -16th July | On Request | 30 November | 1st - 10th Dec. | 40000000 | Procurement Dept. | Director Weather Forecasting Services
Procurement of Conventional Instrument for 54 Met-stations nation-wide | 12 | 12 | BOQ | National Competative Bidding | 81000000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | 26th April to 4th June | 26th April to 4th June | 7th - 18st June | 21th - 30th June | 81000000 | N/A | 1st - 8th July | 9th -16th July | On Request | 30 November | 1st - 10th Dec. | 81000000 | Procurement Dept. | Director Weather Forecasting Services
Resuscitation of RANET Project | 1 | 1 | BOQ | National Competative Bidding | 20000000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | 26th April to 4th June | 26th April to 4th June | 7th - 18st June | 21th - 30th June | 20000000 | N/A | 1st - 8th July | 9th -16th July | On Request | 30 November | 1st - 10th Dec. | 20000000 | Procurement Dept. | Director Applied Met.
Construction of NIMET'S Zonal Office Ibadan | 1 | 1 | BOQ | National Competative Bidding | 35000000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | 26th April to 4th June | 26th April to 4th June | 7th - 18st June | 21th - 30th June | 35000000 | N/A | 1st - 8th July | 9th -16th July | On Request | 30 November | 1st - 10th Dec. | 35000000 | Procurement Dept. | Director Admin and Supply
Upgrading Agro-met Information Service | 1 | 1 | BOQ | National Competative Bidding | 10000000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | 26th April to 4th June | 26th April to 4th June | 7th - 18st June | 21th - 30th June | 10000000 | N/A | 1st - 8th July | 9th -16th July | On Request | 30 November | 1st - 10th Dec. | 10000000 | Procurement Dept. | Director Applied Met.
Rehabilitation of livestock Production section (Poultry) in Oshodi | 1 | 1 | BOQ | National Competative Bidding | 10000000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | 26th April to 4th June | 26th April to 4th June | 7th - 18st June | 21th - 30th June | 10000000 | N/A | 1st - 8th July | 9th -16th July | On Request | 30 November | 1st - 10th Dec. | 10000000 | Procurement Dept. | Dierctor Applied Met.
Resuscitation of Voluntary Observers scheme for Rainfall data Collection | 12 | 12 | BOQ | National Competative Bidding | 60000000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | 26th April to 4th June | 26th April to 4th June | 7th - 18st June | 21th - 30th June | 60000000 | N/A | 1st - 8th July | 9th -16th July | On Request | 30 November | 1st - 10th Dec. | 60000000 | Procurement Dept. | Director Applied Met.
Proc. & Inst. of Remote sensing and Geographical information system at Abuja &Lagos | 3 | 3 | BOQ | National Competative Bidding | 30000000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | 26th April to 4th June | 26th April to 4th June | 7th - 18st June | 21th - 30th June | 30000000 | N/A | 1st - 8th July | 9th -16th July | On Request | 30 November | 1st - 10th Dec. | 30000000 | Procurement Dept. | Director Applied Met.
Establishment of 2Nos National Pollution Monitoring Centres at Oshodi & Abuja | 2 | 2 | BOQ | National Competative Bidding | 40000000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | 26th April to 4th June | 26th April to 4th June | 7th - 18st June | 21th - 30th June | 40000000 | N/A | 1st - 8th July | 9th -16th July | On Request | 30 November | 1st - 10th Dec. | 40000000 | Procurement Dept. | Director Weather Forecasting Services
Development of Rainfall Iso-pluvial Maps and Development of dependable Basin Yield maps | 1 | 1 | BOQ | National Competative Bidding | 9000000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | 26th April to 4th June | 26th April to 4th June | 7th - 18st June | 21th - 30th June | 9000000 | N/A | 1st - 8th July | 9th -16th July | On Request | 30 November | 1st - 10th Dec. | 9000000 | Procurement Dept. | Director Applied Met.
Establishment of rainfall intensity Duration-frequency Curve project | 1 | 1 | BOQ | National Competative Bidding | 10000000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | 26th April to 4th June | 26th April to 4th June | 7th - 18st June | 21th - 30th June | 10000000 | N/A | 1st - 8th July | 9th -16th July | On Request | 30 November | 1st - 10th Dec. | 10000000 | Procurement Dept. | Director Applied Met.
Data quality Control and formatting program | 1 | 1 | BOQ | National Competative Bidding | 5000000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | 26th April to 4th June | 26th April to 4th June | 7th - 18st June | 21th - 30th June | 5000000 | N/A | 1st - 8th July | 9th -16th July | On Request | 30 November | 1st - 10th Dec. | 5000000 | Procurement Dept. | Director Weather Forecasting Services
National Drought, Flooding and Climate Change Monitoring Program | 3 | 3 | Lumpsum | National Competative Bidding | 40000000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | 26th April to 4th June | 26th April to 4th June | 7th - 18st June | 21th - 30th June | 40000000 | N/A | 1st - 8th July | 9th -16th July | On Request | 30 November | 1st - 10th Dec. | 40000000 | Procurement Dept. | Director Weather Forecasting Services
Procurement and Installation of 4Nos. Electrolytic Hydrogen Gas Generator (MP8) | 4 | 4 | BOQ | National Competative Bidding | 97279200 | N/A | Parastatal Tender Board | N/A | N/A | N/A | 26th April to 4th June | 26th April to 4th June | 7th - 18st June | 21th - 30th June | 97279200 | N/A | 1st - 8th July | 9th -16th July | On Request | 30 November | 1st - 10th Dec. | 97279200 | Procurement Dept. | Director Weather Forecasting Services
Rehabilitation of Mateo-Station at Ikeja | 2 | 2 | BOQ | National Competative Bidding | 20000000 | N/A | Parastatal Tender Board | N/A | N/A | N/A | 26th April to 4th June | 26th April to 4th June | 7th - 18st June | 21th - 30th June | 20000000 | N/A | 1st - 8th July | 9th -16th July | On Request | 30 November | 1st - 10th Dec. | 20000000 | Procurement Dept. | Director Weather Forecasting Services
Total Cost |  |  |  |  | 1161279200 | [9 empty] | 1161279200 | [6 empty] | 1161279200

## Avitn_DSTP
Ministry/ Department/Agency: FEDERAL MINISTRY OF AVIATION
Budgetary Year: 2011 FGN PROCUREMENT PLAN FOR WORKS
If within MDAs
Desk Officer: Engr. O O. Adebiyi Contact #: 08074577164 |  | Basic Data | [5 empty] | Draft Bid Documents, including specs and quantities,draft SPN |  | Spec Proc Notice Advert
[11 empty] | Bidding Period |  | Bid Evaluation |  | Contract Finalisation |  |  |  |  | Contract Implementation
Project Description | Package Number | Lot Number | Lumpsum or BEME | Procurement Method | Budgetary Amount in Naira | Pre or post Qualification | Approval Thresholds | Prep. & submission by MDAs | MDA Approval | Advertisement for pre qualification | Bid Invitation date | Bid Closing / opening | Submission of Bid Eval Rpt | MDA Approval | Contract Amount certified in N | FEC Approval | Date of contract offer | Date of Contract Signature | Mobilisation Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc. Steps | [5 empty] | If Prequalification |  | 2-3Wks | 1-2 Wks | 2wks | 2-6 wks | 6wks | 2-3 wks | 1-2 wks |  | 2-4wks | 1-2wks | 1wks | 2-3wks
Add 2wks
List of Contracts
ABEOKUTA AIRSTRIP |  | LOT 1 | BEME | NCB | 162042428 |  | MTB | 14-25/2/11 | 21/2-4/3/11 | 7-18/03/11 | 2011-03-21 | 2011-04-18 | 2011-04-29 | 2-13/5/2011 | 160000000 | N/A | 2011-05-19 | 2011-06-01 | 2011-07-04 | 2011-10-01 | 2012-03-01 |  | DSTP | Perm Sec
DEVELOPMENT OF JALINGO AIRSTRIP |  | LOT 2 | BEME | NCB | 191210128 |  | MTB | 14-25/2/11 | 21/2-4/3/11 | 7-18/03/11 | 2011-03-21 | 2011-04-18 | 2011-04-29 | 2-13/5/2011 | 190000000 | N/A | 2011-05-19 | 2011-06-01 | 2011-07-04 | 2011-10-01 | 2012-03-01 |  | DSTP | Perm Sec
FENCING OF 3 AIRSTRIPS (NGURU, POTISKUM, AND KEFFI) |  | LOT 3 | BEME | NCB | 54014161 |  | MTB | 14-25/2/11 | 21/2-4/3/11 | 7-18/03/11 | 2011-03-21 | 2011-04-18 | 2011-04-29 | 2-13/5/2011 | 54014161 | N/A | 2011-05-19 | 2011-06-01 | 2011-07-04 | 2011-10-01 | 2012-03-01 |  | DSTP | Perm Sec
REHABILITATION OF 5 AIRSTRIPS (NGURU, POTISKUM, KEFFI, BACITA, SHIROR AIRSTRIPS) |  | LOT 4 | BEME | NCB | 54014161 |  | MTB | 14-25/2/11 | 21/2-4/3/11 | 7-18/03/11 | 2011-03-21 | 2011-04-18 | 2011-04-29 | 2-13/5/2011 | 54014161 | N/A | 2011-05-19 | 2011-06-01 | 2011-07-04 | 2011-10-01 | 2012-03-01 |  | DSTP | Perm Sec
Total Cost |  |  |  |  | 461280878 | [9 empty] | 458028322

## Information_NIPOST
Ministry/Department/Agency: FMIC/NIPOST
Budgetary Year: 2011 --- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: S. G. WAKAWA |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
PROCUREMENT OF VEHICLES, PLANTS AND MOTORCYCLE
FMIC/NIP/BUD.11/01
date
Purchase of trucks, pick-up vans, pannelled cars, and motorcycles for mail conveyance and distribution in 32 territories nationwide.
|  | Lot 1 - 5 | 372817000 | NCB | post | Post | 3/1/2011 | N/A | 17/1/2011 | 31/1/2011 | 14/2/2011 | 28/2/2011 | N/A | 372817000 | NA | 14/3/2011 | 4/4/2011 | YES | 25/4/2011 | 2/5/2011
Purchase of power plant and back-ups for 4 territories, all counters nationwide, Headquarters and 2 ancillaries buildings.
|  | Lot 6 | 100000000 | NCB | post | post | 3/1/2011 | N/A | 17/1/2011 | 31/1/2011 | 14/2/2011 | 28/2/2011 | N/A | 100000000 |  | 14/3/2011 | 4/4/2011 | YES | 25/4/2011 | 2/5/2011
Purchase of ICT equipments (computers, accessories etc) for Headquarters and territories nationwide.
| FMIC/NIP/BUD.11/02 | Lot 1 | 150000000 | NCB | post | post | 3/1/2011 | N/A | 17/1/2011 | 31/1/2011 | 14/2/2011 | 28/2/2011 | N/A | 150000000 |  | 14/3/2011 | 4/4/2011 | YES | 25/4/2011 | 2/5/2011
PROCUREMENT OF OFFICE EQUIPMENTS AND FURNITURE.
FMIC/NIP/BUD.11/03
Purchase of ofice funiture for Headquarters and 32 territories nationwide.
|  | Lot 1 | 150000000 | NCB | post | post | 3/1/2011 | N/A | 17/1/2011 | 31/1/2011 | 14/2/2011 | 28/2/2011 | N/A | 150000000 |  | 14/3/2011 | 4/4/2011 | YES | 25/4/2011 | 2/5/2011
Purchase of office equipments (filing cabinets,photocopiers, refridgerators, fire extinguishers, air conditioners, fans, etc) for Headquarters and 32 territories nationwide
|  | Lot 2 | 100000000 | NCB | post | post | 3/1/2011 | N/A | 17/1/2011 | 31/1/2011 | 14/2/2011 | 28/2/2011 | N/A | 100000000 |  | 14/3/2011 | 4/4/2011 | YES | 25/4/2011 | 2/5/2011
Purchase and postal/mechanical equipments (sorting frames, trolleys, nest of letter boxes, etc) for 32 territories nationwide.
| FMIC/NIP/BUD.11/04 | Lot 1 | 150000000 | NCB | post | post | 3/1/2011 | N/A | 17/1/2011 | 31/1/2011 | 14/2/2011 | 28/2/2011 | N/A | 150000000 |  | 14/3/2011 | 4/4/2011 | YES | 25/4/2011 | 2/5/2011
Total Cost
Fill gray cells only!
Budgetary Year: 2011 --- Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: S. G. WAKAWA |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
DEVELOPMENT AND MODERNIZATION OF POSTAL INFRASTRUCTURES NATIONWIDE. | FMIC/NIP/BUD.11/01
Rehabilitation/Remodelling of existing Post Office buildings in 60 locations across the country. |  | LOT 1 - 60 | BOQ | NCB | 600000000 | Pre-Qual | Prio-review | 1/2/2011 | N/A | 14/2/2011 | 28/2/2011 | 14/3/2011 | 28/3/2011 | N/A | 600000000 | N/A | 12/4/2011 | 3/5/2011 | NIL | 3/6/2011 | 10/6/2011 | 600,000,000.00
Rehabilitation of ancillaries office/Postal buildings in 5 locations across the country. |  | LOT 61 - 65 | BOQ | NCB | 94500000 | Pre-Qual | Prio-review | 1/2/2011 | N/A | 14/2/2011 | 28/2/2011 | 14/3/2011 | 28/3/2011 | N/A | 94500000 | N/A | 12/4/2011 | 3/5/2011 | NIL | 3/6/2011 | 10/6/2011 | 94500000
Construction of neighbourhood Post Offices in 12 loctions across the geo-political zones in the country. |  | LOT 66 - 77 | BOQ | NCB | 216000000 | Pre-Qual | Prio-review
[8 empty] | 1/2/2011 | N/A | 14/2/2011 | 28/2/2011 | 14/3/2011 | 28/3/2011 | N/A | 216000000 | N/A | 12/4/2011 | 3/5/2011 | NIL | 3/6/2011 | 10/6/2011 | 216000000
Rehabilitation and equiping of NIPOST workshops in 3 locations |  | LOT 78 - 80 | BOQ | NCB | 50000000 | Pre-Qual | Prio-review
[8 empty] | 1/2/2011 | N/A | 14/2/2011 | 28/2/2011 | 14/3/2011 | 28/3/2011 | N/A | 50000000 | N/A | 12/4/2011 | 3/5/2011 | NIL | 3/6/2011 | 10/6/2011 | 50000000
Refurbishment of 20 No operational vans across the country. | FMIC/NIP/BUD.11/02 | LOT 1 | BOQ | NCB | 8000000 | Pre-Qual | Prio-review | 1/2/2011 | N/A | 14/2/2011 | 28/2/2011 | 14/3/2011 | 28/3/2011 | N/A | 8000000 | N/A | 12/4/2011 | 3/5/2011 | NIL | 3/6/2011 | 10/6/2011 | 8000000
Refurbishment of 20 No utility vans across the country. |  | LOT 2 | BOQ | NCB | 7000000 | Pre-Qual | Prio-review | 1/2/2011 | N/A | 14/2/2011 | 28/2/2011 | 14/3/2011 | 28/3/2011 | N/A | 7000000 | N/A | 12/4/2011 | 3/5/2011 | NIL | 3/6/2011 | 10/6/2011 | 7000000
COMPLETION OF ON-GOING AND ABANDONED POSTAL INFRASTRUCTURES NATIONWIDE | FMIC/NIP/BUD.11/01
Completion of abandoned NIPOST corporate Headquarters complex, Maitama Abuja. |  | LOT 1 | BOQ | NCB | 3429590000 | Pre-Qual | Prior | 17/1/2011 | 31/1/2011 | 14/2/2011 | 28/2/2011 | 14/3/2011 | 4/4/2011 | 18/4/2011 | 3429590000 | 2/5/2011 | 9/5/2011 | 30/5/2011 | YES | 9 weeks | 8/8/2011 | 3429590000
Completion of on-going Post Office Construction/Rehabilitation projects in 66 locations across the country.
| FMIC/NIP/BUD.11/01 | 008 | BOQ | NCB | 380000000 | 2 weeks |  | 17/1/2011 | 31/1/2011 | 14/2/2011 | 28/2/2011 | 14/3/2011 | 4/4/2011 | 18/4/2011 | 380000000 |  | 9/5/2011 | 30/5/2011 | YES | 9 weeks | 8/8/2011 | 380000000
Completion of abandoned Post Office projects in 35 locations across the country.
| FMIC/NIP/BUD.11/01 | 009 | BOQ | NCB | 122000000 | 2 weeks |  | 17/1/2011 | 31/1/2011 | 14/2/2011 | 28/2/2011 | 14/3/2011 | 4/4/2011 | 18/4/2011 | 122000000 |  | 9/5/2011 | 30/5/2011 | YES | 9 weeks | 8/8/2011 | 122000000
CERTIFICATION AND DEMARCATION OF NIPOST LANDS AND LANDED PROPERTIES NATIONWIDE.
Survey and acquisition of C. of O. of existing NIPOST lands and landed properties in 42 locations across the country.
| FMIC/NIP/BUD.11/01 | 010 | BOQ | NCB | 80000000 | 2 weeks |  | 17/1/2011 | 31/1/2011 | 14/2/2011 | 28/2/2011 | 14/3/2011 | 4/4/2011 | 18/4/2011 | 80000000 |  | 9/5/2011 | 30/5/2011 | YES | 9 weeks | 8/8/2011 | 80000000
Fencing of NIPOST lands and landed properties in 42 locations aacross the country.
| FMIC/NIP/BUD.11/01 | 011 | BOQ | NCB | 70000000 | 2 weeks |  | 17/1/2011 | 31/1/2011 | 14/2/2011 | 28/2/2011 | 14/3/2011 | 4/4/2011 | 18/4/2011 | 70000000 |  | 9/5/2011 | 30/5/2011 | YES | 9 weeks | 8/8/2011 | 70000000
Total Cost

## Information_APCN
Ministry/Department/Agency: ADVERTISING PRACTITIONERS COUNCIL OF NIGERIA
2011 -- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
BIMBOLA IPAYE (MRS) |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
Wide Area Network | FMIC/APCN/01
date
Vsat for Kaduna, Port harcourt, Owerri and Enugu |  | Lot 01 | 8400000 | NCB | POST | POST | 2 WKS | N/A | 2 WKS | 2 WKS | 6 WKS | 2 WKS | N/A | 8400000 | N/A | 2 WKS | 2 WKS | NIL | 2 WKS | 2 WKS
Servers for Kaduna,Port Harcourt, Owerri and Enugu and LAN for the four Zonal Offices |  | LOT 02 | 1000000 | NCB | POST | POST | 2 WKS | N/A | 2 WKS | 2 WKS | 6 WKS | 2 WKS | N/A | 1000000 | N/A | 2 WKS | 2 WKS | NIL | 2 WKS | 2 WKS
LAN for the Four Zonal Offices |  | LOT 03 | 600000 | NCB | POST | POST | 2 WKS | N/A | 2 WKS | 2 WKS | 6 WKS | 2 WKS | N/A | 600000 | N/A | 2 WKS | 2 WKS | NIL | 2 WKS | 2 WKS
MONITORING, ENFORCEMENT EQUIPMENT | FMIC/APCN/02
Purchase of 2 no. Billboard blanking high-rise hydraulic crane |  | LOT 01 | 54250000 | NCB | POST | POST | 2 WKS | N/A | 2 WKS | 2 WKS | 6 WKS | 2 WKS | N/A | 54250000 | N/A | 2 WKS | 2 WKS | NIL | 2 WKS | 2 WKS
Purchase of 3 no. Monitoring Van for Lagos, Abuja and Enugu Offices. |  | LOT 02 | 15750000 | NCB | POST | POST | 2 WKS | N/A | 2 WKS | 2 WKS | 6 WKS | 2 WKS | N/A | 15750000 | N/A | 2 WKS | 2 WKS | NIL | 2 WKS | 2 WKS
Purchase of 1 no. 120 Kva generator for Lagos |  | LOT 03 | 5000000 | NCB | POST | POST | 2 WKS | N/A | 2 WKS | 2 WKS | 6 WKS | 2 WKS | N/A | 5000000 | N/A | 2 WKS | 2 WKS | NIL | 2 WKS | 2 WKS
Total Cost |  |  | 85000000 | [10 empty] | 85000000
|  |  | 0 | [10 empty] | 0

## Information_DPC
FMIC/DPC
2011 -- Consultancy Service |  | If Post-Review, No-objection Dates are not needed |  |  |  |  | Request for Expression of Interest (when required)
Mr. CHARLES CHIKEZIE |  | Contract Type |  |  | Preparation Request for Proposals |  |  |  | Short List |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [6 empty] | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Prior/Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement | Lead-time before shortlist | Submission Date | No-objection Date | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks |  | 4 wk |  | 3 wks
List of Contracts
Training/Induction Programme at NIPI Kaduna, for 90 Information Officers redeployed by the Office of The Head of Service of the Federation to the Ministry to acquaint them with Information Management | NCB | Lumpsum | 17000000 | Prior ReviewPlan | 1/2/2011 | Not Needed | 15/2/2011 | 2/3/2011 | 16/3/2011 | Not Needed | 16/4/2011 | 23/5/2011 | 14/6/2011 | Not Needed | 28/6/2011 | 12/7/2011 | 27/7/2011 | 11/8/2011 | Not Neede | 17000000 | 12/9/2011 |  | 3/10/2011 | Not Needed | 18/10/2011 | 3/11/2011 | 17,000,000.00
Capacity-building workshops organized locally for Information/Aministrative Officers | NCB | Lumpsum | 10000000 | Prior ReviewPlan | 1/2/2011 | Not Needed | 15/2/2011 | 2/3/2011 | 16/3/2011 | Not Needed | 16/4/2011 | 23/5/2011 | 14/6/2011 | Not Needed | 28/6/2011 | 12/7/2011 | 27/7/2011 | 11/8/2011 | Not Needed | 10000000 | 12/9/2011 |  | 3/10/2011 | Not Needed | 18/10/2011 | 3/11/2011 | 10,000,000.00
Suppliments and Advertisements in Foreign Media by External Publicity | NCB | Lumpsum | 55000000 | Prior ReviewPlan | 1/2/2011 | Not Needed | 15/2/2011 | 2/3/2011 | 16/3/2011 | Not Needed | 16/4/2011 | 23/5/2011 | 14/6/2011 | Not Needed | 28/6/2011 | 12/7/2011 | 27/7/2011 | 11/8/2011 | Not Needed | 55000000 | 12/9/2011 |  | 3/10/2011 | Not Needed | 18/10/2011 | 3/11/2011 | 55,000,000.00
Security Services for 6 FIRCs (4 for each FIRC) & 31 FICs (3 for each FIC | NCB | Lumpsum | 21060000 | Prior ReviewPlan | 1/2/2011 | Not Needed | 15/2/2011 | 2/3/2011 | 16/3/2011 | Not Needed | 16/4/2011 | 23/5/2011 | 14/6/2011 | Not Needed | 28/6/2011 | 12/7/2011 | 27/7/2011 | 11/8/2011 | Not Needed | 21060000 | 12/9/2011 |  | 3/10/2011 | Not Needed | 18/10/2011 | 3/11/2011 | 21,060,000.00
Cleaning Services For 6 FIRCs (3 each) & 31 FICs (2each) | NCB | Lumpsum | 14400000 | Prior ReviewPlan | 1/2/2011 | Not Needed | 15/2/2011 | 2/3/2011 | 16/3/2011 | Not Needed | 16/4/2011 | 23/5/2011 | 14/6/2011 | Not Needed | 28/6/2011 | 12/7/2011 | 27/7/2011 | 11/8/2011 | Not Needed | 14400000 | 12/9/2011 |  | 3/10/2011 | Not Needed | 18/10/2011 | 3/11/2011 | 14,400,000.00
Publicity and Production of Publicity Materials for Independennce Celebration | NCB | Lumpsum | 10000000 | Prior ReviewPlan | 1/2/2011 | Not Needed | 15/2/2011 | 2/3/2011 | 16/3/2011 | Not Needed | 16/4/2011 | 23/5/2011 | 14/6/2011 | Not Needed | 28/6/2011 | 12/7/2011 | 27/7/2011 | 11/8/2011 | Not Needed | 10000000 | 12/9/2011 |  | 3/10/2011 | Not Needed | 18/10/2011 | 3/11/2011 | 10,000,000.00
Publicity for Democracy Day | NCB | Lumpsum | 10000000 |  | 1/2/2011 | Not Needed | 15/2/2011 | 2/3/2011 | 16/3/2011 | Not Needed | 16/4/2011 | 23/5/2011 | 14/6/2011 | Not Needed | 28/6/2011 | 12/7/2011 | 27/7/2011 | 2wks | Not Needed | 10000000 | 12/9/2011 |  | 3/10/2011 | Not Needed | 18/10/2011 | 3/11/2011 | 10,000,000.00
Total Cost |  |  | 137460000 | [16 empty] | #REF! | [6 empty] | #REF!
[20 empty] | #REF! | [6 empty] | #REF!
Fill gray cells only!
FMIC/DPC
2011 - Works | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
MR. CHARLES CHIKEZIE |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
Purchase of Press Materials for coverage of State House Activities | FMIC/DPC/01 | LOT 01 | 12000000 | NCB | post | post | 3/1/2011 | Not Applicable | SPN | 17/1/2011 | 3/3/2011 | 24/3/2011 | Not Applicable | 12000000 | Not Needed | 7/4/2011 | 30/4/2011 | Not Applicable | 16/5/2011 | 31/5/2011
Purchase of 5 Computers and their Accessories for Bilateral Relations unit |  | LOT 02 | 1500000 | NCB | post | post | 3/1/2011 | Not Applicable | SPN | 17/1/2011 | 3/3/2011 | 24/3/2011 | Not Applicable | 1500000 | Not Needed | 7/4/2011 | 30/4/2011 | Not Applicable | 16/5/2011 | 31/5/2011
Production of TV Commercials, Radio Jingles, Pamphlets, Posters & Documentaries on Federal Government Programmes, MDGs, VISIO 202020, Critical Sectors of the Economy |  | LOT 03 | 200000000 | NCB | post | post | 3/1/2011 | Not Applicable | SPN | 17/1/2011 | 3/3/2011 | 24/3/2011 | Not Applicable | 200000000 | Not Needed | 7/4/2011 | 30/4/2011 | Not Applicable | 16/5/2011 | 31/5/2011
Total Cost |  |  | 213500000 | [10 empty] | 213500000
Fill gray cells only!
2011 --- Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
MR. CHARLES CHIKEZIE |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
Complete overhaul of 6 Zoned FIRCs at Kaduna, Yola, Minna, Ado-Ekiti, Awka and Calabar | FMIC/DPC/01 | 01 | Bill of Quantities | NCB | 100000000 | Pre QualificationPrior Review |  | 1/2/2011 | Not Applicable | 15/2/2011 | 2/3/2011 | 1/4/2011 | 15/4/2011 | Not Applicable | 100000000 | Not Applicable2wks | 22/4/2011 | 6/5/2011 | Not Needed | 4wks | 6/6/2011 | 100,000,000.00
prior
Purchase of 6 AV Drum 21 Mobile Marine Boats for Public Enlihgtenment Campaigns in Reverine Areas at Boro (for River Niger area), Lokoja (for Kogi area), Rivers Delta, Bayelsa, Cross Rivers and Akw Ibom |  | 02 | Lumpsum | NCB | 47000000 | Pre Qualification | Prior Review | 1/2/2011 | Not Applicable | 15/2/2011 | 2/3/2011 | 1/4/2011 | 15/4/2011 | Not Applicable | 47000000 | Not Applicable2wks | 22/4/2011 | 6/5/2011 | Not Needed | 4wks | 6/6/2011 | 47,000,000.00
Procurement of 31 Land Rovers for FICs for Grass-root Mobilization and Media Campaign Tours on Federal Government Policies and Projects Nationwide |  | 03 | Lumpsum | NCB | 363000000 | Pre QualificationPrior Review | [8 empty] | 363000000 | Not Applicable2wks | 22/4/2011 | 6/5/2011 | Not Needed | 4wks | 6/6/2011 | 363,000,000.00
Complete Renovation and Re-equiping of 17 FICs; Ibadan, Lagos, Oshogbo, Abeokuta, Ilorin, Akure, Port-Harcourt, Yenagoa, Owerri, Enugu, Bauchi, Gombe, Maiduguri, Sokoto, Gusau, Kano and Kastina |  | 04 | Lumpsum | NCB | 135000000 | Pre QualificationPrior Review |  | 1/2/2011 | Not Applicable | 15/2/2011 | 2/3/2011 | 1/4/2011 | 15/4/2011 | Not Applicable | 135000000 | Not Applicable | 22/4/2011 | 6/5/2011 | Not Needed | 4wks | 6/6/2011 | 135,000,000.00
Total Rehabilitation and Re- equiping of National Press Center |  | 05 | Lumpsum | NCB | 150000000 | Pre QualificationPrior Reviewpla | Prior Review | 1/2/2011 | Not Applicable | 15/2/2011 | 2/3/2011 | 1/4/2011 | 15/4/2011 | Not Applicable | 150000000 | Not Applicable | 22/4/2011 | 6/5/2011 | Not Needed | 4wks | 6/6/2011 | 150,000,000.00
Purchase of Media Accreditation Materials/Equipment & Renovation of 4 Office Rooms |  | 06 | Lumpsum | NCB | 9300000 | Pre QualificationPrior Review |  | 1/2/2011 | Not Applicable | 15/2/2011 | 2/3/2011 | 1/4/2011 | 15/4/2011 | Not Applicable | 9300000 | Not Applicable | 22/4/2011 | 6/5/2011 | Not Needed | 4wks | 6/6/2011 | 9,300,000.00
[5 empty] | 810300000 | [9 empty] | 810300000 | [6 empty] | 810300000
Total Cost |  |  |  |  | 810300000 | [9 empty] | 810300000 | [6 empty] | 810300000

## information_FG Press
Ministry/Department/Agency: FMIC/FEDERAL GOVT PRESS
2011 -- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
M.O. ASHAFA |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
Installation of Digital Equipment | FMIC/FGP/01 | LOT 1 | 20000000 | SELECTIVE | POST | POST | 3/1/2011 | NA | 24/1/2011 | 9/2/2011 | 24/2/2011 | 10/3/2011 | NA | 20000000 | NA | 17/3/2011 | 31/3/2011 | NIL | 14/4/2011 | 21/4/2011
PURCHASE OF UTILITY VEHICLES FOR FGP LAGOS AND ABUJA. | FMIC/FGP/02 | LOT 1 | 10000000 | SELECTIVE | POST | POST | 3/1/2011 | NA | 24/1/2011 | 9/2/2011 | 24/2/2011 | 10/3/2011 | NA | 10000000 | NA | 17/3/2011 | 31/3/2011 | NIL | 14/4/2011 | 21/4/2011
PAPER AND BOARDS | FMIC/FGP/03 | LOT 1 | 130000000 | SELECTIVE | POST | POST | 3/1/2011 | NA | 24/1/2011 | 9/2/2011 | 24/2/2011 | 10/3/2011 | NA | 130000000 | NA | 17/3/2011 | 31/3/2011 | NIL | 14/4/2011 | 21/4/2011
BINDING LITHOGRAPHIC MATERIALS AND COMPUTER ACCESSORIES | FMIC/FGP/04 | LOT 1 | 55000000 | SELECTIVE | POST | POST | 3/1/2011 | NA | 24/1/2011 | 9/2/2011 | 24/2/2011 | 10/3/2011 | NA | 55000000 | NA | 17/3/2011 | 31/3/2011 | NIL | 14/4/2011 | 21/4/2011
Total Cost |  |  | 215000000 | [10 empty] | 215000000
Ministry/Department/Agency:FMIC/FEDERAL GOVT PRESS
2011 -- Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
M.O. ASHAFA |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
REHABILITATION OF INFRASTRUCTURAL FACILITIES AT FOUR (4) LOCATIONS OF FGP IN LAGOS | FMIC/FGP/01 | LOT1 | BOQ | NCB | 10000000 | Pre-QUAL | Prior | 4/4/2011 | NA | 18/4/2011 | 2/5/2011 | 16/5/2011 | 30/5/2011 | NA | 10000000 | NA | 7/6/2011 | 30/6/2011 | NIL | 30/7/2011 | 15/8/2011 | 22/8/2011
ENERGISING OF NEW FGP FACTORY AND ADMINISTRATIVE BLOCK, ABUJA. | FMIC/FGP/02 | LOT 1 | BOQ | NCB | 10000000 | Pre-QUAL | Prior | 4/4/2011 | NA | 18/4/2011 | 2/5/2011 | 16/5/2011 | 30/5/2011 | NA | 10000000 | NA | 7/6/2011 | 30/6/2011 | NIL | 30/7/2011 | 15/8/2011 | 22/8/2011
Total Cost |  |  |  |  | 20000000

## Information_IT
Ministry/Department/Agency: INFORMATION AND COMMUNICATIONS
Budgetary Year: 2011 --- Consultancy Service | [6 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: AMIOLEMEN MARCUS |  | Contract Type |  |  | Preparation Request for Proposals |  |  |  | Short List |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [6 empty] | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Prior/Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement | Lead-time before shortlist | Submission Date | No-objection Date | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks |  | 4 wk |  | 3 wks
List of Contracts
Resuscitating, Relaunching, Hosting, Registration and Management of the National Web Portal www.nigeria.gov.ng for 2 years | Selective Tendering | Time-Based | 17000000 |  | 1/3/2011 | NA | 28/3/2011 | 12/4/2011 | 25/4/2011 | NA | 25/5/2011 | 11/7/2011 | 2/8/2011 | NA | 16/8/2011 | 30/8/2011 | 14/9/2011 | 28/9/2011 | NA | 17000000 | 21/10/2011 | 28/3/2011 | 14/11/2011 | NIL | 28/11/2011 | 12/12/2011 | 17000000
Consultancy, Hosting and Management of FMIC Website www.fmic.gov.ng for 2 years. | Selective Tendering | Time-Based | 7500000 |  | 1/3/2011 | NA | 28/3/2011 | 12/4/2011 | 25/4/2011 | NA | 25/5/2011 | 11/7/2011 | 2/8/2011 | NA | 16/8/2011 | 30/8/2011 | 14/9/2011 | 28/9/2011 | NA | 7500000 | 21/10/2011 | 28/3/2011 | 14/11/2011 | NIL | 28/11/2011 | 12/12/2011 | 7500000
Annual Lecture on a Topical issues organised by the FMIC Web Management Team for the purpose of awareness Creation | Selective Tendering | Lumpsum | 3500000 |  | 1/3/2011 | NA | 28/3/2011 | 12/4/2011 | 25/4/2011 | NA | 25/5/2011 | 11/7/2011 | 2/8/2011 | NA | 16/8/2011 | 30/8/2011 | 14/9/2011 | 28/9/2011 | NA | 3500000 | 21/10/2011 | 28/3/2011 | 14/11/2011 | NIL | 28/11/2011 | 12/12/2011 | 3500000
Consultancy services for Web Traffic Report, Opinion Poll and Analysis for both the National Web Portal and the FMIC Website. | Selective Tendering | Time-Based | 5000000 |  | 1/3/2011 | NA | 28/3/2011 | 12/4/2011 | 25/4/2011 | NA | 25/5/2011 | 11/7/2011 | 2/8/2011 | NA | 16/8/2011 | 30/8/2011 | 14/9/2011 | 28/9/2011 | NA | 5000000 | 21/10/2011 | 28/3/2011 | 14/11/2011 | NIL | 28/11/2011 | 12/12/2011 | 5000000
Renewal of 400 Multi Users licence Smart Suite Antivirus (Enterprise Version) | Selective Tendering | Lumpsum | 2880000 |  | 1/3/2011 | NA | 28/3/2011 | 12/4/2011 | 25/4/2011 | NA | 25/5/2011 | 11/7/2011 | 2/8/2011 | NA | 16/8/2011 | 30/8/2011 | 14/9/2011 | 28/9/2011 | NA | 2880000 | 21/10/2011 | 28/3/2011 | 14/11/2011 | NIL | 28/11/2011 | 12/12/2011 | 2880000
Procurement of Relevant Application Software (Adobe Suite, Audio and Video Streaming editing suite) for the National Portal and FMIC website | Selective Tendering | Lumpsum | 7500000 |  | 1/3/2011 | NA | 28/3/2011 | 12/4/2011 | 25/4/2011 | NA | 25/5/2011 | 11/7/2011 | 2/8/2011 | NA | 16/8/2011 | 30/8/2011 | 14/9/2011 | 28/9/2011 | NA | 7500000 | 21/10/2011 | 28/3/2011 | 14/11/2011 | NIL | 28/11/2011 | 12/12/2011 | 7500000
Total Cost |  |  | 43380000 | [16 empty] | 43380000 | [6 empty] | 43380000
Fill gray cells only!
Ministry/Department/Agency: Information and Communications
Budgetary Year: 2011 --- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: Amiolemen O. Marcus |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation | [6 empty] | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks | [8 empty] | Actual
List of Contracts
Procurement of 70 units of HP Desktop Intel Core 2 duo or i3 Quard Processor Computer Systems with 750 APC UPS | 70 | 275000 | 19250000 | Selective Tendering | POST | POST | 2 wks | 2 wks | 2 wks | 2 wks | 4 wks | 2 wks | 2 wks | Plan
Actual
date
Upgrade of the Ministry's Data Centre Network HP EU G7 Rack Servers and other Accessories for optimal network performance | 3 | 1350000 | 4050000 | Direct Procurement | 2 wks |  | 2 wks | 2 wks | 2 wks | 2 wks | 4 wks | 2 wks | 2 wks | Plan
Actual
Upgrade / Expansion of the Ministry's Local Area Network (LAN) with Core Layer 3 Cisco Switches at all the Intermediate Distribution Level for efficient Data and Voice traffic on the Network | LOT | 12000000 | 12000000 | Selective Tendering | 2 wks |  | 2 wks | 2 wks | 2 wks | 2 wks | 4 wks | 2 wks | 2 wks | Plan
Actual
Automation of FMIC Registry (File Tracker Software) | 1 | 8500000 | 8500000 | Selective Tendering | 2 wks |  | 2 wks | 2 wks | 2 wks | 2 wks | 4 wks | 2 wks | 2 wks | Plan
Actual
Procurement of HP Laptops Computers with Intel i3 or i5 Processor configuration and accessories | 40 | 295000 | 11800000 | Selective Tendering | 2 wks |  | 2 wks | 2 wks | 2 wks | 2 wks | 4 wks | 2 wks | 2 wks | Plan
Actual
Procurement of SAS 500GB Backup Hard Drives for Daily Backup of Network Information and content of the National Portal and the FMIC Website | 3 | 550000 | 1650000 | Direct Procurement | 2 wks |  | 2 wks | 2 wks | 2 wks | 2 wks | 4 wks | 2 wks | 2 wks | Plan
Actual
Procurement of HP LaserJet 2055 Printers | 25 | 115000 | 2875000 | Direct Procurement | 2 wks |  | 2 wks | 2 wks | 2 wks | 2 wks | 4 wks | 2 wks | 2 wks | Plan
Actual
Procurement of HP 2600n Color LaserJet Printers | 5 | 350000 | 1750000 | Direct Procurement | 2 wks |  | 2 wks | 2 wks | 2 wks | 2 wks | 4 wks | 2 wks | 2 wks | Plan
Actual
Implementation of Document Management system (DMS) | 1 | 8200000 | 8200000 | Selective Tendering | 2 wks |  | 2 wks | 2 wks | 2 wks | 2 wks | 4 wks | 2 wks | 2 wks
Procurement of Sony CyberShoot Professional Digital Camera for management of the Ministry's Website and the National Portal | 4 | 325000 | 1300000 | Direct Procurement | 3 wks |  | 2 wks | 2 wks | 2 wks | 2 wks | 4 wks | 2 wks | 2 wks
Procurement of Computer Accessories, Flash Drives, Keyboard, External CD/DVD Writer, Mouse, Toners, Catrigdes | LOT | 6500000 | 6500000 | Selective Tendering | 2 wks |  | 2 wks | 2 wks | 2 wks | 2 wks | 4 wks | 2 wks | 2 wks
Procurement of 1700 Lumens Infocus Projector and Tripod Strand | 3 | 750000 | 2250000 | Direct Procurement | 3 wks |  | 2 wks | 2 wks | 2 wks | 2 wks | 4 wks | 2 wks | 2 wks
Procurement of HP Multi-user Scanners | 15 | 75000 | 1125000 | Direct Procurement | 3 wks |  | 2 wks | 2 wks | 2 wks | 2 wks | 4 wks | 2 wks | 2 wks
Total Cost |  | 39285000 | 61875174 | [10 empty] | Plan
|  |  | 61875174 | [10 empty] | Actual
Fill gray cells only!
Ministry/Department/Agency: Information and Communications
Budgetary Year: 2011 - Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: Amiolemen Marcus |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
Management of Wide Area Network (WAN) and Local Area Network (LAN) Systems within the Ministry's Headquarter, Communications Arm and the Six Zonal Information Resources Centres | FMIC/IT/01 | 1 | BOQ | Selective Tendering | 28500000 | 3/1/2011 | POST | 17/1/2011 | NA | 2/2/2011 | 16/2/2011 | 16/3/2011 | 30/3/2011 | NA | 28500000 | NA | 14/4/2011 | 7/5/2011 | NIL | DEC.2011 | 31/12/2011 | 28,500,000.00
Maintenance of Computer Systems and its Local Area Network at the Thirty-Six Federal Information Centres | FMIC/IT/02 | 1 | Lumpsum | Selective Tendering | 34200000 | 3/1/2011 | POST | 17/1/2011 | NA | 2/2/2011 | 16/2/2011 | 16/3/2011 | 30/3/2011 | NA | 34200000 | NA | 14/4/2011 | 7/5/2011 | NIL | DEC.2011 | 31/12/2011 | 34200000
Procurement of VNC/Network Management Software to manage the WAN connection between the Ministry's Hqrt and the ZIRC centres | FMIC/IT/03 | 1 | Lumpsum | Selective Tendering | 6500000 | 3/1/2011 | POST | 17/1/2011 | NA | 2/2/2011 | 16/2/2011 | 16/3/2011 | 30/3/2011 | NA | 6500000 | NA | 14/4/2011 | 7/5/2011 | NIL | DEC.2011 | 31/12/2011 | 6500000
Networking Equipment - 10/100/1000kbps Ethernet Cables, Face plates, Pattrex, Terminating Tool and LAN Testers | FMIC/IT/04 | 1 | BOQ | Selective Tendering | 5000000 | 3/1/2011 | POST | 17/1/2011 | NA | 2/2/2011 | 16/2/2011 | 16/3/2011 | 30/3/2011 | NA | 5000000 | NA | 14/4/2011 | 7/5/2011 | NIL | DEC.2011 | 31/12/2011 | 5000000
Maintenance of Wireless Radio Connectivity for IPPIS Implementation | FMIC/IT/O5 | 1 | Lumpsum | Selective Tendering | 3000000 | 3/1/2011 | POST | 17/1/2011 | NA | 2/2/2011 | 16/2/2011 | 16/3/2011 | 30/3/2011 | NA | 3000000 | NA | 14/4/2011 | 7/5/2011 | NIL | DEC.2011 | 31/12/2011 | 3000000
IT capacity building for System Administrators, Web Masters and Desk Officers | FMIC/IT/06 | 1 | BOQ | Selective Tendering | 3750000 | 3/1/2011 | POST | 17/1/2011 | NA | 2/2/2011 | 16/2/2011 | 16/3/2011 | 30/3/2011 | NA | 3750000 | NA | 14/4/2011 | 7/5/2011 | NIL | DEC.2011 | 31/12/2011 | 3750000
Total Cost |  |  |  |  | 80950000 | [9 empty] | 80950000 | [6 empty] | 80950000
Fill gray cells only!

## Information_NBC
Ministry/Department/Agency: NATIONAL BROADCASTING COMMISSION | [7 empty] | Request for Expression of Interest (when required)
Budgetary Year: 2011 --- Consultancy Service
Desk Officer/Contact #: Ruth Caleb,0803-450-5256 & Adegoke Nseabasi |  | Contract Type |  |  | Preparation Request for Proposals |  |  |  | Short List |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [6 empty] | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Prior/Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement | Lead-time before shortlist | Submission Date | No-objection Date | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks |  | 4 wk |  | 3 wks
List of Contracts
AUDIT ACTIVITIES | DP | LS | 22000000 | POST | 3wks | NA | 2wks | 2wks | 2wks | NA | 4wks | 8wks | 3wks | NA | 2wks | 2wks | NA | NA | NA | 22000000 | NA | NA | NA | NA | NA | NA | 22,000,000.00
FINANCE ACTIVITIES | DP | " | 21700000 | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | 21700000 | " | " | " | " | " | " | 21,700,000.00
LEGAL ACTIVITIES | DP | " | 53139000 | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | 53139000 | " | " | " | " | " | " | 53,139,000.00
UTILITY SERVICES | DP | " | 11978000 | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | 11978000 | " | " | " | " | " | " | 11,978,000.00
PRINTING | NS | " | 10000000 | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | 10000000 | " | " | " | " | " | " | 10,000,000.00
DIRECT LABOUR | NCB | " | 20000000 | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | 20000000 | " | " | " | " | " | " | 20,000,000.00
STAFF PROMOTION | DP | " | 10000000 | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | 10000000 | " | " | " | " | " | " | 10,000,000.00
STAFF PENSION | DP | " | 25000000 | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | 25000000 | " | " | " | " | " | " | 25,000,000.00
SECURITY SERVICES | NCB | " | 30000000 | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | 30000000 | " | " | " | " | " | " | 30,000,000.00
LOCAL/FOREIGN TRAININGS | NCB | LS | 72854000 | POST | 4wks | 2wks | 2wks | 2wks | NA | NA | 2wks | 3wks | 3wks | NA | NA | NA | NA | NA | NA | 72854000 | NA | NA | 3wks | NA | NA | NA | 72,854,000.00
FUELING OF VEHICLES/MAINTAINENCE | NS | " | 28000000 | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | 28000000 | " | " | " | " | " | " | 28,000,000.00
FUELING OF GENERATOR | NS | " | 17000000 | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | 17000000 | " | " | " | " | " | " | 17,000,000.00
CLEANING,FUMIGATION |  | " | 30000000 | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | 30000000 | " | " | " | " | " | " | 30,000,000.00
NCB
RENT | NS | " | 15000000 | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | 15000000 | " | " | " | " | " | " | 15,000,000.00
INSURANCE | NCB | " | 50000000 | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | 50000000 | " | " | " | " | " | " | 50,000,000.00
MAIL SERVICES | NS | " | 4000000 | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | 4000000 | " | " | " | " | " | " | 4,000,000.00
\
MEETINGS | NS |  | 3000000 | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | " | 3000000 | " | " | " | " | " | " | 3,000,000.00
Total Cost |  |  | 219854000 | [16 empty] | 219854000 | [6 empty] | 219854000
0
Fill gray cells only!
Budgetary Year: 2011 --- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: | Caleb R.N, 0803-450-5256 & Adegoke Nseabasi | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
STATIONARY ITEMS | FMIC/NBC/001 | 1 | 7687890 | NS | POSTQual | POST | 2WKS | N/A | 2WKS | 2WKS | NA | 2WKS | NA | 7687890 | 2wks | 1WK | 1WK | N A
date
OFFICE EQUIPMENT | FMIC/NBC/002 | 1 | 15611500 | NS | 2WKS | " | " | " | " | " | " | " | " | 15611500 | " | " | " | "
OFFICE FURNITURE/FITTINGS | FMIC/NBC/003 | 1 | 10143000 | NS | 2WKS | " | " | " | " | " | " | " | " | 10143000 | " | " | " | "
PURCHASE OF NEW VEHICLES | FMIC/NBC/004 | 1 | 10000000 | NS | 2WKS | " | " | " | " | " | " | " | " | 10000000 | " | " | " | "
PURCHASE OF LAND,OFFICE AND FENCING | FMIC/NBC/005 | 1 | 100000000 | NCB | 2WKS | '' | " | " | " | " | " | " | " | 100000000 | " | " | " | "
GENERATOR | FMIC/NBC/006 | 1 | 1000000 | NS | 2WKS | " | " | " | " | " | " | " | " | 1000000 | " | " | " | "
MONITORING SETS | FMIC/NBC/007 | 1 | 2000000 | NS | NA | " | " | " | " | " | " | " | " | 2000000 | " | " | " | "
Total Cost |  |  | 146442390 | [10 empty] | 146442390
#REF!
Fill gray cells only! |  |  | S
Budgetary Year: 2011 ---Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: | Caleb R.N 0803-450-5256 &Adegoke Nseabasi | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
ENGINEERING ACTIVITIES/UPGRADING OF INTERNET | FMIC/NBC/001 | 001 | LS | DP | 5200000 | 2WKS | POST | 3 wks | NA | 2WKS | 2WKS | 6WKS | 2WKS | NA | 5200000 | NA | NA | 1WK |  |  |  | 5,200,000.00
'
CCTV CAMERAS |  | 002 | LS | NS | 2500000 | " | " | 3WKS | " | " | " | " | " | " | 2500000 | " | " | " |  |  |  | 2,500,000.00
EARTHING OF OFFICE COMPLEX |  | 003 | LS | NS | 2500000 | " | " | " | " | " | " | " | " | " | 2500000 | " | " | " |  |  |  | 2,500,000.00
BROADCAST SIGNALS SURVEY |  | 004 | LS | NCB | 100000000 | " | " | " | " | " | " | " | " | " | 100000000 | " | " | " |  |  |  | 100,000,000.00
INSTALLATION OF TRANSMITTER |  | 005 | LS | NS | 2500000 | " | " | " | " | " | " | " | " | " | 2500000 | " | " | " |  |  |  | 2,500,000.00
\
PROVISION OF FLAT SCREEN |  | 006 | LS | NS | 5000000 | " | " | " | " | " | " | " | " | " | 5000000 | " | " | " |  |  |  | 5,000,000.00
PROVISION OF SECURITY FOR COMPUTERS,LAN,V-SAT |  | 007 | LS | NS | 2750000 | " | " | " | " | " | " | " | " | " | 2750000 | " | " | " |  |  |  | 2,750,000.00
TECHICAL SUPPORT FOR TECHNICAL MONITORING |  | 008 | LS | DP | 6400000 | " | " | " | " | " | " | " | " | " | 6400000 | " | " | " |  |  |  | 6,400,000.00
MEASUREMENT TOOLS |  | 009 | LS | DP | 83719000 | " | " | " | " | " | " | " | " | " | 83719000 | " | " | " |  |  |  | 83,719,000.00
INSTALLATION OF PABX | FMIC/NBC/001 | 010 | LS | NS | 2050000 | 2WKS | POST | 2WKS | NA | 2WKS | 2WKS | 6WKS | 3WKS | NA | 2050000 | NA | 2WKS | 2WKS | NA |  |  | 2,050,000.00
DISTRIBUTION OF INTERNET FACILITY |  | 011 | LS | NS | 2000000 | " | " | " | " | " | " | " | " | ' | 2000000 | " | " | " | " |  |  | 2,000,000.00
PHOTO ARCHIVE |  | 012 | LS | NS | 200000 | " | " | " | " | " | " | " | " | ' | 200000 | " | " | " | " |  |  | 200,000.00
OFFICE RENOVATION | FMIC/NBC/002001 | 001 | LS | NS | 5000000 | " | " | " | " | " | " | " | " | ' | 5000000 | " | " | " | " |  |  | 5,000,000.00
BUILDING OF NBC HQ/OFFICES | FMIC/NBC/003 | 001 | LS | NS | 100000000 | " | " | " | " | " | " | " | " | " | 100000000 | " | " | " | " |  |  | 100,000,000.00
Total Cost |  |  |  |  | 109250000 | [9 empty] | #REF! | [6 empty] | 109250000
#REF!
Fill gray cells only!

## Inforamtion_NIPI
Ministry/Department/Agency: FEDERAL MINISTRY OF INFORMATION AND COMMUNICATIONS/NIGERIAN OF INSTITUTE OF PUBLIC INFORMATION, KADUNA
Budgetary Year: 2011 --- Consultancy Services | [6 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  | Preparation Request for Proposals |  |  |  | Short List |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [6 empty] | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Prior/ Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement | Lead-time before shortlist | Submission Date | No-objection Date | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks |  | 4 wk |  | 3 wks
List of Contracts
NIPI CLINIC WORKS | OPEN | TIME BASED | 2700708
Total Cost |  |  | 2700708
Ministry/Department/Agency: | FEDERAL MINISTRY OF INFORMATION AND COMMUNICATIONS/NIGERIAN OF INSTITUTE OF PUBLIC INFORMATION, KADUNA
Budgetary Year: 2011---Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
NIPI CLINIC CONSTRUCTION WORKS | 1 | 1 | BOQ | NCB | 2700708 | POST | Post Review | 15/2/2011 | N/A | SPN ADVERT | 2/3/2011 | 14/4/2011 | 28/4/2011 | N/A | 2700708 | N/A | 19/5/2011 | 2/6/2011 | 15% | 16/8/2011 | 30/8/2011 | 2700708
COMPLETE RENOVATION OF THE FEMALE HOSTEL | 2 | 1 | BOQ | NCB | 5401416 | POST | Post Review | N/A | N/A | SPN ADVERT | 2/3/2011 | 14/4/2011 | 28/4/2011 | N/A | 5401416 | N/A | 19/5/2011 | 2/6/2011 | 15% | 16/8/2011 | 30/8/2011 | 5401416
INSTITUTE LIBRARY, E-EQUIPMENT AND BOOKS | 3 | 1 | BOQ | NCB | 3780991 | POST | Post Review | N/A | N/A | SPN ADVERT | 2/3/2011 | 14/4/2011 | 28/4/2011 | N/A | 3780991 | N/A | 19/5/2011 | 2/6/2011 | 15% | 16/8/2011 | 30/8/2011 | 3780991
Total Cost |  |  |  |  | 11883115 | [9 empty] | 11883115 | [6 empty] | 11883115

## Information_NPC
Ministry/Department/Agency: Nigerian Press Council
Budgetary Year: 2011 --- Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: Muhammad A.H. |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
E- Library | FMIC/NPC/OI | LOT 01 | Lumpsum | NCB | 40000000 | Pre- Qualification | Prior Review | 3 wks | NA | 2 wks | 2 wks | 6 wks | 3 wks | NA | 40000000 | NA | 2 wks | 3 wks | NA | 2 wks | 1 wk | 40000000
Digitisation of Archival Registry | FMIC/NPC/O2 | LOT 01 | Lumpsum | NCB | 50000000 | Pre- Qualification | Prior Review | 3 wks | NA | 2 wks | 2 wks | 6 wks | 3 wks | NA | 50000000 | NA | 2 wks | 3 wks | NA | 2 wks | 1 wk | 50000000
Computerisation , Internet Facility and Website Upgrade | FMIC/NPC/O3 | LOT 01 | Lumpsum | NCB | 10000000 | Pre- Qualification | Prior Review | 3wks | NA | 2 wks | 2 wks | 6 wks | 3 wks | NA | 10000000 | NA | 2 wks | 3 wks | NA | 2 wks | 1 wk | 10000000
Total Cost |  |  |  |  | 100000000 | [9 empty] | 100000000 | [6 empty] | 100000000
Fill gray cells only!

## Information_NTA
Ministry/Department/Agency: NTA
Budgetary Year: 2011 --- Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #:ENGR. OLUTOLA OKUNEYE |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
COMPLETION OF 10 NEW STATIONS | NTA/2011/PR/001 |  | Bill of quantities | NCB | 150000000 | PRE-qualification | Prior Review | 21/2 to 6/3/2011 | 21/3 to 31/3/2011 | 1/4 to 14/4/2011 | 15/4/2011 | 30/4/2011 | 1/5 to 14/5/2011 | 15/5 to 28/5/2011 | 150000000 |  | 29/5 to 4/6/2011 | 24/6/2011 | 22500000 | 75000000 | 45000000 | 7500000
REFURBISHING OF EDITING SUITES AND FACILITIES | NTA/2011/PR/002 |  | Bill of quantities | Competitive bidding | 50000000 | Post qualification | Prior Review | 21/2 to 6/3/2011 | 21/3 to 31/3/2011 | 1/4 to 14/4/2011 | 15/4/2011 | 30/4/2011 | 1/5 to 14/5/2011 | 15/5 to 28/5/2011 | 50000000 |  | 29/5 to 4/6/2011 | 24/6/2011 | 7500000 | 25000000 | 15000000 | 2500000
Total Cost |  |  |  |  | 200000000 | [9 empty] | 200000000 | [6 empty] | 10000000
Fill gray cells only!

## Information_VON
Ministry/Department/Agency: VOICE OF NIGERIA
Budgetary Year: 2011 --- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN
Desk Officer/Contact #: MR AYOOLA |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
Provision of morden broadcast equipment for News and Programmes gathering, including fully digitalised OBV | fmic/von/p01 | LOT 1 | 200000000 | Nat. comp. bidding | Pre - Qualification | Post - Review | 3/1/2011 | NA | 24/1/2011 | 7/2/2011 | 21/2/2011 | 14/3/2011 | 28/3/2011 | 200, 000, 000 | NA | 12/4/2011 | 3/5/2011 | NA | 24/5/2011 | 14/6/2011
date
Procurement of 2Nos of 1000KVA, 11KVA generating plant with synchronisation and control panel | FMIC/VON/P02 | LOT 1 | 100000000 | Nat. comp. bidding | Pre - Qualification | Post - Review | 3/1/2011 | NA | 24/1/2011 | 7/2/2011 | 21/2/2011 | 14/3/2011 | 28/3/2011 | 100, 000, 000 | NA | 12/4/2011 | 3/5/2011 | NA | 24/5/2011 | 14/6/2011
Information technology infrastructure, supply of computer hardwares, LAN, WAN, V - SAT, computerisation of Finance and Admin records | FMIC/VON/P03 | LOT 1 | 80000000 | National comp. bidding | Pre - Qualification | Post Review | 3/1/2011 | NA | 24/1/2011 | 7/2/2011 | 21/2/2011 | 14/3/2011 | 28/3/2011 | 80, 000, 000 | NA | 12/4/2011 | 3/5/2011 | NA | 24/5/2011 | 14/6/2011
Regular procurement of AGO and PMS AGO - 1, 632, 000 litres/P.A PMS - 528, 000litres/P.A | FMIC/VON/P04 | LOT 1 | 228480000 | competitive bidding | SPN ADVERT | Post - Review | 3/1/2011 | NA | 24/1/2011 | 7/2/2011 | 21/2/2011 | 14/3/2011 | 28/3/2011 | 228, 480, 000 | NA | 12/4/2011 | 3/5/2011 | NA | 24/5/2011 | 14/6/2011
PMS-528,000 LITRES/PA |  | LOT 2 | 39600000 | competitive bidding | SPN ADVERT | Post - Review | 3/1/2011 | NA | 24/1/2011 | 7/2/2011 | 21/2/2011 | 14/3/2011 | 28/3/2011 | 39600000 | NA | 12/4/2011 | 3/5/2011 | NA | 24/5/2011 | 14/6/2011
Total Cost |  |  | 648080000
Fill gray cells only!
Ministry/Department/Agency: VOICE OF NIGERIA
Budgetary Year: 2011 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: MR AYOOLA |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* |  | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
Upgrading of power supply to TX station Abuja and step down of 33KVA at Lugbe | FMIC/VON/P05 | LOT 1 | Bill of Quantity | Nat. comp. bidding | 50000000 | Pre - Qualification | Post - Review | 1/2/2011 | NA | 15/2/2011 | 2/3/2011 | 18/3/2011 | 8/4/2011 | NA | 50000000 | NA | 24/4/2011 | 16/5/2011 | NIL | 30/6/2011 | 7/7/2011 | 21/7/2011
Construction of the second phase of VON permanent transmitting station Abuja. Installation and commissioning f 2Nos of 250KW, SW super power transmitter and Engineering operational offices | FMIC/VON/P06 | LOT 1 | Bill of Quantity | Nat. comp. bidding | 1100000000 | Pre - Qualification | Post Reviw | 1/2/2011 | NA | 15/2/2011 | 2/3/2011 | 18/3/2011 | 8/4/2011 | NA | 1100000000 | NA | 24/4/2011 | 16/5/2011 | NIL | 30/6/2011 | 7/7/2011 | 21/7/2011
Construction of morden studio facilities and links and Admin corporate offices and Engineering workshop at Lugbe TX Abuja | FMIC/VON/P07 | LOT 1 | Bill of Quantity | Nat. comp. bidding | 600000000 | Pre - Qualification | Post Review | 1/2/2011 | NA | 15/2/2011 | 2/3/2011 | 18/3/2011 | 8/4/2011 | NA | 600000000 | NA | 24/4/2011 | 16/5/2011 | NIL | 30/6/2011 | 7/7/2011 | 21/7/2011
Total Cost |  |  |  |  | 1750000000 | [9 empty] | 1750000000

## Information_Tel&Post Serv
Ministry/Department/Agency: TELECOMS AND POSTAL SERVICES
Budgetary Year: 2011 --- Consultancy Services | [6 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: ENGR. (Mrs.) N. O. Ogujiofor |  | Contract Type |  |  | Preparation Request for Proposals |  |  |  | Short List |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [6 empty] | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Prior/Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement | Lead-time before shortlist | Submission Date | No-objection Date | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks |  | 4 wk |  | 3 wks
List of Contracts
Telecomunications Policy Implementation for National Rural Telephony Projects and Rigional programme
NRTP Project Monitoring and Evaluation. | Direct Labour | Time - Based | 10000000 | On going | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3 wks | N/A | N/A | 2 wks | N/A | 2 wks | N/A | 10000000 | N/A | N/A | N/A | N/A | 30th March | 30th November | 10,000,000.00
NRTP Network security Payment Arrears. | Direct Labour | Time - Based | 5000000 | On going | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3 wks | N/A | N/A | 2 wks | N/A | 2 wks | N/A | 5000000 | N/A | N/A | N/A | N/A | 30th June | 30/7/2011 | 5,000,000.00
Nigeria - Niger - Algeria Terrestrial Cable feasibility Study and Consultancy.
2nd Quarter Nigeria - Niger - Algeria, Fiber Optic Cable, Expression of Intrest | NCB, ICB | Time - Based | 5000000 |  | 2/1/2011 | NA | 16/1/2011 | 1/2/2011 | 15/2/2011 | N/A | N/A | N/A | 7/3/2011 | N/A | 21/3/2011 | 5/4/2011 | 19/4/2011 | 4/5/2011 | N/A | 5000000 | 19/5/2011 | 2/6/2011 | 23/6/2011 | N/A | 30/6/2011 | 7/7/2011 | 5,000,000.00
3rd Quarter Nigeria - Niger - Algeria, Fiber Optic Cable, feasibilty Study and Engagement of Consultant | NCB, ICB | Time - Based | 30000000 |  | 2/1/2011 | NA | 16/1/2011 | 1/2/2011 | 15/2/2011 | N/A | N/A | N/A | 7/3/2011 | N/A | 21/3/2011 | 5/4/2011 | 19/4/2011 | 4/5/2011 | N/A | 30000000 | 19/5/2011 | 2/6/2011 | 23/6/2011 | N/A | 30/6/2011 | 7/7/2011 | 30,000,000.00
4th Quarter Nigeria - Niger - Algeria, Fiber Optic Cable, feasibilty Study Engagement of Technical partner. | NCB, ICB | Time - Based | 5000000 |  | 2/1/2011 | NA | 16/1/2011 | 1/2/2011 | 15/2/2011 | N/A | N/A | N/A | 7/3/2011 | N/A | 21/3/2011 | 5/4/2011 | 19/4/2011 | 4/5/2011 | N/A | 5000000 | 19/5/2011 | 2/6/2011 | 23/6/2011 | N/A | 30/6/2011 | 7/7/2011 | 5,000,000.00
Total Cost |  |  | 55000000 | [16 empty] | 55000000 | [6 empty] | 55000000

## Information_Sp Mgt
Ministry/Department/Agency: FMIC/Spectrum Management
Budgetary Year: 2011 -- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: Engr. K.N. Binga |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
IRMS INFRASTRUCTURAL DEVELOPMENT | FMIC/SM/P/01
date
Purchase of 3 Nos industrial Sharp Photocopiers for use at Abuja Headquarters |  | 01 | 1800000 | NCB | Post | Post Review | 2 weeks | N/A | 2 weeks | 2 weeks | 6 weeks | 2 weeks | N/A | 1800000 | N/A | 1 week | 1 week | Nil | 2 weeks | 1 week
Norm Duration of Proc Steps
[5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 3 wks
List of Contracts |  |  |  |  | add 2 wks
TESTS AND MEASUREMENTS EQUIPMENT LABORATORY
FMIC/SM/P/02
(1) Purchase of 12 Nos HP Laptops with softwares | [14 empty] | date
|  | 03 | 3600000 |  | Post | Post Review | 2 weeks | N/A | 2 weeks | 2 weeks | 6 weeks | 2 weeks | N/A | 3600000 | N/A | 1 week | 1 week | Nil | 3 weeks | 1 week
(2) Purchase of 12 Nos HP Desktop computers
|  | 04 | 2200000 |  | Post | Post Review | 2 weeks | N/A | 2 weeks | 2 weeks | 6 weeks | 2 weeks | N/A | 2200000 | N/A | 1 week | 1 week | Nil | 3 weeks | 1 week
Purchase of 4 Nos Digital Multimeters, 4 Nos Digital Frequency Counters, 2Nos Signal Generators including Two weeks Training
|  | 05 | 4100000 |  | Post | Post Review | 2 weeks | N/A | 2 weeks | 2 weeks | 6 weeks | 2 weeks | N/A | 4100000 | N/A | 1 week | 1 week | Nil | 3 weeks | 1 week
Total Cost |  |  | 11700000
Ministry/Department/Agency: FMIC/RES. & PROD. DEP.
Budgetary Year: 2011 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: L. NDAM |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual
List of Contracts
PUBLICATIONS | FMIC/R&P/01 | [5 empty] | Plan
Actual
date
1. Sectoral Booklet on Blueprint on Power - 20,000 Copies |  | LOT 1 | N5m | NCB | POST | POST | Plan | 21/2/2011 | N/A | 7/3/2011 | 21/3/2011 | 4/4/2011 | 18/4/2011 | N/A | N5m | N/A | 26/4/2011 | 17/5/2011 | N/A | 31/5/2011 | 7/6/2011
Actual
2. Inaugural Address of In - coming President on May 29, 2011 - 20,000 Copies |  | LOT 2 | N5m | NCB | POST | POST | Plan | 21/2/2011 | N/A | 7/3/2011 | 21/3/2011 | 4/4/2011 | 18/4/2011 | N/A | N5m | N/A | 26/4/2011 | 17/5/2011 | N/A | 31/5/2011 | 7/6/2011
Actual
Plan
Actual
FILM & DOCUMENTARIES | FMIC/R&P/02 | [5 empty] | Plan
Actual
1. Documentary on The Making of a President |  | LOT 1 | N5m | NCB | POST | POST | Plan | 21/2/2011 | N/A | 7/3/2011 | 21/3/2011 | 4/4/2011 | 18/4/2011 | N/A | N5m | N/A | 26/4/2011 | 17/5/2011 | N/A | 31/5/2011 | 7/6/2011
Actual
2. Documentary on Wealth Creation |  | LOT 2 | N3m | NCB | POST | POST | Plan | 21/2/2011 | N/A | 7/3/2011 | 21/3/2011 | 4/4/2011 | 18/4/2011 | N/A | N3m | N/A | 26/4/2011 | 17/5/2011 | N/A | 31/5/2011 | 7/6/2011
Actual
3. Distribution of Publicity Materials |  | LOT 3 | N2m | NCB | POST | POST | Plan | 21/2/2011 | N/A | 7/3/2011 | 21/3/2011 | 4/4/2011 | 18/4/2011 | N/A | N2m | N/A | 26/4/2011 | 17/5/2011 | N/A | 31/5/2011 | 7/6/2011
Actual
Plan
Actual
Total Cost |  |  | N20m |  |  |  | Plan | [7 empty] | N20m
[7 empty] | Actual | [7 empty] | 0
[7 empty] | Actual | [7 empty] | 11700000
Budgetary Year: 2011 --- Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: Engr. K.N. Binga |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
IRMS INFRASTRUCTURAL DEVELOPMENT | FMIC/SM/P/01
(1) Installation of Lighning Arrestor at IRMS Gusau |  | 01 | BOQ | NCB | 300000 | Pre Qualification | Prior Review | 21/2/2011 | N/A | 7/3/2011 | 21/3/2011 | 7/4/2011 | 21/4/2011 | N/A | 300000 | N/A | 28/4/2011 | 19/5/2011 | Nil | 2/6/2011 | 9/6/2011 | 300,000.00
(2) Renovation of three (3) Offices at IRMS Gusau |  | 02 | BOQ | NCB | 1900000 | Pre-Qualification | Prior Review | 21/2/2011 | N/A | 7/3/2011 | 21/3/2011 | 7/4/2011 | 21/4/2011 | N/A | 1900000 | N/A | 28/4/2011 | 19/5/2011 | Nil | 2/6/2011 | 9/6/2011 | 1,900,000.00
(3) Reconstruction of collapsed 70m perimeter fence at IRMS Ipaja, Lagos |  | 03 | BOQ | NCB | 1500000 | Pre-Qualification | Prior Review | 21/2/2011 | N/A | 7/3/2011 | 21/3/2011 | 7/4/2011 | 21/4/2011 | N/A | 1500000 | N/A | 28/4/2011 | 19/5/2011 | Nil | 2/6/2011 | 9/6/2011 | 1,500,000.00
(4) Rehabilitation of Community Centre including renovation of the building, provision of furniture, fence, landscaping of the area, etc at IRMS Ipaja, Lagos. |  | 04 | BOQ | NCB | 7000000 | Pre-Qualification | Prior Review | 21/2/2011 | N/A | 7/3/2011 | 21/3/2011 | 7/4/2011 | 21/4/2011 | N/A | 7000000 | N/A | 28/4/2011 | 19/5/2011 | Nil | 2/6/2011 | 9/6/2011 | 7,000,000.00
Installation of 5 Nos solar power security lights at IRMS Ipaja, Lagos |  | 05 | BOQ | NCB | 2000000 | Pre-Qualification | Prior Review | 21/2/2011 | N/A | 7/3/2011 | 21/3/2011 | 7/4/2011 | 21/4/2011 | N/A | 2000000 | N/A | 28/4/2011 | 19/5/2011 | Nil | 2/6/2011 | 9/6/2011 | 2,000,000.00
Laying of water pipe network from the overhead tank reservoir to the residential quarters and radio monitoring building at IRMS Ogoja |  | 06 | BOQ | NCB | 3500000 | Pre-Qualification | Prior Review | 21/2/2011 | N/A | 7/3/2011 | 21/3/2011 | 7/4/2011 | 21/4/2011 | N/A | 3500000 | N/A | 28/4/2011 | 19/5/2011 | Nil | 2/6/2011 | 9/6/2011 | 3,500,000.00
Rehabilitation of Community Centre including renovation of the building, provision of furniture, fence, landscaping of the area, etc at IRMS Azare |  | 07 | BOQ | NCB | 7000000 | Pre-Qualification | Prior Review | 21/2/2011 | N/A | 7/3/2011 | 21/3/2011 | 7/4/2011 | 21/4/2011 | N/A | 7000000 | N/A | 28/4/2011 | 19/5/2011 | Nil | 2/6/2011 | 9/6/2011 | 7,000,000.00
Total Cost |  |  |  |  | 23200000 | [9 empty] | 23200000 | [6 empty] | 23200000
Ministry/Department/Agency: FMIC/Spectrum Management
Budgetary Year: 2011 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: Engr. K.N. Binga |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
TESTS AND MEASUREMENTS EQUIPMENT LABORATORY | FMIC/SM/P/02
Installation of 1 No 15 KVA Inverters as back-up power supply system at the Annex Office of the Ministry at Wuse II, Abuja |  | 01 | Bill of Quantities | NCB | 2600000 | Pre-Qualification | Prio Review | 21/2/2011 | N/A | 7/3/2011 | 21/3/2011 | 7/4/2011 | 21/4/2011 | N/A | 2600000 | N/A | 28/4/2011 | 19/5/2011 | Nil | 2/6/2011 | 9/6/2011 | 2,600,000.00
Provision of Internet Service with Wi-Fi Connection including one year bandwidth subscription at the Annex Office of the Ministry at Wuse II, Abuja |  | 02 | Bill of Quantities | Selective | 2500000 | Pre-Qualification | Prior Review | 21/2/2011 | N/A | 7/3/2011 | 21/3/2011 | 7/4/2011 | 21/4/2011 | N/A | 2500000 | N/A | 28/4/2011 | 19/5/2011 | Nil | 2/6/2011 | 9/6/2011 | 2,500,000.00
Total Cost |  |  |  |  | 5100000 | [9 empty] | 5100000

## Information_fin&Acct
Ministry/Department/Agency: FMIC/FINANCE AND ACCOUNTS DEPT.
2011 -- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
NDA YAKUBU |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
COMPUTERISATION OF FINANCE AND ACCOUNT DEPARTMENT. | FMIC/F&A/01
date
PROCUREMENT OF COMPUTER HARDWARES: DESKTOPS AND LAPTOPS |  | LOT1 | 8910000 | NCB | POST | POST | 1/3/2011 | NA | 21/3/2011 | 5/4/2011 | 12/5/2011 | 26/5/2011 | NA | 8910000 | NA | 9/6/2011 | 30/6/2011 | NIL | 14/7/2011 | 21/7/2011
COMPUTER ACCESSORIES:PRINTERS, UPS,STABLIZERS ETC. |  | LOT2 | 1170000 |  | POST | POST | 1/3/2011 | NA | 21/3/2011 | 5/4/2011 | 12/5/2011 | 26/5/2011 | NA | 1170000 | NA | 9/6/2011 | 30/6/2011 | NIL | 14/7/2011 | 21/7/2011
ACCOUNTING SOFTWARES/INSTALLAATION,NETWORKING. |  | LOT3 | 6124248 |  | POST | POST | 1/3/2011 | NA | 21/3/2011 | 5/4/2011 | 12/5/2011 | 26/5/2011 | NA | 6124248 | NA | 9/6/2011 | 30/6/2011 | NIL | 14/7/2011 | 21/7/2011
Total Cost |  |  | 16204248 | [10 empty] | 16204248
Fill gray cells only!

## Information_Legal Unit
Ministry/Department/Agency: FMIC/LEGAL UNIT
Budgetary Year: 2011 -- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: MRS I. J. UCHE-OKORO |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
LEGAL SERVICES | FMIC/LU/01
date
PROCUREMENT OF BOOK SHELVES |  | LOT 1 | 2000000 | NCB | QUOTATION | POST | 21/2/2011 | NA | NA | 7/3/2011 | 21/3/2011 | 7/4/2011 | NA | 3000000 | NA | 21/4/2011 | 2/5/2011 | NIL | 16/5/2011 | 23/5/2011
PROCUREMENT OF SAFE |  | LOT 2 | 4000000 | NCB | QUOTATION | POST | 21/2/2011 | NA | NA | 7/3/2011 | 21/3/2011 | 7/4/2011 | NA | 2000000 | NA | 21/4/2011 | 2/5/2011 | NIL | 16/5/2011 | 23/5/2011
PROCUREMENT SAFE |  | LOT 3 | 300000 | NCB | QUOTATION | POST | 21/2/2011 | NA | NA | 7/3/2011 | 21/3/2011 | 7/4/2011 | NA | 2000000 | NA | 21/4/2011 | 2/5/2011 | NIL | 16/5/2011 | 23/5/2011
Total Cost |  |  | 6300000 | [10 empty] | 7000000
Fill gray cells only!

## Information_PR unit
Ministry/Department/Agency: FMIC/PUBLIC RELATIONS AND PROTOCOL UNIT
Budgetary Year: 2011 -- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: MRS. V. AGBA-ATTAH (AD) |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
Collaboration with Orgnaisations (MDA, NGOs, CSO) on various aspects of Rebranding | FMIC/PRPU/1 | LOT 1 | N20,000,000 | NCB | Post Qual. | Post Review | 3 Wks | NA | 2 wks | 2 Wks | 6 Wks | 2 Wks | NA | N20,000,000 | NA | 1 Wk | 1 Wk | YES | 2 Wks | 2 Wks
Production of Souvenirs and promotional items | FMIC/PRPU/2 | LOT 1 | N15,000,000 | NCB | PQ | PR | 3 wks | NA | 2 wks | 2 wks | 6 wks | 2 wks | NA | N15,000,000 | NA | 1 wk | 1 wk | YES | 2 wks | 2 wks
Production of Newsletter | FMIC/PRPU/3 | LOT 1 | N24,000,000 | Direct Labour | PQ | PR | 3 wks | NA | 2 wks | 2 wks | 6 wks | 2 wks | NA | N24,000,000 | NA | 1 wk | 1 wk | YES | 2 wks | 2 wks
Production of HIV/AIDS IEC Materials | FMIC/PRPU/4 | LOT 1 | N20,000,000 | NCB | PQ | PR | 3 wks | NA | 2 wks | 2 wks | 6 wks | 2 wks | NA | N20,000,000 | NA | 1 wk | 1 wk | YES | 2 wks | 2 wks
Publicity and Media engagements (HMIC and PSIC) | FMIC/PRPU/5 | LOT 1 | N20,000,000 | Direct Labour | PQ | PR | 3 wks | NA | 2 wks | 2 wks | 6 wks | 2 wks | NA | N20,000,000 | NA | 1 wk | 1 wk | YES | 2 wks | 2 wks
Production of promotional items: Billboards across Nigeria | FMIC/PRPU/6 | LOT 1 | N50,000,000 | NCB | PQ | PR | 3 wks | NA | 2 wks | 2 wks | 6 wks | 2 wks | NA | N50,000,000 | NA | 1 wk | 1 wk | YES | 2 wks | 2 wks
Advertising and Publicity | FMIC/PRPU/7 | LOT 1 | N30,000,000 | NCB | PQ | PR | 3 wks | NA | 2 wks | 2 wks | 6 wks | 2 wks | NA | N30,000,000 | NA | 1 wk | 1 wk | YES | 2 wks | 2 wks
Production of President's Portraits | FMIC/PRPU/8 | LOT 1 | N10,000,000 | NCB | PQ | PR | 3 wks | NA | 2 wks | 2 wks | 6 wks | 2 wks | NA | N10,000,000 | NA | 1 wk | 1 wk | YES | 2 wks | 2 wks
Production of Hon. Minister's Portrait | FMIC/PRPU/9 | LOT 1 | N5,000,000 | NCB | PQ | PR | 3 wks | NA | 2 wks | 2 wks | 6 wks | 2 wks | NA | N5,000,000 | NA | 1 wk | 1 wk | YES | 2 wks | 2 wks
Production of Coat of Arms | FMIC/PRPU/10 | LOT 1 | N10,000,000 | NCB | PQ | PR | 3 wks | NA | 2 wks | 2 wks | 6 wks | 2 wks | NA | N10,000,000 | NA | 1 wk | 1 wk | YES | 2 wks | 2 wks
Production of Nationla Flag | FMIC/PRPU/11 | LOT 1 | N10,000,000 | NCB | PQ | PR | 3 wks | NA | 2 wks | 2 wks | 6 wks | 2 wks | NA | N10,000,000 | NA | 1 wk | 1 wk | YES | 2 wks | 2 wks
Gift Items | FMIC/PRPU/12 | LOT 1 | N10,000,000 | NCB | PQ | PR | 3 wks | NA | 2 wks | 2 wks | 6 wks | 2 wks | NA | N10,000,000 | NA | 1 wk | 1 wk | YES | 2 wks | 2 wks
Food Information Project activities | FMIC/PRPU/13 | LOT 1 | N20,000,000 | Direct Labour | PQ | PR | 3 wks | NA | 2 wks | 2 wks | 6 wks | 2 wks | NA | N20,000,000 | NA | 1 wk | 1 wk | YES | 2 wks | 2 wks
Interface with the Mass Media | FMIC/PRPU/14 | LOT 1 | N20,000,000 | Direct Labour | PQ | PR | 3 wks | NA | 2 wks | 2 wks | 6 wks | 2 wks | NA | N20,000,000 | NA | 1 wk | 1 wk | YES | 2 wks | 2 wks
Update Directory of Federal Ministries & Parastatals | FMIC/PRPU/15 | LOT 1 | N2,000,000 | Direct Labour | PQ | PR | 3 wks | NA | 2 wks | 2 wks | 6 wks | 2 wks | NA | N2,000,000 | NA | 1 wk | 1 wk | YES | 2 wks | 2 wks
Workshop on HIV/AIDS for Senior Staff of FMIC & Parastatals | FMIC/PRPU/16 | LOT 1 | N5,000,000 | Direct Labour | PQ | PR | 3 wks | NA | 2 wks | 2 wks | 6 wks | 2 wks | NA | N5,000,000 | NA | 1 wk | 1 wk | YES | 2 wks | 2 wks
Periodic Get-together/Interactive Session with Editors and Foreign Correcpondents (2nd and 4th Quarter) | FMIC/PRPU/17 | LOT 1 | N10,000,000 | Direct Labour | PQ | PR | 3 wks | NA | 2 wks | 2 wks | 6 wks | 2 wks | NA | N10,000,000 | NA | 1 wk | 1 wk | YES | 2 wks | 2 wks

## Information_Res.&Prod
Ministry/Department/Agency: FMIC/RES. & PROD. DEP.
Budgetary Year: 2011 --- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: L. NDAM |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
PUBLICATIONS | FMIC/R&P/01
date
1. Sectoral Booklet on Blueprint on Power - 20,000 Copies |  | LOT 1 | N5m | NCB | POST | POST | 1/2/2011 | N/A | SPN ADVERT | 15/2/2011 | 15/3/2011 | 30/3/2011 | N/A | N5m | N/A | 7/4/2011 | 21/4/2011 | N/A | 6/5/2011 | 13/5/2011
2. Inaugural Address of In - coming President on May 29, 2011 - 20,000 Copies |  | LOT 2 | N5m | NCB | POST | POST | 1/2/2011 | N/A | SPN ADVERT | 15/2/2011 | 15/3/2011 | 30/3/2011 | N/A | N5m | N/A | 7/4/2011 | 21/4/2011 | N/A | 6/5/2011 | 13/5/2011
FILM & DOCUMENTARIES | FMIC/R&P/02
1. Documentary on The Making of a President |  | LOT 1 | N5m | NCB | POST | POST | 1/2/2011 | N/A | SPN ADVERT | 15/2/2011 | 15/3/2011 | 30/3/2011 | N/A | N5m | N/A | 7/4/2011 | 21/4/2011 | N/A | 6/5/2011 | 13/5/2011
2. Documentary on Wealth Creation |  | LOT 2 | N3m | NCB | POST | POST | 1/2/2011 | N/A | SPN ADVERT | 15/2/2011 | 15/3/2011 | 30/3/2011 | N/A | N3m | N/A | 7/4/2011 | 21/4/2011 | N/A | 6/5/2011 | 13/5/2011
3. Distribution of Publicity Materials |  | LOT 3 | N2m | NCB | POST | POST | 1/2/2011 | N/A | SPN ADVERT | 15/2/2011 | 15/3/2011 | 30/3/2011 | N/A | N2m | N/A | 7/4/2011 | 21/4/2011 | N/A | 6/5/2011 | 13/5/2011
Total Cost |  |  | N20m | [10 empty] | N20m

## Information_HR
Ministry/Department/Agency: FMIC/HUMAN RESOURCES MANAGEMENT DEPT.
Budgetary Year: 2011 -- Consultancy Services | [6 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: A. K. SHERIF |  | Contract Type |  |  | Preparation Request for Proposals |  |  |  | Short List |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [6 empty] | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Prior/ Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement | Lead-time before shortlist | Submission Date | No-objection Date | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks |  | 4 wk |  | 3 wks
List of Contracts
LOCAL TRAINING
TEAM BUILDING FOR ENHANCED PRODUCTIVITY | NCB | T-BASED | 11,000,000.00 | POST | 27/2/2011 | NA | 14/3/2011 | 28/3/2011 | 5/4/2011 | NA | 29/4/2011 | 16/6/2011 | 7/7/2011 | NA | 21/7/2011 | 8/8/2011 | 22/8/2011 | 5/9/2011 | NA | 11,000,000.00 | 22/9/2011 | 15/9/2011 | 7/10/2011 | NIL | 21/10/2011 | 7/11/2011 | 11,000,000.00
BASIC MANAGEMENT COURSE FOR SECRETARY AND PERSONNEL ASSISTANT | NCB | T-BASED | 11,000,000.00 | POST | 27/2/2011 | NA | 14/3/2011 | 28/3/2011 | 5/4/2011 | NA | 29/4/2011 | 16/6/2011 | 7/7/2011 | NA | 21/7/2011 | 8/8/2011 | 22/8/2011 | 5/9/2011 | NA | 11,000,000.00 | 22/9/2011 | 15/9/2011 | 7/10/2011 | NIL | 21/10/2011 | 7/11/2011 | 11,000,000.00
BASIC COMPUTER APPRECIATION | NCB | T-BASED | 11,000,000.00 | POST | 27/2/2011 | NA | 14/3/2011 | 28/3/2011 | 5/4/2011 | NA | 29/4/2011 | 16/6/2011 | 7/7/2011 | NA | 21/7/2011 | 8/8/2011 | 22/8/2011 | 5/9/2011 | NA | 11,000,000.00 | 22/9/2011 | 15/9/2011 | 7/10/2011 | NIL | 21/10/2011 | 7/11/2011 | 11,000,000.00
PRE-RETIREMENT TRAINING ON ENTERPRENEURSHIP INVESTMENT AND BUS. DEV. | NCB | T-BASED | 11,238,284.57 | POST | 27/2/2011 | NA | 14/3/2011 | 28/3/2011 | 5/4/2011 | NA | 29/4/2011 | 16/6/2011 | 7/7/2011 | NA | 21/7/2011 | 8/8/2011 | 22/8/2011 | 5/9/2011 | NA | 11,238,284.57 | 22/9/2011 | 15/9/2011 | 7/10/2011 | NIL | 21/10/2011 | 7/11/2011 | 11,238,284.57
BUDGET IMPLEMENTATION AND PROC. PROCCESS | NCB | T-BASED | 11,000,000.00 | POST | 27/2/2011 | NA | 14/3/2011 | 28/3/2011 | 5/4/2011 | NA | 29/4/2011 | 16/6/2011 | 7/7/2011 | NA | 21/7/2011 | 8/8/2011 | 22/8/2011 | 5/9/2011 | NA | 11,000,000.00 | 22/9/2011 | 15/9/2011 | 7/10/2011 | NIL | 21/10/2011 | 7/11/2011 | 11,000,000.00
RETREAT FOR TOP GOVT. OFFICIALS | NCB | T-BASED | 11,000,000.00 | POST | 27/2/2011 | NA | 14/3/2011 | 28/3/2011 | 5/4/2011 | NA | 29/4/2011 | 16/6/2011 | 7/7/2011 | NA | 21/7/2011 | 8/8/2011 | 22/8/2011 | 5/9/2011 | NA | 11,000,000.00 | 22/9/2011 | 15/9/2011 | 7/10/2011 | NIL | 21/10/2011 | 7/11/2011 | 11,000,000.00
IN-HOUSE TRAINING FOR CAPACITY BUILDING | NCB | T-BASED | 11,000,000.00 | POST | 27/2/2011 | NA | 14/3/2011 | 28/3/2011 | 5/4/2011 | NA | 29/4/2011 | 16/6/2011 | 7/7/2011 | NA | 21/7/2011 | 8/8/2011 | 22/8/2011 | 5/9/2011 | NA | 11,000,000.00 | 22/9/2011 | 15/9/2011 | 7/10/2011 | NIL | 21/10/2011 | 7/11/2011 | 11,000,000.00
BOOK-KEEPING AND RECORD MANAGEMENT | NCB | T-BASED | 11,000,000.00 | POST | 27/2/2011 | NA | 14/3/2011 | 28/3/2011 | 5/4/2011 | NA | 29/4/2011 | 16/6/2011 | 7/7/2011 | NA | 21/7/2011 | 8/8/2011 | 22/8/2011 | 5/9/2011 | NA | 11,000,000.00 | 22/9/2011 | 15/9/2011 | 7/10/2011 | NIL | 21/10/2011 | 7/11/2011 | 11,000,000.00
INTERNATIONAL TRAINING
INT. FINANCIAL MGT TRAINING FOR MANAGEMENT OFFICIALS | NCB/ICB | T-BASED | 6750000 | POST | 21/2/2011 | NA | 14/3/2011 | 30/3/2011 | 7/4/2011 | NA | 7/5/2011 | 7/7/2011 | 29/7/2011 | NA | 15/8/2011 | 30/8/2011 | 14/9/2011 | 28/9/2011 | NA | 6750000 | 28/10/2011 | 28/9/2011 | 21/11/2011 | NIL | 30/11/2011 | 8/12/2011 | 6750000
CHANGE LEADERSHIP AND STRESS MGT. TRAINING | NCB/ICB | T-BASED | 6750000 | POST | 21/2/2011 | NA | 14/3/2011 | 30/3/2011 | 7/4/2011 | NA | 7/5/2011 | 7/7/2011 | 29/7/2011 | NA | 15/8/2011 | 30/8/2011 | 14/9/2011 | 28/9/2011 | NA | 6750000 | 28/10/2011 | 28/9/2011 | 21/11/2011 | NIL | 30/11/2011 | 8/12/2011 | 6750000
EFFECTIVE SPEECH WRITING/ PRESENTATION SKILLS | NCB/ICB | T-BASED | 6750000 | POST | 21/2/2011 | NA | 14/3/2011 | 30/3/2011 | 7/4/2011 | NA | 7/5/2011 | 7/7/2011 | 29/7/2011 | NA | 15/8/2011 | 30/8/2011 | 14/9/2011 | 28/9/2011 | NA | 6750000 | 28/10/2011 | 28/9/2011 | 21/11/2011 | NIL | 30/11/2011 | 8/12/2011 | 6750000
WEB CONTENT MGT. TRAINING | NCB/ICB | T-BASED | 6750000 | POST | 21/2/2011 | NA | 14/3/2011 | 30/3/2011 | 7/4/2011 | NA | 7/5/2011 | 7/7/2011 | 29/7/2011 | NA | 15/8/2011 | 30/8/2011 | 14/9/2011 | 28/9/2011 | NA | 6750000 | 28/10/2011 | 28/9/2011 | 21/11/2011 | NIL | 30/11/2011 | 8/12/2011 | 6750000
PROCUREMENT PRACTICES AND INT. BEST PRACTICES | NCB/ICB | T-BASED | 6750000 | POST | 21/2/2011 | NA | 14/3/2011 | 30/3/2011 | 7/4/2011 | NA | 7/5/2011 | 7/7/2011 | 29/7/2011 | NA | 15/8/2011 | 30/8/2011 | 14/9/2011 | 28/9/2011 | NA | 6750000 | 28/10/2011 | 28/9/2011 | 21/11/2011 | NIL | 30/11/2011 | 8/12/2011 | 6750000
SYSTEM STUDY VISITS | NCB/ICB | T-BASED | 7635142.29 | POST | 21/2/2011 | NA | 14/3/2011 | 30/3/2011 | 7/4/2011 | NA | 7/5/2011 | 7/7/2011 | 29/7/2011 | NA | 15/8/2011 | 30/8/2011 | 14/9/2011 | 28/9/2011 | NA | 7635142.29 | 28/10/2011 | 28/9/2011 | 21/11/2011 | NIL | 30/11/2011 | 8/12/2011 | 7635142.29
OFFICE MGT. PROCESS, PLANNING, TIMING FOR ORG. EFFECIENCY | NCB/ICB | T-BASED | 6750000 | POST | 21/2/2011 | NA | 14/3/2011 | 30/3/2011 | 7/4/2011 | NA | 7/5/2011 | 7/7/2011 | 29/7/2011 | NA | 15/8/2011 | 30/8/2011 | 14/9/2011 | 28/9/2011 | NA | 6750000 | 28/10/2011 | 28/9/2011 | 21/11/2011 | NIL | 30/11/2011 | 8/12/2011 | 6750000
MANAGEMENT ACCOUNTING AND BUSINESS STRATEGY | NCB/ICB | T-BASED | 6750000 | POST | 21/2/2011 | NA | 14/3/2011 | 30/3/2011 | 7/4/2011 | NA | 7/5/2011 | 7/7/2011 | 29/7/2011 | NA | 15/8/2011 | 30/8/2011 | 14/9/2011 | 28/9/2011 | NA | 6750000 | 28/10/2011 | 28/9/2011 | 21/11/2011 | NIL | 30/11/2011 | 8/12/2011 | 6750000
Total Cost
Budgetary Year: 2011 --- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: A. K. SHARIF |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
MATERIALS AND SUPPLIES -GENERAL | FMIC/HRM/01
date
SUPPLIES OF STATIONARIES-PRINTING PAPERS ( GENERAL) |  | LOT I | 45000000 | NCB | POST | POST | 1/3/2011 | NA | 15/3/2011 | 29/3/2011 | 30/3/2011 | 14/4/2011 | NA | 45000000 | NA | 29/4/2011 | 14/5/2011 | NA | 2 WKS | 1 WEEK
SUPPLY OF OTHER STORES ITEMS EG PINS, STAPLER,BIRO, PENCIL ETC |  | LOT 2 | 30392840.29 | NCB | POST | POST | 1/3/2011 | NA | 15/3/2011 | 29/3/2011 | 30/3/2011 | 14/4/2011 | NA | 30392840.29 | NA | 29/4/2011 | 14/5/2011 | NA | 2 WKS | 1 WEEK
COMPUTER CONSUMABLES 1 : Computer Tonner, |  | LOT 3 | 25000000 | NCB | POST | POST | 1/3/2011 | NA | 15/3/2011 | 29/3/2011 | 30/3/2011 | 14/4/2011 | NA | 25000000 | NA | 29/4/2011 | 14/5/2011 | NA | 2 WKS | 1 WEEK
COMPUTER CONSUMABLES 2: Anti-virus, Flash drives and other accessories |  | LOT 4 | 7311219.84 | NCB | POST | POST | 1/3/2011 | NA | 15/3/2011 | 29/3/2011 | 30/3/2011 | 14/4/2011 | NA | 7311219.84 | NA | 29/4/2011 | 14/5/2011 | NA | 2 WKS | 1 WEEK
DRUGS AND MEDICAL SUPPLIES | FMIC/HRM/02 | LOT 1 | 10383000 | NCB | POST | POST | 7/3/2011 | NA | 21/3/2011 | 5/4/2011 | 20/4/2011 | 5/5/2011 | NA | 10383000 | NA | 13/5/2011 | 28/5/2011 | NA | 2 WKS | 2 WKS
MAINTENANCE SERVICES- GENERAL | FMIC/HRM/03
MOTOR VEHICLE/TRANSPORT EQUIPMENT |  | LOT 1 | 30583107.19 | NCB | POST | POST | 7/3/2011 | NA | 21/3/2011 | 5/4/2011 | 20/4/2011 | 5/5/2011 | NA | 10583000 | NA | 13/5/2011 | 28/5/2011 | NA | 2 WKS | 2 WKS
MAINTENANCE OF OFFICE FURNITURE |  | LOT 2 | 10,383,000.00` | NCB | POST | POST | 7/3/2011 | NA | 21/3/2011 | 5/4/2011 | 20/4/2011 | 5/5/2011 | NA | 10383000 | NA | 13/5/2011 | 28/5/2011 | NA | 2 WKS | 2 WKS
MAINTENANCE OF PLANTS/GENERATORS | FMIC/HRM/04
date
MTCE OF 2 NOS. 1000KVA FROM JAN. TO DEC. 2011 |  | LOT 1 | 14000000 | NCB | BOQ | POST | 21/2/2011 | NA | 14/3/2011 | 30/3/2011 | 14/4/2011 | 28/4/2011 | NA | 14000000 | NA | 16/5/2011 | 7/6/2011 | NIL | 12 MONTHS | 31/12/2011
MTCE OF 1 NO. 200KVA FROM JAN. TO DEC. 2011 |  | LOT2 | 3831055.44 | NCB | BOQ | POST | 21/2/2011 | NA | 14/3/2011 | 30/3/2011 | 14/4/2011 | 28/4/2011 | NA | 3831055.44 | NA | 16/5/2011 | 7/6/2011 | NIL | 12 MONTHS | 31/12/2011
MTCE OF 1 NO. 100KVA FROM JAN. TO DEC. 2011 |  | LOT 3 | 2000000 | NCB | BOQ | POST | 21/2/2011 | NA | 14/3/2011 | 30/3/2011 | 14/4/2011 | 28/4/2011 | NA | 2000000 | NA | 16/5/2011 | 7/6/2011 | NIL | 12 MONTHS | 31/12/2011
MTCE OF GEN. AT THE 6 ZONAL OFFICES |  | LOT 4 | 6000000 | NCB | BOQ | POST | 21/2/2011 | NA | 14/3/2011 | 30/3/2011 | 14/4/2011 | 28/4/2011 | NA | 6000000 | NA | 16/5/2011 | 7/6/2011 | NIL | 12 MONTHS | 31/12/2011
MTCE OF GEN AT 5 RADIO MONITORING STATIONS. JAN-DEC, 2011 |  | LOT 5 | 5000000 | NCB | BOQ | POST | 21/2/2011 | NA | 14/3/2011 | 30/3/2011 | 14/4/2011 | 28/4/2011 | NA | 5000000 | NA | 16/5/2011 | 7/6/2011 | NIL | 12 MONTHS | 31/12/2011
OTHER SERVICES GENERAL | FMIC/HRM/05
FURMIGATION OF FMIC RADIO HOUSE OFFICES, ABUJA , ZONAL OFFICES, STATIONS AND CENTRES |  | LOT 1 | 50000000 | NCB | BOQ | POST | 21/2/2011 | NA | 14/3/2011 | 30/3/2011 | 14/4/2011 | 28/4/2011 | NA | 50000000 | NA | 16/5/2011 | 7/6/2011 | NIL | 12 MONTHS | 31/12/2011
MTCE OF OFFICE EQUIPMENT SUCH AS PHOTOCOPIERS AND COMMUNICATION EQUIPMENT |  | LOT 2 | 34619189.16 | NCB | BOQ | POST | 21/2/2011 | NA | 14/3/2011 | 30/3/2011 | 14/4/2011 | 28/4/2011 | NA | 34619189.16 | NA | 16/5/2011 | 7/6/2011 | NIL | 12 MONTHS | 31/12/2011
PROCUREMNENT OF SPORTING MATERIALS AND EQUIPMENT | FMIC/HRM/06 | LOT 1 | 10229800 | NCB | QUOTATION | POST | 21/2/2011 | NA | 7/3/2011 | 21/3/2011 | 4/4/2011 | 25/4/2011 | NA | 10229800 | NA | 3/5/2011 | 25/5/2011 | NIL | 9/6/2011 | 17/6/2011
date
DEMOCRACY DAY-PROCUREMENT OF SOUVENIERS | FMIC/HRM/07 | LOT 1 | 4263495 | NCB | QUOTATION | POST | 21/2/2011 | NA | NA | 7/3/2011 | 21/3/2011 | 4/4/2011 | NA | 4263495 | NA | 25/4/2011 | 3/5/2011 | NIL | 25/5/2011 | 27/5/2011
INDEPENDENCE DAY CELEBRATION-PROCUREMENT OF SOUVENIERS | FMIC/HRM/08 | LOT 1 | 10417550 | NCB | QUOTATION | POST | 21/2/2011 | NA | 7/3/2011 | 21/3/2011 | 4/4/2011 | 25/4/2011 | NA | 10417550 | NA | 3/5/2011 | 25/5/2011 | NIL | 9/6/2011 | 17/6/2011
PLANT/GENERATOR FUEL (DIESEL) FOR 4 GENERATORS - JAN-DEC, 2011 | FMIC/HRM/09 | LOT 1 | 48888113.61 | NCB | QUOTATION | POST | 21/2/2011 | NA | 7/3/2011 | 21/3/2011 | 4/4/2011 | 25/4/2011 | NA | 48888113.61 | NA | 3/5/2011 | 25/5/2011 | NIL | 9/6/2011 | 17/6/2011
Total Cost
Budgetary Year: Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
|  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
MINTAINANCE OF OFFICE BUILDING | FMIC/HRM/01
MTCE OF RADIO HOUSE BUILDING |  | LOT 1 | BOQ | NCB | 80000000 | POST | POST | 21/2/2011 | NA | 8/3/2011 | 22/3/2011 | 5/4/2011 | 19/4/2011 | NA | 80000000 | NA | 26/4/2011 | 17/5/2011 | NIL | 17/6/2011 | 1/7/2011 | 80000000
MTCE OF FED. RESOURCES CENTRES AND FIRC & FICS |  | LOT2 | BOQ | NCB | 30000000 | POST | POST | 21/2/2011 | NA | 8/3/2011 | 22/3/2011 | 5/4/2011 | 19/4/2011 | NA | 30000000 | NA | 26/4/2011 | 17/5/2011 | NIL | 17/6/2011 | 1/7/2011 | 30000000
MTCE OF NAT. PRESS CENTRE BUILDING |  | LOT 3 | BOQ | NCB | 3970347.29 | POST | POST | 21/2/2011 | NA | 8/3/2011 | 22/3/2011 | 5/4/2011 | 19/4/2011 | NA | 3970347.29 | NA | 26/4/2011 | 17/5/2011 | NIL | 17/6/2011 | 1/7/2011 | 3970347.29
MTCE OF RADIO HOUSE ANNEX 1 & 2 BUILDINGS |  | LOT 4 | BOG | NCB | 500000 | POST | POST | 21/2/2011 | NA | 8/3/2011 | 22/3/2011 | 5/4/2011 | 19/4/2011 | NA | 500000 | NA | 26/4/2011 | 17/5/2011 | NIL | 17/6/2011 | 1/7/2011 | 500000
MTCE OF FED. SECRETARIAT PHASE 1 COMMUNICATION BUILDING |  | LOT 5 | BOQ | NCB | 500000 | POST | POST | 21/2/2011 | NA | 8/3/2011 | 22/3/2011 | 5/4/2011 | 19/4/2011 | NA | 500000 | NA | 26/4/2011 | 17/5/2011 | NIL | 17/6/2011 | 1/7/2011 | 500000
MTCE OF WUSE 2 MONITORING STATIONS |  | LOT 6 | BOQ | NCB | 1000000 | POST | POST | 21/2/2011 | NA | 8/3/2011 | 22/3/2011 | 5/4/2011 | 19/4/2011 | NA | 1000000 | NA | 26/4/2011 | 17/5/2011 | NIL | 17/6/2011 | 1/7/2011 | 1000000
MTCE OF INT. MONITORING STAATIONS AT 5 STATIONS |  | LOT 7 | BOQ | NCB | 25000000 | POST | POST | 21/2/2011 | NA | 8/3/2011 | 22/3/2011 | 5/4/2011 | 19/4/2011 | NA | 25000000 | NA | 26/4/2011 | 17/5/2011 | NIL | 17/6/2011 | 1/7/2011 | 25000000
MTCE OF FED. GOVT. PRESS - 4 OFFICE BUILDINGS AT LAGOS |  | LOT 8 | BOQ | NCB | 10000000 | POST | POST | 21/2/2011 | NA | 8/3/2011 | 22/3/2011 | 5/4/2011 | 19/4/2011 | NA | 10000000 | NA | 26/4/2011 | 17/5/2011 | NIL | 17/6/2011 | 1/7/2011 | 10000000
Total Cost
0

## Works Fin&Acc
Ministry/Department/Agency: FEDERAL MINSITRY OF WORKS: DEPARTMENT OF FINANCE AND ACCOUNT
Budgetary Year: 2011 --- Consultancy Services | [7 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [6 empty] | Contract Finalization |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/ Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | No-objection Date | FEC Approval | Contract Amount in Naira | Contract Offer | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | Plan | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks |  | 1- 2 wk | 2 wks
Actual
List of Contracts
ACCOUNTS DATA BASE MANAGEMENT SOFTWARE FOR E- PAYMENT EXPENDITURE/OTHER RETURNS. | OCB | L/S | 25000000 | MTB | Plan | 14th Feb - 7th March | 8th March - 22nd March | N/A | N/A | N/A | N/A | 28th March - | 11th April | 12th April - 25th April | 26th April - 10th May | 11th May - 25th May | 26th May - 9th June | 13th June - 27th June | N/A | N/A | 15000000 | 28th June - 12th July | 13th July - 27th July | 1st Aug - 15th Aug | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Actual
QUARTERLY VERIFICATION AND REPORTING OF BUDGET OVERHEAD COST AND INTERNALLY GENERATED REVENUE UTILISATION IN ALL 36 FIELD OFFICES. | OCB | L/S | 20000000 | MTB | Plan | 14th Feb - 7th March | 8th March - 22nd March | N/A | N/A | N/A | N/A | 28th March - | 11th April | 12th April - 25th April | 26th April - 10th May | 11th May - 25th May | 26th May - 9th June | 13th June - 27th June | N/A | N/A | 34585519.6 | 28th June - 12th July | 13th July - 27th July | 1st Aug - 15th Aug | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Actual
ESTABLISHMENT BUDGET DATABASE SOFTWARE FOR ANAYSIS OF BUDGETARY ALLOCATIONS, EXPENDITURES AND RETURNS. | OCB | L/S | 10000000 | MTB | Plan | 14th Feb - 7th March | 8th March - 22nd March | N/A | N/A | N/A | N/A | 28th March - | 11th April | 12th April - 25th April | 26th April - 10th May | 11th May - 25th May | 26th May - 9th June | 13th June - 27th June | N/A | N/A | 73621050 | 28th June - 12th July | 13th July - 27th July | 1st Aug - 15th Aug | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
TOTAL | [20 empty] | 123206569.6
Budgetary Year: 2010 -- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization | [5 empty] | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Plan vs. Actual | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 2 wks | Plan | 2 - 3 wks | T | 2 wks
[5 empty] | add 2 wks | [8 empty] | Actual |  |  |  |  | Actual
List of Contracts
PURCHASE OF OFFICE EQUIPMENT,XEROX PANASONIC,PHOTOCOPIERS, AND SCANERS,STABILIZERS ETC. |  | 1 | 20000000 | OCB | N/A | MTB | 14th Feb - 7th March | 8th March - 22nd March |  | 29th March - | 3rd May | 18th May -1st June | 2nd June - 16th June | Plan | 20000000 | 20th June - 4th July | 6th July - 20th July | 21st July - 4th Aug | Plan | 8th Aug - 22nd Aug | 17th Aug - 14th Sept. | 14th Sept - 28th Sept. | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
[14 empty] | Actual |  |  |  |  | Actual
CASTING MACHINES,DIGITAL CACULATORS AND CASTING ROLLS. |  | 2 | 5000000 | OCB | N/A | MTB | 14th Feb - 7th March | 8th March - 22nd March |  | 29th March - | 3rd May | 18th May -1st June | 2nd June - 16th June | Plan | 5000000 | 20th June - 4th July | 6th July - 20th July | 21st July - 4th Aug | Plan | 8th Aug - 22nd Aug | 17th Aug - 14th Sept. | 14th Sept - 28th Sept. | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
[14 empty] | Actual |  |  |  |  | Actual
ACQUISITION OF I.T. EQUIPMENT FOR BUDGET ACTIVITIES. |  | 3 | 20000000 | OCB | N/A | MTB | 14th Feb - 7th March | 8th March - 22nd March |  | 29th March - | 3rd May | 18th May -1st June | 2nd June - 16th June | Plan | 20000000 | 20th June - 4th July | 6th July - 20th July | 21st July - 4th Aug | Plan | 8th Aug - 22nd Aug | 17th Aug - 14th Sept. | 14th Sept - 28th Sept. | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
[14 empty] | Actual |  |  |  |  | Actual
GUBABI FIRE PROOF CABINET FOR SECURITY DOCUMENTS. |  | 4 | 15000000 | OCB | N/A | MTB | 14th Feb - 7th March | 8th March - 22nd March |  | 29th March - | 3rd May | 18th May -1st June | 2nd June - 16th June | Plan | 15000000 | 20th June - 4th July | 6th July - 20th July | 21st July - 4th Aug | Plan | 8th Aug - 22nd Aug | 17th Aug - 14th Sept. | 14th Sept - 28th Sept. | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
[14 empty] | Actual |  |  |  |  | Actual
SPLIT A/C AND 40 NO. AIR CONDITIONERS FOR HEADQUARTERS ,STATE OFFICES AND FCT. |  | 5 | 15000000 | OCB | N/A | MTB | 14th Feb - 7th March | 8th March - 18th March |  | 25th April - | 16th May | 18th May -1st June | 2nd June - 16th June | Plan | 15000000 | 20th June - 4th July | 6th July - 20th July | 21st July - 4th Aug | Plan | 8th Aug - 22nd Aug | 17th Aug - 14th Sept. | 14th Sept - 28th Sept. | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
[14 empty] | Actual |  |  |  |  | Actual
Ministry/Department/Agency: WORKS - FINANCE &ACCOUNT
Budgetary Year: 2011 --- Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 12 Months
[6 empty] | add 2 wks | [8 empty] | Actual
List of Contracts
CREATION/DEMORCATION OF ADDITIONAL OFFICES SPACE AND COMPLETE RENOVATION OF CENTRAL PAY OFFICE (CPO), DIRECTOR, DEPUTY DIRECTOR AND FIVE ASSISTANT DIRECTORS OFFICE. |  | 1 | BEME | OCB | 30000000 | N/A | MTB | 7th Feb - 28th Feb | 28th Feb - 14th March |  | 21st March - | 2nd May | 9th May - 30th May | 6th June - 20th June | Plan | 30000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Actual
UP-GRADING OF BUDGET OFFICE EQUIPMENTS. |  | 2 | BEME | OCB | 5000000 | N/A | MTB | 7th Feb - 28th Feb | 28th Feb - 14th March |  | 21st March - | 2nd May | 9th May - 30th May | 6th June - 20th June | Plan | 5000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Actual
CAPITAL BUDGET IMPLEMENTATION MONITORING AND EVALUATION PUBLICATION OF REPORTS |  | 3 | BEME | OCB | 25000000 | N/A | MTB | 7th Feb - 28th Feb | 28th Feb - 14th March |  | 21st March - | 2nd May | 9th May - 30th May | 6th June - 20th June | Plan | 25000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Actual
TOTAL |  |  |  |  | 60000000 | [10 empty] | 60000000

## Works Hways const&Rehabilitn
Ministry/Department/Agency: WORKS - HIGHWAYS CONSTRUCTION & REHABILITATION
Budgetary Year: 2011 -- Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 12 Months
add 2 wks
List of Contracts
REHABILITATION OF DIKWA-MONGUNO ROAD |  | 1 | BEME | OCB | 2500000000 | PRE - QUAL | FEC | 7th Feb - 28th Feb | 28th Feb - 8th March | 8th March- 22nd March | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | 2500000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
REHABILITATION OF BIU-LITTLE GOMBI ROAD |  | 2 | BEME | OCB | 2500000000 | PRE - QUAL | FEC | 7th Feb - 28th Feb | 28th Feb - 8th March | 8th March- 22nd March | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | 2500000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
EMERGENCY RECONSTRUCTION OF SOKOTO-ILELLA ROAD IN SOKOTO STATE |  | 3 | BEME | OCB | 2000000000 | PRE - QUAL | FEC | 7th Feb - 28th Feb | 28th Feb - 8th March | 8th March- 22nd March | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | 2000000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
REHABILITATATION OF BAYAMARI-GASHUA ROAD IN YOBE STATE |  | 4 | BEME | OCB | 2000000000 | PRE - QUAL | FEC | 7th Feb - 28th Feb | 28th Feb - 8th March | 8th March- 22nd March | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | 2000000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
REHABILITATION OF ONTSHA-OGWUIKPELE-NDONI ROAD WITH SPUR TO OGWUANAOCHA IN ANAMBRA STATE(65KM) |  | 5 | BEME | OCB | 2000000000 | PRE - QUAL | FEC | 7th Feb - 28th Feb | 28th Feb - 8th March | 8th March- 22nd March | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | 2000000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
REHABILITATION OF ENUGU-PORT HARCOURT DUALCARRAIGEWAY SECTION II: UMUAHIA-PORT HARCOURT |  | 6 | BEME | OCB | 2000000000 | PRE - QUAL | FEC | 7th Feb - 28th Feb | 28th Feb - 8th March | 8th March- 22nd March | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | 2000000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
REAHIBILIATION OF ILORIN-JEBBA-MOKWA ROAD : JEBBE -MOKWA IN NIGER STATE |  | 7 | BEME | OCB | 1000000000 | PRE - QUAL | FEC | 7th Feb - 28th Feb | 28th Feb - 8th March | 8th March- 22nd March | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | 1000000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
REHABILITATION OF IPELE-ISSUA ROAD SECTION II IN ONDO STATE |  | 8 | BEME | OCB | 1000000000 | PRE - QUAL | FEC | 7th Feb - 28th Feb | 28th Feb - 8th March | 8th March- 22nd March | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | 1000000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
REHABILITATION OF JALINGO-NUMAN |  | 9 | BEME | OCB | 625000000 | PRE - QUAL | FEC | 7th Feb - 28th Feb | 28th Feb - 8th March | 8th March- 22nd March | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | 625000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
EMERGENCY REPAIR OF WASHOUT ON 9TH MILE TO ENUGU ROAD IN ENUGU STATE |  | 10 | BEME | OCB | 700000000 | PRE - QUAL | FEC | 7th Feb - 28th Feb | 28th Feb - 8th March | 8th March- 22nd March | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | 700000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
REINSTATEMENT OF WASHOUT AND REHABILITATION OF SOKOTO-ILLELA ROAD IN SOKOTO STATE |  | 11 | BEME | OCB | 3500000000 | PRE - QUAL | FEC | 7th Feb - 28th Feb | 28th Feb - 8th March | 8th March- 22nd March | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | 3500000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
EMERGENCY REPAIR OF WASHOUT ON ABEOKUTA-IBADAN ROAD IN OGUN/OYO STATES |  | 12 | BEME | OCB | 700000000 | PRE - QUAL | FEC | 7th Feb - 28th Feb | 28th Feb - 8th March | 8th March- 22nd March | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | 700000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
REHABILITATION OF BENIN-SHAGAMU DUAL CARRIAGEWAY (OFOSU-ORE SECTION) IN ONDO STATE |  | 13 | BEME | OCB | 10000000000 | PRE - QUAL | FEC | 7th Feb - 28th Feb | 28th Feb - 8th March | 8th March- 22nd March | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | 10000000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
REINSTATEMENT OF WASHOUT AT KA-OJI BRIDGES IN KEBBI STATE |  | 14 | BEME | OCB | 1000000000 | PRE - QUAL | FEC | 7th Feb - 28th Feb | 28th Feb - 8th March | 8th March- 22nd March | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | 1000000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
DUALIZATION OF LOKOJA(OBAJANA JUNCTION)-BENIN ROAD IN KOGI/EDO STATES |  | 15 | BEME | OCB | 20000000000 | PRE - QUAL | FEC | 7th Feb - 28th Feb | 28th Feb - 8th March | 8th March- 22nd March | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | 20000000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
EXPANSION OF OSHODI-MURTALA MOHAMMED INTERNATIONAL AIRPORT DUAL CARRIAGEWAY TO 6 LANES WITH HARD SHOULDERS |  | 16 | BEME | OCB | 5000000000 | PRE - QUAL | FEC | 7th Feb - 28th Feb | 28th Feb - 8th March | 8th March- 22nd March | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | 5000000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
REHABILITATION OF DAMATURU-GUJBA-BIU ROAD |  | 17 | BEME | OCB | 1000000000 | PRE - QUAL | FEC | 7th Feb - 28th Feb | 28th Feb - 8th March | 8th March- 22nd March | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | 1000000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
CONTIGENCY PROVISION FOR EMERGENCY WORKS |  | 18 | BEME | OCB | 20000000 | PRE - QUAL | MTB | [7 empty] | 20000000 | [7 empty] | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
TOTAL |  |  |  |  | 57545000000 | [9 empty] | 57545000000

## Works_Hways Plan&Works
Ministry/Department/Agency: WORKS - HIGHWAYS PLANNING & DESIGN
Budgetary Year: 2011 --- Consultancy Service | [7 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  | Preparation Request for Proposals |  |  |  | Short List |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [6 empty] | Contract Finalization |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | No-objection Date | FEC Approval | Contract Amount in Naira | Contract Offer | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks |  | 1- 2 wk | 2 wks
List of Contracts
CONDUCT A STUDY AND PROVIDE EQUIPMENTS TO ESTABLISH A PHASED PROGRAM FOR THE ACHIEVEMENT OF A COMPREHENSIVE MANAGEMENT INFORMATION SYSTEM (MIS) FOR FEDERAL HIGHWAYS(DATA BASE/AUTO/CIVILCAD) | OCB | L/S | 15000000 | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 15000000 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
CONSULTANCY AWARD FOR THE DEVELOPMENT OF A NATIONAL BRIDGE MANAGEMENT INFORMATION SYSTEMS | OCB | L/S | 34585519.6 | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 34585519.6 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
DYNAMIC MEASUREMENT OF MAJOR BRIDGES AS WELL AS OVERALL BRIDGE RATING BY CONSULTANTS | OCB | L/S | 73621050 | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 73621050 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
UNDERWATER INSPECTION OF BRIDGES NATIONWIDE | OCB | L/S | 80000000 | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 80000000 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
ENGINEERING DESIGN FOR REHABILITATION AND ASPHALT OVERLAY OF ANGIGBA – IDAH ROAD IN KOGI STATE | OCB | L/S | 11455609 | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 11455609 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
ENGINEERING DESIGN FOR CONTRUCTION OF ODOOBA – TAIKE – GAMBARI SECTION | OCB | L/S | 66900328.12 | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | 3 - 14 May | 17 - 28 May | 66900328.12 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Engineering Design of Mokwa-New Bussa-Kaima-Kosubosu road in Niger/Kwara States | OCB | L/S | 9096495.12 | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | 3 - 14 May | 18 - 28 May | 9096495.12 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Engineering Design of Langtang-Wase Road in Plateau State | OCB | L/S | 30934980 | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | 3 - 14 May | 19 - 28 May | 30934980 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Engineering design of dualization of Keffi-Akwanga-Jos road in Nasarawa/Plateau States(Section II) | OCB | L/S | 5088725 | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | 3 - 14 May | 20 - 28 May | 5088725 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Engineering Design of Dualization of Okene – Auchi (Section IIB) | OCB | L/S | 45499920 | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | 3 - 14 May | 21 - 28 May | 45499920 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
ENGINEERING DESIGN OF OTURKPO – IGUNMALE – OKWONGBO WITH SPUR TO INIKIRI AND OGBALLA | OCB | L/S | 39000000 | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 39000000 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
NEW DESIGNS IN NORTH CENTRAL ZONE
Design for the Rehabilitation of Idah – Adoru – Nsuka Road in kogi state. | OCB | L/S | 80000000 | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | 3 - 14 May | 21 - 28 May | 7272727.3 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Design of Markurdi-Naka-Ankpa road | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | 3 - 14 May | 21 - 28 May | 7272727.3 | 17th June -1st July | 4th July - 18th July |  | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Design for the Rehabilitation of Otukpa – Ayangba – Ajaokuta – Okene road Phase II (Ajaokuta – Okene) in kogi state | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | 3 - 14 May | 21 - 28 May | 7272727.3 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Design of Iyemoye – Isua Road in Kogi state. | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 7272727.3 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Design for the Rehabilitation of Lambala – laisu – Bida Road in Niger State. | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 7272727.3 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Design for the Rehabilitation of suleja – Chaza Bamburu Road with spur to Rafin Samiyi in Niger state. | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 7272727.3 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Design for the Rehabilitation of Tunga Shamu – Zariyawa – Suleja – Road. | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 7272727.3 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Design of Mokwa – Bida road | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 7272727.3 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Design of Ilorin – Omuaka – kabba | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 7272727.3 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Design of Ajasse ipo – offa – Enile Osun State Bridge. | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 7272727.3 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Design of Lafia Bypass Road (Asuba through Sendan to Lafia Obi) in Nasarawa State. | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 7272727.3 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
NEW DESIGNS IN NORTH EAST ZONE
ENGINEERING DESIGN FOR DIKWA-GAJIRAM-GUBIO ROAD IN BORNO STATE | OCB | L/S | 60000000 | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 30000000 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
ENGINEERING DESIGN FOR MAMBILLA RING ROAD IN TARABA STATE | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 30000000 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
NEW DESIGNS IN NORTH WEST ZONE
ENGINEERING DESIGN FOR THE DUALIZATION OF KADUNA-BIRNIN GWARI-TEGINA ROAD | OCB | L/S | 80000000 | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 10000000 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
ENGINEERING DESIGN FOR THE REHABILITATION OF BIRNIN GWARI -FUNTUA ROAD | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 10000000 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
ENGINEERING DESIGN FOR THE REHABILITATION OF BIRNIN YAURI-KONTAGORA ROAD | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 10000000 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
ENGINEERING DESIGN FOR THE CONSTRUCTION OF WASAGU CHAFE ROAD | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 10000000 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
ENGINEERING DESIGN FOR THE DUALIZATION OF KANO-GWARZO ROAD | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 10000000 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
ENGINEERING DESIGN FOR THE CONSTRUCTION OF CHAFE - DAYI ROAD | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 10000000 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
ENGINEERING DESIGN FOR THE REHABILITATION OF BIRNIN GWARI-DANGULBI ROAD | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 10000000 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
ENGINEERING DESIGN FOR THE CONSTRUCTION OF BIRNIN YAURI-ROFIA-AGWARA ROAD | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 10000000 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
NEW DESIGNS IN THE SOUTH EAST ZONE
ENGINEERING DESIGN FOR OZALLA-AGBOGUGU-IHE-OWERU-OGUGU-NENWE-MGBO-AWGU ROAD IN ENUGU STATE | OCB | L/S | 70000000 | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 23333333 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
ENGINEERING DESIGN FOR MBANO-OKIGWE ROAD IN IMO STATE | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 23333333 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
ENGINEERING DESIGN FOR UZOUWANI-ANAKU-OTUOCHA ROAD IN ANAMBRA/ENUGU ROAD | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 23333333 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
NEW DESIGNS IN THE SOUTH SOUTH ZONE
Design of calabar – Oban – Ekang Road Section II (Oban Ekang Road) in Cross River State. (68km) | OCB | L/S | 100000000 | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 7142857.1 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Design of Adin – Agwagune – Ikun – Ohia – Road and with Bridges with Spur from Ikun – Unwana Afikpo (40km) | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 7142857.1 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Design of Asarama – Unyeada – Akaradi – Ngo with Bridges (Approx. 13km) Rivers | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 7142857.1 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Oloibiri (Ogbia) – Emago – Kugbo – amuruto – Akani – Adaada road (23km) with 710m Bridges. | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 7142857.1 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Ogbia – Oloibiri – Sabatoru – Okokokiri – Nembe road and Bridges – (40km) in Bayelsa State. | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 7142857.1 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Improvement of the alignment of Benin – Asaba Road (Benin –Agbor Section, (Onitsha Road) in Edo State. | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 7142857.1 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Design for full overlay Auchi – Igara – Ibilo (64km) F117 | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 7142857.1 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Design for full overlay, Irrua – Uromi – Ihushi. F116 (50km) | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 7142857.1 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Rehabilitation of Owu – Ugo – Agdonta. F16, (63km) | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 7142857.1 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Design of the Rehabilitation of Ofunmwegde – Ogbese – Ondo & Border F14 (36km) | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 7142857.1 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Benin Agbor upgrading of substandard line. | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 7142857.1 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Design of Abak-Ikot Ibiritam-Ikot Ekara Road | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 7142857.1 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Ikot Asua-Okopedi-Oron-Ewang-Jamestown road | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 7142857.1 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Design of Azumini-Ekparakwa-Etinan-Ndiya-Ikot Ubo Road | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 7142857.1 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
NEW DESIGNS IN THE SOUTH WEST ZONE
ENGINEERING DESIGN FOR ARAMOKO-IJERO-IDDO EKITI ROAD | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 10000000 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
90000000
ENGINEERING DESIGN FOR THE REHABILITATION OF ABEOKUTA-OLORUNDA-IMEKO ROAD | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 10000000 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
ENGINEERING DESIGN FOR ITAWURE-OKEMESI-ESA-OKE ROAD | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 10000000 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
ENGINEERING DESIGN FOR IJORA-CAUSEWAY-APAPA ROAD | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 10000000 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
ENGINEERING DESIGN FOR IJOUN-IJALE KETU (BENIN REPUBLIC BOARDER) VIA ILARA ROAD | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 10000000 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
ENGINEERING DESIGN FOR ILESHA-BARUBA KW STATE BOARDER -SAKI AGO ARE-ALAJA ROAD | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 10000000 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
ENGINEERING DESIGN FOR DUDGE -ODO-OWO APATA-BAKATARI OGUN S/B ROAD | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 10000000 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
ENGINEERING DESIGN FOR IJEBU-IJESHA-ILESHA-IFE ROAD | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 10000000 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
ENGINEERING DESIGN FOR IKORODU-IMOTA ROAD | OCB | L/S |  | MTB | 14th Feb - 28th Feb | 1st March - 15th March | N/A | N/A | N/A | N/A | 16th March | 30th March | 1st April - 15th April | 18th April -2nd May | 3rd May - 17th May | 18th May - 1st June | 2nd June - 16th June | N/A | N/A | 10000000 | 17th June -1st July | 4th July - 18th July | 25th July - 8th Aug. | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
TOTAL | [19 empty] | 891182625.54
Ministry/Department/Agency: WORKS - HIGHWAY PLANNING & DESIGN
Budgetary Year: 2010 --- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN
Desk Officer/Contact #: |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
add 2 wks
List of Contracts
PROVISION OF ROAD FURNITURE ON FEDERAL HIGHWAYS NATIONWIDE |  | 1 | 1500000000 | OCB | N/A | FEC | 14Feb - 28th Feb | 28th Feb - 8th March | 8th March - 22nd March | 12th April | 26th April | 10th May - 24th May | 14th June -21st June | 1500000000 | 28th June -12th July | 19th July - 26th July | 26th July -2nd Aug. | 3rd Aug -17th Aug. | 17th Aug - 14th Sept. | 14th Sept - 28th Sept. | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Ministry/Department/Agency: WORKS - HIGHWAYS PLANNING & DESIGN
Budgetary Year: 2011 --- Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN
Desk Officer/Contact #: |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 12 Months
[6 empty] | add 2 wks | [8 empty] | Actual
List of Contracts
FEDERAL ROADS AUTHORITY TAKE-OFF FUND (INCLUDING HEADQUARTERS OFFICE IN ABUJA AND ZONAL & STATE OFFICES) |  | 1 | BEME | OCB | 90000000 | N/A | MTB | 7th Feb - 28th Feb | 28th Feb - 8th March |  | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | 90000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Actual
UPGRADING OF FACILITIES AND PROCUREMENT OF LABORATORY TESTING EQUIPMENT FOR PAVEMENT EVALUATION UNIT AT KADUNA,OWERRI, JOS, LAGOS FOR QUALITY CONTROL OF OUR ROADS |  | 2 | BEME | OCB | 70000000 | N/A | MTB | 7th Feb - 28th Feb | 28th Feb - 8th March |  | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | 70000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Actual
CONSTRUCTION OF MATERIALS TESTING AND GEOTECHNICS LABORATORY COMPLEX AT SHEDA TOWN (FCT) FOR QUALITY CONTROLOF OUR ROADS |  | 3 | BEME | OCB | 101532418.58 | N/A | MTB | 7th Feb - 28th Feb | 28th Feb - 8th March |  | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | 101532418.58 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Actual
UPGRADING OF FACILITIES AND PROCUREMENT OF TEACHING AIDS FOR HIGHWAY TRAINIING SCHOOLS AT KADUNA, BADAGRY & UGONEKI |  | 4 | BEME | OCB | 50000000 | N/A | MTB | 7th Feb - 28th Feb | 28th Feb - 8th March |  | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | 50000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Actual
HIGHWAYS TRAFFIC EVALUATION INCLUDING: EQUIPMENT, TRAFFIC CENSUS AND OPERATIONS |  | 5 | BEME | OCB | 50000000 | N/A | MTB | 7th Feb - 28th Feb | 28th Feb - 8th March |  | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | 50000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Actual
Rehabilitation of River Niger Bridge at Onitsha (phase 2) |  | 6 | BEME | OCB | 100000000 | N/A | MTB | 7th Feb - 28th Feb | 28th Feb - 8th March |  | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | 100000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Actual
ENGINEERING DESIGN AND CONSTRUCTION OF BRIDGE TO REPLACE SUB-STANDARD BRIDGES ALONG ILORIN-IGBETTI ROAD IN KWARA STATE |  | 8 | BEME | OCB | 100000000 | N/A | MTB | 7th Feb - 28th Feb | 28th Feb - 8th March |  | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | 100000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Actual
ENGINEERING DESIGN AND CONSTRUCTION OF BRIDGE TO REPLACE SUB-STANDARD BRIDGE AT CH.50+450 ALONG OGBOMOSHO-OKO-ILOGBO-OSHOGBO ROAD IN OYO/OSUN STATES |  | 9 | BEME | OCB | 100000000 | N/A | MTB | 7th Feb - 28th Feb | 28th Feb - 8th March |  | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | 100000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Actual
DESIGN AND CONSTRUCTION OF BRIDGE TO REPLACE COLLAPSED IBESIT BRIDGE AT CH.36+000 ALONG NSAK-IKOT EKPENE-IKOT IBRITAM-IKOT EKPENE ROAD IN AKWA IBOM STATE |  | 10 | BEME | OCB | 100000000 | N/A | MTB | 7th Feb - 28th Feb | 28th Feb - 8th March |  | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | 100000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Actual
DESIGN AND CONSTRUCTION OF BRIDGE TO REPLACE SUB-STANDARD ILADO BRIDGE LINKING IJU/ITA-OGBOLU COMMUNITIES IN AKURE NORTH LGA AND IKARE IN ONDO/EKITI STATES |  | 11 | BEME | OCB | 100000000 | N/A | MTB | 7th Feb - 28th Feb | 28th Feb - 8th March |  | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | 100000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Actual
TECHNICAL EVALUATION AND REPLACEMENT OF BRIDGE AT LAFIAGI (CH.22+800) ALONG JEBBA-MOKWA-TEGINA-BIRNIN GWARI-KADUNA ROAD |  | 12 | BEME | OCB | 100000000 | N/A | MTB | 7th Feb - 28th Feb | 28th Feb - 8th March |  | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | 100000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Actual
Rehabilitation of Markurdi bridge in Benue State |  | 13 | BEME | OCB | 200000000 | N/A | MTB | 7th Feb - 28th Feb | 28th Feb - 8th March |  | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | 200000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Actual
[24 empty] | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Rehabilitation of River Niger Bridge at Onitsha (phase 2) |  | 14 | BEME | OCB | 100000000 | N/A | MTB | 7th Feb - 28th Feb | 28th Feb - 8th March |  | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | 100000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Actual
Rehabilitation of Jeba Bridge |  | 16 | BEME | OCB | 5000000000 | PRE QUAL | FEC | 7th Feb - 28th Feb | 28th Feb - 8th March | 8th March- 22nd March | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | 5000000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Actual
DESIGN AND CONSTRUCTION OF BRIDGE TO REPLACE SUB-STANDARD BRIDGE AT CH.0+850 (NASARAWA TOWN) ALONG NASARAWA -TOTO-ABAJI ROAD |  | 17 | BEME | OCB | 100000000 | N/A | MTB | 7th Feb - 28th Feb | 28th Feb - 8th March |  | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | 100000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Actual
CONSTRUCTION OF CHANCHANGI BRIDGE ALONG IBI-WUKARI ROAD AND PAMANGA BRIDGE ALONG JALINGO-GARBA CHEDE ROAD IN TARABA STATE |  | 18 | BEME | OCB | 100000000 | N/A | MTB | 7th Feb - 28th Feb | 28th Feb - 8th March |  | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | 100000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
Actual
DESIGN AND REPLACEMENT OF 1No. ABUTMENT AND EXTENSION BY 15M SPAN OF BRIDGE AT CH.89+100 AT SERTI ALONG BALI-MAYOSELBE-GEMBU ROAD IN TARABA STATE |  |  | BEME | OCB | 70000000 | N/A | MTB | 7th Feb - 28th Feb | 28th Feb - 8th March |  | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | 70000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
CONSTRUCTION OF DRAINS ALONG APAPA-OSHODI EXPRESSWAY |  |  | BEME | OCB | 90000000 | N/A | MTB | 7th Feb - 28th Feb | 28th Feb - 8th March |  | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | 90000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
CONSTRUCTION OF FLYOVER BRODGES AT SILVER JUBILEE AND KUNDILA ROUNDABOUTS IN KANO STATE |  |  | BEME | OCB | 50000000 | N/A | MTB | 7th Feb - 28th Feb | 28th Feb - 8th March |  | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | 50000000 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
BRIDGE MAINTENANCE OPERATIONS AND EQUIPMENTS |  |  | BEME | OCB | 61898245.25 | N/A | MTB | 7th Feb - 28th Feb | 28th Feb - 8th March |  | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | 61898245.25 | 4th July - 18th July | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th Aug -22nd Aug | August 2013 | August 2014 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
TOTAL |  |  |  |  | 6733430663.83 | [10 empty] | 6733430663.83

## Works_HR
Ministry/Department/Agency: Min. WORKS - HUMAN RESOURCES | [6 empty] | THE TIME LINE IS TO BE COMPARED WITH THE COUNCILS APPROVAL
Budgetary Year: 2011 -- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #:MR.I.M.BADEIRI 08036174364 |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval /BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
add 2 wks
List of Contracts
Provision of Sporting Equipment |  | 1 | 5011094 | OCB | N/A | MTB | 17th Jan - 31st Jan | 31st Jan - 7th Feb |  | 28th Feb | 11th April | 14th April- 5th May | 6th May - 13th May | 5011094 |  | 6th May - 20th may | 20th May - 4th June | 11th June - 25th June | 29th Aug | 12th September | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Total Cost |  |  | 5011094
Fill gray cells only!
2011 -- Works
[8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
| Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
[5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
1 |  | LUMPSUM | OCB | 30000000 | PRE-QUAL | MTB | Plan | 17th-Jan-31st Jan. | N/A | 7th Feb.-21stFeb | 28th Feb. | 11th April | 14th April-5th May | 6th May-13th May | Plan | 30000000 | N/A | 16th May-21st May | 23rd May- 28th May | N/A | 1st June- 18th June | 18th June -Nov.18 | 30000000 | Mr.I.M.badeiri | Engr.J.O.Chukwu
[7 empty] | Actual | [7 empty] | Actual
| 1 | LUMPSUM | OCB | 20000000 | N/A | MTB | Plan | 17th-Jan-31st Jan. | 7th Feb.-21stFeb |  | 22nd Feb. | 28th March. | 14th April-5th May | 6th May-13th May | Plan | 20000000 | N/A | 16th May-21st May | 23rd May- 28th May | N/A | 20th Oct | Nov.18 |  | Mr.I.M.badeiri | Engr.J.O.Chukwu
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
|  |  |  | #REF! |  |  | Plan | [7 empty] | Plan | #REF! | [6 empty] | #REF!
|  |  |  | #REF! |  |  | Actual | [7 empty] | Actual | #REF! | [6 empty] | #REF!

## Works_Legal unit
Ministry/Department/Agency: Min. WORKS - LEGAL UNIT
Budgetary Year: 2011 --- Consultancy Unit | [6 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  | Preparation Request for Proposals |  |  |  | Short List |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | Plan vs. Actual | No-objection Date | FEC Approval | Contract Amount in Naira | Contract Offer | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 1- 2 wk | 2 wks
Actual
List of Contracts
Continuous Legal Education for the improvement of the Professional staff of the Legal Unit at the Headquarters | OCB | L/S | 4000000 | MTB | 17th Jan - 11th Feb | 14th Feb - 28th Feb | N/A | N/A | N/A | N/A | 7th March - 21st march | 22nd March - 5th April | 11th April - 25th April | 26th April - 10th May | 11th May - 25th May | 30th May - 13th June | 14th June - 28th June | Plan | N/A | N/A | 4000000 | 4th July - 18th July | 19th July - 2nd Aug | 8th Aug - 22nd Aug | 15 Sep | 15 Dec |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
TOTAL |  |  | 4000000 | [17 empty] | 4000000
Budgetary Year: 2011---Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 12 Months
add 2 wks
List of Contracts
Establishment of Law Library Continouous up-date of the Law Library at the Headquarters:- |  | 1 | BEME | OCB | 6000000 | N/A | MTB | 17th Jan - 7th Feb | 10th Feb - 24th Feb | N/A | 1st March - | 29th March | 5th April - 19th April | 20th April- 29th April | 6000000 |  | 2nd May - 16th May | 17th May - 24th May | 30th May -13th June | August 2011 | Sept. 2011 |  | ADP- I.M BADEIRI | DPP-ENGR.J.O CHUKWU
TOTAL |  |  |  |  | 6000000 | [9 empty] | 6000000

## Works_PR unit
Ministry/Department/Agency: Min. WORKS - PRESS & PUBLIC RELATION UNIT
Budgetary Year: 2011 --- Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #:Mr.I.M.Badeiri i/08036174364 |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
add 2 wks
List of Contracts
Purchase of Digital Equipment/Upgrading of Camera & Editing suite from Analog to Digital High Definition |  | 1 | Lumpsum | OCB | 2500000 | N/A | MTB | 14th Feb.-7th Mar. | 8th March - 18th March |  | Mar.21st - | 15th April | 18th April - 9th May | 16th May - 30th May |  | N/A | 1st Jun-8th June | 15th June |  | 30th June | Dec 15th |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Quarterly Production of Documentary |  | 2 | Lumpsum | OCB | 3000000 | N/A | MTB | 14th Feb.-7th Mar. | 8th March - 18th March |  | 25th April | 16th May | 30th May | N/A |  | N/A | 1st Jun-8th June | 15th June |  | 30th June | Dec 15th |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Publication of In-House Journal/binding of newspapers Magazines |  | 3 | Lumpsum | OCB | 5000000 | n/A | MTB | 14th Feb.-7th Mar. | 8th March - 18th March | Mar.21st-Apr.4th | 25th April | 16th May | 30th May | N/A |  | N/A | 1st Jun-8th June | 15th June |  | 30th June | Dec 15th |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Total Cost

## Works_Public Procur
Ministry/Department/Agency: WORKS - PUBLIC PROCUREMENT
Budgetary Year: 2011 --- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
add 2 wks
List of Contracts
Establishment,Design,Installation of Procurement Data Bank Soft Wares and Evaluation of Bid Documents |  | 1 | 15000000 | OCB | N/A | MTB | Jan.17th-Feb.7th | 8th March - 18th March |  | 21st March- | 18th April | 19th April - 3rd May | 4th May-12th May | 15000000 | N/A | May 13th- May20th | May 23rd- May27th | N/A | 1st June-8th June | May 9th-16th June | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Purchase of Office Furniture for 37 FHQS and HQ |  | 2 | 45000000 | OCB | N/A | MTB | Jan.17th-Feb.7th | 8th March - 18th March |  | 21st March- | 18th April | 19th April - 3rd May | 4th May-12th May | 45000000 | N/A | May 13th- May20th | May 23rd- May27th | N/A | 1st June-8th June | May 9th-16th June | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Purchase of various items of Office Equipment for 37 FHQS |  | 3 | 50000000 | OCB | N/A | MTB | Jan.17th-Feb.7th | 8th March - 18th March |  | 21st March- | 18th April | 19th April - 3rd May | 4th May-12th May | 50000000 | N/A | May 13th- May20th | May 23rd- May27th | N/A | 1st June-8th June | May 9th-16th June | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Store handling including partitioning of Store Space |  | 4 | 4460000 | OCB | N/A | MTB | Jan.17th-Feb.7th | 8th March - 18th March |  | 21st March- | 18th April | 19th April - 3rd May | 4th May-12th May | 4460000 | N/A | May 13th- May20th | May 23rd- May27th | N/A | 1st June-8th June | May 9th-16th June | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Procurement Monitoring Compliance Evaluation of Road Projects in the 36 States. |  | 5 | 20999127 | OCB | N/A | MTB | Jan.17th-Feb.7th | 8th March - 18th March |  | 21st March- | 18th April | 19th April - 3rd May | 4th May-12th May | 20999127 | N/A | May 13th- May20th | May 23rd- May27th | N/A | 1st June-8th June | May 9th-16th June | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Placement of Advertisements in National Dailies and Tenders Journals for Procurement of Capital Projects. |  |  | 5000000 | OCB | N/A | MTB | [7 empty] | 5000000
6
Total Cost |  |  | 140459127 | [10 empty] | 140459127
Fill gray cells only!

## Works_Eng serv
Ministry/Department/Agency: WORKS - ENGINEERING SERVICES
Budgetary Year: 2011 --- Consultancy Service | [6 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: Mr.I.M.Badeiri/08036174364 |  | Contract Type |  |  | Preparation Request for Proposals |  |  |  | Short List |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [6 empty] | Contract Finalization |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | No-objection Date | FEC Approval | Contract Amount in Naira | Contract Offer | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks |  | 1- 2 wk | 2 wks
List of Contracts
Consultancy/Water System Development at Engineering Training School,Abeokuta | OCB | Time Based | 16000000 | MTB | 14th Feb- 14th March | 15th March - 25th March | 28th March- 11th April | N/A | 25th April | N/A | 26th April- | 18th May | 19th May- 2nd June | 3rd June-17th June | 19th June-26th June | 30th Jun-31st June | 1st July-8th July | N/A | N/A | 16,000,000.00 | 11th July-25th July | 27th July-10th Aug. | N/A | 16th Sept | 16th Dec |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Consultancy/Construction Services for 1No.32 Bedroom Storey Hostel at Engineering Training School,Abeokuta | OCB | Time Based | 12000000 | MTB | 14th Feb- 14th March | 15th March - 25th March | 28th March- 11th April | N/A | 25th April | N/A | 26th April- | 18th May | 19th May- 2nd June | 3rd June-17th June | 19th June-26th June | 30th Jun-31st June | 1st July-8th July | N/A | N/A | 12000000 | 11th July-25th July | 27th July-10th Aug. | N/A | 16th Sept | 16th Dec |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Consultancy/Construction Services for 1No.32 Bedroom Storey Hostel at Engineering Training School,Kuje | OCB | Time Based | 6000000 | MTB | 14th Feb- 14th March | 15th March - 25th March | 28th March- 11th April | N/A | 25th April | N/A | 26th April- | 18th May | 19th May- 2nd June | 3rd June-17th June | 19th June-26th June | 30th Jun-31st June | 1st July-8th July | N/A | N/A | 6000000 | 11th July-25th July | 27th July-10th Aug. | N/A | 16th Sept | 16th Dec |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Equiping of Mechanical/Electrical Workshop at the Engineering Training School,Kuje | OCB | Time Based | 4000000 | MTB | 14th Feb- 14th March | 15th March - 25th March | 28th March- 11th April | N/A | 25th April | N/A | 26th April- | 18th May | 19th May- 2nd June | 3rd June-17th June | 19th June-26th June | 30th Jun-31st June | 1st July-8th July | N/A | N/A | 4000000 | 11th July-25th July | 27th July-10th Aug. | N/A | 16th Sept | 16th Dec |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Total Cost
Fill gray cells only!
Budgetary Year: 2011 --- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: MR.I.M.BADEIRI/08036174364 |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
add 2 wks
List of Contracts
Procurement of Modern Workshop Tools/Teaching Aids for Engineering Training School at Abeokuta. |  | 1 | 15000000 | OCB | N/A | MTB | 14th Feb- 7th March | 8th March - 22nd March |  | 29th March - | 26th April | 3rd May - 17th May | 18th May - 31st May | 15000000 | N/A | 1st June-8th June | 9th June- 16th June | N/A | 17th June- 30th June | 1st July-15th July | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Procurement of Modern Workshop Tools/Teaching Aids for Engineering Development Centre at Ijora |  | 2 | 10000000 | OCB | N/A | MTB | 14th Feb- 7th March | 8th March - 22nd March |  | 29th March - | 26th April | 3rd May - 17th May | 18th May - 31st May | 10000000 | N/A | 1st June-8th June | 9th June- 16th June | N/A | 17th June- 30th June | 1st July-15th July | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Purchase of Tools and Equipment for Teaching at Engineering Training School,Kuje |  | 3 | 5549396 | OCB | N/A | MTB | 14th Feb- 7th March | 8th March - 22nd March |  | 29th March - | 26th April | 3rd May - 17th May | 18th May - 31st May | 5549396 | N/A | 1st June-8th June | 9th June- 16th June | N/A | 17th June- 30th June | 1st July-15th July | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Activation and Commissioning of 11KV HT Control Panel with replacement and supply of upgrading cable at headquarters,Mabushi |  | 4 | 10000000 | OCB | N/A | MTB | 14th Feb- 7th March | 8th March - 22nd March |  | 29th March - | 26th April | 3rd May - 17th May | 18th May - 31st May | 10000000 | N/A | 1st June-8th June | 9th June- 16th June | N/A | 17th June- 30th June | 1st July-15th July | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Provision of 5No.Material handling equipment and fourwheel drive vehicle for Streetlighting Operations in the Six Geopolitical zone |  | 5 | 35000000 |  | N/A | MTB | 14th Feb- 7th March | 8th March - 22nd March |  | 29th March - | 26th April | 3rd May - 17th May | 18th May - 31st May | 35000000 | N/A | 1st June-8th June | 9th June- 16th June | N/A | 17th June- 30th June | 1st July-15th July | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Provision Design Equipment and Software for Mechanical Services |  |  | 5000000 |  | N/A | MTB | 14th Feb- 7th March | 8th March - 22nd March |  | 29th March - | 26th April | 3rd May - 17th May | 18th May - 31st May | 5000000 | N/A | 1st June-8th June | 9th June- 16th June | N/A | 17th June- 30th June | 1st July-15th July | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Total Cost
Fill gray cells only!
Budgetary Year: 2011 --- Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #:MR.I.M. BADEIRI/08036174364 |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
add 2 wks
List of Contracts
Consultancy/Construction of Engineering Training School Library at Ijora. |  | 1 | BEME | OCB | 15000000 | N/A | MTB | 14th Feb- 7th March | 8th March - 18th March |  | 25th April | 16th May | 30th May | N/A | 15000000 | N/A | 31st May-7th June | 8th June-15th June | N/A | June 2012 | December 2012 |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Rehabilitation of Federal Ministry of Works Headquarters Building. |  | 2 | BEME | OCB | 45000000 | N/A | MTB | 14th Feb- 7th March | 8th March - 18th March |  | 25th April | 16th May | 30th May | N/A | 45000000 | N/A | 31st May-7th June | 8th June-15th June | N/A | June 2012 | December 2012 |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Electrical Installations at the New Engineering Workshop Blocks, Kuje. |  | 3 | BEME | OCB | 4000000 | N/A | MTB | 14th Feb- 7th March | 8th March - 18th March |  | 25th April | 16th May | 30th May | N/A | 4000000 | N/A | 31st May-7th June | 8th June-15th June | N/A | June 2012 | December 2012 |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Installation of 36No. Higher Rating Substations in 36 FHQS of the Federation |  | 4 | BEME | OCB | 8000000 | N/A | MTB | 14th Feb- 7th March | 8th March - 18th March |  | 25th April | 16th May | 30th May | N/A | 8000000 | N/A | 31st May-7th June | 8th June-15th June | N/A | June 2012 | December 2012 |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Consultancy/Water system Development at Engineering centre Kuje. |  | 5 | BEME | OCB | 8000000 | N/A | MTB | 14th Feb- 7th March | 8th March - 18th March |  | 25th April | 16th May | 30th May | N/A | 15000000 | N/A | 31st May-7th June | 8th June-15th June | N/A | June 2012 | December 2012 |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
6No. Streetlighting/Security Installation of minimum of 3Km each on Federal roads /Bridges in South East Zone |  | 6 | BEME | OCB | 300000000 | PRE-QUAL | MTB | 14th Feb- 7th March | 8th March - 18th March | 21st March-4th April | 25th April | 16th May | 30th May |  | 300000000 | N/A | 31st May-7th June | 8th June-15th June | N/A | June 2012 | December 2012 |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
6No. Streetlighting/Security Installation of minimum of 3Km each on Federal roads /Bridges in South West Zone |  | 7 | BEME | OCB | 300000000 | PRE-QUAL | MTB | 14th Feb- 7th March | 8th March - 18th March | 21st March-4th April | 25th April | 16th May | 30th May |  | 300000000 | N/A | 31st May-7th June | 8th June-15th June | N/A | June 2012 | December 2012 |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
6No. Streetlighting/Security Installation of minimum of 3Km each on Federal roads /Bridges in South South Zone |  | 8 | BEME | OCB | 300000000 | PRE-QUAL | MTB | 14th Feb- 7th March | 8th March - 18th March | 21st March-4th April | 25th April | 16th May | 30th May | N/A | 300000000 | N/A | 31st May-7th June | 8th June-15th June | N/A | June 2012 | December 2012 |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
6No. Streetlighting/Security Installation of minimum of 3Km each on Federal roads /Bridges in North West Zone |  | 9 | BEME | OCB | 300000000 | PRE-QUAL | MTB | 14th Feb- 7th March | 8th March - 18th March | 21st March-4th April | 25th April | 16th May | 30th May | N/A | 300000000 | N/A | 31st May-7th June | 8th June-15th June | N/A | June 2012 | December 2012 |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
6No. Streetlighting/Security Installation of minimum of 3Km each on Federal roads /Bridges in North Central Zone |  | 10 | BEME | OCB | 300000000 | PRE-QUAL | MTB | 14th Feb- 7th March | 8th March - 18th March | 21st March-4th April | 25th April | 16th May | 30th May | N/A | 300000000 | N/A | 31st May-7th June | 8th June-15th June | N/A | June 2012 | December 2012 |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
6No. Streetlighting/Security Installation of minimum of 3Km each on Federal roads /Bridges in North East Zone |  | 11 | BEME | OCB | 300000000 | PRE-QUAL | MTB | 14th Feb- 7th March | 8th March - 18th March | 21st March-4th April | 25th April | 16th May | 30th May | N/A | 300000000 | N/A | 31st May-7th June | 8th June-15th June | N/A | June 2012 | December 2012 |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Central Workshop Automobile Training School at Ijora. |  | 12 | BEME | OCB | 300000000 | PRE-QUAL | MTB | 14th Feb- 7th March | 8th March - 18th March | 21st March-4th April | 25th April | 16th May | 30th May | N/A | 300000000 | N/A | 31st May-7th June | 8th June-15th June | N/A | June 2012 | December 2012 |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Upgrading of Water supply and treatment Plant at the Federal Ministry of Works Heaquarters, Abuja. |  | 13 | BEME | OCB | 10,000,000.00 | N/A | MTB | 14th Feb- 7th March | 8th March - 18th March |  | 25th April | 16th May | 30th May | N/A | 10000000 | N/A | 31st May-7th June | 8th June-15th June | N/A | June 2012 | December 2012 |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Provision and Installation of 12Nos Foundry Machine tools & Equipments at Ijora Central Workshop |  | 14 | BEME | OCB | 30,000,000.00 | N/A | MTB | 14th Feb- 7th March | 8th March - 18th March |  | 25th April | 16th May | 30th May | N/A | 30000000 | N/A | 31st May-7th June | 8th June-15th June | N/A | June 2012 | December 2012 |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Provision and Installation of Engineering material Testing equipments at Ijora Central Workshop. |  | 15 | BEME | OCB | 30,000,000.00 | N/A | MTB | 14th Feb- 7th March | 8th March - 18th March |  | 25th April | 16th May | 30th May | N/A | 30000000 | N/A | 31st May-7th June | 8th June-15th June | N/A | June 2012 | December 2012 |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Provision and Installation of Machine Tools and Equipments at Ijora Central Workshop. |  | 16 | BEME | OCB | 60,000,000.00 | N/A | MTB | 14th Feb- 7th March | 8th March - 18th March |  | 25th April | 16th May | 30th May | N/A | 60000000 | N/A | 31st May-7th June | 8th June-15th June | N/A | June 2012 | December 2012 |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu

## Works_Stock Ver
Ministry/Department/Agency: WORKS - STOCK VERIFICATION
Budgetary Year: 2011 --- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN
Desk Officer/Contact #:Mr.I.M.Badeiri /08036174364 |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
add 2 wks
List of Contracts
Purchase of Inventory data base for stock Verification unit/Abuja. |  | 1 | 2000000 | OCB | N/A | MTB | Jan.17th-Feb.7th | 8th Feb - 18th Feb | Feb.21st- March.7th | Mar.7th - | Apr.29th | Apr.29th- May13th | N/A | 2000000 | N/A | 16th May- 20th May | 20th May- 27th May | N/A | 10th May | 10th May- 17th May | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Total Cost |  |  | 2000000 | [10 empty] | 2000000
Fill gray cells only!
Budgetary Year: 2011 --- Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #:Mr.I.M.Badeiri i/08036174364 |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
add 2 wks
List of Contracts
Construction of Dump Stores for the Headquarters and the Zonal Offices |  | 1 | Lumpsum | OCB | 1200000 | N/A | N/A | Jan.17th-Feb.7th | Feb.21st-Mar.7th |  | Mar.7th - | Apr.29th | Apr.29th - May13th | May 13th - May 20th | 1200000 | N/A | N/A | 20thMay- 27th May | N/A | 31st May | Dec 15th |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Developing of Stock Verifier data base system and Six(6) Zonal Offices Abuja. |  | 2 | Lumpsum | OCB | 2000000 | N/A | N/A | Jan.17th-Feb.7th | Feb.21st-Mar.7th |  | Mar.7th - | Apr.29th | Apr.29th-May13th | May 13th - May 20th | 2000000 | N/A | N/A | 20thMay- 27th May | N/A | 31st May | Dec 15th |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Total Cost |  |  |  |  | 3200000 | [9 empty] | 3200000
Fill gray cells only!

## Works_Intr Audit
Ministry/Department/Agency: WORKS -INTERNAL AUDIT
Budgetary Year: 2011 --- Consultancy services | [6 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #:Mr.I.M.Badeiri |  | Contract Type |  |  | Preparation Request for Proposals |  |  |  | Short List |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [6 empty] | Contract Finalization |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | No-objection Date | FEC Approval | Contract Amount in Naira | Contract Offer | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks |  | 1- 2 wk | 2 wks
List of Contracts
Internal Audit Sentitization on Prudent Budget Implementation | OCB | Lumpsum | 6000000 | MTB | 14th Feb.-7th March | 8th March - 18th March |  |  | 21st March- 4th April | 11th April-25th April | 25th April- | 23rd May | 24th May-31st May | 1st June-15th June | 20th June-30th June | 4th July-8th July | 11th July-July 22 |  | N/A | 6,000,000.00 | 25th July -8th Aug | 9th Aug - 23rd Aug | N/A | 26th Oct | 25th Nov |  | Mr.I.M. Badeiri | Engr.J.O.Chukwu
Total Cost | [19 empty] | 6,000,000.00
Budgetary Year: 2011 --- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #:Mr.I.M.Badeiri |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
add 2 wks
List of Contracts
Activitation and Updating of the Integrated Payroll and Personnel information system(IPPIS),Connectivity in the Internal Audit | 1 |  | 5500000 | OCB | N/A | MTB | 14th Feb- 7th March | 21st March-4th April |  | 25th April | 16th May | 16th May - 30th May | 31st May-8th June |  | N/A | 9th June-16th June | 17th June- 30th June | N/A | 30th Sept | 31st Nov | Mr.I.M.Baderi | Engr.J.O.Chukwu
Acquisition of I.T.Equipments |  |  | 2500000 | OCB | N/A | MTB | 14th Feb- 7th March | 21st March-4th April |  | 25th April | 16th May | 16th May - 30th May | 31st May-8th June |  | N/A | 9th June-16th June | 17th June- 30th June | N/A | 30th Sept | 31st Nov | Mr.I.M.Baderi | Engr.J.O.Chukwu
Production of Internal Audit Security Materials |  |  | 6000000 | OCB | N/A | MTB | 14th Feb- 7th March | 21st March-4th April |  | 25th April | 16th May | 16th May - 30th May | 31st May-8th June |  | N/A | 9th June-16th June | 17th June- 30th June | N/A | 30th Sept | 31st Nov | Mr.I.M.Baderi | Engr.J.O.Chukwu
Total Cost
Ministry/Department/Agency: WORKS - INTERNAL AUDIT
Budgetary Year: 2011 --- Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #:Mr.I.M.Badeiri/ |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
add 2 wks
List of Contracts
Internal Audit Prepayment and Verification of Execute Capital |  | 1 | LumpSum | OCB | 5884706 | N/A | MTB | 14th Feb- 7th March | 21st March-4th April |  | 25th April | 16th May | 30th May | 1st June-8th June | 5884706 | N/A | 9th June-16th June | 16th June - 30th June | N/A | Sept 30th | Dec.15th |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Internal Audit Value for Money Evaluation of Capital Projects |  | 2 | LumpSum | OCB | 5884706 | N/A | MTB | 14th Feb- 7th March | 21st March-4th April |  | 25th April | 16th May | 30th May | 1st June-8th June | 5884706 | N/A | 9th June-16th June | 16th June - 30th June | N/A | Sept 30th | Dec.15th |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Total Cost | [14 empty] | 11769412
Fill gray cells only!

## Works_PRS
Ministry/Department/Agency: Works-PRS
Budgetary Year: 2011 --- Consultancy Service | [6 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #:Mr.I.M.Badeiri/ 08036174364 |  | Contract Type |  |  | Preparation Request for Proposals |  |  |  | Short List |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [6 empty] | Contract Finalization |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | No-objection Date | FEC Approval | Contract Amount in Naira | Contract Offer | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks |  | 1- 2 wk | 2 wks
List of Contracts
Development and hosting of Interactive Web Portal for the | OCB | Lumpsum | 5000000 | MTB | 21st March-4th April | 5th April - 15th April | 18th April- 2nd May | N/A | 9th May- 23rd May | N/A | 24th May - | 20th June | 21st June- 30th June | 4th July-15th July | 17th July-29th | 1st Aug.-5th Aug. | 8th Aug - 22nd Aug | N/A | N/A | 5,000,000.00 | 23rd Aug - 6th Sept | 7th Sept - 21st Sept | 22nd Sept -6th Oct | 23rd Nov | 15th Dec |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Maximixing Systems Network Management Administration Potentials for IT-Staff | OCB | Lumpsum | 3000000 | MTB | 21st March-4th April | 5th April - 15th April | 18th April- 2nd May | N/A | 9th May- 23rd May | N/A | 24th May - | 20th June | 21st June- 30th June | 4th July-15th July | 17th July-29th | 1st Aug.-5th Aug. | 8th Aug - 22nd Aug | N/A | N/A | 3000000 | 23rd Aug - 6th Sept | 7th Sept - 21st Sept | 22nd Sept -6th Oct | 23rd Nov | 15th Dec |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Development and Deployment of File/Mail Tracking Management Information System in the Ministry | OCB | Lumpsum | 2000000 | MTB | 21st March-4th April | 5th April - 15th April | 18th April- 2nd May | N/A | 9th May- 23rd May | N/A | 24th May - | 20th June | 21st June- 30th June | 4th July-15th July | 17th July-29th | 1st Aug.-5th Aug. | 8th Aug - 22nd Aug | N/A | N/A | 2000000 | 23rd Aug - 6th Sept | 7th Sept - 21st Sept | 22nd Sept -6th Oct | 23rd Nov | 15th Dec |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Development and Deployment of Inventory Control System in the Ministry | OCB | Lumpsum | 30000000 | MTB | 21st March-4th April | 5th April - 15th April | 18th April- 2nd May | N/A | 9th May- 23rd May | N/A | 24th May-9th June | 13th June-20th June | 21st June- 30th June | 4th July-15th July | 17th July-29th | 1st Aug.-5th Aug. | 8th Aug - 22nd Aug | N/A | N/A | 30000000 | 23rd Aug - 6th Sept | 7th Sept - 21st Sept | 22nd Sept -6th Oct | 23rd Nov | 15th Dec |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Total Cost
Ministry/Department/Agency: Works-PRS
Budgetary Year: 2011 --- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #:Mr.I.M.Badeiri/ 08036174364 |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
add 2 wks
List of Contracts
Purchase and Installation of Network Anti-Virus Software(300 User License) for Hqtrs.Building |  | 1 | 5000000 | OCB | N/A | MTB | 14th Feb - 28th Feb | 7th March-21st April |  | 4th April | 18th April | 20th April- 11th May | 12th -19th May | 5000000 | N/A | 20th-27th May | 1st June-15th June | N/A | Sept 2011 | Nov 2011 | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Total Cost
Ministry/Department/Agency: Works-PRS
Budgetary Year: 2011 --- Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #:Mr.I.M.Badeiri/ 08036174364 |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
add 2 wks
List of Contracts
Maintenance of Internet/Intranet Network facilities at the FMW Headquarters and its expansion to the new office building of the Ministry
|  | 1 | Lumpsum | OCB | 60206974 | N/A | MTB | 14th-28th Feb 2011 | 7th March-21st April |  | 4th april | 18th April | 20th April - 11th May | 12th May- 19th MAy | 60206974 | N/A | 20th May-27th May | 30th May - 6th May | N/A | 15th Sept | Dec 15th |  | Mr.I.M.Badeiri | Engr.J.O.Chukwu
Total Cost

## Works_Plan_Design
Ministry/Department/Agency: FEDERAL MINISTRY OF WORKS, HIGHWAYS (PLANNING AND DESIGN)
Budgetary Year: 2011 --- Consultancy Services | [6 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  | Preparation Request for Proposals |  |  |  | Short List |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [6 empty] | Contract Finalization |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/ Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | No-objection Date | FEC Approval | Contract Amount in Naira | Contract Offer | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks |  | 1- 2 wk | 2 wks
List of Contracts
Training on Modern Techniques for Planning & Design of Roads (Lot 1) | LC | L/S | 40000000 | MTB | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | N/A | N/A | 10000000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 10000000 | DDHP- Engr C. P Enwonwu | DHPD-J.C.O Bosah
Specialized Computer training on Highway Design (Lot 2) | LC | L/S |  | MTB | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | N/A | N/A | 10000000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 10000000 | DDHP- Engr C. P Enwonwu | DHPD-J.C.O Bosah
Training on the use of Modern Highway Survey Instrument (Total Station) (Lot 3) | LC | L/S |  | MTB | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | N/A | N/A | 10000000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 10000000 | DDHP- Engr C. P Enwonwu | DHPD-J.C.O Bosah
Training by IRF on preserving our Highway Infrastructure and Contract maintenance/ Asset management (Lot 4) | LC | L/S |  | MTB | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | N/A | N/A | 10000000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 10000000 | DDHP- Engr C. P Enwonwu | DHPD-J.C.O Bosah
Consultancy services for the procurement of Hard and Software for archiving Engineering Design projects Data | LC | L/S | 50000000 | MTB | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | N/A | N/A | 50000000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 50000000 | DDHP- Engr C. P Enwonwu | DHPD-J.C.O Bosah
Consultancy services for the rehabilitation Markurdi bridge in Benue State | LC | L/S | 100000000 | FEC | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | 3 - 14 May | 17 - 28 May | 100000000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 100000000 | DDHP- Engr C. P Enwonwu | DHPD-J.C.O Bosah
Consultancy services for the Rehabilitation of Ajaokuta Bridge across River Niger | LC | L/S | 100000001 | FEC | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | 3 - 14 May | 18 - 28 May | 100000001 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 100000001 | DD( R)E -Engr E. E. Ije | DHPD-J.C.O Bosah
Consultancy services for the Rehabilitation of River Niger Bridge at Onitsha (phase 2) | LC | L/S | 100000002 | FEC | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | 3 - 14 May | 19 - 28 May | 100000002 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 100000002 | DD( R)E -Engr E. E. Ije | DHPD-J.C.O Bosah
Consultancy services for the Rehabilitation of Muritala Mohamed bridge at Kotonkarfi | LC | L/S | 100000003 | FEC | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | 3 - 14 May | 20 - 28 May | 100000003 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 100000003 | DD(R )C-Engr Y. M Bulama | DHPD-J.C.O Bosah
Consultancy services for the Rehabilitation of Jeba Bridge | LC | L/S | 100000004 | FEC | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | 3 - 14 May | 21 - 28 May | 100000004 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 100000004 | DD( R)W-Engr. G.O.Ikenga | DHPD-J.C.O Bosah
Consultancy services for the Emergency repair of serti bridge at KM 89+100 along Bali - Mayo Selbe - Gembu road | LC | L/S | 50000000 | MTB | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | N/A | N/A | 50000000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 50000000 | DD(R )C-Engr Y.M. Bulama | DHPD-J.C.O Bosah
Consultancy services for the Repair of 3rd Mainland bridge (phase 2) | LC | L/S | 200000000 | FEC | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | 3 - 14 May | 21 - 28 May | 200000000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 200000000 | DD(BD)-Engr B.K. Okafor | DHPD-J.C.O Bosah
Consultancy services for the Restoration of 2No. burnt bridges between Ijora and Akpagbon | LC | L/S | 300000000 | FEC | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | 3 - 14 May | 21 - 28 May | 300000000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 300000000 | DD(BD)-Engr B.K. Okafor | DHPD-J.C.O Bosah
Consultancy services for the Restoration of burnt Marine beach bridge at Apapa Lagos | LC | L/S | 100000000 | FEC | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | 3 - 14 May | 21 - 28 May | 100000000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 100000000 | DD(BD)-Engr B.K. Okafor | DHPD-J.C.O Bosah
Consultancy services for the Design of Makurdi-Adoka-Ankpa Road in Benue/Kogi States (Lot 1) | LC | L/S | 40000000 | MTB | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | N/A | N/A | 13000000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 13000000 | DD(R )C-Engr Y. M. Bulama | DHPD-J.C.O Bosah
Consultancy services for the Design of Okene-Osono-Ojirami-Igara-Okpe-Idogun in Kogi State (Lot 2) | LC | L/S |  | MTB | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | N/A | N/A | 13000000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 13000000 | DD(R )C-Engr Y. M. Bulama | DHPD-J.C.O Bosah
Consultancy services for the Design of Omuaran-Isanlu Road in Kwara State ()Lot 3 | LC | L/S |  | MTB | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | N/A | N/A | 12000000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 12000000 | DD(R )C-Engr Y. M. Bulama | DHPD-J.C.O Bosah
Consultancy services for the Design of Dikwa-Gajiram-Gubio Road in Borno State | LC | L/S | 40000000 | MTB | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | N/A | N/A | 20000000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 20000000 | DD( R)E -Engr E. E. Ije | DHPD-J.C.O Bosah
Consultancy services for the Design of Mambilla Ring Road | LC | L/S |  | MTB | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | N/A | N/A | 20000000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 20000000 | DD( R)E -Engr E. E. Ije | DHPD-J.C.O Bosah
Consultancy services for the Design of Zaria-Funtua Rd. in Kaduna/Katsina States | LC | L/S | 40000000 | MTB | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | N/A | N/A | 20000000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 20000000 | DD(R )C-Engr Y.M. Bulama | DHPD-J.C.O Bosah
Consultancy services for the Design of Gaya-Balare Rd. in Kano State | LC | L/S |  | MTB | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | N/A | N/A | 20000000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 20000000 | DD(R )C-Engr Y.M.Bulama | DHPD-J.C.O Bosah
Consultancy services for the Design of Ozalla-Agbogugu-Ihe-Oweru-Ogugu-Nenwe-Mgbowo Awgu Road in Enugu State | LC | L/S | 40000000 | MTB | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | N/A | N/A | 13000000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 13000000 | DD( R)E -Engr E. E. Ije | DHPD-J.C.O Bosah
Consultancy services for the Design of Mbano-Okigwe Road in Imo State | LC | L/S |  | MTB | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | N/A | N/A | 13000000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 13000000 | DD( R)E -Engr E. E. Ije | DHPD-J.C.O Bosah
Consultancy services for the Design of Uzouwani-Anaku-Otuocha Ananbra/Enugu State | LC | L/S |  | MTB | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | N/A | N/A | 13000000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 13000000 | DD( R)E -Engr E. E. Ije | DHPD-J.C.O Bosah
Consultancy services for the Design of Okutukutu-Tombia Road | LC | L/S | 40000000 | MTB | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | N/A | N/A | 13000000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 13000000 | DD( R)E -Engr E. E. Ije | DHPD-J.C.O Bosah
Consultancy services for the Design of Bomadi-Warri Road | LC | L/S |  | MTB | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | N/A | N/A | 13000000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 13000000 | DD(R )C-Engr Y.M.Bulama | DHPD-J.C.O Bosah
Consultancy services for the Design of Asaba-Ogwushiwu-Umunede—Agbor-Edo State Border | LC | L/S |  | MTB | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | N/A | N/A | 13000000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 13000000 | DD(R )C-Engr Y. M. Bulama | DHPD-J.C.O Bosah
Consultancy services for the Design of Idoani-Idogun-Imeri-Aiyegunle Road in Ondo State | LC | L/S | 40000000 | MTB | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | N/A | N/A | 20000000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 20000000 | DD(R )W-Engr G.O.Ikenga | DHPD-J.C.O Bosah
Consultancy services for the Design of IIseyin-Alaga-Saki-Ilesha-Baruba Rd. (Ipapo-Alyaga Section in Oyo State | LC | L/S |  | MTB | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | N/A | N/A | 20000000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 20000000 | DD(R )W-Engr G.O.Ikenga | DHPD-J.C.O Bosah
Consultancy services for the Inspetion of Bridges Nationwide | LC | L/S | 40000000 | MTB | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | N/A | N/A | 40000000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 40000000 | DD(BD)-Engr B. K Okafor | DHPD-J.C.O Bosah
Consultancy services for the Automatic Count on 6 road each in the North & South of the country | LC | L/S | 30000000 | MTB | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | N/A | N/A | 4500000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 4500000 | DDHP- Engr C. P Enwonwu | DHPD-J.C.O Bosah
Consultancy services for the Manual traffic Count on Federal roads, 9roads each in the North and South of the Country | LC | L/S |  | MTB | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | N/A | N/A | 6400000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 6400000 | DDHP- Engr C. P Enwonwu | DHPD-J.C.O Bosah
Consultancy services for the Review of Road Inventory nationwide 2010 | LC | L/S |  | MTB | 8 - 29 Jan | 2-17 Feb. | N/A | N/A | N/A | N/A | 18 Feb. | 18 Mar | 19Mar - 2Apr. | 5 - 19 Apr | 20 Apr - 5 May | 6 - 20 May | 21 - 31May | N/A | N/A | 10500000 | 1 - 8 June | 9 - 23 June |  | 15 Sep | 15 Dec | 10500000 | DDHP- Engr C. P Enwonwu | DHPD-J.C.O Bosah
TOTAL
Ministry/Department/Agency: FEDERAL MINISTRY OF WORKS, HOUSING AND URBAN DEV. HIGHWAYS | [6 empty] | THE TIME LINE IS TO BE COMPARED WITH THE COUNCILS APPROVAL
Budgetary Year: 2010 --- Goods | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
[5 empty] | add 2 wks |  | Actual
List of Contracts
Procurement of the Automatic Traffic Counter with complete accessries, Asphaltic belt, nails, clips, tube including the training of 3 officers on the machine operations. | 1 |  | 8000000 | OCB | N/A | MTB | Plan | N/A | N/A | N/A | 17 Feb | 31 Mar | 1 - 16 Apr | 19 Apr - 3 May | 8000000 | N/A | 4 - 11 May | 12 - 26 May | N/A | 15 June | 16 - 30 June | DDHP- Engr C. P Enwonwu | DHPD-J.C.O Bosah
Actual
Supply of Laboratory Testing Equipment of PEU, Kaduna | 2 | A | 10000000 | OCB | N/A | MTB | Plan | N/A | N/A | N/A | 17 Feb | 31 Mar | 1 - 16 Apr | 19 Apr - 3 May | 10000000 | N/A | 4 - 11 May | 12 - 26 May | N/A | 15 June | 16 - 30 June | DD(M&G)-Engr S. Abu | DHPD-J.C.O Bosah
Actual
Supply of Laboratory Testing Equipment of PEU, Lagos | 2 | B | 10000000 | OCB | N/A | MTB | Plan | N/A | N/A | N/A | 17 Feb | 31 Mar | 1 - 16 Apr | 19 Apr - 3 May | 10000000 | N/A | 4 - 11 May | 12 - 26 May | N/A | 15 June | 16 - 30 June | DD(M&G)-Engr S. Abu | DHPD-J.C.O Bosah
Actual
Supply of Laboratory Testing Equipment of PEU, Owerri | 2 | C | 10000000 | OCB | N/A | MTB | Plan | N/A | N/A | N/A | 17 Feb | 31 Mar | 1 - 16 Apr | 19 Apr - 3 May | 10000000 | N/A | 4 - 11 May | 12 - 26 May | N/A | 15 June | 16 - 30 June | DD(M&G)-Engr S. Abu | DHPD-J.C.O Bosah
Actual
Supply of Laboratory Testing Equipment of PEU, Jos | 2 | D | 5000000 | OCB | N/A | MTB | Plan | N/A | N/A | N/A | 17 Feb | 31 Mar | 1 - 16 Apr | 19 Apr - 3 May | 5000000 | N/A | 4 - 11 May | 12 - 26 May | N/A | 15 June | 16 - 30 June | DD(M&G)-Engr S. Abu | DHPD-J.C.O Bosah
Actual
Supply of 2No. H In x Vehicles to PEU, Sheda Town for Electric Operations | 3 | A | 15000000 | OCB | N/A | MTB | Plan | N/A | N/A | N/A | 17 Feb | 31 Mar | 1 - 16 Apr | 19 Apr - 3 May | 15000000 | N/A | 4 - 11 May | 12 - 26 May | N/A | 15 June | 16 - 30 June | DD(M&G)-Engr S. Abu | DHPD-J.C.O Bosah
Actual
Supply of Laboratory Equipment to M & G laboratory, Sheda | 3 | B | 20000000 | OCB | N/A | MTB | Plan | N/A | N/A | N/A | 17 Feb | 31 Mar | 1 - 16 Apr | 19 Apr - 3 May | 20000000 | N/A | 4 - 11 May | 12 - 26 May | N/A | 15 June | 16 - 30 June | DD(M&G)-Engr S. Abu | DHPD-J.C.O Bosah
Actual
Provision of 5No Total Station Survey Equipmenmt | 4 |  | 30000000 | OCB | N/A | MTB | Plan | N/A | N/A | N/A | 17 Feb | 31 Mar | 1 - 16 Apr | 19 Apr - 3 May | 30000000 | N/A | 4 - 11 May | 12 - 26 May | N/A | 15 June | 16 - 30 June | DD(M&G)-Engr S. Abu | DHPD-J.C.O Bosah
Actual
Procurement of Bridgwe maintenance/Testing Tools and equipment | 5 |  | 10000000 | OCB | N/A | MTB | Plan | N/A | N/A | N/A | 17 Feb | 31 Mar | 1 - 16 Apr | 19 Apr - 3 May | 10000000 | N/A | 4 - 11 May | 12 - 26 May | N/A | 15 June | 16 - 30 June | DD(M&G)-Engr S. Abu | DHPD-J.C.O Bosah
Actual
Procurement of Bailey Bridge Components/Fittings | 6 |  | 10000000 | OCB | N/A | MTB | Plan | N/A | N/A | N/A | 17 Feb | 31 Mar | 1 - 16 Apr | 19 Apr - 3 May | 10000000 | N/A | 4 - 11 May | 12 - 26 May | N/A | 15 June | 16 - 30 June | DD(BD)-Engr B. K Okafor | DHPD-J.C.O Bosah
Actual
TOTAL |  |  | 128000000 | [11 empty] | 128000000
Ministry/Department/Agency: FEDERAL MINISTRY OF WORKS, HOUSING AND URBAN DEV. HIGHWAYS
Budgetary Year: 2010 --- Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 12 Months
add 2 wks
List of Contracts
DUALISATION OF IBADAN - ILORIN ROAD, SECTION II | 1 |  | BEME | OCB | 1000000000 | PRE - QUAL | FEC | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 1000000000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | June 2014 | June 2015 | 48000000000 | DD(CR)W-Engr.R.O.C. Agosobo | DH(C&R)-Engr. S. K.Haliru
POTISKUM-UDUBO-GAMAWA-GAMYIN ROAD (R333) SECTION II(UDUBO - GAMAWA - GAMAYIN ROAD) IN BAUCHI | 2 |  | BEME | OCB | 800000000 | PRE - QUAL | MTB | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 800000000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | June 2012 | June 2013 | 5000000000 | DD(CR)NE - Engr U. C. Ekenna | DH(C&R)-Engr. S. K.Haliru
REHABILITATION OF LAFIA-OBI-AWE-TUNGA ROAD IN NASARAWA STATE | 3 |  | BEME | OCB | 800000000 | PRE - QUAL | MTB | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 800000000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | Mar 2012 | Mar 2013 | 4800000000 | DD(CR)C -Engr. G.O. Anaduaka | DH(C&R)-Engr. S. K.Haliru
REHABILITATION OF HADEJIA-NGURU ROAD IN JIGAWA STATE, PHASE II KIRIKASAMA-NGURU | 4 |  | BEME | OCB | 1000000000 | PRE - QUAL | FEC | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 1000000000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | June 2012 | June2013 | 5200000000 | DD(CR)C -Engr. G.O. Anaduaka | DH(C&R)-Engr. S. K.Haliru
REHABILITATION OF APAPA - OSHODI EXPRESSWAY IN LAGOS | 5 |  | BEME | OCB | 3000000000 | PRE - QUAL | FEC | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 3000000000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | Dec 2012 | Dec 2013 | 15000000000 | DD(CR)W-Engr.R.O.C. Agosobo | DH(C&R)-Engr. S. K.Haliru
REHABILITATION OF BAUCHI - DASS- TAFAWA BALEAWA ROAD | 6 |  | BEME | OCB | 1000000000 | PRE - QUAL | FEC | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 1000000000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | Mar 2012 | Mar 2013 | 4500000000 | DD(CR)C -Engr. G.O. Anaduaka | DH(C&R)-Engr. S. K.Haliru
DAMASAK - DUTSE (NIGERIA) - DIFFA (NIGER REPUBLIC) ROAD | 7 |  | BEME | OCB | 1000000000 | PRE - QUAL | FEC | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 1000000000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | Mar 2012 | Mar 2013 | 5700000000 | DD(CR)NE - Engr U. C. Ekenna | DH(C&R)-Engr. S. K.Haliru
AWGU - NDIABOH-MPU-AKAEZE ROAD | 8 |  | BEME | OCB | 750000000 | PRE - QUAL | MTB | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 750000000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | June 2012 | June 2013 | 6200000000 | DD(CR)E-Engr. G.O. Osakwe | DH(C&R)-Engr. S. K.Haliru
REHABILITATION OF MAIDUGURI - DIKWA - GAMBORU ROAD,. SECTION II DIKWA - GAMBORU | 9 |  | BEME | OCB | 1500000000 | PRE - QUAL | FEC | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 1500000000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | Dec 2012 | Dec 2013 | 7500000000 | DD(CR)NE - Engr U. C. Ekenna | DH(C&R)-Engr. S. K.Haliru
REHABILITATION OF YANA-SHIRA-AZARE ROAD | 10 |  | BEME | OCB | 800000000 | PRE - QUAL | MTB | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 800000000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | Mar 2012 | Mar 2013 | 4900000000 | DD(CR)C -Engr. G.O. Anaduaka | DH(C&R)-Engr. S. K.Haliru
OSHOGBO - ILESHA ROAD IN OSHUN STATE | 11 |  | BEME | OCB | 120000000 | PRE - QUAL | MTB | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 120000000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | June 2012 | June 2013 | 700000000 | DD(CR)W-Engr.R.O.C. Agosobo | DH(C&R)-Engr. S. K.Haliru
CONSTRUCTION OF WAREHOUSE AT PH WEIGHBRIDGE STATION | 12 | A | BEME | OCB | 3700000 | PRE - QUAL | MTB | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 3700000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | Aug 2010 | Jan 2011 | 3700000 | DDHP- Engr C. P Enwonwu | DHPD-J.C.O Bosah
STREETLIGHT INSTALLATION AT OWODE ONIRIN WEIGHBRIDGE STATION INCLUDING PROVISION FOR SECURITY FOR 12 MONTHS | 12 | B | BEME | OCB | 3700000 | PRE - QUAL | MTB | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 3700000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | Aug 2010 | Sep 2010 | 3700000 | DDHP- Engr C. P Enwonwu | DHPD-J.C.O Bosah
STREETLIGHT INSTALLATION AT PH WEIGHBRIDGE STATION INCLUDING PROVISION OF SECURITY FOR 12MONTHS | 12 | C | BEME | OCB | 4200000 | PRE - QUAL | MTB | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 4200000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | Aug 2010 | Sep 2010 | 4200000 | DDHP- Engr C. P Enwonwu | DHPD-J.C.O Bosah
REVONATION OF ADMINISTRATION BLOCK, POLICE POST, AT PH WEIGHBRIDGE STATION | 12 | D | BEME | OCB | 3300000 | PRE - QUAL | MTB | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 3300000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | Aug 2010 | Sep 2010 | 3300000 | DDHP- Engr C. P Enwonwu | DHPD-J.C.O Bosah
STREETLIGHT INSTALLATION AT MAIDUGURI WEIGHBRIDGE STATION INCLUDING PROVISION OF SECURITY FOR 12MONTHS | 12 | E | BEME | OCB | 4000000 | PRE - QUAL | MTB | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 4000000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | Aug 2010 | Sep 2010 | 4000000 | DDHP- Engr C. P Enwonwu | DHPD-J.C.O Bosah
ACCESS ROAD TO WEIGHBRIDGE STATION REPAIRS AT OWODE ONIRIN | 12 | F | BEME | OCB | 7700000 | PRE - QUAL | MTB | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 7700000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | Aug 2010 | Aug 2011 | 7700000 | DDHP- Engr C. P Enwonwu | DHPD-J.C.O Bosah
DIGITAL BMS AVERY WEIGHBRIDGE AT PH | 12 | G | BEME | OCB | 20000000 | PRE - QUAL | MTB | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 20000000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | June 2011 | Dec 2011 | 20000000 | DDHP- Engr C. P Enwonwu | DHPD-J.C.O Bosah
DIGITAL BMS AVERY WEIGHBRIDGE AT OWODE ONIRIN | 12 | H | BEME | OCB | 20000000 | PRE - QUAL | MTB | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 20000000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | June 2011 | Dec 2011 | 20000000 | DDHP- Engr C. P Enwonwu | DHPD-J.C.O Bosah
40KVA SOUNDPROOF GENERATOR INCLUDING INSTALLATIONFOR PH WEIGHBRIDGE | 12 | I | BEME | OCB | 3700000 | PRE - QUAL | MTB | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 3700000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | Aug 2010 | Sep 2010 | 3700000 | DDHP- Engr C. P Enwonwu | DHPD-J.C.O Bosah
40KVA SOUNDPROOF GENERATOR INCLUDING INSTALLATION FOR OWODE ONIRIN WEIGHBRIDGE STATION | 12 | J | BEME | OCB | 3700000 | PRE - QUAL | MTB | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 3700000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | Aug 2010 | Sep 2010 | 3700000 | DDHP- Engr C. P Enwonwu | DHPD-J.C.O Bosah
40KVA SOUNDPROOF GENERATOR INCLUDING INSTALLATION FOR OPI WEIGHBRIDGE STATION | 12 | K | BEME | OCB | 3700000 | PRE - QUAL | MTB | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 3700000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | Aug 2010 | Sep 2010 | 3700000 | DDHP- Engr C. P Enwonwu | DHPD-J.C.O Bosah
40KVA SOUNDPROOF GENERATOR INCLUDING INSTALLATION FOR MAIDUGURI WEIGHBRIDGE STATION | 12 | L | BEME | OCB | 3700000 | PRE - QUAL | MTB | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 3700000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | Aug 2010 | Sep 2010 | 3700000 | DDHP- Engr C. P Enwonwu | DHPD-J.C.O Bosah
ACCESS ROAD TO WEIGHBRIDGE STATION REPAIRS AT PH | 12 | M | BEME | OCB | 7700000 | PRE - QUAL | MTB | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 7700000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | Aug 2010 | Aug 2011 | 7700000 | DDHP- Engr C. P Enwonwu | DHPD-J.C.O Bosah
RE-CONSTRUCTION OF DAMAGED FENCE AT MATERIAL AND GEOTECHNIC LABORATORY SHEDA | 13 | A | BEME | OCB | 50000000 | PRE - QUAL | MTB | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 50000000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | Aug 2010 | Aug 2010 | 50000000 | DD(M&G)-Engr S. Abu | DHPD-J.C.O Bosah
CONSTRUCTION OF EARTH ROAD WITHIN THE LABORATORY COMPLEX AT SHEDA TOWN, FCT | 13 | B | BEME | OCB | 12000000 | PRE - QUAL | MTB | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 12000000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | June 2011 | June 2012 | 12000000 | DD(M&G)-Engr S. Abu | DHPD-J.C.O Bosah
RENOVATION OF SOIL AND ASPHALT LABORATORY AT PEU, KADUNA | 14 | A | BEME | OCB | 60000000 | PRE - QUAL | MTB | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 60000000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | Aug 2010 | Sep 2010 | 60000000 | DD(M&G)-Engr S. Abu | DHPD-J.C.O Bosah
UPGRADING OF PEU, JOS ENVIRONMENT (FENCE) | 14 | B | BEME | OCB | 10000000 | PRE - QUAL | MTB | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 10000000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | Aug 2010 | Sep 2010 | 10000000 | DD(M&G)-Engr S. Abu | DHPD-J.C.O Bosah
UPGRADING OF PEU, LABORATORY OWERRI | 14 | C | BEME | OCB | 10000000 | PRE - QUAL | MTB | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 10000000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | Aug 2010 | Sep 2010 | 10000000 | DD(M&G)-Engr S. Abu | DHPD-J.C.O Bosah
REPAIR OF BRIDGE MAINTENANCE OFFICES AT HIGHWAY CAMPS AT SULEJA AND IPONRI | 15 |  | BEME | OCB | 40000000 | PRE - QUAL | MTB | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 40000000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | Aug 2010 | Sep 2010 | 40000000 | DD(BD)-Engr B.K.Okafor | DHPD-J.C.O Bosah
UPGRADING OF FACILITIES FOR HIGHWAY TRAINING SCHOOL KADUNA | 16 | A | BEME | OCB | 25000000 | PRE - QUAL | MTB | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 25000000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | Aug 2010 | Sep 2010 | 25000000 | DD(M&G)-Engr S. Abu | DHPD-J.C.O Bosah
UPGRADING OF FACILITIES FOR HIGHWAY TRAINING SCHOOL LAGOS | 16 | B | BEME | OCB | 25000000 | PRE - QUAL | MTB | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 25000000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | Aug 2010 | Sep 2010 | 25000000 | DD(M&G)-Engr S. Abu | DHPD-J.C.O Bosah
UPGRADING OF FACILITIES FOR HIGHWAY TRAINING SCHOOL UGONEKI | 16 | C | BEME | OCB | 30000000 | PRE - QUAL | MTB | 8 - 29 Jan | 2 -17 Feb. | 17 Feb -3 Mar | 4 Mar | 1Apr | 2 -16 Apr | 19 - 26 Apr. | 30000000 | 27Apr-11 May | 12-19 May | 20 - 27 May | 1 - 8 June | Aug 2010 | Sep 2010 | 30000000 | DD(M&G)-Engr S. Abu | DHPD-J.C.O Bosah
TOTAL |  |  |  |  | 12121100000 | [9 empty] | 12121100000

## PHCN_Benin
Ministry/Department/Agency: BENIN ELECTRICITY DISTRIBUTION COMPANY
Budgetary Year: 2011 --- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
|  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
add 2 wks
List of Contracts
FEEDER PILLARS AND RMU
Supply of Feeder Pillar and RMU |  | Lot 8 | 20000000 | NCB | Pre-qualification | PTB | January 19 - February 3, 2011 | February 3, 2011 - February 24, 2011 | February 24, 2011 - March 9, 2011 | March 10, 2011 | March 13, 2011 | March 7, 2011 - March 14, 2010 | April 13, 2011 - April 27, 2010 |  | NA | March 14 - 21, 2011 | April 22 - April 29, 2011 | On Demand | May 1 - July 1, 2011 | July 2-July 15, 2011 | Engr. M. Adebayo | AGM (Tech. Serv(Engr. Umoren)
SUPPLY OF HT AND LT CABLES AND TERMINATION KITS
Supply of HT and LT Cables and Termination Kits |  | Lot 15 | 60000000 | NCB | Pre-qualification | MTB | January 19 - February 3, 2011 | February 3, 2011 - February 24, 2011 | February 24, 2011 - March 9, 2011 | March 10, 2011 | March 13, 2011 | March 7, 2011 - March 14, 2010 | April 13, 2011 - April 27, 2010 |  | NA | March 14 - 21, 2011 | April 22 - April 29, 2011 | On Demand | May 1 - July 1, 2011 | July 2-July 15, 2011 | Engr. M. Adebayo | AGM (Tech. Serv(Engr. Umoren)
SUPPLY OF 33KV FIBRE GLASS CROSS ARMS TO REHABILITATE WEAK 33KV LINES
Supply of 33kv Fibre Glass Cross Arms to Rehabilitate Weak 33KV Lines |  | Lot 16 | 25000000 | NCB | Pre-qualification | PTB | January 19 - February 3, 2011 | February 3, 2011 - February 24, 2011 | February 24, 2011 - March 9, 2011 | March 10, 2011 | March 13, 2011 | March 7, 2011 - March 14, 2010 | April 13, 2011 - April 27, 2010 |  | NA | March 14 - 21, 2011 | April 22 - April 29, 2011 | On Demand | May 1 - July 1, 2011 | July 2-July 15, 2011 | Engr. M. Adebayo | AGM (Tech. Serv(Engr. Umoren)
Total Cost
105000000
Budgetary Year: 2011 --- Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
|  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
add 2 wks
List of Contracts
COMPLETION OF 1 X 7.5MVA, 33/11KV INJECTION SUBSTATION AT OKPANAM |  |  |  |  | 10000000
1 x 7.5MVA, 33/11KV Injection Substation at Okpanam |  | Lot 1 |  | NCB |  | Pre-Qualification | PTB | January 18, 2011 | January 19 - February 3, 2011 | February 3, 2011 - February 24, 2011 | February 24, 2011 - March 9, 2011 | March 10, 2011 | March 13, 2011 | March 7, 2011 - March 14, 2010 |  | N/A | March 14 - 21, 2011 | April 22 - April 29, 2011 | On Demand | June 29, 2011 | June 30 - December 31, 2011 |  | Engr. M. Adebayo | AGM (Tech. Serv(Engr. Umoren)
COMPLETION OF 1 X 7.5MVA, 33/11KV INJECTION SUBSTATION AT ONICHA UKU |  |  |  |  | 10000000
1 x 7.5MVA, 33/11KV Injection Substation at Onicha Uku |  | Lot 2 |  | NCB |  | Pre-Qualification | PTB | January 18, 2011 | January 19 - February 3, 2011 | February 3, 2011 - February 24, 2011 | February 24, 2011 - March 9, 2011 | March 10, 2011 | March 13, 2011 | March 7, 2011 - March 14, 2010 |  | N/A | March 14 - 21, 2011 | April 22 - April 29, 2011 | On Demand | June 29, 2011 | June 30 - December 31, 2011 |  | Engr. M. Adebayo | AGM (Tech. Serv(Engr. Umoren)
COMPLETION OF 33KV DOUBLE CIRCUIT O/M LINE TO EVBUOTUBU | 43000012530000 |  |  |  | 85000000
Completion of 33KV Double Circuit O/M Line to Evbuotubu |  | Lot 3 |  | NCB |  | Pre-Qualification | PTB | January 18, 2011 | January 19 - February 3, 2011 | February 3, 2011 - February 24, 2011 | February 24, 2011 - March 9, 2011 | March 10, 2011 | March 13, 2011 | March 7, 2011 - March 14, 2010 |  | N/A | March 14 - 21, 2011 | April 22 - April 29, 2011 | On Demand | June 29, 2011 | June 30 - December 31, 2011 |  | Engr. M. Adebayo | AGM (Tech. Serv(Engr. Umoren)
11KV AND 33KV RECONDOCTORING |  |  |  |  | 50000000
11KV and 11KV Reconductoring |  | LOT 4 |  |  |  | Pre-Qualification | PTB | January 18, 2011 | January 19 - February 3, 2011 | February 3, 2011 - February 24, 2011 | February 24, 2011 - March 9, 2011 | March 10, 2011 | March 13, 2011 | March 7, 2011 - March 14, 2010 |  | N/A | March 14 - 21, 2011 | April 22 - April 29, 2011 | On Demand | June 29, 2011 | June 30 - December 31, 2011 |  | Engr. M. Adebayo | AGM (Tech. Serv(Engr. Umoren)
TRACE CLEARING FOR 11KV AND 33KV LINES
Trace Clearing of 11KV and 33KV Lines |  | LOT 5 |  |  | 10000000 | Pre-Qualification | PTB | January 18, 2011 | January 19 - February 3, 2011 | February 3, 2011 - February 24, 2011 | February 24, 2011 - March 9, 2011 | March 10, 2011 | March 13, 2011 | March 7, 2011 - March 14, 2010 |  | N/A | March 14 - 21, 2011 | April 22 - April 29, 2011 | On Demand | June 29, 2011 | June 30 - December 31, 2011 |  | Engr. Ekeleme | AGM (Tech. Serv(Engr. Umoren)
REPLACEMENT OF OBSOLETE SWITCHGEARS |  | Lot 6 |  |  | 10000000 | Pre-Qualification | PTB | January 18, 2011 | January 19 - February 3, 2011 | February 3, 2011 - February 24, 2011 | February 24, 2011 - March 9, 2011 | March 10, 2011 | March 13, 2011 | March 7, 2011 - March 14, 2010 |  | N/A | March 14 - 21, 2011 | April 22 - April 29, 2011 | On Demand | June 29, 2011 | June 30 - December 31, 2011 |  | Engr. M. Adebayo | AGM (Tech. Serv(Engr. Umoren)
11KV AND 33KV OVERHEAD LINES |  | Lot 7 |  | NCB | 20000000 | Pre-Qualification | PTB | January 18, 2011 | January 19 - February 3, 2011 | February 3, 2011 - February 24, 2011 | February 24, 2011 - March 9, 2011 | March 10, 2011 | March 13, 2011 | March 7, 2011 - March 14, 2010 |  | N/A | March 14 - 21, 2011 | April 22 - April 29, 2011 | On Demand | June 29, 2011 | June 30 - December 31, 2011 |  | Engr. M. Adebayo | AGM (Tech. Serv(Engr. Umoren)
REHABILITATION OF DISTRIBUTION TRANSFORMERS (OIL, FUSES, ETC) |  | Lot 9 |  | NCB | 10000000 | Pre-Qualification | PTB | January 18, 2011 | January 19 - February 3, 2011 | February 3, 2011 - February 24, 2011 | February 24, 2011 - March 9, 2011 | March 10, 2011 | March 13, 2011 | March 7, 2011 - March 14, 2010 |  | N/A | March 14 - 21, 2011 | April 22 - April 29, 2011 | On Demand | June 29, 2011 | June 30 - December 31, 2011 |  | Engr. M. Adebayo | AGM (Tech. Serv(Engr. Umoren)
ENERHEN SUBSTATION UPGRADE FROM 2X7.5MVA TO 2 X 15MVA, 33/11KV SUBSTATION WITH COMPLETE ACCESSORIES (150M) |  | Lot 10 |  | NCB | 120000000 | Pre-Qualification | PTB | January 18, 2011 | January 19 - February 3, 2011 | February 3, 2011 - February 24, 2011 | February 24, 2011 - March 9, 2011 | March 10, 2011 | March 13, 2011 | March 7, 2011 - March 14, 2010 |  | N/A | March 14 - 21, 2011 | April 22 - April 29, 2011 | On Demand | June 29, 2011 | June 30 - December 31, 2011 |  | Engr. M. Adebayo | AGM (Tech. Serv(Engr. Umoren)
CONSTRUCTION OF 2X15MVA, 33/11KV INJECTION SUBSTATION COMPLETE WITH ACCESSORIES AT PTI |  | Lot 11 |  | NCB | 120000000 | Pre-Qualification | PTB | January 18, 2011 | January 19 - February 3, 2011 | February 3, 2011 - February 24, 2011 | February 24, 2011 - March 9, 2011 | March 10, 2011 | March 13, 2011 | March 7, 2011 - March 14, 2010 |  | N/A | March 14 - 21, 2011 | April 22 - April 29, 2011 | On Demand | June 29, 2011 | June 30 - December 31, 2011 |  | Engr. M. Adebayo | AGM (Tech. Serv(Engr. Umoren)
CONSTRUCTION OF 14KM PTI 33KV FEEDER FROM EFFURUN T/S |  | Lot 12 |  | NCB | 56000000 | Pre-Qualification | MTB | January 18, 2011 | January 19 - February 3, 2011 | February 3, 2011 - February 24, 2011 | February 24, 2011 - March 9, 2011 | March 10, 2011 | March 13, 2011 | March 7, 2011 - March 14, 2010 |  | N/A | March 14 - 21, 2011 | April 22 - April 29, 2011 | On Demand | June 29, 2011 | June 30 - December 31, 2011 |  | Engr. M. Adebayo | AGM (Tech. Serv(Engr. Umoren)
CONSTRUCTION OF 33KV FEEDER FROM ONDO T/S TO ONDO TOWN WITH T-OFF TO ILU-OLUJI AND OWENA/BOLORUNDURO |  | Lot 13 |  | NCB | 50000000 | Pre-Qualification | PTB | January 18, 2011 | January 19 - February 3, 2011 | February 3, 2011 - February 24, 2011 | February 24, 2011 - March 9, 2011 | March 10, 2011 | March 13, 2011 | March 7, 2011 - March 14, 2010 |  | N/A | March 14 - 21, 2011 | April 22 - April 29, 2011 | On Demand | June 29, 2011 | June 30 - December 31, 2011 |  | Engr. M. Adebayo | AGM (Tech. Serv(Engr. Umoren)
CONSTRUCTION OF DISTRIBUTION SUBSTATIONS TO RELIEV OVERLOADED ONES ACROSS THE ZONE |  | Lot 14 |  | NCB | 50000000 | Pre-Qualification | PTB | January 18, 2011 | January 19 - February 3, 2011 | February 3, 2011 - February 24, 2011 | February 24, 2011 - March 9, 2011 | March 10, 2011 | March 13, 2011 | March 7, 2011 - March 14, 2010 |  | N/A | March 14 - 21, 2011 | April 22 - April 29, 2011 | On Demand | June 29, 2011 | June 30 - December 31, 2011 |  | Engr. M. Adebayo | AGM (Tech. Serv(Engr. Umoren)
Total Cost |  |  |  |  | 601000000

## PHCN_Jebba
PROCUREMENT PLAN - GOODS - 2011
Ministry/Department/Agency: PHCN: Jebba Hydro Electric Plc.
Budgetary Year: 2011 | [8 empty] | Draft and Documents | If withing MDAs Threshold, No-objection Date not required
Desk Officer/Contact #: Surajo Abdullahi (08051388884) Email: pmprocjebbahydro@yahoo.com | [6 empty] | Draft Bid Documents |  | including spec. and | General Proc. Notice | Bidding Period |  | Bid Evaluation |  | Contract Finalization
|  |  | BASIC DATA |  |  |  | Spec and quantity |  | quantity draft SPN | Advert | [10 empty] | Contract Implementation
Project Description | Package | Lot Number | Estimated | Procurement | Pre-qualification | Approval | Prep & | Project Description | MDAs | Advertisment | Bid Invitation | Bid Closing- | Submission | MDAs | Certifiable | FEC Approval | Date | Project Description | Date | Mobilization | Arrival of Goods | Inspection | Action Party | Champion
| Number |  | Amount in Naira | Method |  | Threshold | Submission |  | Approval | for Pre- | Date | Opening | Bid Eval. Rpt. | Approval/BPP | Amount per |  | Contract |  | Contract | Advance |  | Final
[7 empty] | by MDAs |  |  | Qualification |  |  |  | No Objection | Contract |  | Offer |  | Signature | Payment |  | Acceptance
Norm Dureation of Proc. Steps |  |  |  |  | If Prequalification |  |  | Norm Duration of Proc. Steps | 1 - 2 Wks | 2 Wks | 2 - 4 Wks | 6 Wks | 2 Wks | 1 - 2 Wks |  | 2 Wks | 1 - 2 Wks | Norm Duration of Proc. Steps | 2 Wks | 2 - 3 Wks | T | 2 Wks
add 2 wks
List of Contracts |  |  | 250000000 |  | (General Procurement Notice) |  |  | List of Contracts | [9 empty] | List of Contracts
Oil Pumps | "A" | LOT 1 |  | National Competitive Bidding | 2011-07-02 | PTB | 14/01/11 - 30/03/11 | Oil Pumps | 14/01/11 - 30/03/11 | 07/02 - 20/02/11 | 01/03/11 - 30/03/11 | 30/03/2011 | 15/03/2011 | 01/04 - 15/04/2011 |  | N/A | 16/04/11 - 30/04/11 | Oil Pumps | 2011-01-04 | N/A | 01/04 - 30/4 | 1 Week | PM (Turbine) | AGM(M)
[10 empty] | (2 Wks) | [5 empty] | N/A
Valves | “A” | LOT 2 |  | National Competitive Bidding | 2011-07-02 | PTB | 14/01/11 - 30/03/11 | Valves | 14/01/11 - 30/03/11 | 07/02 - 20/02/11 | 01/03/11 - 30/03/11 | 30/03/2011 | 15/03/2011 | 01/04 - 15/04/2011 |  |  | 16/04/11 - 30/04/11 | Valves | 2011-01-04 | N/A | 01/04 - 30/4 | 1 Week | PM (Mtce) | AGM(M)
[10 empty] | (2 Wks) | [5 empty] | N/A
Plant equipment and tools | “A” | LOT 3 |  | National Competitive Bidding | 2011-07-02 | PTB | 14/01/11 - 30/03/11 | Plant equipment and tools | 14/01/11 - 30/03/11 | 07/02 - 20/02/11 | 01/03/11 - 30/03/11 | 30/03/2011 | 15/03/2011 | 01/04 - 15/04/2011 |  | N/A | 16/04/11 - 30/04/11 | Plant equipment and tools | 2011-01-04 | N/A | 01/04 - 30/4 | 1 Week | PM (Mtce) | AGM(M)
(2 Wks)
[5 empty] | 6 Weeks |  |  | Plant consumables | 14/01/11 - 30/03/11 | 07/02 - 20/02/11 | 01/03/11 - 30/03/11 | 30/03/2011 | 15/03/2011 | 01/04 - 15/04/2011 |  | N/A | 16/04/11 - 30/04/11 | Plant consumables | 2011-01-04 | N/A | 01/04 - 30/4 | 1 Week | PM (Mtce) | AGM(M)
Plant consumables | “A” | LOT 4 |  | National Competitive Bidding | 2011-07-02 | PTB | 14/01/11 - 30/03/11 |  |  | (2 Wks)
[8 empty] | Controllers, Switches, Contactors and Circuit breakers | 14/01/11 - 30/03/11 | 07/02 - 20/02/11 | 01/03/11 - 30/03/11 | 30/03/2011 | 15/03/2011 | 01/04 - 15/04/2011 |  | N/A | 16/04/11 - 30/04/11 | Controllers, Switches, Contactors and Circuit breakers | 2011-01-04 | N/A | 01/04 - 30/4 | 1 Week | PM (Tech. Services) | AGM(M)
Controllers, Switches, Contactors and Circuit breakers | “A” | LOT 5 |  | National Competitive Bidding | 2011-07-02 | PTB | 14/01/11 - 30/03/11 |  |  | (2 Wks)
[8 empty] | Electronic cards/modules and relays | 14/01/11 - 30/03/11 | 07/02 - 20/02/11 | 01/03/11 - 30/03/11 | 30/03/2011 | 15/03/2011 | 01/04 - 15/04/2011 |  | N/A | 16/04/11 - 30/04/11 | Electronic cards/modules and relays | 2011-01-04 | N/A | 01/04 - 30/4 | 1 Week | PM (Elect or PC M) | AGM(M)
Electronic cards/modules and relays | “A” | LOT 6 |  | National Competitive Bidding | 2011-07-02 | PTB | 14/01/11 - 30/03/11 |  |  | (2 Wks)
[8 empty] | Electrical Appliances and fittings | 14/01/11 - 30/03/11 | 07/02 - 20/02/11 | 01/03/11 - 30/03/11 | 30/03/2011 | 15/03/2011 | 01/04 - 15/04/2011 |  | N/A | 16/04/11 - 30/04/11 | Electrical Appliances and fittings | 2011-01-04 | N/A | 01/04 - 30/4 | 1 Week | PM (Electrical) | AGM(M)
Electrical Appliances and fittings | “A” | LOT 7 |  | National Competitive Bidding | 2011-07-02 | PTB | 14/01/11 - 30/03/11 |  |  | (2 Wks)
[8 empty] | Hydrology facilities | 14/01/11 - 30/03/11 | 07/02 - 20/02/11 | 01/03/11 - 30/03/11 | 30/03/2011 | 15/03/2011 | 01/04 - 15/04/2011 |  | N/A | 16/04/11 - 30/04/11 | Hydrology facilities | 2011-01-04 | N/A | 01/04 - 30/4 | 1 Week | PM (Hydrology or Dam Instrument | AGM (O)
Hydrology facilities | “A” | LOT 8 |  | National Competitive Bidding | 2011-07-02 | PTB | 14/01/11 - 30/03/11 |  |  | (2 Wks)
[8 empty] | Building materials, furniture and plumbing materials | 14/01/11 - 30/03/11 | 07/02 - 20/02/11 | 01/03/11 - 30/03/11 | 30/03/2011 | 15/03/2011 | 01/04 - 15/04/2011 |  | N/A | 16/04/11 - 30/04/11 | Building materials, furniture and plumbing materials | 2011-01-04 | N/A | 01/04 - 30/4 | 1 Week | PM (Civil) | AGM (O)
Building materials, furniture and plumbing materials | “A” | LOT 9 |  | National Competitive Bidding | 2011-07-02 | PTB | 14/01/11 - 30/03/11 |  |  | (2 Wks)
[8 empty] | Computer with accessaries/consumables and stationaries | 14/01/11 - 30/03/11 | 07/02 - 20/02/11 | 01/03/11 - 30/03/11 | 30/03/2011 | 15/03/2011 | 01/04 - 15/04/2011 |  | N/A | 16/04/11 - 30/04/11 | Computer with accessaries/consumables and stationaries | 2011-01-04 | N/A | 01/04 - 30/4 | 1 Week | PM (Planning) | AGM (O)
Computer with accessaries/consumables and stationaries | “A” | LOT 10 |  | National Competitive Bidding | 2011-07-02 | PTB | 14/01/11 - 30/03/11 |  |  | (2 Wks)
[8 empty] | Environmental Control facilities | 14/01/11 - 30/03/11 | 07/02 - 20/02/11 | 01/03/11 - 30/03/11 | 30/03/2011 | 15/03/2011 | 01/04 - 15/04/2011 |  | N/A | 16/04/11 - 30/04/11 | Environmental Control facilities | 2011-01-04 | N/A | 01/04 - 30/4 | 1 Week | PM (Hydrology or HR) | AGM (O)
Environmental Control facilities | “A” | LOT 11 |  | National Competitive Bidding | 2011-07-02 | PTB | 14/01/11 - 30/03/11 |  |  | (2 Wks)
Total |  |  | 250000000
PROCUREMENT PLAN - WORKS
Ministry/Department/Agency: PHCN: Jebba Hydro Electric Plc.
Budgetary Year: 2011
Desk Officer/Contact #: Surajo Abdullahi: (08051388884) Email: pmprocjebbahydro@yahoo.com | [8 empty] | Draft Bid Documents including |  | If with MDAs
|  |  | BASIC DATA | [5 empty] | Spec and quantities, draft SPN |  | Spec. Proc.
Project Description | Package | Lot | Lumpsum or Bill | Procurement | Estimated | Pre-or Post | Approval | Plan | Prep & | MDAs' | Advert |  | Bidding Period |  | Bid Evaluation |  | Contract Finalization | [5 empty] | Contract Implementation
| Number | Number | of Quantities | Method | Amount in | Qualification | Threshold | Vs | Submission | Approval | Notice | Project Description | Bid Invitation | Bid Closing- | Submission | MDAs | Contract Amount | FEC Approval | Date of | Date | Mobilization | Project Description | Substantial | Final | Final | Action Party | Champion
[5 empty] | Naira |  |  | Actual | by MDAs |  |  |  | Date | Opening | Bid Eval Rept. | Approval | Certified in N |  | Contract | Contract | Advance |  | Completion | Acceptance | Cost
Norm Dureation of Proc. Steps | [5 empty] | If Prequalification | [12 empty] | Offer | Signature | Payment
[6 empty] | add 2 wks | [5 empty] | Norm Dureation of Proc. Steps | 2 - 6 Wks | 6 Wks | 2 - 3 Wks | 1 - 2 Wks |  | 2 - 4 Wks | 1 - 2 Wks | 2 Wks |  | Norm Dureation of Proc. Steps |  | 6 Months
List of Contracts | [5 empty] | 6 Wks | [5 empty] | List of Contracts | [9 empty] | List of Contracts
Rehabilitation of 96.4MW Hydro Turbine Cenerating Unit 2G6 | "B" | LOT 1 | RRP | Selective | 3.1b- N6.2b | Concluded | FEC | Plan | Concluded | Concluded | N/A | Rehabilitation of 96.4MW Hydro Turbine Cenerating Unit 2G6 | Concluded | Concluded | Concluded | Concluded | In-view | 1/02-28/02 | 01/3-15/3 | 15-30/03 | On Demand | Rehabilitation of 96.4MW Hydro Turbine Cenerating Unit 2G6 | 1905-07-04 | 2012 |  | AGM (m) | CEO
[6 empty] | (6 Weeks) |  | Actual
Construction of Residential Camp | “B” | LOT 2 | BEME | National Competitive Bidding | 350000000 | 15/02-30/03 | PTB | Plan | 3/02-28/02 | 1st March | 1/03-30/03 | Construction of Residential Camp | 1/03-30/03 | 30/03 | 01/04-22/04 | 23/04-7/05 | In-view | N/A | 8/5-22/5 | 22/05-30/05 | On Demand | Construction of Residential Camp | 2011-01-09 | 2011-01-10 |  | PM(Civil) | AGM (M)
[6 empty] | (6 Weeks) |  | Actual
Plant Annual Inspection/Enhancement | “B1” | LOT 3 | BEME | National Competitive Bidding |  | 15/02 - 30/03 | PTB | Plan | 3/02-28/02 | Ist Macrh | 1/03-30/03 | Plant Annual Inspection/Enhancement 2G4 | 01/02 - 28/02 | 28/02 | 20/02 - 28/02 | 01/03 - 08/03 | In-view | N/A | 08/03 | 08/03 | On Demand | Plant Annual Inspection/Enhancement Unit 2G4 | 24/03/11 | 2011-01-04 |  | PM(Planning) | AGM (M)
[12 empty] | Plant Annual Inspection/Enhancement 2G1 | 21/03-15/04 | 15/04 | 16/04-28/04 | 28/04-03/05 | In-view | N/A | 03/05-06/05 | 06/05 | On Demand | Plant Annual Inspection/Enhancement Unit 2G1 | 24/06/11 | 2011-01-01 |  | PM(Planning) | AGM (M)
| “B2” | LOT 3 | BEME | National Competitive Bidding
[12 empty] | Plant Annual Inspection/Enhancement 2G2 | 15/09-16/10 | 16/10 | 16/10-31/10 | 01/11-07/11 | In-view | N/A | 05/11-08/11 | 08/11 | On Demand | Plant Annual Inspection/Enhancement 2G2 | 31/12/11 | 30/6/12 |  | PM(Planning) | AGM (M)
| “B3” | LOT 3 | BEME | National Competitive Bidding

## PHCN_Kainji
PROCUREMENT PLAN - GOODS - 2011
Ministry/Department/Agency: PHCN: Kainji Hydro Electric Plc.
Budgetary Year: 2011
Desk Officer/Contact #: Abdul Aziz Ibrahim: (08054426191) Email: mairauta@yahoo.com | [6 empty] | Draft Bid Documents |  |  | Draft and Documents | If withing MDAs Threshold, No-objection Date not required
|  |  | BASIC DATA |  |  |  | Spec and quantity |  |  | including spec. and | Spec. Proc. Notice | Bidding Period |  | Bid Evaluation |  | Contract Finalization
Project Description | Package | Lot Number | Estimated | Procurement | Pre-qualification | Approval | Prep & |  |  | quantity draft SPN | Advert | [10 empty] | Contract Implementation
| Number |  | Amount in Naira | Method |  | Threshold | Submission |  | Project Description | MDAs | Advertisment | Bid Invitation | Bid Closing- | Submission | MDAs | Certifiable | FEC Approval | Date |  | Project Description | Date | Mobilization | Arrival of Goods | Inspection | Action Party | Champion
[7 empty] | by MDAs |  |  | Approval | for Pre- | Date | Opening | Bid Eval. Rpt. | Approval/BPP | Amount per |  | Contract |  |  | Contract | Advance |  | Final
Norm Dureation of Proc. Steps |  |  |  |  | If Prequalification | [5 empty] | Qualification |  |  |  | No Objection | Contract |  | Offer |  |  | Signature | Payment |  | Acceptance
[5 empty] | add 2 wks |  |  |  | Norm Duration of Proc. Steps | 1 - 2 Wks | 2 Wks | 2 - 4 Wks | 6 Wks | 2 Wks | 1 - 2 Wks |  | 2 Wks | 1 - 2 Wks |  | Norm Duration of Proc. Steps | 2 Wks | 2 - 3 Wks | T | 2 Wks
List of Contracts
Heavy Duty Oil for Turbine and Generator Thrust Bearing and Transformer Oil |  |  |  |  | 6 Weeks |  | 24/1/11-11/4/11 |  | List of Contracts | [10 empty] | List of Contracts
| "A" | LOT 1 |  | National Competitive Bidding | 2011-01-03 | PTB |  |  | Heavy Duty Oil for Turbine and Generator Thrust Bearing and Transformer Oil | 11/4 - 12/4/11 | 1/3 -15/3/11 | 18/4/11-2/5/11 | 2011-07-05 | 16/5-23/5/11 | 23/5-6/6/11 |  | N/A | 6/6/11 - 20/6/11 |  | Heavy Duty Oil for Turbine and Generator Thrust Bearing and Transformer Oil | 20/6-6/7/11 | N/A | 2011-01-08 | 1 Week | PM (Turbine) | AGM(M)
Instrumentation, Protection Relays and Control |  |  |  |  | 6 Weeks |  | 24/1/11-11/4/11 |  |  |  | (2 Wks) | [5 empty] | N/A
Devices | “A” | LOT 2 |  | National Competitive Bidding | 2011-01-03 | PTB |  |  | Instrumentation, Protection Relays and Control Devices | 11/4 - 12/4/11 | 1/3 -15/3/11 | 18/4/11-2/5/11 | 2011-07-05 | 16/5-23/5/11 | 23/5-6/6/11 |  |  | 6/6/11 - 20/6/11 |  | Instrumentation, Protection Relays and Control Devices | 20/6-6/7/11 | N/A | 2011-01-08 | 1 Week | PM (PC&M) | AGM(M)
High and Medium Voltage Switch Gear, Transformer Measuring Instrument and Associated Auxiliaries |  |  |  |  | 6 Weeks |  | 24/1/11-11/4/11 |  |  |  | (2 Wks) | [5 empty] | N/A
| “A” | LOT 3 |  | National Competitive Bidding | 2011-01-03 | PTB |  |  | High and Medium Voltage Switch Gear, Transformer Measuring Instrument and Associated Auxiliaries | 11/4 - 12/4/11 | 1/3 -15/3/11 | 18/4/11-2/5/11 | 2011-07-05 | 16/5-23/5/11 | 23/5-6/6/11 |  | N/A | 6/6/11 - 20/6/11 |  | High and Medium Voltage Switch Gear, Transformer Measuring Instrument and Associated Auxiliaries | 20/6-6/7/11 | N/A | 2011-01-08 | 1 Week | PM (Electrical) | AGM(M)
[5 empty] | 6 Weeks | [5 empty] | (2 Wks)
Water and Oil Pumps for various application and |  |  |  |  | 6 Weeks |  | 24/1/11-11/4/11 |  | Water and Oil Pumps for various application and Ratings | 11/4 - 12/4/11 | 1/3 -15/3/11 | 18/4/11-2/5/11 | 2011-07-05 | 16/5-23/5/11 | 23/5-6/6/11 |  | N/A | 6/6/11 - 20/6/11 |  | Water and Oil Pumps for various application and | 20/6-6/7/11 | N/A | 2011-01-08 | 1 Week | PM (Auxiliary) | AGM(M)
Ratings | “A” | LOT 4 |  | National Competitive Bidding | 2011-01-03 | PTB |  |  |  |  | (2 Wks) | [8 empty] | Ratings
Special equipment - Procurement of Hiab and Fire Tender Pick-Up |  |  |  |  | 6 Weeks |  | 24/1/11-11/4/11 |  | Special equipment - Procurement of Hiab and Fire Tender Pick-Up | 11/4 - 12/4/11 | 1/3 -15/3/11 | 18/4/11-2/5/11 | 2011-07-05 | 16/5-23/5/11 | 23/5-6/6/11 |  | N/A | 6/6/11 - 20/6/11 |  | Special equipment - Procurement of Hiab and Fire Tender Pick-Up | 20/6-6/7/11 | N/A | 2011-01-08 | 1 Week | PM (Tech. Services) | AGM(M)
| “A” | LOT 5 |  | National Competitive Bidding | 2011-01-03 | PTB |  |  |  |  | (2 Wks)
Supply of Utility Vehicles |  |  |  |  | 6 Weeks |  | 24/1/11-11/4/11 |  | Supply of Utility Vehicles | 11/4 - 12/4/11 | 1/3 -15/3/11 | 18/4/11-2/5/11 | 2011-07-05 | 16/5-23/5/11 | 23/5-6/6/11 |  | N/A | 6/6/11 - 20/6/11 |  | Supply of Utility Vehicles | 20/6-6/7/11 | N/A | 2011-01-08 | 1 Week | PM (Tech. Services) | AGM(M)
| “A” | LOT 6 |  | National Competitive Bidding | 2011-01-03 | PTB |  |  |  |  | (2 Wks)
Procurement of Tool Boxes for Maintenance Staff |  |  |  |  | 6 Weeks |  | 24/1/11-11/4/11 |  | Procurement of Tool Boxes for | 11/4 - 12/4/11 | 1/3 -15/3/11 | 18/4/11-2/5/11 | 2011-07-05 | 16/5-23/5/11 | 23/5-6/6/11 |  | N/A | 6/6/11 - 20/6/11 |  | Procurement of Tool Boxes for Maintenance Staff | 20/6-6/7/11 | N/A | 2011-01-08 | 1 Week | PM (Turbine) | AGM(M)
| “A” | LOT 7 |  | National Competitive Bidding | 2011-01-03 | PTB |  |  | Maintenance Staff |  | (2 Wks)
Procurement of Hospital Laboratory equipment |  |  |  |  | 6 Weeks |  | 24/1/11-11/4/11 |  | Procurement of Hospital Laboratory equipment | 11/4 - 12/4/11 | 1/3 -15/3/11 | 18/4/11-2/5/11 | 2011-07-05 | 16/5-23/5/11 | 23/5-6/6/11 |  | N/A | 6/6/11 - 20/6/11 |  | Procurement of Hospital Laboratory equipment | 20/6-6/7/11 | N/A | 2011-01-08 | 1 Week | PM (Medical) | AGM (O)
| “A” | LOT 8 |  | National Competitive Bidding | 2011-01-03 | PTB |  |  |  |  | (2 Wks)
Plumb Line Micrometer Portable Pressure Logger |  |  |  |  | 6 Weeks |  | 24/1/11-11/4/11 |  | Plumb Line Micrometer Portable Pressure Logger | 11/4 - 12/4/11 | 1/3 -15/3/11 | 18/4/11-2/5/11 | 2011-07-05 | 16/5-23/5/11 | 23/5-6/6/11 |  | N/A | 6/6/11 - 20/6/11 |  | Plumb Line Micrometer Portable Pressure Logger | 20/6-6/7/11 | N/A | 2011-01-08 | 1 Week | PM (Dam Inst.) | AGM (O)
| “A” | LOT 9 |  | National Competitive Bidding | 2011-01-03 | PTB |  |  |  |  | (2 Wks)
Hydraulic Piezometer Pressure Logger |  |  |  |  | 6 Weeks |  | 24/1/11-11/4/11 |  | Hydraulic Piezometer Pressure Logger | 11/4 - 12/4/11 | 1/3 -15/3/11 | 18/4/11-2/5/11 | 2011-07-05 | 16/5-23/5/11 | 23/5-6/6/11 |  | N/A | 6/6/11 - 20/6/11 |  | Hydraulic Piezometer Pressure Logger | 20/6-6/7/11 | N/A | 2011-01-08 | 1 Week | PM (Dam Inst.) | AGM (O)
| “A” | LOT 10 |  | National Competitive Bidding | 2011-01-03 | PTB |  |  |  |  | (2 Wks)
Vibarating Wire Piezometer Read Out Unit |  |  |  |  | 6 Weeks |  | 24/1/11-11/4/11 |  | Vibarating Wire Piezometer Read Out Unit | 11/4 - 12/4/11 | 1/3 -15/3/11 | 18/4/11-2/5/11 | 2011-07-05 | 16/5-23/5/11 | 23/5-6/6/11 |  | N/A | 6/6/11 - 20/6/11 |  | Vibarating Wire Piezometer Read Out Unit | 20/6-6/7/11 | N/A | 2011-01-08 | 1 Week | PM (Dam Inst.) | AGM (O)
| “A” | LOT 11 |  | National Competitive Bidding | 2011-01-03 | PTB |  |  |  |  | (2 Wks)
Total | [6 empty] | 24/1/11-11/4/11 |  | Total | [10 empty] | Total
GOODS
Desk Officer/Contact #: Abdul Aziz Ibrahim: (08054426191) Email: mairauta@yahoo.com | [7 empty] | Draft Bid Documents including |  | If with MDAs
|  |  | BASIC DATA |  |  |  |  | Spec and quantities, draft SPN |  | Spec. Proc. |  |  | Bidding Period |  | Bid Evaluation |  | Contract Finalization | [5 empty] | Contract Implementation
Project Description | Package | Lot | Lumpsum or Bill | Procurement | Budgetary | Pre-or Post | Approval | Prep & | MDAs' | Advert |  | Project Description | Bid Invitation | Bid Closing- | Submission | MDAs | Contract Amount | FEC Approval | Date of | Date | Mobilization | Project Description | Substantial | Final | Final | Action Party | Champion
| Number | Number | of Quantities | Method | Amount in | Qualification | Threshold | Submission | Approval | Notice |  |  | Date | Opening | Bid Eval Rept. | Approval | Certified in N |  | Contract | Contract | Advance |  | Completion | Acceptance | Cost
[5 empty] | Naira |  |  | by MDAs | [10 empty] | Offer | Signature | Payment
Norm Duration of Proc. Steps | [5 empty] | If Prequalification | [5 empty] | Norm Dureation of Proc. Steps | 2 - 6 Wks | 6 Wks | 2 - 3 Wks | 1 - 2 Wks |  | 2 - 4 Wks | 1 - 2 Wks | 1Wk |  | Norm Dureation of Proc. Steps |  | 6 Months
[6 empty] | add 2 wks | [5 empty] | List of Contracts | [9 empty] | List of Contracts
List of Contracts | [5 empty] | 6 Wks | [5 empty] | Supply of Unit 1G10 Complete Generator Stator Assembly Phase 1 | N/A | N/A | N/A | 1/6-30/6/11 | Budgetary Proposal by OEM being awaited | 1/6-30/6/11 | 4/7-24/8/11 | 24/8-31/8/11 | On Demand | Supply of Unit 1G10 Complete Generator Stator Assembly Phase 1 | 31/4/13 | 2013-01-11 | - | AGM(M) | CEO
Supply of Unit 1G10 Complete Generator Stator Assembly Phase 1 | N/A | N/A | BEME | DP(OEM) | 2320644454 | N/A | FEC |  | June, 2011 | OEM | [11 empty] | Total Cost
Total
Actual

## PHCN_Main_Plann_R&Stat
Ministry of Power: Department of Planning, Research & Statistics
Budgetary Year: 2011 --- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: Adebawo, M.A. - 08065333875 |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
SUPPLY OF HIGH SPEED COMPUTER COLOUR PRINTERS (10NOS). | 1 | 1A | 5600000 | OPEN | 2WKS
|  |  |  | TENDERING |  |  |  | 2WKS | 2WKS | 2 | 6 | 2WKS | 2WKS
date
SUPPLY OFAPPLE IPAD (15NOS.) | 1 | 1B | 6000000 | OPEN | 2WKS |  |  | 2WKS | 2WKS | 2 | 6 | 2WKS | 2WKS
TENDERING
SUPPLY OF BLACK BERY PHONES (15NOS) | 1 | 1C | 1800000 | DIRECT | 2WKS
|  |  |  | PURCHASE |  |  |  | 2WKS | 2WKS | 2 | 5 | 2WKS | 2WKS
SUPPLY OF LAPTOP COMPUTERS (10NOS.) | 1 | 1D | 2100000 | DIRECT
PURCHASE
SUPPLY OF DESKTOP COMPUTERS (20NOS) | 1 | 1E | 5120000 | OPEN
|  |  |  | TENDERING |  |  |  | 2WKS | 2WKS | 2 | 5 | 2WKS | 2WKS
PROCUREMENT OF SYSTEMS/UTILITY SOFTWARES | 1 | LOT | 3180000 | DIRECT
|  |  |  | PURCHASE |  |  |  | 2WKS | 2WKS | 2 | 5 | 2WKS | 2WKS
Total Cost |  |  | 23800000
Ministryof Power: Department of Planning, Research & Statistics (IT INFRASTRUCTURE, NETWORKING AND SOFTWARE DEVELOPMENT)
Budgetary Year: 2011 --- Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: Adebawo, A.M. - 08065333875 |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 3 wks
add 2 wks
List of Contracts
PERFORMANCE MIS NEEDS ASSESSMENT AND REQUIREMENT DEFINITION OF THE MINISTRY TO CATER FOR ANNUAL IMPROVEMENT | 2 | 2A |  | SELECTIVE | 3800000 | 2WKS |  |  |  |  | 2 | 4
TENDERING
LOCAL/WIDE AREA NETWORK (LAN/WAN) | 2 | 2B |  | SELECTIVE | 20000000 | 2WKS |  |  |  |  | 2 | 4
TENDERING
E-LEARNING/ON-LINE DATABASE | 2 | 2C |  | SELECTIVE | 15000000 | 2WKS |  |  |  |  | 2 | 4
TENDERING
WEBSITE DEVELOPMENT/CONTENT MANAGEMENT | 2 | 2D |  | SELECTIVE | 5400000 | 2WKS |  |  |  |  | 2 | 4
TENDERING
Total Cost |  |  |  |  | 44200000
Fill gray cells only!

## PHCN_PH
2011 PROCUREMENT PLAN FOR GOODS
MINISTRY/DEPARTMENT/AGENCY: PORT HARCOURT ELECTRICITY DISTRIBUTION COMPANY
BUDGETARY YEAR: 2011
DESK OFFICER/CONTACT: PM Procurement |  | BASIC DATA |  |  |  |  | Draft Bid Documents including Specs and Quantities, Draft SPN |  | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
PROJECT DESCRIPTION | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Threshold | Prep & Submission by MDAs | MTB Approval | Advertisement for Pre-qualification | Bid Invitation Date | Bid Closing/ Opening | Submission Bid Eval. Rpt | MTB Approval/BPP "No Objection" | Certifiable Amount Per Contract | MTB Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection/Final Acceptance | Action Party | Champion
Normal Duration of Proc Steps
List of Contracts
Procurement of High Voltage Underground Cables | Lot C 1 | Lot C1-1 | 17584593 | NCB | YES | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | N/A | 16/04/11 -15/06/11 | 16/06/11 - 30/06/11 | Mgr. Stores | AGM TS
Procurement of Low Voltage Underground Cables | Lot C1 | Lot C1-2 | 23010407 | NCB | YES | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | N/A | 16/04/11 -15/06/11 | 16/06/11 - 30/06/11 | Mgr. Stores | AGM TS
Procurement of Termination Kits | Lot C1 | Lot C1-3 | 9405000 | NCB | YES | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | N/A | 16/04/11 -15/06/11 | 16/06/11 - 30/06/11 | Mgr. Stores | AGM TS
Procurement of Walkie Talkie and Other Communication Equipment | Lot C5 | Lot C5 | 5000000 | NCB | YES | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | N/A | 16/04/11 -15/06/11 | 16/06/11 - 30/06/11 | Mgr. Stores | AGM TS
Procurement of 5No 33KV Control Panels | Lot C6 | Lot C6-1 | 18150000 | NCB | YES | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | N/A | 16/04/11 -15/06/11 | 16/06/11 - 30/06/11 | Mgr. Stores | AGM TS
Procurement of 2No 33KV Outdoor SF6 Breaker | Lot C6 | Lot C6-2 | 7850000 | NCB | YES | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | N/A | 16/04/11 -15/06/11 | 16/06/11 - 30/06/11 | Mgr. Stores | AGM TS
Procurement of Servers,Workstations and Printers | Lot C7 | Lot C7 | 2000000 | National Shopping | YES | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | N/A | 16/04/11 -15/06/11 | 16/06/11 - 30/06/11 | Mgr. Stores | AGM CS
Procurement of Test Equipment ( Earth Resistance Tester, Insulation, Oil Tester and Clip-on Ammeter | Lot C8 | Lot C8 | 5000000 | NCB | YES | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | N/A | 16/04/11 -15/06/11 | 16/06/11 - 30/06/11 | Mgr. Stores | AGM TS
Procurement of 30No HT and 20No LT Fibre Glass Ladders | Lot C9 | Lot C9 | 10000000 | NCB | YES | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | N/A | 16/04/11 -15/06/11 | 16/06/11 - 30/06/11 | Mgr. Stores | AGM TS
Procurement of 110V DC Tripping Unit and heavy duty batteries | Lot C11 | Lot C11 | 8000000 | NCB | YES | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | N/A | 16/04/11 -15/06/11 | 16/06/11 - 30/06/11 | Mgr. Stores | AGM TS
Procurement of Drums Transformer Oil | Lot C13 | Lot C13-1 | 10500000 | NCB | YES | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | N/A | 16/04/11 -15/06/11 | 16/06/11 - 30/06/11 | Mgr. Stores | AGM TS
Total |  |  | 116500000
2011 PROCUREMENT PLAN FOR WORKS
MINISTRY/DEPARTMENT/AGENCY: PORT HARCOURT ELECTRICITY DISTRIBUTION COMPANY
BUDGETARY YEAR: 2011
DESK OFFICER/CONTACT: PM Procurement |  | BASIC DATA | [5 empty] | Draft Bid Documents including Specs and Quantities, Draft SPN |  | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
PROJECT DESCRIPTION | Package Number | Lot Number | Lump Sum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Post or Pre-qualification | Approval Threshold | Prep & Submission by MDAs | MTB Approval | Advertisement for Pre-qualification | Bid Invitation Date | Bid Closing /Opening | Submission Bid Eval. Rpt | MTB Approval/BPP "No Objection" | Certifiable Amount Per Contract | MTB Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Normal Duration of Proc Steps
List of Contracts
Supply of Overhead Materials and Construction of 5Km of 33KV Line to extend Ndoki/Asa 33KV Line from Kom-Kom to Umuebulle to Link Airport 33KV Feeder | Lot C2 | Lot C2-1 | Bill of Quantities | NCB | 13700000 | Pre-Qualification | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | On Demand | 16/04/11 - 18/07/11 | 19/07/11 - 20/12/11 |  | PM P & C | AGM TS
Supply of Overhead and Underground materials and Construction of proposed Njamenze Street 11KV feeder Ex proposed Silver Bird 1x15MVA,33/11KV Injection Substation | Lot C2 | Lot C2-2 | Bill of Quantities | NCB | 6300000 | Pre-Qualification | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | On Demand | 16/04/11 - 18/07/11 | 19/07/11 - 20/12/11 |  | PM P & C | AGM TS
Completion of Agip-Okporo 1x15MVA, 33/11KV Injection Substation, Port Harcourt | Lot C3 | Lot C3 | Bill of Quantities | NCB | 31856100 | Pre-Qualification | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | On Demand | 16/04/11 - 18/07/11 | 19/07/11 - 20/12/11 |  | PM P & C | AGM TS
Construction of 33KV Feeder and Completion of Silver Bird 1x15MVA, 33/11KV Injection Substation, Port Harcourt | Lot C4 | Lot C4 | Bill of Quantities | NCB | 103143900 | Pre-Qualification | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | On Demand | 16/04/11 - 18/07/11 | 19/07/11 - 20/12/11 |  | PM P & C | AGM TS
Route Sequencing GIS-Customer Management for Borokiri Business Unit | Lot C10 | Lot C10-1 | Lump Sum | NCB | 8435649.98 | Pre-Qualification | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | On Demand | 16/04/11 - 18/07/11 | 19/07/11 - 20/12/11 |  | PM Marketing | AGM CS
Procurement and Installation of Prepayment Meters in Port Harcourt, Rivers State | Lot C10 | Lot C10-2 | Bill of Quantities | NCB | 36564350.02 | Pre-Qualification | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | On Demand | 16/04/11 - 18/07/11 | 19/07/11 - 20/12/11 |  | PM Marketing | AGM CS
Procurement of 1No 15MVA, 33/11KV Transformer to replace faulty Power Transformer in Port Harcourt Electricity Distribution Company | Lot C12 | Lot C12-1 | Bill of Quantities | NCB | 49700000 | Pre-Qualification | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | On Demand | 16/04/11 - 18/07/11 | 19/07/11 - 20/12/11 |  | PM P & C | AGM TS
Procurement of Distribution Transformers to replace faulty ones in Cross River, Akwa Ibom, Rivers and Bayelsa State | Lot C12 | Lot C12-2 | Bill of Quantities | NCB | 44300000 | Pre-Qualification | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | On Demand | 16/04/11 - 18/07/11 | 19/07/11 - 20/12/11 |  | PM P & C | AGM TS
Rehabilitation of Golden Liliy Injection Substation Building/Switchyard | Lot C13 | Lot C13-2 | Bill of Quantities | NCB | 10338500 | Pre-Qualification | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | On Demand | 16/04/11 - 18/07/11 | 19/07/11 - 20/12/11 |  | PM P & C | AGM TS
Rehabilitation of Trans-Amadi Injection Substation Building/Switchyard | Lot C13 | Lot C13-3 | Bill of Quantities | NCB | 10338500 | Pre-Qualification | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | On Demand | 16/04/11 - 18/07/11 | 19/07/11 - 20/12/11 |  | PM P & C | AGM TS
Supply and rehabilitation of faulty 15MVA Transformer at Port Harcourt Disco and Re-installation at school of Nursing Injection Substation. | Lot C13 | Lot C13-4 | Bill of Quantities | NCB | 8823000 | Pre-Qualification | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | On Demand | 16/04/11 - 18/07/11 | 19/07/11 - 20/12/11 |  | PM P & C | AGM TS
Trace Clearing of Afam Town (Ndoki) 33KV Feeder | Lot C14 | Lot C14-1 | Lump Sum | National Shopping | 1047375 | Pre-Qualification | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | On Demand | 16/04/11 - 18/07/11 | 19/07/11 - 20/12/11 |  | PM P & C | AGM TS
Trace Clearing of Isiokpo 33KV Feeder | Lot C14 | Lot C14-2 | Lump Sum | National Shopping | 3020125 | Pre-Qualification | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | On Demand | 16/04/11 - 18/07/11 | 19/07/11 - 20/12/11 |  | PM P & C | AGM TS
Trace Clearing of Ahoada 33KV Feeder | Lot C14 | Lot C14-3 | Lump Sum | National Shopping | 1627500 | Pre-Qualification | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | On Demand | 16/04/11 - 18/07/11 | 19/07/11 - 20/12/11 |  | PM P & C | AGM TS
Trace Clearing of Mbo 33KV Feeder | Lot C14 | Lot C14-4 | Lump Sum | National Shopping | 3780000 | Pre-Qualification | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | On Demand | 16/04/11 - 18/07/11 | 19/07/11 - 20/12/11 |  | PM P & C | AGM TS
Trace Clearing of Onna 33KV Feeder | Lot C14 | Lot C14-5 | Lump Sum | National Shopping | 4725000 | Pre-Qualification | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | On Demand | 16/04/11 - 18/07/11 | 19/07/11 - 20/12/11 |  | PM P & C | AGM TS
Trace Clearing of Abakaliki-Ugep-Ikom 33KV Feeder | Lot C14 | Lot C14-6 | Lump Sum | NCB | 7400000 | Pre-Qualification | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | On Demand | 16/04/11 - 18/07/11 | 19/07/11 - 20/12/11 |  | PM P & C | AGM TS
Trace Clearing of Yahe-Ogoja 33KV Feeder | Lot C14 | Lot C14-7 | Lump Sum | NCB | 8400000 | Pre-Qualification | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | On Demand | 16/04/11 - 18/07/11 | 19/07/11 - 20/12/11 |  | PM P & C | AGM TS
Rehabilitation of Old Airport 33KV Feeder | Lot C15 | Lot C15-1 | Bill of Quantities | NCB | 30000000 | Pre-Qualification | CEO | 10/01/11 - 17/01/11 | 18/01/11 | 20/01/11 - 03/02/11 | 07/02/11 - 07/03/11 | 2011-07-03 | 08/03/11 - 22/03/11 | 23/03/11 - 30/03/11 |  | 31/03/11 - 07/04/11 | 08/04/11 - 15/04/11 | 08/04/11 - 15/04/11 | On Demand | 16/04/11 - 18/07/11 | 19/07/11 - 20/12/11 |  | PM P & C | AGM TS
Total |  |  |  |  | 383500000

## PHCN_Yola
Ministry/Department/Agency: PHCN Plc, Yola Zone
Budgetary Year: 2010 --- On-going project | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot No. | Estimated Amount in Naira | Prcmnt Mthd | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advert. for Pre- Qualification | Bid Invitation Date | Bid Closing- Opening | Submission Bid Eval Rpt | MDA Approval/ BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
ON-GOING PROJECTS
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
add 2 wks
List of Contracts
Design and commencement of constructing of standard Company Stores at the proposed site |  | 6 | 65000000 | Int. Bidding | 2 weeks | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Completion of 1x7.5MVA, 33/11KV Injection Substation at Cross Kanwa in Borno State |  | 2A5 | 70000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
1x7.5MVA, 33/11kv Abuja road,Damare inj. s/s Yola Town |  | S | 85000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
2x7.5MVA, 33/11KV Gashua Town |  | T | 270000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Wuro Gayadi, Kuda, Koe, Kaya Fada, Bitiki, Yinagu in Adamawa State |  | 2E1 | 25000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Wuro Ngiki, Watsala, Hubishi, Kali Utham, Mampe, Thuku, Zah in Adamawa State |  | 2E2 | 25000000 |  |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Muvur, Batande and Didif in Adamawa State |  | 2E3 | 25000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Dubudubu, Wodili and Mbuluman in Adamawa State |  | 2E4 | 20000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Maiha Gari, Wuro Iya, Wuro Alhaji, Wuro Boka, Wuro Ladde in Adamawa State |  | 2E5 | 25000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Yusufari ITC/TDN, Yusufari LGA (On-going) Yobe State |  | 2F4 | 10000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Substation Level at Daraburin, Busari LGA (On-going) Yobe State |  | 2F6 | 10000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Teteba, Dukshi in Gulani LGA (On-going) Yobe State |  | 2F1 | 20000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Kelluri, Mallammti, Balle in Geidam LGA (On-going) Yobe State |  | 2G1 | 20000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Bulafara, Gulani, Nilbuluwa TDN, Nibuluwa ITC/2-1MVAss in Gulani LGA (On-going) Yobe State |  | 2F2 | 20000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Beluri, Dammawa in Busari LGA (On-going) Yobe State |  | 2G2 | 20000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  |  | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Mr. JFA Kalam ITC/TDN in Damaturu (On-going) Yobe State |  | 2F3 | 20000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Electrification of Mayo Ranewo, Tau in Taraba State |  | 2D5 | 27000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Boshikiri to Zakawon, Guyuk LGA (On-going) in Adamawa State |  | 2C1 | 12000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Taraba On-going Electrification: Muri N4M, Zailani N4M |  | 2D3 | 8000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  |  | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Provision of Electricity in Malunity, Lawanti, Danani, Gumsa |  | 2G3 | 138320000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Electrification project (On-going) at Kukargadu, Daya, Chana and Siminti of Fika/Fune Fed. Constituency, Yobe State |  | 2G4 | 32259232 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Electrification of Godowoli, Gashinge and Gamari |  | 2G5 | 65268185 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Electrification of Tello, Marmari, Bindigi and Borno Kichi |  | 2G6 | 40792603 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Completion of Gasarwa-Sugum Electrification in Bade LGA. |  | 2F5 | 68582062 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Completion of Gololo-Jakusko Electrification in Akusko LGA |  | 2G7 | 43152757 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  |  | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Construction of 4.5 33KV line and installation of 1x7.5MVA, 33/11KV Injection Substation at Ngumeri Ward in Maiduguri, Borno State |  | 2A1 | 140000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Extension of Electricity to Kauji Talala, Kautikari, Mboa, Dure Barawa and Umankara in Gwoza LGA in Borno State |  | 2A2 | 200000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Extension of Electricity to Jido Damaiya, Ajiri Gamsa, Juluri and Damnawa in Busari LGA Yobe State |  | 2G8 | 40000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Extension of Electricity to Kucikuokiri, Lawan and Gumsa in Gaidam LGA Yobe State |  | 2G9 | 30000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Extension of Electricity in Mararaba - Sabon Gida Tukura - Didan - Baisa - Gwanda to National Grid in Taraba State |  | 2D4 | 70000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Completion of Electrification projects at Askira/Uba & Hawul, Borno State |  | 2B2 | 50000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Completion of Electrification projects at Ga'anda, Gabun |  | 2E6 | 120000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Electrification of Lumbu, Butu, Taraba |  | K | 142000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Electrification of Jangtu, Kwabai (LGA), Taraba |  | L | 179000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Electrification of Banki, Borno State |  | M | 145000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Electrification of Mutum biyu and sunkari (LGA), Taraba |  | N | 200000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Electrification of fikyu and jenuwa kogi, Taraba |  | O | 145000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Electrification of Gundun bali (2.5MVA) in Borno state |  | P | 100000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Electrification of Gamboro Ngala Borno state |  | Q | 225000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Electrification of Dikur Borno state |  | R | 189999999 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[6 empty] | a | 7/2/11-28/2/11 | 28/2/11-7/3/11
Total Cost(=N=) |  |  | 3141374838
Ministry/Department/Agency: PHCN Plc, Yola Zone
Budgetary Year: 2011 --- New Projects | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot No. | Estimated Amount in Naira | Prcmnt Mthd | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advert. for Pre- Qualification | Bid Invitation Date | Bid Closing- Opening | Submission Bid Eval Rpt | MDA Approval/ BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
add 2 wks
List of Contracts
Line reinforcement/replacement of all broken Cross Arms, Weak jumpers etc (Rehabilitation of Overhead HT & LT lines) |  | A1 |  | Int. Bidding | 2 weeks | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
|  |  | 19890000 |  |  |  | 7/2/11-28/2/11 | 28/2/11-7/3/11
Rehabilitation of Distribution Transformers/ Substations |  | A2 | 23800000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Trace Clearing for 11KV and 33KV O/H lines |  | A3 | 45000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Tower Crossing Along River Benue of 33kv feeder at Jimeta |  | A4 | 200000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Rehabilitation of jabbi lamba to Song 33kv line |  | A5 | 95000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Rehabilitation of Gombi to Mararaba junction, Mubi |  | A6 | 25000000 |  |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Rehabiltation of Fika 33kv feeder from Potiskum |  | A7 | 25000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Rehabiltation of Lamurde & Guyuk 33kv lines from Savanah TS |  | A8 | 30000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Rehabilitation of Shani 33kv Line from Biu TS |  | A9 | 30000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Rehabilitation of Zing 33kv line from Jalingo TS |  | A10 | 15000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Reconstruction of geidam 33kv feeder from Potiskum using mini tower |  | A11 | 375000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Rehabilitation of Bama & Mongono 33kv lines from Maiduguri |  | A12 | 100000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Rehabilitation of Benisheik 33kv line from Maiduguri |  | A13 | 45000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Replacement of obsolete 33KV outdoor breaker 6No. |  | B | 27000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Reconductoring of HT & LT Netowrks in Yola zone |  | C | 150000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  |  | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Procurement and installation of 50No. 300KVA &50No. 500KVA Transformers |  | D | 310000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Conversion of Zing Town raticulations from 33/0.415kv to 11/0.415kv voltage ratio. |  | E1 | 40000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
2x7.5MVA 33/11kv kasuwar wake, inj. s/s Maiduguri |  | E2 | 200000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
1x7.5MVA, 33/11KV Mayo-Belwa Injection Substation |  | E3 | 150000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  |  | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Conversion of Jada Town raticulations from 33/0.415kv to 11/0.415kv voltage ratio. |  | E4 | 40000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Construction of 11KV and 33KV O/H line associated with Injection S/S. |  | F1 | 100000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Electrification of malam fatori (2.5MVA) in Borno state |  | F2 | 160000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Construction of Magumeri 33KV feeder |  | F3 | 200000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Construction of 20km of 33kv line from Savanah TS to Numan Town. |  | F4 | 85000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Supply Heavy equipment Vehicles, Cranes ETC. |  | G | 50000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  |  | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Procurement of 3.8km of HT and 779m of LT cables & 125 Terminating and Jointing Kts for Network expansion (U/G. HT and LT cables) |  | H1 | 31705850 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Provision of 30No. 800A, 4-Way Feeder Pillars and 1 set of complete Ring Main Unit and extension |  | H2 | 8438181 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
provision of Additional distribution materials for maintenance |  | H3 | 100000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Procurement of cables |  | H4 | 120000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Supply of 7board panel for Numan Road inj. s/s |  | H5 | 30000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Supply of 7board panel for baga road inj. s/s, Maiduguri |  | H6 | 30000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Supply of 7board panel for Jalingo inj. s/s, (2x7.5MVA) |  | H7 | 30000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Supply of 7board panel for FUTY inj. s/s, Yola |  | H8 | 30000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Supply of 7board panel for nguru inj. s/s, |  | H9 | 30000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Supply of 7board panel for mubi inj. s/s, Mubi |  | H10 | 30000000 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Tripping unit spares |  | H11 | 9999999 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Procurement of VHF Base Radios and Walkie Talkie and other Communication Equipment and systems |  | I1 | 6485391 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Provision for Test equipment |  |  | 20753752 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Provision of mechanical and electrical tool boxes and Safety wears |  |  | 29363636 | " |  | PTB | 7/2/11-28/2/11 | 28/2/11-7/3/11 | 7/3/2011-21/3/11 | 11/4/1-2/5/11 | 2/5/2011 | 2/5/2011 -23/5/11 | 23/5/2011 -6/6/11 |  | NA | 20/6/2011 | 20/6/2011-27/6/11 | On Request | 27/9/2011 | 11/10/2011 | Engr. B. A. Dogo | Engr. M. S. Roro
[7 empty] | 7/2/11-28/2/11 | 28/2/11-7/3/11
Total Cost(=N=) |  |  | 3047436809

## PHCN_Enugu
ENUGU ELECTRICITY DISTRIBUTION COMPANY
Budgetary Year: 2010 --- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Engr. J. C. OKEKE/08033964039 |  | Basic Data | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection/final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
add 2 wks
List of Contracts
CABLES AND KITS FOR NETWORK EXPANSION (UNDERGROUND HT AND LT CABLES) | N/A | EEDC 2.2.1 | 33633516.88 | NCB |  | PTB | Jan 4th - Jan 17th | Jan 18th - Jan 31st | Feb 1st - Mar 8th | Mar 9th - Apr 5th | Mar 9th - Apr 5th | Apr 6th - Apr 19th | N/A | N/A | N/A | Apr 20th - May 4th | May 5th - May 18th | May 19th - Jun 1st | Jun 2nd - Aug 31st | Sept 1st - Sept 30th
[7 empty] | Jan 4th - Feb 1st | Feb 2nd - Feb 28th | Mar 1st - Mar 22nd | Mar 23rd - May 4th | Mar 23rd - May 4th | May 5th - Jun 1st | N/A | N/A | N/A | Jun 2nd - Jun 30th | Jul 1st - Jul 29th | Aug 1st - Aug 29th | Sep 1st - Nov 3oth | Dec 1st - Dec 30th
FEEDER PILLARS AND RMUs |  | EEDC 2.3.1 | 16340691.25 | NCB |  | PTB | Jan 4th - Jan 17th | Jan 18th - Jan 31st | Feb 1st - Mar 8th | Mar 9th - Apr 5th | Mar 9th - Apr 5th | Apr 6th - Apr 19th | N/A | N/A | N/A | Apr 20th - May 4th | May 5th - May 18th | May 19th - Jun 1st | Jun 2nd - Aug 31st | Sept 1st - Sept 30th
[7 empty] | Jan 4th - Feb 1st | Feb 2nd - Feb 28th | Mar 1st - Mar 22nd | Mar 23rd - May 4th | Mar 23rd - May 4th | May 5th - Jun 1st | N/A | N/A | N/A | Jun 2nd - Jun 30th | Jul 1st - Jul 29th | Aug 1st - Aug 29th | Sep 1st - Nov 3oth | Dec 1st - Dec 30th
PROVISION OF TEST EQUIPMENT |  | EEDC 2.5.1 | 23338563.75 | NCB |  | PTB | Jan 4th - Jan 17th | Jan 18th - Jan 31st | Feb 1st - Mar 8th | Mar 9th - Apr 5th | Mar 9th - Apr 5th | Apr 6th - Apr 19th | N/A | N/A | N/A | Apr 20th - May 4th | May 5th - May 18th | May 19th - Jun 1st | Jun 2nd - Aug 31st | Sept 1st - Sept 30th
[7 empty] | Jan 4th - Feb 1st | Feb 2nd - Feb 28th | Mar 1st - Mar 22nd | Mar 23rd - May 4th | Mar 23rd - May 4th | May 5th - Jun 1st | N/A | N/A | N/A | Jun 2nd - Jun 30th | Jul 1st - Jul 29th | Aug 1st - Aug 29th | Sep 1st - Nov 3oth | Dec 1st - Dec 30th
HEAVY EQUIPMENT VEHICLES, CRANES ETC. |  | EEDC 2.7.1 | 25168325.63 | NCB |  | PTB | Jan 4th - Jan 17th | Jan 18th - Jan 31st | Feb 1st - Mar 8th | Mar 9th - Apr 5th | Mar 9th - Apr 5th | Apr 6th - Apr 19th | N/A | N/A | N/A | Apr 20th - May 4th | May 5th - May 18th | May 19th - Jun 1st | Jun 2nd - Aug 31st | Sept 1st - Sept 30th
[7 empty] | Jan 4th - Feb 1st | Feb 2nd - Feb 28th | Mar 1st - Mar 22nd | Mar 23rd - May 4th | Mar 23rd - May 4th | May 5th - Jun 1st | N/A | N/A | N/A | Jun 2nd - Jun 30th | Jul 1st - Jul 29th | Aug 1st - Aug 29th | Sep 1st - Nov 3oth | Dec 1st - Dec 30th
REPLACEMENT OF OBSOLETE SWITCHGEAR; MAXIMUM DEMAND (MD) METERING INFRASTRUCTURES |  | EEDC 3.2.1 | 19298014.38 | NCB |  | PTB | Jan 4th - Jan 17th | Jan 18th - Jan 31st | Feb 1st - Mar 8th | Mar 9th - Apr 5th | Mar 9th - Apr 5th | Apr 6th - Apr 19th | N/A | N/A | N/A | Apr 20th - May 4th | May 5th - May 18th | May 19th - Jun 1st | Jun 2nd - Aug 31st | Sept 1st - Sept 30th
[7 empty] | Jan 4th - Feb 1st | Feb 2nd - Feb 28th | Mar 1st - Mar 22nd | Mar 23rd - May 4th | Mar 23rd - May 4th | May 5th - Jun 1st | N/A | N/A | N/A | Jun 2nd - Jun 30th | Jul 1st - Jul 29th | Aug 1st - Aug 29th | Sep 1st - Nov 3oth | Dec 1st - Dec 30th
REHABILITATION OF DISTRIBUTION TRANSFORMERS/SUBSTATIONS |  | EEDC 3.1.1 | 41859070 | NCB |  | PTB | Jan 4th - Jan 17th | Jan 18th - Jan 31st | Feb 1st - Mar 8th | Mar 9th - Apr 5th | Mar 9th - Apr 5th | Apr 6th - Apr 19th | N/A | N/A | N/A | Apr 20th - May 4th | May 5th - May 18th | May 19th - Jun 1st | Jun 2nd - Aug 31st | Sept 1st - Sept 30th
[7 empty] | Jan 4th - Feb 1st | Feb 2nd - Feb 28th | Mar 1st - Mar 22nd | Mar 23rd - May 4th | Mar 23rd - May 4th | May 5th - Jun 1st | N/A | N/A | N/A | Jun 2nd - Jun 30th | Jul 1st - Jul 29th | Aug 1st - Aug 29th | Sep 1st - Nov 3oth | Dec 1st - Dec 30th
UPGRADE OF INFRASTRUCTURES IN BILLING LOCATIONS (SERVERS, WORKSTATIONS, PRINTERS, WEB HOSTING INFRASTRUCTURE) |  | EEDC 2.4.1 | 22198973.13 | NCB |  | PTB | Jan 4th - Jan 17th | Jan 18th - Jan 31st | Feb 1st - Mar 8th | Mar 9th - Apr 5th | Mar 9th - Apr 5th | Apr 6th - Apr 19th | N/A | N/A | N/A | Apr 20th - May 4th | May 5th - May 18th | May 19th - Jun 1st | Jun 2nd - Aug 31st | Sept 1st - Sept 30th
|  |  | - |  |  |  | Jan 4th - Feb 1st | Feb 2nd - Feb 28th | Mar 1st - Mar 22nd | Mar 23rd - May 4th | Mar 23rd - May 4th | May 5th - Jun 1st | N/A | N/A | N/A | Jun 2nd - Jun 30th | Jul 1st - Jul 29th | Aug 1st - Aug 29th | Sep 1st - Nov 3oth | Dec 1st - Dec 30th
-
Total Cost |  |  | 181837155.02
Fill gray cells only!
ENUGU ELECTRICITY DISTRIBUTION COMPANY
Budgetary Year: 2010 --- Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Engr. J. C. OKEKE/08033964039 |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
add 2 wks
List of Contracts
11KV AND 33KV OVERHEAD LINE ASSOCIATED WITH INJECTION SUBSTATIONS | NA |  | EEDC 1.1.1 | NCB | 34872946.88 |  | PTB | Jan 4th - Jan 17th | Jan 18th - Jan 31st | Feb 1st - Mar 8th | Mar 9th - Apr 5th | Mar 9th - Apr 5th | Apr 6th - Apr 19th | N/A | N/A | N/A | Apr 20th - May 4th | May 5th - May 18th | May 19th - Jun 1st | Jun 2nd - Aug 31st | Sept 1st - Sept 30th
[8 empty] | Jan 4th - Feb 1st | Feb 2nd - Feb 28th | Mar 1st - Mar 22nd | Mar 23rd - May 4th | Mar 23rd - May 4th | May 5th - Jun 1st | N/A | N/A | N/A | Jun 2nd - Jun 30th | Jul 1st - Jul 29th | Aug 1st - Aug 29th | Sep 1st - Nov 3oth | Dec 1st - Dec 30th
11KV AND 33KV RECONDUCTORING | NA |  | EEDC 2.1.1 | NCB | 41483492.5 |  | PTB | Jan 4th - Jan 17th | Jan 18th - Jan 31st | Feb 1st - Mar 8th | Mar 9th - Apr 5th | Mar 9th - Apr 5th | Apr 6th - Apr 19th | N/A | N/A | N/A | Apr 20th - May 4th | May 5th - May 18th | May 19th - Jun 1st | Jun 2nd - Aug 31st | Sept 1st - Sept 30th
[8 empty] | Jan 4th - Feb 1st | Feb 2nd - Feb 28th | Mar 1st - Mar 22nd | Mar 23rd - May 4th | Mar 23rd - May 4th | May 5th - Jun 1st | N/A | N/A | N/A | Jun 2nd - Jun 30th | Jul 1st - Jul 29th | Aug 1st - Aug 29th | Sep 1st - Nov 30th | Dec 1st - Dec 30th
COMMUNICATION EQUIPMENT AND SYSTEMS | NA |  | EEDC 2.1.6 | NCB | 9432077.5 |  | PTB | Jan 4th - Jan 17th | Jan 18th - Jan 31st | Feb 1st - Mar 8th | Mar 9th - Apr 5th | Mar 9th - Apr 5th | Apr 6th - Apr 19th | N/A | N/A | N/A | Apr 20th - May 4th | May 5th - May 18th | May 19th - Jun 1st | Jun 2nd - Aug 31st | Sept 1st - Sept 30th
[8 empty] | Jan 4th - Feb 1st | Feb 2nd - Feb 28th | Mar 1st - Mar 22nd | Mar 23rd - May 4th | Mar 23rd - May 4th | May 5th - Jun 1st | N/A | N/A | N/A | Jun 2nd - Jun 30th | Jul 1st - Jul 29th | Aug 1st - Aug 29th | Sep 1st - Nov 3oth | Dec 1st - Dec 30th
TRACE CLEARING OF 11KV AND 33KV LINES | NA |  | EEDC 3.1.4 | NCB | 24016578.75 |  | PTB | Jan 4th - Jan 17th | Jan 18th - Jan 31st | Feb 1st - Mar 8th | Mar 9th - Apr 5th | Mar 9th - Apr 5th | Apr 6th - Apr 19th | N/A | N/A | N/A | Apr 20th - May 4th | May 5th - May 18th | May 19th - Jun 1st | Jun 2nd - Aug 31st | Sept 1st - Sept 30th
[8 empty] | Jan 4th - Feb 1st | Feb 2nd - Feb 28th | Mar 1st - Mar 22nd | Mar 23rd - May 4th | Mar 23rd - May 4th | May 5th - Jun 1st | N/A | N/A | N/A | Jun 2nd - Jun 30th | Jul 1st - Jul 29th | Aug 1st - Aug 29th | Sep 1st - Nov 3oth | Dec 1st - Dec 30th
[8 empty] | Jan 4th - Feb 1st | Feb 2nd - Feb 28th | Mar 1st - Mar 22nd | Mar 23rd - May 4th | Mar 23rd - May 4th | May 5th - Jun 1st | N/A | N/A | N/A | Jun 2nd - Jun 30th | Jul 1st - Jul 29th | Aug 1st - Aug 29th | Sep 1st - Nov 3oth | Dec 1st - Dec 30th
CONSTRUCTION OF STANDARD COMPANY STORES | NA |  | EEDC 3.1.5 | NCB | 12755868.75 |  | PTB | Jan 4th - Jan 17th | Jan 18th - Jan 31st | Feb 1st - Mar 8th | Mar 9th - Apr 5th | Mar 9th - Apr 5th | Apr 6th - Apr 19th | N/A | N/A | N/A | Apr 20th - May 4th | May 5th - May 18th | May 19th - Jun 1st | Jun 2nd - Aug 31st | Sept 1st - Sept 30th
[8 empty] | Jan 4th - Feb 1st | Feb 2nd - Feb 28th | Mar 1st - Mar 22nd | Mar 23rd - May 4th | Mar 23rd - May 4th | May 5th - Jun 1st | N/A | N/A | N/A | Jun 2nd - Jun 30th | Jul 1st - Jul 29th | Aug 1st - Aug 29th | Sep 1st - Nov 3oth | Dec 1st - Dec 30th
LINE REINFORCEMENT/ REPLACEMENT (REHABILITATION OF OVERHEAD HT AND LT LINES) | NA |  | EEDC 3.1.7 | NCB | 48785201.25 |  | PTB | Jan 4th - Jan 17th | Jan 18th - Jan 31st | Feb 1st - Mar 8th | Mar 9th - Apr 5th | Mar 9th - Apr 5th | Apr 6th - Apr 19th | N/A | N/A | N/A | Apr 20th - May 4th | May 5th - May 18th | May 19th - Jun 1st | Jun 2nd - Aug 31st | Sept 1st - Sept 30th
[5 empty] | - |  |  | Jan 4th - Feb 1st | Feb 2nd - Feb 28th | Mar 1st - Mar 22nd | Mar 23rd - May 4th | Mar 23rd - May 4th | May 5th - Jun 1st | N/A | N/A | N/A | Jun 2nd - Jun 30th | Jul 1st - Jul 29th | Aug 1st - Aug 29th | Sep 1st - Nov 3oth | Dec 1st - Dec 30th
DISTRIBUTION AUTOMATION/SCADA/ OMS |  |  |  |  | 24194359.38 |  | PTB | Jan 4th - Jan 17th | Jan 18th - Jan 31st | Feb 1st - Mar 8th | Mar 9th - Apr 5th | Mar 9th - Apr 5th | Apr 6th - Apr 19th | N/A | N/A | N/A | Apr 20th - May 4th | May 5th - May 18th | May 19th - Jun 1st | Jun 2nd - Aug 31st | Sept 1st - Sept 30th
[5 empty] | - |  |  | Jan 4th - Feb 1st | Feb 2nd - Feb 28th | Mar 1st - Mar 22nd | Mar 23rd - May 4th | Mar 23rd - May 4th | May 5th - Jun 1st | N/A | N/A | N/A | Jun 2nd - Jun 30th | Jul 1st - Jul 29th | Aug 1st - Aug 29th | Sep 1st - Nov 3oth | Dec 1st - Dec 30th
Total Cost |  |  |  |  | 195540525.01

## Mine&Steel_COMEG
Ministry/Department/Agency:Mine and Steel COMEG
Budgetary Year: 2011 --- Consultancy services | [6 empty] | Request for Expression of Interest (when required)
Busari/08023042658 |  | Contract Type |  |  | Preparation Request for Proposals |  |  |  | Short List |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [6 empty] | Contract Finalization |  |  | Contract Implementation
CONSULTANCY | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | No-objection Date | FEC Approval | Contract Amount in Naira | Contract Offer | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks |  | 1- 2 wk | 2 wks
List of Contracts
Assessment of Academic Standard in Tertiary Institutions in Nigeria | NCB | Lumpsum | 62500000 | COMEG Tender | 21/2 - 14/3/11 | 14/3 - 21/3/11 | 28/3 - 11/4/11 | 11/4 - 18/4/11 | 19/4/2011 | 2/5 - 16/5/11 | 16/5 - 30/5/11 | 6/6 - 4/7/11 | 6/7 - 20/7/11 | 21/7 - 4/8/11 | 5/8 - 19/8/11 | 20/8 - 3/9/11 | [5 empty] | 12/9 - 19/9/11 |  | 7/11/11 | 31/12/11 |  |  | Registrar
Board (CTB)
Professional Investigation | NCB | Lumpsum | 60000000 | COMEG Tender | 21/2 - 14/3/11 | 14/3 - 21/3/11 | 28/3 - 11/4/11 | 11/4 - 18/4/11 | 19/4/2011 | 2/5 - 16/5/11 | 16/5 - 30/5/11 | 6/6 - 4/7/11 | 6/7 - 20/7/11 | 21/7 - 4/8/11 | 5/8 - 19/8/11 | 20/8 - 3/9/11 | [5 empty] | 12/9 - 19/9/11 |  | 7/11/11 | 31/12/11 |  |  | Registrar
Board (CTB)
Establishment of Data Bank for Professionals | NCB | Lumpsum | 20000000 | COMEG Tender | 21/2 - 14/3/11 | 14/3 - 21/3/11 | 28/3 - 11/4/11 | 11/4 - 18/4/11 | 19/4/2011 | 2/5 - 16/5/11 | 16/5 - 30/5/11 | 6/6 - 4/7/11 | 6/7 - 20/7/11 | 21/7 - 4/8/11 | 5/8 - 19/8/11 | 20/8 - 3/9/11 | [5 empty] | 12/9 - 19/9/11 |  | 7/11/11 | 31/12/11 |  |  | Registrar
Board (CTB)
Monitoring and Evaluation of Professionals and Corporate Bodies | NCB | Lumpsum | 20000000 | COMEG Tender | 21/2 - 14/3/11 | 14/3 - 21/3/11 | 28/3 - 11/4/11 | 11/4 - 18/4/11 | 19/4/2011 | 2/5 - 16/5/11 | 16/5 - 30/5/11 | 6/6 - 4/7/11 | 6/7 - 20/7/11 | 21/7 - 4/8/11 | 5/8 - 19/8/11 | 20/8 - 3/9/11 | [5 empty] | 12/9 - 19/9/11 |  | 7/11/11 | 31/12/11 |  |  | Registrar
Board (CTB)
Total Cost |  |  | 162500000
Ministry/Department/Agency: COMEG
Budgetary Year: 2011 --- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Busari/08023042658 |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
GOODS | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing/ Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection/ Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 4 -6 wks |  | 2 wks | 2 - 4 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
add 2 wks
List of Contracts
Purchase of office equipment and computers for the Head office and zonal offices. |  |  |  | NCB |  | COMEG Tender | 21/2 - 14/3/2011 | 21/2 - 14/3/2012 |  | 2/5 - 13/6/2011 | 2/5 - 13/6/2012 | 2/5 - 13/6/2013 | 2/5 - 13/6/2014 |  |  | 29/8/2011 | 29/8/2012 |  | 2011-03-10 | 7/11 - 21/11/11 | Procurement Officer | Registrar
|  | LOT 01 | 12000000 |  |  | Board (CTB)
Establishment of specialised libraries and IT centres |  | LOT 02 | 40000000 | NCB |  | COMEG Tender | 21/2 - 14/3/2011 | 21/2 - 14/3/2012 |  | 2/5 - 13/6/2011 | 2/5 - 13/6/2012 | 2/5 - 13/6/2013 | 2/5 - 13/6/2014 |  |  | 29/8/2011 | 29/8/2012 |  | 2011-03-10 | 7/11 - 21/11/11 | Procurement Officer | Registrar
Board (CTB)
Total Cost |  |  | 52000000
Note on K28: BPP:

## Mine&Steel_Main
Ministry of Mines & Steel Development HQ
Budgetary Year: 2011 --- Consultancy Service | [7 empty] | Request for Expression of Interest (when required)
Busari/08023042658 |  | Contract Type |  |  | Preparation Request for Proposals |  |  |  | Short List |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [6 empty] | Contract Finalization |  |  | Contract Implementation
Consultancy | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | No-objection Date | FEC Approval | Contract Amount in Naira | Contract Offer | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion
Normal Duration of Procurement Steps |  |  |  |  | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks | 2 - 4 wks | 1 - 2 wks | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks |  | 1- 2 wk | 2 wks | 2 - 3 wks
List of Contracts
Procurement of Consultancy Services | QCB | Time Based | 57037450 | MTB | 14-28/01/11 | 1-15/02/11 | 2-16/02/11 | 16-23/02/11 | 28/2/11-21/3/11 | 29/03/11-4/4/11 | 11-22/04/11 | 25/04/11-23/05/11 | 24/05/11-7/06/11 | 13-24/06/11 | 27/06/11-11/07/11 | 18-29/07/11 | 1- 12/08/11 | 15-19/08/11 | NA | 57037450 | 22-26/08/11 | 29/08/11-2/09/11 | 5-16/09/11 | NA | 19-23/09/11 | NA | Bello M. T | Busari K. O. I
Security & Inspection of illegal miners | QCB | Time Based | 50000000 | MTB | 14-28/01/11 | 1-15/02/11 | 2-16/02/11 | 16-23/02/11 | 28/2/11-21/3/11 | 29/03/11-4/4/11 | 11-22/04/11 | 25/04/11-23/05/11 | 24/05/11-7/06/11 | 13-24/06/11 | 27/06/11-11/07/11 | 18-29/07/11 | 1-12/08/11 | 15-19/08/11 | NA | 50000000 | 22-26/08/11 | 29/08/11-2/9/11 | 5-16/09/11 | NA | 19-23/09/11 | NA | Uba Muktar | Busari K. O. I
International Exhibition of Nigerian Minerals | QCB | Time Based | 20000000 | MTB | 14-28/01/11 | 1-15/02/11 | 2-16/02/11 | 16-23/02/11 | 28/2/11-21/3/11 | 29/03/11-4/4/11 | 11-22/04/11 | 25/04/11-23/05/11 | 24/05/11-7/06/11 | 13-24/06/11 | 27/06/11-11/07/11 | 18-29/07/11 | 1-12/08/11 | 15-19/08/11 | NA | 20000000 | 22-26/08/11 | 29/08/11-2/9/11 | 5-16/09/11 | NA | 19-23/09/11 | NA | Musa Garba | busari K. O. I
Exterblishment of Extention Services to Artisanal & Small Scale Miners | QCB | Time Based | 50000000 | MTB | 14-28/01/11 | 1-15/02/11 | 2-16/02/11 | 16-23/02/11 | 28/2/11-21/3/11 | 29/03/11-4/4/11 | 11-22/04/11 | 25/4/11-23/5/11 | 24/5/11-7/6/11 | 13-24/6/11 | 27/6/11-11/7/11 | 18-29/7/11 | 1-12/8/11 | 15-19/8/11 | NA | 50000000 | 22-26/8/11 | 29/8/11-2/9/11 | 5-16/9/11 | NA | 19-23/9/11 | NA | Akporno Joyce | Busari. K. O. I
Publication and Publicity | QCB | Time Based | 15000000 | MTB | 14-28/01/11 | 1-15/02/11 | 2-16/02/11 | 16-23/02/11 | 28/2/11-21/3/11 | 29/03/11-4/4/11 | 11-22/04/11 | 25/04/11-23/05/11 | 24/05/11-7/06/11 | 13-24/06/11 | 27/06/11-11/07/11 | 18-29/07/11 | 1-12/08/11 | 15-19/08/11 | NA | 15000000 | 22-26/08/11 | 29/08/11-2/09/11 | 5-16/09/11 | NA | 19-23/09/11 | NA | Uba Muktar | Busari K. O. I.
Education and Stakeholders Outreach | QCB | Time Based | 10000000 | MTB | 14-28/01/11 | 1-15/02/11 | 2-16/02/11 | 16-23/02/11 | 28/2/11-21/3/11 | 29/03/11-4/4/11 | 11-22/04/11 | 25/04/11-23/05/11 | 24/05/11-7/06/11 | 13-24/06/11 | 27/06/11-11/07/11 | 18-29/07/11 | 1-12/08/11 | 15-19/08/11 | NA | 10000000 | 22-26/08/11 | 29/08/11-2/09/11 | 5-16/09/11 | NA | 19-23/09/11 | NA | Dauda I. B. | Busari K. O. I.
Casual Services and Consultancies & Sites :Location on the Field Positioning | QCB | Time Based | 7000000 | MTB | 14-28/01/11 | 1-15/02/11 | 2-16/02/11 | 16-23/02/11 | 28/2/11-21/3/11 | 29/03/11-4/4/11 | 11-22/04/11 | 25/04/11-23/05/11 | 24/05/11-7/06/11 | 13-24/06/11 | 27/06/11-11/07/11 | 18-29/07/11 | 1-12/08/11 | 15-19/08/11 | NA | 7000000 | 22-26/08/11 | 29/08/11-2/09/11 | 5-16/09/11 | NA | 19-23/09/11 | NA | Bello M. T. | Busari K. O. I.
Total Cost |  |  | 209037450 | [16 empty] | 209037450
Ministry of Mines & Steel Development, HQ
Budgetary Year: 2011 --- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Busari/08023042658 |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
Goods | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Normal Duration of Procurement Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
add 2 wks
List of Contracts
Procurement of local & Int'l law books | MMSD/NCB/G/11/01 | Lot 1 | 6000000 | NCB | Post-qualification | MTB | 14-28/01/11 | 31/01/11-4/02/11 | 7-14/02/11 | 21/02/11-18/03/11 | 21/03/11-22/04/11 | 25/04/11-6/05/11 | 9/05/11-23/05/11 | 6000000 | NA | 30/05/11-13/06/11 | 20-24/06/11 | 27/06/11-11/07/11 | 2 Months | 5/09/11-9/09/11 | Bello M. T | Busari K. O. I
Purchase of field / office equipment | MMSD/NCB/G/11/02 | Lot 2 | 50000000 | NCB | Post-qualification | MTB | 14- 28/01/11 | 31/01/11-4/02/11 | 7-14/02/11 | 21/02/11-18/03/11 | 21/03/11-22/04/11 | 25/04/11-6/05/11 | 9/05/11-23/05/11 | 50000000 | NA | 30/05/11-13/06/11 | 20-24/06/11 | 27/06/11-11/07/11 | 2 Months | 5/09/11-9/09/11 | Uba Muktar | Busari K. O. I
Equipping the Ministry library | MMSD/NCB/G/11/03 | lot 3 | 10000000 | NCB | Post- qualification | MTB | 14-28/01/11 | 31/01/11-4/02/11 | 7-14/02/11 | 21/02/11-18/03/11 | 21/03/11-22/04/11 | 25/04/11-6/05/11 | 9/05/11-23/05/11 | 10000000 | NA | 30/05/11-13/06/11 | 20-24/06/11 | 27/06/11-11/07/11 | 2 Months | 5/09/11-9/09/11 | Musa Garba | Busari k. O. I
Procurement of IT Equipment & Dev.of MIS | MMSD/NCB/G/11/04 | Lot 4 | 20000000 | NCB | Post- qualification | MTB | 14-28/01/11 | 31/01/11-4/02/11 | 7-14/02/11 | 21/02/11-18/03/11 | 21/03/11-22/04/11 | 25/04/11-6/05/11 | 9/05/11-23/05/11 | 20000000 | NA | 30/05/11-13/06/11 | 20-24/06/11 | 27/06/11-11/07/11 | 2 Months | 5/09/11-9/09/11 | Akporno Joyce | Busari K. O. I
Transport (vehicles) -2- Hilux 4 wheel for each zonal office | MMSD/NCB/G/11/05 | Lot 5 | 8000000 | NCB | Post- qualification | MTB | 14-28/01/11 | 31/01/11-4/02/11 | 7-14/02/11 | 21/02/11-18/03/11 | 21/03/11-22/04/11 | 25/04/11-6/05/11 | 9/05/11-23/05/11 | 8000000 | NA | 30/05/11-13/06/11 | 20-24/06/11 | 27/06/11-11/07/11 | 1 Month | 04/08/11-11/08/11 | Bello M. T. | Busari K. O. I.
procurement of Monitoring & Evaluation Equipment. | MMSD/NCB/G/11/06 | Lot 6 | 10000000 | NCB | Post- qualification | MTB | 14-28/01/11 | 31/01/11-4/02/11 | 7-14/02/11 | 21/02/11-18/03/11 | 21/03/11-22/04/11 | 25/04/11-6/05/11 | 9/05/11-23/05/11 | 10000000 | NA | 30/05/11-13/06/11 | 20-24/06/11 | 27/06/11-11/07/11 | 2 Months | 5/09/11-9/09/11 | Akporno Joyce | Busari K. O. I
Production of Annual journal on Mineral & Metal | MMSD/NCB/G/11/07 | Lot 7 | 4000000 | NCB | Post-qualification | MTB | 14-28/01/11 | 31/01/11-4/02/11 | 7-14/02/11 | 21/02/11-18/03/11 | 21/03/11-22/04/11 | 25/04/11-6/05/11 | 9/05/11-23/05/11 | 4000000 | NA | 30/05/11-13/06/11 | 20-24/06/11 | 27/06/11-11/07/11 | 2 Months | 5/09/11-9/09/11 | Dauda I. B. | Busari K. O. I
Procurement of Metallurgical Testing Equipment | MMSD/NCB/G/11/08/9 | Lot 8 & 9 | 45000000 | NCB | Post- qualification | MTB | 14-28/01/11 | 31/01/11-4/02/11 | 7-14/02/11 | 21/02/11-18/03/11 | 21/03/11-22/04/11 | 25/04/11-6/05/11 | 9/05/11-23/05/11 | 45000000 | NA | 30/05/11-13/06/11 | 20-24/06/11 | 27/06/11-11/07/11 | 2 Months | 5/09/11-9/09/11 | Bello M. T | Busari K. O. I.
Total Cost |  |  | 153000000 | [10 empty] | 153000000
0
Fill gray cells only!
Ministry of Mines & Steel Development HQ
Budgetary Year: 2011 --- Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Busari/08023042658 |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
Works | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Normal Duration of Procurement Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
add 2 wks
List of Contracts
Drilling of 3 Core Holes & Logging analysis | MMSD/NCB/W/11/01 | Lot 1 | Time Based | NCB | 50000000 | 14-28/01/11 | MTB | 1-15/02/11 | 16-23/02/11 | 2-16/03/11 | 21/03/11-22/04/11 | 26/04/11-27/05/11 | 30/05/11-13/06/11 | 14-21/06/11 | 50000000 | NA | 22-29/06/11 | 4-8/07/11 | 11-18/07/11 | 3 Months | 4 Months | NA | Uba Muktar | Busari, K. O. I
Upgrading of IT equipment Phase I | MMSD/NCB/W/11/02 | Lot 2 | Time Based | NCB | 30000000 | 14-28/01/11 | MTB | 1-15/02/11 | 16-23/02/11 | 2-16/03/11 | 21/03/11-22/04/11 | 26/04/11-27/05/11 | 30/05/11-13/06/11 | 14-21/06/11 | 30000000 | NA | 22-29/06/11 | 4-8/07/11 | 11-18/07/11 | 3 Months | 4 Months | NA | Dauda I. B. | Busari K. O. I.
Construction of Steel Racks & Purchase of Steel Cabinet for Store | MMSD/NCB/W/11/03 | Lot 3 | Time Based | NCB | 10000000 | 14-28/01/11 | MTB | 1-15/02/11 | 16-23/02/11 | 2-16/03/11 | 21/03/11-22/04/11 | 26/04/11-27/05/11 | 30/05/11-13/06/11 | 14-21/06/11 | 10000000 | NA | 22-29/06/11 | 4-8/07/11 | 11-18/07/11 | 3 Months | 4 Months | NA | Musa Garba | Busari K. O. I.
Rehabilitation of Concentrate Plant 1 & 2 | MMSD/NCB/W/11/04 | Lot 4 | Lump Sum | NCB | 500000000 | 14-28/01/11 | MTB | 1-15/02/11 | 16-23/02/11 | 2-16/03/11 | 21/03/11-22/04/11 | 26/04/11-27/05/11 | 30/05/11-13/06/11 | 14-21/06/11 | 500000000 | NA | 22-29/06/11 | 4-8/07/11 | 11-18/07/11 | 4 Months | 6 Months | NA | Bello M. T. | Busari K. O. I.
Sourcing of Raw Materials | MMSD/NCB/W/11/05 | Lot 5 | Time Based | NCB | 25000000 | 14-28/01/11 | MTB | 1-15/02/11 | 16-23/02/11 | 2-16/03/11 | 21/03/11-22/04/11 | 26/04/11-27/05/11 | 30/05/11-13/06/11 | 14-21/06/11 | 25000000 | NA | 22-29/06/11 | 4-8/07/11 | 11-18/07/11 | 3 Months | 4 Months | NA | Akponor J. | Busari K. O. I.
Completion of the installation of super concentrate line | MMSD/NCB/W/11/06 | Lot 6 | Lump Sum | NCB | 400000000 | 14-28/01/11 | MTB | 1-15/02/11 | 16-23/02/11 | 2-16/03/11 | 21/03/11-22/04/11 | 26/04/11-27/05/11 | 30/05/11-13/06/11 | 14-21/06/11 | 400.000,000.00 | NA | 22-29/06/11 | 4-8/07/11 | 11-18/07/11 | 4 Months | 6 Months | NA | Bello M. T. | Busari K. O. I.
Establishment of Exstension Services for the Downstream SMEs in the Metals Sector. | MMSD/NCB/W/11/07 | Lot 7a | Time Based | NCB | 18000000 | 14-28/01/11 | MTB | 1-15/02/11 | 16-23/02/11 | 2-16/03/11 | 21/03/11-22/04/11 | 26/04/11-27/05/11 | 30/05/11-13/06/11 | 14-21/06/11 | 18000000 | NA | 22-29/06/11 | 4-8/07/11 | 11-18/07/11 | 2 Months | 3 Months | NA | Musa Garba | Busari K. O. I.
Establishment of Nigeria Steel Forum |  | Lot 7b | Time Based | NCB | 15000000 | 14-28/01/11 | MTB | 1-15/02/11 | 16-23/02/11 | 2-16/03/11 | 21/03/11-22/04/11 | 26/04/11-27/05/11 | 30/05/11-13/06/11 | 14-21/06/11 | 15000000 | NA | 22-29/06/11 | 4-8/07/11 | 11-18/07/11 | 2 Months | 3 Months | NA | Uba Muktar | Busari K. O. I.
Upgrading and Updating of Data Bank on Steel & non-ferrous Metal Sector |  | Lot 7c | Time Based | NCB | 7000000 | 14-28/01/11 | MTB | 1-15/02/11 | 16-23/02/11 | 2-16/03/11 | 21/03/11-22/04/11 | 26/04/11-27/05/11 | 30/05/11-13/06/11 | 14-21/06/11 | 7000000 | NA | 22-29/06/11 | 4-8/07/11 | 11-18/07/11 | 2 Months | 3 Months | NA | Bello M. T. | Busari K. O. I.
Blast furnace Raw materials & Coking Coal Ratio Programme in Iron making Tech |  | Lot 7d | Time Based | NCB | 10000000 | 14-28/01/11 | MTB | 1-15/02/11 | 16-23/02/11 | 2-16/03/11 | 21/03/11-22/04/11 | 26/04/11-27/05/11 | 30/05/11-13/06/11 | 14-21/06/11 | 10000000 | NA | 22-29/06/11 | 4-8/07/11 | 11-18/07/11 | 2 Months | 3 Months | NA | Bello M. T. | Busari K. O. I.
Reclamation of Abandoned Mine sites | MMSD/NCB/W/11/08 | Lot 8 | Lump Sum | NCB | 200000000 | 14-28/01/11 | MTB | 1-15/02/11 | 16-23/02/11 | 2-16/03/11 | 21/03/11-22/04/11 | 26/04/11-27/05/11 | 30/05/11-13/06/11 | 14-21/06/11 | 200000000 | NA | 22-29/06/11 | 4-8/07/11 | 11-18/07/11 | 4 Months | 6 Months | NA | Akponor J. | Busari K. O. I.
Total Cost |  |  |  |  | 1265000000

## Mine&Steel_NMDC
National Metallurgical Development Centre, Jos
Budgetary Year: 2011 -- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Busari/08023042658 |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
GOODS | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
add 2 wks
List of Contracts
Tools, Spares and Consumles | NMDCJ/NCB/G/11/01 | Lot 1 | 45387500 | NCB |  | NMDCJ Tender Board | 21/2 - 14/3/2011 | 21/2 - 14/3/2012 |  | 2/5 - 13/6/2011 | 2/5 - 13/6/2012 | 2/5 - 13/6/2013 | 2/5 - 13/6/2014 | 45387500 |  | 29/8/2011 | 29/8/2012 |  | 2011-03-10 | 7/11 - 21/11/11
Operation field Vehicle |  | Lot 2 | 21000000 | NCB |  | NMDCJ Tender Board | 21/2 - 14/3/2011 | 21/2 - 14/3/2012 |  | 2/5 - 13/6/2011 | 2/5 - 13/6/2012 | 2/5 - 13/6/2013 | 2/5 - 13/6/2014 | 21000000 |  | 29/8/2011 | 29/8/2012 |  | 2011-03-10 | 7/11 - 21/11/11
Total Cost |  |  | 66387500 | [10 empty] | 66387500
National Metallurgical Development Centre, Jos
Budgetary Year: 2011 -- Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Busari/08023042658 |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
WORKS | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
add 2 wks
List of Contracts
Completion of Lead-Zinc Smelting Pilot Plant & Installation of Dust & Gas Cleaning System & Pilot Sulphuric Acid Distillation Plant | NMDCJ/NCB/W/11/01 | Lot 1 | Lump Sum | NCB | 40000000 | 14-28/01/11 | NMDC Tender Board | 1-15/02/11 | 16-23/02/11 | 2-16/03/11 | 21/03/11-22/04/11 | 26/04/11-27/05/11 | 30/05/11-13/06/11 | 14-21/06/11 | 40000000 | NA | 22-29/06/11 | 4-8/07/11 | 11-18/07/11 | 3 Months | 4 Months | NA
Completion and Commissioning of Electric Arc Furnance Pilot Plant |  | Lot 2 | Lump Sum | NCB | 56250000 | 14-28/01/11 | NMDC Tender Board | 1-15/02/11 | 16-23/02/11 | 2-16/03/11 | 21/03/11-22/04/11 | 26/04/11-27/05/11 | 30/05/11-13/06/11 | 14-21/06/11 | 56250000 | NA | 22-29/06/11 | 4-8/07/11 | 11-18/07/11 | 3 Months | 4 Months | NA
Rehabilitation of Laboratories, Workshop and Infrastructures |  | Lot 3 | Lump Sum | NCB | 40000000 | 14-28/01/11 | NMDC Tender Board | 1-15/02/11 | 16-23/02/11 | 2-16/03/11 | 21/03/11-22/04/11 | 26/04/11-27/05/11 | 30/05/11-13/06/11 | 14-21/06/11 | 40000000 | NA | 22-29/06/11 | 4-8/07/11 | 11-18/07/11 | 3 Months | 4 Months | NA
Total Cost |  |  |  |  | 136250000 | [9 empty] | 136250000 | [6 empty] | #VALUE!
#REF!

## Mine&Steel_NMTI
National Metrological Training Institute, Onitsha
Budgetary Year: 2011 --- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Busari/08023042658 |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
GOODS | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
add 2 wks
List of Contracts
Purchase of Department/Pool Vehicle | MTIO/NCB/G/11/01 | Lot 1 | 6000000 | NCB |  | NMTI Tender Board | 21/2 - 14/3/2011 | 21/2 - 14/3/2012 |  | 2/5 - 13/6/2011 | 2/5 - 13/6/2012 | 2/5 - 13/6/2013 | 2/5 - 13/6/2014 | 6000000 |  | 29/8/2011 | 29/8/2012 |  | 2011-03-10 | 7/11 - 21/11/11
.
Purchase of Staff/Student Buses |  | Lot 2 | 10000000 | NCB |  | NMTI Tender Board | 21/2 - 14/3/2011 | 21/2 - 14/3/2012 |  | 2/5 - 13/6/2011 | 2/5 - 13/6/2012 | 2/5 - 13/6/2013 | 2/5 - 13/6/2014 | 10000000 |  | 29/8/2011 | 29/8/2012 |  | 2011-03-10 | 7/11 - 21/11/11
Purchase of Additional CNC Lathe, Milling and Shaping Machines for Mech. Engineering Course |  | Lot 3 | 22000000 | NCB |  | NMTI Tender Board | 21/2 - 14/3/2011 | 21/2 - 14/3/2012 |  | 2/5 - 13/6/2011 | 2/5 - 13/6/2012 | 2/5 - 13/6/2013 | 2/5 - 13/6/2014 | 22000000 |  | 29/8/2011 | 29/8/2012 |  | 2011-03-10 | 7/11 - 21/11/11
Purchase of Pneumatic, Coiling & Electrical Installation Equipment |  | Lot 4 | 25000000 | NCB |  | NMTI Tender Board | 21/2 - 14/3/2011 | 21/2 - 14/3/2012 |  | 2/5 - 13/6/2011 | 2/5 - 13/6/2012 | 2/5 - 13/6/2013 | 2/5 - 13/6/2014 | 25000000 |  | 29/8/2011 | 29/8/2012 |  | 2011-03-10 | 7/11 - 21/11/11
Total Cost |  |  | 63000000 | [10 empty] | 63000000
Fill gray cells only!
National Metrological Training Institute, Onitsha
Budgetary Year: 2011 --- Works | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Busari/08023042658 |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
WORKS | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
add 2 wks
List of Contracts
Construction of Auditorium | MTIO/NCB/W/11/01 | Lot 1 | Lump Sum | NCB | 118300000 | 14-28/01/11 | NMTI Tender Board | 1-15/02/11 | 16-23/02/11 | 2-16/03/11 | 21/03/11-22/04/11 | 26/04/11-27/05/11 | 30/05/11-13/06/11 | 14-21/06/11 | 118300000 | NA | 22-29/06/11 | 4-8/07/11 | 11-18/07/11 | 3 Months | 4 Months | NA
Construction of Hostel block |  | Lot 2 | Lump Sum | NCB | 40903453 | 14-28/01/11 | NMTI Tender Board | 1-15/02/11 | 16-23/02/11 | 2-16/03/11 | 21/03/11-22/04/11 | 26/04/11-27/05/11 | 30/05/11-13/06/11 | 14-21/06/11 | 40903453 | NA | 22-29/06/11 | 4-8/07/11 | 11-18/07/11 | 3 Months | 4 Months | NA
Completion of Technical Facilities Phase 1A-Contract C |  | Lot 3 | Lump Sum | NCB | 13887500 | 14-28/01/11 | NMTI Tender Board | 1-15/02/11 | 16-23/02/11 | 2-16/03/11 | 21/03/11-22/04/11 | 26/04/11-27/05/11 | 30/05/11-13/06/11 | 14-21/06/11 | 13887500 | NA | 22-29/06/11 | 4-8/07/11 | 11-18/07/11 | 3 Months | 4 Months | NA
Final Account on Technical Facilities Phase 1A- Contract A&B |  | Lot 4 | Lump Sum | NCB | 57415000 | 14-28/01/11 | NMTI Tender Board | 1-15/02/11 | 16-23/02/11 | 2-16/03/11 | 21/03/11-22/04/11 | 26/04/11-27/05/11 | 30/05/11-13/06/11 | 14-21/06/11 | 57415000 | NA | 22-29/06/11 | 4-8/07/11 | 11-18/07/11 | 3 Months | 4 Months | NA
Total Cost |  |  |  |  | 159203453 | [9 empty] | #REF! | [6 empty] | #VALUE!
[15 empty] | #REF! | [6 empty] | #REF!
Fill gray cells only!

## Mine&Steel_NSRMEA
NATIONAL STEEL RAW MATERIALS EXPLORATION AGENCY, KADUNA
Budgetary Year: 2011 --- Goods | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Busari/08023042658 |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  |  | Contract Implementation
GOODS | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
add 2 wks
List of Contracts
Procurement of 1No. Atlas Copco Multi- Purpose Drilling Rig (MUSTANGS 5-P4) | NSRMEA/NCB/G/11/01 | Lot 1 | 265000000 | NCB |  | NSRMEA Tender Board | 21/2 - 14/3/2011 | 21/2 - 14/3/2012 |  | 2/5 - 13/6/2011 | 2/5 - 13/6/2012 | 2/5 - 13/6/2013 | 2/5 - 13/6/2014 | 265000000 |  | 29/8/2011 | 29/8/2012 |  | 2011-03-10 | 7/11 - 21/11/11
Procurement of Drilling Materials/ Geotechnical Consumbles-Had alloys, Diamond bits, etc |  | Lot 2 | 40000000 | NCB |  | NSRMEA Tender Board | 21/2 - 14/3/2011 | 21/2 - 14/3/2012 |  | 2/5 - 13/6/2011 | 2/5 - 13/6/2012 | 2/5 - 13/6/2013 | 2/5 - 13/6/2014 | 40000000 |  | 29/8/2011 | 29/8/2012 |  | 2011-03-10 | 7/11 - 21/11/11
Procurement of Field Vehicles - 5 Nos. Toyota Hilux Vans |  | Lot 3 | 25000000 | NCB |  | NSRMEA Tender Board | 21/2 - 14/3/2011 | 21/2 - 14/3/2012 |  | 2/5 - 13/6/2011 | 2/5 - 13/6/2012 | 2/5 - 13/6/2013 | 2/5 - 13/6/2014 | 25000000 |  | 29/8/2011 | 29/8/2012 |  | 2011-03-10 | 7/11 - 21/11/11
Procurement of Geotechnical (Geophysics) Equipment - 4Nos. Terrameter |  | Lot 4 | 20000000 | NCB |  | NSRMEA Tender Board | 21/2 - 14/3/2011 | 21/2 - 14/3/2012 |  | 2/5 - 13/6/2011 | 2/5 - 13/6/2012 | 2/5 - 13/6/2013 | 2/5 - 13/6/2014 | 20000000 |  | 29/8/2011 | 29/8/2012 |  | 2011-03-10 | 7/11 - 21/11/11
Procurement of Geotechnical (Survey) Equipment - 2Nos. Promark 3 GPS System |  | Lot 5 | 9000000 | NCB |  | NSRMEA Tender Board | 21/2 - 14/3/2011 | 21/2 - 14/3/2012 |  | 2/5 - 13/6/2011 | 2/5 - 13/6/2012 | 2/5 - 13/6/2013 | 2/5 - 13/6/2014 | 9000000 |  | 29/8/2011 | 29/8/2012 |  | 2011-03-10 | 7/11 - 21/11/11
Procurement of Geotechnical (Survey) Equipment - 2Nos. Leica Total Station Survey Equipment |  | Lot 6 | 7000000 | NCB |  | NSRMEA Tender Board | 21/2 - 14/3/2011 | 21/2 - 14/3/2012 |  | 2/5 - 13/6/2011 | 2/5 - 13/6/2012 | 2/5 - 13/6/2013 | 2/5 - 13/6/2014 | 7000000 |  | 29/8/2011 | 29/8/2012 |  | 2011-03-10 | 7/11 - 21/11/11
Procurement of ICT Software - Computers and Internet Conectivity, Furniture and Fittings. |  | Lot 7 | 424097 | NCB |  | NSRMEA Tender Board | 21/2 - 14/3/2011 | 21/2 - 14/3/2012 |  | 2/5 - 13/6/2011 | 2/5 - 13/6/2012 | 2/5 - 13/6/2013 | 2/5 - 13/6/2014 | 424097 |  | 29/8/2011 | 29/8/2012 |  | 2011-03-10 | 7/11 - 21/11/11
Total Cost |  |  | 366424097 | [10 empty] | 366000000
Fill gray cells only!