## Surveyor-Gen
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) : |  | OFFICE OF THE SURVEYOR-GENERAL OF THE FEDERATION
MINISTRY : |  | FMW
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2014 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | TOPOGRAPHIC MAPPING IN DIGITAL FORMAT COVERNG AKURE STANDAND SHEET 264 AT SCALE 1:25,000 | 24th March 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 7th April 2014 | 8th April 2014 | N64,915,300.00 | NIL | 5TH/5/2014 | YES | M/S GENESIS DATA GATHERERS LTD | 21st May 2014 | 8892560 | 6WKS | NA | N8,892,560.00 |  | COMPLETED | 100% | NIL | NIL
2 | TOPOGRAPHIC MAPPING IN DIGITAL FORMAT COVERNG TWO STANDART SHEET 242 AT SCALE 1:25,000 | 24th March 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 7th April 2014 | 8th April 2014 | N64,915,300,00 | NIL | 5TH/5/2014 | YES | M/S EMEZ NIG. LTD | 21st May 2014 | 8864800 | 6WKS | NA | N8,864,800.00 |  | COMPLETED | 100% | NIL | NIL
3 | TOPOGRAPHIC MAPPING IN DIGITAL FORMANT COVERING ILLUSHI STANDARD SHEET 286 AT SCALE 1:25,000 | 24th March 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 7th April 2014 | 8th April 2014 | N64,915,300.00 | NIL | 5TH/5/2014 | YES | M/S AUSPICEY GLOBAL SER, LTD. | 21st May 2014 | 8888400 | 6WKS | NA | N8,888,400.00 |  | COMPLETED | 100% | NIL | NIL
4 | TOPOGRAPHIC MAPPING IN DIGITAL FORMAT COVERING EJEKWE STANDARD SHEET 289 AT SCALE 1:25,000 | 24th March 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 7th April 2014 | 8th April 2014 | N64,915,300.00 | NIL | 5TH/5/2014 | YES | M/S DESICIVE SURVEYS LTD | 21st May 2014 | 8796480 | 6WKS | NA | N8,796,480.00 |  | COMPLETED | 100% | NIL | NIL
5 | TOPOGRAPHIC MAPPING IN DIGITAL FORMAT COVERING KATSINA STANDARD SHEET 34 AT SCALE 1:25,000 | 24th March 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 7th April 2014 | 8th April 2014 | N64,915,300.00 | NIL | 5TH/5/2014 | YES | M/S CHUKA & ASS. LTD | 21st May 2014 | 8880200 | 6WKS | NA | N8,880,200.00 |  | COMPLETED | 100% | NIL | NIL
6 | TOPOGRAPHIC MAPPING IN DIGITAL FORMAT COVERING KUNYE STANDARD SHEET 58 AT SCALE 1:25,000 | 24th March 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 7th April 2014 | 8th April 2014 | N64,915,300.00 | NIL | 5TH/5/2014 | YES | M/S ALPHA SURVEYS & MAPPING NIG. LTD | 21st May 2014 | 8864600 | 6WKS | NA | N8,864,600.00 |  | COMPLETED | 100% | NIL | NIL
7 | TOPOGRAPHIC MAPPING IN DIGITAL FORMAT COVERING IJEBU-IFE STANDARD SHEET 281 AT SCALE 1:25,000 | 24th March 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 7th April 2014 | 8th April 2014 | N64,915,300.00 | NIL | 5TH/5/2014 | YES | M/S SUBMILLIMETER TECHNOLOGIES LTD | 21st May 2014 | 8,950.000.00 | 6WKS | NA | N8,950.000.00 |  | COMPLETED | 100% | NIL | NIL
8 | UPGRADING OF TOPOGRAPHIC MAP SHEETS AT SCALE 1:50,000 C0VERING: SS 298 BENIN CITY | 24th March 2014 | MTB | NCB | 7th April 2014 | 8th April 2014 | N8,355,200.00 | NIL | 5TH/5/2014 | YES | M/S AR-ER GEPMATRIX SUR. LTD | 21st May 2014 | 6460800 | 6WKS | NA | N6,460,800.00 |  | COMPLETED | 100% | NIL | NIL
9 | REVISION OF TOPOGRAPHIC MAP SHEET IN DIGITAL FORMAT COVERING LOKOJA STANDARD SHEET 247 AT SCALE 1:50,000 | 24th March 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 7th April 2014 | 8th April 2014 | N6,480,640.00 | NIL | 5TH/5/2014 | YES | M/S UZOR SURVEYS NIG. LTD | 21st May 2014 | 6480640 | 6WKS | NA | N6,480,640.00 |  | COMPLETED | 100% | NIL | NIL
10 | TOPOGRAPHIC MAPPING IN DIGITAL FORMAT COVERING KAZAURE STANDARD SHEET 35 AT SCALE 1:100,000 | 24th March 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 7th April 2014 | 8th April 2014 | N6,759,700.00 | NIL | 5TH/5/2014 | YES | M/S MILAD SURVEYS CONSULT LTD | 21st May 2014 | 6,446,920,00 | 6WKS |  | N6,446,920,00 |  | COMPLETED | 100% | NIL | NIL
11 | TOURISM DEV./TOURIST SITES MAPPING OF SOUTH-EAST GEO-POLITICAL ZONE (ABIA, ANAMBRA, EBONYI, ENUGU & IMO STATES | 24th March 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 7th April 2014 | 8th April 2014 | N4,256,740.00 | NIL | 5TH/5/2014 | YES | M/S PERPETUA POINT PILLAR LTD | 21st May 2014 | 4256740 | 6WKS |  | N4,256,740.00 |  | COMPLETED | 100% | NIL | NIL
12 | FIELD TRACING & PROVISIONAL DEMARCATION OF ABIA/AKWA IBOM INTERSTATE BOUNDRY SECTOR I FROM TRIPARTITE POINT OF ABIA/EBONYI/AKWA IBOM STATES TO A POINT ON RIVER INYANG ITU (46KM) | 24th March 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 7th April 2014 | 8th April 2014 | N35,347,200.00 | NIL | 5TH/5/2014 | YES | M/S FIG SPATIAL MAPPING & GEOSPATIAL SERVICES | 21st May 2014 | 7770000 | 30DAYS |  | N7,770,000.00 |  | COMPLETED | 100% | NIL | NIL
13 | TRACING OF DISPUTED SECTOR OF EBONYI/ENUGU INTERSTATE BOUNDARY | 24th March 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 7th April 2014 | 8th April 2014 | N35,347,200.00 | NIL | 5TH/5/2014 | YES | M/S PYTHAGORAS SURV. CONCERNS LTD | 21st May 2014 | 6860000 | 21DAYS |  | N23,050,000.00 |  | COMPLETED | 100% | NIL | NIL
14 | FIELD TRACING AND PROVISIONAL DEMARCATION OF KANO/KATSINA INTERSTATE BOUNDARY SECTOR: (45 KM) | 17th March 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 31st March 2014 | 1st April 2014 | N35,347,200.00 | NIL | 5TH/5/2014 | YES | M/S DIGITOPS CONSULTANT LTD | 21st May 2014 | 7750000 | 21DAYS |  | N7,750,000.00 |  | COMPLETED | 100% | NIL | NIL
15 | EMPLACEMENT OF MAIN BEACONS ALONG EKITI/OSUN INTERSTATE BOUNDARY | 17th March 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 31st March 2014 | 1st April 2014 | N34,303,488.00 | NIL | 5TH/5/2014 | YES | M/S PAT-EVERLASTING SURVEYSS LTD | 21st May 2014 | 6770000 | 22DAYS |  | N6,770,000.00 |  | COMPLETED | 100% | NIL | NIL
16 | MAINTANANCE OF ADAMAWA/TARABA INTERSTATE BOUNDARYCORRIDOR SECTOR III, FROM PILLAR FSN/AD/TR 21 AT GANGWERE TO PILLAR FSN/AD/TR 23 AT SAMARI A DISTANCE OF ABOUT 22KM | 17th March 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 31st March 2014 | 1st April 2014 | N34,136,320.00 | NIL | 5TH/5/2014 | YES | M/S GBANGBALA SURVEYS LTD | 21st May 2014 | 3300000 | 21DAYS |  | N3,300,000.00 |  | COMPLETED | 100% | NIL | NIL
17 | MAINTENANCE OF KWARA/OYO INTERSTATE BOUNDARY CORRIDOR SECTOR III, FROM PILLAR NP/SP 180(NEAR BATABI KWARA STATE) TO PILLAR NP/SP 122 (NEAR ADAGBANGBA, OYO STATE) DISTANCE=24KM. | 17th March 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 31st March 2014 | 1st April 2014 | N34,136,320.00 | NIL | 5TH/5/2014 | YES | M/S LANE DIGITAL VENTURES LTD | 21st May 2014 | 3648500 | 14DAYS |  | N3,648,500.00 |  | COMPLETED | 100% | NIL | NIL
18 | SUEVEY/FIELD ASSESSMENT OF BOUNDARY CORRIDOR ON NIGERA-CAMEROON INTERNATIONAL BOUNDRY FROM 06° 31'N, 09° 37'E TO 06° 47'N, 09° 46'E (DISTANCE 46KM) IN TSEANDE, BENUE STATE, NIGERIA/ESSU, NORTH REGION, CAMEROON SECTION OF THE BOUNDARY | 24th March 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 7th April 2014 | 8th April 2014 | N34,840,000.00 | NIL | 5TH/5/2014 | YES | M/S 3-ALPHA SURVEYS & ENGEERING LTD | 21st May 2014 | 5003145 | 15DAYS |  | N5,003,145.00 |  | COMPLETED | 100% | NIL | NIL
19 | SURVEY/FIELD ASSESSMENT BOUNDARY[ CORRIDOR ON NIGERIAN/CAMEROON INTERNATIONAL BOUNDARY FROM 09° 44'N 13°16'E TO 10° 03'N, 17'E (DISTANCE45KM IN HOLMARE, ADAMAWA STATE, NIGERIA/OURO ARDO-BAN, NORTH REGION, CAMEROON SECTION OF THE BOUNDARY | 24th March 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 7th April 2014 | 8th April 2014 | N34,840,000.00 | NIL | 5TH/5/2014 | YES | M/S GLOBAL SURVEYORS & ASSOCIATE LTD | 21st May 2014 | 5000320 | 2WKS |  | N5,000,320.00 |  | COMPLETED | 100% | NIL | NIL
20 | 2ND ORDER GPS RE-OBSERVATION OF 21 NO PILLARS (FROM PILLAR 110 TO PILLAR 110-111/20 LOCATED IN GUTTU. JIGAWA STATE. NIGERIA/DOGO DOGO ZINDER REGION. NIGER SECTION OF NIGERIA/NIGER BOUNDARY | 24th March 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 7th April 2014 | 8th April 2014 | N33,280,000.00 | NIL | 5TH/5/2014 | YES | M/S EM & JAY SURVEYS NIG LTD | 21st May 2014 | 4201250 | 27DAYS |  | N4,201,250.00 |  | COMPLETED | 100% | NIL | NIL
21 | 2ND ORDER GPS RE-OBSERVATION ON 29 INTERMIDIATE PILLARS BETWEEN MAIN PILLARS 68 AND 69 AT KATSINA STATE/MARADU REGION OF NIGERIA/NIGER INTERNATIONAL BOUNDRY | 17th March 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 31st April 2014 | 9th May 2014 | N33,280,000.00 | NIL | 5TH/5/2014 | YES | M/S 3D GEOPHYSICAL & SURVEYS LTD | 21st May 2014 | 5600000 | 21DAYS |  | N5,600,000.00 |  | COMPLETED | 100% | NIL | NIL
22 | CONSTRUCTION OF 26 NO. INTERMEDIATE PILLARS BETWEEN MAIN PILARS 29 AND 30 ALONG KEBBI/SOSSO SECTOR OF NIGERIA/NIGER INTERNATIONAL BOUNDRIES | 17th March 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 31st April 2014 | 9th May 2014 | N15,60,000.00 | NIL | 5TH/5/2014 | YES | M/SF.A. KASSIM SURVEY ASSOCIATES LTD | 21st May 2014 | 7200000 | 21DAYS |  | N7,200,000.00 |  | COMPLETED | 100% | NIL | NIL
23 | SURVEY & DERMACATION OF RIGHT OF WAY (ROW) ALONG LAFIA /MAKURDI HIGHWAY (92Km FROM LAFIA TO AWE IN NASSARAWA STATE INCLUDING PROCESSING OF HIGH RESOLUTION STATELITE IMAGERIES COVERING THE ENTIRE HIGHWAY. | 24/3/14 (OSGOF NOTICE BOARD) | MTB | NCB | 2014-07-04 | 2014-08-04 | N28,221,588.97 | NIL | 5TH/5/2014 | YES | M/S IGNAGO CONSULTS LTD | 21st May 2014 | 8980000 | 2MOMTHS |  | N8,980,000.00 |  | COMPLETED | 100% | NIL | NIL
24 | SURVEY & DEMACATION OF RIGHT OF WAY (ROW) ALONG AKURE-OMU ARAN HIGHWAY (90KM FROM AKURE TO AYETORO-EKITI IN EKITI STATE), INCLUDING PROCESSING OF HGIH RESOLUTION SATELITE IMAGERIES COVERING THE ENTIRE HIGHWAY | 24/3/14 (OSGOF NOTICE BOARD) | MTB | NCB | 2014-07-04 | 2014-08-04 | N28,221,588.97 | NIL | 5TH/5/2014 | YES | M/S PANEZ SURVEYS ASSOCIATE LTD | 21st May 2014 | 8748900 | 2MONTHS |  | N8,748,900.00 |  | COMPLETED | 100% | NIL | NIL
25 | SURVEYS & DEMACATION OF RIGHT OF WAY (ROW) ALONG LAGOS-KADUNA RAILWAY (80Km FROM MOKWA TO BOKANA IN NIGER STATE INCLUDING PROCESSING OF HIGH RESOLUTION IMAGERIES COVERINF THE ENTIRE RAILWAY | 24/3/14 (OSGOF NOTICE BOARD) | MTB | NCB | 2014-07-04 | 2014-08-04 | N28,221,588.97 | NIL | 5TH/5/2014 | YES | M/S PATHFINDER GEO-SPATIAL ANALYSIS LTD | 21st May 2014 | 8693750 | 2MONTHS |  | N8,693,750.00 |  | COMPLETED | 100% | NIL | NIL
26 | GPS OBSERVATION OF TEN (10Nos) CONSTRUCTED PRIMARY PILLARS IN ENUGU (4) ANAMBRA ($) AND EBONYI(2) STATES | 24/3/14 (OSGOF NOTICE BOARD) | MTB | NCB | 2014-07-04 | 2014-08-04 | N11,900,000.00 | NIL | 5TH/5/2014 | YES | M/S EHIREMEN SURVEYS & ASSOCIATES LTD | 21st May 2014 | 3900000 | 14DAYS |  | N3,900,000.00 |  | COMPLETED | 100% | NIL | NIL
27 | GPS OBSERVATION OF TEN (10Nos) CONSTRUCTED PRIMARY PILLARS IN ONDO (3), OGUN (3) AND LAGOS (4) STATES | 24/3/14 (OSGOF NOTICE BOARD) | MTB | NCB | 2014-07-04 | 2014-08-04 | N11,900,000.00 | NIL | 5TH/5/2014 | YES | M/S EQUATORIAL MAPPING CONSULTANT LTD | 21st May 2014 | 3945048 | 14DAYS |  | N3,945,048.00 |  | COMPLETED | 100% | NIL | NIL
28 | GPS OBSERVATION OF TEN (10Nos.) CONSTRUTED PRIMARY PILLARS IN RIVERS (2), EDO (2), BAYELSA (2), COSS RIVERS (2) & AKWA IBOM (2) STATES | 24/3/14 (OSGOF NOTICE BOARD) | MTB | NCB | 2014-07-04 | 2014-08-04 | N11,900,000.00 | NIL | 5TH/5/2014 | YES | M/S NOTRE AFRIQUE LTD | 21st May 2014 | 3945500 | 14DAYS |  | N3,945,500.00 |  | COMPLETED | 100% | NIL | NIL
29 | OBSERVATION OF SIXTEEN (16Nos) CONSTRUCTED PRIMARY PILLARS IN TARABA (6) BAUCHI (5) & GOMBE (5) STATES. | 24/3/14 (OSGOF NOTICE BOARD) | MTB | NCB | 2014-07-04 | 2014-08-04 | N8,500,000.00 | NIL | 5TH/5/2014 | YES | M/SALPHA SURVEYS & MAPPING NIG LTD | 21st May 2014 | 5810000 | 14DAYS |  | N5,810,000.00 |  | COMPLETED | 100% | NIL | NIL
30 | COORDINATION & SUPERVISION OF FIELD OPERATION OF MAPPING CADASTRAL, INTERSTATE BOUNDARY AND CONTROL EXTENSION IN THE SOUTH-EAST GEO-POLITICAL ZONE | 24/4/2014 (OSGOF NOTICE BOARD) | MTB | NCB | 16/4/14 | 17/4/14 | N5,000.000.00 | NIL | 5TH/5/2014 | YES | M/S JUDEN NIG. LTD | 21st May 2014 | 4961250 | 21DAYS |  | N4,961,250.00 |  | COMPLETED | 100% | NIL | NIL
31 | CONSULTANCY SERVICES ON MONITORING AND SUPERVISION OF PROJECT CARRIED OUT IN VIEW OF COUNTER NOTICE ISSUED TO TEOBRIGE LTD FOR THE DIGITAL AERIAL SURVEY & MAPPING OF PLATEAU TATE - PHASE I | 24/3/14 (OSGOF NOTICE BOARD) | MTB | NCB | 2014-07-04 | 2014-08-04 | N6,000,000.00 | NIL | 5TH/5/2014 | YES | M/S DEVELOPMENT IMPERATIVE NIG. LTD | 21st May 2014 | 2899000 | 20DAYS |  | N2,899,000.00 |  | COMPLETED | 100% | NIL | NIL
32 | UPGRADING OF INFRASTRUCTURE IN THE NORTH CENTRAL ZONE, MAKURDI WHICH INCLUDES THE FOLLOWING (WORKS) FUMIGATION, CONSTRUCTION & PAINTING OF THE FOLLOWING IN-SITU: 10Nos. CUSTOMISED STELL RACKS, 20 CABINET DRAWERS, 5 EXECUTIVE TABLES WITH CHAIRS | 24/3/14 (OSGOF NOTICE BOARD) | MTB | NCB | 2014-07-04 | 2014-08-04 | N8,000,000.00 | NIL | 5TH/5/2014 | YES | M/S SAMLOFS GLOBAL RESOURCES LTD | 21st May 2014 | 4460000 | 21DAYS |  | N4,460,000.00 |  | COMPLETED | 100% | NIL | NIL
33 | CONSULTANCY SERVICES ON MONITORING AND SUPERVISION OF PROJECT CARRIED OUT IN VIEW OF COUNTER NOTICE ISSUED TO SIRAJ NIG LTD FOR THE DIGITAL AERIAL PHOTOGRAPY OF QUEEN EDE SOIL EROSION AND FLOOD CONTROL PROJECT IN EDO STATE - PHASE I | 24/3/14 (OSGOF NOTICE BOARD) | MTB | NCB | 2014-07-04 | 2014-08-04 | N6,000,000.00 | NIL | 5TH/5/2014 | YES | M/S SIRAJ NIG LTD | 21st May 2014 | 2925000 | 21DAYS |  | N2,925,000.00 |  | COMPLETED | 100% | NIL | NIL
34 | UPGRADING OF INFRASTRUCTURE FOR MAP DEPOT IN THE NORTH CENTRAL ZONE MAKURDI (GOOD}S: SUPPLY OF 2Nos WORKSTATIO & ACCESSORIESS. 3 NO JPAD 4 1No. HP LAPTOP, 2Nos. (LG) AIR CONDITIONER, 3Nos. HP LASERJET PRINTER, 1 No. SHARP PHOTOCPIER, 10 NORTION ANTIVIRUS, 4Nos. HP 85A TONER, 5Nos. 2000W STABILIZERS & 5Nos. MERCURY 1000A UPS. | 24/3/14 (OSGOF NOTICE BOARD) | MTB | NCB | 2014-07-04 | 2014-08-04 | N8,000,000.00 | NIL | 5TH/5/2014 | YES | M/SJETOKA INTERGRATED SERVICES LTD | 21st May 2014 | 34360000 | 7DAYS |  | N3,436,0000.00 |  | COMPLETED | 100% | NIL | NIL
35 | COMPLETION OF ADMINISTRATIVE BUILDING PHASE VII AT RECTAS, ILE-IFE. | THE GUIDIAN, TENDERS JOUNAL & DAILY TRUST 3RD/4/14 | MTB | NCB | 30/4/14 | 1ST/5/14 | N72,000,000.00 | NIL | 5TH/5/2014 | YES | M/S BETSTEV NIG LTD | 21st May 2014 | 37956100 | 8WEEKS |  | N37,956,100.00 |  | COMPLETED | 100% | NIL | NIL
36 | COMPLETION OF INTERNATIONAL STUDENTS' HOSTEL (BLOCK B PHASE IV) AT RECTAS, ILE-IFE. | THE GUIDIAN, TENDERS JOUNAL & DAILY TRUST 3RD/4/14 | MTB | NCB | 30/4/14 | 1ST/5/14 | N72,000,000.00 | NIL | 5TH/5/2014 | YES | M/S KODELAK (NIG LTD | 21st May 2014 | 23800000 | 6WEEKS |  | N23,800,000.00 |  | COMPLETED | 100% | NIL | NIL
37 | CADASTRAL MAPPING OF ANAOCHA LOCAL GOV. AREA OF ANAMBRA STATE | 24/3/14 (OSGOF NOTICE BOARD) | MTB | NCB | 2014-07-04 | 2014-08-04 | N20,000,000.00 | NIL | 5TH/5/2014 | YES | M/S ALL WEATHER SURVEYS & BUSINESS LTD | 21st May 2014 | 9964500 | 2MONTHS |  | N9,964,500.00 |  | COMPLETED | 100% | NIL | NIL
38 | PRODUCTION OF UTILITY MAP COVERING ASABA TOWNSHIP | 24/3/14 (OSGOF NOTICE BOARD) | MTB | NCB | 2014-07-04 | 2014-08-04 | N7,530,000.00 | NIL | 5TH/5/2014 | YES | M/S GEO-LOCATORS & SURVEYING SERVICES LTD | 21st May 2014 | 7518000 | 28DAYS |  | N7,518,000.00 |  | COMPLETED | 100% | NIL | NIL
39 | CONSTRUCTION OF 32 NoS. 2ND ORDER CADASTRAL CONTROL IN KEBBI STATE | 24/3/14 (OSGOF NOTICE BOARD) | MTB | NCB | 2014-07-04 | 2014-08-04 | N8,000,000.00 | NIL | 5TH/5/2014 | YES | M/S JAIRO TERENG LTD | 21st May 2014 | 7943625 | 28DAYS |  | N7,943,625.00 |  | COMPLETED | 100% | NIL | NIL
40 | PRODUCTION OF LINE (VECTORIZED) MAP OF BENIN TOWNSHIP COVERING 105 SQKm AT COMPOSITE SCALE 1:10,000 AND SUB-DIVISION SCALE 1:2,000 | 24/3/14 (OSGOF NOTICE BOARD) | MTB | NCB | 2014-07-04 | 2014-08-04 | N11,470,000.00 | NIL | 5TH/5/2014 | YES | M/S PRACTICAL GIS INTL. LTD | 21st May 2014 | 9776992.25 | 6 WEEKS |  | N9,776,992.25 |  | COMPLETED | 100% | NIL | NIL
41 | CADASTRAL MAPPING OF OGBIA LOCAL GOVERNMENT AREA OF BAYELSA STATE | 24/3/14 (OSGOF NOTICE BOARD) | MTB | NCB | 2014-07-04 | 2014-08-04 | N20,000,000.00 | NIL | 5TH/5/2014 | YES | M/S B.I SURVEYS & CONSULTANT | 21st May 2014 | 9969750 | 2MONTHS |  | N9,969,750.00 |  | COMPLETED | 100% | NIL | NIL
42 | RECONNAISSANCE EXERCISE FOR MAINTENACE OF 18 NO PILLARS (FROM PILLAR 85 TO PILLARS 85-86/18) LOCATED IN YAROGEL, KATSINA STATE NIGERIA/ROUNDJI, ZINDER REGION, NIGER REPUBLIC SECTION OF NIGERIA/NIGER BOUNDARY | 24/3/14 (OSGOF NOTICE BOARD) | MTB | NCB | 2014-07-04 | 2014-08-04 | N9,000,000.00 | NIL | 5TH/5/2014 | YES | M/S JOKY SURVEYS INTL. LTD | 21st May 2014 | 3345580 | 22DAYS |  | N3,345,580.00 |  | COMPLETED | 100% | NIL | NIL
43 | EXTRACTION OF ROADS AND WATER BODIES FROM SATELITE IMAGERIES COVERING SIX STATES IN THE NORTH-EAST AND SOUTH-SOUTH GEO-POLITICAL ZONES OF NIGERIA AT SCALE 1:25,000 | 24/3/14 (OSGOF NOTICE BOARD) | MTB | NCB | 2014-07-04 | 2014-08-04 | N7,367,000.00 | NIL | 15TH/5/2014 | YES | M/S QUANTUM SURVEYORS & MAPPERS LTD | 2nd June 2014 | 7125000 | 3WEEKS |  | N7,125,000.00 |  | COMPLETED | 100% | NIL | NIL
44 | PROCUREMENT OF 15KVA INDUSTRIAL STAVO AND UPGRADING OF POWER SUPPLY FACILITY AT AFREF STREAMING DATA CENTRE AT OSGOF HEADQUARTERS, ABUJA | 2/4/2014 (OSGOF NOTICE BOARD) | MTB | NCB | 16/4/14 | 17/4/14 | N5,440,000.00 | NIL | 15TH/5/2014 | YES | M/S 3-ALPHA SURVEYS & ENGEERING LTD | 2nd June 2014 | 5414000 | 1WEEK |  | N5,414,000.00 |  | COMPLETED | 100% | NIL | NIL
45 | UPDATING OF ABUJA STREET GUIDE IN PREPARATION FOR GPS NAVIGATION | 2/4/2014 (OSGOF NOTICE BOARD) | MTB | NCB | 16/4/14 | 17/4/14 | N2,735,000.00 | NIL | 15TH/5/2014 | YES | M/S PANEZ SURVEYS ASSOCIATE LTD | 2nd June 2014 | 2725500 | 2 WEEKS |  | N2,725,500.00 |  | COMPLETED | 100% | NIL | NIL
46 | PRODUCTION OF DIGITAL STREET GUIDE MAP OF ABAKALIKI, CAPITAL OF EBONYI STATE | 2/4/2014 (OSGOF NOTICE BOARD) | MTB | NCB | 16/4/14 | 17/4/14 | N6,721,000.00 | NIL | 15TH/5/2014 | YES | M/S STAR SURVEYORS LTD | 2nd June 2014 | 6721000 | 4 WEEKS |  | N6,721,000.00 |  | COMPLETED | 100% | NIL | NIL
47 | ORGANISING CAPACITY BUILDING ON AFREF THROUGH CONSULTANCY SERVICES | 2/4/2014 (OSGOF NOTICE BOARD) | MTB | NCB | 16/4/14 | 17/4/14 | N4,650,000.00 | NIL | 15TH/5/2014 | YES | M/S MCABIGAIL GEOMETRIC LTD | 2nd June 2014 | 4595000 | 2 WEEKS |  | N4,595,000.00 |  | COMPLETED | 100% | NIL | NIL
48 | FACILITATION OF PARTICIPATION OF OSGOF DELEGATION AT ESRI INTERNATIONAL USER CONFERENCE IN SAN DIEGO CALIFONIA, USA | 2/4/2014 (OSGOF NOTICE BOARD) | MTB | NCB | 16/4/14 | 17/4/14 | N3,980,000.00 | NIL | 15TH/5/2014 | YES | M/S DUKAR APPOLO NIG. LTD. | 2nd June 2014 | 3074000 | 3 WEEKS |  | N3,074,000.00 |  | COMPLETED | 100% | NIL | NIL
49 | Upgrading of Remote Support Services for HP Scitex TJ 8350 | 1st July 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 1st August, 2014 | 1st August 2014 | 5027400 | NA | 17th July 2014 | YES | Fazsal Nigeria Ltd | 18th August 2014 | 5000000 | 2Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
50 | Upgrading of Litho-Machine | 1st July 2014. (OSGOF NOTICE BOARD) | MTB | NCB | 1st August, 2014 | 1st August 2014 | 4141150 | NA | 17th July 2014 | YES | RHZ Generation Concept Nigeria Ltd | 18th August 2014 | 3980000 | 2Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
51 | Topographic Mapping in Digital Format Covering Degema Standard Sheet 328 at Scale 1:25,000 | 1st July 2014. (OSGOF NOTICE BOARD) | MTB | NCB | 1st August, 2014 | 1st August 2014 | 8800000 | NA | 16th July 2014 | YES | Mujam Integrated Services Nigeria Ltd | 18th August 2014 | 8748980 | 4Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
52 | Topographic Mapping in Digital Format Covering Burutu Standard Sheet 318 at Scale 1:25,000 | 1st July 2014. (OSGOF NOTICE BOARD) | MTB | NCB | 1st August, 2014 | 1st August 2014 | 8800000 | NA | 16th July 2014 | YES | V-K Technical Company Ltd | 18th August 2014 | 8764840 | 4Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
53 | Revision of Topographic Map Sheet in Digital Format Covering Ibeju Standard Sheet 280A at Scale1:50,000 | 1st July 2014. (OSGOF NOTICE BOARD) | MTB | NCB | 1st August, 2014 | 1st August 2014 | 6020000 | NA | 16th July 2014 | YES | Pat-Everlasting Surveys Ltd | 18th August 2014 | 6004480 | 4Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
54 | Revision of Topographic Map Sheet in Digital Format Covering Zungeru Standard Sheet 163 A at Scale1:50,000 | 1st July 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 1st August, 2014 | 1st August 2014 | 6020000 | NA | 16th July 2014 | YES | Equilibrum Geo Spatial Concept Ltd | 18th August 2014 | 6010000 | 4Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
55 | Revision of Topographic Map Sheet inDigital Format Covering RIRIWAI Standard Sheet 126 at Scale 1:50,000 | 1st July 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 1st August, 2014 | 1st August 2014 | 6020000 | NA | 16th July 2014 | YES | Jetoks Integrated Services Ltd | 18th August 2014 | 5998600 | 4Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
56 | Production of Digital Street Guide Map of Osogbo, Capital of Osun State. | 1st July 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 1st August, 2014 | 1st August 2014 | 6220000 | NA | 16th July 2014 | YES | AK-40 digital Services Nigeria Ltd | 18th August 2014 | 6197000 | 5Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
57 | Observation and Processing of Ten (10)nos. Controls with Orthometric Heights within North Central Zone - FCT & Environs for Geoidal Undulation Parameter Determination | 28th July 2014 (OSGOF NOTICE BOARD) | MTB | NCB/ BOQ | 11th August 2014 | 12th August 2014 | 4095000 | NA | 25th July 2014 | YES | Star Surveyors Ltd | 18th August 2014 | 4050000 | 3Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
58 | Production of Line (Vectorized) Map of Makurdi Township Covering 105 SQ KM at Composite Scale of 1:2,000 | 28th July 2014 (OSGOF NOTICE BOARD) | MTB | NCB/ BOQ | 11th August 2014 | 12th August 2014 | 9968000 | NA | 21st August 2014 | YES | Bonan Surveys Ltd | 18th August 2014 | 9881996.25 | 8Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
59 | Construction of Council Chambers and Presidential Suite at SURCON Headquaters, Abuja. | 1st and 2nd June, 2014. (Sunday Newswatch, and Abuja Weekly) | MTB | NCB/ BOQ | 30th June 2014 | 30th June 2014 | 43600000 | NA | 30th June 2014 | YES | Bauh Nigeria Ltd | 15th August 2014 | 38395602 | 16Weeks |  | Lumpsum |  | Completed | !00% | NA | NA
60 | Organizing Five (5) Days Presidential Retreat for Council Members on Improving Standard of Survey Practice in Nigeria. | 28th July 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 11th August 2014 | 12th August 2014 | 17000000 | NA | 30th June 2014 | YES | Larry Consults Ltd | 15th August 2014 | 9568000 | 5 Days |  | Lumpsum |  | Completed | 100% | NA | NA
61 | Procurement of Rehabilitation of Infrastructure Facilities, Electricity and Street Lights at RECTAS. | RECTAS/ NB, 1st April 2014 | Accounting Officer | National Shopping | 30th April 2014 | 27th October 2014 | 22111399 | NA | 29th March 2014 | YES | 5 Jays Global Engineering Nigeria Ltd | 30th October 2014 | 2839359.76 | 2Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
62 | Procurement of Digital Facility/Software for Photogrammetry and Remote Sensing(PRS) Laboratory at RECTAS. | The Guardian and Daily Trust, 1st and 3rd April, 2014. | MTB | NCB | 30th April 2014 | 27th October 2014 | 22111399 | NA | 29th March 2014 | YES | Geosoft Solutions Ltd | 30th October 2014 | 11891071.56 | 2Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
63 | Procurement of Digital Facilities/Software for Geographic Information System (GIS) Laboratories at RECTAS. | The Guardian and Daily Trust, 1st and 3rd April, 2014. | MTB | NCB | 30th April 2014 | 27th October 2014 | 25126590 | NA | 29th March 2014 | YES | Verity Associates Ltd | 31st October 2014 | 8849880 | 2Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
64 | Procurement of Digital Facilities/Software for Cartography Laboratories at RECTAS. | The Guardian and Daily Trust, 1st and 3rd April, 2014. | MTB | NCB | 30th April 2014 | 27th October 2014 | 25126590 | NA | 26th March 2014 | YES | Eastwind Laboratories | 4th November 2014 | 7551180 | 2Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
65 | Procurement of Digital Facilities/Software for Information and Communication Technology(ICT) Laboratory | The Guardian and Daily Trust, 1st and 3rd April, 2014. | MTB | NCB | 30th April 2014 | 27th October 2014 | 25126590 | NA | 26th March 2014 | YES | Geosoft Solutions Ltd | 4th November 2014 | 11107819.8 | 2Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
66 | Procurement of 3No. Sokkia Theodolite DT 740/40LF and Training of Staff on various Instrument | 15th October, 2014 | MTB | NCB | 25th October 2014 | 27th October 2014 | 6650000 | NA | 1st July 2014 | YES | Geosoft Solutions Ltd | 4th November 2014 | 6300000 | 2Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
67 | Procurement of Surveying Equipment | The Punch and Tribune 12th June 2014 | MTB | NCB | 30th July 2014 | 30th July 2014 | 8800000 | NA | 1st July 2014 | YES | Wellie Grow Nigeria Ltd | 4th November 2014 | 8700000 | 2Days |  | Lumpsum |  | Completed | 100% | NA | NA
68 | Topographic Mapping in Digital Format Covering Garkida (Adamawa and Borno States) Sheet 155 AT Scale 1:25,000 | 14th October 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 28th October 2014 | 28th October 2014 | 27366700 | NA | 14th October 2014 | YES | Pat-Everlasting Surveys Ltd | 17th November 2014 | 8908960 | 3Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
69 | Topographic Mapping in Digital Format Covering Wudil(Kano State) Sheet 81 AT Scale 1:25,000 | 14th October 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 28th October 2014 | 28th October 2014 | 27366700 | NA | 14th October 2014 | YES | Genesis Data Gatherer Ltd | 17th November 2014 | 8920000 | 3Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
70 | Topograpic Mapping in Digital Format Covering Kaura Namoda Standard Sheet 32 AT Scale 1:25,000 | 24th JULY 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 7th August 2014 | 7th August 2014 | 9000000 | NA | 18th August 2014 | YES | Quantum Surveyors and Mappers Ltd | 4th November 2014 | 8780400 | 4Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
71 | Carrying Out the Inventories and Coordination of 50No.(Each Per Zone) Monuments (Active and Passive)- Survey Monuments, Historical Monuments and Other Monument in Both South West and North West Geo-Political Zones | 24th JULY 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 18th August 2014 | 19th August 2014 | 6000000 | NA | 2nd August 2014 | YES | Ehiremen Surveys and Associates Ltd | 4th November 2014 | 5965000 | 4Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
72 | Training of 8No. Staff on Operators of Machine Basics and Colour Management for Five Days | 18th July 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 31st July 2014 | 31st July 2014 | 9304400 | NA | 17th July 2014 | YES | RHZ Generation Concept Nigeria Ltd | 4th November 2014 | 4205000 | 2Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
73 | Subsidence/Deformation Monitoring of Three (3 Nos.) Bridges | 29th July 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 12th August 2014 | 15th August 2014 | 5600000 | NA | 28th July 2014 | YES | Ultimate Digital Services Ltd | 28th AUGUST 2014 | 5554800 | 4Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
74 | Emplacement of Six (6Nos.) Main Beacons Along Kaduna/Plateau Interstate Boundary,SectorII | 14th AUGUST 2014 (OSGOF NOTICE BOARD) | MTB | NCB/ BOQ | 26th August 2014 | 29th August 2014 | 24303488 | NA | 15th August 2014 | YES | Pathfinder Geo-Spatial Analysis Ltd | 28th AUGUST 2014 | 3789000 | 4Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
75 | Topographic Mapping in Digital Format Covering Ilesha (Osun,Oyo, and Ekiti States) Sheet 243 AT Scale1:25000 | 14th October 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 28th October 2014 | 30th October 2014 | 27366700 | NA | 14th October 2014 | YES | McAbigail Geometric Ltd | 4th November 2014 | 8916800 | 4Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
76 | Upgrading of Converted Topo Maps Covering Mallam Maduri(Jigawa and Yobe States) SS38 AT Scale 1:50,000 | 14th October 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 28th October 2014 | 30th October 2014 | 7416000 | NA | 14th October 2014 | YES | Decisive Surveys Ltd | 4th November 2014 | 6528600 | 3Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
77 | Upgrading of Gazettee of Place Names for Electronic National Atlas. | 14th October 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 28th October 2014 | 30th October 2014 | 5806500 | NA | 14th October 2014 | YES | Digitops Consultants Ltd | 4th November 2014 | 5715000 | 3Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
78 | Construction of 8Nos. Primary Pillars in Abuja FCT | 14th October 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 28th October 2014 | 7th November 2014 | 5000000 | NA | 13th October 2014 | YES | Dareco Global Venture Ltd | 17th November 2014 | 4985925 | 2Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
79 | Adjustment of Power Supply to the Data Centre | 14th October 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 30th October 2014 | 3rd November 2014 | 5000000 | NA | 15th October 2014 | YES | Heroic Pace Nigeria Ltd | 17th November 2014 | 4990000 | 2Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
80 | Establishment of Registry of Stakeholders in Survey Coordination At the Office of the Surveyor-General of the Federation | 14th October 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 21st November 2014 | 18th November 2015 | 4000000 | NA | 7th November 2014 | YES | Jairo Tereng Ltd | 29th November 2014 | 4000000 | 2Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
81 | Ugrade and Installation of the ARCGIS 10.2 Desktop Advanced Software for Offices. | 18th November 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 3rd December 2014 | 4th December 2014 | 7400000 | NA | 17th November 2014 | YES | Integrated Spatial and Enviromental Managers Ltd | 4th December 2014 | 3450000 | 2Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
82 | Payment of Annual Internet Subscription to Galaxy Backbone for 2014/15 |  | Accounting Officer | NA |  |  | 3900000 | NA | 17th November 2014 | NO | Galaxy Backbone Ltd | 16th December 2014 | 3080469 |  |  | Lumpsum |  | Completed | 100% | NA | NA
83 | Pooling of Surveyors in All MDAs in the Country | 19th - 24th March 2014 | Accounting Officer | National Shopping | 24th March 2014 | 30th April 2014 | 2000000 | NA | 7th May 2014 | YES | Panez Surveyors Associates Ltd | 2nd June 2014 | 1999850 | 3 Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
84 | Training of PRD Department Staff on ON-POINT SOFTWARE for Data Centre in OSGOF. | 20th March 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 7th April 2014 | 8th April 2014 | 47000000 | NA | 19th March 2014 | YES | Interspatial Technology Nig. Limited | 2nd June 2014 | 7437307.5 | 1Week |  | Lumpsum |  | Completed | 100% | NA | NA
85 | Monitoring and Evaluation of Kaduna - Niger and FCT - Kaduna Boundary Projects in the North West/ North Central Zones of Nigeria. | 23rd March 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 7th April 2014 | 8th April 2014 | 16000000 | NA | 19th March 2014 | YES | Kumeni Services Ltd | 2nd June 2014 | 9850000 | 3Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
86 | Updating and Maintenance of the OSGOF Web Portal Abuja. | 23rd March 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 7th April 2014 | 8th April 2014 | 47000000 | NA | 19th March 2014 | YES | Carter Consulting Limited | 2nd June 2014 | 3484500 | 1Week |  | Lumpsum |  | Completed | 100% | NA | NA
87 | Consultancy Services for Stakeholders Meeting on Review/ Updating of Survey Coordination Act of 1962 and its Amendment Holding in Abuja. | 23rd March 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 7th April 2014 | 8th April 2014 | 8000000 | NA | 19th March 2014 | YES | Joky Surveys International Ltd | 2nd June 2014 | 4000000 | 2Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
88 | Consultancy Services for Holding of 2014 Survey Coodination Conference at Makurdi(Benue State)4th - 8th August 2014 | 23rd March 2014 (OSGOF NOTICE BOARD) | MTB | NCB | 7th April 2014 | 8th April 2014 | 20000000 | NA | 19th March 2014 | YES | Grafos Rock Properties and Engineering Ltd | 2nd June 2014 | 9820000 | 3Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
89 | Construction of Fifteen (15No.) Primary Pillars in Abia (3No.) in Imo (3No) in Delta SouthEast and (3No.) in Rivers (3No.) in Cross Rivers in South South Zones. | 24th March 2014 (OSGOF NOTICE BOARD) | MTB | NCB/ BOQ | 7th April 2014 | 22nd April2014 | 11754025 | NA | 20th April 2014 | YES | Terracraft Services Ltd | 2nd June 2014 | 7023000 | 2Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
90 | Construction of Ten(10No) Primary Pillars in Ondo (3), Oyo (3) and Abuja; FCT (4) | 24th March 2014 (OSGOF NOTICE BOARD) | MTB | NCB/ BOQ | 7th April 2014 | 22nd April2014 | 11754025 | NA | 20th April 2014 | YES | Ehiremen Surveys and Associates Ltd | 2nd June 2014 | 4540000 | 2Weeks |  | Lumpsum |  | Completed | 100% | NA | NA
91 | Purchase of Stock Verification on Inventory Board- 250 Copies and Developing of stock Verification Data Base System for South East Zonal Offices | 8th -13th March 2014, Notice Board | Accounting Officer | National Shopping | 13th March 2014 | NA | 1,000, 000.00 | NA | 21st March 2014 | YES | Messers Royal Jewel Nigeria Ltd | 21st March 2014 | 998000 | 2Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
92 | Procurement of 16 No's Customized Stock Verification Completion Certificate with Security Coded Numbers in Triplicate colours | 3rd - 14th August 2014 | Accounting Officer | National Shopping | 14th August 2014 | NA | 700000 | NA | 18th August 2014 | YES | Messers Global Surveyor and Associates Ltd | 20th August 2014 | 695000 | 1 Week | NA | Lumpsum |  | Completed | 100% | NA | NA
93 | Establishment/Equipment of Law Library and Purchase of Legal Books and Accessories | 10th - 25th March 2014 | Accounting Officer | National Shopping | 25th March 2014 | NA | 3500000 | NA | 30th March 2014 | YES | Messers Lamisawa Nigeria Ltd | 1st April 2014 | 2000000 | 3 Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
94 | Legal Consultancy and Software Training | 10th - 25th March 2014 | Accounting Officer | National Shopping | 25th March 2014 | NA | 2500000 | NA | 30th March 2014 | YES | Messers Rukysan Nig Ltd | 1st April 2014 | 2498000 | 3Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
95 | Partitioning of Legal Unit and Creation of Legal Archives | 10th - 25th March 2014 | Accounting Officer | National Shopping | 25th March 2014 | NA | 2500000 | NA | 30th March 2014 | YES | Furano General Enterprises | 1st April 2014 | 1500000 | 3Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
96 | Training of 31No.Staff of Finance and Accounts Department on Accounts Database Management | 7th-12th August 2014 | Accounting Officer | National Shopping | 12th August 2014 | NA | 2040000 | NA | 19th August 2014 | YES | Fit-Time Integrated Services Ltd | 20th August 2014 | 744000 | 1Week | NA | Lumpsum |  | Completed | 100% | NA | NA
97 | Manpower Development in Public Finance and Treasury Practices | 17th-19th March 2014 | Accounting Officer | National Shopping | 19th March 2014 | NA | 2470000 | NA | 20th March 2014 |  | Fit-Time Integrated Services Ltd | 21st March 2014 | 2466000 | 1Week | NA | Lumpsum |  | Completed | 100% | NA | NA
98 | Upgrading of Accounts Database Management Software | 17th-19th March 2014 | Accounting Officer | National Shopping | 19th March 2014 | NA | 1960000 | NA | 20th March 2014 | YES | GanRead Global Ventures Ltd | 21st March 2014 | 1955000 | 1Week | NA | Lumpsum |  | Completed | 100% | NA | NA
99 | Acquisition of Materials for Headquarters | 17th-18th March 2014 | Accounting Officer | National Shopping | 18th March 2014 | NA | 5000000 | NA | 21st March 2014 | YES | F. Jauni Int'l Ltd | 21st March 2014 | 2485000 | 2Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
100 | Establishment of Commercial Unit,The Production of Advertisement and Publicity Materials | 25th March- 8th April 2014 | Accounting Officer | National Shopping | 8th April 2014 | NA | 900000 | NA | 24th April 2014 | YES | Fadfem Inter. Investment Nig Ltd | 25th April 2014 | 895000 | 3Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
101 | Consultancy Services for the Training of Audit Staff on Electronics Computer based Audit System | 4th-12th August 2014 | Accounting Officer | National Shopping | 12th August 2014 | NA | 2000000 | NA | 19th August 2014 | YES | P-Zeal Business Solution Ltd | 20th August 2014 | 1995000 | 2Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
102 | Awareness Campaign on the roles of Surveying and Mapping in Achieving Vision 20:2020 | 25th-28th March 2014 | Accounting Officer | National Shopping | 28th March 2014 | NA | 1600000 | NA | 4th April 2014 | YES | Lamisawa Nig Ltd | 7th April 2014 | 1598000 | 1Day | NA | Lumpsum |  | Completed | 100% | NA | NA
103 | Inauguration of ACTU Sub Units in Six Zonal Offices | 25th March- 8th April 2014 | Accounting Officer | National Shopping | 8th April 2014 | NA | 700000 | NA | 22nd April 2014 | YES | Furano General Enterprises | 23rd April 2014 | 597000 | 1Week | NA | Lumpsum |  | Completed | 100% | NA | NA
104 | Purchase of Investigative/Security Document Material | 24th March 2014 | Accounting Officer | National Shopping | 8th April 2014 | NA | 100000 | NA | 9th April 2014 | YES | Furano General Enterprises | 23rd April 2014 | 98000 | 1Week | NA | Lumpsum |  | Completed | 100% | NA | NA
105 | Capital Projects, Monitoring and Evaluation (Technical Projects)(Mapping Projects in the SouthWest Geo- political Zone) | 12th-18th March 2014 | Accounting Officer | National Shopping | 18th March 2014 | NA | 3000000 | NA | 21st March 2014 |  | Trail Finder Associates Ltd | 21st March 2014 | 2490000 | 3Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
106 | Pre-Payment Verification of Executed Project in the South South and North East Zones | 13th -20th March 2014 | Accounting Officer | National Shopping | 20th March 2014 | NA | 1550000 | NA | 21st March 2014 |  | Abuja City Enterprises | 21st March 2014 | 1550000 | 3Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
107 | Technical Support For Verification of Survey Projects | 13th -20th March 2014 | Accounting Officer | National Shopping | 20th March 2014 | NA | 2150000 | NA | 21st March 2014 |  | Anita Abunche Enterprises Ltd | 21st March 2014 | 2150000 | 3Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
108 | Capital Projects Monitoring to Ensure Compliance | 13th - 20th March 2014 | Accounting Officer | National Shopping | 20th March 2014 | NA | 2300000 | NA | 21st March 2014 |  | Turaki Resources Ltd | 21st March 2014 | 2300000 | 3Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
109 | Monitoring and Evaluation of Selected Survey Projects in the North West Geo-Political Zone | 14th - 18th March 2014 | Accounting Officer | National Shopping | 18th March 2014 | NA | 3000000 | NA | 25th March 2014 |  | Zeal Golden Global Concept Ltd | 25th March 2014 | 2495000 | 3Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
110 | Consultancy services for Evaluation of Technical Projects (Procurement of Printer Toner) | 10th-18th March 2014 | Accounting Officer | National Shopping | 18th March 2014 | NA | 3000000 | NA | 24th March 2014 |  | S & F Inter Products & Marketing Ltd | 26th March 2014 | 495000 | 1Week | NA | Lumpsum |  | Completed | 100% | NA | NA
111 | Procurement of Office Accessories | 10th -18th March 2014 | Accounting Officer | National Shopping | 18th March 2014 | NA | 600000 | NA | 24th March 2014 |  | F. Jauni Int'l Ltd | 26th March 2014 | 592000 | 1Week | NA | Lumpsum |  | Completed | 100% | NA | NA
112 | Procurement of Office Equipments | 4th-14th August 2014 | Accounting Officer | National Shopping | 14th August 2014 | NA | 2055000 | NA | 19th August 2014 |  | P-Zeal Business Solution Ltd | 20th August 2014 | 2050000 | 2Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
113 | Procurement of Customized Software for the Categorization of Contractors, Installation, Programme and Training of 4N0. Staff. | 3rd -5th November 2014 | Accounting Officer | National Shopping | 5th November 2014 | NA | 1500000 | NA | 6th November 2014 |  | P-Zeal Business Solution Ltd | 11th November 2014 | 1485000 | 3Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
114 | Production of News Bulletin and Exclusive Media Documentary on OSGOF by NTA. | 11th - 15 August 2014 | Accounting Officer | National Shopping | 15th August 2014 | NA | 800000 | NA | 22nd August 2014 |  | Dearug Global Ltd | 22nd August 2014 | 800000 | 3Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
115 | Sensitization/Press Interview on OSGOF Activities by SGOF Anchored by NTA | 12th-18th November 2014 | Accounting Officer | National Shopping | 18th November 2014 | NA | 400000 | NA | 21st November 2014 |  | Dearug Global Ltd | 21st November 2014 | 400000 | 1Week | NA | Lumpsum |  | Completed | 100% | NA | NA
116 | Implementation of International Public Sector Accounting Standards(IPSAS) | 12th - 19th March 2014 | Accounting Officer | National Shopping | 19th March 2014 | NA | 2400000 | NA | 20th March 2014 |  | Habsan Nigeria Enterprises | 21st March 2014 | 2394400 | 1Week | NA | Lumpsum |  | Completed | 100% | NA | NA
117 | Government Integrated Financial and Management Information System(GISMIS) | 12th - 19th March 2014 | Accounting Officer | National Shopping | 19th March 2014 | NA | 2500000 | NA | 21st March 2014 |  | Fit-Time Integrated Services Ltd | 21st March 2014 | 2495000 | 1Week | NA | Lumpsum |  | Completed | 100% | NA | NA
118 | Acquisition of Materials for Budget Activities | 12th - 19th March 2014 | Accounting Officer | National Shopping | 19th March 2014 | NA | 1370000 | NA | 20th March 2014 |  | TJ And Sons Nigeria Ltd | 21st March 2014 | 1364000 | 1Week | NA | Lumpsum |  | Completed | 100% | NA | NA
119 | Replacement of Office Equipment (Printers,Photocopiers, and Toners,Scanners,Binding Machines,and other Consumables | 12th - 19th March 2014 | Accounting Officer | National Shopping | 19th March 2014 | NA | 2500000 | NA | 21st March 2014 |  | Fit-Time Integrated Services Ltd | 21st March 2014 | 2496000 | 1Week | NA | Lumpsum |  | Completed | 100% | NA | NA
120 | Maintenance of Internet Infrastructure | 11th August 2014 | Accounting Officer | National Shopping | 22nd September 2014 | NA | 2350000 | NA | 10th October 2014 |  | Lane Digital Ventures Ltd | 14th October 2014 | 2330000 | 1Week | NA | Lumpsum |  | Completed | 100% | NA | NA
121 | Harmonization of LAN | 19th - 24th March 2014 | Accounting Officer | National Shopping | 24th March 2014 | NA | 2500000 | NA | 13th May 2014 |  | Heroic Pace Nigeria Ltd | 14th May 2014 | 2495000 | 1Week | NA | Lumpsum |  | Completed | 100% | NA | NA
122 | Maintenance of Data Centre | 11th August 2014 | Accounting Officer | National Shopping | 22nd September 2014 | NA | 2390000 | NA | 2nd October 2014 |  | Geolev Nigeria Ltd | 9th October 2014 | 2363000 | 1Week | NA | Lumpsum |  | Completed | 100% | NA | NA
123 | Purchase of ISO Standards for Conventional Survey Equipment | 11th August 2014 | Accounting Officer | National Shopping | 22nd September 2014 | NA | 1125000 | NA | 2nd October 2014 |  | Alpha Geo Resources Ltd | 9th October 2014 | 1124958 | 1Week | NA | Lumpsum |  | Completed | 100% | NA | NA
124 | Map Completion Exercise on the Boundary Corridor between Latitude and Longitude along Nigeria/Benin International Boundaries (22km) | 15th March - 8th April 2014 | Accounting Officer | National Shopping | 8th April 2014 | NA | 2450000 | NA | 8th April 2014 |  | Mujam Integrated Services Nigeria Ltd | 9th April 2014 | 2300000 | 4Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
125 | Map Completion Exercise on the Boundary Corridor between Pillar 9 and Pillar 10 Latitude and Longitude along Nigeria/Niger International Boundaries (21km) | 15th March - 8th April 2014 | Accounting Officer | National Shopping | 8th April 2014 | NA | 2380000 | NA | 8th April 2014 |  | Mujam Integrated Services Nigeria Ltd | 9th April 2014 | 2300000 | 4Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
126 | 2ND Order GPS Re-Observation on 12 No. Intermediate Pillars between Main Pillar 90 to Main Pillar 91 in Katsina State/Zinder Region Along Nigeria/Niger International Boundaries | 22nd - 28th August 2014 | Accounting Officer | National Shopping | 28th August 2014 | NA | 2450000 | NA | 3rd September 2014 |  | Namaranye Techno Ltd | 4th September 2014 | 2430000 | 4Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
127 | 2nd Order GPS Re-Observation on 10 No. Intermediate Pillars between Main Pillar 101/1 to Main Pillar 101/10 in Katsina State/Zinder Region Along Nigeria/Niger International Boundaries | 14th - 20th November 2014 | Accounting Officer | National Shopping | 20th November 2014 | NA | 2250000 | NA | 21st November 2014 |  | Namaranye Techno Ltd | 21st November 2014 | 2200000 | 4Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
128 | Procurement of Office Equipments | 15th - 22nd December 2014 | Accounting Officer | National Shopping | 22nd December 2014 | NA | 1400000 | NA | 23rd December 2014 |  | P-Zeal Business Solution Ltd | 23rd December 2014 | 1398000 | 1Week | NA | Lumpsum |  | Completed | 100% | NA | NA
129 | supply of 2No. Laptops 750GB HDD 5GB RAM Core i3 Processor | 14th - 20th November 2014 | Accounting Officer | National Shopping | 20th November 2014 | NA | 480000 | NA | 20th November 2014 |  | S & F Inter Products & Marketing Ltd | 21st November 2014 | 480000 | 1Week | NA | Lumpsum |  | Completed | 100% | NA | NA
130 | Purchase of Camping Materials for Field Equipment | 18th - 25th AUGUST 2014 | Accounting Officer | National Shopping | 25th August 2014 | NA | 806000 | NA | 3rd September 2014 |  | Habsan Nigeria Enterprises | 4th September 2014 | 780000 | 1Week | NA | Lumpsum |  | Completed | 100% | NA | NA
131 | 2nd Order GPS Re-Observation of 9 No. Pillars (From Pillar 4-5/1 to pillar 4-5/9) located in Kamba, Kebbi State, Nigeria/Aoudou Tounga. Nigeria/Niger International Boundaries | 13th-28th August 2014 | Accounting Officer | National Shopping | 28th August 2014 | NA | 1750000 | NA | 3rd September 2014 |  | Jairo Tereng Ltd | 3rd September 2014 | 1740000 | 4Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
132 | Digital Equipment Maintenance/Overhauling | 7th - 14th April 2014 | Accounting Officer | National Shopping | 14th April 2014 | NA | 1345000 | NA | 6th June 2014 |  | Vickflo Tech & Company | 11th June 2014 | 1336750 | 3Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
133 | Procurement of the under Listed Items: 1No. Trimble R8 External Battery, 1No. Trimble Battery Charger, 8No. Internal Trimble Battery, 4No. Bridge Stone Dweller Vehicle Tyre(205x80x16R), Bridge Stone Dweller Vehicle Tyre 4No.(235x75x16R) | 3rd - 6th June 2014 | Accounting Officer | National Shopping | 6th June 2014 | NA | 1845000 | NA | 16th June 2014 |  | F. Jauni Int'l Ltd | 16th June 2014 | 1800000 | 2Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
134 | Procurement of Mail/file Tracking System for OSGOF. | 5th - 14th November 2014 | Accounting Officer | National Shopping | 14th November 2014 | NA | 2000000 | NA | 18th November 2014 |  | Abiontec Limited | 21st November 2014 | 1968750 | 2Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
135 | Map Completion Exercise on the Boundary Corridor between Latitude 11 and Longitude 03@ E (13Km) | 22nd - 28th August 2014 | Accounting Officer | National Shopping | 28th August 2014 | NA | 1400000 | NA | 3rd September 2014 |  | Vimuk Associates Nig. Ltd | 4th September 2014 | 1370000 | 4Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
136 | Production of Digital Elevation Software and Data for Township Mapping of Benin City Covering 105 SQ KM (DEM) | 22- 31 March 2014 | Accounting Officer | National Shopping | 31st March 2014 | NA | 1500000 | NA | 6th August 2014 |  | Cemba Surveys Nigeria Ltd | 19th August 2014 | 1470000 | 4Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
137 | Field Tracing and Provisional Demarcation, Determination of Anambra/Enugu/Kogi Tripartite Point & Tracing of the Point in Anambra/Kogi ISB. | 25th November - 1st December 2014 | Accounting Officer | National Shopping | 1st December 2014 | NA | 2170000 | NA | 10th December 2014 |  | Marcus Grace Associates | 10th December 2014 | 1934750 | 2Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
138 | Vista Clearing & Maintenace of Interstate Boundary Corridor of Kaduna/Katsina ISB (6m wide). | 24th - 29 th November 2014 | Accounting Officer | National Shopping | 29th November 2014 | NA | 1991500 | NA | 4th December 2014 |  | All-Weather Surveys and Business Ltd | 5th December 2014 | 1815000 | 2Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
139 | Survey/Field Assessment of Boundary Corridor on Nigeria/Cameroon International Boundary(Distance 19Km) in Shamaki,Taraba State , Nigeria/Badji, Adamawa Region, Cameroon Section of the Boundary | 20th - 27th November 2014 | Accounting Officer | National Shopping | 27th November 2014 | NA | 2055000 | NA | 3rd December 2014 |  | Omega Surveys and Mapping Nigeria Ltd | 4th December 2014 | 2050000 | 2Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
140 | Recnnaissance Exercise for Maintenance of 9No. Pillars (from pillar 1-2/1 to pillar 1-2/9) located in Kokwali,Kebbi State, Nigeria/Zanloa Tounga, Dosso region Niger Republic. | 20th - 27th November 2014 | Accounting Officer | National Shopping | 27th November 2014 | NA | 1325000 | NA | 3rd December 2014 |  | All-Weather Surveys and Business Ltd | 4th December 2014 | 1320500 | 2Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
141 | Acquisition of Office Materials for Zonal Offices in OSGOF | 28th November - 5th December 2014 | Accounting Officer | National Shopping | 5th December 2014 | NA | 2000000 | NA | 9th December 2014 |  | Heroic Pace Nigeria Ltd | 9th December 2014 | 1995000 | 1Week | NA | Lumpsum |  | Completed | 100% | NA | NA
142 | Supply of 7No. Inverter Batteries (200 Ah/12V) | 11th - 13th June 2014 | Accounting Officer | National Shopping | 13th June 2014 | NA | 595000 | NA | 16th June 2014 |  | Fem Integrated Concepts Services Ltd | 16th June 2014 | 574000 | 1Week | NA | Lumpsum |  | Completed | 100% | NA | NA
143 | African Geodetic Reference Frame (AFREF), Establishment of Continuos Reference Station in Major Cities, (15KVA Inverter) | 18th - 28th AUGUST 2014 | Accounting Officer | National Shopping | 28th August 2014 | NA | 1770000 | NA | 3rd September 2014 |  | Ufo and Company Ltd | 3rd September 2014 | 1775000 | 1Week | NA | Lumpsum |  | Completed | 100% | NA | NA
144 | Supply and Installation of Plotter-HP CR651A T1300 Design Jet Large Format Colour Inkjet e- Printer. 44" Sizewith Stand, 32GB Memory,160GB Hard Disk USB,Network. | 22nd - 31st March 2014 | Accounting Officer | National Shopping | 31st March 2014 | NA | 2250000 | NA | 25th April 2014 |  | Microchips System Ltd | 29th April 2014 | 2195000 | 4Weeks | NA | Lumpsum |  | Completed | 100% | NA | NA
762455459.12

## Sokoto Rima RBDA
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) : |  | SOKOTO-RIMA RIVER BASIN DEVELOPMENT AUTHORITY
MINISTRY : |  | FEDERAL MINISTRY OF WATER RESOURCES
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2014 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | COMPLETION ZAMFARA AREA OFFICE | 22ND APRIL 2013(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 3RD JUNE 2013 | 12TH AUG 2013 | 20002640.264 | NA | 19TH AUG. 2013 | YES | Zam Builders Nig Ltd | 10TH DEC. 2013 | 49115381.7 | 12MONTHS | 17TH DEC. 2013 | 20002640 | 2014-12-01 | ONGOING | 78% | NA | NA
2 | INGAWA/DALLAJE DAM AND IRRIGATION PROJECT | 20TH APRIL 2009(FEDERAL TENDERS JOURNAL, DAILY TRUST AND NEW NIGERIAN NEWSPAPER) | FEC | NCB | 19TH MAY 2009 | 9TH JUNE 2009 | 35005280.5308 | 7TH SEPT. 2009 | 7TH SEPT. 2009 | YES | Hassuni Nig Ltd | 16th OCT. 2009 | 4307277152.25 | 24 MONTHS | 2010 | 9550880.19 | SETP. 2011 | ONGOING | 50% | NA | NA
3 | RECONSTRUCTION OF DANMARKE DAM/IRRIGATION PROJECT | 20TH APRIL 2009(FEDERAL TENDERS JOURNAL, DAILY TRUST AND NEW NIGERIAN NEWSPAPER) | PTB | NCB | 19TH MAY 2009 | 9TH JUNE 2009 | 2122765.668 | NA | 16TH JUNE 2009 | YES | Akoon Nig Ltd | 9TH JUNE 2009 | 68698178.8 | 3 MONTHS | 2009-06-01 | 1447887.76 | SEPT. 2009 | ONGOING | 65% | NA | NA
4 | CONSTRUCTION OF MASKA EARTH DAM (Design Review) | 25TH JULY 2011(FEDERAL TENDERS JOURNAL, DAILY TRUST AND NEW NIGERIAN NEWSPAPER) | MTB | NCB | 5TH SEPT. 2011 | 17TH OCT. 2011 | 10561056.104 | NA | 24TH OCT. 2011 | YES | Mainiyo Nig Ltd | 31st OCT. 2011 | 206549627.75 | 12 MONTHS | NOV. 2011 | 10334958.45 | NOV. 2012 | ONGOING | 85% | NA | NA
5 | HEADQUATERS DEVELOPMENT | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 17280528.052 | NA | 19TH SEPT. 2014 | YES | PROJECT NINETEEN LTD | 22ND SEPT. 2014 | 15272790.06 | 3 MONTHS | 15/10/14 | 9959767.14 | 15/01/015 | COMPLETED | 100% | NA | NA
6 | MAINTENANCE OF CAPITAL INFRASTRUCTURE( DAM,BOREHOLES,CANALS AND DRAINAGES) | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 14001320.132 | NA | 19TH SEPT. 2014 | YES | MARCX & CONSTRUCTION LTD | 22ND SEPT. 2014 | 11310580.31 | 3 MONTHS | OCT. 2014 | 11034660 | JAN. 2015 | COMPLETED | 100% | NA | NA
7 | COMPLETION AND COMMISSIONING OF SMALL IRRIGATION SCHEMES IN KATSINA STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 6600660 | NA | 19TH SEPT. 2014 | YES | Danyak Nig Ltd | 22ND SEPT. 2014 | 153750000 | 3 MONTHS | OCT. 2014 | 6600659.95 | JAN. 2015 | ONGOING | 85% | NA | NA
8 | CONSTRUCTION OF DUTSI/MASHI WATER SUPPLY | 31ST MAY 2010 (FEDERAL TENDERS JOURNAL, DAILY TRUST AND NEW NIGERIAN NEWSPAPER) | MTB | NCB | 13th OCT. 2010 | 12TH NOV. 2010 | 1240924 | NA | 25TH NOV. 2010 | YES | CLS Nig Ltd | 28TH SEPT. 2010 | 249690723.74 | 12 MONTHS | 2010 | 1240924 | 2011 | ONGOING | 85% | NA | NA
9 | CONSTRUCTION OF TAFKIN SAURI/ABDALLAWA DAM/IRRIGATION PROJECT | 25TH JULY 2011(FEDERAL TENDERS JOURNAL, DAILY TRUST AND NEW NIGERIAN NEWSPAPER) | MTB | NCB | 5TH SEPT. 2011 | 17TH OCT. 2011 | 9240924 | NA | 24TH OCT. 2011 | YES | Fabuzillo Inter. Co. Ltd | 31st OCT. 2011 | 481949874.09 | 24 MONTHS | 2011 | 8905929.74 | 2013 | ONGOING | 75% | NA | NA
10 | OPERATION OF JIBIYA IRRIGATION PROEJCT | 22ND APRIL 2013(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 3RD JUNE 2013 | 12TH AUG 2013 | 13201320 | NA | 19TH AUG. 2013 | YES | Mainiyo Nig Ltd | 10TH DEC. 2013 | 227724310.79 | 6 MONTHS | DEC. 2013 | 10000000 | 2014-06-01 | COMPLETED | 100% | NA | NA
11 | OPERATION AND MAITENANCE OFBAKOLORI IRRIGATION PROJECT | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 11122112.212 | NA | 19TH SEPT. 2014 | YES | JOMAX CONTRACT SERV. LTD | 22ND SEPT. 2014 | 9634786.6 | 3 MONTHS | 24/11/014 | NIL | 2014-02-24 | COMPLETED | 100% | NA | NA
12 | DESIGN AND CONSTRUCTION OF MANGAHI GINGIN-DAMINAWA-AAWA GIDAN NAKWARI 11.8KM RURAL FEEDER ROAD IN MUSAWA LGA, KATSINA (NEW) | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 150000000 | NA | 19TH SEPT. 2014 | YES | MAS CONSTRUCTION NIG LTD | 22ND SEPT. 2014 | 140984470.51 | 12 MONTHS | OCT. 2014 | 54057746 | OCT. 2015 | ONGOING | 80% | NA | NA
13 | SUPPLY OF WATER PUMPING MACHINES AT SOKOTO CENTRAL SENTORIAL DISTRICT | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 150000000 | NA | 19TH SEPT. 2014 | YES | BELLO SABON BIRNI GLOBAL VEN LTD | 22ND SEPT. 2014 | 135831252.38 | 12 MONTHS | OCT. 2014 | 135831252 | OCT. 2015 | COMPLETED | 100% | NA | NA
14 | FILIN GWAMNA SMALL SCALE IRRIGATION SCHEME | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 20000000 | NA | 19TH SEPT. 2014 | YES | MAI-AKWAI JAREDE NIG LTD | 22ND SEPT. 2014 | 17005012.5 | 3 MONTHS | 20/12/014 | 1231996.9 | 2015-03-20 | COMPLETED | 100% | NA | NA
15 | SMALL IRRIGATION SCHEME IN GUMMI LGA, ZAMFARA STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 50000000 | NA | 19TH SEPT. 2014 | YES | AL-AMEEN VENTURE LTD. | 22ND SEPT. 2014 | 41500200 | 3 MONTHS | 16/10/014 | 1500000 | 2015-01-16 | COMPLETED | 100% | NA | NA
16 | PROVISION OF TUBEWELLS AND 300 PUMPING MACHINES TO SAKABA LGA, KEBBI STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 10000000 | NA | 19TH SEPT. 2014 | YES | HUNNINGDALE INTG LTD | 22ND SEPT. 2014 | 7197246 | 3 MONTHS | 20/10/014 | NIL | 2015-01-20 | COMPLETED | 100% | NA | NA
17 | CONSTRUCTION OF SOLAR BOREHOLE AT NO1 ANGWAN MALAMI MASALLACIN KARA,GWAZAGI,ANGWAN KWANO ARGUNGU L.G.A KEBBI STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 10000000 | NA | 19TH SEPT. 2014 | YES | YAHAYA BUHARI& SONS LTD. | 22ND SEPT. 2014 | 6534222.45 | 3 MONTHS | 20/10/014 | NIL | 2015-01-20 | COMPLETED | 100% | NA | NA
18 | CONSTRUCTION OF SOLAR BOREHOLE AT ANGWAN KURBABI,LAYIN SULE NA LAMI DANDUME L.G.A KATSINA STATE. | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 10000000 | NA | 19TH SEPT. 2014 | YES | DANYAK NIG LTD | 22ND SEPT. 2014 | 8255450.97 | 3 MONTHS | 20/10/014 | NIL | 2015-01-20 | COMPLETED | 100% | NA | NA
19 | CONSTRUTION OF SOLAR BOREHOLE AT JIBRI FUNTUA L.G.A KATSINA | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 10000000 | NA | 19TH SEPT. 2014 | YES | JEPATI MULTI LINKS NIG LTD | 22ND SEPT. 2014 | 6887623.31 | 3 MONTHS | 20/10/014 | NIL | 2015-01-20 | COMPLETED | 100% | NA | NA
20 | CONSTRUCTION OF SOLAR BOREHOLE AT LAYIN DANMALIKI, ZOOLALE BAKORI L.G.A KATSINA STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 10000000 | NA | 19TH SEPT. 2014 | YES | HAJIYA SADIYA GEN. ENT LTD | 22ND SEPT. 2014 | 7081692.71 | 3 MONTHS | 20/10/014 | NIL | 2015-01-20 | COMPLETED | 100% | NA | NA
21 | CONSTRUCTION OF SOLAR BOREHOLE AT MINANNATA SOKOTO SOUTH L.G.A SOKOTO STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 10000000 | NA | 19TH SEPT. 2014 | YES | SISOCO CIVIL ENGG CO LTD | 22ND SEPT. 2014 | 8305905.56 | 3 MONTHS | 20/10/014 | 8103322.5 | 2015-01-20 | COMPLETED | 100% | NA | NA
22 | CONSTRUCTION OF ZOGIRIMA POULDER, BIRNI KEBBI | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 30000000 | NA | 19TH SEPT. 2014 | YES | SAIHAL NIG LTD | 22ND SEPT. 2014 | 25001970 | 3 MONTHS | 20/10/014 | NIL | 2015-01-20 | COMPLETED | 100% | NA | NA
23 | SUPPLY OF GRAINS AT YAURI/SHANGA/NGASKI FEDERAL CONSTITUENCY OF KEBBI STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 50000000 | NA | 19TH SEPT. 2014 | YES | GAGI CONSTRUCTION CO. LTD | 22ND SEPT. 2014 | 40122600 | 3 MONTHS | 20/10/014 | NIL | 2015-01-20 | COMPLETED | 100% | NA | NA
24 | SUPPLY OF FERTILIZER AT YAURI/SHANGA/NGASKI FEDERAL CONSTITUENCY OF KEBBI STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 45000000 | NA | 19TH SEPT. 2014 | YES | MAKURYA GLOBAL VENTURES | 22ND SEPT. 2014 | 35186550 | 3 MONTHS | 17/10/014 | 28000000 | 2015-01-17 | COMPLETED | 100% | NA | NA
25 | DRILLING OF BOREHOLES FOR IRRIGATION PURPOSES | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 250000000 | NA | 19TH SEPT. 2014 | YES | NCHETA GLOBAL RES. | 22ND SEPT. 2014 | 230420183.06 | 12 MONTHS | 17/10/014 | 24142388 | 2015-10-17 | COMPLETED | 100% | NA | NA
26 | SSUPPLY OF PUMPING MACHINES FOR IRRIGATION | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 250000000 | NA | 19TH SEPT. 2014 | YES | UMKA NIG LTD | 22ND SEPT. 2014 | 245383762.31 | 12 MONTHS | 17/10/014 | 2000000 | 2015-10-17 | COMPLETED | 100% | NA | NA
27 | OPERATION AND MAITENANCE OF MIDDLE RIMA VALLEY IRRIGATION PROJECT | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 9240924 | NA | 19TH SEPT. 2014 | YES | MARCX & CONSTRUCTION LTD | 22ND SEPT. 2014 | 7468335 | 3 MONTHS | 23/10/014 | NIL | 2015-01-23 | COMPLETED | 100% | NA | NA
28 | OPERATION AND MAITENANCE OF ZAURO PLODER IRRIGATION PROJECT | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 14201980 | NA | 19TH SEPT. 2014 | YES | FIRST GEO MULTI WORKS LTD | 22ND SEPT. 2014 | 10752161.75 | 3 MONTHS | 1/11/014 | NIL | 2015-02-11 | ONGOING | 50% | NA | NA
29 | OPERATION AND MAITENANCE OF NIGER VALLEY IRRIGATION PROJECT | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 9280528.052 | NA | 19TH SEPT. 2014 | YES | ABALAN & CHAMU INVST. LTD | 22ND SEPT. 2014 | 6854505 | 3 MONTHS | 23/10/014 | 5000000 | 2015-01-23 | COMPLETED | 100% | NA | NA
30 | CONSTRUCTION OF BILBIS IRRIGATION SCHEME | 31ST MAY 2010 (FEDERAL TENDERS JOURNAL, DAILY TRUST AND NEW NIGERIAN NEWSPAPER) | PTB | NCB | 13th OCT. 2010 | 12TH NOV. 2010 | 9280128.052 | NA | 19TH NOV. 2010 | YES | Rahusa Ventures Co. Ltd | 28TH SEPT. 2010 | 166620825 | 12 MONTHS | OCT. 2010 | 9252000 | OCT. 2011 | ONGOING | 95% | NA | NA
31 | SHAGARI DAM AND WATER SUPPLY PROJECT | 31ST MAY 2010 (FEDERAL TENDERS JOURNAL, DAILY TRUST AND NEW NIGERIAN NEWSPAPER) | MTB | NCB | 13th OCT. 2010 | 12TH NOV. 2010 | 10403960.4 | NA | 19TH NOV. 2010 | YES | Acelodester Nig Ltd | 25TH NOV. 2010 | 746678780.3 | 24 MONTHS | DEC. 2010 | 10403960 | DEC. 2012 | ONGOING | 40% | NA | NA
32 | ROMO/GINDI WATER SUPPLY PROJECT | 22ND APRIL 2013(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | MTB | NCB | 3RD JUNE 2013 | 12TH AUG 2013 | 214778422.8728 | NA | 19TH AUG. 2013 | YES | Mainiyo Nig Ltd + Consultant | 10TH DEC. 2013 | 528542726.41 | 24 MONTHS | DEC. 2013 | 183836615.55 | DEC. 2015 | ONGOING | 80% | NA | NA
33 | MADDACCI/BAKAYA EROSION CONTROL | 22ND APRIL 2013(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | MTB | NCB | 3RD JUNE 2013 | 12TH AUG 2013 | 40200792.064 | NA | 19TH SEPT. 2014 | YES | Dasna Nig Ltd | 2013 | 664886073.72 | 24 MONTHS | 2013 | 40200792 | 2015 | ONGOING | 40% | NA | NA
34 | OPERATION AND MAINETANCE OF ZOBE IRRIGATION PROJECT | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 12001320.132 | NA | 19TH SEPT. 2014 | YES | SAHAL MULTI LINKS NIG LTD | 22ND SEPT. 2014 | 10187159.45 | 3 MONTHS | 8/10/014 | NIL | 2015-01-08 | COMPLETED | 100% | NA | NA
35 | KAURAN NAMODA WATER SUPPLY PROJECT | 31ST MAY 2010 (FEDERAL TENDERS JOURNAL, DAILY TRUST AND NEW NIGERIAN NEWSPAPER) | MTB | NCB | 13th OCT. 2010 | 12TH NOV. 2010 | 9201320 | NA | 19TH NOV. 2010 | YES | Maron Ronmark Nig Ltd | 25TH NOV. 2010 | 636748184.52 | 24 MONTHS | DEC. 2010 | 9201320 | DEC. 2012 | ONGOING | 80% | NA | NA
36 | 3NO. SOLAR POWERED BOREHOLES AT ANKA/MARAFA LGAS | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 7994665.1066 | NA | 19TH SEPT. 2014 | YES | LEOFLINCH NIG LTD | 22ND SEPT. 2014 | 5839079.53 | 3 MONTHS | OCT. 2014 | NIL | JAN. 2015 | COMPLETED | 100% | NA | NA
37 | CONSTRUCTION OF 250 TUBE WELLS IN DIFFERENT LOCATIONS WITHIN BAGUDO/SURU FED. CONST. | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 7994665.1066 | NA | 19TH SEPT. 2014 | YES | MUNACHIKI MULTI RESOURCES | 22ND SEPT. 2014 | 6597465 | 3 MONTHS | 5/10/014 | NIL | 2015-01-05 | COMPLETED | 100% | NA | NA
38 | 50 NOS. TUBEWELLS, IRRIGATION PUMPS AND MOTOCYCLES FOR FARMERS IN KEBBE LGA | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 11944410.3676 | NA | 19TH SEPT. 2014 | YES | CIMMULA NIG. LTD | 22ND SEPT. 2014 | 9113900.25 | 3 MONTHS | OCT. 2014 | NIL | JAN. 2015 | COMPLETED | 100% | NA | NA
39 | 100 UNITS OF TUBE WELLS AND WATER PUMPS AND CONSTRUCTION OF 4NO SOLAR BOREHOLES AT MASHI/DUTSI FED. CONST. | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 15227933.5364 | NA | 19TH SEPT. 2014 | YES | ANAS TECH. & CONST. WORKS LTD | 22ND SEPT. 2014 | 15248821.23 | 3 MONTHS | 10/10/014 | 13990584.52 | 10/01/015 | COMPLETED | 100% | NA | NA
40 | SIX MOTORISED BOREHOLES AT YABO/SHAGARI FED. CONST. YABO LGA: MOTORISED BOREHOLES 1. BAKALE VILLAGE 2. YABO B WARD 3. BIRNIN RUWA HANDPUMPS: 1. KWAIDAZAQ KILGORI WARD 2. MUZA IN TORANKAWA WARD 3. FAKKA WARD 4. MAGACCI WARD 5. ADAMU VILLAGE SHAGARI LGA: MOTORISED BOREHOLES: 1. DORAWA WARD 2. TAKALAFIYA WARD 3. KALANGU HANDPUMPS: 1. RUGGAR BUDA WARD 2. YANDO WARD 3. GIDAN ARDO 4. BABUJE VILLAGE 5. GOLORUN VILLAGE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 38069833.8409 | NA | 19TH SEPT. 2014 | YES | YALISA GEN ENT. LTD | 22ND SEPT. 2014 | 30897254.06 | 3 MONTHS | 10/10/014 | NIL | 10/01/015 | COMPLETED | 100% | NA | NA
41 | PROVISION OF HANDPUMP BOREHOLES AT BAKORI/DANJA FED. CONST. | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 15227933.5364 | NA | 19TH SEPT. 2014 | YES | GAZEBO MULTI RES LTD | 22ND SEPT. 2014 | 10377083.49 | 3 MONTHS | OCT. 2014 | NIL | JAN. 2015 | COMPLETED | 100% | NA | NA
42 | 15NO. HANDPUMP BOREHOLE IN ZANGO/BAURE FEDERAL CONSTITUENCY | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 5710475.0761 | NA | 19TH SEPT. 2014 | YES | A ' M Nig Ltd | 22ND SEPT. 2014 | 5498797.73 | 3 MONTHS | OCT. 2014 | 5710431.27 | JAN. 2015 | COMPLETED | 100% | NA | NA
43 | PROCUREMENT OF TUBEWELLS IRRIGATION PUMPS, MOTORCYCLES AND FERTILIZERS FOR FARMERS ALONG DAMARI RIVER AND COMPLETION OF KANKIA DAM IN KATSINA STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 50365741 | NA | 19TH SEPT. 2014 | YES | Ben Ladan Int. Ltd | 22ND SEPT. 2014 | 50573615.92 | 3 MONTHS | OCT. 2014 | 20199375 | JAN. 2015 | COMPLETED | 100% | NA | NA
44 | 15NO SOLAR POWERED BOREHOLE AT DOGON DAJI - JABO | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 45683800.6091 | NA | 19TH SEPT. 2014 | YES | GS SHEHU NIG LTD | 22ND SEPT. 2014 | 37354278.58 | 3 MONTHS | OCT. 2014 | 15000000 | JAN. 2015 | COMPLETED | 100% | NA | NA
45 | 15NO SOLAR POWERED BOREHOLE AT SANYINNA - GINDI | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 45683800.6091 | NA | 19TH SEPT. 2014 | YES | YALISA GEN ENTP LTD | 22ND SEPT. 2014 | 37300322 | 3 MONTHS | OCT. 2014 | 13000000 | JAN. 2015 | COMPLETED | 100% | NA | NA
46 | 10NO SOLAR POWERED BOREHOLE AT KEBBE - KUCHI | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 30455867.0727 | NA | 19TH SEPT. 2014 | YES | YALISA GEN. ENT LTD. | 22ND SEPT. 2014 | 24521920.39 | 3 MONTHS | OCT. 2014 | 22500000 | JAN. 2015 | COMPLETED | 100% | NA | NA
47 | PROCUREMENT OF FERTILISER FOR FARMERS JABO | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 5000000 | NA | 19TH SEPT. 2014 | YES | ABALAN & CHAMU INVEST LTD | 22ND SEPT. 2014 | 4325448.75 | 3 MONTHS | OCT. 2014 | NIL | JAN. 2015 | COMPLETED | 100% | NA | NA
48 | SOLAR POWERED/MOTORISED BOREHOLES IN MASKA/KATUKA DISTRICTS | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 50000000 | NA | 19TH SEPT. 2014 | YES | ABDULLAH JABBI & SONS | 22ND SEPT. 2014 | 43057895.37 | 3 MONTHS | OCT. 2014 | NIL | JAN. 2015 | ONGOING | 50% | NA | NA
49 | DRAINAGES AND CULVERTS IN FUNTUA AND DAN'DUME | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 100841900.3045 | NA | 19TH SEPT. 2014 | YES | AKUMAU VENT. NIG LTD. | 22ND SEPT. 2014 | 83106424.5 | 6 MONTHSW | OCT. 2014 | NIL | 2015-04-22 | COMPLETED | 100% | NA | NA
50 | WATER SUPPLY AND SMALL IRRIGATION SCHEME AT MALA - MARINA | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 2664888.3689 | NA | 19TH SEPT. 2014 | YES | NAMIRANIYYAH NIG. LTD | 22ND SEPT. 2014 | 2014425 | 3 MONTHS | 5/11/014 | NIL | 2015-02-05 | COMPLETED | 100% | NA | NA
51 | CONSTRUCTION OF SOLAR POWERED BOREHOLE AT TUNDUN BALA MAIDUNA, MALUMFASHI LGA, MALUMFASHI TOWN, KATSINA STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 5000000 | NA | 19TH SEPT. 2014 | YES | TARSAND GLOBAL INVST. LTD | 22ND SEPT. 2014 | 4585914.9 | 3 MONTHS | 5/11/014 | NIL | 2015-02-05 | COMPLETED | 100% | NA | NA
52 | SOLAR POWER BOREHOLE AT FARUN BALA IN JIBIA LGA, KATSINA STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 5000000 | NA | 19TH SEPT. 2014 | YES | TARSAND GLOBAL INVST. LTD. | 22ND SEPT. 2014 | 4489524.9 | 3 MONTHS | 5/11/014 | NIL | 2015-02-05 | COMPLETED | 100% | NA | NA
53 | CONSTRUCTION OF BOREHOLES IN DIFFERENT LOCATIONS OF ZAMFARA NORTH SENATORIAL DISTRICT | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 20000000 | NA | 19TH SEPT. 2014 | YES | ALMAMBO INTEGRATED RES.NIG LTD | 22ND SEPT. 2014 | 16345600 | 3 MONTHS | 5/11/014 | NIL | 2015-02-05 | COMPLETED | 100% | NA | NA
54 | CONSTRUCTION SOLAR POWERED BOREHOLE AT NUMBER 16 GRA - ABARMA ROAD, GUSAU, ZAMFARA | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 5000000 | NA | 19TH SEPT. 2014 | YES | SULAWAL NIG LTD | 22ND SEPT. 2014 | 4821075 | 3 MONTHS | 5/11/014 | NIL | 2015-02-05 | COMPLETED | 100% | NA | NA
55 | CONSTRUCTION OF SOLAR POWERED BOREHOLE AT RAMALAN MODEL PRIMARY SCHOOL BAKORI | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 5000000 | NA | 19TH SEPT. 2014 | YES | TARSANDS GLO INVT LTD | 22ND SEPT. 2014 | 3943314.9 | 3 MONTHS | 5/11/014 | NIL | 2015-02-05 | COMPLETED | 100% | NA | NA
56 | 25NOS. TUBE WELLS, IRRIGATION PUMPS AND MOTORCYCLES FOR FARMERS IN JIBIA LGA | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 5972205.1838 | NA | 19TH SEPT. 2014 | YES | SEPSAL NIGERIA LTD. | 22ND SEPT. 2014 | 4436733 | 3 MONTHS | 3/11/014 | NIL | 2014-02-03 | COMPLETED | 100% | NA | NA
67 | RURAL WATER SUPPLY PROJECT IN KASTINA NORTH SENATORIAL DISTRICT, KASTINA STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 20000000 | NA | 19TH SEPT. 2014 | YES | RAHUSA VENTURES LTD | 22ND SEPT. 2014 | 16585389.19 | 3 MONTHS | 3/11/014 | 16180867.5 | 2014-02-03 | COMPLETED | 100% | NA | NA
58 | BUNZA WATER SUPPLY PROJECT | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 8000000 | NA | 19TH SEPT. 2014 | YES | Water and Filtraration Ltd | 22ND SEPT. 2014 | 7942222.17 | 3 MONTHS | 3/11/014 | 7942222.17 | 2014-02-03 | ONGOING |  | NA | NA
59 | COMPLETION OF NATU IRRIGATION PROEJCT | 31ST MAY 2010 (FEDERAL TENDERS JOURNAL, DAILY TRUST AND NEW NIGERIAN NEWSPAPER) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 10500299.336 | NA | 19TH SEPT. 2014 | YES | Havage Nig Ltd | 22ND SEPT. 2014 | 230191631.25 | 3 MONTHS | 3/11/014 | 10500299.34 | 2014-02-03 | COMPLETED | 100% | NA | NA
60 | COMPLETION OF MOTORISED BOREHOLES IN FOUR STATES | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 15881188.12 | NA | 19TH SEPT. 2014 | YES | Varoius Constracts | 22ND SEPT. 2014 | 15881188.12 | 3 MONTHS | 3/11/014 | 13900091.5 | 2014-02-03 | ONGOING | 75% | NA | NA
61 | CONSTRUCTION OF BOREHOLES IN DRAUGHT PRONE AREAS OF ZAMFARA STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 4936000 | NA | 19TH SEPT. 2014 | YES | MINISTAKO NIG LTD | 22ND SEPT. 2014 | 4131642.4 | 3 MONTHS | 3/11/014 | NIL | 2014-02-03 | ONGOING | 60% | NA | NA
62 | MINOR IRRIGATION SCHEME IN KEBBI STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 10201320.132 | NA | 19TH SEPT. 2014 | YES | BASHIA GLOBAL LTD | 22ND SEPT. 2014 | 8298288.58 | 3 MONTHS | 12/10/014 | 8252088.58 | 2015-01-12 | COMPLETED | 100% | NA | NA
63 | BATAGARAWA DAM/IRRIGATION PROEJCT | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 9042904.292 | NA | 19TH SEPT. 2014 | YES | SAHEL ASSOCIATES | 22ND SEPT. 2014 | 8983481 | 3 MONTHS | 12/10/014 | 8983481 | 2015-01-12 | COMPLETED | 100% | NA | NA
64 | RAFIN DUMA WATER SUPPLY PROJECT | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 9280528.052 | NA | 19TH SEPT. 2014 | YES | MARINTEC ENGR. NIG. LTD | 22ND SEPT. 2014 | 8456804 | 3 MONTHS | 12/10/014 | NIL | 2015-01-12 | COMPLETED | 100% | NA | NA
65 | YAURI/NGASKI DAM/IRRIGATION PROJECT | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 10241584 | NA | 19TH SEPT. 2014 | YES | Afrina Nig Ltd | 22ND SEPT. 2014 | 8075760 | 3 MONTHS | 12/10/014 | 1617497.86 | 2015-01-12 | COMPLETED | 100% | NA | NA
66 | RE ACQUISITION OF BAKOLORI IRRIGATION PROJECT | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 20000000 | NA | 19TH SEPT. 2014 | YES | Zamfara State Govt. | 22ND SEPT. 2014 | 20000000 | 3 MONTHS | 12/10/014 | NIL | 2015-01-12 | COMPLETED | 100% | NA | NA
67 | MINOR IRRIGATION SCHEME IN ZAMFARA STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 8524372.272 | NA | 19TH SEPT. 2014 | YES | G.S SHEHU NIG. LTD | 22ND SEPT. 2014 | 7084987.27 | 3 MONTHS | 12/10/014 | 2000000 | 2015-01-12 | COMPLETED | 100% | NA | NA
68 | PROVISION OF IRRIGATION PUMPS IN KATSINA STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 |  | NA | 19TH SEPT. 2014 | YES | ANAS TECH. & CONST. WORKS LTD | 22ND SEPT. 2014 | 39737250 | 3 MONTHS | 12/10/014 | 39737250 | 2015-01-12 | COMPLETED | 100% | NA | NA
69 | CONSTRUCTION OF 2 NOS. SMALL IRRIGATION SCHEME AT BAKURA JUNCTION, ZAMFARA WEST SENATORIAL DISTRICT | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | MTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 460000000 | NA | 19TH SEPT. 2014 | YES | Bukata Resources Nig Ltd/Tresda Irrigation Ltd | 22ND SEPT. 2014 | 234312616.13 | 12 MONTHS | 2/12/014 | 330367565.17 | 2015-09-22 | COMPLETED | 100% | NA | NA
| Phase II | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | MTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 |  | NA | 19TH SEPT. 2014 | YES | Tresda Nig Ltd | 22ND SEPT. 2014 | 234312616.13 | 12 MONTHS | 2/12/014 |  | 2015-12-02 | ONGOING | 65% | NA | NA
70 | FARMERS SUPPORT PROGRAMME IN BAKURA, MARADUN & T/MAFARA LGA , ZAMFARA WEST SENATORIAL DISTRICT, ZAMFARA STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 100000000 | NA | 19TH SEPT. 2014 | YES | HIDAN GLOBAL SERVICES LTD | 22ND SEPT. 2014 | 102254512.5 | 12 MONTHS | 9/10/014 | 94936015.23 | 2015-10-09 | COMPLETED | 100% | NA | NA
71 | FARMERS SUPPORT PROGRAMME IN GUMMI, BUKKUYUM & ANKA LGA , ZAMFARA WEST SENATORIAL DISTRICT, ZAMFARA STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 100000000 | NA | 19TH SEPT. 2014 | YES | AL-FURQAAN GLOBAL SERV. MASY NIG LTD. | 22ND SEPT. 2014 | 85134603.75 | 6 MONTHSW | 9/10/014 | 100000000 | 2015-04-09 | COMPLETED | 100% | NA | NA
|  | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 |  | NA | 19TH SEPT. 2014 | YES | MASY NIG LTD | 22ND SEPT. 2014 | 25582541.98 | 3 MONTHS | 9/10/014 |  | 2015-04-09 | COMPLETED | 100% | NA | NA
72 | NATU IRRIGATION PROJECT IN BAKURA | 31ST MAY 2010 (FEDERAL TENDERS JOURNAL, DAILY TRUST AND NEW NIGERIAN NEWSPAPER) | PTB | NCB | 13th OCT. 2010 | 12TH NOV. 2010 | 40000000 | NA | 19TH NOV. 2010 | YES | Havage Nig Ltd | 2010 | 230191631.25 | 12 MONTHS | 2010 | 40000000 | 2011 | COMPLETED | 100% | NA | NA
73 | CONSTRUCTION OF ANKA EARTH DAM (ON-GOING) | 20TH APRIL 2009(FEDERAL TENDERS JOURNAL, DAILY TRUST AND NEW NIGERIAN NEWSPAPER) | MTB | NCB | 13th OCT. 2010 | 12TH NOV. 2010 | 60000000 | NA | 25TH NOV. 2010 | YES | Mimis Nig Ltd | 30th NOV. 2010 | 901267157.7 | 12 MONTHS | DEC. 2010 | 60000000 | DEC. 2011 | ONGOING | 55% | NA | NA
74 | STUDY AND DESIGN OF BABA BRIDGE IN KANKARA TOWN KANKARA LOCAL GOVERNMENT AREA OF KATSINA SOUTH SENATORIAL DISTRICT, KATSINA STATE. | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 15000000 | NA | 19TH SEPT. 2014 | YES | Intratec Consult Nig Ltd | 22ND SEPT. 2014 | 14850000 | 3 MONTHS | OCT. 2014 | NIL | JAN. 2015 | COMPLETED | 100% | NA | NA
75 | CONSTRUCTION OF MUSAWA DAM IN MUSAWA LOCAL GOVERNMENT AREA OF KATSINA SOUTH SENATORIAL DISTRICT, KATSINA STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 75000000 | NA | 19TH SEPT. 2014 | YES | J.S Vision Nig Ltd | 22ND SEPT. 2014 | 116365103.5 | 3 MONTHS | OCT. 2014 | 9345250 | JAN. 2015 | COMPLETED | 100% | NA | NA
76 | CONSTRUCTION OF TUKUSHA DAM IN FASKARI LOCAL GOVERNMENT AREA OF KATSINA SOUTH SENATORIAL DISTRICT, KATSINA STATE. | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 75000000 | NA | 19TH SEPT. 2014 | YES | A.G Vision Nig ltd | 22ND SEPT. 2014 | 111433407.32 | 3 MONTHS | OCT. 2014 | 40887000 | JAN. 2015 | ONGOING | 45% | NA | NA
77 | FARMERS SUPPORT AND EMPOWERMENT PROGRAMME | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | MTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 217840000 | NA | 19TH SEPT. 2014 | YES | IDLE PILLERS TECHN LTD | 22ND SEPT. 2014 | 216991372.5 | 6 MONTHSW | 17/10/014 | 190529010 | 2015-04-17 | COMPLETED | 100% | NA | NA
78 | PROVISION OF TWO THOUSAND (2,000) UNITS OF TUBE WELLS FOR EIGHT (8) LGA | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 90000000 | NA | 19TH SEPT. 2014 | YES | THE LANE CONST CO LTD | 22ND SEPT. 2014 | 89996788.1 | 6 MONTHSW | 17/10/014 | 89996788 | 2015-04-17 | COMPLETED | 100% | NA | NA
79 | THE RE-CONSTRUCTION/IMPROVEMENT OF RAFIN DUMA SMALL EARTH DAM IN GADA LGA OF SOKOTO EAST SENATORIAL DISTRICT | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 20000000 | NA | 19TH SEPT. 2014 | YES | HAJIYA SADIYA GEN. INT. LTD | 22ND SEPT. 2014 | 17205615 | 3 MONTHS | 17/10/014 | 4254649.25 | 2015-01-17 | COMPLETED | 100% | NA | NA
80 | THE PROVISION OF HAND PUMP BOREHOLES FOR EIGHT (8) LGAS OF SOKOTO EAST SENATORIAL DISTRICT | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 16000000 | NA | 19TH SEPT. 2014 | YES | AKOON MULTI SERVICE LTD | 22ND SEPT. 2014 | 12616179.19 | 3 MONTHS | 17/10/014 | 123087467.61 | 2015-01-17 | ONGOING | 50% | NA | NA
81 | CONSTRUCTION OF SOLAR POWERED BOREHOLES IN KEBBI SOUTH SENATORIAL DISTRICT | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 60000000 | NA | 19TH SEPT. 2014 | YES | DASNA INTERNATIONAL COMPANY | 22ND SEPT. 2014 | 50963085 | 3 MONTHS | 17/10/014 | NIL | 2015-01-17 | ONGOING | 50% | NA | NA
82 | YOUTH EMPOWERMENT PROGRAMME IN ELEVEN (II) LGAS OF KATSINA SOUTH SENATORIAL DISTRICT | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 100000000 | NA | 19TH SEPT. 2014 | YES | FASTECH NIG. LTD | 22ND SEPT. 2014 | 83269462.5 | 6 MONTHSW | 21/10/014 | 50173691.1 | 2015-04-21 | COMPLETED | 100% | NA | NA
83 | MAINTENANCE OF TUBE WELLS/REPAIRING OF ELEVEN (II) BORE HOLES IN KATSINA SOUTH SENATORIAL DISTRICT | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 23000000 | NA | 19TH SEPT. 2014 | YES | FASTECH NIGERIA LTD. | 22ND SEPT. 2014 | 18159566.25 | 3 MONTHS | OCT. 2014 | NIL | JAN. 15 | COMPLETED | 100% | NA | NA
84 | CONSTRUCTION OF HAND PUMPS IN ELEVEN LGA OF KATSINA CENTRAL | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 20000000 | NA | 19TH SEPT. 2014 | YES | ALLESTREE VENT. NIG. LTD | 22ND SEPT. 2014 | 16507020.55 | 3 MONTHS | OCT. 2014 | 3000000 | JAN. 15 | COMPLETED | 100% | NA | NA
85 | YOUTH EMPOWERMENT IN KEBBI SOUTH SENATORIAL DISTRICT | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 60000000 | NA | 19TH SEPT. 2014 | YES | BEN LADAN LIMITED | 22ND SEPT. 2014 | 53287100 | 3 MONTHS | 17/10/014 | NIL | 2015-01-17 | COMPLETED | 100% | NA | NA
86 | COMMUNITY BASED WATER SUPPLY WITH PUBLIC STAND AT MAGAJIN GARI B,SOKOTO NORTH,SOKOTO STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 12500000 | NA | 19TH SEPT. 2014 | YES | CIMMULA NIGERIA LTD. | 22ND SEPT. 2014 | 12297044.16 | 3 MONTHS | 2014-11-11 | NIL | 2015-02-11 | ONGOING | 50% | NA | NA
87 | COMMUNITY BASED WATER SUPPLY WITH PUBLIC STAND AT SARKIN ADAR GAIDU,SOKOTO NORTH,SOKOTO STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 12500000 | NA | 19TH SEPT. 2014 | YES | HAJIYA SADIYA GEN. | 22ND SEPT. 2014 | 12298766.16 | 3 MONTHS | 2014-11-11 | NIL | 2015-02-11 | ONGOING | 50% | NA | NA
88 | COMMUNITY BASED WATER SUPPLY WITH PUBLIC STAND AT SARKIN ADAR GIDAN IGWUE,SOKOTO NORTH,SOKOTO STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 12500000 | NA | 19TH SEPT. 2014 | YES | TIMADE ASSOCIATES NIG LTD | 22ND SEPT. 2014 | 10000000.02 | 3 MONTHS | 2014-11-11 | NIL | 2015-02-11 | ONGOING | 50% | NA | NA
89 | COMMUNITY BASED WATER SUPPLY WITH PUBLIC STAND AT GABI B,,SOKOTO SOUTH,SOKOTO STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 12500000 | NA | 19TH SEPT. 2014 | YES | CIMMULA NIGERIA LTD. | 22ND SEPT. 2014 | 12298228.03 | 3 MONTHS | 2014-11-11 | NIL | 2015-02-11 | ONGOING | 60% | NA | NA
90 | COMMUNITY BASED WATER SUPPLY WITH PUBLIC STAND AT SARKIN ZAMFARA B ,SOKOTO SOUTH,SOKOTO STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 12500000 | NA | 19TH SEPT. 2014 | YES | CIMMULA NIGERIA LTD. | 22ND SEPT. 2014 | 12296828.91 | 3 MONTHS | 2014-11-11 | NIL | 2015-02-11 | ONGOING | 60% | NA | NA
91 | COMMUNITY BASED WATER SUPPLY WITH PUBLIC STAND AT SARKIN ADAR KAFAR ATIKU ,SOKOTO SOUTH,SOKOTO STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 12500000 | NA | 19TH SEPT. 2014 | YES | HAJIYA SADIYA GEN. ENT. LTD | 22ND SEPT. 2014 | 9734869.6 | 3 MONTHS | 2014-11-11 | NIL | 2015-02-11 | ONGOING | 50% | NA | NA
92 | COMMUNITY BASED WATER SUPPLY WITH PUBLIC STAND AT TUDUN WADA A ,SOKOTO SOUTH,SOKOTO STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 12500000 | NA | 19TH SEPT. 2014 | YES | AUTA INTGR.SERVICE LTD. | 22ND SEPT. 2014 | 12295655.03 | 3 MONTHS | 2014-11-11 | NIL | 2015-02-11 | ONGOING | 65% | NA | NA
93 | COMMUNITY BASED WATER SUPPLY WITH PUBLIC STAND AT TAFAWA BALEWA ROAD RIJIA B,SOKOTO SOUTH,SOKOTO STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 12500000 | NA | 19TH SEPT. 2014 | YES | AUTA INTEGRAL NIG. LTD | 22ND SEPT. 2014 | 11758219.59 | 3 MONTHS | 2014-11-11 | NIL | 2015-02-11 | ONGOING | 55% | NA | NA
94 | PROVISION OF MOTOR CYCLE(KASIA 125 MODEL) TO KWARE/WAMAKKO L.G.A SOKOTO STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 56000000 | NA | 19TH SEPT. 2014 | YES | A A MAIDOYA CO NIG LTD | 22ND SEPT. 2014 | 54922651.88 | 3 MONTHS | OCT. 2014 | NIL | JAN. 2015 | COMPLETED | 100% | NA | NA
95 | FARMERS SUPPORT/EMPOWERMENT PROGRAMME IN GADA/GORONYO FED CONST IN SOKOTO STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 100288599 | NA | 19TH SEPT. 2014 | YES | BHIZA UNIV. INVST. LTD | 22ND SEPT. 2014 | 99069697.67 | 3 MONTHS | OCT. 2014 | NIL | JAN. 2015 | COMPLETED | 100% | NA | NA
96 | COMMUNITY BASED WATER SUPPLY POST AT SHIYYAR ALASAWA SALAME ,GWADABAWA L.G. SOKOTO | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 21750000 | NA | 19TH SEPT. 2014 | YES | DOGON MARKE INVEST. LTD | 22ND SEPT. 2014 | 16960408.5 | 3 MONTHS | OCT. 2014 | 8952724.38 | JAN. 2015 | COMPLETED | 100% | NA | NA
97 | COMMUNITY BASED WATER SUPPLY POST (SOLAR POWERED) AT TAMBAGAR,GWADABAWA L.G. SOKOTO SATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 21750000 | NA | 19TH SEPT. 2014 | YES | DOGON MARKE INVST LTD | 22ND SEPT. 2014 | 15646522.5 | 3 MONTHS | OCT. 2014 | NIL | JAN. 2015 | COMPLETED | 100% | NA | NA
98 | COMMUNITY BASED WATER SUPPLY POST (SOLAR POWERED)AT DARNA TSOLAWA VILLAGE,IIELA L.G. SOKOTO SATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 21750000 | NA | 19TH SEPT. 2014 | YES | DOGON MARKE INVEST LTD | 22ND SEPT. 2014 | 16368471 | 3 MONTHS | OCT. 2014 | NIL | JAN. 2015 | COMPLETED | 100% | NA | NA
99 | COMMUNITY BASED WATER SUPPLY POST (MOTORISED)AT DARNA TSOLAWA VILLAGE,IIELA L.G. SOKOTO SATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 17850000 | NA | 19TH SEPT. 2014 | YES | HANDIN KAI NIGERIA LIMITED. | 22ND SEPT. 2014 | 14175692.34 | 3 MONTHS | OCT. 2014 | NIL | JAN. 2015 | COMPLETED | 100% | NA | NA
100 | HANDPUMP BOREHOLE AT SABON GARIN HUCHI VILLAGE, GWADABAWA,SOKOTO | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 1700000 | NA | 19TH SEPT. 2014 | YES | ARAB & PARTNERS | 22ND SEPT. 2014 | 1501637.81 | 3 MONTHS | OCT. 2014 | NIL | JAN. 2015 | COMPLETED | 100% | NA | NA
101 | FARMERS SUPPORT/EMPOWERMENT PROGRAMME IN GADA/GORONYO FED CONST IN SOKOTO STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 1700000 | NA | 19TH SEPT. 2014 | YES | ARABS & PARTNERS LTD | 22ND SEPT. 2014 | 1436793.75 | 3 MONTHS | OCT. 2014 | NIL | JAN. 2015 | COMPLETED | 100% | NA | NA
102 | HANDPUMP BOREHOLE AT G.G.S.S ILLELA L.G.A,SOKOTO STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 1700000 | NA | 19TH SEPT. 2014 | YES | ARAB & PARTNERS LTD | 22ND SEPT. 2014 | 1203516.56 | 3 MONTHS | OCT. 2014 | NIL | JAN. 2015 | COMPLETED | 100% | NA | NA
103 | SUPPLY OF 19 UNITS OF TRICYCLE TO GWADABAWA/ILELA L.G.A SOKOTO STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 11400000 | NA | 19TH SEPT. 2014 | YES | ARABS & PARTNERS LTD | 22ND SEPT. 2014 | 8810720.63 | 3 MONTHS | OCT. 2014 | NIL | JAN. 2015 | COMPLETED | 100% | NA | NA
104 | SUPPLY OF 22 SEWING MACHINE TO GWADABAWA/ILELA L.G.A SOKOTO STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 660000 | NA | 19TH SEPT. 2014 | YES | ARABS & PARTNERS LTD | 22ND SEPT. 2014 | 594090 | 3 MONTHS | OCT. 2014 | NIL | JAN. 2015 | COMPLETED | 100% | NA | NA
105 | PROVISION OF SOLAR STREET LIGHT AT BIRNIN KEBBI/KALGO/BUNZA FED CONST OF KEBBI STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 36000000 | NA | 19TH SEPT. 2014 | YES | SAVANA SCAPE REALTORS LTD. | 22ND SEPT. 2014 | 30345487 | 3 MONTHS | OCT. 2014 | NIL | JAN. 2015 | COMPLETED | 100% | NA | NA
106 | SOLAR STREET LIGHT IN KAMBA, KEBBI STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 14000000 | NA | 19TH SEPT. 2014 | YES | GAMZAKI GLOBAL VENT. NIG. LTD | 22ND SEPT. 2014 | 10524436 | 3 MONTHS | 20/10/014 | NIL | 2015-01-20 | COMPLETED | 100% | NA | NA
107 | SKILL ACQUISITION TRAINING AND EMPOWERMENT ON VARIOUS TRADE FOR YOUTH DEVELOPMENT AND WOMEN IN KANGIWA,KEBBI STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 10000000 | NA | 19TH SEPT. 2014 | YES | ALH.MUH’D ABDULLAHI & SON LTD | 22ND SEPT. 2014 | 7428750 | 3 MONTHS | 17/10/014 | NIL | 2015-01-17 | COMPLETED | 100% | NA | NA
108 | SOLAR STREET LIGHT IN KWABKWABA/TUNGAR, KEBBI STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 7000000 | NA | 19TH SEPT. 2014 | YES | GALUMMA INVST. NIG. LTD | 22ND SEPT. 2014 | 4129696.2 | 3 MONTHS | 17/10/014 | NIL | 2015-01-17 | COMPLETED | 100% | NA | NA
109 | SKILL ACQUISITION TRAINING AND EMPOWERMENT ON VARIOUS TRADE FOR YOUTH DEVELOPMENT AND WOMEN IN KAMBA,KEBBI STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 10000000 | NA | 19TH SEPT. 2014 | YES | GAMZAKI MOTORS B/KEBBI | 22ND SEPT. 2014 | 8110200 | 3 MONTHS | 17/10/014 | NIL | 2015-01-17 | COMPLETED | 100% | NA | NA
110 | SMALL SCALE IRRIGATION PROJECT IN KAMBA,KEBBI STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 15000000 | NA | 19TH SEPT. 2014 | YES | BARAKA GLOBAL RES. CO LTD. | 22ND SEPT. 2014 | 9102400 | 3 MONTHS | 20/10/014 | NIL | 2015-01-20 | COMPLETED | 100% | NA | NA
112 | SOLAR STREET LIGHT IN FINGILLAH/GORU, KEBBI STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 5000000 | NA | 19TH SEPT. 2014 | YES | EMCHEZ HERITAGE LTD. | 22ND SEPT. 2014 | 4331631.36 | 3 MONTHS | 2014-10-01 | NIL | 2015-01-01 | COMPLETED | 100% | NA | NA
113 | PROCUMENT AND DISTRIBUTION OF FERTILIZER AT ZURU/FAKA/SAKABA/DANKO-WASAGU IN KEBBI STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 100000000 | NA | 19TH SEPT. 2014 | YES | AMALAN MARKETING &CONST LTD | 22ND SEPT. 2014 | 84969150 | 6 MONTHSW | 2014-10-01 | 47441000 | 2015-04-01 | COMPLETED | 100% | NA | NA
114 | SOLAR POWERED STREET LIGHT IN MAZA MAZA ,JANBIRNI,ADAI,SAKABA L.G.A, KEBBI STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 5000000 | NA | 19TH SEPT. 2014 | YES | BELFORT INTL LTD | 22ND SEPT. 2014 | 3458847 | 3 MONTHS | 2014-10-20 | NIL | 2015-01-20 | COMPLETED | 100% | NA | NA
115 | IRRIGATION PUMPING MACHINE AT YAURI,SHANGA,NGASKI OF KEBBI STATE. | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 25000000 | NA | 19TH SEPT. 2014 | YES | MUJAYA ENGINEERING SERVICES | 22ND SEPT. 2014 | 21020340.6 | 3 MONTHS | 17/10/014 | 21001965.6 | 2015-01-17 | COMPLETED | 100% | NA | NA
116 | SUPPLY OF MOTOR CYCLES IN YAURI,SHANGA,NGASKI OF KEBBI STATE. | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 25000000 | NA | 19TH SEPT. 2014 | YES | MAIGERO GLOBAL VENTURES | 22ND SEPT. 2014 | 21051450 | 3 MONTHS | 17/10/014 | 20947500 | 2015-01-17 | COMPLETED | 100% | NA | NA
117 | PROVISON OF IRRIGATION PUMPING MACHINE AT BAGUDO/SURU, KEBBI STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 25000000 | NA | 19TH SEPT. 2014 | YES | CIMMULA NIG LTD | 22ND SEPT. 2014 | 19689075 | 3 MONTHS | 17/10/014 | 10902168.1 | 2015-01-17 | COMPLETED | 100% | NA | NA
118 | PROVISON OF MOTOR CYCLES AT BAGUDO/SURU, KEBBI STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 20000000 | NA | 19TH SEPT. 2014 | YES | DANYAK NIG LTD | 22ND SEPT. 2014 | 18251100 | 3 MONTHS | 17/10/014 | 11153956.56 | 2015-01-17 | COMPLETED | 100% | NA | NA
119 | PROVISON OF SOLAR STREET LIGHTS AT BAGUDO/SURU, KEBBI STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 20000000 | NA | 19TH SEPT. 2014 | YES | MATAZU VENTURES LTS | 22ND SEPT. 2014 | 15042846 | 3 MONTHS | 22/10/014 | NIL | 2014-12-22 | COMPLETED | 100% | NA | NA
120 | PROVISION OF SOLAR STREET LIGHT AT ALIERO/GWANDU/JEGA FED CONST OF KEBBI STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 42000000 | NA | 19TH SEPT. 2014 | YES | SHAFF COMMUNICATION LTD | 22ND SEPT. 2014 | 31597314 | 3 MONTHS | 16/10/014 | NIL | 2015-01-16 | COMPLETED | 100% | NA | NA
121 | PROVISION OF ACCESS ROAD TO MAMMAWA FROM GANJE JUNCTION IN GWANDU L.G.A OF KEBBI STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 10000000 | NA | 19TH SEPT. 2014 | YES | SHAFF COMMUNICATION LTD | 22ND SEPT. 2014 | 6778800 | 3 MONTHS | OCT. 14 | NIL | JAN. 15 | COMPLETED | 100% | NA | NA
122 | PROVISION OF CLASSROOMS AT MADARASATU LIYA'U SUNNA DANWARAI,ALIERO L.G.A KEBBI STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 9000000 | NA | 19TH SEPT. 2014 | YES | USMANIYA NIG. LTD | 22ND SEPT. 2014 | 8347332 | 3 MONTHS | 2014-10-25 | 4000000 | 2015-01-25 | COMPLETED | 100% | NA | NA
123 | PROVISION OF CLASSROOMS AT SHEIKH AL-FAUZAN ISLAMIC CENTRE ALIERO,ALIERO L.G.A KEBBI STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 10000000 | NA | 19TH SEPT. 2014 | YES | IDI-ATO GLOBAL INVST. LTD | 22ND SEPT. 2014 | 8777871.9 | 3 MONTHS | 2014-10-25 | NIL | 2015-01-25 | COMPLETED | 100% | NA | NA
124 | CONSTRUCTION OF BOREHOLE AT NGASKI, KEBBI STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 14000000 | NA | 19TH SEPT. 2014 | YES | MALAMI MINANATA AND SONS LTD | 22ND SEPT. 2014 | 10903882.5 | 3 MONTHS | 2014-10-25 | NIL | 2015-01-25 | COMPLETED | 100% | NA | NA
125 | FARMER'S SUPPORT PROGRAMME IN GUMMI/BUKKUYUM FEDERAL CONSTITUENCY, ZAMFARA STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 100000000 | NA | 19TH SEPT. 2014 | YES | AMORE GLO MARCHANDIS NID LTD | 22ND SEPT. 2014 | 85100000 | 6 MONTHS | 17/10/014 | NIL | 2015-01-17 | COMPLETED | 100% | NA | NA
126 | COMPLETION OF TRADE AND SKILL ACQUISITION CENTRE IN KANKARA TOWN, KANKARA L.G.A KATSINA STATE | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 30000000 | NA | 19TH SEPT. 2014 | YES | SKYLOLO NIG LTD | 22ND SEPT. 2014 | 97367935.6 | 3 MONTHS | 16/10/014 | 10422970 | 2015-01-16 | ONGOING | 67% | NA | NA
127 | PROCUREMNT OF PUMING MACHINES FOR KEBBI STATES | 16TH JUNE 2014(FEDERAL TENDERS JOURNAL, PAOPLES DAILY AND DAILY SUN) | PTB | NCB | 4TH AUGUST, 2014 | 8TH SEPT. 2014 | 80000000 | NA | 19TH SEPT. 2014 | YES | YAHAYA BUHARI& SONS LTD. | 22ND SEPT. 2014 | 79521750 | 6 MONTHS | 11/11/014 | 79521750 | 2015-05-11 | COMPLETED | 100% | NA | NA
[11 empty] | 128 |  | 13819448326.13

## DMO
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) : |  | DEBT MANAGEMENT OFFICE
MINISTRY : |  | FEDERAL MINISTRY OF FINANCE
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014(NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2014 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | Procurement & Installation of Office Furnitures (Lot 1) | September 17, 2014 | Parastatal Tenders Board | National Competitive Bidding | October 29, 2014 | November 20, 2014 | 8460000 | N/A | November 21, 2014 | Woods & Frames Limited | Woods & Frames Limited | Novermber 24, 2014 | 8347395 | 3 weeks | Novermber 24, 2014 | 7552405 | December 15, 2014 | completed | 100% completed | N/A | N/A | Contract awarded and satisfactorily completed
2 | Procurement & Installation of Computer Systems & Accessories (Lot 2) | September 17, 2014 | Parastatal Tenders Board | National Competitive Bidding | October 29, 2014 | November 20, 2014 | 4932580 | N/A | November 21, 2014 | Hasob Integrated Services Limited | Hasob Integrated Services Limited | Novermber 24, 2014 | 4277468.31 | 3 Weeks | Novermber 24, 2014 | 3870090.37 | December 15, 2014 | completed | 100% completed | N/A | N/A | Contract awarded and satisfactorily completed
3 | Procurement & Installation of Computer Software (Lot 3) | September 17, 2014 | Parastatal Tenders Board | National Competitive Bidding | October 29, 2014 | November 20, 2014 | 11000000 | N/A | November 21, 2014 | Nghamlin Limited | Nghamlin Limited | No Contract was awarded | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No contract was awarded because funds released was inadequate
| TOTAL | [11 empty] | 12624863.31

## ENERGY COMM
2014 ECN CONSTITUENCY/INTERVENTION PROJECTS
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) : |  | ENERGY COMMISSION OF NIGERIA
MINISTRY : |  | MINISTRY OF SCIENCE AND TECHNOLOGY
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2014 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | SOLAR POWERED STREETLIGHTS IYEWA SOUTH, OGUN STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 60000000 | 2014-11-17 | 2014-11-17 | √ | BRIDGE OIL & ENERGY LTD | 2014-11-19 | 17160000 | 30DAYS | 2014-11-26 | 17160000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
2 | SOLAR POWERED STREETLIGHTS IPOKIA, OGUN STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 60000000 | 2014-11-17 | 2014-11-17 | √ | PYZ INTERACTIVE CONCEPT LTD | 2014-11-19 | 17160000 | 30DAYS | 2014-11-26 | 17160000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
| SOLAR POWERED STREETLIGHTS AKOKO, ONDO STATE (60,000,000.00) | [5 empty] | 60000000
3 | SOLAR POWERED STREETLIGHTS IN IKUN, ONDO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 15000000 | 2014-11-17 | 2014-11-17 | √ | BUMMASON INVESTMENT LTD | 2014-11-19 | 3900000 | 30DAYS | 2014-11-26 | 3900000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
4 | SOLAR POWERED STREETLIGHTS IN ILEPA, ONDO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 15000000 | 2014-11-17 | 2014-11-17 | √ | PRECIOUS & VALUE INTL LTD | 2014-11-19 | 3900000 | 30DAYS | 2014-11-26 | 3900000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
5 | SOLAR POWERED STREETLIGHTS IN ARIGIDI, ONDO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 10000000 | 2014-11-17 | 2014-11-17 | √ | DUMBY GLOBAL VENTURES LTD | 2014-11-19 | 9360000 | 30DAYS | 2014-11-26 | 9360000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
6 | SOLAR POWERED STREETLIGHTS IN SOSAN, ONDO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 10000000 | 2014-11-17 | 2014-11-17 | √ | NUTEK CORPORATE SOLUTION LTD | 2014-11-19 | 7020000 | 30DAYS | 2014-11-26 | 7020000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
7 | SOLAR POWERED STREETLIGHTS IN ISE, ONDO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 10000000 | 2014-11-17 | 2014-11-17 | √ | DUWAN COMPANY LTD | 2014-11-19 | 2340000 | 30DAYS | 2014-11-26 | 2340000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
8 | SOLAR POWERED STREETLIGHTS KUDAN, KADUNA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 50000000 | 2014-11-17 | 2014-11-17 | √ | SEGABA INTL CO. LTD | 2014-11-19 | 14040000 | 30DAYS | 2014-11-26 | 14040000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
| SOLAR POWERED STREETLIGHTS IN VARIOUS LOCATIONS NATIONA WIDE (200,000,000.00) | [5 empty] | 200000000
9 | SOLAR POWERED STREETLIGHTS AT IPOKIA, OGUN STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 50000000 | 2014-11-17 | 2014-11-17 | √ | VASALVA VENTURES LTD | 2014-11-19 | 14040000 | 30DAYS | 2014-11-26 | 14040000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
10 | SOLAR POWERED STREETLIGHTS AT DAWAKIN KUDU TOWN, DAWAKIN KUDU/WARAWA, KANO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 30000000 | 2014-11-17 | 2014-11-17 | √ | AJULO JAB NIG LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
11 | SOLAR POWERED STREETLIGHTS AT OWODE-YEWA, YEWA SOUTH, OGUN STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 50000000 | 2014-11-17 | 2014-11-17 | √ | MACY,S MULTI VENTURES SERVICES LTD | 2014-11-19 | 14040000 | 30DAYS | 2014-11-26 | 14040000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
12 | SOLAR POWERED STREETLIGHTS AT MAZUGAL WARD, DALA, KANO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 25000000 | 2014-11-17 | 2014-11-17 | √ | WRITES ENERGY LTD | 2014-11-19 | 11700000 | 30DAYS | 2014-11-26 | 11700000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
13 | SOLAR POWERED STREETLIGHTS AT BALANGA, GOMBE STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 25000000 | 2014-11-17 | 2014-11-17 | √ | 4 PLUS SOLAR ENERGY LTD | 2014-11-19 | 11700000 | 30DAYS | 2014-11-26 | 11700000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
14 | SOLAR POWERED STREETLIGHTS AT MUSHIN/ISOLO, LAGOS STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | SAMCOSIN GLOBAL CONCEPT LTD | 2014-11-19 | 5460000 | 30DAYS | 2014-11-26 | 5460000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
| PROVISION OF SOLAR-POWERED STREETLIGHTS IN GWARZO LGA, KANO NORTH SENATORIAL DISTRICT, KANO STATE (80,000,000.00) | [5 empty] | 80000000
15 | PROVISION OF SOLAR-POWERED STREETLIGHTS IN GOBIRAWA, GWARZO LGA, KANO NORTH SENATORIAL DISTRICT, KANO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 41000000 | 2014-11-17 | 2014-11-17 | √ | FHG NIG LTD | 2014-11-19 | 11700000 | 30DAYS | 2014-11-26 | 11700000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
16 | PROVISION OF SOLAR-POWERED STREETLIGHTS IN MADADI, GWARZO LGA, KANO NORTH SENATORIAL DISTRICT, KANO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 39000000 | 2014-11-17 | 2014-11-17 | √ | EKOFIELD MULTICONCEPT LTD | 2014-11-19 | 10920000 | 30DAYS | 2014-11-26 | 10920000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
17 | CONSTRUCTION OF SOLAR POWERED STREET LIGHT IN VARIOUS HAMLETS IN AMABOKWU, AKU, IGBO ETITI LGA, ENUGU STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 10000000 | 2014-11-17 | 2014-11-17 | √ | SUNERGY POWER TECHNOLOGY LTD | 2014-11-19 | 2340000 | 30DAYS | 2014-11-26 | 2340000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
18 | SOLAR POWER STREET LIGHT IN ILE-OLUIJI / OKEIGBO & ODIGBO FEDERAL CONSTITUENCY, ONDO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 10000000 | 2014-11-17 | 2014-11-17 | √ | EWAKITTY NIGERIA LTD | 2014-11-19 | 2340000 | 30DAYS | 2014-11-26 | 2340000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
| SOLAR POWERED STREETLIGHT AT ORHIONMWON/UHUNMWODE FEDERAL CONSTITUENCY (N100,000,000.00) | [5 empty] | 100000000
19 | SOLAR POWERED STREETLIGHT AT ORHIONMWON/UHUNMWODE FEDERAL CONSTITUENCY 1 | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 50000000 | 2014-11-17 | 2014-11-17 | √ | BALISHA CONCEPT LTD | 2014-11-19 | 14040000 | 30DAYS | 2014-11-26 | 14040000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
20 | SOLAR POWERED STREETLIGHT AT ORHIONMWON/UHUNMWODE FEDERAL CONSTITUENCY 2 | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 25000000 | 2014-11-17 | 2014-11-17 | √ | MBK STANDARD VISSION LTD | 2014-11-19 | 7020000 | 30DAYS | 2014-11-26 | 7020000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
21 | SOLAR POWERED STREETLIGHT AT ORHIONMWON/UHUNMWODE FEDERAL CONSTITUENCY 3 | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 25000000 | 2014-11-17 | 2014-11-17 | √ | VENCHUDIS NIG LTD | 2014-11-19 | 7020000 | 30DAYS | 2014-11-26 | 7020000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
22 | INSTALLATION OF SOLAR STREET LIGHT AT OWERRI NORTH LGA, IMO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 30000000 | 2014-11-17 | 2014-11-17 | √ | BASLEN VENTURES LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
23 | INSTALLATION OF SOLAR STREET LIGHT AT AMUDI OBIZI ROAD, EZINIHITTE LGA, IMO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 15000000 | 2014-11-17 | 2014-11-17 | √ | CIRCLE CONTRACTORS LTD | 2014-11-19 | 7800000 | 30DAYS | 2014-11-26 | 7800000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
24 | INSTALLATION OF SOLAR STREET LIGHT AT UMUEZEALA ROAD, UMUMBIRI, AHIAZUMBAISE LGA, IMO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 15000000 | 2014-11-17 | 2014-11-17 | √ | MERCANTILE INFORMATION SYSTEMS LTD | 2014-11-19 | 3900000 | 30DAYS | 2014-11-26 | 3900000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
25 | INSTALLATION OF SOLAR STREET LIGHT AT IHEWUORIE AHIAZUMBAISE LGA, IMO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | FUSE ENGINEERS | 2014-11-19 | 5460000 | 30DAYS | 2014-11-26 | 5460000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
26 | INSTALLATION OF SOLAR STREET LIGHT AT ONUIMO LGA, IMO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 30000000 | 2014-11-17 | 2014-11-17 | √ | ADAVIC INTEGRATED SERVICES LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
27 | INSTALLATION OF SOLAR STREET LIGHT AT MBUTU SECONDARY SCHOOL, MBUTU ABOH MBAISE LGA, IMO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | CEDAR CREED LTD | 2014-11-19 | 5460000 | 30DAYS | 2014-11-26 | 5460000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
28 | INSTALLATION OF SOLAR STREET LIGHT AT AWALA IDEATO SOUTH LGA, IMO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 30000000 | 2014-11-17 | 2014-11-17 | √ | AMKORPART TECH LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
29 | INSTALLATION OF SOLAR STREET LIGHT AT KATAGUM FEDERAL CONSTITUENCY, BAUCHI STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 30000000 | 2014-11-17 | 2014-11-17 | √ | AKUSTAN ENGINEERING LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
30 | INSTALLATION OF SOLAR STREET LIGHT AT NEW FOBUR JOS EAST, PLATEAU STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | DAYLIGHT ENERGY (OIL & GAS) INDUSTRY LTD | 2014-11-19 | 5460000 | 30DAYS | 2014-11-26 | 5460000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
| SOLAR STREET LIGHT IN AZINIFE NNEWI SOUTH L.G.A ANAMBRA STATE (N100,000,000.00) | [5 empty] | 100000000
31 | SOLAR POWER STREETLIGHT IN OSUMENYI TOWN, AZINIFE NNEWI SOUTH L.G.A,ANAMBRA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 50000000 | 2014-11-17 | 2014-11-17 | √ | POWER CLIET LIMITED | 2014-11-19 | 14040000 | 30DAYS | 2014-11-26 | 14040000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
32 | SOLAR POWER STREETLIGHT IN UMUMMAN VILLAGE,AZINIFE NNEWI SOUTH L.G.A, ANAMBRA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 50000000 | 2014-11-17 | 2014-11-17 | √ | SKATEL ESTATE LTD | 2014-11-19 | 14040000 | 30DAYS | 2014-11-26 | 14040000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
| SOLAR STREET LIGHT IN AMICHI TOWN NNEWI SOUTH L.G.A ANAMBRA STSTE (N200,000,000.00) | [5 empty] | 200000000
33 | SOLAR POWER STREETLIGHT IN AMICHI TOWN,AMICHI TOWN NNEWI SOUTH L.G.A ANAMBRA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 50000000 | 2014-11-17 | 2014-11-17 | √ | UNIQUE-LIFE PROPERTIES LTD | 2014-11-19 | 14040000 | 30DAYS | 2014-11-26 | 14040000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
34 | SOLAR POWER STREETLIGHT IN OKPOKOLO VILLAGE, NNEWI SOUTH L.G.A ANAMBRA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 50000000 | 2014-11-17 | 2014-11-17 | √ | FAB HENR NIGERIA LTD | 2014-11-19 | 14040000 | 30DAYS | 2014-11-26 | 14040000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
35 | SOLAR POWER STREETLIGHT IN OBIOFIA,VILLAGE, NNEWI SOUTH L.G.A, ANAMBRA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 50000000 | 2014-11-17 | 2014-11-17 | √ | FECHTON & SONS INVESTMENT | 2014-11-19 | 14040000 | 30DAYS | 2014-11-26 | 14040000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
36 | SOLAR POWER STREETLIGHT IN UMUNWEYI VILLAGE, NNEWI SOUTH L.G.A, ANAMBRA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 50000000 | 2014-11-17 | 2014-11-17 | √ | SUNSHINE ESTATE & INVWSTMENT LTD | 2014-11-19 | 14040000 | 30DAYS | 2014-11-26 | 14040000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
| SOLAR PILOT PROJECT IN KADUNA STATE (N200,000,000.00) | [5 empty] | 200000000
37 | SOLAR POWER STREETLIGHT IN KUDAN, KADUNA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 50000000 | 2014-11-17 | 2014-11-17 | √ | DIGITAL GEOPATIAL TECHNOLIGY SOLUTION LTD | 2014-11-19 | 14040000 | 30DAYS | 2014-11-26 | 14040000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
38 | SOLAR POWER STREETLIGHT IN MAKARF KADUNA STATEI | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 50000000 | 2014-11-17 | 2014-11-17 | √ | KENAZOD INVESTMENT LTD | 2014-11-19 | 14040000 | 30DAYS | 2014-11-26 | 14040000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
39 | SOLAR POWER STREETLIGHT IN HUNKUYI, KADUNA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 50000000 | 2014-11-17 | 2014-11-17 | √ | LANSOJ NIGERIA LIMITED | 2014-11-19 | 14040000 | 30DAYS | 2014-11-26 | 14040000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
40 | SOLAR POWER STREETLIGHT IN GUBUCI, KADUNA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 50000000 | 2014-11-17 | 2014-11-17 | √ | MP FRED LOGISTIC LIMITED | 2014-11-19 | 14040000 | 30DAYS | 2014-11-26 | 14040000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
| SOLAR PILOT PROJECT IN PLATEAU STATE (N100,000,000.00) | [5 empty] | 100000000
41 | SOLAR POWERE STREETLIGHT IN WASE, WASE LGA, PLATEAU STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 50000000 | 2014-11-17 | 2014-11-17 | √ | CATCHMATE VENTURES LTD | 2014-11-19 | 14040000 | 30DAYS | 2014-11-26 | 14040000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
42 | SOLAR POWER STREETLIGHT IN UBEL, OPPOSITE UNIVERSITY OF JOS PERMANENT SITE, JOS NORTH LGA, PLATEAU STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 50000000 | 2014-11-17 | 2014-11-17 | √ | COMPASS ESTATE MANAGEMENT LTD | 2014-11-19 | 14040000 | 30DAYS | 2014-11-26 | 14040000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
43 | INSTALLATION OF SOLAR POWERED STREETLIGHT IN SOKO NORTH/SOUTH FEDERAL CONSTITUENCY, DELTA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | ODUNWA ENGINEERING AND CONSTRUCTION LTD | 2014-11-19 | 5460000 | 30DAYS | 2014-11-26 | 5460000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
| SOLAR STREET LIGHTS AT BOGORO/DASS/TAFAWA BALEWA FEDERAL CONSTITUENCY, BAUCHI STATE (40,000,000.00) | [5 empty] | 40000000
44 | SOLAR STREET LIGHTS AT BOGORO/TAFAWA BALEWA FEDERAL CONSTITUENCY, BAUCHI STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 30000000 | 2014-11-17 | 2014-11-17 | √ | NAFTECH SOLAR ENERGY LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
45 | SOLAR STREET LIGHTS AT TAFAWA BALEWA FEDERAL CONSTITUENCY, BAUCHI STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 10000000 | 2014-11-17 | 2014-11-17 | √ | SOLID ALTERNATIVE LTD | 2014-11-19 | 2340000 | 30DAYS | 2014-11-26 | 2340000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
46 | SOLAR STREETLIGHTS IN MINJIBIR/UNGOGO FEDERAL CONSTITUENCY, KANO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 30000000 | 2014-11-17 | 2014-11-17 | √ | SANROUK ENGINEERING SERVICES LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
47 | SOLAR STREET LIGHTS (20) IN SHEKAU VILLAGE, SHEKAU WARD, TARMUWA LGA, YOBE STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | OCTUS INTERRACTIVE LTD | 2014-11-19 | 5460000 | 30DAYS | 2014-11-26 | 5460000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
48 | RURAL ELECTRIFICATION IN OHAOZARA/ONICHA/IVO FEDERAL COSNTITEUNCY, EBONYI STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | ROCK DOOR NIG LTD | 2014-11-19 | 5460000 | 30DAYS | 2014-11-26 | 5460000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
49 | SOLAR STREET LIGHTS IN EMESU COMMUNITY ABUA/ODUAL LGA, RIVER STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 10000000 | 2014-11-17 | 2014-11-17 | √ | EBIK ENGINEERING LTD | 2014-11-19 | 2340000 | 30DAYS | 2014-11-26 | NIL | 2014-12-31 | NOT EXECUTED | 0% | N/A | NIL
50 | SOLAR STREET LIGHT IN EGUNUGHAN COMMUNITY ABUA/ODUAL LGA, RIVER STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 10000000 | 2014-11-17 | 2014-11-17 | √ | DUMBILI MEGA SERVICES LTD | 2014-11-19 | 2340000 | 30DAYS | 2014-11-26 | 2340000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
51 | PROVISION OF SOLAR STREET LIGHTS IN JESSE CLAN, ETHIOPE WEST LGA, DELTA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 30000000 | 2014-11-17 | 2014-11-17 | √ | AGODA INTERNATIONAL LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
52 | PROVISION OF 50 SOLAR STREET LIGHT AT AWOIDEMILI/IHIOMA, ORLU LGA, IMO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | WHITE-BIM NIGERIA LTD | 2014-11-19 | 7800000 | 30DAYS | 2014-11-26 | 7800000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
53 | SUPPLY AND INSTALLATION OF SOLAR STREET LIGHTS IN ABI/YAKURR FEDERAL CONSTITUENCY, CROSS RIVER STATE 1 | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 50000000 | 2014-11-17 | 2014-11-17 | √ | HEZEL & CO SYNERGYIES LTD | 2014-11-19 | 14040000 | 30DAYS | 2014-11-26 | 8580000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
54 | SOLAR STREET LIGHTS AT MADA STATION TO EGGAH BRU BRU, NASARAWA NORTH FEDERAL CONSTITUENCY, NASARAWA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | HUDALLAH GRAND SERVICES LTD | 2014-11-19 | 5460000 | 30DAYS | 2014-11-26 | 5460000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
55 | SOLAR POWERED STREET LIGHT AT IFON, OSE LGA, ONDO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 50000000 | 2014-11-17 | 2014-11-17 | √ | JRB SOLAR INVESTMENT LTD | 2014-11-19 | 14040000 | 30DAYS | 2014-11-26 | 14040000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
56 | SOLAR STREET LIGHT IN PARTS OF OKIGWE SOUTH FEDERAL CONSTITUENCY | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 10000000 | 2014-11-17 | 2014-11-17 | √ | JOATECH HERRITAGE SERVICES NIGERIA LTD | 2014-11-19 | 2340000 | 30DAYS | 2014-11-26 | 2340000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
57 | PROVISION OF SOLAR STREET LIGHT AT YALLAM/DAMARGU BICHI LGA, KANO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 10000000 | 2014-11-17 | 2014-11-17 | √ | PROGREESIVE SITE ENGINNERING LTD | 2014-11-19 | 2340000 | 30DAYS | 2014-11-26 | 2340000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
58 | PROVISION OF SOLAR STREET LIGHT AT GEZAWA/GABASAWA FEDERAL CONSTITUENCY, KANO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | EMJAS ALLIED NIGERIA LTD | 2014-11-19 | 5460000 | 30DAYS | 2014-11-26 | 5460000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
| SUPPLY AND INSTALLATION OF SOLAR STREET LIGHT IN BALI/GASSOL (34,000,000.00) | [5 empty] | 34000000
59 | SUPPLY AND INSTALLATION OF SOLAR STREET LIGHT IN BALI | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | ABAHA INTEGRATED CONCEPT LTD | 2014-11-19 | 9360000 | 30DAYS | 2014-11-26 | 9360000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
60 | SUPPLY AND INSTALLATION OF SOLAR STREET LIGHT IN GASSOL | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 14000000 | 2014-11-17 | 2014-11-17 | √ | RAYLIGHT MULTI FUNCTIONAL SERVICES LTD | 2014-11-19 | 7800000 | 30DAYS | 2014-11-26 | 7800000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
61 | PROVISION OF 15 NO POLES OF SOLAR POWERED STREET LIGHT AT IBIWE STREET, MISSION ROAD TO THE END OF IBIWE, EDO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 10500000 | 2014-11-17 | 2014-11-17 | √ | EH-LED GLOBAL SERVICES LTD | 2014-11-19 | 2340000 | 30DAYS | 2014-11-26 | 2340000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
62 | CONSTRUCTION OF SOLAR POWERED STREETLIGHT IN AFIA NSIT URANKO IN NSIT IBOM LGA, AKWA IBOM STATE (CORRIGENDUM) | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 10000000 | 2014-11-17 | 2014-11-17 | √ | JAM & BAY NIG LTD | 2014-11-19 | 2340000 | 30DAYS | 2014-11-26 | 2340000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
| SOLAR POWER STREET LIGHT AT KIRU L.G.A, KIRU/BEBEJI FEDERAL CONSTITUENCY,KANO STATE (100,000,000.00) | [5 empty] | 100000000
63 | SOLAR POWER STREET LIGHT AT ZUWO, YAKO, BARGONI AND DASHI, KIRU L.G.A, KIRU/BEBEJI FEDERAL CONSTITUENCY,KANO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 50000000 | 2014-11-17 | 2014-11-17 | √ | EASH PROGRESSIVE VENTURES LTD | 2014-11-19 | 14040000 | 30DAYS | 2014-11-26 | 14040000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
64 | SOLAR POWER STREET LIGHT AT KIRU, KOGO, BADAFI AND YALWA, KIRU L.G.A, KIRU/BEBEJI FEDERAL CONSTITUENCY,KANO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 50000000 | 2014-11-17 | 2014-11-17 | √ | SABITI NIGERIA LTD | 2014-11-19 | 14040000 | 30DAYS | 2014-11-26 | 14040000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
| SOLAR POWER STREET LIGHT AT BEBEJI L.G.A, KIRU/BEBEJI FEDERAL CONSTITUENCY,KANO STATE (N100,000,000.00) | [5 empty] | 100000000
65 | SOLAR POWER STREET LIGHT AT RANKA, BEBEJI, AND KOFA, BEBEJI L.G.A, KIRU/BEBEJI FEDERAL CONSTITUENCY,KANO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 39000000 | 2014-11-17 | 2014-11-17 | √ | OPEN DOOR SYSTEM INTL LTD | 2014-11-19 | 10920000 | 30DAYS | 2014-11-26 | 10920000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
66 | SOLAR POWER STREET LIGHT AT ANADARIYA, RAHAMA AND WAK, BEBEJI L.G.A, KIRU/BEBEJI FEDERAL CONSTITUENCY,KANO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 39000000 | 2014-11-17 | 2014-11-17 | √ | B. SOLAR ENERGY LTD | 2014-11-19 | 10920000 | 30DAYS | 2014-11-26 | 10920000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
67 | SOLAR POWER STREET LIGHT AT DURMAWA AND GWARMAI, BEBEJI L.G.A, KIRU/BEBEJI FEDERAL CONSTITUENCY,KANO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 22000000 | 2014-11-17 | 2014-11-17 | √ | EXCLUSIVE ENERGY LTD | 2014-11-19 | 6240000 | 30DAYS | 2014-11-26 | 6240000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
| BOREHOLES | [10 empty] | 2014-11-19 |  | 30DAYS | 2014-11-26 |  | 2014-12-31 | COMPLETED | 100% | N/A | NIL
| SOLAR BOREHOLES IN VARIOUS LOCATIONS NATION WIDE N80,000,000.00) | [5 empty] | 80000000
1 | SOLAR BOREHOLES IN ISAGA, ADO-ODO, OGUN STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 |  | 2014-11-17 | 2014-11-17 | √ | VASALVA VENTURES LTD | 2014-11-19 | 6500000 | 30DAYS | 2014-11-26 | 6500000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
2 | SOLAR BOREHOLES IN ILOYE SANGO, OGUN STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 |  | 2014-11-17 | 2014-11-17 | √ | SEGABA INTL CO. LTD | 2014-11-19 | 6500000 | 30DAYS | 2014-11-26 | 6500000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
3 | SOLAR BOREHOLES IN ILO-OTA, OGUN STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 |  | 2014-11-17 | 2014-11-17 | √ | GASARI VENTURES LTD | 2014-11-19 | 6500000 | 30DAYS | 2014-11-26 | 6500000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
| SOLAR BOREHOLES IN YEWA SOUTH/IPOKIA/IMEKO (28,000,000) | [5 empty] | 28000000
4 | SOLAR BOREHOLES IN YEWA SOUTH/IPOKIA/IMEKO 1 | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 |  | 2014-11-17 | 2014-11-17 | √ | MACYS MULTI VENTURES LTD | 2014-11-19 | 6500000 | 30DAYS | 2014-11-26 | 6500000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
5 | SOLAR BOREHOLES IN YEWA SOUTH/IPOKIA/IMEKO 2 | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 |  | 2014-11-17 | 2014-11-17 | √ | UGOTHEL RESOURCES LTD | 2014-11-19 | 6500000 | 30DAYS | 2014-11-26 | 6500000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
| CONSTRUCTION AND INSTALLATION OF SOLAR POWER BOREHOLE IN IDIROKO, OGUN STATE (CORRIGENDUM) (50,000,000.00) | [5 empty] | 50000000 | 2014-11-17 | 2014-11-17 |  |  | 2014-11-19 |  | 30DAYS | 2014-11-26 |  | 2014-12-31 | COMPLETED | 100% | N/A | NIL
6 | SOLAR BOREHOLES IN TUBE,ELEKULE AND IJOFIN, YEWA/IPOKIA FED. CONSTUENCY, OGUN STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 |  | 2014-11-17 | 2014-11-17 | √ | AJULO JAB NIG LTD | 2014-11-19 | 6500000 | 30DAYS | 2014-11-26 | 6500000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
7 | SOLAR BOREHOLES IN AGOSASA, OKEODAN AND ILARO, YEWA/IPOKIA FEDRAL CONSTITUENCY, OGUN STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 |  | 2014-11-17 | 2014-11-17 | √ | TRIPPLE P BUSINESS SOLUTION LTD | 2014-11-19 | 6500000 | 30DAYS | 2014-11-26 | 6500000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
| CONSTRUCTION AND INSTALLATION OF SOLAR POWERBOREHOLES IN AKOKO, ONDO STATE (CORRIGENDUM) (50,000,000.00) | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 50000000 | 2014-11-17 | 2014-11-17 |  |  | 2014-11-19 |  | 30DAYS | 2014-11-26 |  | 2014-12-31 | COMPLETED | 100% | N/A | NIL
8 | 2NO. CONSTRUCTION AND INSTALLATION OF SOLAR POWERBOREHOLES IRUN& ERUSU IN AKOKO, ONDO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 |  | 2014-11-17 | 2014-11-17 | √ | NIMNOF NIG LTD | 2014-11-19 | 6500000 | 30DAYS | 2014-11-26 | 6500000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
9 | CONSTRUCTION AND INSTALLATION OF SOLAR POWERBOREHOLES IMO-ARIGIDI IN AKOKO, ONDO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 |  | 2014-11-17 | 2014-11-17 | √ | DHL UNIVERSAL BATTERY LTD | 2014-11-19 | 6500000 | 30DAYS | 2014-11-26 | 6500000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
| SOLAR POWERED BOREHOLES AT KONTAGORA/MAIRIGA/MAISHEHU/WUSHISHI FEDERAL CONSTITUENCY, NIGER STATE (30,000,000) | [5 empty] | 30000000
10 | SOLAR POWERED BOREHOLES AT KONTAGORA/MAIRIGA/MAISHEHU/WUSHISHI FEDERAL CONSTITUENCY, NIGER STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 15000000 | 2014-11-17 | 2014-11-17 | √ | VENUS ENERGY & SUSTAINABLE INFRASTRUCTURE NIG LTD | 2014-11-19 | 6500000 | 30DAYS | 2014-11-26 | 6500000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
11 | SOLAR POWERED BOREHOLES AT KONTAGORA/MAIRIGA/MAISHEHU/WUSHISHI FEDERAL CONSTITUENCY, NIGER STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 15000000 | 2014-11-17 | 2014-11-17 | √ | MULTICAST SYSTEMS LTD | 2014-11-19 | 6500000 | 30DAYS | 2014-11-26 | 6500000 | 2014-12-31 | COMPLETED | 100% | N/A | NIL
SENATE STREETLIGHT AND BOREHLOS
| SOLAR POWERED STREETLIGHTS IN KANO NORTH SENATORIAL DISTRICT, KANO STATE (N140,000,000.00) | [5 empty] | 140000000
1 | SOLAR POWERED STREETLIGHTS IN RIGA, GWARZO LGA, KANO NORTH SENATORIAL DISTRICT, KANO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 40900000 | 2014-11-17 | 2014-11-17 | √ | GABDIRE INTERNATIONAL LTD | 2014-11-19 | 17940000 | 30DAYS | 2014-11-26 | 17940000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
2 | SOLAR POWERED STREETLIGHTS IN SALIHAWA, GWARZO LGA, KANO NORTH SENATORIAL DISTRICT, KANO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 39000000 | 2014-11-17 | 2014-11-17 | √ | RUMAYA ENTERPRISES NIGERIA LTD | 2014-11-19 | 17160000 | 30DAYS | 2014-11-26 | 17160000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
3 | SOLAR POWERED STREETLIGHTS IN KARA, GWARZO LGA, KANO NORTH SENATORIAL DISTRICT, KANO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 60100000 | 2014-11-17 | 2014-11-17 | √ | ALMUKAB DYNAMICS LTD | 2014-11-19 | 26520000 | 30DAYS | 2014-11-26 | 26520000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
4 | CONSTRUCTION OF SOLAR STREET LIGHT AT OKPOROWO COMMUNITY IN AHOADA-EAST LGA, RIVERS STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | STONEGATE COMMUNICATION AND SECURITY SERVICES LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
5 | CONSTRUCTION OF SOLAR STREET LIGHT AT ODIEREKE-UBIE IN AHOADA-WEST LGA, RIVERS STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | SAFIYATU GLOBAL RESOURCES LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
6 | CONSTRUCTION OF SOLAR STREET LIGHT AT IHUOWO COMMUNITY IN AHOADA-EAST LGA, RIVERS STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | HAK GLOBAL INVESTMENT LTD | 2014-11-19 | 15600000 | 30DAYS | 2014-11-26 | 15600000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
| SUPPLY OF 200 (TWO HUNDRED) SOLAR POWERED STREET LIGHTS AT N670,000 IN VARIOUS LOCATIONS IN LAGOS WEST SENATORIAL DISTRICT, LAGOS STATE. (N135,000,000.00) | [5 empty] | 135000000
7 | SUPPLY OF SOLAR POWERED STREET LIGHTS AT OLAJIDE STREET, TANIMOWO STREET, ALHAJI LASISI STREET, IDI ORO, AND IMASUEN STREET OFF LADIPO STRRET, MUSHIN IN LAGOS WEST SENATORIAL DISTRICT, LAGOS STATE. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 34000000 | 2014-11-17 | 2014-11-17 | √ | VALOB CELOS INGRATED LED | 2014-11-19 | 14820000 | 30DAYS | 2014-11-26 | 14820000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
8 | SUPPLY OF SOLAR POWERED STREET LIGHTS AT IDI-OJO STREET AND AJAYE QUARTERS, IWORO,(BADAGRY), OWONI-OJE RD OFF LASU, IGANDO-OJO IN LAGOS WEST SENATORIAL DISTRICT, LAGOS STATE. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 27000000 | 2014-11-17 | 2014-11-17 | √ | J15 NIGERIA LTD | 2014-11-19 | 11700000 | 30DAYS | 2014-11-26 | 11700000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
9 | SUPPLY OF SOLAR POWERED STREET LIGHTS AT CHARLES AVENUE OFF OJO ROAD, AJEGUNLE APAPA-AJEROMI IFELODUN, JOHNSON STREET KIRIRI-AMUWO ODOFIN IN LAGOS WEST SENATORIAL DISTRICT, LAGOS STATE. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | GREEN LEAF AGRIC RESOURCES LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
10 | SUPPLY OF SOLAR POWERED STREET LIGHTS ATALESHINLOYE STR, ORISUNBARE, OKE-RUBE, ABERANJE, IKOTUN, AWOTEDU STR, PIPELINE ABORU, IYANA IPAJA-ALIMOSHO IN LAGOS WEST SENATORIAL DISTRICT, LAGOS STATE. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 27000000 | 2014-11-17 | 2014-11-17 | √ | D@ECH NIG LTD | 2014-11-19 | 11700000 | 30DAYS | 2014-11-26 | 11700000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
11 | SUPPLY OF SOLAR POWERED STREET LIGHTS ATKOLAWOLE SEBILI STR,EJIGBO-OSHODI/ISOLO, HARUNA STR, IFAKO-AJAIYE AND ISALE AWORI/IPODO ROAD, IKEJA IN LAGOS WEST SENATORIAL DISTRICT, LAGOS STATE. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 27000000 | 2014-11-17 | 2014-11-17 | √ | B & U GLOBAL RESOURCES LTD | 2014-11-19 | 15600000 | 30DAYS | 2014-11-26 | 15600000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
| PROVISION OF SOLAR POWERED STREET LIGHTS IN KADUNA NORTH SENATORIAL DISTRCT (N100,000,000.00) | [5 empty] | 100000000
12 | PROVISION OF SOLAR POWERED STREET LIGHTS IN KADUNA NORTH SENATORIAL DISTRCT (MAKARFI AND KUDAN LGA) | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 25000000 | 2014-11-17 | 2014-11-17 | √ | ABIDINE LTD | 2014-11-19 | 10920000 | 30DAYS | 2014-11-26 | 10920000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
13 | PROVISION OF SOLAR POWERED STREET LIGHTS IN KADUNA NORTH SENATORIAL DISTRCT(ZARIA AND S/GARI LGA) | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 25000000 | 2014-11-17 | 2014-11-17 | √ | ROGOJI INVESTMENT NIG LTD | 2014-11-19 | 10920000 | 30DAYS | 2014-11-26 | 10920000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
14 | PROVISION OF SOLAR POWERED STREET LIGHTS IN KADUNA NORTH SENATORIAL DISTRCT (SOBA AND IKARA LGA) | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 25000000 | 2014-11-17 | 2014-11-17 | √ | TASKIYA GLOBAL LIMITED | 2014-11-19 | 10920000 | 30DAYS | 2014-11-26 | 10920000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
15 | PROVISION OF SOLAR POWERED STREET LIGHTS IN KADUNA NORTH SENATORIAL DISTRCT (LERE AND KUBAU LGA) | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 25000000 | 2014-11-17 | 2014-11-17 | √ | TROW NIGERIA LIMITED | 2014-11-19 | 10920000 | 30DAYS | 2014-11-26 | 10920000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
16 | CONSTRUCTION OF SOLAR STREET LIGHT IN ZURU AND YAURI EMIRATE LGAS KEBBI SOUTH SENATORIAL DISTRICT | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 40000000 | 2014-11-17 | 2014-11-17 | √ | MONEX GLOBAL SERVICES LTD | 2014-11-19 | 17940000 | 30DAYS | 2014-11-26 | 17940000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
17 | CONSTRUCTION OF SOLAR STREET LIGHT AT UMUAKU ISUOCHI IN UMUNNEOCHI, LGA, ABIA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 15000000 | 2014-11-17 | 2014-11-17 | √ | TAKI M GLOBAL SERVICES LTD | 2014-11-19 | 6240000 | 30DAYS | 2014-11-26 | 6240000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
18 | CONSTRUCTION OF SOLAR STREET LIGHT AT IDIMA ABAM, AROCHUKWU LGA, ABIA STATE. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 10000000 | 2014-11-17 | 2014-11-17 | √ | SOLID MARK ASSOCIATES LTD | 2014-11-19 | 3900000 | 30DAYS | 2014-11-26 | 3900000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
19 | CONSTRUCTION OF SOLAR STREET LIGHT AT ELUAMA, ISUIKWUATO, ISUIKWUATO LGA, ABIA STATE. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 7000000 | 2014-11-17 | 2014-11-17 | √ | AL-HAY NIG LTD | 2014-11-19 | 3120000 | 30DAYS | 2014-11-26 | 3120000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
20 | CONSTRUCTION OF SOLAR STREET LIGHT AT NKPORO, OHAFIA LGA, ABIA STATE. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 15000000 | 2014-11-17 | 2014-11-17 | √ | SUNLITE INTEGRATED SERVICES LTD | 2014-11-19 | 6240000 | 30DAYS | 2014-11-26 | 6240000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
21 | CONSTRUCTION OF SOLAR STREET LIGHTS IN GOMBE CENTRAL SENATORIAL DISTRICT | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 70000000 | 2014-11-17 | 2014-11-17 | √ | TAMUSA NIG LTD | 2014-11-19 | 31200000 | 30DAYS | 2014-11-26 | 31200000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
| CONSTRUCTION OF SOLAR POWERED STREET LIGHTS AT FUFORE, YOLA SOUTH, YOLA NORTH, GIREI, GOMBI AND HONG LGA IN ADAMAWA CENTRAL SENATORIAL DISTRICT (N100,000,000.00) | [5 empty] | 100000000
22 | CONSTRUCTION OF SOLAR POWERED STREET LIGHTS AT FUFORE, YOLA SOUTH, YOLA NORTH LGA IN ADAMAWA CENTRAL SENATORIAL DISTRICT | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 60000000 | 2014-11-17 | 2014-11-17 | √ | D & A FACILITIES MANAGERS AND PROPERTIES SERV. LTD | 2014-11-19 | 26520000 | 30DAYS | 2014-11-26 | 26520000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
23 | CONSTRUCTION OF SOLAR POWERED STREET LIGHTS AT FUFORE, GIREI LGA IN ADAMAWA CENTRAL SENATORIAL DISTRICT | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | GREAT TALENTS INVESTMENTS LIMITED | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
24 | CONSTRUCTION OF SOLAR POWERED STREET LIGHTS AT GOMBI AND HONG LGA IN ADAMAWA CENTRAL SENATORIAL DISTRICT | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | ABYAN ENERGY & SERVICES LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
| PROVISION OF SOLAR STREET LIGHTS IN GUSAU AND BUNGUDU LGA OF ZAMFARA STATE (N160,000,000.00) | [5 empty] | 160000000
25 | PROVISION OF SOLAR STREET LIGHTS IN GUSAU LGA OF ZAMFARA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 80000000 | 2014-11-17 | 2014-11-17 | √ | K.K. TECHNOLOGIES LTD | 2014-11-19 | 35550178.31 | 30DAYS | 2014-11-26 | 35550178.31 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
26 | PROVISION OF SOLAR STREET LIGHTS IN BUNGUDU LGA OF ZAMFARA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 80000000 | 2014-11-17 | 2014-11-17 | √ | AHMADY WATER WORKS LTD | 2014-11-19 | 35550178.31 | 30DAYS | 2014-11-26 | 35550178.31 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
27 | CONSTRUCTION OF SOLAR STREET LIGHT AT GURI IN ALANJO VILLAGE IN JIGAWA NORTH-EAST SENATORIAL DISTRICT | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 12500000 | 2014-11-17 | 2014-11-17 | √ | MATSON HITEK NETWORK SERVICES LTD | 2014-11-19 | 5460000 | 30DAYS | 2014-11-26 | 5460000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
28 | CONSTRUCTION OF SOLAR STREET LIGHT AT K/KASAMMA IN TURABU VILLAGE JIGAWA NORTH-EAST SENATORIAL DISTRICT | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 30000000 | 2014-11-17 | 2014-11-17 | √ | INJI CONSULT NIG LTD | 2014-11-19 | 13260000 | 30DAYS | 2014-11-26 | 13260000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
29 | CONSTRUCTION OF SOLAR STREET LIGHT IN MIGA, JAHUN, KIYAWA, DUTSE, BIRNIN KUDU, BUJI AND GWARAM LGA OF JIGAWA SOUTH WEST | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | MICROCELL TECHNOLOGIES LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
30 | PROVISION OF SOLAR POWERED STREET LIGHT FOR ODOGBOLU LGA, OGUN EAST SENATORIAL DISTRICT, OGUN STATE. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | TAMGAJ CORPORATE SERVICES LTD | 2014-11-19 | 6240000 | 30DAYS | 2014-11-26 | 6240000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
31 | PROVISION OF SOLAR POWERED STREET LIGHT FOR IJEBU-ODE LGA, OGUN EAST SENATORIAL DISTRICT, OGUN STATE. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 15000000 | 2014-11-17 | 2014-11-17 | √ | GREEN PLAINS ENEGYSERVICES LTD | 2014-11-19 | 6240000 | 30DAYS | 2014-11-26 | 6240000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
32 | PROVISION OF SOLAR POWERED STREET LIGHT FOR IJEBU-NORTH EAST LGA, OGUN EAST SENATORIAL DISTRICT, OGUN STATE. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 15000000 | 2014-11-17 | 2014-11-17 | √ | CIRCLE ELECTRIC LTD | 2014-11-19 | 6240000 | 30DAYS | 2014-11-26 | 6240000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
33 | PROVISION OF SOLAR POWERED STREET LIGHT FOR IJEBU-NORTH LGA, OGUN EAST SENATORIAL DISTRICT, OGUN STATE. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 15000000 | 2014-11-17 | 2014-11-17 | √ | JAMAJI NIGERIA LTD | 2014-11-19 | 6240000 | 30DAYS | 2014-11-26 | 6240000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
34 | PROVISION OF SOLAR POWERED STREET LIGHT FOR IJEBU-EAST LGA, OGUN EAST SENATORIAL DISTRICT, OGUN STATE. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 15000000 | 2014-11-17 | 2014-11-17 | √ | BELTECH NIG LTD | 2014-11-19 | 6240000 | 30DAYS | 2014-11-26 | 6240000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
35 | PROVISION OF SOLAR POWERED STREET LIGHT FOR OGUN WATERSIDE LGA, OGUN EAST SENATORIAL DISTRICT, OGUN STATE. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 15000000 | 2014-11-17 | 2014-11-17 | √ | TELEQUIP AND DIGITAL LTD | 2014-11-19 | 6240000 | 30DAYS | 2014-11-26 | 6240000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
36 | PROVISION OF SOLAR POWERED STREET LIGHT FOR SAGAMU LGA, OGUN EAST SENATORIAL DISTRICT, OGUN STATE. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 15000000 | 2014-11-17 | 2014-11-17 | √ | AFOVAGE SOLAR NIG LTD | 2014-11-19 | 6240000 | 30DAYS | 2014-11-26 | 6240000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
37 | PROVISION OF SOLAR POWERED STREET LIGHT FOR IKENNE LGA, OGUN EAST SENATORIAL DISTRICT, OGUN STATE. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 15000000 | 2014-11-17 | 2014-11-17 | √ | M. S. AKOWIND NIG LTD | 2014-11-19 | 6240000 | 30DAYS | 2014-11-26 | 6240000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
38 | PROVISION OF SOLAR POWERED STREET LIGHT FOR REMO NORTH LGA, OGUN EAST SENATORIAL DISTRICT, OGUN STATE. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 15000000 | 2014-11-17 | 2014-11-17 | √ | AMAL EGINEERING LTD | 2014-11-19 | 6240000 | 30DAYS | 2014-11-26 | 6240000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
| PROVISION OF 110 SOLAR STREET LIGHTS AT VARIOUS LOCATION IN ONDO NORTH SENATORIAL DISTRICT, ONDO STATE. (65,000,000.00) | [5 empty] | 65000000
39 | SOLAR POWERED STREETLIGHTSAT IBOJE/OWASE/OKIA/AGBA IN ONDO NORTH DEAORIAL DISTRICT, ONDO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 25000000 | 2014-11-17 | 2014-11-17 | √ | ADMOAK CONSTRUCTION INTL LTD | 2014-11-19 | 10920000 | 30DAYS | 2014-11-26 | 10920000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
40 | SOLAR POWERED STREETLIGHTSAT IGEDEGEDE/ERUSU/IYE IN ONDO NORTH SENATORIAL DISTRICT, ONDO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 25000000 | 2014-11-17 | 2014-11-17 | √ | M.J. ECO PROJECT LTD | 2014-11-19 | 10920000 | 30DAYS | 2014-11-26 | 10920000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
41 | SOLAR POWERED STREETLIGHTS IN ARIMOGIJA/IJAGBA IN ONDO NORTH SENATORIAL DISTRICT, ONDO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 15000000 | 2014-11-17 | 2014-11-17 | √ | GENUZA NIGERIA LTD | 2014-11-19 | 6240000 | 30DAYS | 2014-11-26 | 6240000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
| PROVISION OF SOLAR POWER STREET LIGHT FOR IIRUA, UBIAJA, UROMI, EKPOMA AND IGUEBEN IN EDO CENTRAL SENATORIAL DISTRICT, EDO STATE. (50,000,000.00) | [5 empty] | 50000000
42 | PROVISION OF SOLAR POWER STREET LIGHT FOR IIRUA, UBIAJA, UROMI, IN EDO CENTRAL SENATORIAL DISTRICT, EDO STATE. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 30000000 | 2014-11-17 | 2014-11-17 | √ | TAKUA NIG LTD | 2014-11-19 | 13260000 | 30DAYS | 2014-11-26 | 13260000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
43 | PROVISION OF SOLAR POWER STREET LIGHT FOR EKPOMA AND IGUEBEN IN EDO CENTRAL SENATORIAL DISTRICT, EDO STATE. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | AL-AHAN MULTI SERVICES LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
SOLAR MINIGRID
1 | SOLAR POWEREDMINI GRID IN KANO NORTH SENATORIAL DISTRICT, KANO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 140000000 | 2014-11-17 | 2014-11-17 | √ | MKAIS NIGERIA LTD | 2014-11-19 | 62629320 | 30DAYS | 2014-11-26 | 62629320 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
MAINTENANCE
1 | MAINTENANCE OF SOLAR STREET LIGHTS IN ABIA NORTH SENATORIAL DISTRICT, ABIA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | JOSHUEL GLOBAL VENTURES LTD | 2014-11-19 | 8945547 | 30DAYS | 2014-11-26 | 8945547 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
2 | REPAIRS OF EXISTING SOLAR STREET LIGHTS IN GOMBE CENTRAL SENATORIAL DISTRICT | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 30000000 | 2014-11-17 | 2014-11-17 | √ | ABDUL ZAIMAN GLOBAL RESORSES LTD | 2014-11-19 | 13465314 | 30DAYS | 2014-11-26 | 13465314 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
3 | SERVICING AND REFURBISHING OF EXISTING 44 POLES SOLAR RURAL ELECTRIFICATION AT BODE OLUDE, ASA YOBO, OKE OGUN IN ODEDA, EWEKORO, ABEOKUTA NORTH & ABEOKUTA SOUTH LGAs, OGUN CENTRAL SENATORIAL DISTRICT, OGUN STATE. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 8000000 | 2014-11-17 | 2014-11-17 | √ | NASA GLOBAL RESOURCES SERVICES LTD | 2014-11-19 | 3501057 | 30DAYS | 2014-11-26 | 3501057 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
√
[12 empty] | 2014-11-19 |  | 30DAYS | 2014-11-26 |  | 2015-03-31 | COMPLETED | 100% | N/A | NIL
BOREHOLES
1 | CONSTRUCTION OF SOLAR POWERED BOREHOLES IN AUYO LGA AT KALAURI VILLAGE IN JIGAWA NORTH-EAST SENATORIAL DISTRICT | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 7500000 | 2014-11-17 | 2014-11-17 | √ | SAMHA CONCEPT LINK LTD | 2014-11-19 | 6500000 | 30DAYS | 2014-11-26 | 6500000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
2 | CONSTRUCTION OF SOLAR POWERED BOREHOLES IN KIRIKASAMMA AT SABONGARI VILLAGE IN JIGAWA NORTH-EAST SENATORIAL DISTRICT | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 7500000 | 2014-11-17 | 2014-11-17 | √ | IYKENEZ GLOBAL RESOURCES LTD | 2014-11-19 | 6500000 | 30DAYS | 2014-11-26 | 6500000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
3 | CONSTRUCTION OF SOLAR POWERED BOREHOLES IN KAFIN HAUSA AT DUDUMA VILLAGE IN JIGAWA NORTH-EAST SENATORIAL DISTRICT | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 7500000 | 2014-11-17 | 2014-11-17 | √ | TRANSTIME NIG LTD | 2014-11-19 | 6500000 | 30DAYS | 2014-11-26 | 6500000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
| CONSTRUCTION OF 10 NOS. SOLAR POWERED BOREHOLES IN VARIOUS LOCATIONS IN ONDO NORTH SENATORIAL DISTRICT, ONDO STATE. (65,000,000.00) | [5 empty] | 65000000
4 | CONSTRUCTION OF4No. SOLAR POWERED BOREHOLES IN IPELE/IMERI/IDOANI/EBIRIN, ONDO NORTH SENATORIAL DISTRICT, ONDO STATE. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 32500000 | 2014-11-17 | 2014-11-17 | √ | FOLUS ENTERPISES NIG LTD | 2014-11-19 | 26000000 | 30DAYS | 2014-11-26 | 26000000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
5 | CONSTRUCTION OF 4No. SOLAR POWERED BOREHOLES IN IKESE/AKUNGBA/EBO/IDOFIN, ONDO NORTH SENATORIAL DISTRICT, ONDO STATE. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 32500000 | 2014-11-17 | 2014-11-17 | √ | FORTIFIED CITY TECHNOLOGY LTD | 2014-11-19 | 26000000 | 30DAYS | 2014-11-26 | 26000000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
REPS. STREETLIGHT AND BOREHOLES
| PROVISION OF SOLAR STREET LIGHT (50 POLES) AT KUTIGI ENAGI & MOKWA TOWN, LAVUN,EDATI & MOKWA LGAs, NIGER STATE (N41,000,000.00) | [5 empty] | 41000000
1 | PROVISION OF SOLAR STREET LIGHT (50 POLES) AT KUTIGI ENAGI & MOKWA TOWN, NIGER STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20500000 | 2014-11-17 | 2014-11-17 | √ | JM & AS LIMITED | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
2 | PROVISION OF SOLAR STREET LIGHT (50 POLES) AT LAVUN,EDATI & MOKWA LGAs, NIGER STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20500000 | 2014-11-17 | 2014-11-17 | √ | INCO INVESTMENT LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
| PROVISION OF 50 NOS SOLAR STREET LIGHTS IN VARIUOS COMMUNITIES OF RIJAU/MAGAMA, NIGER STATE (N41,000,000.00) | [5 empty] | 41000000
3 | PROVISION OF 50 NOS SOLAR STREET LIGHTS IN VARIUOS COMMUNITIES OF RIJAU, NIGER STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20500000 | 2014-11-17 | 2014-11-17 | √ | BLACK CONSTRUCTIO LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
4 | PROVISION OF 50 NOS SOLAR STREET LIGHTS IN VARIUOS COMMUNITIES OF MAGAMA, NIGER STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20500000 | 2014-11-17 | 2014-11-17 | √ | TREASURE BOND NIGERIA LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
5 | PROVISION AND INSTALLATION OF 30 NOS OF SOLAR STEREET LIGHTS IN TOTO TOWN, NASARAWA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 18000000 | 2014-11-17 | 2014-11-17 | √ | HALA GLOBAL ENTERPRISES LTD | 2014-11-19 | 7800000 | 30DAYS | 2014-11-26 | 7800000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
| SOLAR STREET LIGHTS AT KILGORI,YABO L.G.A , DAGAWA VILLAGE,YABO L.G.A, KAJIJI VILLAGE,SHAGARI L.G.A , KAMBAMA VILLAGE,SHAGARI L.G.A, OF SOKOTO STATE. (46,800,000.00) | [5 empty] | 46800000
6 | SOLAR STREET LIGHTS AT KILGORI,YABO L.G.A , DAGAWA VILLAGE,YABO L.G.A, OF SOKOTO STATE. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 23400000 | 2014-11-17 | 2014-11-17 | √ | AHZAF GENERAL ENTERPRISES LTD | 2014-11-19 | 10140000 | 30DAYS | 2014-11-26 | 10140000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
7 | SOLAR STREET LIGHTS AT KAJIJI VILLAGE,SHAGARI L.G.A , KAMBAMA VILLAGE,SHAGARI L.G.A, OF SOKOTO STATE. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 23400000 | 2014-11-17 | 2014-11-17 | √ | DYNAMIC CROWN NIG LTD | 2014-11-19 | 10140000 | 30DAYS | 2014-11-26 | 10140000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
8 | CONSTRUCTION OF SOLAR STREET LIGHT IN BICHI TOWN KANO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 13500000 | 2014-11-17 | 2014-11-17 | √ | AIGA ENGINEERING & TECHNICAL SERVICES LTD | 2014-11-19 | 5460000 | 30DAYS | 2014-11-26 | 5460000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
| PROVISION OF SOLAR STREET LIGHTS IN DOGUWA AND TUDUNWADA L.G.A ,KANO STATE (40,000,000.00) | [5 empty] | 40000000
10 | PROVISION OF SOLAR STREET LIGHTS IN DOGUWA L.G.A ,KANO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | CHESTINO INVESTMENT LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
11 | PROVISION OF SOLAR STREET LIGHTS IN TUDUNWADA L.G.A ,KANO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | POWER MINISTER LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
12 | SOLAR STREET LIGHT IN RANO TOWN, RANO L.G.A KANO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 40000000 | 2014-11-17 | 2014-11-17 | √ | PLATINE GLOBAL RESOURCES LTD | 2014-11-19 | 17940000 | 30DAYS | 2014-11-26 | 17940000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
| SOLAR STREETLIGHTR AT OKIGWE LGA, IMO STATE (40,00,000.00) | [5 empty] | 40000000
13 | SOLAR STREETLIGHTR AT OKIGWE LGA, IMO STATE 1 | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | KOMTEK ENGINEERING LTD | 2014-11-19 | 15600000 | 30DAYS | 2014-11-26 | 15600000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
14 | SOLAR STREETLIGHTR AT OKIGWE LGA, IMO STATE 2 | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | ZENCON INVESTMENT LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
15 | SOLAR STREETLIGHTR AT ONUIMO LGA, IMO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 40000000 | 2014-11-17 | 2014-11-17 | √ | OMMASON GREAT ENTERPRISES LTD | 2014-11-19 | 17940000 | 30DAYS | 2014-11-26 | 17940000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
16 | SOLAR STREETLIGHTR AT ISIALA MBANO LGA, IMO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 40000000 | 2014-11-17 | 2014-11-17 | √ | ZAKUB LOGISTICS SERVICES LTD | 2014-11-19 | 17940000 | 30DAYS | 2014-11-26 | 17940000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
17 | SOLAR STREETLIGHTS AT NDIANICHE UNO, IDEATO NORTH, IMO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | YAFTAHA ENG.LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
18 | SOLAR STREETLIGHTS AT DIKENAFAI, IDEATO SOUTH, IMO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | OCCEAN NETWAY NIG LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
19 | SOLAR STREETLIGHTS AT UMUALAOMA, IDEATO NORTH, IMO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 15000000 | 2014-11-17 | 2014-11-17 | √ | NIPHEMY SOLUTION LTD | 2014-11-19 | 6240000 | 30DAYS | 2014-11-26 | 6240000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
20 | SOLAR STREETLIGHTS AT OSINA, IDEATO NORTH, IMO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 15000000 | 2014-11-17 | 2014-11-17 | √ | AD-BOTOG INT'L LTD | 2014-11-19 | 6240000 | 30DAYS | 2014-11-26 | 6240000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
| SOLAR STREETLIGHTR AT NNEATO, UMUCHIEZE, UTURU, ISUOCHI AND ISUIKWUATO, UMUNNEOCHI LGA, ABIA STATE (N80,000,000.00) | [5 empty] | 80000000
21 | SOLAR STREETLIGHTR AT NNEATO, UMUCHIEZE, ISUOCHI, UMUNNEOCHI LGA, ABIA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 50000000 | 2014-11-17 | 2014-11-17 | √ | WESTWOOD GLOBAL CONCEPT LIMITED | 2014-11-19 | 21840000 | 30DAYS | 2014-11-26 | 21840000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
22 | SOLAR STREETLIGHTR AT UTURU ISUIKWUATO, ISUIKWUATO LGA, ABIA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 30000000 | 2014-11-17 | 2014-11-17 | √ | DANGUDEY RESOURCES LTD | 2014-11-19 | 15600000 | 30DAYS | 2014-11-26 | 15600000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
23 | INSTALLATION OF SOLAR POWERED STREET LIGHTS AT OYANGBENE, BURUTU LGA, DELTA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | BROWN INTEGRATED ENERGYSERVICES LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
24 | INSTALLATION OF SOLAR POWERED STREET LIGHTS AT EGODOR, BURUTU LGA, DELTA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 15000000 | 2014-11-17 | 2014-11-17 | √ | PHISH UPDATE LTD | 2014-11-19 | 6240000 | 30DAYS | 2014-11-26 | 6240000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
25 | INSTALLATION OF SOLAR POWERED STREET LIGHTS AT KIAGBODO,BURUTU LGA, DELTA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 15000000 | 2014-11-17 | 2014-11-17 | √ | JEOPHISH GLOBAL SERVICES LTD | 2014-11-19 | 6240000 | 30DAYS | 2014-11-26 | 6240000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
26 | INSTALLATION OF SOLAR POWERED LIGHTS AT KENLOGBENE / OKORODUDU, BURUTU LGA,DELTA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | JAYJAY BADMUS INVESTMENT LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
27 | PROVISION OF 17 NOS. OF SOLAR POWERED STREET LIGHT AT JAMES WATT ROAD, OREDO FED. CONSTITUENCY, EDO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 11900000 | 2014-11-17 | 2014-11-17 | √ | MWAYI INVESTMENT LTD | 2014-11-19 | 4680000 | 30DAYS | 2014-11-26 | 4680000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
28 | PROVISION OF 22 NOS. OF SOLAR POWERED STREET LIGHT AT ONI STREET, OREDO FED. CONSTITUENCY, EDO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 15400000 | 2014-11-17 | 2014-11-17 | √ | SUNGREEN TECHNOLOGY LIMITED | 2014-11-19 | 6240000 | 30DAYS | 2014-11-26 | 6240000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
29 | PROVISION OF 30 NOS. OF SOLAR STREET LIGHTS: AT EWOHIMI,(WARDS 2) ESAN SOUTH EAST LGA, EDO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 30000000 | 2014-11-17 | 2014-11-17 | √ | WILON SURGICAL & SCIENTIFIC EQUIPMENT LTD | 2014-11-19 | 13260000 | 30DAYS | 2014-11-26 | 13260000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
30 | PROVISION OF SOLAR STREET LIGHT (12 POLES) TO OLD YABA ROAD LAGOS MAINLAND, LAGOS. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 6000000 | 2014-11-17 | 2014-11-17 | √ | NOBLE DREAMS ASSOC. | 2014-11-19 | 2340000 | 30DAYS | 2014-11-26 | 2340000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
31 | PROVISION OF SOLAR STREET LIGHT (14 POLES) TO IWAYA & MAKOKO,LAGOS MAINLAND, LAGOS. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 7000000 | 2014-11-17 | 2014-11-17 | √ | AKIBOLOS VENTURES LTD | 2014-11-19 | 3120000 | 30DAYS | 2014-11-26 | 3120000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
32 | PROVISION OF SOLAR STREET LIGHT (14 POLES) TO ABULE- JESHA,LAGOS MAINLAND, LAGOS. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 7000000 | 2014-11-17 | 2014-11-17 | √ | FARIQ INTERBIZ LTD | 2014-11-19 | 3120000 | 30DAYS | 2014-11-26 | 3120000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
33 | PROVISION OF SOLAR STREET LIGHT (14 POLES) TO OTO ROAD,LAGOS MAINLAND, LAGOS. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 7000000 | 2014-11-17 | 2014-11-17 | √ | ZAYDAH HALEEM RESOURCES NIG LTD | 2014-11-19 | 3120000 | 30DAYS | 2014-11-26 | 3120000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
34 | PROVISION OF SOLAR STREET LIGHT (14 POLES) TO APAPA ROAD,LAGOS MAINLAND, LAGOS. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 7000000 | 2014-11-17 | 2014-11-17 | √ | VEECEE ENERGY LTD | 2014-11-19 | 3120000 | 30DAYS | 2014-11-26 | 3120000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
35 | PROVISION OF SOLAR STREET LIGHT (14 POLES) TO ABULENLA,LAGOS MAINLAND, LAGOS. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 7000000 | 2014-11-17 | 2014-11-17 | √ | WE CAN ACHIEVE LTD | 2014-11-19 | 3120000 | 30DAYS | 2014-11-26 | 3120000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
36 | PROVISION AND INSTALLATION OF (20 POLES) SOLAR POWERED STREET LIGHT AT IBADAN NORTH LGA | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 10000000 | 2014-11-17 | 2014-11-17 | √ | NICE POWER PROJECT LTD | 2014-11-19 | 3900000 | 30DAYS | 2014-11-26 | 3900000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
| PROVISION OF 77 PLOES SOLAR STREET LIGHT, IJEBU EAST, IJEBU NORTH, OGUN WATERSIDE, OGUN STATE (50,000,000.00) | [5 empty] | 50000000
37 | PROVISION OF 77 PLOES SOLAR STREET LIGHT, IJEBU EAST, OGUN WATERSIDE, OGUN STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 25000000 | 2014-11-17 | 2014-11-17 | √ | QUARTZ SOLAR ENERGY SYSTEMS LTD | 2014-11-19 | 15600000 | 30DAYS | 2014-11-26 | 15600000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
38 | PROVISION OF 77 PLOES SOLAR STREET LIGHT, IJEBU NORTH, OGUN WATERSIDE, OGUN STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 25000000 | 2014-11-17 | 2014-11-17 | √ | SAHIH ENGINEERING SERVIVES LTD | 2014-11-19 | 15600000 | 30DAYS | 2014-11-26 | 15600000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
| SOLAR POWERED STREET LIGHT (70 POLES), ONDO EAST, ONDO STATE (40,000,000.00) | [5 empty] | 40000000
39 | SOLAR POWERED STREET LIGHT (70 POLES), ONDO EAST, ONDO STATE 1 | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | FIRST GOLDEN VENTURES LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
40 | SOLAR POWERED STREET LIGHT (70 POLES), ONDO EAST, ONDO STATE 2 | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | TIMAJE VENTURES LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
41 | SOLAR POWERED STREET LIGHT (42 POLES) FOR AKOKO SOUTH WEST, ONDO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 28000000 | 2014-11-17 | 2014-11-17 | √ | BIZERVE NIG LTD | 2014-11-19 | 12480000 | 30DAYS | 2014-11-26 | 12480000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
42 | SOLAR POWERED STREET LIGHT (15 POLES) FOR AKOKO SOUTH EAST, ONDO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 10000000 | 2014-11-17 | 2014-11-17 | √ | YERI GLOBAL RESOURCES LTD | 2014-11-19 | 3900000 | 30DAYS | 2014-11-26 | 3900000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
43 | SOLAR POWERED STREET LIGHT (46 POLES) FOR ILAJE LGA, ONDO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 30000000 | 2014-11-17 | 2014-11-17 | √ | SUBANGA INVESTMENT LTD | 2014-11-19 | 13260000 | 30DAYS | 2014-11-26 | 13260000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
44 | SOLAR POWERED STREET LIGHT (46 POLES) FOR IPELE/IYAYU/ARUMOGIJA AREA OF ONDO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 30000000 | 2014-11-17 | 2014-11-17 | √ | CLIFFESSE GENERAL CONTRACTORS NIG LTD | 2014-11-19 | 13260000 | 30DAYS | 2014-11-26 | 13260000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
45 | SOLAR POWERED STREETLIGHTS AT AKOKO NORTH EAST, EDO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | ADSAK INVESTMENT RESOURCES LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
46 | SOLAR POWERED STREETLIGHT AT BURUTU, BURUTU LGA, DELTA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 10000000 | 2014-11-17 | 2014-11-17 | √ | TRADE LOGICS LTD | 2014-11-19 | 3900000 | 30DAYS | 2014-11-26 | 3900000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
| ONGOING PROVISION OF SOLAR POWERED STREETLIGHT IN 30 COMMUNITIES IN GURARA/SULEJA/TAFA FEDERAL CONSTITUENCY, NIGER STATE (N50,000,000.00) | [5 empty] | 50000000
47 | ONGOING PROVISION OF SOLAR POWERED STREETLIGHT IN KWAKWA, DIKO AND GAWU, GURARA LGA, GURARA/SULEJA/TAFA FEDERAL CONSTITUENCY, NIGER STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 15000000 | 2014-11-17 | 2014-11-17 | √ | DANKU INTEGRATED SERVICES LTD | 2014-11-19 | 6240000 | 30DAYS | 2014-11-26 | 6240000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
48 | ONGOING PROVISION OF SOLAR POWERED STREETLIGHT IN IJAH GBAGYI, BEARI, GAURAKA AND GARAM, TAFA LGA, GURARA/SULEJA/TAFA FEDERAL CONSTITUENCY, NIGER STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 15000000 | 2014-11-17 | 2014-11-17 | √ | NATIVE EXPRESSION LTD | 2014-11-19 | 6240000 | 30DAYS | 2014-11-26 | 6240000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
49 | ONGOING PROVISION OF SOLAR POWERED STREETLIGHT IN SULEJA, SULEJA LGA, GURARA/SULEJA/TAFA FEDERAL CONSTITUENCY, NIGER STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | FLAMSESON GLOBAL RESOURCES LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
50 | CONSTRUCTION OF SOLAR LIGHT IN KAMPANI - ZURAK IN WASE LGA, PLATEAU STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | GODIRI INTERNATIONAL LTD | 2014-11-19 | 8580000 | 30DAYS | 2014-11-26 | 8580000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
| SOLAR POWERED STREETLIGHT IN ORHINMWON/UHUNMWODE FED. CONSTITUENCY, EDO STATE (N150,000,000.00) | [5 empty] | 150000000
51 | SOLAR POWERED STREETLIGHT IN ORHINMWON/UHUNMWODE FED. CONSTITUENCY 4, EDO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 50000000 | 2014-11-17 | 2014-11-17 | √ | BUKAR AND BOUNTY LTD | 2014-11-19 | 21840000 | 30DAYS | 2014-11-26 | 21840000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
52 | SOLAR POWERED STREETLIGHT IN ORHINMWON/UHUNMWODE FED. CONSTITUENCY 5, EDO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 50000000 | 2014-11-17 | 2014-11-17 | √ | BEST BROTHERS INTL NIG LTD | 2014-11-19 | 21840000 | 30DAYS | 2014-11-26 | 21840000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
53 | SOLAR POWERED STREETLIGHT IN ORHINMWON/UHUNMWODE FED. CONSTITUENCY 6, EDO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 25000000 | 2014-11-17 | 2014-11-17 | √ | BERNAUX SERVICES LTD | 2014-11-19 | 10920000 | 30DAYS | 2014-11-26 | 10920000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
54 | SOLAR POWERED STREETLIGHT IN ORHINMWON/UHUNMWODE FED. CONSTITUENCY 7, EDO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 25000000 | 2014-11-17 | 2014-11-17 | √ | SAAB COMMERCIAL NIG LTD | 2014-11-19 | 10920000 | 30DAYS | 2014-11-26 | 10920000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
55 | ESTABLISHMENT OF 38NOS STAND SOLAR POWER STREETLIGHT AT UHUNMWODE LGA 1, EDO STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 35000000 | 2014-11-17 | 2014-11-17 | √ | HELMA ENGINEERING CONSULTANTS LTD | 2014-11-19 | 15600000 | 30DAYS | 2014-11-26 | 15600000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
56 | SOLAR POWERED STREETLIGHT AT OKAKA, ILORIN, KWARA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 10000000 | 2014-11-17 | 2014-11-17 | √ | NANYEL NIG LTD | 2014-11-19 | 3900000 | 30DAYS | 2014-11-26 | 3900000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
MAINTENANCE
1 | REHABILITATION OF SOLAR POWERED BOREHOLES AT SOBA FEDERAL CONSTITUENCY, KADUNA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 20000000 | 2014-11-17 | 2014-11-17 | √ | EAUXWELL NIG LTD | 2014-11-19 | 8974350 | 30DAYS | 2014-11-26 | NIL | 2015-03-31 | NOT EXECUTED | 0% | N/A | NIL
2 | REHABILITATION OF SOLAR POWERED STREET LIGHTS SOBA FEDERAL CONSTITUENCY, KADUNA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 10000000 | 2014-11-17 | 2014-11-17 | √ | TURK- AFRIQUE ENERGY LTD | 2014-11-19 | 4472773 | 30DAYS | 2014-11-26 | 4472773 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
BOREHOLES
| PROVISION OF 6 NOS SOLAR POWERED BOREHOLES, KABBA - BUNU & IJUMU LGAs, KOGI STATE (N45,000,000.00) | [5 empty] | 45000000 | [13 empty] | NIL
1 | PROVISION OF 6 NOS SOLAR POWERED BOREHOLES, KABBA LGAs, KOGI STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 |  | 2014-11-17 | 2014-11-17 | √ | MASON GLOBAL CONSTRUCTION LTD | 2014-11-19 | 6500000 | 30DAYS | 2014-11-26 | 6500000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
2 | PROVISION OF 6 NOS SOLAR POWERED BOREHOLES, BUNU LGAs, KOGI STATE 1 | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 |  | 2014-11-17 | 2014-11-17 | √ | KAYBOS NIG LTD | 2014-11-19 | 6500000 | 30DAYS | 2014-11-26 | 6500000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
3 | PROVISION OF 6 NOS SOLAR POWERED BOREHOLES, BUNU LGAs, KOGI STATE 2 | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 |  | 2014-11-17 | 2014-11-17 | √ | SAWFAJ RESOURCES & INVST. LTD | 2014-11-19 | 6500000 | 30DAYS | 2014-11-26 | 6500000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
4 | SOLAR POWERED BOREHOLE AT KAJOLA AREA OF KABBA TOWN, KABBA/BUNU LGA, KOGI STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 10000000 | 2014-11-17 | 2014-11-17 | √ | TOLIVIA NIG LTD | 2014-11-19 | 6500000 | 30DAYS | 2014-11-26 | 6500000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
5 | SOLAR WATER SCHEME AT ASHAKA, NDOKWA/UKWUANI FEDERAL CONSTITUENCY, DELTA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 10000000 | 2014-11-17 | 2014-11-17 | √ | IGZIABAAHER LTD | 2014-11-19 | 6500000 | 30DAYS | 2014-11-26 | 6500000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
6 | SOLAR WATER SCHEME AND DISTRIBUTION IN ABBI, NDOKWA/UKWUANI FEDERAL CONSTITUENCY, DELTA STATE | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 10000000 | 2014-11-17 | 2014-11-17 | √ | SKYVIEW INTEGRATED MULTI CONCEPT LTD | 2014-11-19 | 6500000 | 30DAYS | 2014-11-26 | 6500000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
| SOLAR BOREHOLES AT YEWA NORTH/IMEKO-AFON FEDERAL CONSTITUENCY OF OGUN STATE. (N21,000,000.00) | [5 empty] | 21000000
7 | SOLAR BOREHOLES AT YEWA NORTH, YEWA NORTH /IMEKO-AFON FEDERAL CONSTITUENCY OF OGUN STATE. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 |  | 2014-11-17 | 2014-11-17 | √ | MAJUVC ENGINEERING NIG LTD | 2014-11-19 | 6500000 | 30DAYS | 2014-11-26 | 6500000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
8 | SOLAR BOREHOLES AT IMEKO-AFON, YEWA NORTH /IMEKO-AFON FEDERAL CONSTITUENCY OF OGUN STATE. | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 |  | 2014-11-17 | 2014-11-17 | √ | DAHALA CONSTRUCTION NIG LTD | 2014-11-19 | 6500000 | 30DAYS | 2014-11-26 | 6500000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
| SOLAR POWERED BOREHOLE (4 POLES) IN ARUMOGIJA/AJAGBA AXIS, ILAJE/ESEODO, ONDO STATE (26,000,000) | [5 empty] | 26000000
9 | SOLAR POWERED BOREHOLE (4 POLES) IN ARUMOGIJA/AJAGBA AXIS, ILAJE/ESEODO, ONDO STATE 1 | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 |  | 2014-11-17 | 2014-11-17 | √ | BROWN INTERATED ENEGY LIMITED | 2014-11-19 | 6500000 | 30DAYS | 2014-11-26 | 6500000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
10 | SOLAR POWERED BOREHOLE (4 POLES) IN ARUMOGIJA/AJAGBA AXIS, ILAJE/ESEODO, ONDO STATE 2 | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 |  | 2014-11-17 | 2014-11-17 | √ | FASTRACK ENGINEERING LTD | 2014-11-19 | 6500000 | 30DAYS | 2014-11-26 | 6500000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
ECN CORE PROJECTS
1 | PROCUREMENT OF PROJECT MONITORING EQUIPMENT (PEUGEOT 508, ALLURE, FULL OPTION AUTO) | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N50M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 10000000 | 2014-11-17 | 2014-11-17 | √ | ASD MOTORS NIG LTD | 2014-11-19 | 9350000 | 18WKS | 2014-11-26 | 9350000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
| UPGRADING AND OVERHAULING OF ECN FACILITIES AND EQUIPMENTS: A) COMPUTERIZATION OF FINANCE AND ADMINISTRATIVE DEPARTMENT (N15M), B) SECURITY FACILITIES (N5M), PABX AND ACCESSORIES(N5M), COMPUTER AND INTERNET FACILITIES (N10M) etc (5,000,000) | [5 empty] | 5000000
2 | UPGRADING AND OVERHAULING OF ECN FACILITIES AND EQUIPMENTS: B) SECURITY FACILITIES (N5M), | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N50M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 2050000 | 2014-11-17 | 2014-11-17 | √ | JOKIATOSAM ENGINEERING LTD | 2014-11-19 | 2047950 | 18WKS | 2014-11-26 | 2047950 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
3 | UPGRADING AND OVERHAULING OF ECN FACILITIES AND EQUIPMENTS: INTERNET BANDWIDTH SUBCRIPTION ACESS (1.5Mbps) Via Fibre | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N50M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 2950000 | 2014-11-17 | 2014-11-17 | √ | GALAXY BACKBONE LTD | 2014-11-19 | 2875194 | 18WKS | 2014-11-26 | 2875194 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
4 | PILOT BIOMASS PROJECT: A) DEVELOPMENT OF ENERGY FARM FOR THE PRODUCTION OF BIO DIESEL FROM JATROPHA, B) BIOGAS PLANT FOR HEATING, C) AWARENESS CREATION | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 6935333 | 2014-11-17 | 2014-11-17 | √ | KUNDISA ENTERPRISES LTD | 2014-11-19 | 6683905 | 18WKS | 2014-11-26 | 6683905 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
5 | COMPLETE RENOVATION AND FURNISHING OF ECN PODIUM BUILDING | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N50M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 5000000 | 2014-11-17 | 2014-11-17 | √ | UNIVERSAL ENGINEERING PILLARS LTD | 2014-11-19 | 4911637.5 | 18WKS | 2014-11-26 | 4911637.5 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
6 | SOLAR PV HYBRID AS ALTERNATIVE ELECTRICITY SOURCE PILOT PROJECTS (SOLAR/WIND, SOLAR/BIOMASS, SOLAR/HYDROPLANT | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 10000000 | 2014-11-17 | 2014-11-17 | √ | SOLAR TECH ENERGY DEVELOMENT CO LTD | 2014-11-19 | 9341062 | 18WKS | 2014-11-26 | 9341062 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
7 | NEW HYDROPOWER SYSTEMS: A) PROMOTION OF HYDROKINETIC POWER TURBINES, B) FEASIBILITIES OF SHP POTENTIALS IN OGUN AND ONDO STATES (75,000,000) | [5 empty] | 75000000
| NEW HYDROPOWER SYSTEMS: B) FEASIBILITIES OF SHP POTENTIALS IN ONDO STATES | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N50M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 21000000 | 2014-11-17 | 2014-11-17 | √ | O.T. OTIS ENGINEERING LTD | 2014-11-19 | 20890531 | 18WKS | 2014-11-26 | 20890531 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
| NEW HYDROPOWER SYSTEMS: A) PROMOTION OF HYDROKINETIC POWER TURBINES, PILOT PLANT OGUN STATES | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N250M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 54000000 | 2014-11-17 | 2014-11-17 | √ | GEOSOFT SOLUTION LTD | 2014-11-19 | 25164562.5 | 18WKS | 2014-11-26 | 25164562.5 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
8 | NATIONAL ENERGY DATA BANK DEVELOPMENT (HARDWARE AND SPECIALISED SOFTWARES, ETC.) | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N50M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 10000000 | 2014-11-17 | 2014-11-17 | √ | PATIBON SERVICES LTD | 2014-11-19 | 9860812 | 18WKS | 2014-11-26 | 9860812 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
9 | COUNTERPART FUNDING A) ESTABLISHMENT OF UNIDO REGIONAL CENTRE FOR SMALL HYDRO POWER IN ABUJA. B) IRENA AND WEC. C) UNDP – NIGERIA ENERGY LABELING PROGRAMME | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N50M | OPEN COMPETATIVE BIDING | 2014-08-11 | 2014-10-09 | 10000000 | 2014-11-17 | 2014-11-17 | √ | UNIDO, IRENA & WEC | 2014-11-19 | 10000000 | 18WKS | 2014-11-26 | 10000000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
10 | COUNTERPART FUNDING ON THE ESTABLISHMENT OF CLEAN COOK STOVE STANDARD TESTING AND TRAINING LABORATORY: A) TRAINING OF ARTISANS, WOMEN AND CRAFTSMEN, B) PROCUREMENT OF EQUIPMENT AT NCERD, NSUKKA | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N50M | OPEN COMPETITIVE BIDING | 2014-08-11 | 2014-10-09 | 5000000 | 2014-11-17 | 2014-11-17 | √ | ICEED | 2014-11-19 | 5000000 | 18WKS | 2014-11-26 | 5000000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL
ECN IN-HOUSE CORE PROJECTS
1 | SUSTAINABLE ENERGY DEVELOPMENT: A) ENERGY MODELLING: MEAD, MESSAGE,WASP (IAEA), 2050 PATHWAY CALCULATOR (BRITISH COUNCIL), REEL COST (DOE), ENVIRONMENTAL AND CLIMATE CHANGE IMPACT; B) AWARENESS CREATION | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N50M | R&D | N/A | N/A | 15000000 | 2014-11-17 | 2014-11-17 | √ | ECN | N/A | 15000000 | 18WKS | 2014-11-26 | 15000000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL | BPP APPROVED (BPP/S.1/14/A&WR/VOL.1/023)
2 | REVIEW OF NATIONAL ENERGY MASTER-PLAN PHASE II: A) NATIONAL ENERGY POLICY REVIEW B) NATIONAL EMP AND REVIEW C) LEGAL INSTRUMENT DEVELOPMENT | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N50M | R&D | N/A | N/A | 20000000 | 2014-11-17 | 2014-11-17 | √ | ECN | N/A | 20000000 | 18WKS | 2014-11-26 | 20000000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL | BPP APPROVED (BPP/S.1/14/A&WR/VOL.1/023)
3 | DEVELOPMENT OF ENERGY BALANCE FOR NIGERIA | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N50M | R&D | N/A | N/A | 10000000 | 2014-11-17 | 2014-11-17 | √ | ECN | N/A | 10000000 | 18WKS | 2014-11-26 | 10000000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL | BPP APPROVED (BPP/S.1/14/A&WR/VOL.1/023)
4 | NATIONAL ENERGY SUMMIT FOR STAKEHOLDERS IN ENERGY SECTOR | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N50M | R&D | N/A | N/A | 20000000 | 2014-11-17 | 2014-11-17 | √ | ECN | N/A | 20000000 | 18WKS | 2014-11-26 | 20000000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL | BPP APPROVED (BPP/S.1/14/A&WR/VOL.1/023)
5 | ECN/NYSC RENEWABLE ENERGY TRAINING PROGRAMME - PROMOTION OF SELF EMPLOYMENT OPPORTUNITIES AND JOB CREATION FOR CORP MEMBERS IN SIX (6) GEO POLITICAL ZONES (15 MILIION PER ZONE) | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N50M | R&D | N/A | N/A | 15000000 | 2014-11-17 | 2014-11-17 | √ | ECN | N/A | 15000000 | 18WKS | 2014-11-26 | 15000000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL | BPP APPROVED (BPP/S.1/14/A&WR/VOL.1/023)
6 | MONITORING THE IMPLEMENTATION OF GOVERNMENT POLICIES ON ENERGY. A) CONDUCT OF SURVEYS AND SEMINARS B) PRODUCTION OF ANNUAL ENERGY REPORTS AND OUTLOOK | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N50M | R&D | N/A | N/A | 10000000 | 2014-11-17 | 2014-11-17 | √ | ECN | N/A | 10000000 | 18WKS | 2014-11-26 | 10000000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL | BPP APPROVED (BPP/S.1/14/A&WR/VOL.1/023)
7 | STUDY/SURVEY ON ENERGY CONSUMPTION PATTERN IN HOUSEHOLD, SERVICES, INDUSTRIES AND TRANSPORT SECTORS | DAILY TRUST, THE GUARDIAN NEWSPAPERS AND FEDERAL TENDER JOURNAL (14/07/14) | LESS THAN N50M | R&D | N/A | N/A | 10000000 | 2014-11-17 | 2014-11-17 | √ | ECN | N/A | 10000000 | 18WKS | 2014-11-26 | 10000000 | 2015-03-31 | COMPLETED | 100% | N/A | NIL | BPP APPROVED (BPP/S.1/14/A&WR/VOL.1/023)
OUTSTANDINDING PAYMENTS
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2014 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | COMPLETION OF ONGOING SOLAR STREET PROJECTS IN OGBOMOSHO NORTH LGA 1, OYO STATE | N/A | LESS THAN N250M | N/A | N/A | N/A | 22800000 | 2014-09-17 | 2014-09-17 | N/A | FUSE ENGINEERS LTD | 2012 | 30400000 | 6WKS | 2014-11-17 | 22800000 | N/A | COMPLETED | 100% | N/A | NIL | PAYMENT OF 2012 OUTSTANDING PROJECTS
2 | COMPLETION OF ONGOING SOLAR STREET PROJECTS IN ORIRE LGA, OYO STATE | N/A | LESS THAN N250M | N/A | N/A | N/A | 22800000 | 2014-09-17 | 2014-09-17 | N/A | KGLM INTERNATIONAL LTD | 2012 | 30400000 | 6WKS | 2014-11-17 | 22800000 | N/A | COMPLETED | 100% | N/A | NIL | PAYMENT OF 2012 OUTSTANDING PROJECTS
3 | COMPLETION OF ONGOING SOLAR STREET PROJECTS IN OGBOMOSHO SOUTH LGA 1, OYO STATE | N/A | LESS THAN N250M | N/A | N/A | N/A | 30400000 | 2014-09-17 | 2014-09-17 | N/A | MERCHANTILE INFO SYSTEMS LTD | 2012 | 30400000 | 6WKS | 2014-11-17 | 30400000 | N/A | COMPLETED | 100% | N/A | NIL | PAYMENT OF 2012 OUTSTANDING PROJECTS
| COMPLETION OF SOLAR BOREHOLE IN OGBOMOSHO 1,2 AND 7, OYO STATE | [5 empty] | 17500000
4 | COMPLETION OF SOLAR BOREHOLE IN OGBOMOSHO 1, OYO STATE | N/A | LESS THAN N250M | N/A | N/A | N/A |  | 2014-09-17 | 2014-09-17 | N/A | FUSE ENGINEERS LTD | 2012 | 7750000 | 6WKS | 2014-11-17 | 5250000 | N/A | COMPLETED | 100% | N/A | NIL | PAYMENT OF 2012 OUTSTANDING PROJECTS
5 | COMPLETION OF SOLAR BOREHOLE IN OGBOMOSHO 2 OYO STATE | N/A | LESS THAN N250M | N/A | N/A | N/A |  | 2014-09-17 | 2014-09-17 | N/A | FUSE ENGINEERS LTD | 2012 | 7750000 | 6WKS | 2014-11-17 | 6125000 | N/A | COMPLETED | 100% | N/A | NIL | PAYMENT OF 2012 OUTSTANDING PROJECTS
6 | COMPLETION OF SOLAR BOREHOLE IN OGBOMOSHO 7 OYO STATE | N/A | LESS THAN N250M | N/A | N/A | N/A |  | 2014-09-17 | 2014-09-17 | N/A | ARTIC INTEGRATED SERVICES LTD | 2012 | 7750000 | 6WKS | 2014-11-17 | 6125000 | N/A | COMPLETED | 100% | N/A | NIL | PAYMENT OF 2012 OUTSTANDING PROJECTS
| CONSTRUCTION OF SOLAR STREET LIGHT IN SELECTED AREAS OF GOMBE NORTH SENATORIAL DISTRICT (ONGOING) | [5 empty] | 50000000
7 | CONSTRUCTION OF SOLAR STREET LIGHT IN SELECTED AREAS OF GOMBE NORTH SENATORIAL DISTRICT (ONGOING) (GOMBE 1) | N/A | LESS THAN N250M | N/A | N/A | N/A |  | 2014-09-17 | 2014-09-17 | N/A | FESHARE GLOBAL NETWORK LTD | 2012 | 12000000 | 6WKS | 2014-11-17 | 12000000 | N/A | COMPLETED | 100% | N/A | NIL | PAYMENT OF 2012 OUTSTANDING PROJECTS
8 | CONSTRUCTION OF SOLAR STREET LIGHT IN SELECTED AREAS OF GOMBE NORTH SENATORIAL DISTRICT (ONGOING) (FUNAKAYE LGA) | N/A | LESS THAN N250M | N/A | N/A | N/A |  | 2014-09-17 | 2014-09-17 | N/A | JAMAJI WORLDWIDE SOLUTION LTD | 2012 | 12000000 | 6WKS | 2014-11-17 | 12000000 | N/A | COMPLETED | 100% | N/A | NIL | PAYMENT OF 2012 OUTSTANDING PROJECTS
9 | CONSTRUCTION OF SOLAR STREET LIGHT IN SELECTED AREAS OF GOMBE NORTH SENATORIAL DISTRICT (ONGOING) (KWAMI LGA) | N/A | LESS THAN N250M | N/A | N/A | N/A |  | 2014-09-17 | 2014-09-17 | N/A | NAFSON GLOBAL INVESTMENT LTD | 2012 | 12000000 | 6WKS | 2014-11-17 | 12000000 | N/A | COMPLETED | 100% | N/A | NIL | PAYMENT OF 2012 OUTSTANDING PROJECTS
10 | SOLAR STREET LIGHT AT BUNUNU (OUTSTANDING LIABILITY) | N/A | LESS THAN N250M | N/A | N/A | N/A | 30000000 | 2014-09-17 | 2014-09-17 | N/A | SUBULA INTEGRATED SERVICES LTD | 2010 | 33540000 | 6WKS | 2014-11-17 | 28509000 | N/A | COMPLETED | 100% | N/A | NIL | PAYMENT OF 2010 OUTSTANDING PROJECTS
11 | SOLAR STREETLIGHT AT IKEM - ISU - UZOR LGA, ENUGU STATE | N/A | LESS THAN N250M | N/A | N/A | N/A | 30000000 | 2014-09-17 | 2014-09-17 | N/A | BOLDOVE NIGERIA LTD | 2010 | 49920000 | 6WKS | 2014-11-17 | 22464000 | N/A | COMPLETED | 100% | N/A | NIL | PAYMENT OF 2010 OUTSTANDING PROJECTS
| TOTAL | [11 empty] | 2396724371.62

## FINANCE
RETURNS ON YEAR 2014 CAPITAL PROJECTS
PROCURING ENTITY (MDA) : |  | FEDERAL MINISTRY OF FINANCE
MINISTRY : |  | FEDERAL MINISTRY OF FINANCE, HEADQUARTERS, ABUJA
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2014 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | BROAD BAND- INSTALLATION OF INTERNET ACCESS CONNECTIVITY TO THE FMF WI-FI | 2014-07-17 | MTB | NCB | 2014-07-23 | 2014-07-23 | 37500000 | NIL | 30/07/14 | M/S LAYER 3 | M/S LAYER 3 | 30/07/14 | 9797046 | 1 Year | 2014-09-01 | 9797046 | 1 Year | COMPLETED | 100% IMPLEMENTED | NIL | NIL | To include mtce. retainership
2 | BROAD BAND- PROVISION OF FIBRE CABLING FROM CITY FIBRE METRO TO FMF | 2014-07-17 | MTB | NCB | 2014-07-23 | 2014-07-23 | same | NIL | 30/07/14 | M/S SUNNEX | M/S SUNNEX | 30/07/14 | 9397000 | 1 month | 2014-09-01 | 9397000 | 1 Month | COMPLETED | 100% IMPLEMENTED | NIL | NIL
3 | CONDUCT MONITORING & EVALUATION ON THE MINISTRY FEDERAL EXECUTIVE COUNCIL APPROVED PROJECTS, DONOR PROJECTS & PROGRAMME OF FMF & PURCHASE OF TOYOTA LAND CRUISER V X V 8 ENGINE & TOYOTA HILUX DOUBLE CABIN 2.7 L PETROL ENGINE. | June 16-June 29 | MTB | NCB | 2014-08-05 | 2015-11-03 | same | NIL | 14/11/14 | M/S ERNST ABEGBE & CO. | M/S ERNST ABEGBE & CO. | 14/11/14 | 55500500 | 1 Year |  | 20000000 | 1 Year | ONGOING | 70% IMPLEMENTED INTERIM REPORT SUBMITTED. | NIL | NIL | To conduct on quarterly basis. Vehicles already purchased.
4 | CONDUCT STUDY ON ANALYSIS OF NAT. TRADE POLICY PROCESS CREATION OF BEST PRACTICES IN TRADE MAKING IN NIG. FOREIGN DIRECT INFLOW OF INV. TO NIG. | 16-19/06/2014 | MTB | NCB | 2014-08-05 | 2014-11-03 | 291147591 | NIL | 14/11/14 | M/S ECHO TECH. P & S LTD. | M/S ECHO TECH. P & S LTD. | 14/11/14 | 14855000 | 6 Months | 2014-12-15 | NIL | 6 Months | ONGOING | 50% IMPLEMENTED INTERIM REPORT SUBMITTED. | NIL | NIL | Project on going.
5 | CONDUCT STUDY REVIEW OF GOVT. POLICIES & INTERVENTION IN PUBLIC HOUSING FINANCING IN NIG. FOR FMF | 16-19/06/2014 | MTB | NCB | 2014-08-05 | 2014-11-03 | same | NIL | 14/11/14 | M/S INSTITUTE FOR HUMAN SETTLEMENT & ENVIRONMENT | M/S INSTITUTE FOR HUMAN SETTLEMENT & ENVIRONMENT | 14/11/14 | 20025000 | 1 Year | 2014-12-15 | NIL | 6 Months | ONGOING | 50% IMPLEMENTED INTERIM REPORT SUBMITTED. | NIL | NIL | Project on going.
6 | CONDUCT STUDY ON ASSESSMENT OF FOREIGN DIRECT INFLOW OF INV. TO NIG. 1999-2013 | 16-19/06/2014 | MTB | NCB | 2014-08-05 |  | same | NIL | 14/11/14 | M/S EQUILIBRIA CONSULTING NIG. LTD. | M/S EQUILIBRIA CONSULTING NIG. LTD. | 2014-11-14 | 20025000 | 1 Year | 2014-12-15 | NIL | 6 Months | ONGOING | 50% IMPLEMENTED INTERIM REPORT SUBMITTED. | NIL | NIL | Project on going.
7 | CONDUCT STUDY ON COST BENEFIT ANALYSIS EXPORT EXPANSION GRANT IN NIG. | 16-19/06/2014 | MTB | NCB | 2014-08-05 | 2014-11-03 | same | NIL | 14/11/14 | M/S CONSULTING NIG. LTD. | M/S CONSULTING NIG. LTD. | 14/11/14 | 14084069 | 1 Year | 2014-12-15 | NIL | 6 Months | ONGOING | 50% IMPLEMENTED INTERIM REPORT SUBMITTED. | NIL | NIL | Project on going.
8 | PROCUREMENT OF 1NO. PROJECT VEHICHLE LAND CRUISER V X V 8 ENGINE 4-SPEED AUTOMATIC TRANSMISSION | 16-19/06/2014 | MTB | NCB | 2014-08-05 | 2014-12-11 | 568859940 | NIL | 24/12/2014 | M/S ERNST ABEGBE & CO. | M/S ERNST ABEGBE & CO. | 24/12/2014 | 26000000 | 1 Year | 2015-01-25 | NIL | 2 Weeks | COMPLETED | 100% IMPLEMENTED . | NIL | NIL | Project completed.
9 | PROCUREMENT OF 1NO. 18 SEATER TOYOTA HIACE BUS FOR NEMT/EMIT | 16-19/06/2014 | MTB | NCB | 2014-08-05 | 2014-12-11 | same | NIL | 24/12/2014 | M/S BLESSING & FAITH NIG. LTD. | M/S BLESSING & FAITH NIG. LTD. | 24/12/2014 | 9560000 |  | 2015-01-25 | NIL | 2 Weeks | COMPLETED | GOODS DELIVERED, BUT NOT YET PAID. | NIL | NIL | Project completed.
10 | INSTALLATION OF 3NOS. MOTOTRISED GATE BARRIER, CAR PARK INTRUSION, MGT. SYSTEM AND 2NOS. FULL BODY SCANNERS | 16-19/06/2014 | MTB | NCB | 2014-08-05 | 2014-10-09 | 600000000 | NIL | 23/10/14 | M/S MUBARAK REAL SOLID SYSTEM LTD. | M/S MUBARAK REAL SOLID SYSTEM LTD. | 23/10/14 | 248550000 | 1 Year | 2015-11-24 | 50000000 | 1 Year | ONGOING | 60% IMPLEMENTED. | NIL | NIL | Project on going.
11 | PROCUREMENT OF VEHICLES 2NOS. 4x4 JEEP, 1NO. 4WHEEL DRIVE VAN & 1NO. SALOON CAR | 16-19/06/2014 | MTB | NCB | 2014-08-05 | 2014-10-09 | 8000000000 | NIL | 23/10/14 | M/S BLESSING & FAITH MOTORS NIG. LTD. | M/S BLESSING & FAITH MOTORS NIG. LTD. | 23/10/14 | 52400000 | 1 Year | 2015-11-24 | 26000000 | 2 Weeks | COMPLETED | 100% IMPLEMENTED. | NIL | NIL | Project completed.
12 | PROCUREMENT OF CONSULTANTS FOR THE YOUWIN VENTURE CAPITAL FUND TO SUPPORT THE SMES IN NIGERIA | 16-19/06/2014 | MTB | NCB | 2014-08-05 | 2014-11-06 | same | NIL | 2014-11-21 | M/S ERNST & YOUNG FIRM OF CHARTERED ACCOUNTANT | M/S ERNST & YOUNG FIRM OF CHARTERED ACCOUNTANT | 2014-11-21 | 54341000 | 3 Months | 2014-12-22 | NIL | 3 Month | COMPLETED | 90% IMPLEMENTED. | NIL | NIL | Project completed.
| TOTAL | [11 empty] | 534534615

## FCSC
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) : |  | FEDERAL CIVIL SERVICE COMMISSION
MINISTRY :
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2014 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | Supply of 10,000 Litres of Diesel (AGO) to FCSC | RFQ on 30-01-14 | Accounting officer | National Shopping | 2014-02-03 | 2014-02-03 | 18800142 | N/A | 2014-02-04 | Yes | M/S A.G.M Engineering Allied Service Ltd | 2014-02-04 | 1980000 | 7 days | 2014-02-06 | 1980000 | 2014-02-11 | Completed | 100% | Nil | Nil
2 | Supply of 10,000 Litres of Diesel (AGO) to FCSC | RFQ on 19-03-14 | Accounting officer | National Shopping | 2014-03-21 | 2014-03-21 | 18800142 | N/A | 2014-03-21 | Yes | M/S A.G.M Engineering Allied Service Ltd | 2014-03-21 | 1985000 | 7 days | 2014-03-21 | 1985000 | 2014-03-28 | Completed | 100% | Nil | Nil
3 | Supply of 10,000 Litres of Diesel (AGO) to FCSC | RFQ on 09-04-14 | Accounting officer | National Shopping | 2014-04-11 | 2014-04-11 | 18800142 | N/A | 2014-04-11 | Yes | M/S A.G.M Engineering Allied Service Ltd | 2014-04-11 | 1990000 | 7 days | 2014-04-10 | 1990000 | 2014-04-18 | Completed | 100% | Nil | Nil
4 | Supply of 10,000 Litres of Diesel (AGO) to FCSC | RFQ on 28-05-14 | Accounting officer | National Shopping | 2014-05-30 | 2014-05-30 | 18800142 | N/A | 2014-06-06 | Yes | M/S Usbabs Petroleum Ltd | 2014-06-06 | 1985000 | 7 days | 2014-06-06 | 1985000 | 2014-06-13 | Completed | 100% | Nil | Nil
5 | Supply of 10,000 Litres of Diesel (AGO) to FCSC | RFQ on 02-07-14 | Accounting officer | National Shopping | 2014-07-04 | 2014-07-04 | 18800142 | N/A | 2014-07-04 | Yes | M/S Usbabs Petroleum Ltd | 2014-07-04 | 1985000 | 7 days | 2014-07-06 | 1985000 | 2014-07-13 | Completed | 100% | Nil | Nil
6 | Supply of Consumable Store Items. | RFQ on 18-07-14 | Accounting officer | National Shopping | 2014-07-25 | 2014-07-27 | 16178332 | N/A | 2014-07-27 | Yes | M/S New World Corporate Business Venture Ltd | 2014-07-28 | 2489400 | 7 days | 2014-07-30 | 2489400 | 2014-08-03 | Completed | 100% | Nil | Nil
7 | Cleaning & Janitorial Services of the main Office of the FCSC & AAPSCOMs Building for One (1) year | 2013 | Accounting officer | Repeat Procurement Method | 2014 | 2014 | 14074914 | N/A | 2014-07-31 | Yes | M/S Sepsal Nig. Ltd | 2014-08-01 | 10610250 | 12 Months | 2014-08-01 | 4420937 | 2015-07-31 | On-Going | 42% | Nil | Nil
8 | Horticulture & Cleaning Services of the entire Surroundings of the FCSC for one (1) year | 2013 | Accounting officer | Repeat Procurement Method | 2014 | 2014 | 14074914 | N/A | 2014-07-31 | Yes | M/S Okebehz Nig. Ltd | 2014-08-01 | 6299475 | 12 Months | 2014-08-01 | 2624782 | 2015-07-31 | On-Going | 42% | Nil | Nil
9 | Supply of 10,000 Litres of Diesel (AGO) to FCSC | RFQ on 06-08-14 | Accounting officer | National Shopping | 2014-08-08 | 2014-08-12 | 18800142 | N/A | 2014-08-12 | Yes | M/S Algab Global Concept Nig. Ltd | 2014-08-12 | 1980000 | 7 days | 2014-08-12 | 1980000 | 2014-08-13 | Completed | 100% | Nil | Nil
10 | Supply of Consumable Store Items. | RFQ on 18-08-14 | Accounting officer | National Shopping | 2014-08-25 | 2014-08-26 | 16178332 | N/A | 2014-08-27 | Yes | M/S Todas Ventures & Co. Nig Ltd | 2014-08-27 | 2492100 | 7 days | 2014-08-29 | 2492100 | 2014-09-02 | Completed | 100% | Nil | Nil
11 | Printing of Official Documents of FCSC | Notice Board Advert on 29-08-14 | Accounting Officer | National Shopping | 2014-09-18 | 2014-09-18 | 6544800 | N/A | 2014-09-24 | Yes | M/S Charvid Digital Press | 2014-09-24 | 4853800 | 7days | 2014-09-24 | 4853800 | 2014-10-02 | Completed | 100% | Nil | Nil
12 | Supply of Consumable Store Items. | RFQ on 05-09-14 | Accounting officer | National Shopping | 2014-09-12 | 2014-09-16 | 16178332 | N/A | 2014-09-16 | Yes | M/S Isham Ventures & Consulting Limited | 2014-09-16 | 2493450 | 7 days | 2014-09-17 | ₦2,493,450.00 | 2014-09-22 | Completd | 100% | Nil | Nil
13 | Supply of 10,000 Litres of Diesel (AGO) to FCSC | RFQ on 11-09-14 | Accounting officer | National Shopping | 2014-09-15 | 2014-09-15 | 18800142 | N/A | 2014-09-16 | Yes | M/S Usbabs Petroleum Ltd | 2014-09-16 | 1985000 | 7 days | 2014-09-16 | 1985000 | 2014-09-22 | Completed | 100% | Nil | Nil
14 | Supply of 685 Bags of Rice & 300 ctns of Vegetable Oil | RFQ on 17-09-14 | MTB | National Shopping | 2014-09-22 | 2014-09-22 | 30715831 | N/A | 2014-09-24 | Yes | M/S Algab Global Concept Nig. Ltd | 2014-09-26 | 10718400 | 7 Days | 2014-09-27 | 10718400 | 2014-10-03 | Completed | 100% | Nil | Nil
15 | Supply of 10,000 Litres of Diesel (AGO) to FCSC | RFQ on 03-11-14 | Accounting officer | Repeat Procurement Method | 2014-09-15 | 2014-09-15 | 18800142 | N/A | 2014-11-03 | Yes | M/S Usbabs Petroleum Ltd | 2014-11-03 | 1985000 | 7 days | 2014-11-04 | 1985000 | 2014-11-10 | Completed | 100% | Nil | Nil
16 | Supply of 10,000 Litres of Diesel (AGO) to FCSC | RFQ on 24-11-14 | Accounting officer | National Shopping | 2014-11-25 | 2014-11-26 | 18800142 | N/A | 2014-11-26 | Yes | M/S Algab Global Concept Nig. Ltd | 2014-11-26 | 1985000 | 7 days | 2014-11-26 | 1985000 | 2014-12-01 | Completed | 100% | Nil | Nil
17 | Renovation of Room 321, 3rd Floor of FCSC | RFQ on 18-11-14 | Accounting officer | National Shopping | 2014-11-25 | 2014-11-25 | 14074914 | N/A | 2014-11-26 | Yes | M/S Etokams Ventures Ltd | 2014-11-26 | 1582581 | 14 days | 2014-11-26 | N/A | 2014-12-09 | Completed on 19-12-14 & Paid on 02-04-15 | 100% | Nil | Nil
18 | Supply & Installation of 20 Nos Computer Tables & Chairs | RFQ on 21-11-14 | Accounting officer | National Shopping | 2014-11-28 | 2014-12-01 | 2349000 | N/A | 2014-12-01 | Yes | M/S Victo Tech & Company | 2014-12-01 | 2400000 | 14 days | 2014-12-02 | 2400000 | 2014-12-10 | Completed | 100% | Nil | Nil
19 | Supply & Installation of IP Phones, PA System, Dell Projector & Headphones in FCSC | RFQ on 24-11-14 | Accounting officer | National Shopping | 2014-12-01 | 2014-12-02 | 2727000 | N/A | 2014-12-01 | Yes | M/S Davas Business Services Ltd | 2014-12-02 | 2400000 | 14 days | 2014-12-03 | 2160000 | 2014-12-17 | Completed on 29-12-14 | 100% | Nil | Nil
20 | Supply and Installation of VisaFone DeskTop and PABX TDA 100 Panasonic 64 Extentions | Nil | Accounting officer | Direct Procurement (Single Source) | Nil | 2014-12-03 | 5452494 | N/A | 2014-12-03 | N/A | M/S Gigaxy Soft Nig. Ltd | 2014-12-03 | 1496100 | 7 days | 2014-12-03 | N/A | 2014-12-10 | Completed on 10-12-14 and paid on 25-02-15 | 100% | Nil | Nil
21 | Supply & Installation of Server & Networking Services in the FCSC | RFQ on 24-11-14 | Accounting officer | National Shopping | 2014-11-24 | 2014-12-05 | 3780000 | N/A | 2014-12-05 | Yes | M/S Marcus Grace Associates | 2014-12-05 | 3600000 | 14 days | 2014-12-08 | 3600000 | 2014-12-15 | Completed | 100% | Nil | Nil
22 | Supply & Installation of 10 Nos. HP all-in one Touch Screen Work Stations Quard Core 1.5 8GB & application softwares. | RFQ on 28-11-14 | Accounting officer | National Shopping | 2014-12-05 | 2014-12-08 | 4657500 | N/A | 2014-12-08 | Yes | M/S Perpetua Point Pillar Ltd | 2014-12-08 | 4600000 | 14 days | 2014-12-10 | 4600000 | 2014-12-24 | Completed on 17-12-14 | 100% | Nil | Nil
23 | Design, review & Development of a web portal for FCSC. | RFQ on 09-11-14 | Accounting officer | National Shopping | 2014-12-03 | 2014-12-04 | 5452494 | N/A | 2014-12-04 | Yes | M/S Jubilee Systems Ltd | 2014-12-09 | 620000 | 2 weeks | 2014-12-10 | N/A | 2014-12-24 | Completed on 19-12-14 & Paid on 02-04-15 | 100% | Nil | Nil
24 | Supply & Installation of 10 KVA Inverter (190V) Power Cable, Batteries, APC Surg Suppresors & UPS in the FCSC | RFQ on 03-12-145 | Accounting officer | National Shopping | 2014-12-10 | 2014-12-10 | 3408750 | N/A | 2014-12-10 | Yes | M/S McAbigail Geometric Ltd | 2014-12-10 | 3608000 | 14 days | 2014-12-11 | 3608000 | 2014-12-22 | Completed | 100% | Nil | Nil
25 | Supply of 685 Bags of Rice & 360 ctns of Vegetable Oil | RFQ on 11-12-14 | MTB | National Shopping | 2014-12-15 | 2014-12-15 | 30715831 | N/A | 2014-12-16 | Yes | M/S Algab Global Concept Nig. Ltd | 2014-12-17 | 11600000 | 5 Days | 2014-12-17 | N/A | 2014-12-21 | Completd & Paid on 19-02-15 | 100% | Nil | Nil
| TOTAL | [11 empty] | 89723556

## EDUCATION
PROCUREMENT RECORD
PROCURING ENTITY (MDA) : |  | FEDERAL MINISTRY OF EDUCATION
MINISTRY : |  | FEDERAL MINISTRY OF EDUCATION
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 13/05/2015 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 13/05/2015 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | CONSTRUCTION OF ONE (1) BLOCK OF 3 CLASSROOMS IBEREKODO HIGH SCHOOL, IGBOORA, IBARAKPA CENTRAL LGA OYO STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 17500000 | NIL | 21ST NOVEMBER, 2014 | VICNI ENGINEERING SERVICES LIMITED | VICNI ENGINEERING SERVICES LIMITED | 1ST DEC. 2014 | 12280988.22 | 8 WEEKS | 15TH. DECEMBER, 2014 | 12280988.22 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
2 | PROCUREMENT OF FURNITURES FOR PUPILS IBEREKODO HIGH SCHOOL, IGBOORA, IBARAKPA CENTRAL LGA OYO STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 22nd NOVEMBER, 2014 | VICNI ENGINEERING SERVICES LIMITED | VICNI ENGINEERING SERVICES LIMITED | 1ST DEC. 2014 | 4569000 | 8 WEEKS | 15TH. DECEMBER, 2015 | 4569000 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
3 | CONSTRUCTION OF 3 CLASSROOMS AT AUD MAIN PRY SCHOOL ABEOKUTA NORTH OGUN STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 10000000 | NIL | 23rd NOVEMBER, 2014 | MANIFOLD INTG SERVICES LTD | MANIFOLD INTG SERVICES LTD | 1ST DEC. 2014 | 9800516.22 | 8 WEEKS | 15TH. DECEMBER, 2016 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
4 | CONSTRUCTION OF 3 CLASSROOM BLOCKS AT OLG PRIMARY SCHOOL MALAAKA ALABATA WARD, OGUN STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 10000000 | NIL | 24th NOVEMBER, 2014 | ARICOTECH RES. ENGR LTD | ARICOTECH RES. ENGR LTD | 1ST DEC. 2014 | 9655440.15 | 8 WEEKS | 15TH. DECEMBER, 2017 | 9655440.15 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
5 | CONSTRUCTION OF 3 CLASSROOM BLOCKS OBA/OWODE, OGUN STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 10000000 | NIL | 25th NOVEMBER, 2014 | UGHAI CO. LIMITED | UGHAI CO. LIMITED | 1ST DEC. 2014 | 9978018 | 8 WEEKS | 15TH. DECEMBER, 2018 | 9978018 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
6 | CONSTRUCTION OF 1 NOS. BLOCKS OF 3 CLASSROOMS IJEMO, ABEOKUTA SOUTH OGUN STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 15000000 | NIL | 26th NOVEMBER, 2014 | ACROSS BORDER NIG. LTD | ACROSS BORDER NIG. LTD | 1ST DEC. 2014 | 12900004.5 | 8 WEEKS | 15TH. DECEMBER, 2019 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
7 | CONSTRUCTION OF 1 NOS. BLOCKS OF 3 CLASSROOMS AKE, ABEOKUTA SOUTH OGUN STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 15000000 | NIL | 27th NOVEMBER, 2014 | PRO-PLUS SYNERGY CONCEPTS LTD | PRO-PLUS SYNERGY CONCEPTS LTD | 1ST DEC. 2014 | 13774630 | 8 WEEKS | 15TH. DECEMBER, 2020 | 13774630 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
8 | CONSTRUCTION OF 1 NOS. BLOCKS OF 3 CLASSROOMS OLRUNTEDO, ABEOKUTA SOUTH OGUN STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 15000000 | NIL | 28th NOVEMBER, 2014 | HAVILA PARIOLA NIG. LIMITED | HAVILA PARIOLA NIG. LIMITED | 1ST DEC. 2014 | 12810121.4 | 8 WEEKS | 15TH. DECEMBER, 2021 | 12810121.4 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
9 | CONSTRUCTION OF 1 BLOCKS OF 3 CLASSROOMS AT LAYEMI PRIMARY SCH LAYEMI OGUN STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 10000000 | NIL | 29th NOVEMBER, 2014 | MAY FLOWS GLOBAL SERVICES LTD | MAY FLOWS GLOBAL SERVICES LTD | 1ST DEC. 2014 | 9898886.97 | 8 WEEKS | 15TH. DECEMBER, 2022 | 9898886.97 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
10 | CONSTRUCTION OF 1 BLOCKS OF 3 CLASSROOMS AT METHODIST HIGH SCH ARIGBAJO, IFO, EWEKORO OGUN STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH SEPTEMBER, -WEDNESDAY 10TH SEPTEMBER, 2023 | 19TH NOVEMBER, 2014 | 10000000 | NIL | 30th NOVEMBER, 2014 | NYIPTECH INTEGRATED RESOURCES LIMITED | NYIPTECH INTEGRATED RESOURCES LIMITED | 1ST DEC. 2014 | 9489000 | 8 WEEKS | 15TH. DECEMBER, 2023 | 9489000 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
11 | CONSTRUCTION OF A BLOCK OF THREE (3) CLASSROOMS IKORODU LGA, LAGOS WEST SENATORIAL DISTRICT LAGOS STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH SEPTEMBER, -WEDNESDAY 10TH SEPTEMBER, 2024 | 19TH NOVEMBER, 2014 | 12500000 | NIL | 31st NOVEMBER, 2014 | UNI-CHRIS NIG LTD | UNI-CHRIS NIG LTD | 1ST DEC. 2014 | 12261301.5 | 8 WEEKS | 15TH. DECEMBER, 2024 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
12 | CONSTRUCTION OF LIBRARY, SPORTS FIELD, ICT CENTRE TAKWA BAY IN ETI-OSA LGA (IRU LOCAL COMMUNITY DEVELOPMENT AREA) LAGOS CENTRAL SENATORIAL DISTRICT LAGOS STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH SEPTEMBER, -WEDNESDAY 10TH SEPTEMBER, 2025 | 19TH NOVEMBER, 2014 | 50000000 | NIL | 32nd NOVEMBER, 2014 | RAPEED LIMITED | RAPEED LIMITED | 1ST DEC. 2014 | 27235108.85 | 8 WEEKS | 15TH. DECEMBER, 2025 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
13 | CONSTRUCTION OF CLINIC/SICKBAY TAKWA BAY IN ETI-OSA LGA (IRU LOCAL COMMUNITY DEVELOPMENT AREA) LAGOS CENTRAL SENATORIAL DISTRICT LAGOS STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH SEPTEMBER, -WEDNESDAY 10TH SEPTEMBER, 2026 | 19TH NOVEMBER, 2014 |  | NIL | 33rd NOVEMBER, 2014 | GEOTECH TECHNOLOGIES LTD | GEOTECH TECHNOLOGIES LTD | 1ST DEC. 2014 | 13289342.11 | 8 WEEKS | 15TH. DECEMBER, 2026 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
14 | CONSTRUCTION OF CLASSROOM BLOCKS WITH VIP TOILET OBAFEMI OWODE LGA, OGUN CENTRAL SENATORIAL DISTRICT OGUN STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH SEPTEMBER, -WEDNESDAY 10TH SEPTEMBER, 2027 | 19TH NOVEMBER, 2014 | 12000000 | NIL | 34th NOVEMBER, 2014 | KENNY NIG SERVICES ENTP. LTD | KENNY NIG SERVICES ENTP. LTD | 1ST DEC. 2014 | 11880000 | 8 WEEKS | 15TH. DECEMBER, 2027 | 11880000 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
15 | CONSTRUCTION OF CLASSROOM BLOCKS WITH VIP TOILET OBAFEMI OWODE LGA, OGUN CENTRAL SENATORIAL DISTRICT OGUN STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH SEPTEMBER, -WEDNESDAY 10TH SEPTEMBER, 2028 | 19TH NOVEMBER, 2014 | 12000000 | NIL | 35th NOVEMBER, 2014 | JIPON VENTURE LTD | JIPON VENTURE LTD | 1ST DEC. 2014 | 10565500 | 8 WEEKS | 15TH. DECEMBER, 2028 | 10565500 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
16 | CONSTRUCTION OF 3 CLASSROOM BLOCK WITH VIP TOILET IGBARIAM, ANAMBRA EAST ANAMBRA | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 15000000 | NIL | 36th NOVEMBER, 2014 | WATER WICK LTD | WATER WICK LTD | 1ST DEC. 2014 | 13007428.5 | 8 WEEKS | 15TH. DECEMBER, 2029 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
17 | CONSTRUCTION OF 3 CLASSROOM BLOCK WITH VIP TOILET UMUMBO, AYAMELUM LGA ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 15000000 | NIL | 37th NOVEMBER, 2014 | KOBELLS LOGISTICS INVESTMENT COMPANY LTD | KOBELLS LOGISTICS INVESTMENT COMPANY LTD | 1ST DEC. 2014 | 12822368.65 | 8 WEEKS | 15TH. DECEMBER, 2030 | 12822368.65 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
18 | CONSTRUCTION OF 3 CLASSROOM BLOCK WITH VIP TOILET IYIOWA, ODEKPE, OGBARU LGA ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 15000000 | NIL | 38th NOVEMBER, 2014 | SUSSEXPOINT INTL RESOURCES LIMITED | SUSSEXPOINT INTL RESOURCES LIMITED | 1ST DEC. 2014 | 12837628.73 | 8 WEEKS | 15TH. DECEMBER, 2031 | 12837628.73 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
19 | CONSTRUCTION OF 3 CLASSROOM BLOCK OCHUCHE OGBARU LGA ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 15000000 | NIL | 39th NOVEMBER, 2014 | KOBELLS LOGISTICS INVESTMENT COMPANY LTD | KOBELLS LOGISTICS INVESTMENT COMPANY LTD | 1ST DEC. 2014 | 12992345 | 8 WEEKS | 15TH. DECEMBER, 2032 | 12992345 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
20 | CONSTRUCTION OF 3 CLASSROOM BLOCK WITH VIP TOILET AT FURNITURE AND WATER HANDPUMP FEDERAL HOUSING EST. ONITSHA NORTH ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 20000000 | NIL | 40th NOVEMBER, 2014 | DEVINE CONSTRUCTION SERVICES LTD | DEVINE CONSTRUCTION SERVICES LTD | 1ST DEC. 2014 | 15988500 | 8 WEEKS | 15TH. DECEMBER, 2033 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
21 | CONSTRUCTION OF 3 CLASSROOM BLOCK WITH VIP TOILET AT FURNITURE AND WATER HANDPUMP ODOAKPU, ONITSHA SOUTH ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 20000000 | NIL | 41st NOVEMBER, 2014 | DESTINY INTERCONTINENTAL PROJECT NIG. LTD | DESTINY INTERCONTINENTAL PROJECT NIG. LTD | 1ST DEC. 2014 | 13465880 | 8 WEEKS | 15TH. DECEMBER, 2034 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
22 | CONSTRUCTION OF 3 CLASSROOM BLOCK WITH VIP TOILET AT FURNITURE AND WATER HANDPUMP OGBUNIKE, OYI LGA, ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 20000000 | NIL | 42nd NOVEMBER, 2014 | MR. KING RESOURCES LTD | MR. KING RESOURCES LTD | 1ST DEC. 2014 | 16534098 | 8 WEEKS | 15TH. DECEMBER, 2035 | 16534098 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
23 | CONSTRUCTION OF 3 CLASSROOM BLOCK IMO STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH SEPTEMBER, -WEDNESDAY 10TH SEPTEMBER, 2036 | 19TH NOVEMBER, 2014 | 10000000 | NIL | 43rd NOVEMBER, 2014 | SHATUS COMPANY LIMITED | SHATUS COMPANY LIMITED | 1ST DEC. 2014 | 9987651.25 | 8 WEEKS | 15TH. DECEMBER, 2036 | 9987651.25 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
24 | CONSTRUCTION OF 3 CLASSROOM BLOCK WITH VIP TOILET AND WATER HANDPUMP , ADAMAWA CENTRAL SENATORIAL DISTRICT , ADAMAWA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH SEPTEMBER, -WEDNESDAY 10TH SEPTEMBER, 2037 | 19TH NOVEMBER, 2014 | 150000000 | NIL | 44th NOVEMBER, 2014 | COCKHEAD VENTURES NIG. LTD | COCKHEAD VENTURES NIG. LTD | 1ST DEC. 2014 | 15904789.56 | 8 WEEKS | 15TH. DECEMBER, 2037 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
25 | CONSTRUCTION OF 3 CLASSROOM BLOCK WITH VIP TOILET AND WATER HANDPUMP GIREI, ADAMAWA CENTRAL SENATORIAL DISTRICT , ADAMAWA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH SEPTEMBER, -WEDNESDAY 10TH SEPTEMBER, 2038 | 19TH NOVEMBER, 2014 |  | NIL | 45th NOVEMBER, 2014 | RISHAB GLOBAL LTD | RISHAB GLOBAL LTD | 1ST DEC. 2014 | 16190874 | 8 WEEKS | 15TH. DECEMBER, 2038 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
26 | CONSTRUCTION OF 3 CLASSROOM BLOCK WITH VIP TOILET AND WATER HANDPUMP GOMBI, ADAMAWA CENTRAL SENATORIAL DISTRICT , ADAMAWA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 46th NOVEMBER, 2014 | GONDAL GLOBAL RES. LTD. | GONDAL GLOBAL RES. LTD. | 1ST DEC. 2014 | 16866328.5 | 8 WEEKS | 15TH. DECEMBER, 2039 | 16866328.5 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
27 | CONSTRUCTION OF 3 CLASSROOM BLOCK WITH VIP TOILET AND WATER HANDPUMP HONG LGA, ADAMAWA CENTRAL SENATORIAL DISTRICT , ADAMAWA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 47th NOVEMBER, 2014 | D & A FACILITIES MGT. & PROPERTIES LIMITED | D & A FACILITIES MGT. & PROPERTIES LIMITED | 1ST DEC. 2014 | 14887328.5 | 8 WEEKS | 15TH. DECEMBER, 2040 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
28 | CONSTRUCTION OF 3 CLASSROOM BLOCK WITH VIP TOILET AND WATER HANDPUMPYOLA NORTH, ADAMAWA CENTRAL SENATORIAL DISTRICT , ADAMAWA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 48th NOVEMBER, 2014 | FIXGLO INTERNATIONAL LTD | FIXGLO INTERNATIONAL LTD | 1ST DEC. 2014 | 16885500 | 8 WEEKS | 15TH. DECEMBER, 2041 | 16885500 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
29 | CONSTRUCTION OF 3 CLASSROOM BLOCK WITH VIP TOILET AND WATER HANDPUMP YOLA SOUTH, ADAMAWA CENTRAL SENATORIAL DISTRICT , ADAMAWA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 49th NOVEMBER, 2014 | SHAMRUF ENGINEERING SERVICES LTD | SHAMRUF ENGINEERING SERVICES LTD | 1ST DEC. 2014 | 16008328.5 | 8 WEEKS | 15TH. DECEMBER, 2042 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
30 | PROCUREMENT OF PRIMARY SCHL BOOKS, TEACHING AID ETC, ,YOLA SOUTH/FUFORE LGA; ADAMAWA S/DISTR, ADAMAWA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 50th NOVEMBER, 2014 | TOYOSPEL VENTS LTD | TOYOSPEL VENTS LTD | 1ST DEC. 2014 | 11276250 | 8 WEEKS | 15TH. DECEMBER, 2043 | 11276250 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
31 | PROCUREMENT OF PRIMARY SCHL BOOKS, TEACHING AID ETC, AT YOLA NORTH/GIREI LGA; ADAMAWA S/DISTR , ADAMAWA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 51st NOVEMBER, 2014 | KIBECC NIGERIA LIMITED | KIBECC NIGERIA LIMITED | 1ST DEC. 2014 | 11106250 | 8 WEEKS | 15TH. DECEMBER, 2044 | 11106250 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
32 | PROCUREMENT OF PRIMARY SCHL BOOKS, TEACHING AID ETC,GOMBI/HONG LGA; ADAMAWA S/DISTR, ADAMAWA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 70000000 | NIL | 52nd NOVEMBER, 2014 | ELCON INTGR. & ALLIED SERVICES LIMITED | ELCON INTGR. & ALLIED SERVICES LIMITED | 1ST DEC. 2014 | 10706850 | 8 WEEKS | 15TH. DECEMBER, 2045 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
33 | CONSTRUCTION OF 2 CLASSROOM BLOCK WITH VIP TOILET AUGIE LGA IN KEBBI NORTH SENATORIAL DISTRICT KEBBI STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH SEPTEMBER, -WEDNESDAY 10TH SEPTEMBER, 2046 | 19TH NOVEMBER, 2014 |  | NIL | 53rd NOVEMBER, 2014 | OVALSITE LIMITED | OVALSITE LIMITED | 1ST DEC. 2014 | 11270744.5 | 8 WEEKS | 15TH. DECEMBER, 2046 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
34 | CONSTRUCTION OF 2 CLASSROOM BLOCK WITH VIP TOILET ARGUNGU LGA IN KEBBI NORTH SENATORIAL DISTRICTKEBBI STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH SEPTEMBER, -WEDNESDAY 10TH SEPTEMBER, 2047 | 19TH NOVEMBER, 2014 |  | NIL | 54th NOVEMBER, 2014 | MANIFOLD INTG SERVICES LTD | MANIFOLD INTG SERVICES LTD | 1ST DEC. 2014 | 11000000 | 8 WEEKS | 15TH. DECEMBER, 2047 | 11000000 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
35 | CONSTRUCTION OF 2 CLASSROOM BLOCK WITH VIP TOILET AREWA LGA IN KEBBI NORTH SENATORIAL DISTRICTKEBBI STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH SEPTEMBER, -WEDNESDAY 10TH SEPTEMBER, 2048 | 19TH NOVEMBER, 2014 |  | NIL | 55th NOVEMBER, 2014 | DE-DONEX INTG GLOBAL LIMITED | DE-DONEX INTG GLOBAL LIMITED | 1ST DEC. 2014 | 11126703 | 8 WEEKS | 15TH. DECEMBER, 2048 | 11126703 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
36 | CONSTRUCTION OF 2 CLASSROOM BLOCK WITH VIP TOILET SURU LGA IN KEBBI NORTH SENATORIAL DISTRICT KEBBI STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH SEPTEMBER, -WEDNESDAY 10TH SEPTEMBER, 2049 | 19TH NOVEMBER, 2014 |  | NIL | 56th NOVEMBER, 2014 | SLOBA & COMPANY INT`L LTD | SLOBA & COMPANY INT`L LTD | 1ST DEC. 2014 | 10918000 | 8 WEEKS | 15TH. DECEMBER, 2049 | 10918000 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
37 | CONSTRUCTION OF 2 CLASSROOM BLOCK WITH VIP TOILETBAGUDO LGA IN KEBBI NORTH SENATORIAL DISTRICTKEBBI STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 57th NOVEMBER, 2014 | G-MEN SUPPLIES SERVICES LIMITED | G-MEN SUPPLIES SERVICES LIMITED | 1ST DEC. 2014 | 11204865 | 8 WEEKS | 15TH. DECEMBER, 2050 | 11204865 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
38 | CONSTRUCTION OF 2 CLASSROOM BLOCK WITH VIP TOILETDANDI LGA IN KEBBI NORTH SENATORIAL DISTRICT KEBBI STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 100000000 | NIL | 58th NOVEMBER, 2014 | ADEWUMI AYOADE INVESTMENT | ADEWUMI AYOADE INVESTMENT | 1ST DEC. 2014 | 11360443.5 | 8 WEEKS | 15TH. DECEMBER, 2051 | 11360443.5 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
39 | CONSTRUCTION OF 3 CLASSROOM BLOCK WITH VIP TOILET AUGIE LGA IN KEBBI NORTH SENATORIAL DISTRICT KEBBI STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 59th NOVEMBER, 2014 | OLUBUCK NIGERIA LIMITED | OLUBUCK NIGERIA LIMITED | 1ST DEC. 2014 | 11924009.25 | 8 WEEKS | 15TH. DECEMBER, 2052 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
40 | CONSTRUCTION OF 3 CLASSROOM BLOCK WITH VIP TOILET AT ARGUNGU LGA IN KEBBI NORTH SENATORIAL DISTRICT KEBBI STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 60th NOVEMBER, 2014 | MAINSTREAM CONTR. NIG. LTD. | MAINSTREAM CONTR. NIG. LTD. | 1ST DEC. 2014 | 14045214.75 | 8 WEEKS | 15TH. DECEMBER, 2053 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
41 | CONSTRUCTION OF 3 CLASSROOM BLOCK WITH VIP TOILET AT AREWA LGA IN KEBBI NORTH SENATORIAL DISTRICT, KEBBI STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 61st NOVEMBER, 2014 | STILL JD LIMITED | STILL JD LIMITED | 1ST DEC. 2014 | 13615780.5 | 8 WEEKS | 15TH. DECEMBER, 2054 | 13615780.5 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
42 | CONSTRUCTION OF 3 CLASSROOM BLOCK WITH VIP TOILET AT SURU LGA IN KEBBI NORTH SENATORIAL DISTRICT KEBBI STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 62nd NOVEMBER, 2014 | ROYAL VALUE INT'L LTD | ROYAL VALUE INT'L LTD | 1ST DEC. 2014 | 14107713.75 | 8 WEEKS | 15TH. DECEMBER, 2055 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
43 | CONSTRUCTION OF 3 CLASSROOM BLOCK WITH VIP TOILET AT BAGUDO LGA IN KEBBI NORTH SENATORIAL DISTRICT KEBBI STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 63rd NOVEMBER, 2014 | REKKIUS GLOBAL SERV. LTD | REKKIUS GLOBAL SERV. LTD | 1ST DEC. 2014 | 13765000 | 8 WEEKS | 15TH. DECEMBER, 2056 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
44 | CONSTRUCTION OF 3 CLASSROOM BLOCK WITH VIP TOILET AT DANDI LGA IN KEBBI NORTH SENATORIAL DISTRICT KEBBI STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 64th NOVEMBER, 2014 | KUSEPH & DIOR LIMITED | KUSEPH & DIOR LIMITED | 1ST DEC. 2014 | 13508280 | 8 WEEKS | 15TH. DECEMBER, 2057 | 13508280 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
45 | PROCUREMENT OF PRIMARY SCHL BOOKS, TEACHING AIDS ETC, AT AUGIE/ARGUNGU, K/NORTH SEN.DISTRICT KEBBI STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 65th NOVEMBER, 2014 | U & I INTEGRATED GLOBAL SERVICES | U & I INTEGRATED GLOBAL SERVICES | 1ST DEC. 2014 | 5935860 | 8 WEEKS | 15TH. DECEMBER, 2058 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
46 | PROCUREMENT OF PRIMARY SCHL BOOKS, TEACHING AIDS ETC, AT AREWA/DANDI, K/NORTH SEN.DISTRICT KEBBI STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 66th NOVEMBER, 2014 | MUBARAK REAL SOLID | MUBARAK REAL SOLID | 1ST DEC. 2014 | 5999505 | 8 WEEKS | 15TH. DECEMBER, 2059 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
47 | PROCUREMENT OF PRIMARY SCHL BOOKS, TEACHING AIDS ETC, AT SURU/BAGUDO, K/NORTH SEN.DISTRICT KEBBI STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 12500000 | NIL | 67th NOVEMBER, 2014 | NATHANILLS INVESTMENT LIMITED | NATHANILLS INVESTMENT LIMITED | 1ST DEC. 2014 | 5814000 | 8 WEEKS | 15TH. DECEMBER, 2060 | 5814000 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
48 | CONSTRUCTION OF ONE BLOCK 3 CLASSROOMS WITH OFFICE AND TOILET AT KAPWIS BARKIN LADI LGA PLATEAU STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 12000000 | NIL | 68th NOVEMBER, 2014 | OLUJUMEX NIGERIA LIMITED | OLUJUMEX NIGERIA LIMITED | 1ST DEC. 2014 | 13142867.5 | 8 WEEKS | 15TH. DECEMBER, 2061 | 13142867.5 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
49 | CONSTRUCTION OF ONE BLOCK 3 CLASSROOMS WITH OFFICE AND TOILET AT GANAWURI RIYOM LGA PLATEAU STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 12000000 | NIL | 69th NOVEMBER, 2014 | ACROSS BORDER NIG. LTD | ACROSS BORDER NIG. LTD | 1ST DEC. 2014 | 11609252.55 | 8 WEEKS | 15TH. DECEMBER, 2062 | 11609252.55 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
50 | CONSTRUCTION OF ONE BLOCK 3 CLASSROOMS WITH OFFICE AND TOILET AT RIYOM, RIYOM LGA PLATEAU STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 12000000 | NIL | 70th NOVEMBER, 2014 | CONAWILSON LTD. | CONAWILSON LTD. | 1ST DEC. 2014 | 11897709 | 8 WEEKS | 15TH. DECEMBER, 2063 | 11897709 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
51 | CONSTRUCTION OF ONE BLOCK 3 CLASSROOMS WITH OFFICE AND TOILET AT NUKUR RIYOM LGA PLATEAU STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 12000000 | NIL | 71st NOVEMBER, 2014 | THOMCOM GLOBAL LINKS NIG. LTD. | THOMCOM GLOBAL LINKS NIG. LTD. | 1ST DEC. 2014 | 11879709 | 8 WEEKS | 15TH. DECEMBER, 2064 | 11879709 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
52 | CONSTRUCTION OF ONE BLOCK OF TWO CLASSROOMS MIGA LGA, JIGAWA SOUTH WEST SENATORIAL DISTRICT JIGAWA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 60000000 | NIL | 72nd NOVEMBER, 2014 | KENYO-DAX NIG. LTD | KENYO-DAX NIG. LTD | 1ST DEC. 2014 | 8598440 | 8 WEEKS | 15TH. DECEMBER, 2065 | 8598440 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
53 | CONSTRUCTION OF ONE BLOCK OF TWO CLASSROOMS JAHUN LGA, JIGAWA SOUTH WEST SENATORIAL DISTRICT JIGAWA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 73rd NOVEMBER, 2014 | GONDAL GLOBAL RES. LTD. | GONDAL GLOBAL RES. LTD. | 1ST DEC. 2014 | 9054750.45 | 8 WEEKS | 15TH. DECEMBER, 2066 | 9054750.45 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
54 | CONSTRUCTION OF ONE BLOCK OF TWO CLASSROOMS KIYAWA, JIGAWA SOUTH WEST SENATORIAL DISTRICT JIGAWA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 74th NOVEMBER, 2014 | COGENT GLOBAL RESOURCES LIMITED | COGENT GLOBAL RESOURCES LIMITED | 1ST DEC. 2014 | 9154162.5 | 8 WEEKS | 15TH. DECEMBER, 2067 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
55 | CONSTRUCTION OF ONE BLOCK OF TWO CLASSROOMS AT BIRNIN KUDU, JIGAWA SOUTH WEST SENATORIAL DISTRICT JIGAWA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 75th NOVEMBER, 2014 | TIMSI GLOBAL RESOURCES LIMITED | TIMSI GLOBAL RESOURCES LIMITED | 1ST DEC. 2014 | 9200500 | 8 WEEKS | 15TH. DECEMBER, 2068 | 9200500 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
56 | CONSTRUCTION OF ONE BLOCK OF TWO CLASSROOMS IN BUJI, JIGAWA SOUTH WEST SENATORIAL DISTRICT JIGAWA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 76th NOVEMBER, 2014 | MASHIDA NIG LTD | MASHIDA NIG LTD | 1ST DEC. 2014 | 9379009 | 8 WEEKS | 15TH. DECEMBER, 2069 | 9379009 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
57 | CONSTRUCTION OF ONE BLOCK OF TWO CLASSROOMS GWARAM LGA, JIGAWA SOUTH WEST SENATORIAL DISTRICT JIGAWA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 77th NOVEMBER, 2014 | SIKOT INTG. SERVICES LIMITED | SIKOT INTG. SERVICES LIMITED | 1ST DEC. 2014 | 9300450 | 8 WEEKS | 15TH. DECEMBER, 2070 | 9300450 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
58 | CONSTRUCTION OF ONE BLOCK OF TWO CLASSROOMS AT DUTSE , JIGAWA SOUTH WEST SENATORIAL DISTRICT JIGAWA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 78th NOVEMBER, 2014 | MEGA VISION MULTIP. CONCEPT LTD | MEGA VISION MULTIP. CONCEPT LTD | 1ST DEC. 2014 | 9054745.45 | 8 WEEKS | 15TH. DECEMBER, 2071 | 9054745.45 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
59 | LANDSCAPING OF 1 NO. PRIMARY SCHOOL AT PALLAM PRIMARY SCHOOL, LANGTANG NORTH LGA OF PLATEAU SOUTH SENATORIAL DISTRICT PLATEAU STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 56000000 | NIL | 79th NOVEMBER, 2014 | ZUAM IMPEX CONCEPT LTD | ZUAM IMPEX CONCEPT LTD | 1ST DEC. 2014 | 24596340.5 | 8 WEEKS | 15TH. DECEMBER, 2072 | 24596340.5 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
60 | LANDSCAPING OF 2 NOS.OF PRIMARY SCHOOL ZOMO PRIMARY SCHOOL-MIKANG LGA OF PLATEAU SOUTH SENATORIAL DISTRICT PLATEAU STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 80th NOVEMBER, 2014 | IGABY LUSSY NIGERIA LIMITED | IGABY LUSSY NIGERIA LIMITED | 1ST DEC. 2014 | 23985750 | 8 WEEKS | 15TH. DECEMBER, 2073 | 23985750 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
61 | CONSTRUCTION OF ONE MODEL PRIMARY SCHOOL BLOCK OF STOREY BUILDING OF 12 NO CLASSROOMS AT TAKWA BAY IN ETI-OSA LGA, LAGOS CENTRAL SENATORIAL DISTRICT LAGOS STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 28000000 | NIL | 81st NOVEMBER, 2014 | KOBIDO LIMITED | KOBIDO LIMITED | 1ST DEC. 2014 | 54981165.75 | 8 WEEKS | 15TH. DECEMBER, 2074 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
62 | CONSTRUCTION OF ONE MODEL PRIMARY SCHOOL BLOCK OF STOREY BUILDING OF 12 NO CLASSROOMS AT TAKWA BAY IN ETI-OSA LGA, LAGOS CENTRAL SENATORIAL DISTRICT LAGOS STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 9336600 | NIL | 82nd NOVEMBER, 2014 | GODIRI INTL LIMITED | GODIRI INTL LIMITED | 1ST DEC. 2014 | 49936579.5 | 8 WEEKS | 15TH. DECEMBER, 2075 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
63 | CONSTRUCTION OF BUNGALOW OF 6 ROOM OFFICES WITH IN BUILT TOILET FOR ADMINISTRATION AT TAKWA BAY IN ETI-OSA LGA, LAGOS CENTRAL SENATORIAL DISTRICT LAGOS STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 170000000 | NIL | 83rd NOVEMBER, 2014 | IGABY LUSSY NIGERIA LIMITED | IGABY LUSSY NIGERIA LIMITED | 1ST DEC. 2014 | 24055443.5 | 8 WEEKS | 15TH. DECEMBER, 2076 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
64 | PROCUREMENT OF SCHL BOOKS, COMPUTERS,UPS,FURNITURES, AUDIO-VISUAL/MULTI-MEDIA AIDS, MODERN LIBRARY/ICT CENTRE, AT TAKWA BAY IN ETI-OSA LGA, LAGOS CENTRAL SENATORIAL DISTRICT LAGOS STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 84th NOVEMBER, 2014 | KEYVAN NIGERIA LIMITED | KEYVAN NIGERIA LIMITED | 1ST DEC. 2014 | 9006975.75 | 8 WEEKS | 15TH. DECEMBER, 2077 | 9006975.75 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
65 | PROCUREMENT OF PRIMARY SCHL BOOKS, T/AIDS ,FURNITURES,SPORTS KITS, FOR 12 CLASSROOM STOREY BLOCK TAKWA BAY IN ETI-OSA LGA, LAGOS CENTRAL SENATORIAL DISTRICT LAGOS STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 85th NOVEMBER, 2014 | JERILYNE NIG LTD | JERILYNE NIG LTD | 1ST DEC. 2014 | 17420800 | 8 WEEKS | 15TH. DECEMBER, 2078 | 17420800 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
66 | PROCUREMENT OF PRIMARY SCHL BOOKS, COMPUTERS/ICT ,FURNITURE, FOR 6 ROOM OFFICE BLOCK AT TAKWA BAY IN ETI-OSA LGA, LAGOS CENTRAL SENATORIAL DISTRICT LAGOS STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 86th NOVEMBER, 2014 | J.M PHIROK NIG. LIMITED | J.M PHIROK NIG. LIMITED | 1ST DEC. 2014 | 8450222.5 | 8 WEEKS | 15TH. DECEMBER, 2079 | 8450222.5 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
67 | PROCUREMENT OF PRIMARY SCHL BOOKS, T/AIDS ,FURNITURES, FOR 12 CLASSROOM STOREY BLOCK AT TAKWA BAY IN ETI-OSA LGA, LAGOS CENTRAL SENATORIAL DISTRICT LAGOS STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 87th NOVEMBER, 2014 | MAT-LAD TECH NIG. LIMITED | MAT-LAD TECH NIG. LIMITED | 1ST DEC. 2014 | 12500000 | 8 WEEKS | 15TH. DECEMBER, 2080 | 12500000 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
68 | CONSTRUCTION OF 1 BLOCKS OF 3 CLASSROOMS, OFFICE AT RCM SCHOOL, MANDAKI, GWER-WEST LGA BENUE STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 30000000 | NIL | 88th NOVEMBER, 2014 | QUEENS OF ANGELS INVESTMENT LIMITED | QUEENS OF ANGELS INVESTMENT LIMITED | 1ST DEC. 2014 | 11849088 | 8 WEEKS | 15TH. DECEMBER, 2081 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
69 | CONSTRUCTION OF 1 BLOCKS OF 3 CLASSROOMS, OFFICE AT RCM SCHOOL ACHACH MKAR GBOKO LGA BENUE STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 89th NOVEMBER, 2014 | SUMEC INTERCONTINENTAL LIMITED | SUMEC INTERCONTINENTAL LIMITED | 1ST DEC. 2014 | 13099750 | 8 WEEKS | 15TH. DECEMBER, 2082 | 13099750 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
70 | CONSTRUCTION OF 3 CLASSROOM BLOCKS AT ELEYELE, EWEKORO LGA, OGUN CENTRAL SENATORIAL DISTRICT OGUN STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 10000000 | NIL | 90th NOVEMBER, 2014 | DIVINE INTERVENTION INVESTMENT LTD | DIVINE INTERVENTION INVESTMENT LTD | 1ST DEC. 2014 | 9875450 | 8 WEEKS | 15TH. DECEMBER, 2083 | 9875450 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
71 | CONSTRUCTION OF 3 CLASSROOM BLOCKS AT EWEKORO LGA, OGUN CENTRAL SENATORIAL DISTRICT OGUN STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 10000000 | NIL | 91st NOVEMBER, 2014 | CY ENDURANCE NIG LTD | CY ENDURANCE NIG LTD | 1ST DEC. 2014 | 9878018 | 8 WEEKS | 15TH. DECEMBER, 2084 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
72 | CONSTRUCTION OF 3 CLASSROOM BLOCKS ABEOKUTA NORTH LGA, OGUN CENTRAL SENATORIAL DISTRICT OGUN STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 10000000 | NIL | 92nd NOVEMBER, 2014 | OVERFLOW LOGISTIC NIG LTD | OVERFLOW LOGISTIC NIG LTD | 1ST DEC. 2014 | 9875450 | 8 WEEKS | 15TH. DECEMBER, 2085 | 9875450 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
73 | CONSTRUCTION OF 3 CLASSROOM BLOCKS AT ABEOKUTA NORTH LGA, OGUN CENTRAL SENATORIAL DISTRICT OGUN STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 10000000 | NIL | 93rd NOVEMBER, 2014 | ZENAROL INTEGRATED SERV, LTD | ZENAROL INTEGRATED SERV, LTD | 1ST DEC. 2014 | 9918500 | 8 WEEKS | 15TH. DECEMBER, 2086 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
74 | CONSTRUCTION OF 3 CLASSROOM BLOCKS AT ABEOKUTA NORTH LGA, OGUN CENTRAL SENATORIAL DISTRICT OGUN STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 10000000 | NIL | 94th NOVEMBER, 2014 | SAMDAVIDSON NIG. LTD. | SAMDAVIDSON NIG. LTD. | 1ST DEC. 2014 | 9875450 | 8 WEEKS | 15TH. DECEMBER, 2087 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
75 | CONSTRUCTION OF ONE PUBLIC TOILET AT AMUTO SQUARE AND LAFIAJI IN LAGOS ISLAND LAGOS STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 20000000 | NIL | 95th NOVEMBER, 2014 | UMAR SANUSI & SONS | UMAR SANUSI & SONS | 1ST DEC. 2014 | 9350000 | 8 WEEKS | 15TH. DECEMBER, 2088 | 9350000 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
76 | CONSTRUCTION OF ONE PUBLIC TOILET AT ITA FAJI AND SAND GROUSE IN LAGOS ISLAND LAGOS STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 96th NOVEMBER, 2014 | NATHAN HILLS GLOBAL SERVICES LTD | NATHAN HILLS GLOBAL SERVICES LTD | 1ST DEC. 2014 | 9425375 | 8 WEEKS | 15TH. DECEMBER, 2089 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
77 | REHABLITATION OF CLASSROOM BLOCK ISEKENDIDA CENTRAL SCHOOL AMICHI COMMUNITY SECONDARY SCHOOL ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 9500000 | NIL | 97th NOVEMBER, 2014 | TAROT ENGR. LTD | TAROT ENGR. LTD | 1ST DEC. 2014 | 9350000 | 8 WEEKS | 15TH. DECEMBER, 2090 | 9350000 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
78 | REHABLITATION OF CLASSROOM BLOCKEZENE PRIMARY SCHOOL, OKO; COMMUNITY PRIMARY SCHOOL, NDIUKWUENU, ORUMBA NORTH LGAANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 9500000 | NIL | 98th NOVEMBER, 2014 | NORANTO ROYALE RESOURCES LTD | NORANTO ROYALE RESOURCES LTD | 1ST DEC. 2014 | 9486592.5 | 8 WEEKS | 15TH. DECEMBER, 2091 | 9486592.5 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
79 | REHABLITATION OF CLASSROOM BLOCK EASTERN PRIMARY SCHOOL, AGBATA, NDIOWU; GIRL'S SECONDARY SCHOOL, AWGBU, ORUMBA NORTH LGA ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 15000000 | NIL | 99th NOVEMBER, 2014 | NOTELINK CONSTR. CO. LTD | NOTELINK CONSTR. CO. LTD | 1ST DEC. 2014 | 9350000 | 8 WEEKS | 15TH. DECEMBER, 2092 | 9350000 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
80 | REHABLITATION OF CLASSROOM BLOCKNWANNEBO PRIMARY SCHOOL, ULA, EKWULOBIA; OGBUGBOGU COMMUNITY PRIMARY SCHOOL, EZINIFITA, ACHINA CENTRAL SCHOOL, UGA, ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 25000000 | NIL | 100th NOVEMBER, 2014 | POWER MINISTER NIGERIA LIMITED | POWER MINISTER NIGERIA LIMITED | 1ST DEC. 2014 | 13010501.3 | 8 WEEKS | 15TH. DECEMBER, 2093 | 13010501.3 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
81 | REHABLITATION OF CLASSROOM BLOCKCOMMUNITY PRIMARY SCHOOL, IKENGA, COMMUNITY SECONDARY SCHOOL, ACHINA ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 101st NOVEMBER, 2014 | JUDI ROSE VENT. | JUDI ROSE VENT. | 1ST DEC. 2014 | 9500000 | 8 WEEKS | 15TH. DECEMBER, 2094 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
82 | REHABLITATION OF CLASSROOM BLOCKAT ST. MARY PRIMARY SCHOOL, URUAGU, NNEWI, NNEWI NORTH LGA ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 5000000 | NIL | 102nd NOVEMBER, 2014 | NEUTHIM LTD | NEUTHIM LTD | 1ST DEC. 2014 | 4819000 | 8 WEEKS | 15TH. DECEMBER, 2095 | 4819000 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
83 | REHABLITATION OF CLASSROOM BLOCKAT ST STEPHEN'S PRIMARY SCHOOL, UMUDIM, NNEWI NORTH LGA ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 5000000 | NIL | 103rd NOVEMBER, 2014 | KENDELBERT RESOURCES NIG LTD | KENDELBERT RESOURCES NIG LTD | 1ST DEC. 2014 | 4046631.88 | 8 WEEKS | 15TH. DECEMBER, 2096 | 4046631.88 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
84 | REHABLITATION OF CLASSROOM BLOCK ST. ANDREW'S PRIMARY SCHOOL, NKWO, TRIANGLE, NNEWI NORTH LGA ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 5000000 | NIL | 104th NOVEMBER, 2014 | SLOGAN ENG. LTD | SLOGAN ENG. LTD | 1ST DEC. 2014 | 4929276 | 8 WEEKS | 15TH. DECEMBER, 2097 | 4929276 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
85 | REHABLITATION OF CLASSROOM BLOCK COMMUNITY PRIMARY SCHOOL, AMAKOM, IFITE ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 5000000 | NIL | 105th NOVEMBER, 2014 | GREAT SAMMIO INVEST. LTD | GREAT SAMMIO INVEST. LTD | 1ST DEC. 2014 | 4888100 | 8 WEEKS | 15TH. DECEMBER, 2098 | 4888100 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
86 | REHABLITATION OF CLASSROOM BLOCK T ORIFITE COMMUNITY PRIMARY SCHOOL, AMAKWA ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 5000000 | NIL | 106th NOVEMBER, 2014 | NEUTHIM LTD | NEUTHIM LTD | 1ST DEC. 2014 | 4522952 | 8 WEEKS | 15TH. DECEMBER, 2099 | 4522952 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
87 | REHABLITATION OF CLASSROOM BLOCK OZUBULU COMMUNITY SECONDARY SCHOOL, IHEMBOSI, EKWUSIGO, LGA ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 5000000 | NIL | 107th NOVEMBER, 2014 | FIRST ATLAS VENTURES GLOBAL LTD | FIRST ATLAS VENTURES GLOBAL LTD | 1ST DEC. 2014 | 5422952 | 8 WEEKS | 15TH. DECEMBER, 2100 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
88 | REHABLITATION OF CLASSROOM BLOCK UMUCHIMA PRIMARY SCHOOL, UMUAKU, ULI ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 5000000 | NIL | 108th NOVEMBER, 2014 | DANSTACHER TURNKEY CONTRACTORS LTD | DANSTACHER TURNKEY CONTRACTORS LTD | 1ST DEC. 2014 | 4795260.09 | 8 WEEKS | 15TH. DECEMBER, 2101 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
89 | REHABLITATION OF CLASSROOM BLOCK ST. PATRICK'S PRIMARY SCHOOL, UBAHUMONUM, OKIJA ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 5000000 | NIL | 109th NOVEMBER, 2014 | BUDDIE NELSOM NIG LTD | BUDDIE NELSOM NIG LTD | 1ST DEC. 2014 | 4993170 | 8 WEEKS | 15TH. DECEMBER, 2102 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
90 | REHABLITATION OF CLASSROOM BLOCK AT UMUNAMEHI PRIMARY SCHOOL, IHIALA, IHIALA LGA ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 5000000 | NIL | 110th NOVEMBER, 2014 | SKYZ HOUSE LIMITED | SKYZ HOUSE LIMITED | 1ST DEC. 2014 | 4848690 | 8 WEEKS | 15TH. DECEMBER, 2103 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
91 | REHABLITATION OF CLASSROOM BLOCK AT COMMUNITY PRIMARY SCHOOL, UMUCHUKWU ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 5000000 | NIL | 111th NOVEMBER, 2014 | SLOGAN ENG. LTD | SLOGAN ENG. LTD | 1ST DEC. 2014 | 4993170 | 8 WEEKS | 15TH. DECEMBER, 2104 | 4993170 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
92 | REHABLITATION OF CLASSROOM BLOCK AT CENTRAL SCHOOL, AGBUDU, ORUMBA SOUTH LGA ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 5000000 | NIL | 112th NOVEMBER, 2014 | SKYZ HOUSE LTD | SKYZ HOUSE LTD | 1ST DEC. 2014 | 4845750 | 8 WEEKS | 15TH. DECEMBER, 2105 | 4845750 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
93 | REROOFING/REHABLITATION OF CLASSROOM BLOCK OZUBULU BOY'S, EKWUSIGO LGA ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 5000000 | NIL | 113th NOVEMBER, 2014 | NAPOCHRIS NIG LIMITED | NAPOCHRIS NIG LIMITED | 1ST DEC. 2014 | 4692500 | 8 WEEKS | 15TH. DECEMBER, 2106 | 4692500 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
94 | REROOFING/REHABLITATION OF CLASSROOM BLOCK AT ICHI TECHNICAL COLLEGE, EKWUSIGO LGA ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 5000000 | NIL | 114th NOVEMBER, 2014 | TECNO-KRISS INTL. SEV. LTD | TECNO-KRISS INTL. SEV. LTD | 1ST DEC. 2014 | 4982531 | 8 WEEKS | 15TH. DECEMBER, 2107 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
95 | REROOFING/REHABLITATION OF CLASSROOM BLOCK AT OKONGWU MEMORIAL GRAMMAR SCHOOL, NNEWI LGA ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 5000000 | NIL | 115th NOVEMBER, 2014 | HAPPY-LINKS LTD | HAPPY-LINKS LTD | 1ST DEC. 2014 | 4982531 | 8 WEEKS | 15TH. DECEMBER, 2108 | 4982531 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
96 | REROOFING/REHABLITATION OF CLASSROOM BLOCK UNION SECONDARY SCHOOL ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 5000000 | NIL | 116th NOVEMBER, 2014 | SULANY NIG. LIMITED | SULANY NIG. LIMITED | 1ST DEC. 2014 | 4986450 | 8 WEEKS | 15TH. DECEMBER, 2109 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
97 | REROOFING/REHABLITATION OF CLASSROOM BLOCK AT EBE COMMUNITY SCHOOL, UKPOR, NNEWI SOUTH LGA ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 5000000 | NIL | 117th NOVEMBER, 2014 | VINCART INT'L VENTURES | VINCART INT'L VENTURES | 1ST DEC. 2014 | 4892250 | 8 WEEKS | 15TH. DECEMBER, 2110 | 4892250 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
98 | REROOFING/REHABLITATION OF CLASSROOM BLOCK AT ORAIFITE BOY'S, EKWUSIGO LGA ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 5000000 | NIL | 118th NOVEMBER, 2014 | NORAH HOMES LTD | NORAH HOMES LTD | 1ST DEC. 2014 | 4990154 | 8 WEEKS | 15TH. DECEMBER, 2111 | 4990154 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
99 | FURNISHING OF BLOCKS OF 3 CLASSROOM -11NO SCHOOLS AT BENUE NORTH CENTRAL SENATORIAL DISTRICT BENUE STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 30000000 | NIL | 119th NOVEMBER, 2014 | ALEXUS MUTUAL PARTNERS LTD | ALEXUS MUTUAL PARTNERS LTD | 1ST DEC. 2014 | 14693421.05 | 8 WEEKS | 15TH. DECEMBER, 2112 | 14693421.05 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
100 | FURNISHING OF BLOCKS OF 3 CLASSROOM -10NO SCHOOLS BENUE NORTH WEST SENATORIAL DISTRICT BENUE STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 |  | NIL | 120th NOVEMBER, 2014 | A & S BISOLAD INVESTMENTS NIG. LTD | A & S BISOLAD INVESTMENTS NIG. LTD | 1ST DEC. 2014 | 14000000 | 8 WEEKS | 15TH. DECEMBER, 2113 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
101 | PROCUREMENT OF COMPUTERS/ACESSORIES COMPLETE AT KADUNA SOUTH SEN.DISTRICT,WARD 2 KADUNA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 15000000 | NIL | 121st NOVEMBER, 2014 | IMINI AGBEDE NIG. LTD | IMINI AGBEDE NIG. LTD | 1ST DEC. 2014 | 14187562 | 8 WEEKS | 15TH. DECEMBER, 2114 | 14187562 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
102 | PROCUREMENT OF COMPUTERS/ACESSORIES COMPLETE AT KADUNA SOUTH SEN.DISTRICT,WARD 4 KADUNA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 15000000 | NIL | 122nd NOVEMBER, 2014 | HI-ISSUS SERVICES LIMITED | HI-ISSUS SERVICES LIMITED | 1ST DEC. 2014 | 14553000 | 8 WEEKS | 15TH. DECEMBER, 2115 | 14553000 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
103 | PROCUREMENT OF COMPUTERS/ACCESSORIES /ICT MATERIALS, BOOKS, LIBRARY FURNITURES, AT AMUWO ODOFIN, LAGOS STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 8539773.38 | NIL | 123rd NOVEMBER, 2014 | UNI-CHRIS NIGERIA LIMITED | UNI-CHRIS NIGERIA LIMITED | 1ST DEC. 2014 | 7845000 | 8 WEEKS | 15TH. DECEMBER, 2116 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
104 | COMPLETION OF ON-GOING WATER PROJECT/PROVISION OF 30KVA GENERATOR IN EZEAFULUKWE EZEAFULUKWE,SQURE, UMUCHU ANAMBRA STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 3000000 | NIL | 124th NOVEMBER, 2014 | LIGHTUS INTEGRATED RESOURCES LIMITED | LIGHTUS INTEGRATED RESOURCES LIMITED | 1ST DEC. 2014 | 2983879 | 8 WEEKS | 15TH. DECEMBER, 2117 | 2983879 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
105 | PROCUREMENT OF 15SEATER,2.70CC PETROL,2.7 LITRES ENGINE CAPACITY (4NR) LAGOS ISLAND COUNCILSLAGOS STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 28000000 | NIL | 125th NOVEMBER, 2014 | CFAO MOTORS LIMITED | CFAO MOTORS LIMITED | 1ST DEC. 2014 | 27465000 | 8 WEEKS | 15TH. DECEMBER, 2118 | 27465000 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
106 | PROCUREMENT OF 15 SEATER,2.70CC PETROL,2.7 LITRES ENGINE CAPACITY (2NR) ST PAUL SCH,BREADFRUIT STR;ISALE EKO GRAM SCHL, OROYIN LAGOS LAGOS STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 14000000 | NIL | 126th NOVEMBER, 2014 | ADEKUNLE ABOGUN MOTORS NIG LTD | ADEKUNLE ABOGUN MOTORS NIG LTD | 1ST DEC. 2014 | 13991000 | 8 WEEKS | 15TH. DECEMBER, 2119 | 13991000 | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
107 | CONSTRUCTION OF COMMUNITY LIBRARY AND INFORMATION TELECOMUNICATION CENTRE ORIADE LCDA, AMUWO ODOFIN LGA LAGOS STATE | GUARDIAN AND VANGUARD NEWSPAPERS OF JULY 24TH, 2014 AS WELL AS FEDERAL TENDERS JOURNAL OF JULY 28TH - AUGUST 10 2014. | MINISTERIAL TENDERS BOARD | NATIONAL COMPETITIVE BIDDING | MONDAY 8TH - WEDNESDAY 10TH SEPTEMBER, 2014 | 19TH NOVEMBER, 2014 | 27500000 | NIL | 127th NOVEMBER, 2014 | BRIDGEVINE RESOURCES LIMITED | BRIDGEVINE RESOURCES LIMITED | 1ST DEC. 2014 | 27302894.74 | 8 WEEKS | 15TH. DECEMBER, 2120 | NILL | 16TH FEBRUARY 2015 | COMPLETED | 100% | NILL | NILL | PROJECT HANDED OVER TO END USER
| TOTAL | [11 empty] | 1284154548.87

## LABOUR
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) :
MINISTRY : |  | FEDERAL MINISTRY OF LABOUR AND PRODUCTIVITY
FINANCIAL YEAR : |  |  |  |  | 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014/ TO DATE | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2014 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | Supply and delivery of tricycles and training for empowerment of unemployed Youths in Ijebu-Ode/Odugbolu/Ijebu North East in Ijebu Central Federal Constituency | Guardian Newspaper of Monday 1st Sept.2014 | MTB | NCB | 29th Sept.,2014 | 3rd Oct.,2014 | 2014 Zonal intervention/ Constituency Project Code 1040 (N60,000,000.00) | NA | 14th Oct., 2014 | LERB | Messrs Denod Energy Resources Limited | 16th Oct., 2014 | 59000000 | 4 Weeks | 2014-10-16 | N29,654,672.20 | 2014-10-29 | 2014 Constituency Project | 100% | Nil | Nil | The Contractor has Completed the Job and half of the Contract Sum has so far been paid
2 | Supply of 1 toyota Land Cruiser Jeep to FMLP | Direct proc. By presidential approval | MTB | RFQ/Direct Proc | 16th April,2014 | 16th April,2014 | Project Code FMLP001001620 (N34,000,000.00) | NA | 29th April,2014 | LERB | Messrs Legacy Automobile Ltd. | 16th April, 2014 | 20350000 | 1 week | 2014-05-05 | N 20,350,000.00 | 2014-05-12 | Procurement of 1 Toyota Jeep | 100% | Nil | Nil | Fully paid
3 | Supply of 1 toyota Land Cruiser Jeep to FMLP | '' | MTB | RFQ/Direct Proc | 16th April,2014 | 16th April,2014 | Project Code FMLP001001620 (N34,000,000.00) | NA | 2014-07-01 | LERB | Messrs Legacy Automobile Ltd. | 3rd July, 2014 | 20350000 | 1 week | 2014-07-03 | N20,350,000.00 | 2014-07-10 | Proc.of 1 toyota Jeep | 100% | Nil | Nil | Fully paid
4 | Printing of Labour Statistic Bulletin | 3rd.Nov.2014 Invitation to Bid | AO | National Shoping | 3rd Dec., 2014 | 3rd Dec., 2014 | Project Code 22020305 (N3,910,471.00) | NA | 2014-12-03 | LERB | Messrs DSC Print | 3rd Dec., 2014 | 3250000 | 3 week | 2014-12-03 | N3,250,000.00 | 2014-12-10 | Printing of labour Bulletin | 100% | Nil | Nil | Fully paid
| TOTAL | [11 empty] | 102950000

## TRANSPORT
PROCUREMENT RECORDS
PROCURING ENTITY |  | FMOT
MINISTRY |  | FEDERAL MINISTRY OF TRANSPORT
FINANCIAL YEAR |  | 2014
BASIC DATA | [12 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/No. | Contract Description | Date Advert Published and Media | Approval Threshold | Procurement Method | Bid Opening Date | Bid Evaluation Report Date | Budgetary Provision (NGN) | Date of Certificate of No Objection | Approval Date by AO/MTB/FEC | Awarded to Least Tenderer | Contractor | Date of Contract Award | Contract Value (NGN) | Contract Period | Date of Commencement (Physical Mobilisation) | Amount Paid as at 31/12/2014 (NGN) | Expected Completion Date | Project Status | % of Completion as at 31/12/2014 | Date of Variation Approval if Any | Variation Amount (NGN) | Remarks
1 | Printing of Non-Security Documents-Lot 7 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 20607210 | N/A | AO | Yes | M/s Patsoj Nig. Limited | 29/10/2014 | 3465000 | 1 Week | N/A | 3465000 | 2014-05-11 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
2` | Printing of Non-Security Documents-Lot 3 | 2014-05-08 | Perm Sec, | Notice Board Advert | 2014-10-08 | 2014-10-08 | 20607210 | N/A | AO | Yes | M/s Aflum Nig. Ltd. | 2014-12-08 | 1417500 | 1 Week | N/A | 1417500 | 20/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
3 | Printing and Supply of Non-Security Documents-Lot 6 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 20607210 | N/A | AO | Yes | M/s RaphChrist Global Link Ltd. | 2014-08-08 | 2772000 | 1 Week | N/A | 2772000 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
4 | Printing of Non-Security Documents-Lot 8 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 20607210 | N/A | AO | Yes | M/s Costod Nig. Ldt. | 2014-08-08 | 2772000 | 1 Week | N/A | 2772000 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
5 | Printing of Non-Security Documents-Lot 3 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 20607210 | N/A | AO | Yes | M/s De Only One Life Int'l Ltd. | 2014-08-08 | 2800000 | 1 Week | N/A | 2800000 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
6 | Printing of Non-Security Documents-Lot 12 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 20607210 | N/A | AO | Yes | M/s Kings Word Publishers Ltd. | 2014-08-08 | 1709400 | 1 Week | N/A | 1,709.400.00 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
7 | Maintenance of Vehicle/Trans Equipment -Lot 1 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 16134000 | N/A | AO | Yes | M/s A/C Ogwulu Service Ltd | 2014-08-08 | 2778300 | 1 Week | N/A | 2778300 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
8 | Installation of Street Light | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 16134000 | N/A | AO | Yes | M/s Windward Concept Ltd. | 2014-08-08 | 4608300 | 1 Week | N/A | 4608300 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
9 | FMOT Sport Club Welfare Matters | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 7988669 | N/A | AO | Yes | M/s V.C.N. Inter Ltd. | 2014-08-08 | 4967200 | 1 Week | N/A | 4967200 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
10 | Improvement of Hon. Minister's Rest Room | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 16134000 | N/A | AO | Yes | M/s Lubell Nig. Ltd | 2014-08-08 | 931355 | 1 Week | N/A | 931355 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
11 | Maintenance of Office - Lot 1 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 20512117 | N/A | AO | Yes | M/s EL'Umma Global Service Ltd. | 2014-08-08 | 1307250 | 1 Week | N/A | 1307250 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
12 | Maintenance of Office - Lot 6 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 20512117 | N/A | AO | Yes | M/s Choxyrozy Inter.Ltd. | 2014-08-08 | 3495500 | 1 Week | N/A | 3495500 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
13 | Maintenance of Office - Lot 2 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 20512117 | N/A | AO | Yes | M/s Camsiyo Nwa W/A Ltd. | 2014-08-08 | 2795625 | 1 Week | N/A | 2795625 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
14 | Maintenanc/Services - Lot 4 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 20512117 | N/A | AO | Yes | M/s Cato Tech. Ltd. | 2014-08-08 | 3465000 | 1 Week | N/A | 3465000 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
15 | Maintenanc/Services - Lot 4 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 20512117 | N/A | AO | Yes | M/S Aaser Creative Ltd. | 2014-08-08 | 2425500 | 1 Week | N/A | 2425500 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
16 | Maintenanc/Services - Lot 4 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 20512117 | N/A | AO | Yes | M/s Qs & GS Ltd. | 2014-08-08 | 3470250 | 1 Week | N/A | 3470250 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
17 | Maintenanc/Services - Lot 1 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 20512117 | N/A | AO | Yes | M/s Gold Rock Bus. Venture Ltd. | 2014-08-08 | 2793000 | 1 Week | N/A | 2793000 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
18 | Maintenanc/Services - Lot 4 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 20512117 | N/A | AO | Yes | M/s Costod Nig. Ldt. | 2014-08-08 | 2793000 | 1 Week | N/A | 2793000 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
19 | Maintenance of Office - Lot 9 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 20512117 | N/A | AO | Yes | M/s Mustard Seed Ltd. | 2014-08-08 | 1994475 | 1 Week | N/A | 1994475 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
20 | Maintenance of Office - Lot 7 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 20512117 | N/A | AO | Yes | M/s Juikebez Nig. Ltd. | 2014-08-08 | 3507000 | 1 Week | N/A | 3507000 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
21 | Supply of Office Items - Lot 9 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 16134000 | N/A | AO | Yes | M/s Sandtec Inter. Service Ltd. | 2014-08-08 | 3491250 | 1 Week | N/A | 3491250 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
22 | Supply of Office Items - Lot 10 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 16134000 | N/A | AO | Yes | M/s Kirkwood Engineering Ltd. | 2014-08-08 | 1470000 | 1 Week | N/A | 1470000 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
23 | Supply of Office Items - Lot 4 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 16134000 | N/A | AO | Yes | M/s Juikebez Nig. Ltd. | 2014-08-08 | 1260000 | 1 Week | N/A | 1260000 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
24 | Supply of Office Items - Lot 20 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 16134000 | N/A | AO | Yes | M/s Gemenet Nig. Ltd. | 2014-08-08 | 2772000 | 1 Week | N/A | 2772000 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
25 | Supply of Office Items - Lot 2 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 16134000 | N/A | AO | Yes | M/s Booksworth Ltd. | 2014-08-08 | 1411200 | 1 Week | N/A | 1411200 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
26 | Supply of Office Items - Lot 5 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 16134000 | N/A | AO | Yes | M/s Felchio Consultants Nig. Ltd. | 2014-08-08 | 1417500 | 1 Week | N/A | 1417500 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
27 | Supply of Office Items - Lot 15 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 16134000 | N/A | AO | Yes | M/s Toebo Nig. Ltd. | 2014-08-08 | 1344000 | 1 Week | N/A | 1344000 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
28 | Supply of Office Items - Lot 18 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 16134000 | N/A | AO | Yes | M/s RaphChrist Global Link Ltd. | 2014-08-08 | 1491000 | 1 Week | N/A | 1491000 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
29 | Supply of Office Items - Lot 3 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 16134000 | N/A | AO | Yes | M/s Felchio Consultants Nig. Ltd. | 2014-08-08 | 1386000 | 1 Week | N/A | 1386000 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
30 | Supply of Office Items - Lot 8 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 16134000 | N/A | AO | Yes | M/s Juikebez Nig. Ltd. | 2014-08-08 | 1344000 | 1 Week | N/A | 1344000 | 15/08/2014 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
31 | Purchase of Photocopying Machines and Fans - Lot 5 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 20512117 | N/A | AO | Yes | M/s Mustang Global Ltd. | 2014-08-09 | 2730000 | 1 Week | N/A | 2730000 | 15/08/2015 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
32 | Purchase of Photocopying Machines and Fans - Lot 1 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 9126670 | N/A | AO | Yes | M/s Senotech Computer Ltd. | 2014-08-10 | 1500000 | 1 Week | N/A | 1500000 | 15/08/2016 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
33 | Purchase of Photocopying Machines and Fans - Lot 2 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 9126670 | N/A | AO | Yes | M/s/ B.S.C. Ltd. | 2014-08-11 | 2703750 | 1 Week | N/A | 2703750 | 15/08/2017 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
34 | Computer Accessories and Maintenance Lot 16 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 61185717 | N/A | AO | Yes | M/s Bhiza Universla Ltd. | 2014-08-12 | 3494400 | 1 Week | N/A | 3494400 | 15/08/2018 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
35 | Computer Accessories and Maintenance Lot 4 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 61185717 | N/A | AO | Yes | M/s Hudaco Nig. Ltd. | 2014-08-13 | 2761500 | 1 Week | N/A | 2761500 | 15/08/2019 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
36 | Computer Accessories and Maintenance Lot 17 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 61185717 | N/A | AO | Yes | M/s Pazie Global Con. Ltd. | 2014-08-14 | 2772000 | 1 Week | N/A | 2772000 | 15/08/2020 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
37 | Computer Accessories and Maintenance Lot 24 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 61185717 | N/A | AO | Yes | M/s Aide & Aide Global Ltd | 2014-08-15 | 2756250 | 1 Week | N/A | 2756250 | 15/08/2021 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
38 | Computer Accessories and Maintenance Lot 6 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 61185717 | N/A | AO | Yes | M/s Ollyvon Nig. Ltd. | 2014-08-16 | 1389150 | 1 Week | N/A | 1389150 | 15/08/2022 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
39 | Computer Accessories and Maintenance Lot 11 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 61185717 | N/A | AO | Yes | M/s/ Imma Ekong Nig. Ltd. | 2014-08-17 | 2520000 | 1 Week | N/A | 2520000 | 15/08/2023 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
40 | Computer Accessories and Maintenance Lot 27 | 22/07/2014 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 61185717 | N/A | AO | Yes | M/s Mcvin Integrated Services Ltd. | 2014-08-18 | 2625000 | 1 Week | N/A | 2625000 | 15/08/2024 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
41 | Computer Accessories and Maintenance Lot 22 | 22/07/2015 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 61185717 | N/A | AO | Yes | M/s Kit of Virtue Ltd. | 2014-08-19 | 1500000 | 1 Week | N/A | 1500000 | 15/08/2025 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
42 | Computer Accessories and Maintenance Lot 26 | 22/07/2016 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 61185717 | N/A | AO | Yes | M/s Impeccable Effects Venture Ltd. | 2014-08-20 | 1417500 | 1 Week | N/A | 1417500 | 15/08/2026 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
43 | Purchase Computers/Computerisation - Lot 3 | 22/07/2017 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 25682127 | N/A | AO | Yes | M/s Loma Multi Resources Ltd. | 2014-08-21 | 1428000 | 1 Week | N/A | 1428000 | 15/08/2027 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
44 | Purchase Computers/Computerisation - Lot 16 | 22/07/2018 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 25682127 | N/A | AO | Yes | M/s Sam-Val Resources W/A Ltd. | 2014-08-22 | 1475250 | 1 Week | N/A | 1475250 | 15/08/2028 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
45 | Purchase Computers/Computerisation - Lot 6 | 22/07/2019 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 25682127 | N/A | AO | Yes | M/s Input Project Partners Ltd. | 2014-08-23 | 3477600 | 1 Week | N/A | 3477600 | 15/08/2029 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
46 | Purchase Computers/Computerisation - Lot 5 | 22/07/2020 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 25682127 | N/A | AO | Yes | M/s Qs & GS Ltd. | 2014-08-24 | 3497130 | 1 Week | N/A | 3497130 | 15/08/2030 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
47 | Purchase Computers/Computerisation - Lot 17 | 22/07/2021 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 25682127 | N/A | AO | Yes | M/S Visible Global Ltd. | 2014-08-25 | 2778300 | 1 Week | N/A | 2778300 | 15/08/2031 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
48 | Purchase Computers/Computerisation - Lot 8 | 22/07/2022 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 25682127 | N/A | AO | Yes | M/s Welzi Int'l Ltd. | 2014-08-26 | 2761500 | 1 Week | N/A | 2761500 | 15/08/2032 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
49 | Purchase Computers/Computerisation - Lot 4 | 22/07/2023 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 25682127 | N/A | AO | Yes | M/s EL'Umma Global Service Ltd. | 2014-08-27 | 3328000 | 1 Week | N/A | 3328000 | 15/08/2033 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
50 | Purchase Computers/Computerisation - Lot 7 | 22/07/2024 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 25682127 | N/A | AO | Yes | M/s Katanga Nig. Ltd. | 2014-08-28 | 2723540 | 1 Week | N/A | 2723540 | 15/08/2034 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
51 | Purchase Computers/Computerisation - Lot 9 | 22/07/2016 | Perm Sec, | Notice Board Advert | 2014-05-08 | 2014-07-08 | 25682127 | N/A | AO | Yes | M/s Mabaufu Ltd. | 2014-08-29 | 1984500 | 1 Week | N/A | 1984500 | 15/08/2035 | Fully Completed | 100% | N/A | N/A | Completed as Scheduled
| TOTAL | [11 empty] | 125277975

## NCRM-IDP
PROCUREMENT RECORDS
| PROCURING ENTITY (MDA) : | National Commission for Refugees Migrant IDP
MINISTRY :
| FINANCIAL YEAR : | 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2014 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | Supply of 18 Seater Buses to Abia State | May 2nd 2014 | PTB | National Cometitive Bidding |  | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Enyis Global System & Power Ltd | 14th 0ctober, 2014 | 12916000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Obiangua/ Osisoma/Ugwunagbo Federal Constituency
2 | supply of 10 Nos. of Cars Innoson to Abia State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Dach Global Resources Nig ltd | 14th 0ctober, 2014 | 37500000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Obiangua/ Osisoma/Ugwunagbo Federal Constituency
3 | Supply of 10NosGolf Cars to Adamawa state | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Frankchigo Enterprises Ltd | 14th 0ctober, 2014 | 37500000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Michika/ Madagi Federal Constituency
4 | supply of 5 Nos. of Cars (Golf) to Bauchi State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Insular NIG LTD | 14th 0ctober, 2014 | 17425000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Katagum/ Azare Federal Constituency
5 | Supply of 2 NosGolf Cars to Borno state | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Moboshe Global Concept Ltd | 14th 0ctober, 2014 | 10230000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Dikwa/ Mafa/ Konduga Federal Constituency
6 | Supply of 1NosBus to Cross River | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Incogni Solutions Ltd | 14th 0ctober, 2014 | 18750000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Yala/ Ogoja Federal Constituency
7 | Supply of 2NosBuses to Cross River State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S IncogniSolutions Ltd | 14th 0ctober, 2014 | 10230000 | 4 Weeks | N/A | ₦10,230,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Yala/ Ogoja Federal Constituency
8 | supply of 12 Nos. of Cars to Cross River State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Pinbad Int. Service. LTD | 14th 0ctober, 2014 | 46312000 | 4 Weeks | N/A | N 46,312,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Yakurr/ Abi Federal Constituency
9 | supply of 4 Nos. of Buses (18 Seater) to Enugu State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Quaise NIG LTD | 14th 0ctober, 2014 | 49000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Udenu Federal Constituency
10 | supply of 9 Nos. of Cars to Enugu State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Phatigee NIG LTD | 14th 0ctober, 2014 | 34875500 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Udenu Federal Constituency
11 | Supply of 13 Nos Gulf Cars to Gombe State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S RAID NIG. Ltd | 14th 0ctober, 2014 | 48750000 | 4 Weeks | N/A | ₦48,750,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Kwami/ Funa Kaye Federal Constituency
12 | Supply of 13 Nos Golf Cars to Gombe State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Usmaniya Motrs Nig Ltd | 14th 0ctober, 2014 | 22500000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Yamaltu/ Deba Federal Constituency
13 | Supply of 9NosGulf Cars to Imo State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Emico International Ltd | 14th 0ctober, 2014 | 34875000 | 4 Weeks | N/A | ₦34,875,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Ohaji/ Egbema- Oguta Oru West
14 | Supply of 1NosInnoson Taxi to Imo State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Core Contractors Nig. Ltd | 14th 0ctober, 2014 | 7500000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Orlu/ Orsu/ Oru East Federal Constituency
15 | Supply of 9NosGulf Cars to Imo State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Kolvey Company Ltd | 14th 0ctober, 2014 | 34875000 | 4 Weeks | N/A | N34,875,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Nkwere/ Nwangele Njaba
16 | Supply of 9 Nos of Golf Cars to Imo State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Emico International Ltd | 14th 0ctober, 2014 | 34875000 | 4 Weeks | N/A | N34,875,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Ohaji/ Egbema- Oguta Oru West
17 | Supply of 7 Nos Gulf Cars to Jigawa state | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Bon Voyage Marine Concept Ltd | 14th 0ctober, 2014 | 23865000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Auyo/ Karfin Hausa Federal Constituency
18 | Supply of 5 Nos of Golf Cars to Jigawa State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Mirabel Global Resources Nig Ltd | 14th 0ctober, 2014 | 20460000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Kazaure Federal Constituency
19 | Supply of 5 Nos of Golf Cars to Jigawa State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Mirabel Global Resources Nig Ltd | 14th 0ctober, 2014 | 19980000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Kazaure Federal Constituency
20 | supply of 12 Nos. of Cars to Kaduna State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | ABS Construction LTD | 14th 0ctober, 2014 | 45000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Makarfi/ Kudan Federal Constituency
21 | Supply of 13NosGulf Cars to Kano State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Global Legend Integr. Concept Ltd | 14th 0ctober, 2014 | 48750000 | 4 Weeks | N/A | N48,750,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Kiru/ Bebeji Federal Constituency
22 | supply of 3 Nos. of 18 Seater Buses to Kebbi State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Quaise NIG LTD | 14th 0ctober, 2014 | 46250000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Augie/ Argungu Federal Constituency
23 | Supply of 1 Nos of 18 Seater Bus to Lagos state | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Success and Resources int mgt Ltd | 14th 0ctober, 2014 | 10537500 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Oshodi/Isolo Federal Constituency
24 | Supply of 4NosInnoson Cars to Lagos State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S President Choice Water Ltd | 14th 0ctober, 2014 | 17710000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Kosofe Federal Constituency
25 | Supply of 1 Nos of 18 Seater to Lagos State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Tiosifab Nig Ltd | 14th 0ctober, 2014 | 10537500 | 4 Weeks | N/A | N10,537,500.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Isolo / Ejigbo Federal Constituency
26 | supply of 12 Nos. of Innoson Cars to Lagos State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S President Choice Water LTD. | 14th 0ctober, 2014 | 22831000 | 4 Weeks | N/A | N22,831,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Kosofe Federal Constituency
27 | supply of 1 Nos. of 18 Seater Buses to Lagos State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Charlotte Project Concept LTD | 14th 0ctober, 2014 | 10537000 | 4 Weeks | N/A | N10,537,500.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Ajeronmi/ Ifelodun Federal Constituency
28 | supply of 1 Nos. of 18 Seater Buses to Lagos State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Mason Global Construct LTD | 14th 0ctober, 2014 | 10537000 | 4 Weeks | N/A | N10,537,500.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Mushin Federal Constituency
29 | supply of 4 Nos. of 18 Seater Buses to Lagos State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | VeeCee Energy LTD | 14th 0ctober, 2014 | 46250000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Surulere 1 Federal Constituency
30 | supply of 12 Nos. of cars (Innoson) to Lagos State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | VeeCee Synergy LTD | 14th 0ctober, 2014 | 46250000 | 4 Weeks | N/A | N46,250,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Surulere 1 Federal Constituency
31 | supply of 12 Nos. of cars (Innoson) to Lagos State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Tripple Tee Int.l Proj. LTD | 14th 0ctober, 2014 | 46250000 | 4 Weeks | N/A | N46,250,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Surulere 1 Federal Constituency
32 | supply of 12 Nos. of cars (Innoson) to Lagos State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | The Metropolitan Skills LTD | 14th 0ctober, 2014 | 45500000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Surulere 1 Federal Constituency
33 | supply of 4 Nos. of Buses (18 Seater) (Innoson) to Lagos State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | The Brown Horse Global Resr | 14th 0ctober, 2014 | 45500000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Surulere 1 Federal Constituency
34 | supply of 4 Nos. of Buses (18 Seater) (Innoson) to Lagos State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | The Brown Horse Global Resr | 14th 0ctober, 2014 | 46250000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Surulere 1 Federal Constituency
35 | supply of 12 Nos. of Cars (Innoson) to Lagos State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | We can Achieve LTD | 14th 0ctober, 2014 | 45500000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Surulere 1 Federal Constituency
36 | supply of 4 Nos. of 18 Seater Buses to Lagos State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | We Can Achieve LTD | 14th 0ctober, 2014 | 39960000 | 4 Weeks | N/A | N46,250,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Surulere 1 Federal Constituency
37 | supply of 3 Nos. of Buses to Lagos State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Brizmont NIG LTD | 14th 0ctober, 2014 | 33600000 | 4 Weeks | N/A | N33,600,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Surulere Ward G, E, E1 Federal Constituency
38 | supply of 3 Nos. of Buses (18 Seater) in favour of to Lagos State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Brizmont Energy NIG LTD | 14th 0ctober, 2014 | 33600000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Surulere Ward G, E, E1 Federal Constituency
39 | supply of 3 Nos. of Buses (18 Seater) to Lagos State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Quaise NIG LTD | 14th 0ctober, 2014 | 46250000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Surulere Ward G1,G2, G3 Federal Constituency
40 | Supply of 7NosGulf Cars to Plateau State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Jamokwet Invst. Ltd | 14th 0ctober, 2014 | 26650000 | 4 Weeks | N/A | ₦26,650,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Barkin Ladi/ Riyom Federal Constituency
41 | Supply of 1 Nos of Bus to Rivers State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Mahacc Nigr Ltd | 14th 0ctober, 2014 | 10230000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Obio/ Akpor Federal Constituency
42 | Supply of 6NosGolf Cars to Taraba State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Green Links Resources Concept | 14th 0ctober, 2014 | 23750000 | 4 Weeks | N/A | ₦23,750,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Bail/Gassol Federal Constituency
43 | Supply of 10NosGolf Cars to Taraba State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Funa Konsult Nig. Ltd | 14th 0ctober, 2014 | 37050000 | 4 Weeks | N/A | N 37,050,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Taraba/ Jalingo/ Yorro/ Zing Federal Constituency
44 | supply of 6 Nos. of Taxies Cars to Taraba State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Greenlinks Business Concept LTD | 14th 0ctober, 2014 | 23750000 | 4 Weeks | N/A | N 23,750,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Bail / Gassol Federal Constituency
45 | Supply of 2NosBus to Yobe State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Multibase Invst. Ltd | 14th 0ctober, 2014 | 15200000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Fika/ Funa Federal Constituency
46 | Supply of 12NosGolf Cars to Zamfara State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Jamokwet Inv. Ltd | 14th 0ctober, 2014 | 46250000 | 4 Weeks | N/A | ₦46,250,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Bakura/ Maradun Federal Constituency
47 | Supply of Golf Cars to Rivers State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S H.M.B. PACEO LTD | 14th 0ctober, 2014 | 48000000 | 4 Weeks | N/A | ₦48,000,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Akuku-Toru / Asari Federal Constituency Rivers State
48 | Supply of Golf Cars to Gombe State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S RAID NIG LTD | 14th 0ctober, 2014 | 48750000 | 4 Weeks | N/A | ₦48,750,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Kwami/ Funakaye Federal Constituency Gombe State
49 | Supply of Golf Cars to Jigawa State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S MELBURY CIVIL ENGR. CONSTRUCTION LTD | 14th 0ctober, 2014 | 22500000 | 4 Weeks | N/A | ₦22,500,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Jahun/ Miga Federal Constituency Jigawa State
[7 empty] | ₦ 9,666,390,788.00 | [9 empty] | 11th November, 2014
50 | Supply of 128 Nos Innoson Taxi Cars to Anambra state | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S H.M.B Paceo Ltd | 14th 0ctober, 2014 | 48000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Idemmili North/ South Senatorial district
51 | Supply of 1Nos Bus to Ananmbra state | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Candale Nig. Ltd | 14th 0ctober, 2014 | 10230000 | 4 Weeks | N/A | 10230000 | 11th November, 2014 | completed | 100% | N/A | N/A | Idemmili North/ South Senatorial district
52 | Supply of 10NosGulf Cars to Delta State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Ere Streams Ltd | 14th 0ctober, 2014 | 37500000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Isoko North/ South Senatorial District
53 | supply of 2 Nos. of 18 Seater Buses Toyota Haice to Delta State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Zeddy Global International LTD | 14th 0ctober, 2014 | 41820000 | 4 Weeks | N/A | N 41,820,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Isoko North/ South Senatorial District
54 | Supply of 9 Nos of Golf Cars to Imo State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Emico International Ltd | 14th 0ctober, 2014 | 34875000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Ohaji/ Egbema- Oguta Oru West Senatorial District
55 | Supply of 1 Nos of 18 Seater Buses to Kaduna State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Jamec West Africa Ltd | 14th 0ctober, 2014 | 10230000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Kaduna North Senatorial District
56 | Supply of 5 Nos of Golf Cars to Kaduna State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Jamec West Africa Ltd | 14th 0ctober, 2014 | 18750000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Kaduna North Senatorial District
57 | Supply of Cars to Ogun State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Marrigold Consult Services Ltd | 14th 0ctober, 2014 | 34875000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Ijebu North/ Ijebu East Senatorial District
58 | Supply of 10 Nos of Innoson Cars to Ogun State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Marrigold Consult Services Ltd | 14th 0ctober, 2014 | 34875000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Ijebu North/ Ijebu East Senatorial District
59 | Supply o f1O Nos of Cars to Plateau State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Mobile Associates and TECH Ltd | 14th 0ctober, 2014 | 40000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Jos North/ Bassa Senatorial District
60 | Supply o f 1O Nos of Cars to Plateau State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Mobile Associates and TECH Ltd | 14th 0ctober, 2014 | 37500000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Jos North/ Bassa Senatorial District
61 | Supply o f 2 Nos of Cars to Delta State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S FAIRFIELD ENGINEERING LTD | 14th 0ctober, 2014 | 6650000 | 4 Weeks | N/A | ₦6,650,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Eka North/ Eka South Senatorial District Delta State
[7 empty] | ₦ 9,666,390,788.00 | [9 empty] | 11th November, 2014
62 | Supply of 11NosTricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Moboshe Global Concept Ltd | 14th 0ctober, 2014 | 8000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Dikwa /Mafa/ Kunduga Federal Constituency
63 | Supply of 26NosTricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | f M/S Quantec Construction Ltd | 14th 0ctober, 2014 | 18200000 | 4 Weeks | N/A | ₦18,200,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Orlu/ OrsuOru East Federal Constituency
64 | Supply of 66NosTricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | f M/S Jamokwet Inv. Ltd | 14th 0ctober, 2014 | 46250000 | 4 Weeks | N/A | ₦46,250,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | BakuraMaradun Federal Constituency
65 | Supply of 68NosTricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Jamec West Africa Ltd | 14th 0ctober, 2014 | 47600000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Keffi/Karo/Kokoma Federal Constituency
66 | Supply of 70NosTricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Sabiti Nig. Ltd | 14th 0ctober, 2014 | 49000000 | 4 Weeks | N/A | ₦49,000,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | KiruBebeji Federal Constituency
67 | Supply of 28NosTricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Jamokwet Inv. Ltd | 14th 0ctober, 2014 | 19600000 | 4 Weeks | N/A | ₦19,600,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Barkinladi/ Riyom Federal Constituency
68 | Supply of 57 Nos Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Mobile Associates & Tech Ltd | 14th 0ctober, 2014 | 40537500 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | NangerePotiskum Federal Constituency
69 | Supply of 61NosTricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Mark Global Ltd | 14th 0ctober, 2014 | 43175000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Ikara/ Kubau Federal Constituency
70 | Supply of 32 Nos Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Sungreen Technology Ltd | 14th 0ctober, 2014 | 22410000 | 4 Weeks | N/A | ₦22,410,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Oredo Federal Constituency
71 | Supply of 70NosTricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Sabiti Nig. Ltd | 14th 0ctober, 2014 | 49000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | KiruBebeji Federal Constituency
72 | Supply of 19NosTricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Incogni Solutions Ltd | 14th 0ctober, 2014 | 13300000 | 4 Weeks | N/A | ₦13,300,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Obio/ Akpo Federal Constituency
73 | Supply of 64 Nos Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S BrizmontNig Ltd | 14th 0ctober, 2014 | 45000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Mariga/ Mashegu Federal Constituency
74 | Supply of 64NosTricycles in favour of | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Phatigyee Nig. Ltd | 14th 0ctober, 2014 | 45000000 | 4 Weeks | N/A | 33600000 | 11th November, 2014 | completed | 100% | N/A | N/A | Mariga /Mashegu Federal Constituency
75 | Supply of 24NosTricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Saihal Nig. Ltd | 14th 0ctober, 2014 | 17100000 | 4 Weeks | N/A | ₦17,100,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | BriniKebbiKalgo Bunza Federal Constituency
76 | Supply of 50NosTricycles in favour of | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Siddi-Qui Contractors | 14th 0ctober, 2014 | 35000000 | 4 Weeks | N/A | ₦35,000,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Chachanga Federal Constituency
77 | Supply of 68NosTricycles in favour of | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Jamec West Africa Ltd | 14th 0ctober, 2014 | 47600000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Keffi/Karu/ Kokoma Federal Constituency
78 | Supply of 91NosTricycles in favour of | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Usmaniyya Nig. Ltd | 14th 0ctober, 2014 | 16950000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Aliero/ Jega / Awandu Federal Constituency
79 | Supply of 30NosTricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Bon Voyage Marine Concept Ltd | 14th 0ctober, 2014 | 21000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Auyo/Kafin Hausa Federal Constituency
80 | Supply of 35NosTricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | First Project Ltd | 14th 0ctober, 2014 | 24500000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Burutu Federal Constituency
81 | Supply of 43NosTricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Karif Base Resources Nig. Ltd | 14th 0ctober, 2014 | 30100000 | 4 Weeks | N/A | ₦30,100,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Wurno/Rabah Federal Constituency
82 | Supply of 41NosTricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Sapbi Nig. Ltd | 14th 0ctober, 2014 | 28950000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Kiru Bebeji Federal Constituency
83 | Supply of 65NosTricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Damaram Design Construction t | 14th 0ctober, 2014 | 45600000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Machina/ Nguru Federal Constituency
84 | Supply of 37NosTricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Nino Construction Nig. Ltd | 14th 0ctober, 2014 | 26000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Awe/Doma/ Keana Federal Constituency
85 | Supply of 54 NosTricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Gulf Multi Project Nig. Ltd | 14th 0ctober, 2014 | 38000000 | 4 Weeks | N/A | ₦38,000,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Faskari/ Kankara Sabuwa Federal Constituency
86 | Supply of 42NosTricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S A&G Kurfi Engr. Nig. Ltd | 14th 0ctober, 2014 | 29400000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Malumfashi/ Kafur
87 | Supply of 64NosTricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S I.H Suleiman Company Ltd | 14th 0ctober, 2014 | 45000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Biu/ Bayo/ Shani/ KwayaKusar Federal Constituency
88 | supply of 32 Nos. of Bajaj Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Sungreen Technology Ltd | 14th 0ctober, 2014 | 22410000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Oredo Federal Constituency
89 | Supply of 43Nos Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S De-Godf Energy. Ltd | 14th 0ctober, 2014 | 29400000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | ObingwaUsisoma Ugwunagbo Federal Constituency
90 | Supply of 39 Nos Tricycles in favour of | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S SabekAssocites Ltd | 14th 0ctober, 2014 | 27787500 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | YakurrAbi Federal Constituency
91 | Supply of 64 Nos of Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Nur& Company Ltd | 14th 0ctober, 2014 | 44800000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Irepodun Ilubu Oshogbo Federal Constituency
92 | Supply Of 50Nos Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Ta-zatnig Ltd | 14th 0ctober, 2014 | 35000000 | 4 Weeks | N/A | ₦35,000,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Ogbomosho Orire Federal Constituency
93 | Supply of 40 NosTricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Jamec West Africa Ltd | 14th 0ctober, 2014 | 28062000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Kosofe Federal Constituency
94 | Supply of 101 NosTricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S DD UNIQUE CONCEPT Ltd | 14th 0ctober, 2014 | 22831000 | 4 Weeks | N/A | ₦22,831,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Ojo Federal Constituency
95 | Supply of 40 NosTricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Gavel Global Projects Ltd | 14th 0ctober, 2014 | 28062500 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Isolo/ Ejigbo Federal Constituency
96 | Supply of 64Nos Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Gulla Global Service Ltd | 14th 0ctober, 2014 | 44800000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Yalmaltu Federal Constituency
97 | Supply of 70 NosTricycles in favour of | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Usmaniyya Nig. Ltd | 14th 0ctober, 2014 | 49000000 | 4 Weeks | N/A | ₦16,950,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Yalmaltu Federal Constituency
98 | supply of 64 Nos. of Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Int. Tech Partners LTD | 14th 0ctober, 2014 | 45000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Sumaila Takai Federal Constituency
99 | supply of 63 Nos. of Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | SememaTechnoiques Resources LTD | 14th 0ctober, 2014 | 44400000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Nasarawa/ toto Federal Constituency
100 | supply of 11 Nos. of Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Wave and lala NIG LTD | 14th 0ctober, 2014 | 7700000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Bamadi/Patan Federal Constituency
101 | supply of 6 Nos. of Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | President Choice Water LTD | 14th 0ctober, 2014 | 4275000 | 4 Weeks | N/A | N4,275,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Kosofe Federal Constituency
102 | supply of 40 Nos. of Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | favourHakbim Global LTD | 14th 0ctober, 2014 | 28062500 | 4 Weeks | N/A | N28,062,500.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Oshodi/isolo Federal Constituency
103 | supply of 40 Nos. of Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Global Jobs Concept Resources | 14th 0ctober, 2014 | 28000500 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Okene/Ogori/Magongo Federal Constituency
104 | supply of 64 Nos. of Bajaj Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Phatigyee Nig LTD | 14th 0ctober, 2014 | 45000500 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Mariga/Mashegu Federal Constituency
105 | supply of 32 Nos. of Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S SunGreen Technology LTD | 14th 0ctober, 2014 | 22410000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Oredo Federal Constituency
106 | supply of 64 Nos. of Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Brizmont NIG LTD | 14th 0ctober, 2014 | 45000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Kontangura/ Wushishi Federal Constituency
107 | supply of 151 Nos. of Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Hama Construct LTD | 14th 0ctober, 2014 | 28062000 | 4 Weeks | N/A | N28,062,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Chachange federal constituency
108 | supply of 19 Nos. of Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Incogni Solution LTD | 14th 0ctober, 2014 | 13300000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Surulere Ward F1, F2, F3 Federal Constituency
109 | supply of 35 Nos. of Tricycles in favour | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Phatigyee NIG LTD | 14th 0ctober, 2014 | 25000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Ikom/ Boki Federal Constituency
110 | supply of 43 Nos. of Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Karif base resources LTD | 14th 0ctober, 2014 | 30100000 | 4 Weeks | N/A | N30,100,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Wurno/ Rabah Federal Constituency
111 | supply of 50 Nos. of Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Varush Global Service LTD | 14th 0ctober, 2014 | 35000000 | 4 Weeks | N/A | 33600000 | 11th November, 2014 | completed | 100% | N/A | N/A | Augie/ Argungu Federal Constituency
112 | supply of 50 Nos. of Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Siddi-Qui Contractor | 14th 0ctober, 2014 | 35000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Chachanga Federal Constituency
113 | supply of 48 Nos. of Baja Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | rM/S Brizmont Energy | 14th 0ctober, 2014 | 33600000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Surulere Ward F1, F2, F3 Federal Constituency
114 | supply of 53 Nos. of Tricycles in favour | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Brizmont NIG LTD | 14th 0ctober, 2014 | 37650000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Udenu Federal Constituency
115 | supply of 48 Nos. of Baja Tricycles in favou | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Brizmont Energy | 14th 0ctober, 2014 | 33600000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Surulere Ward F1, F2, F3 Federal Constituency
116 | supply of 42 Nos. of Baja Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Lee & EE | 14th 0ctober, 2014 | 30000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Auyo/Kafin federal constituency
117 | supply of 48 Nos. of Baja Tricycles in favour | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Varush Global Serv. LTD | 14th 0ctober, 2014 | 33600000 | 4 Weeks | N/A | N35,000,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Surulere Ward G, E, E1 Federal Constituency
118 | supply of 65 Nos. of Baja Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Murraypharm LTD | 14th 0ctober, 2014 | 47750000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Surulere Ward F1, F2, F3 Federal Constituency
119 | supply of 65 Nos. of Baja Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Raid Nig Ltd | 14th 0ctober, 2014 | 21070000 | 4 Weeks | N/A | N 21,070,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Ajeronmi/ Ifelodun Federal Constituency
120 | supply of 65 Nos. of Baja Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Youtoo Concept Ltd | 14th 0ctober, 2014 | 28400000 | 4 Weeks | N/A | N 28,400,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Surulere Ward F1, F2, F3 Federal Constituency
121 | supply of 65 Nos. of Baja Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S DD Unique Multi-Concept Ltd | 14th 0ctober, 2014 | 22831000 | 4 Weeks | N/A | 25053222 | 11th November, 2014 | completed | 100% | N/A | N/A | Ojo Federal Constituency
122 | supply of 65 Nos. of Baja Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S SMK Associates Ltd | 14th 0ctober, 2014 | 28062500 | 4 Weeks | N/A | N 28,062,500.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Ajeronmi/ Ifelodun Federal Constituency
123 | Supply of Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Mobile Associates & Tech Ltd | 14th 0ctober, 2014 | 20300000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Zaria Senatorial District
124 | Supply of Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Jamec West Africa Ltd | 14th 0ctober, 2014 | 18200000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Akure North/ South senatorial district
125 | Supply of Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Semema Technoiques Resources LTD | 14th 0ctober, 2014 | 28062000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Niger
126 | Supply of Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Hama Construct LTD | 14th 0ctober, 2014 | 40000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Isoko North/ South senatorial district
127 | Supply of Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Zanny Concerns LTD | 14th 0ctober, 2014 | 45750000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Ilorin East/ South senatorial district
128 | Supply of Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Brizmoont Energy LTD | 14th 0ctober, 2014 | 45750000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Ilorin East South senatorial district
129 | Supply of Tricycles |  | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Phatigyee NIGLTD | 14th 0ctober, 2014 | 45750000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Ilorin East South senatorial district
| Supply of Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Kingsworth Intergrated Services Ltd | 14th 0ctober, 2014 | 24500000 | 4 Weeks | N/A | 24500000 | 11th November, 2014 | completed | 100% | N/A | N/A
| Supply of Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S sunplSH Business Systems Ltd | 14th 0ctober, 2014 | 4995000 | 4 Weeks | N/A | 4995000 | 11th November, 2014 | completed | 100% | N/A | N/A
| Supply of Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Network Solutions Ltd | 14th 0ctober, 2014 | 48100000 | 4 Weeks | N/A | 48100000 | 11th November, 2014 | completed | 100% | N/A | N/A
| Supply of Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Arafaat Network Ltd | 14th 0ctober, 2014 | 42750000 | 4 Weeks | N/A | 42750000 | 11th November, 2014 | completed | 100% | N/A | N/A
| Supply of Tricycles | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Marigold Consult Service | 14th 0ctober, 2014 | 18375000 | 4 Weeks | N/A | 18375000 | 11th November, 2014 | completed | 100% | N/A | N/A
130 | Supply of Motorcycles to various states - | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes |  | 14th 0ctober, 2014 | 46250000 | 4 Weeks | N/A | ₦46,250,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Taraba Central Senatorial District Taraba State
131 | Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Pinnacle Automations Ltd | 14th 0ctober, 2014 | 36950000 | 4 Weeks | N/A | ₦36,950,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Adamawa North Senatorial District Adamawa State
132 | Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S MarriGold Consult Services Ltd | 14th 0ctober, 2014 | 1472500 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Ijebu North/ Ijebu East Senatorial District Ogun State
133 | Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S KudongNig Ltd | 14th 0ctober, 2014 | 19998000 | 4 Weeks | N/A | ₦19,998,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Langtang North/ South Senatorial District Plateau State
134 | Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Network Solutions Ltd | 14th 0ctober, 2014 | 12600000 | 4 Weeks | N/A | 48100000 | 11th November, 2014 | completed | 100% | N/A | N/A | Kano Central Senatorial District Kano State
135 | Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Ere Streams | 14th 0ctober, 2014 | 36100000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Isoko- North Senatorial District
135 | Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Mobile associates | 14th 0ctober, 2014 | 11840000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Kaduna South Senatorial District Kaduna State
137 | Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Racern Inter Global NIG LTD | 14th 0ctober, 2014 | 40700000 | 4 Weeks | N/A | N40,700,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Isoko- North/ South Senatorial District Delta State
137 | Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S BLUE WATER INT. CON. LOG LTD | 14th 0ctober, 2014 | 5510000 | 4 Weeks | N/A | ₦5,510,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Eka North / Eka South Senatorial District
139 | Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S CANDALE NIG LTD | 14th 0ctober, 2014 | 9500000 | 4 Weeks | N/A | ₦9,500,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Idemmili North/ South Senatorial District
| Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Musasa Medical Equipment Ltd | 14th 0ctober, 2014 | 40000000 | 4 Weeks | N/A | 40000000 | 11th November, 2014 | completed | 100% | N/A | N/A
| Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S creative concept construction ltd | 14th 0ctober, 2014 | 19465000 | 4 Weeks | N/A | 19465000 | 11th November, 2014 | completed | 100% | N/A | N/A
| Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Macen J Ltd | 14th 0ctober, 2014 | 19000000 | 4 Weeks | N/A | 19000000 | 11th November, 2014 | completed | 100% | N/A | N/A
| Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Quartz Solar Energy Syatem Ltd | 14th 0ctober, 2014 | 39960000 | 4 Weeks | N/A | 39960000 | 11th November, 2014 | completed | 100% | N/A | N/A
| Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Quartz Solar Energy Syatem Ltd | 14th 0ctober, 2014 | 39960000 | 4 Weeks | N/A | 39960000 | 11th November, 2014 | completed | 100% | N/A | N/A
| Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Saaem Global Link Lts | 14th 0ctober, 2014 | 14100000 | 4 Weeks | N/A | 39960000 | 11th November, 2014 | completed | 100% | N/A | N/A
| Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Hill Trust Ltd | 14th 0ctober, 2014 | 46250000 | 4 Weeks | N/A | 46250000 | 11th November, 2014 | completed | 100% | N/A | N/A
| Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Peter & Partners Interglobal Nig Ltd | 14th 0ctober, 2014 | 48450000 | 4 Weeks | N/A | 48450000 | 11th November, 2014 | completed | 100% | N/A | N/A
| Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Finsbury Investment Ltd | 14th 0ctober, 2014 | 5550000 | 4 Weeks | N/A | 5550000 | 11th November, 2014 | completed | 100% | N/A | N/A
| Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Amijapp Nig. Ltd | 14th 0ctober, 2014 | 44175000 | 4 Weeks | N/A | 44175000 | 11th November, 2014 | completed | 100% | N/A | N/A
| Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Quadstar Nig. Ltd | 14th 0ctober, 2014 | 30500000 | 4 Weeks | N/A | 30500000 | 11th November, 2014 | completed | 100% | N/A | N/A
| Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Greenlinks Business Concept Ltd | 14th 0ctober, 2014 | 33250000 | 4 Weeks | N/A | 33250000 | 11th November, 2014 | completed | 100% | N/A | N/A
| Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Karif Base Resources | 14th 0ctober, 2014 | 31424169 | 4 Weeks | N/A | 31424169 | 11th November, 2014 | completed | 100% | N/A | N/A
| Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Candale Nig. Ltd | 14th 0ctober, 2014 | 22370000 | 4 Weeks | N/A | 22370000 | 11th November, 2014 | completed | 100% | N/A | N/A
| Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S TeeJay Resources Ltd | 14th 0ctober, 2014 | 6840000 | 4 Weeks | N/A | 6840000 | 11th November, 2014 | completed | 100% | N/A | N/A
| Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Biyaks Business Options Ltd | 14th 0ctober, 2014 | 30000000 | 4 Weeks | N/A | 30000000 | 11th November, 2014 | completed | 100% | N/A | N/A
| Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Dach Global Resources Ltd | 14th 0ctober, 2014 | 26250000 | 4 Weeks | N/A | 26250000 | 11th November, 2014 | completed | 100% | N/A | N/A
| Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Tee Jay Rwesources Ltd | 14th 0ctober, 2014 | 3423250 | 4 Weeks | N/A | 3423250 | 11th November, 2014 | completed | 100% | N/A | N/A
| Supply of Motorcycles to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Marigold Consult Service | 14th 0ctober, 2014 | 1423250 | 4 Weeks | N/A | 1423250 | 11th November, 2014 | completed | 100% | N/A | N/A
140 | Supply of 325 Nos of Sewing Machine | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Gulla Global Service Ltd | 14th 0ctober, 2014 | 14625000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Yamaltu/ Deba Federal Constituency
141 | Supply of 950 Nos Sewing Machines | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Global Legend Integrated Ltd | 14th 0ctober, 2014 | 42750000 | 4 Weeks | N/A | ₦42,750,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Kiru Bebeji Federal constituency
142 | Supply of 100 Nos Sewing Machines | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Sabek Associates Ltd | 14th 0ctober, 2014 | 4500000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Bagudo/ Suru Federal Constituency
143 | Supply of 302 Nos Sewing Machines | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Embay International | 14th 0ctober, 2014 | 13606000 | 4 Weeks | N/A | ₦13,606,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Ovia Federal Constituency
144 | Supply of 222 NosSewing Machines | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Musasa Nig. Ltd | 14th 0ctober, 2014 | 10000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Balanga/ Billiri Federal Constituency
145 | Supply of 888 Nos Sewing Machines | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Royal Husband Nig. Ltd | 14th 0ctober, 2014 | 39960000 | 4 Weeks | N/A | ₦39,960,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A
146 | Supply of 413Nos Sewing Machines | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S AsmtShukrlah Ltd | 14th 0ctober, 2014 | 18600000 | 4 Weeks | N/A | ₦18,600,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Fika/ Funa Federal Constituency
147 | Supply of 180 Nos Sewing Machines | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Ziriks Investment Ltd | 14th 0ctober, 2014 | 7600000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Taraba/ Jalingo/ Yorro/ Zing Federal Constituency
148 | Supply of 381 Nos Sewing Machines | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Ergas Intl. Trade Ltd | 14th 0ctober, 2014 | 15250000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Chachanga Federal Constituency
149 | Supply of 190 Nos. of Sewing Machines | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Sungreen Technology Ltd | 14th 0ctober, 2014 | 8550000 | 4 Weeks | N/A | ₦8,550,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Oredo Federal Constituency
150 | Supply 528 Nos of Sewing Machine | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Enyis Global Systemand Power ltd | 14th 0ctober, 2014 | 21120000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Obingwa/ Osisoma/ Ugwunagbo Federal Constituency
151 | Supply 274 Nos of Sewing Machine | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Sabek Associates | 14th 0ctober, 2014 | 11400000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Akuku/Toru/ Asari Federal Constituency
152 | Supply of 220 Nos of Sewing Machines | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Jamec West Africa Ltd | 14th 0ctober, 2014 | 9922000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Mayo/ Belwa/ GanyaTaung Federal Constituency
153 | Supply of 302 Nos. of Butterfly sewing machine | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Embay International Business LTD | 14th 0ctober, 2014 | 13606000 | 4 Weeks | N/A | N13,606,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Ovia Federal Constituency
154 | Supply of 247 Nos. of sewing machine | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Amisua Worldwide Invt. LTD | 14th 0ctober, 2014 | 9900000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Kwani/ Funakaya Federal Constituency
155 | Supply of 536 Nos. of sewing machine | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Varush Global Service LTD | 14th 0ctober, 2014 | 21450000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Ikom/ Boki Federal Constituency
156 | supply of 381 Nos. of Butterfly sewing machine | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Ergas Int’l LTD | 14th 0ctober, 2014 | 9362500 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Chachanga Federal Constituency
157 | supply of 234 Nos. of sewing machine | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Varush Global Services LTD | 14th 0ctober, 2014 | 9362500 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Augie/ Argungu Federal Constituency
158 | supply of 180 Nos. of sewing machine | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Ziriks Investment LTD | 14th 0ctober, 2014 | 7600000 | 4 Weeks | N/A | N7,600,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Taraba/ Jalingo/ Yorro/ Zing Federal Constituency
159 | SUPPLY OF SEWING MACHINES A4 | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Martex Integrated Concept Ltd | 14th 0ctober, 2014 | 5850000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Atakunmosa East-West/ Ilesa East-West senatorial district
160 | SUPPLY OF SEWING MACHINES | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Candale Nig. Ent. Ltd | 14th 0ctober, 2014 | 22370000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Idemili North/ South senatorial district
161 | SUPPLY OF SEWING MACHINES | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Mobile Associates & Tech. Ltd | 14th 0ctober, 2014 | 40537500 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Kaduna South Senatorial District
162 | SUPPLY OF SEWING MACHINES | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Pinnacle Automation Ltd | 14th 0ctober, 2014 | 36950000 | 4 Weeks | N/A | ₦36,950,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Adamawa North senatorial district
163 | SUPPLY OF SEWING MACHINES | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Quadstar Nig. Ltd | 14th 0ctober, 2014 | 30500000 | 4 Weeks | N/A | ₦30,500,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Zamfara central senatorial district
| SUPPLY OF SEWING MACHINES | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Royal Husband International Ltd | 14th 0ctober, 2014 | 39960000 | 4 Weeks | N/A | 39960000 | 11th November, 2014 | completed | 100% | N/A | N/A
| SUPPLY OF SEWING MACHINES | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Teejay Resources Ltd | 14th 0ctober, 2014 | 7125000 | 4 Weeks | N/A | 7125000 | 11th November, 2014 | completed | 100% | N/A | N/A
165 | Supply of grinding machines “big & small” to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Royal Stone Nig Ltd | 14th 0ctober, 2014 | 7125000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Zaria Senatorial District
166 | Supply of grinding machines “big & small” to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S SAO Machinery Ltd | 14th 0ctober, 2014 | 45000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Kano Central Senatorial district
167 | Supply of grinding machines “big & small” to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Pinnacle Automations LTD | 14th 0ctober, 2014 | 36950000 | 4 Weeks | N/A | N36,950,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Adamawa North senatorial district
168 | Supply of grinding machines “big & small” to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Szotyola Energy Serv. Ltd to Anambra State | 14th 0ctober, 2014 | 18850000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A
169 | Supply of grinding machines “big & small” to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Al Furqaan Global Services Ltd to Zamfara State | 14th 0ctober, 2014 | 37250000 | 4 Weeks | N/A | ₦37,250,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Anambra Senatorial District
170 | Supply of grinding machines “big & small” to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Exit 40 Nig. Ltd to Zamfara State | 14th 0ctober, 2014 | 30500000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Zamfara West Senatorial District
171 | Supply of grinding machines “big & small” to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Panat Nig. Ltd to Kano State | 14th 0ctober, 2014 | 33155000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Zamfara Senatorial District
172 | Supply of grinding machines “big & small” to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Jamec West Africa Ltd | 14th 0ctober, 2014 | 27000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Bakora/ Maradun Federal Constituency
173 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Lee and EE Development Ltd | 14th 0ctober, 2014 | 30000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Kazaure Federal Constituency
174 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Mwayi Investment Ltd | 14th 0ctober, 2014 | 13910000 | 4 Weeks | N/A | ₦13,910,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Oredo Federal Constituency
175 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Shafaha Enterprises Ltd | 14th 0ctober, 2014 | 47000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Kiru Bebeji Federal Constituency
176 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Embay International Business Ltd | 14th 0ctober, 2014 | 8550000 | 4 Weeks | N/A | ₦8,550,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Ovia Federal Constituency
177 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Musasa Nig. Ltd | 14th 0ctober, 2014 | 15000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Balanga/ Billiri Federal Constituency
178 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Musasa Nig. Ltd | 14th 0ctober, 2014 |  | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Balanga/ Billiri Federal Constituency
179 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Niglo 4th January Concept Ltd | 14th 0ctober, 2014 | 19960000 | 4 Weeks | N/A | ₦19,960,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Egor/ Ikpoba-Ohka Federal Constituency
180 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Ziriks Investment Ltd | 14th 0ctober, 2014 | 9500000 | 4 Weeks | N/A | 7600000 | 11th November, 2014 | completed | 100% | N/A | N/A | Taraba/Jalingo Yorro/ Zing Federal Constituency
181 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Estivus Nig. Ltd | 14th 0ctober, 2014 | 33155000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Okpobo/ Andoni/ Nkoro Federal Constituency
182 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Bon Voyage Marine Concept Ltd | 14th 0ctober, 2014 | 14805000 | 4 Weeks | N/A | ₦14,805,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Auyo/ Kafin Hausa Federal Constituency
183 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Yamiza Nig. Ltd | 14th 0ctober, 2014 | 8550000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Zaria Senatorial District
184 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | of M/S Jamec West Africa Ltd | 14th 0ctober, 2014 | 5780000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Keffi/ Karu/ Kokoma Federal Constituency
185 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Incogni Solutions Ltd | 14th 0ctober, 2014 | 14805000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Kazaure Federal Constituency
186 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S ASMT shukrlah Ltd to Yobe State | 14th 0ctober, 2014 | 6944000 | 4 Weeks | N/A | ₦6,944,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Nangare Potiskum Federal Constituency
187 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S President Choice Water Ltd | 14th 0ctober, 2014 | 2850000 | 4 Weeks | N/A | ₦2,850,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Kosofe Federal Constituency
188 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/SAmisua Worldwide Investment Ltd | 14th 0ctober, 2014 | 11780000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Kwani/ Funakaye Federal Constituency
189 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Sabek Assocites ltd | 14th 0ctober, 2014 | 11400000 | 4 Weeks | N/A | ₦11,400,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Akuku-Toru/ Asari Federal Constituency
190 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Dach GlobalResources Nig ltd | 14th 0ctober, 2014 | 19960000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Obingwa/ Osisoma/ Ugwunagbo Federal Constituency
191 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S AIG SYNERGY LTD | 14th 0ctober, 2014 | 19500000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Ogbomosho/ Orire Federal Constituency
192 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Mobile Associates and tech Ltd | 14th 0ctober, 2014 | 40537000 | 4 Weeks | N/A | ₦40,537,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Nangere/ Potiskum Federal Constituency
193 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Gulla Global Service Ltd | 14th 0ctober, 2014 | 29845000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Yamaltu/ Deba Federal Constituency
194 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Wave and Lala NIG Ltd | 14th 0ctober, 2014 | 3968000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Bomadi/ Patani Federal Constituency
195 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Embay International Business LTD | 14th 0ctober, 2014 | 8550000 | 4 Weeks | N/A | N8,550,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Ovia Federal Constituency
196 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Incogni Solutions LTD | 14th 0ctober, 2014 | 21123500 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Yala/ Ogoja Federal Constituency
197 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S ABS Construction LTD | 14th 0ctober, 2014 | 47000000 | 4 Weeks | N/A | N47,000,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Makarf/i Kundanka Federal Constituency
198 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Brizmont Energy LTD | 14th 0ctober, 2014 | 28582000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Ikom/ Boki Federal Constituency
199 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Szotyola Energy Serv. Intl. LTD | 14th 0ctober, 2014 | 18850000 | 4 Weeks | N/A | N18,850,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Michika/Madagi Federal Constituency
200 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Varush Global Services LTD | 14th 0ctober, 2014 | 9362500 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Augie/ Argungu Federal Constituency
201 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Ziriks Investment LTD | 14th 0ctober, 2014 | 9500000 | 4 Weeks | N/A | N9,500,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Taraba/ Jalingo/ Yorro/ Zing Federal Constituency
202 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Brizmont LTD | 14th 0ctober, 2014 | 33600000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Surulere Federal Constituency
203 | Supply of grinding machines “big & small” | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Greno Nig LTD | 14th 0ctober, 2014 | 10000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Surulere Federal Constituency
204 | Supply of grinding machines “big & small” to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Maytex Intergrated Concept. Ltd | 14th 0ctober, 2014 | 28000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Atakunmosa East/ West Ilesha East/ West Federal Constituency
205 | Supply of grinding machines “big & small” to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Eleku Construction Ltd | 14th 0ctober, 2014 | 49000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Kiru bebeji Federal Constituency
206 | Supply of grinding machines “big & small” to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Northgate Global Concepts Ltd | 14th 0ctober, 2014 | 9000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Ire/ podun Illobun/ Oshogbo Federal Constituency
207 | Supply of grinding machines “big & small” to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Sabek Assocites Ltd | 14th 0ctober, 2014 | 39900000 | 4 Weeks | N/A | 11400000 | 11th November, 2014 | completed | 100% | N/A | N/A | Okpobo/Nkoro/Andoni Federal Constituency
208 | Supply of grinding machines “big & small” to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Bon Voyage Marine CONCEPTS LTD | 14th 0ctober, 2014 | 10405000 | 4 Weeks | N/A | 14805000 | 11th November, 2014 | completed | 100% | N/A | N/A | Jahun/Miga Federal Constituency
209 | Supply of grinding machines “big & small” to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Shepherd Trade ventures | 14th 0ctober, 2014 | 28000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Tarauni/ Kano Federal Constituency
210 | Supply of grinding machines “big & small” to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Bon Voyage Marine Concept LTD to Jigawa State | 14th 0ctober, 2014 | 10405000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Auyo/Kafin Hausa Federal Constituency
211 | Supply of grinding machines “big & small” to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Brizmont Energy LTD to Lagos State | 14th 0ctober, 2014 | 33600000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Surulere Ward G, E, E1 Federal Constituency
212 | Supply of grinding machines “big & small” to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Varush Global Serv. LTD | 14th 0ctober, 2014 | 33600000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Surulere Ward G, G2, G3 Federal Constituency
213 | Supply of grinding machines “big & small” to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Phatigee NIG LTD to | 14th 0ctober, 2014 | 33600000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Surulere Ward G, E, E1
214 | Supply of grinding machines “big & small” to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Matex Integrated Concept LTD | 14th 0ctober, 2014 | 8250000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Atakunmosa East/ West Ilesha East/ West senatorial district
215 | Supply of grinding machines “big & small” to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Lee & EE Nig LTD | 14th 0ctober, 2014 | 30000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Jahun/Miga Federal constituency
216 | Supply of grinding machines “big & small” to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Moyaam Int Concept LTD | 14th 0ctober, 2014 | 313760000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Ayeda/ Ire-wole Iso-Wole Federal Constituency
| Supply of grinding machines “big & small” to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S ASMT shukrlah Ltd to Yobe State | 14th 0ctober, 2014 | 6944000 | 4 Weeks | N/A | 6944000 | 11th November, 2014 | completed | 100% | N/A | N/A
| Supply of grinding machines “big & small” to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S J circuit concept Ltd | 14th 0ctober, 2014 | 4278000 | 4 Weeks | N/A | 4278000 | 11th November, 2014 | completed | 100% | N/A | N/A
| Supply of grinding machines “big & small” to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Fortnest Nig. Ltd | 14th 0ctober, 2014 | 8550000 | 4 Weeks | N/A | 8550000 | 11th November, 2014 | completed | 100% | N/A | N/A
217 | supply of deep freezers to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Yamiza Nig. Ltd to Kaduna State | 14th 0ctober, 2014 | 8550000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Kano central Senatorial district
218 | supply of deep freezers to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | of M/S J-Circuit Concept Ltd to Plateau State | 14th 0ctober, 2014 | 4278000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Zaria Senatorial District
219 | supply of deep freezers to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Szotyola Energy Serv. Int. Ltd to Anambra State | 14th 0ctober, 2014 | 18850000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Langtang North/ Langtang South Senatorial District
220 | supply of deep freezers to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Mobile Associates and tech Ltd to Kaduna State | 14th 0ctober, 2014 | 1980000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Anambra Senatorial District
221 | supply of deep freezers to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Zeddy Global International Ltd to Delta State | 14th 0ctober, 2014 | 45600000 | 4 Weeks | N/A | N45,600,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Kaduna South Senatorial District
222 | supply of deep freezers to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S President Choice Water Ltd to Lagos State | 14th 0ctober, 2014 | 3420000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A
223 | supply of deep freezers to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Sabek Associates Ltd to Rivers State | 14th 0ctober, 2014 | 4750000 | 4 Weeks | N/A | ₦4,750,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A
224 | supply of deep freezers to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S We can Achieve LTD to Lagos State | 14th 0ctober, 2014 | 2750000 | 4 Weeks | N/A | 2375000 | 11th November, 2014 | completed | 100% | N/A | N/A
225 | supply of deep freezers to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Brizmont NIG LTD to Lagos State | 14th 0ctober, 2014 | 3600000 | 4 Weeks | N/A | N 3,600,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Isoko North/ South Senatorial District
226 | supply of deep freezers to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Quaise NIG LTD to Lagos State | 14th 0ctober, 2014 | 3600000 | 4 Weeks | N/A | N 3,600,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Kosofe Federal Constituency Lagos State
227 | supply of deep freezers to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Phatigee NIG LTD to Lagos State | 14th 0ctober, 2014 | 3600000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Akuku- Toru / Asari Federal Constituency
[7 empty] | ₦ 9,666,390,788.00 |  |  |  |  | 14th 0ctober, 2014 |  |  |  |  | 11th November, 2014
228 | Supply of hair & barbing saloon equipment to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S President Choice Water Ltd to Lagos State | 14th 0ctober, 2014 | 475000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Kosofe Federal Constituency
229 | Supply of hair & barbing saloon equipment to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Mikesede Generation Nig. Ltd to Edo State | 14th 0ctober, 2014 | 8550000 | 4 Weeks | N/A | ₦8,550,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Ovia Federal Constituency
230 | Supply of hair & barbing saloon equipment to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Maytex Intergrated Concept. Ltd | 14th 0ctober, 2014 | 28000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Surulere ward F1, F2, F3Federal Constituency Lagos State
231 | Supply of hair & barbing saloon equipment to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Matex Integrated Concept LTD | 14th 0ctober, 2014 | 8250000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A
232 | Supply of block molding machine to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Maytex Intergrated Concept. Ltd | 14th 0ctober, 2014 | 28000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Surulere1 Federal Constituency Lagos State
233 | Supply of block molding machine to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Matex Integrated Concept LTD | 14th 0ctober, 2014 | 8250000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Surulere ward G, E, E1 Federal Constituency Lagos State
| Supply of block molding machine to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Northgate Global Concept Ltd | 14th 0ctober, 2014 | 9000000 | 4 Weeks | N/A | 9000000 | 11th November, 2014 | completed | 100% | N/A
|  | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Phatigyee Nig. Ltg | 14th 0ctober, 2014 | 33600000 | 4 Weeks | N/A | 33600000 | 11th November, 2014 | completed | 100% | N/A
[7 empty] | ₦ 9,666,390,788.00 |  |  |  |  | 14th 0ctober, 2014 |  |  |  |  | 11th November, 2014
[7 empty] | ₦ 9,666,390,788.00 |  |  |  |  | 14th 0ctober, 2014 |  |  |  |  | 11th November, 2014
234 | SUPPLY OF WELDING MACHINES | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Jamec West Africa Ltd | 14th 0ctober, 2014 | 2968000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Kosofe Federal Constituency
235 | SUPPLY OF WELDING MACHINES | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Shafaha Enterprises Ltd | 14th 0ctober, 2014 | 36000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Ovia Federal Constituency
236 | SUPPLY OF BASIC DRUGS | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Pinnacle Automation Ltd | 14th 0ctober, 2014 | 17000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Adamawa North Senatorial District Adamawa State.
237 | SUPPLY OF BASIC DRUGS | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Zalfa Motors Ltd | 14th 0ctober, 2014 | 23400000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Kaduna North Senatorial District Kaduna State
238 | SUPPLY OF BASIC DRUGS | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Funa Consult Nig. Ltd | 14th 0ctober, 2014 | 16150000 | 4 Weeks | N/A | ₦16,150,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Taraba/ Jalingo/ Yorro/ Zing Federal Constituency Taraba State
239 | SUPPLY OF BASIC DRUGS | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Damaram Design Construction Ltd | 14th 0ctober, 2014 | 28000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Machina/ Nguru Federal Constituency Yobe State
240 | SUPPLY OF BASIC DRUGS | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Insular NIG Ltd | 14th 0ctober, 2014 | 6175000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Katagum/ Azare Federal Constituency Bauchi State
241 | SUPPLY OF WATER PURIFICATION TABLETS | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Multibase Investment Ltd | 14th 0ctober, 2014 | 12908700 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Fika/ Funa Federal Constituency Yobe State
242 | SUPPLY OF WATER PURIFICATION TABLETS | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Mahacc Nig Ltd | 14th 0ctober, 2014 | 47500000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Obio/ Akpor Federal Constituency Rivers State
243 | SUPPLY OF WATER PURIFICATION TABLETS | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Insular Nig Ltd | 14th 0ctober, 2014 | 9400000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Katagum/ Azare Federal Constituency Bauchi State
244 | Supply of10,134NosWrappers-Veritable Wax | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Mobile Associate & Tech. Ltd | 14th 0ctober, 2014 | 40537500 | 4 Weeks | N/A | ₦40,537,500.00 | 11th November, 2014 | completed | 100% | N/A | N/A
245 | 3,500NosWrappers-Veritable Wax | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Mirabel Global Resource Nig. Ltd | 14th 0ctober, 2014 | 14000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A
246 | Supply of2,137NosWrappers-Veritable Wax | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Jiga Multi Inv. Nig. Ltd | 14th 0ctober, 2014 | 8550000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Fika/ Funa Federal Constituency Yobe State
247 | Supply of3,562NosWrappers-Veritable Wax | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Saihal Nig. Ltd | 14th 0ctober, 2014 | 14250000 | 4 Weeks | N/A | ₦14,250,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Obio/ Akpor Federal Constituency Rivers State
248 | Supply of2,362NosWrappers-Veritable Wax | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Contemporary Archvision Nig. | 14th 0ctober, 2014 | 9448000 | 4 Weeks | N/A | ₦9,448,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Katagum/ Azare Federal Constituency Bauchi State
249 | Supply of7,500NosWrappers-Veritable Wax | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Pinnacle Automation Ltd | 14th 0ctober, 2014 | 30000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A
250 | Supply of8, 031Nos Wrappers-Veritable Wax | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Gel-dok Nig. Ltd | 14th 0ctober, 2014 | 32125000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A
251 | Supply of 2137 Nos of Wrappers-Veritable Wax | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Shaff Communication. Ltd | 14th 0ctober, 2014 | 8550000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A
252 | Supply o f 3,537 Nos of Wrappers-Veritable Wax | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Jamec West Africa Ltd | 14th 0ctober, 2014 | 14150000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A
254 | SUPPLY OF FARMING TOOLS | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Sabiti Nig. Ltd | 14th 0ctober, 2014 | 28250000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Kiru/ Bebeji Federal Constituency Kano State
255 | SUPPLY OF FARMING TOOLS | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Damaram Design Construction | 14th 0ctober, 2014 | 21500000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Machina/Nguru Federal Constituency Yobe State
256 | SUPPLY OF FARMING TOOLS | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Jamec West Africa Ltd | 14th 0ctober, 2014 | 2612500 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Mayo/ Belwa/ Ganya/ Taung Federal Constituency Adamawa State
257 | SUPPLY OF GARRI & GRAIN PROCESSING MACHINE | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Ededeku Dev. Serv. Ltd | 14th 0ctober, 2014 | 8455000 | 4 Weeks | N/A | ₦8,455,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A
258 | SUPPLY OF GARRI & GRAIN PROCESSING MACHINE | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Corniche& Spurs Nig. Ltd | 14th 0ctober, 2014 | 35000000 | 4 Weeks | N/A | ₦35,000,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Orlu/ Orsu/ Oru East Federal Constituency Imo State
259 | SUPPLY OF GARRI & GRAIN PROCESSING MACHINE | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Orocotag Global Ltd | 14th 0ctober, 2014 | 23075000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Yala / Ogoja Federal Constituency Cross River State
[7 empty] | ₦ 9,666,390,788.00 | [9 empty] | 11th November, 2014
[7 empty] | ₦ 9,666,390,788.00 | [9 empty] | 11th November, 2014
260 | SUPPLY OF SMOKED FISH UNITS equipment | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S President Choice Water Ltd | 14th 0ctober, 2014 | 1900000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Kosofe Federal Constituency Lagos State
261 | Supply of water pumping machine to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S YS Integrated Ltd to Kaduna State | 14th 0ctober, 2014 | 5985000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Zaria Federal Constituency Kaduna State
262 | Supply of water pumping machine to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Cimmula Nig. Ltd toJigawa State | 14th 0ctober, 2014 | 10080000 | 4 Weeks | N/A | ₦10,080,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Auyo/ Kafin Hausa Federal Constituency Jigawa State
263 | Supply of water pumping machine to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Mutual Infrastructural Ltd to Cross River State | 14th 0ctober, 2014 | 475000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Yakurr/ Abi Federal Constituency Cross River State
264 | Supply of water pumping machine to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Twilight Services to Katsina State | 14th 0ctober, 2014 | 33250000 | 4 Weeks | N/A | 0 | 11th November, 2014 | 4 Weeks | N/A | 4 Weeks | N/A | Bakori/ Danja Federal Constituency Katsina State
| Supply of water pumping machine to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Savana Scape Realator Ltd | 14th 0ctober, 2014 | 8500000 | 4 Weeks | N/A | 8500000 | 11th November, 2014 | 4 Weeks | N/A | 4 Weeks | N/A
| Supply of water pumping machine to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes |  | 14th 0ctober, 2014 | 5985500 | 4 Weeks | N/A | 5985500 | 11th November, 2014 | 4 Weeks | N/A | 4 Weeks | N/A
[7 empty] | ₦ 9,666,390,788.00 | [9 empty] | 11th November, 2014
[7 empty] | ₦ 9,666,390,788.00 | [9 empty] | 11th November, 2014
265 | Supply of motorized fishing boats to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Jianem Eng. Co. Ltd to Imo State | 14th 0ctober, 2014 | 19000000 | 4 Weeks | N/A | ₦19,000,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Kosofe Federal Constituency Lagos State
266 | Supply of fertilizer to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Dube Gen. Ent. Nig. Ltd to Jigawa State | 14th 0ctober, 2014 | 23750000 | 4 Weeks | N/A | ₦23,750,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Yakurr/ Abi Federal Constituency Cross River State
267 | Supply of fertilizer to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Dansyl& Company Ltd to Cross River State | 14th 0ctober, 2014 | 15121500 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Bakori/ Danja Federal Constituency Katsina State
268 | Supply of fertilizer to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Twilight Services to Katsina State | 14th 0ctober, 2014 | 33250000 | 4 Weeks | N/A | ₦33,250,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A
269 | Supply of fertilizer to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Eash Progressive Ventures Ltd to Kano State | 14th 0ctober, 2014 | 42500000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Ohaji/ Egbema- Ogutaoru Federal Constituency Imo State
270 | Supply of fertilizer to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Dutse Granite co.Ltd to Jigawa State | 14th 0ctober, 2014 | 33745000 | 4 Weeks | N/A | ₦33,745,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A
271 | SUPPLY OF GRAINS, MAIZE AND MILLET | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Rogoji Inv. Ltd | 14th 0ctober, 2014 | 40000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Kaduna North Senatorial District
272 | SUPPLY OF GRAINS, MAIZE AND MILLET | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Rogoji Investment NIG LTD | 14th 0ctober, 2014 | 45000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Zaria Senatorial District
[7 empty] | ₦ 9,666,390,788.00 | [9 empty] | 11th November, 2014
[7 empty] | ₦ 9,666,390,788.00 | [9 empty] | 11th November, 2014
[7 empty] | ₦ 9,666,390,788.00 | [9 empty] | 11th November, 2014
273 | Supply of computers to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Eash Progressive Ventures Ltd to Kano State | 14th 0ctober, 2014 | 47600000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Kiru Bebeji Federal Constituency
274 | Supply of computers to various states | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S MWAYI INVESTMENT Ltd to Edo State | 14th 0ctober, 2014 | 16950000 | 4 Weeks | N/A | ₦16,950,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Oredo Federal Constituency
275 | The Supply of Nos Generators | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S MarriGold Consult Services Ltd | 14th 0ctober, 2014 | 1353750 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Ijebu North Federal Constituency
276 | Supply of 15Nos Generators | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S President Choice Water Ltd | 14th 0ctober, 2014 | 712500 | 4 Weeks | N/A | ₦712,500.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Kosofe Federal Constituency
277 | Supply of 21Nos Generators | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S President Choice Water Ltd Ltd | 14th 0ctober, 2014 | 912000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Kosofe Federal Constituency
278 | Supply of 45 Nos. of Generators | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | LANDSLIDE CURVES & CUBES LTD | 14th 0ctober, 2014 | 2000000 | 4 Weeks | N/A | ₦2,000,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Eka North East/ Eka South Federal Constituency
279 | Supply of 38 Nos. of Generators | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Ware and Lala Nig LTD | 14th 0ctober, 2014 | 1850000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Eka North East/ Eka South Federal Constituency
280 | Supply of 20 Nos. of Yamaha 75 Horse Power outboard | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Gold Finger Global Consulting | 14th 0ctober, 2014 | 33000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Bomadi/ Patani Federal Constituency
281 | Supply of 220 Nos. of Generators | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Racern Inter Global NIG LTD | 14th 0ctober, 2014 | 37500000 | 4 Weeks | N/A | 37500000 | 11th November, 2014 | completed | 100% | N/A | N/A | Bomadi/ Patani Federal Constituency
282 | Supply of 20 Nos. of Yahama 40 Horse power outboard Engine Generators | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Pef Divine Concept LTD | 14th 0ctober, 2014 | 38000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Bomadi/ Patani Federal Constituency
283 | Supply of 700 Nos. of Generators (T2700) | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Quaise NIG LTD | 14th 0ctober, 2014 | 33600000 | 4 Weeks | N/A | 33600000 | 11th November, 2014 | completed | 100% | N/A | N/A | Kosofe Federal Constituency
284 | Supply of 1158 Nos. of Generators (T900) | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Brizmont Energy LTD | 14th 0ctober, 2014 | 33600000 | 4 Weeks | N/A | N 33,600,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Kosofe Federal Constituency
284 | Supply of 700 Nos. of Generators (T700) | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Varush Global Serv. LTD | 14th 0ctober, 2014 | 33600000 | 4 Weeks | N/A | N 33,600,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Kosofe Federal Constituency
286 | Supply of 700 Nos. of Generators (T2700) | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Brizmont NIG LTD | 14th 0ctober, 2014 | 33600000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Surulere F1, F2, F3
287 | Supply of 600 Nos. of Generators (T950) | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Varush Global SyS. LTD | 14th 0ctober, 2014 | 17425000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Igboeze North federal Constituency
288 | Supply of2,452 Nos Maize & Millet | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Eleku Construction | 14th 0ctober, 2014 | 44150000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Kiru Bebeji Federal Constituency
289 | Supply of 737 NosGrains | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Savannah Scape Nig Ltd | 14th 0ctober, 2014 | 14250000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Birnin Kebbi/ Kalgo/ Bunza Federal Constituency
290 | Supply of 1,513 Nos25kg Bags of Millet | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Alh. Muhammed Abdullahi& Co. Ltd | 14th 0ctober, 2014 | 27250000 | 4 Weeks | N/A | ₦27,250,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Kamba/ Arwea/ Dandi Federal Constituency
291 | Supply of1,244 Nos50kg Bags of Rice | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Baraka Resources Ltd | 14th 0ctober, 2014 | 28000000 | 4 Weeks | N/A | ₦28,000,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Kamba/ Arwea/ Dandi Federal Constituency
292 | Supply of143Nos50kg Bags of Rice, 175 Nos 50kg bags of Maize, 175 Nos 50kg bags of Sorghum | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Greenlinks Resources Concept | 14th 0ctober, 2014 | 9500000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Bail Gassol Federal Constituency
293 | Supply of380NosGrains | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Shaff Communications Ltd | 14th 0ctober, 2014 | 8550000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Aliero/ Jega/ Gwandu Federal Constituency
294 | Supply of1,399NosGrains | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Frankchigo Enterprises Ltd | 14th 0ctober, 2014 | 31480000 | 4 Weeks | N/A | ₦26,480,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Michika/ Madagi Federal Constituency
295 | Supply of1,500NosGrains | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Jarfu Multi-Systems Ltd | 14th 0ctober, 2014 | 23750000 | 4 Weeks | N/A | ₦23,750,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Tarabar/ Jalingo/ Yorro/ Zing Federal Constituency
296 | Supply of480NosGrains | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Jamec West Africa Ltd | 14th 0ctober, 2014 | 10815000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Mayo/BelwaGanya/ Taung Federal Constituency
297 | M/S Quartz Solar Energy Ltd | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Quartz Solar Energy Ltd | 14th 0ctober, 2014 | 22500000 | 4 Weeks | N/A | ₦22,500,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Fika/Funa Federal Constituenc
298 | Supply of681Nos50kg Bags of Rice, 833 Nos 50kg bags of Maizei | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S ASMT Shukrlah Nig. Ltd | 14th 0ctober, 2014 | 30000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Balanga/ Billiri Federal Constituency
299 | Supply of1,900NosGrains & Cereals | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Gogiti Nig. | 14th 0ctober, 2014 | 47500000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Bida/ Gbako/ Katcha Federal Constituency
300 | Supply of1,801NosGrains | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Mobile Associate & Tech. Ltd | 14th 0ctober, 2014 | 40537500 | 4 Weeks | N/A | 40 ,537,500 | 11th November, 2014 | completed | 100% | N/A | N/A | Nangere/ Potiskum Federal Constituency
301 | Supply of1,333NosGrains | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Karif Base Resources Nig. Ltd Design Construction Ltd | 14th 0ctober, 2014 | 30000000 | 4 Weeks | N/A | ₦30,000,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Wurno/ Rabah Federal Constituency
301 | Supply of1,000 Nos of 50 Kg of Rice | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Damaram Design Construction Ltd | 14th 0ctober, 2014 | 22162000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Machina/ Nguru Federal Constituency
303 | Supply of 1,500 Nos of Bags of Rice and 800 Nos of Bags of Beans | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Mirabel Global Resources Nig Ltd | 14th 0ctober, 2014 | 47500000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Bida/ Gbako/ Katcha Federal Constituency
304 | Supply of 1,900 Nos of Bags of Grains and Cereals | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Mirabel Global Resources Nig Ltd | 14th 0ctober, 2014 | 9500000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Bida/ Gbako/ Katcha Federal Constituency
305 | M/S Muhali Engineering and Tech. Service Ltd | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Muhali Engineering and Tech. Service | 14th 0ctober, 2014 | 9000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Bida/ Gbako/ Katcha
306 | Supply of 380Nosof Grains | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Jiga Multi Invest NIG LTD | 14th 0ctober, 2014 | 8550000 | 4 Weeks | N/A | ₦8,550,000.00 | 11th November, 2014 | completed | 100% | N/A | N/A | Aliero/ Jega/ Gwandu
307 | Supply of 1990Nosof Grains | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Al Usnu NIG | 14th 0ctober, 2014 | 49750000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Makarfi/ Kudan Federal Constituency
308 | Supply of 1,333Nosof 50kg Bags of rice Grains | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Karif Base resources NIG LTD | 14th 0ctober, 2014 | 30000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Wurno/ Rabah Federal Constituency
309 | Supply of 150 Bags of Rice and 100 Bags of Beans | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Browny Gold Ltd | 14th 0ctober, 2014 | 5000000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Awe Doma/ Keana Federal Constituency
[7 empty] | ₦ 9,666,390,788.00 |  |  |  |  | 14th 0ctober, 2014 |  | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A
310 | SUPPLY OF COOKING OIL to adamawa state | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Jamec West Africa Ltd | 14th 0ctober, 2014 | 4,750,000.00 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Mayo/ Belwa/ Ganya/ Taung Federal Constituency
311 | SUPPLY OF COOKING OIL to niger state | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Gogiti Nig. Ltd | 14th 0ctober, 2014 | 9500000 | 4 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Bida/ Gbako/ Katcha Federal Constituency
[7 empty] | ₦ 9,666,390,788.00 | [9 empty] | 11th November, 2014
[7 empty] | ₦ 9,666,390,788.00 | [9 empty] | 11th November, 2014
312 | REHABILITATION OF UNHCR QUARTERS AT ORU CAMP IJEBU ODE OGUN STATE | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S PRUDENCY CONCEPTS LTD | 14th 0ctober, 2014 | 11680271 | 8 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | IJEBU ODE OGUN STATE
313 | REHABILITATION OF PASTORAL BLOCK ANNEX 1 AT ORU CAMP, IJEBU-ODE OGUN STATE | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S BAKEMS NIG LTD | 14th 0ctober, 2014 | 11462868.5 | 8 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | IJEBU ODE OGUN STATE
314 | REHABILITATION OF PASTORAL BLOCK ANNEX 2 AT ORU CAMP, IJEBU-ODE OGUN STATE | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S DORTMAFF INVESTMENT NIG.LTD | 14th 0ctober, 2014 | 12755637 | 8 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | IJEBU ODE OGUN STATE
315 | REHABILITATION OF NAIROBI ANNEX 2 AT ORU CAMP, IJEBU-ODE OGUN STATE | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S BODENIS NIG. LTD | 14th 0ctober, 2014 | 11359181 | 8 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | IJEBU ODE OGUN STATE
316 | REHABILITATION OF NAIROBI ANNEX 3 AT ORU CAMP, IJEBU-ODE OGUN STATE | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S LION WAY VENTURES LTD | 14th 0ctober, 2014 | 13930 | 8 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | IJEBU ODE OGUN STATE
317 | CLEARING OF WEEDS AND LAND SCAPING OF ENTIRE ORU CAMP IN OGUN STATE | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S ISMADE INTERGRATED NIG.LTD | 14th 0ctober, 2014 | 2500000 | 8 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | IJEBU ODE OGUN STATE
318 | SUPPLY OF OFFICES STATIONARIES AND CONSUMABLES TO LAGOS ZONAL OFFICE | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S DACHRISA INTERNATIONAL LTD | 14th 0ctober, 2014 | 1545180 | 8 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | LAGOS STATE
319 | RENOVATION OF LAGOS ZONAL OFFICE | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S SEDIKAT INTERGRATED CONCEPT INTER. LTD | 14th 0ctober, 2014 | 5401808.5 | 8 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | LAGOS STATE
320 | SUPPLY AND INSTALLATION OF OFFICE EQUIPMENT AND FURNITURE IN LAGOS ZONAL OFFICE | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S PATIBON SERVICE LTD | 14th 0ctober, 2014 | 2766750 | 8 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | LAGOS STATE
321 | SUPPLY AND INSTALLATION OF OFFICE EQUIPMENT AND FURNITURE IN CALABAR ZONAL OFFICE | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S CANEDOT MAINTANANCE LTD | 14th 0ctober, 2014 | 2142000 | 8 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Cross River state
322 | REHABILITATION OF OFFICE SPACE FOR NCFRMI AT FEDERAL SECRETARIAT COMPLEX CALABAR | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S BENBOZAONE LTD | 14th 0ctober, 2014 | 8597075 | 8 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Cross River state
323 | RENOVATION AND FURNISHING OF ENUGU ZONAL OFFICE | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S DIGIHOME GLOBAL SERVICES LTD | 14th 0ctober, 2014 | 8096481.25 | 8 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Enugu
324 | SUPPLY OF OFFICES STATIONARIES AND CONSUMABLES TO ENUGU ZONAL OFFICE | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S PATLUCIA NIG.ENT LTD | 14th 0ctober, 2014 | 1544970 | 8 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Enugu
325 | SUPPLY AND INSTALLATION OF OFFICE EQUIPMENT AND FURNISHING OF NCFR QUARTERS OFFICE AD WUSE RECEPTION CENTRE | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S MOTUBE HI-TECH SYSTEM | 14th 0ctober, 2014 | 11657314.2 | 8 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A
326 | Supply of Water and Sanitary Materials for IDPs in Adamawa State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Saksal Company limited | 14th 0ctober, 2014 | 10800000 | 8 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Adamawa State
327 | Supply of Non- Food idpS for IDPs in Adamawa State | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S \Idomag Services Compay ltd | 14th 0ctober, 2014 | 270080983 | 8 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | Adamawa State
328 | SUPPLY AND INSTALLATION OF OFFICE EQUIPMENT AND FURNITURE IN KEBBI STATE | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S NIFFO PROPERTY DEVELOPMENT COMPANY LTD | 14th 0ctober, 2014 | 2142000 | 8 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | KEBBI STATE
329 | SUPPLY OF OFFCE STATIONERIES AND CONSUMABLES TO KEBBI | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S JUDYK VENTURES NIG LTD | 14th 0ctober, 2014 | 1544970 | 8 Weeks | N/A | 0 | 11th November, 2014 | completed | 100% | N/A | N/A | KEBBI STATE
330 | RELIEF MATERIALS | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | A.O Adedoyin Nig Ltd | 14th 0ctober, 2014 | 15250000 | 8 Weeks | N/A | 15250000 | 11th November, 2014 | completed | 100% | N/A | N/A | KEBBI STATE
331 | RELIEF MATERIALS | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Ibtal Global Resources Ltd | 14th 0ctober, 2014 | 10000000 | 8 Weeks | N/A | 10000000 | 11th November, 2014 | completed | 100% | N/A | N/A | KEBBI STATE
332 | SUPPLY OF COOKING OIL | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Sparkling Energy Resources | 14th 0ctober, 2014 | 12783000 | 8 Weeks | N/A | 12783000 | 11th November, 2014 | completed | 100% | N/A | N/A | KEBBI STATE
333 | SUPPLY OF COOKING OIL | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Sparkling Energy Resources | 14th 0ctober, 2014 | 12783000 | 8 Weeks | N/A | 12783000 | 11th November, 2014 | completed | 100% | N/A | N/A | KEBBI STATE
334 | SUPPLY OF COOKING OIL | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Sparkling Energy Resources | 14th 0ctober, 2014 | 14850000 | 8 Weeks | N/A | 14850000 | 11th November, 2014 | completed | 100% | N/A | N/A | KEBBI STATE
335 | SUPPLY OF COOKING OIL | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Sparkling Energy Resources | 14th 0ctober, 2014 | 10000000 | 8 Weeks | N/A | 10000000 | 11th November, 2014 | completed | 100% | N/A | N/A | KEBBI STATE
336 | REGISTRATION OF VEHICLES | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | A2A Firstmile International Ltd | 14th 0ctober, 2014 | 1240000 | 8 Weeks | N/A | 1240000 | 11th November, 2014 | completed | 100% | N/A | N/A | KEBBI STATE
337 | SUPPLY OF GRAINS | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | AFO. B OIL & GAS LTD | 14th 0ctober, 2014 | 5750000 | 8 Weeks | N/A | 5750000 | 11th November, 2014 | completed | 100% | N/A | N/A | KEBBI STATE
338 | INSURANCE COVER | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | METI INSURANCE BROKERS | 14th 0ctober, 2014 | 8322000 | 8 Weeks | N/A | 8322000 | 11th November, 2014 | completed | 100% | N/A | N/A | KEBBI STATE
339 | SUPPLY OF GRAINS | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | DESHO NIG. ENTERPRISES | 14th 0ctober, 2014 | 6750000 | 8 Weeks | N/A | 6750000 | 11th November, 2014 | completed | 100% | N/A | N/A
340 | MONITORING AND EVALUATION | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | OSEYA FUNSHO J | 14th 0ctober, 2014 | 493500 | 8 Weeks | N/A | 493500 | 11th November, 2014 | completed | 100% | N/A | N/A
341 | SUPPLY OF GRAINS | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | MURAB INTERGRATED RESOURCES | 14th 0ctober, 2014 | 15000000 | 8 Weeks | N/A | 15000000 | 11th November, 2014 | completed | 100% | N/A | N/A
342 | SUPPLY OF 15 SEATER BUS | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | INNOSSON VEHICLES MANUFACTURING CO. LTD | 14th 0ctober, 2014 | 9240000 | 8 Weeks | N/A | 9240000 | 11th November, 2014 | completed | 100% | N/A | N/A
343 | RELIEF MATERIALS | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | A.O Adedoyin Nig Ltd | 14th 0ctober, 2014 | 11700000 | 8 Weeks | N/A | 11700000 | 11th November, 2014 | completed | 100% | N/A | N/A
344 | supply of food items | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Lasting Impression Global Solution Nig. Ltd | 14th 0ctober, 2014 | 18780000 | 8 Weeks | N/A | 18780000 | 11th November, 2014 | completed | 100% | N/A | N/A
345 | Supply of Motor vehicle | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Innosson Vehicle Manufacturing Co. Ltd | 14th 0ctober, 2014 | 16180000 | 8 Weeks | N/A | 16180000 | 11th November, 2014 | completed | 100% | N/A | N/A
346 | Supply of Laminating Machine | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Belsha Printing Press Ltd | 14th 0ctober, 2014 | 6500000 | 8 Weeks | N/A | 6500000 | 11th November, 2014 | completed | 100% | N/A | N/A
347 | Supply of motor vehicle | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | innosson Manufacturing Co. | 14th 0ctober, 2014 | 15980000 | 8 Weeks | N/A | 15980000 | 11th November, 2014 | completed | 100% | N/A | N/A
348 | supply of grains | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S centerstage Global Venture | 14th 0ctober, 2014 | 10000000 | 8 Weeks | N/A | 10000000 | 11th November, 2014 | completed | 100% | N/A | N/A
349 | Logistics | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Akinribido Henry | 14th 0ctober, 2014 | 3950000 | 8 Weeks | N/A | 3950000 | 11th November, 2014 | completed | 100% | N/A | N/A
350 | Supply of Schelter | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Abdu Maissminti and Son Enterprise | 14th 0ctober, 2014 | 14310000 | 8 Weeks | N/A | 14310000 | 11th November, 2014 | completed | 100% | N/A | N/A
351 | Monitoring and evaluation | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Akinribido Henry | 14th 0ctober, 2014 | 10078000 | 8 Weeks | N/A | 10078000 | 11th November, 2014 | completed | 100% | N/A | N/A
352 | Supply of fertilizers | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | Jasaj Investment Ltd | 14th 0ctober, 2014 | 10000000 | 8 Weeks | N/A | 10000000 | 11th November, 2014 | completed | 100% | N/A | N/A
353 |  | May 2nd 2014 | PTB | National Cometitive Bidding | 25th August, 2014 | 2nd September 2014 | ₦ 9,666,390,788.00 | N/A | 22nd September, 2014 | Yes | M/S Hammdes Nig Ltd | 14th 0ctober, 2014 | 25000000 | 8 Weeks | N/A | 25000000 | 11th November, 2014 | completed | 100% | N/A | N/A
| TOTAL | [11 empty] | 9396170038.45

## NPC
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) : |  |  | NATIONAL PLANNING COMMISSION
MINISTRY : |  |  | NATIONAL PLANNING COMMISSION
FINANCIAL YEAR : |  |  | 2014
|  | BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N |  | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2014 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | 1 | Printing of 4,000 copies of the 2012 Monitoring and Performance Evaluation Report | 29th November, 2013 / Newspaper (Punch,Daily Trust &FTJ) | MTB | SELECTIVE TENDERING (ST) |  |  | FY2014 | N/A | July, 2014 |  | Messrs Garewa Investment Ltd | 22nd January, 2014 | 41280000 | Dec 2013 - Jan. 2014 | 27th Jan. 2014 | 41280000 |  | Printing | 100% | N/A | N/A
2 | 2 | The Supply of office equipments for SURE-P Monitoring and Evaluation Programme Implementation Units (PIUs) | 29th November, 2013 | MTB | Open Compititive Bidding (OCB) |  |  | Wide FY 2014 | N/A | July, 2014 |  | Messrs Share Merchants Nig. Ltd | 6th March, 2014 | 12215500 | 2014-03-01 | 13th March, 2014 | 12215500 | March, 2014 | Supply | 100% | N/A | N/A
3 |  | Engagement of a Consultant for the Development, Printing and Training on the use of M&E Manual for SURE-P Program | 29th November, 2013 | MTB | OCB |  |  | Wide FY 2014 | N/A | July, 2014 |  | Messrs Ra-ah Consulting Ltd | 12th March, 2014 | 24313500 | 2014-04-01 | 19th March, 2014 | 24313500 | April, 2014 | Services | 100% | N/A | N/A
4 |  | Printing of 1,000 copies of the Booklet on National Planning Commission (NPC) Hand Book | 29th November, 2013 | MTB | ST |  |  | FY 2014 | N/A | July, 2014 |  | Messrs Diza Media Prints Limited | 24th July 2014 | 3755000 | 2014-08-01 | 30th July, 2014 | 3755000 | August, | Printing | 100% | N/A | N/A
5 |  | Printing of 1,000 copies of the Booklet on National Planning Commission (NPC) Strategic Plan | 29th November, 2014 | MTB | ST |  |  | FY 2014 | N/A | July, 2014 |  | Messrs Diza Media Prints Limited | 24th July, 2014 | 4500000 | August,2014 | 30th July , 2014 | 4500000 | August, 2014 | Printing | 100% | N/A | N/A
6 |  | Printing of 1,000 copies of the Booklet on National Planning Commission (NPC) Staff Manual | 29th November,2014 | MTB | ST |  |  | FY 2014 | N/A | July, 2014 |  | Messrs Diza Media Limited | 24th July, 2014 | 4500000 | August, 2014 | 30th July, 2014 | 4500000 | August, 2014 | Printing | 100% | N/A | N/A
7 |  | The Implementation of Parallel-Run Programme for Sure-P | 29th November, 2014 | MTB | OCB |  |  | FY 2014 | N/A | JULY, 2014 |  | Messrs Infobyte Technologies Ltd | 18th August, 2014 | 210000000 | September, 2014 | August, 2014 | 210000000 | September, 2014 | Services | 100% | N/A | N/A
8 |  | The supply of Vehicles to the Commission | NPC BOARD | MTB | ST |  |  | FY 2014 | N/A | August, 2014 |  | Messrs Elizade Nig. Ltd | 20th August, 2014 | 62698001.1 | August, 2014 | August, 2014 | 62698001.1 | August, 2014 | Supply | 100% | N/A | N/A
9 |  | The supply of office equipment for Subsidy Reinvestment Programme’s Implementation Unit (PIU) | 29th November, 2013 | MTB | OCB |  |  | FY 2014 | N/A | August, 2014 |  | Messrs Synops Consulting Ltd | 25th August, 2014 | 9992000 | August,2014 | August, 2014 | 9992000 | August, 2014 | Supply | 100% | N/A | N/A
10 |  | Rehabilitation/ Repair of Waterway (Supply) line/ Civil works | NPC BOARD | MTB | ST |  |  | FY 2014 | N/A | August, 2014 |  | Messrs Aricontek Resources Ltd | 26th August,2014 | 29869349.98 | August,2014 | August, 2014 | 29869349.98 | August, 2014 | Works | 100% | N/A | N/A
11 |  | The Furnishing of Executive Conference with Audio Conference Studio | NPC BOARD | MTB | ST |  |  | FY 2014 | N/A | August, 2014 |  | Messrs Royal Oak Interiors Ltd | 27th August, 2014 | 26586525 | August,2014 | August, 2014 | 26586525 | August, 2014 | Works | 100% | N/A | N/A
12 |  | The Printing of 5,000 Copies of the Report on the Performance of the Economy for year 2013 | NPC BOARD | MTB | Single Sourcing |  |  | FY 2014 | N/A | August, 2014 |  | Messrs Fastrack Investment Company Ltd | 27th August, 2014 | 44510000 | August,2014 | August, 2014 | 44510000 | August, 2014 | Printing | 100% | N/A | N/A
13 |  | The renewal of the contract of the Facility Management of the Commission | On-running | MTB | OCB |  |  | FY 2014 | N/A | August, 2014 |  | Messrs Annai Ltd | 27th August, 2014 | 35270072.26 | August, 2014 | August, 2014 | 35270072.26 | August, 2014 | Services | 100% | N/A | N/A
14 |  | The Appointment of Independent Consultants to conduct and compile Independent Verification and Assessment Exercise of MDAs | NPC BOARD | MTB | ST |  |  | FY 2014 | N/A | August, 2014 |  | Messrs Fasahad Global Resources Ltd | 27th August, 2014 | 99122667 | August, 2014 | August, 2014 | 99122667 | August, 2014 | Services | 100% | N/A | N/A
15 |  | Printing of 4,000 copies of SURE-P Annual Project Report | NPC BOARD | MTB | ST |  |  | FY 2014 | N/A | August, 2014 |  | Messrs Diza Media Prints Ltd | 28th August, 2014 | 20800000 | August,2014 | August, 2014 | 20800000 | August, 2014 | Printing | 100% | N/A | N/A
16 |  | The Printing of 2,000 Copies of 518 pages document of the Proceedings, Resolution and Conclusions of JPB and National Council for Development Planning (NCDP) from 2009 – 2013 | NPC BOARD | MTB | ST |  |  | FY 2014 | N/A | September, 2014 |  | Messrs Busy Brain Imagination Service Ltd | 2nd September, 2014 | 12461500 | August, 2014 | August, 2014 | 12461500 | August, 2014 | Printing | 100% | N/A | N/A
17 |  | The Replacement and Installation of Batteries in Server Room | NPC BOARD | MTB | ST |  |  | FY 2014 | N/A | September, 2014 |  | Messrs Interglobal Ltd | 5th September, 2014 | 2544949.99 | September, 2014 | September, 2014 | 2544949.99 | September, 2014 | Supply | 100% | N/A | N/A
18 |  | Supply of Furniture/Partitioning of NPC Head Office | NPC BOARD | MTB | OCB |  |  | FY 2014 | N/A | September, 2014 |  | Messrs Marvel Nig. Limited | 22nd September, 2014 | 55260000 | September, 2014 | September, 2014 | 55260000 | September, 2014 | Supply | 100% | N/A | N/A
19 |  | Provision of Electronic Library System project | NPC BOARD | MTB | OCB |  |  | FY 2014 | N/A | September, 2014 |  | Messrs Infobyte Technologies Ltd | 22nd September, 2014 | 44564625 | September, 2014 | September, 2014 | 44564625 | ON-GOING | Services | 50% | N/A | N/A
20 |  | Provision of Document Management System project | NPC BOARD | MTB | OCB |  |  | FY 2014 | N/A | September, 2014 |  | Messrs Infobyte Technologies Ltd | 22nd September, 2014 | 70612500 | September, 2014 | September, 2014 | 70612500 | ON-GOING | Services | 30% | N/A | N/A
21 |  | Provision of Maintenance Service contract for the Monitoring and Evaluation GIS project | NPC BOARD | MTB | OCB |  |  | FY 2014 | N/A | September, 2014 |  | Messrs Infobyte Technologies Ltd | 22nd September, 2014 | 36627159.66 | September, 2014 | September, 2014 | 36627159.66 | ON-GOING | Services | 35% | N/A | N/A
22 |  | The Supply of Desktop Computers to NPC | NPC BOARD | MTB | ST |  |  | FY 2014 | N/A | October, 2014 |  | Messrs Liviasoft Tech Ltd | 22nd October, 2014 | 4999950 | October, 2014 | September, 2014 | 4999950 | September, 2014 | Supply | 100% | N/A | N/A
23 |  | The Supply of Laptop Computers for TAs and SAs to the HMNP | NPC BOARD | MTB | ST |  |  | FY 2014 | N/A | October, 2014 |  | Messrs Umulsalam Global Nig. Ltd | October, 2014 | 4919880 | October, 2014 | September, 2014 | 4919880 | September, 2014 | Supply | 100% | N/A | N/A
24 |  | The Printing of 10,000 copies of about 400 pages National Integrated Infrastructure Master Plan (NIIMP) | 14th July, 2014 (Leadership, FTJ and Daily Trust) | MTB | OCB |  |  | FY 2014 | N/A | 4th November, 2014 |  | Messrs Fastrack Investment Company Ltd | November, 2014 | 99500000 | November, 2014 | November, 2014 | 99500000 | November, 2014 | Printing | 100% | N/A | N/A
|  | The award of contract for Consultancy for the First phase of Implementation of NIIMP | 2014 | MTB | OCB |  |  | FY 2014 | N/A | 2014 |  | Messrs World Energy Consult | 2014 | 99500000 | 2014 | 2014 | 99,50,000.00 | 2014 | Services | ON-GOING
|  | Total Facility Management of NPC Head Office May 2013 – May 2014 | May 2013-May 2014 | MTB | OCB |  |  | FY 2014 | N/A | MAY 2013-MAY 2014 |  | Messrs Annai Limited | 2014-05-01 | 24408213.12 | 2014-05-01 | 2014-06-01 | 24408213.12 | 2014 | Services | 100% | N/A | N/A
|  | Review of Baseline Studies and Impact Assessment for SURE-P | 2014 | MTB | OCB |  |  | FY 2014 | N/A | DEC. 2013 |  | Monitoring and Evaluation Institute Limited | DEC. 2013 | 36705088.8 | 2014 | 2014 | 36705088.8 | 2014 | Services | 100% | N/A | N/A
|  | Printing of 5000 copies of the First Operational Plan (FOP) of (NIIMP) | 2014 | MTB | ST |  |  | FY 2014 | N/A |  |  | Messrs Fastrack Investment Company Ltd | 2014 | 14000000 |  | 2014 | 14000000 | 2014 | Printing | 100% | N/A | N/A
|  | Printing of 30,000 copies of Facts and Figures on NIIMP (2014-2043)as flyers for investor’s guide | 2014 | MTB | ST |  |  | FY 2014 | N/A | 2014 |  | Messrs Fastrack Investment Company Ltd | 2014 | 4950000 | 2014 | 2014 | 4950000 | 2014 | Printing | 100% | N/A | N/A
|  | Printing of 5000 Copies of Annual Performance Report on the Nigerian Economy for the year 2013 | 2014 | MTB | ST |  |  | FY 2014 | N/A |  |  | Messrs. Fastrack Investment Co. Ltd | 2014 | 44000000 | 2014 | 2014 | 44000000 | 2014 | Printing | 100% | N/A | N/A
|  | Conferencing and Furnishing of Hon. Minister’s Conference Rooms | 2014 | MTB | OCB |  |  | FY 2014 | N/A | 2014 |  | Messrs. Royal Oaks Interiors Ltd | 2014 | 26586525 | 2014 | 2014 | 26586525 | 2014 | Supply | 100% | N/A | N/A
|  | Purchase of five (5) Nos. Operational Vehicles for the activities of the Commission | 2014 | MTB | ST |  |  | FY 2014 | N/A | 2014 |  | Messrs. Elizade Motors Ltd | 2014 | 62700001.1 | 2014 | 2014 | 62700001.1 | 2014 | Supply | 100% | N/A | N/A
|  | Supply of 50 Nos laptop computers to NPC | 2014 | MTB | OCB |  |  | FY 2014 | N/A | 2014 |  | Messrs Jaybest International Ltd | 2014 |  | 2014 | 2014 | 9259250 | 2014 | Supply | 100% | N/A | N/A
|  | Renewal of Contract on Total Facility Management of the Commission | 2014 | MTB | ST |  |  | FY 2014 | N/A | 2014 |  | Messrs. Annai Ltd | 2014 |  | 2014 | 2014 | 35270072.26 | 2014 | Services | 75% | N/A | N/A
|  | Supply of office equipment (SURE-P) to NPC | 2014 | MTB | OCB |  |  | FY 2014 | N/A | 2014 |  | Messrs Synops Consulting Ltd | 2014 | 9992000 | 2014 | 2014 | 9992000 | 2014 | Supply | 100% |  | N/A
|  | Training of Consultants for SURE-P Monitoring and Evaluation Manual | 2014 | MTB | ST |  |  | FY 2014 | N/A | 2014 |  | Messrs Ra’ah Institute Development Ltd | 2014 | 21956430 | 2014 | 2014 | 21956430 | 2014 | Services | 100% | N/A | N/A
|  | Implementation of Parallel-Run programme for SURE-P |  | MTB | OCB |  |  | FY 2014 | N/A | 2014 |  | Messrs Infobyte Technologies Ltd | 2014 | 210000000 | 2014 | 2014 | 210000000 | 2014 | Services | 70% | N/A | N/A
2014
[15 empty] | 2014 | 2014 |  | 2014
|  | Printing of documentary for the Launch of the National Integrated Infrastructure Master Plan (NIIMP) | 2014 | MTB | ST |  |  | FY 2014 | N/A | 2014 |  | Messrs Lenz Communications | 2014 | 1950000 | 2014 | 2014 | 1950000 | 2014 | Printing | 100% | N/A | N/A
|  | Provision of Robust ICT Platform for National Integrated Infrastructure Master Plan (NIIMP) | 2014 | MTB | OCB |  |  | FY 2014 | N/A | 2014 |  | Messrs Inspiration Technology Ltd | 2014 | 60100000 | 2014 | 2014 | 60100000 | 2014 | Services | 100% | N/A | N/A
|  | Supply of two (2) Toyota Hilux vehicles for SURE-P | 2014 | MTB | OCB |  |  | FY 2014 | N/A | 2014 |  | Messrs Ineh-Mic Autos Co. Ltd | 2014 | 16275000 | 2014 | 2014 | 16275000 | 2014 | Supply | 100% | N/A | N/A
|  | Printing of 2,400 copies of Physical Monitoring Visit of SURE-P | 2014 | MTB | OCB |  |  | FY 2014 | N/A | 2014 |  | Messrs Tuncheck Prime Prints Nig. Ltd | 2014 | 12000000 | 2014 | 2014 | 12000000 | 2014 | Printing | 100% | N/A | N/A
|  | Printing of 4000 copies of SURE-P Performance for the year 2014 | 2014 | MTB | OCB |  |  | FY 2014 | N/A | 2014 |  | Messrs Diza Media Limited | 2014 | 27000000 | 2014 | 2014 | 27000000 | 2014 | Printing | 100% | N/A | N/A
|  | Supply of Desktop computers to NPC | 2014 | MTB | OCB |  |  | FY 2014 | N/A | 2014 |  | Messrs Liviasoft Technologies Ltd | 2014 | 4999950 | 2014 | 2014 | 4999950 | 2014 | Supply | 100% | N/A | N/A
|  | TOTAL | [11 empty] | 1638026388.01

## POPULATION
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) :
MINISTRY : |  | NATIONAL POPULATION COMMISSION.
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2014 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | purchase of a 500KVA sound proof Generating set. | Certificate of No objection to embark on Restricted Tendering. | Miniterial Tenders Board. | Restricted Tendering. | 26th Sept,2014 | 20th oct,2014 | 22000000 | NA | 21st.oct.2014 | Least Tenderer with Favourable condition of payment in line with Govt contract. | JMG LIMITED | 24th oct,2014 | 16375000 | 2 weeks | NA | 16375000 | 10th Nov,2014 | COMPLETED | 100% | NA | NA
| TOTAL | [11 empty] | 16375000

## NEPAD
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) : |  | NEPAD NIGERIA
MINISTRY : |  | OSGF
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014 | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2014 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | Rehabilitation of Nepad Office Building | 16/06/14 Federal Tender journal, Daily trust, Daily Sun | Parastatal Tenders Board | NCB | 2014-08-04 | 18/09/2014 | #34,990,000.00 | NIL | 2014-10-09 | YES | M/S BELLHOUSE TECHNOLOGY LTD. | 2014-10-10 | 114739687.75 | 6 months | 2014-11-29 | #31,551,312.80 | 30/04/2015 | on going | 30% | N/A | NIL | Work on-going
2 | Cleaning and funmigation of Nepad Offce | 16/06/14 Federal Tender journal, Daily trust, Daily Sun | Parastatal Tenders Board | NCB | 2014-08-04 | 18/09/2014 | #7,000,000.00 | NIL | 2014-10-09 | YES | M/S OBIS ASSOCIATES NIGERIA LTD | 2014-10-10 | 6965462.7 | 12 Months | 2014-12-01 | #1,160,910.45 | 2015-12-01 | 0n going | 8.3% | N/A | NIL | Work on-going
3 | Procurement and Installation of Additional Security Equipment | 16/06/14 Federal Tender journal, Daily trust, Daily Sun | Parastatal Tenders Board | NCB | 2014-08-04 | 18/09/2014 | #18,191,579.00 | NIL | 2014-10-09 | YES | MERRY AVIATION COMM. ELECTONIC & INDUSRIES NIG.LTD | 2014-10-10 | 15531000 | 2 Weeks | 2014-12-13 | #15,531,000.00 | 2014-12-24 | Completed | 100% | N/A | NIL | Work on-going
4 | Printing and supply of Security documents | 16/06/14 Federal Tender journal, Daily trust, Daily Sun | Parastatal Tenders Board | NCB | 2014-08-04 | 2014-09-18 | #6,821,842.00 | NIL | 2014-10-22 | YES | M/S ALL SORT PRODUCTION COMPANY LTD | 22/10/2014 | 310024.68 | 2 Weeks | 2014-10-23 | #310,024.68 | 2014-11-05 | Completed | 100% | N/A | NIL | Completed
5 | Production of Sinages (NEON) NEPAD new Logo, Roll Stand, Banners and Flags | NIL | AO | NS | 2014-09-03 | 2014-09-05 | #5,281,999.00 | NIL | 2014-09-19 | YES | M/S BASE PRINTER | 22/09/2014 | 995000 | 1 Week | 2014-10-23 | Not Paid | 2014-10-29 | Completed | 100% | N/A | NIL | Completed
6 | Printing of Official Document (Non -Security) | NIL | AO | NS | 2014-08-27 | 2014-08-27 | #1,819,158.00 | NIL | 2014-08-28 | YES | M/S ESABOF VENTURES LTD. | 2014-09-01 | 2364250 | 2 Weeks | 2014-09-02 | #2,364,250.00 | 15/09/2014 | Completed | 100% | N/A | NIL | Completed
7 | Printing of Official Envelopes | NIL | AO | NS | 2014-08-28 | 2014-08-27 | #1,819,158.00 | NIL | 2014-08-28 | YES | M/S GLAXO GLOBAL VISION | 2014-09-01 | 2487500 | 2 Weeks | 2014-09-02 | #2,487,500.00 | 15/09/2014 | Completed | 100% | N/A | NIL | Completed
8 | procurement of Stationery Items | NIL | AO | NS | 2014-09-26 | 2014-10-03 | #38,202,315.00 | NIL | 2014-10-21 | YES | M/S BISOYE VENTURES | 23/10/2014 | 2415500 | 2 Weeks | 2014-10-26 | #2,415,500.00 | 2014-11-06 | Completed | 100% | N/A | NIL | Completed
9 | Supply of Sharp Toners, Flash Drive | NIL | AO | NS | 2014-09-23 | 2014-10-03 | #38,202,315.00 | NIL | 2014-10-21 | YES | M/S ELNITA NIGERIA LTD. | 23/10/2014 | 2456000 | 2 Weeks | 2014-10-26 | #2,456,000.00 | 2014-11-06 | Completed | 100% | N/A | NIL | Completed
10 | Procurement of Computer Consumables | NIL | AO | NS | 2014-09-29 | 2014-10-08 | #38,202,315.00 | NIL | 2014-10-21 | YES | M/S GRAMID GLOBAL INVESTMENT NIGERIA LTD. | 23/10/2014 | 2448000 | 2 Weeks | 2014-10-24 | #2,448,000.00 | 2014-11-06 | Completed | 100% | N/A | NIL | Completed
11 | Procurement of Office Equipment | NIL | AO | NS | 2014-10-09 | 2014-10-10 | #38,202,315.00 | NIL | 2014-10-21 | YES | M/S ANJUBA GLOBAL RESOURCES LTD | 23/10/2014 | 1893500 | 2 Weeks | 2014-10-24 | #1,893,500.00 | 2014-11-06 | Completed | 100% | N/A | NIL | Completed
12 | Supply of Photocopy Paper | NIL | AO | NS | 2014-09-29 | 2014-10-03 | #38,202,315.00 | NIL | 2014-10-21 | YES | M/S CHESTINO INVESTMENT LTD | 23/10/2014 | 2345000 | 2 Weeks | 2014-10-24 | #2,345,000.00 | 2014-11-06 | Completed | 100% | N/A | NIL | Completed
13 | Procurement of Office Cabinet s | NIL | AO | NS | 2014-09-30 | 2014-10-03 | #38,202,315.00 | NIL | 2014-10-21 | YES | M/S CLET & CLETTA NIGERIA Ltd. | 23/10/2014 | 2046000 | 2 Weeks | 2014-10-26 | #2,046,000.00 | 2014-11-06 | Completed | 100% | N/A | NIL | Completed
14 | Procurement of Laserjet Toner | NIL | AO | NS | 2014-09-29 | 2014-10-03 | #38,202,315.00 | NIL | 2014-10-21 | YES | M/S UGOMEC & ASSOCIATE LTD. | 23/10/2014 | 2170000 | 2 Weeks | 2014-10-25 | #2,170,000.00 | 2014-11-06 | Completed | 100% | N/A | NIL | Completed
15 | supply of Laptop Computers | NIL | AO | NS | 2014-11-06 | 2014-11-20 | #38,202,315.00 | NIL | 2014-11-25 | YES | M/S DIGIT PLUS LTD. | 2014-12-01 | 2220000 | 2 Weeks | 2014-12-02 | #2,220,000.00 | 2014-12-15 | Completed | 100% | N/A | NIL | Completed
16 | Supply od Desktop Computers | NIL | AO | NS | 2014-11-06 | 2014-11-20 | #38,202,315.00 | NIL | 2014-12-05 | YES | M/S DUBEX GLOBAL TECHNOLOGY EQUIPMENT LTD | 2014-12-10 | 2376000 | 2 Weeks | 2014-12-11 | #2,376,000.00 | 2014-12-12 | Completed | 100% | N/A | NIL | Completed
17 | Supply of Office photocopy / Scanner Machine | NIL | AO | NS | 2014-11-06 | 2014-11-20 | #38,202,315.00 | NIL | 2014-12-05 | YES | M/S DOMO TECHNOLOGY LTD | 2014-12-10 | 2350000 | 2 Weeks | 2014-12-11 | #2,350,000.00 | 2014-12-12 | Completed | 100% | N/A | NIL | Completed
18 | Procurement of Intercom Services | 15/09/2014, NEPAD Nigeria Notice Board Wesite | AO | NS | 2014-10-27 | 30/10/2014 | #5,281,999.00 | NIL | 2014-11-03 | YES | M/S FLUENT INT. LTD | 2014-11-03 | 3965535 | 2 Weeks | 2014-11-05 | #3,965,535.00 | 19/11/214 | Completed | 100% | N/A | NIL | Completed
19 | Procurement of Nissan vehicle (Sentra 1.8, Nissan Teanna 3.5L SL Auto | NIL | Parastatal Tenders Boared | NS | NIL | NIL | #316,550,000.00 | 31/10/2014 | 14/11/2014 | Direct Procurement | M/S STALLION NMN LTD | 14/11/2014 | 16957500 | 2 Weeks | 2014-11-17 | #16,957,500.00 | 28/11/2014 | Completed | 100% | N/A | NIL | Completed
20 | Procurement of vehicle (Innoson 17 Seater Bus, Petrol Engine , Nissan Pick up 2.4L STD Maunal) | NIL | Parastatal Tenders Boared | NS | NIL | NIL | #316,550,000.00 | 31/10/2014 | 2014-11-14 | Direct Procurement | M/S STALLION NMN LTD | 2014-12-04 | 27137250 | 2 Weeks | 2014-12-05 | #27,137,250.00 | 18/12/2014 | Completed | 100% | N/A | NIL | Completed
21 | Renovation of SAN's Office Federal Secretariat Complex | NIL | AO | NS | 2014-12-10 | 2014-12-11 | #7,000,000.00 | NIL | 2014-12-12 | YES | M/S BELLHOUSE TECHNOLOGY LTD. | 2014-12-12 | 4945219.47 | 1 Week | 2014-12-15 | #3,130,000.00 | 19/12/2014 | Completed | 100% | N/A | NIL | Completed
22 | Installation of Electrical Fittings & window Blind at SAN's Office Federal Secretariat complex | NIL | AO | NS | 2014-12-10 | 2014-12-12 | #7,000.000.00 | NIL | 2014-12-12 | YES | M/S Seijos nigeria | 2014-12-12 | 4638385 | 1 Week | 2014-12-15 | #2,455,000.00 | 19/12/2014 | Completed | 100% | N/A | NIL | Completed
| TOTAL | [11 empty] | 223756814.6

## NEXIM
PROCURING ENTITY (MDA) : |  | NIGERIAN EXPORT-IMPORT BANK (NEXIM)
MINISTRY : |  | FEDERAL MINISTRY OF FINANCE
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2013 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2013 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | Consultancy Services for the Design and Implementation of the Technical Assistance Program for Capacity Building for Small Medium Enterprises(SMES) | July 14, 2014 in Business Day; The Guardian; Federal Tenders' Journal/African Press Organisation; July 21st, 2014-United Nations Development Business bulletin | Ministerial Tender's board | Quality Based Selection of Consultant | September 24th, 2014 | september 29th, 2014 | 185605617.1 | NIL | NIL | NIL | BDO Management Ent. Consulting Ltd | NOT YET AWARDED | NIL | 5 YEARS | NIL | NIL | NIL | NIL | NIL | NIL | NIL
2 | For the design and implementation of technical Assistance Program for Capacity Building at Nigerian Export-Import Bank | July 14, 2014 in Business Day; The Guardian; Federal Tenders' Journal/ Frican Press Organisation-July 14th, 2014, United Nations Development Business bulletin-July 21st, 2014 | Ministerial Tender's board | Quality Based Selection of Consultant | September 24th, 2014 | September 29th, 2014 | 163,590.000.00 | NIL | NIL | NIL | D & B (Dun & Bradstreet) | NOT YET AWARDED | NIL | 2 YEARS | NIL | NIL | NIL | NIL | NIL | NIL | NIL
| TOTAL | [11 empty] | NIL

## NIGCOMSAT
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) :
MINISTRY : NIGCOMSAT
FINANCIAL YEAR : 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 30/06/2015 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2013 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | Construction, Installation and Commissioning of 9.3 C-Band Antenna(Extended C-Band Earth Station Antenna) | July 28 - August 10, 2014, Federal Tenders Journal | Parastatal Tenders Board | Bids for Tender | September 8th, 2014 | September 10th, 2014 | N950,000,000 for Ground Network Infrastructure, 2014 appropriation | N/A | N/A | Marshill Technology Services Ltd | Marshill Technology Services Ltd | December 5th, 2014 | 59940000 | 2 Months | N/A | 57890000 | 15th January, 2015 | completed | 100%
2 | Construction and Installation of HUB and IP Networking Equipment | July 28-August 10, 2014, Federal Tenders Journal | Parastatal Tenders Board | Bids for Tender | September 8th, 2014 | September 10th, 2014 | N950,000,000 for Ground Network Infrastructure, 2014 Appropriation | N/A | N/A | Business Communication Ltd | Business Communication Ltd | December 4th, 2014 | 94641796.2 | 2 Months | N/A | 94641796.2 | 15th January, 2015 | completed | 100%
| TOTAL | [11 empty] | 154581796.2

## NDDC
PROJECTS AWARDED BY NIGER DELTA DEVELOPMENT COMMISSION FROM MARCH, 2014 TO DATE
PROJECTS BELOW 250M
A: INFRASTRUCTURE
S/N | DATE | PROJECT TITLE | STATE | CONTRACTOR | CONSULTANT | TYPE | COMPLE-TION PERIOD | FILE REF. NO. | AMOUNT
1 | May, 2014 | Award of Contract for the Emergency Road Repair works on Uquo-Etebi Road, Esit Eket Local Govt. Area | Akwa Ibom State | FOUPLANT NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AKS/2014/001 | 235000000
2 | May, 2014 | Award of Contract for the Construction of Niger Delta Regional Specialist Hospital (Children and Maternity Hospital) | Rivers State | REHAB VITAL SOLUTIONS LTD. |  | Specialist Hospital |  | NDDC/EDP/UIDW/PR/RV/2014/002 | 1995700000
2 | May, 2014 | Award of Contract for the Furnishing of the Prototype University Hostel (1 No.) at the University of Science and Technology, Port Harcourt | Rivers State | KEDITA NIG. LTD. |  | Prototype University | 3 months | NDDC/EDP/UIDW/PR/RV/2014/003 | 89812800
3 | May, 2014 | Award of Contract for the Furnishing of the Prototype University Hostel (1 No.) at the University of Benin | Edo State | ASILADRREN GLOBAL CONSULTING LTD. |  | Prototype University | 3 months | NDDC/EDP/UIDW/PR/ED/2014/004 | 89812800
4 | May, 2014 | Award of Contract for the Furnishing of the Prototype University Hostel (1 No.) at the Imo State University, Owerri | Imo State | ENEGOS INTERNATIONAL COMPANY NIG. LTD. |  | Prototype University | 3 months | NDDC/EDP/UIDW/PR/IM/2014/005 | 89812800
5 | May, 2014 | Award of Contract for the Furnishing of NDDC Youth Corpers Aprtment Complex at Otuoke in Ogbia LGA | Bayelsa State | KMBO ASSOCIATES LTD. |  | Furnishing of NDDC Youth Corpers Aprtment Complex | 3 months | NDDC/EDP/UIDW/PR/BY/2014/006 | 20708940
6 | May, 2014 | Award of Contract for the Furnishing of the Prototype University Hostel (1 No.) at University of Uyo Teaching Hospital | Akwa Ibom State | GRANSEL (NIG.) LTD. |  | Prototype University | 3 months | NDDC/EDP/UIDW/PR/AKS/2014/007 | 89812800
7 | May, 2014 | Award of Contract for the Installation of 3 no. 500KVA, 33/0.415KV transformer at Elele Army Barracks, Ikwerre LGA | Rivers State | HENCON GLOBAL LINK LTD. |  | Transformer Installation | 3 months | NDDC/EDP/UIDW/PR/AKS/2014/008 | 13500000
8 | May, 2014 | Award of Contract for the Construction of Migrant Farmers School Road, Phase II, Ukana Ikot Okoro in Essien Udim LGA | Akwa Ibom State | KANSUANA NIG. LTD. |  | Road | 6 months | NDDC/EDP/UIDW/PR/AKS/2014/009 | 79239830
9 | May, 2014 | Award of Contract for the Construction of NDDC IMSU Hostel Link Road, Owerri Municipal LGA | Imo State | CILAZ INTEGRATED SERVICES LTD. |  | Hostel | 12 months | NDDC/EDP/UIDW/PR/IM/2014/010 | 249878210
10 | May, 2014 | Award of Contract for the Construction of Internal Road in Ibiaku Community with Drainage in Ikono LGA | Akwa Ibom State | KANSUANA NIG. LTD. |  | Road | 6 months | NDDC/EDP/UIDW/PR/AKS/2014/011 | 243439235.05
11 | May, 2014 | Award of Contract for the Construction of Henry Wordu Avenue, Off Mummy B Road, Port Harcourt | Rivers State | STREAM CONST. & EQUIPMENT LTD. |  | Road | 3 months | NDDC/EDP/UIDW/PR/AKS/2014/012 | 77512985
12 | June, 2014 | Award of Contract for the Construction of Ewang Internal Road, Phase 1, Mbo LGA | Akwa Ibom State | MID SEA GEOTECHNICAL SERVICES LTD. |  | Road | 4 months | NDDC/EDP/UIDW/PR/AKS/2014/013 | 201986132.15
13 | June, 2014 | Award of Contract for the Construction of Ama John-Ebon Ukpuru Road in Andoni LGA | Rivers State | FRACTAL CONST. NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/014 | 229079400
14 | May, 2014 | Award of Contract for the Maintenance of Waterways at Akipelai Channel, Ogbia LGA | Bayelsa State | EGABOLA MULTI-SERVICES NIG. LTD. |  | Waterways | 12 months | NDDC/EDP/EPC/PR/BY/14/015 | 60695000
15 | May, 2014 | Award of Contract for the construction of Ifie road network, Road A, Phase 1, Ubeji, Warri LGA | Delta State | A & A GENERAL CONTRACTORS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/016 | 249262455
16 | May, 2014 | Award of Contract for the Construction of Ekpan Flyover Link Road, Awholpro Layout to link Celestial Road, Phase 1, Warri LGA | Delta State | FROT PROJECT & PROCUREMENT SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/017 | 240670012
17 | May, 2014 | Award of Contract for the Erosion control/drain works at Ukwu Akpulu-Umuisim road, Ideato LGA | Imo State | JOVAN & JEPHPHAN PROJECT DEV. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/018 | 96993136.75
18 | May, 2014 | Award of Contract for the construction of Ekpan Flyover link road, Awhalpro Layout to link Celestial road, Phase II, Warri LGA | Delta State | JOLLY ENERGY FLEET LTD. |  | Flyover | 12 months | NDDC/EDP/UIDW/PR/DT/14/019 | 248177512.75
19 | May, 2014 | Award of Contract for the construction of Ekpan Flyover link road, Awhalpro Layout to link Celestial road, Phase III, Warri LGA | Delta State | LAKEFIELD ENERGY SERVICES LTD. |  | Flyover | 12 months | NDDC/EDP/UIDW/PR/DT/14/020 | 231127512
20 | May, 2014 | Award of Contract for the Construction of Umuiku-Ozaa Amaoji Obegu road (Phase 1) in Ukwa West LGA | Abia State | KENOCHIL SERVICES NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/021 | 239847350
21 | May, 2014 | Award of Contract for the Construction of Ogbopina-Ama Road, Amassoma, Southern Ijaw LGA | Bayelsa State | NOBLE CAPITAL NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/022 | 219603395
22 | June, 2014 | Award of Contract for the Construction of Ifie road network, Road A, Phase III, Ubeji Warri LGA, Delta State | Delta State | EXCEL CONTRACTORS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/023 | 246780325
23 | June, 2014 | Award of Contract for the Construction of Ifie road network, Road A, Phase II, Ubeji Warri LGA, Delta State | Delta State | NIGERLAND CONTRACTORS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/024 | 246780325
24 | June, 2014 | Award of Contract for the Construction of Eyufo-Uduonim road, Mbo LGA | Akwa Ibom State | MUBEX INT'L LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AKS/14/025 | 246000000
25 | June, 2014 | Award of Contract for the Construction of Moboluwaduro road, Ifon, Ose LGA | Ondo State | PECULIAR ULTIMATE CONCERNS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/ON/14/026 | 150000000
26 | June, 2014 | Award of Contract for the Construction of Umuodu-Afor Umueze 2km road in Ehime, Mbano LGA | Imo State | FIRST UNION PROJECTS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/027 | 249500000
27 | June, 2014 | Award of Contract for the Construction of Akabuka Internal road in Ogba/Egbema/ Ndoni LGA | Rivers State | BASH & BOLTS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/028 | 249000000
28 | June, 2014 | Award of Contract for the Construction of Rigid Pavement Road 2km from Awankuma to Abagwu Rural road, Agwuankuma, Arochukwu LGA | Abia State | BRETT INTEGRATED INVESTMENT LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/029 | 248000000
29 | June, 2014 | Award of Contract for the Construction of Rumuokpara Link road, Rukpoku, Obio Akpor LGA | Rivers State | LIPPIZANER STALLION NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/030 | 249066000
30 | June, 2014 | Award of Contract for the Construction of Umuodu-Umuangwu-Umuihim 3km road, Umueze 1 in Ehime, Mbano LGA | Imo State | OWEN CONSOLIDATED LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/031 | 249000000
31 | June, 2014 | Award of Contract for the Construction of Disney Road with spur to Amawehule Str. Rumuibekwe in Obio Akpor LGA | Rivers State | RENE & DEEN NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/032 | 200000000
32 | June, 2014 | Award of Contract for the Construction of Concrete pavement, Okidiware Quarters Project in Ekeremor LGA | Bayelsa State | AGBEINSCO WORLDWIDE LTD. |  | Concrete Pavement | 12 months | NDDC/EDP/UIDW/PR/RV/14/033 | 245826470
33 | June, 2014 | Award of Contract for the Furnishing of NDDC Hostel (1 No.), Delta State University, Abraka | Delta State | TOSKAT NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/034 | 89812800
34 | June, 2014 | Award of Contract for the Construction of Culverts and opening of Abo Bomaji road in Boki LGA | Cross River State | AMPLE DIMENSION LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/CRS/14/035 | 249933500
35 | June, 2014 | Award of Contract for the Construction of Betukwel-Ohong road in Obudu LGA | Cross River State | MAKRICKY NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/CRS/14/036 | 239354250
36 | June, 2014 | Award of Contract for the Construction of Beduabia/Larry Agim Road in Obudu LGA | Cross River State | VITEX INTERBIZ AGENCY LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/CRS/14/037 | 239354250
37 | June, 2014 | Award of Contract for the Construction of Ogbafor/Mgbala Road in Oguta LGA | Imo State | FRANK & GENE INT'L LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/038 | 249874505
38 | June, 2014 | Award of Contract for the Proposed Fence for the completion of University of Uyo Teaching Hospital at Uyo | Akwa Ibom State | BASESTAR ENG. LTD. |  | Fence | 12 months | NDDC/EDP/UIDW/PR/AKS/14/039 | 97086249.2
39 | June, 2014 | Award of Contract for the Construction of Culverts/Drainages at Agadaga/Ugbesia Adjughur Layout Uvwie LGA | Delta State | DORA-DAN GLOBAL RESOURCES LTD |  | Culverts/ Drainages | 12 months | NDDC/EDP/UIDW/PR/DT/14/040 | 249632500
40 | June, 2014 | Award of Contract for the Construction of Access road at the Univeristy of Uyo Teaching Hospital, Uyo | Akwa Ibom State | BASESTAR ENG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AKS/14/041 | 197400566
41 | June, 2014 | Award of Contract for the Construction of St. Michael Close, Off Bright Hope street, Vienna/Ejevwo Road, Off Polokor, Ugborikoko, Uwvie LGS | Delta State | INGOWET SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/042 | 245000000
42 | June, 2014 | Award of Contract for the Construction of Enikogho Road, Ugborikoko, Uwvie LGA | Delta State | FURST ITEMS NIG. CO. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/043 | 249500000
43 | June, 2014 | Award of Contract for the Supply of Quality control equipment for NDDC Project Monitoring and Supervision | Rivers State | KEMAN INT'L CO. |  | Supply | 12 weeks | NDDC/EDP/UIDW/PR/RV/14/044 | 49655000
44 | June, 2014 | Award of Contract for the Training of Fifty (50) Engineers on the use of Quality control/project monitoring equipment | Rivers State | DEBEVA INT'L UPDATE LTD. |  | Training | 12 weeks | NDDC/EDP/UIDW/PR/RV/14/045 | 49450000
45 | June, 2014 | Award of Contract for the Installation of 5 no. 300KVA, 11/0.415KV Transformer at Atiabong, Okiuso Udung Amkpe, Afaha Ibighi, Afaha Okiuso and Okiuse Umoh Villages in Okobo LGA | Akwa Ibom State | BLUEWATERGATE CONSULTING CONSORTIUM |  | Transformer | 3 months | NDDC/EDP/UIDW/PR/AKS/14/046 | 22500000
46 | June, 2014 | Award of Contract for the Construction of Rigid pavement 1.8km Road from Amauvi-Market Road in Arochukwu LGA | Abia State | TOMEK GLOBAL SERVICE LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/047 | 248500000
47 | June, 2014 | Award of Contract for the Construction of Mini Ndai Street, Opp. College of Education, Port Harcourt LGA | Rivers State | PAMEKSON GLOBAL SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/048 | 249908370
48 | June, 2014 | Award of Contract for the Construction /Rehabilitation of Chukwu Street, Benind Elekahia Police Station, Port Harcourt LGA | Rivers State | FRANEZ NIGERIA LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/049 | 245000000
49 | June, 2014 | Award of Contract for the Construction of Nwagbogwu road and environs (Phase 1) in Ogba/Egbema/Ndoni LGA | Rivers State | RANC CONSTR. CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/050 | 245000000
50 | June, 2014 | Award of Contract for the Construction of Nwagbogwu road and environs (Phase II) in Ogba/Egbema/Ndoni LGA | Rivers State | SIMOKA MARINE LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/051 | 245000000
51 | June, 2014 | Award of Contract for the Construction of G-Rngineering Road, Off Imiringi road in Yenagoa LGA | Bayelsa State | FRACTAL CONST. NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/052 | 248027934.15
52 | June, 2014 | Award of Contract for the Construction of Ewang Internal Road (Phase II), Mbo Local Govt. Area | Akwa Ibom State | LOGISTICS RESOURCES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/053 | 198301776.28
53 | June, 2014 | Award of Contract for the Construction of Multi-purpose Civic Centre in Okwelle, Onuimi | Imo State | NOBLE FACTORS ASSOCIATES CO. LTD. |  | Civic centre | 12 months | NDDC/EDP/UIDW/PR/IM/14/054 | 170000000
54 | June, 2014 | Award of Contract for the Construction of Mini Rumudara link road, Off East West road, Port Harcourt | Rivers State | CEFAROL GLOBAL INVESTMENT LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/055 | 200000000
55 | June, 2014 | Award of Contract for the Construction of Antarex Road, Off Okoribi Road, Effurun in Uvwie LGA | Delta State | PEF DIVINE CONCEPT LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/056 | 199499806.25
56 | June, 2014 | Award of Contract for the Construction of Internal road network at NIIT Extension, Yenagoa, | Bayelsa State | GAPLINKS ENERGY LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/057 | 249000000
57 | June, 2014 | Award of Contract for the Construction of Odabar Concrete pavment at Ezeibiri Town in Bomadi LGA | Delta State | FELLYBEN GLOBAL SERVICE |  | Concrete Pavement | 12 months | NDDC/EDP/UIDW/PR/RV/14/058 | 199313378.75
58 | June, 2014 | Award of Contract for the Construction of Rigid Pavement Internal Road at Ogodobiri, Bomadi LGA | Delta State | GREENER PROJECT CENTRE LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/059 | 199977186.75
59 | June, 2014 | Award of Contract for the Construction of Egberu Kokoma Road, Tai LGA | Rivers State | EUSCO SPLENDORS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/060 | 248950450
60 | June, 2014 | Award of Contract for the Maintenance of Waterways at Oil Mill/Oginigba Channel Creek (3.5km), Port Harcourt | Rivers State | MMX NIGERIA LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/061 | 246462500
61 | June, 2014 | Award of Contract for the Maintenance of Waterways at Esisi Creek (3.5km), Warri (section B) | Delta State | ARCHETYPE INT'L LTD. |  | Maintenance | 12 months | NDDC/EDP/UIDW/PR/DT/14/062 | 246962500
62 | June, 2014 | Award of Contract for the Maintenance of Waterways at Oil Mill/Oginigba Channel Creek (3.5km), Port Harcourt (Section B) | Rivers State | TRITECH-GLOBAL CONCEPT LTD. |  | Maintenance | 12 months | NDDC/EDP/UIDW/PR/RV/14/063 | 246462500
63 | June, 2014 | Award of Contract for the Maintenance of Waterways at Esisi Creek (3.5km), Warri (section A) | Delta State | SYNTEK BUSINESS SERVICES LTD. |  | Maintenance | 12 months | NDDC/EDP/UIDW/PR/DT/14/064 | 246962500
64 | June, 2014 | Award of Contract for the Provision of Electricity facilities at NDDC Acquisition Centre, Patani LGA | Delta State | S.P.I. NIGERIA ENT. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/065 | 15808663.2
65 | July, 2014 | Award of Contract for the Construction of New Layout Internal Roads, Phase 1, Okolomade in Abua/Odual LGA | Rivers State | HIGHSPEC CONST. CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/066 | 238371350
66 | July, 2014 | Award of Contract for the Construction of New Layout Internal Roads, Phase II, Emelego in Abua/Odual LGA | Rivers State | COMBINATIONS ENTERPRISES |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/067 | 245305000
67 | July, 2014 | Award of Contract for the Construction of Omalem-Otari link Road with side drainage in Abua/Odual LGA | Rivers State | STEVENS CONST. GLOBAL CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/068 | 196415762.5
68 | July, 2014 | Award of Contract for the Construction of New Layout Internal Roads, Phase I, Emelego in Abua/Odual LGA | Rivers State | HIGHSPEC CONST. CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/069 | 247745503.5
69 | July, 2014 | Award of Contract for the Construction of Solar powered water project at Okolomade in Abua/Odual LGA | Rivers State | ARIGHT PROJECTS SOLUTION CO. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/070 | 181930260.2
70 | July, 2014 | Award of Contract for the Construction of New Layout Internal Roads, Phase II, Okolomade in Abua/Odual LGA | Rivers State | MID SEA GEOTECHNICAL SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/071 | 245151207.5
71 | July, 2014 | Award of Contract for the Construction of Concrete pavement at Adobu, Patani Road LGA | Delta State | ASIGO CO. NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/072 | 240000000
72 | July, 2014 | Award of Contract for the Construction of Multi-purpose civic centre at Ogriagene, Bomadi LGA | Delta State | FIRST OCEANIC GLOBAL RESOURCES LTD |  | Civic centre | 12 months | NDDC/EDP/UIDW/PR/DT/14/073 | 200000000
73 | July, 2014 | Award of Contract for the Construction of 2 no. six classroom/administrative block and 2 no staff quarters at Onurun Primary School, Ogriagbene, Bomadi LGA | Delta State | SPARK SOLAR LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/074 | 249000000
74 | July, 2014 | Award of Contract for the Construction of Ogaba/Irighi Street, Erera quarters, Emevon, Isoko North LGA | Delta State | CEJONOMI INTEGRATED SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/075 | 240000000
75 | July, 2014 | Award of Contract for the Construction of Rigid pavement, health centre primary school link road, Kpakiama, Bomadi LGA | Delta State | JOUPI NIGERIA LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/077 | 248000000
76 | July, 2014 | Award of Contract for the Construction of Owina Street/Efomo Lane, Off First East Circular Road, Oredo LGA | Edo State | BOLOUPESIBO & SONS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/078 | 249650000
77 | July, 2014 | Award of Contract for the Construction of Udoboh Road, Off Refinery Road, Effurun, Uvwie LGA | Delta State | KOMIXCO NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/079 | 104000000
78 | July, 2014 | Award of Contract for the Construction of Rigid pavement at Koluama II Community | Bayelsa State | ROCANI VENTURES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/080 | 212830500
79 | July, 2014 | Award of Contract for the Construction of Njuru Akpakpan Okerewa Pipeline Road in Obio Akpor LGA | Rivers State | T. K. ENGINEERING CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/081 | 248453460
80 | July, 2014 | Award of Contract for the Construction of Omuwhuechie New Layout Internal Road Network, Phase I, Ikwerre LGA | Rivers State | CHESA LIMITED |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/082 | 229585640
81 | July, 2014 | Award of Contract for the Construction of Olukwu-Rumuowha Road, Eneka, Obio Akpor LGA | Rivers State | N.P.G. NIGERIA LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/083 | 200000000
82 | July, 2014 | Award of Contract for the Construction of New Layout Rigid Pavement Road at Ihuechi Town in Ikwerre LGA | Rivers State | DOLBAN TECHNICAL NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/084 | 244800000
83 | July, 2014 | Award of Contract for the Renovation of 4 blocks of 40 flats at 2nd Bridgade Nigerian Army, Bori Camp Barracks (Lot 4) | Rivers State | VIGOR MULTITUDE AGENCIES LTD. |  | Renovation | 12 months | NDDC/EDP/UIDW/PR/RV/14/085 | 249875220
84 | July, 2014 | Award of Contract for the Renovation of 4 blocks of 40 flats at 2nd Bridgade Nigerian Army, Bori Camp Barracks (Lot 3) | Rivers State | COUNTY-LOCK SERVICES LTD. |  | Renovation | 12 months | NDDC/EDP/UIDW/PR/RV/14/086 | 249875220
85 | July, 2014 | Award of Contract for the Renovation of 4 blocks of 40 flats at 2nd Bridgade Nigerian Army, Bori Camp Barracks (Lot 1) | Rivers State | INSPIRA SYNERGY LIMITED |  | Renovation | 12 months | NDDC/EDP/UIDW/PR/RV/14/087 | 249875220
86 | July, 2014 | Award of Contract for the Renovation of 4 blocks of 40 flats at 2nd Bridgade Nigerian Army, Bori Camp Barracks (Lot 2) | Rivers State | ART GRANHAM CONCEPTS LTD. |  | Renovation | 12 months | NDDC/EDP/UIDW/PR/RV/14/088 | 249875220
87 | July, 2014 | Award of Contract for the Supply of Educational Materials/ Infrastructural Upgrade at Adane Primary School (Lot 4) | Delta State | SHARP GLOBAL VENTURES SERVICES LTD. |  | Supply of Eduational Materials | 12 months | NDDC/EDP/UIDW/PR/DT/14/089 | 249900000
88 | July, 2014 | Award of Contract for the Supply of Educational Materials/ Infrastructural Upgrade at State School, Agesi Central, Abua/Odual LGA | Rivers State | WESTON CHIVAS EMPORIUM LTD. |  | Supply of Eduational Materials | 12 months | NDDC/EDP/UIDW/PR/RV/14/090 | 249900000
89 | July, 2014 | Award of Contract for the Supply of Educational Materials/ Infrastructural Upgrade at Salvation Army Secondary School, Eket LGA | Akwa Ibom State | PANTEJ GLOBAL SERVICES LTD. |  | Supply of Eduational Materials | 12 months | NDDC/EDP/UIDW/PR/AKS/14/091 | 249900000
90 | July, 2014 | Award of Contract for the Supply of Educational Materials/ Infrastructural Upgrade at Niger Delta Schools | Rivers State | ROM-FLEX LIMITED |  | Supply of Eduational Materials | 12 months | NDDC/EDP/UIDW/PR/RG/14/092 | 249900000
91 | July, 2014 | Award of Contract for the Supply of Educational Materials/ Infrastructural Upgrade at Salvation Army Secondary School, Eket LGA | Cross River State | ASILADRREN ENGINEERING LTD. |  | Supply of Eduational Materials | 12 months | NDDC/EDP/UIDW/PR/RG/14/093 | 249900000
92 | July, 2014 | Award of Contract for the Supply of Educational Materials/ Infrastructural Upgrade at St. Theresa's Primary School, Odukpani Town, Odukpani LGA | Cross River State | APLAMATUSE VENTURES |  | Supply of Eduational Materials | 12 months | NDDC/EDP/UIDW/PR/CRS/14/094 | 249900000
93 | July, 2014 | Award of Contract for the Supply of Educational Materials/ Infrastructural Upgrade at Adane Primary School, Orerokpe, Okpe LGA (Lot 3) | Delta State | WEBSTER GLOBAL VENTURES LTD. |  | Supply of Eduational Materials | 12 months | NDDC/EDP/UIDW/PR/DT/14/095 | 249900000
94 | July, 2014 | Award of Contract for the Supply of Educational Materials/ Infrastructural Upgrade at Community Primary School, Toru Orua, Sagbama LGA | Bayelsa State | AMU GLOBAL VENTURES LTD. |  | Supply of Eduational Materials | 12 months | NDDC/EDP/UIDW/PR/DT/14/096 | 249900000
95 | July, 2014 | Award of Contract for the Construction of Ewhen Unenurhie Bridge, Ewhen, Isoko South LGA | Delta State | ERE STEAMS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/097 | 150000000
96 | July, 2014 | Award of Contract for the Solar Light at Ozoro Polytechnics, Ozoro, Isoko North LGA | Delta State | RACEN INTEGRATED GLOBAL LTD. |  | Solar Light | 12 months | NDDC/EDP/UIDW/PR/DT/14/098 | 200000000
97 | July, 2014 | Award of Contract for the Solar Light at Faculty of Law, Delta State University, Oleh Campus, Isoko South LGA | Delta State | LAURELTON GLOBAL RESOURCES LTD. |  | Solar Light | 12 months | NDDC/EDP/UIDW/PR/DT/14/099 | 200000000
98 | July, 2014 | Award of Contract for the Construction of 1.4Km Shalom City Road with spur, Ozoro, Isoko South LGA | Delta State | KAROKOME INT'L GLOBAL RESOURCES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/100 | 150000000
99 | July, 2014 | Award of Contract for the Construction of 1.2Km Okpe-Isoko Ovie Palace Road, Isoko South LGA | Delta State | ZEDDY GLOBAL INT'L LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/101 | 150000000
100 | July, 2014 | Award of Contract for the Construction of 2Km Omodu Street, Emede, Isoko South LGA | Delta State | FERGIO VENTURES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/102 | 200000000
101 | July, 2014 | Award of Contract for the Construction of Water project at Ohenerurie Iyede, Isoko South LGA | Delta State | LESODA OIL & GAS CO. LTD. |  | Water | 12 months | NDDC/EDP/UIDW/PR/DT/14/103 | 45000000
102 | July, 2014 | Award of Contract for the Construction of Uzere Water Scheme, Isoko South LGA | Delta State | K. K.I INTERLINKS SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/104 | 45000000
103 | July, 2014 | Award of Contract for the Construction of Ekisa-Ama Road, Amasoma in Sagbama LGA | Bayelsa State | NOBLE CAPITAL NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/105 | 150000000
104 | July, 2014 | Award of Contract for the Construction of Rigid pavement at Road 13, Ohia Odane, Rumuokwuta in Obio Akpor LGA | Rivers State | TEESET NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/106 | 246000000
105 | July, 2014 | Award of Contract for the Construction of Umuoma/Imogu link road, Phase 1, Ikwerre LGA | Rivers State | FIPHS INFRASTRUCTURE LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/107 | 200000000
106 | July, 2014 | Award of Contract for the Canalisation of 1km DDPA Canal (Lot 2), Uvwie LGA | Delta State | PREZACOM ENGINEERING LTD. |  | Canalisation | 12 months | NDDC/EDP/UIDW/PR/DT/14/108 | 234509189.5
107 | July, 2014 | Award of Contract for the Canalisation of 1km DDPA Canal (Lot 3), Uvwie LGA | Delta State | ENVIROCARE RESOURCES CENTRE LTD. |  | Canalisation | 12 months | NDDC/EDP/UIDW/PR/DT/14/109 | 234509189.5
108 | July, 2014 | Award of Contract for the Canalisation of 1km DDPA Canal (Lot 4), Uvwie LGA | Delta State | VINE PROFESSIONAL PROJECTS LTD. |  | Canalisation | 12 months | NDDC/EDP/UIDW/PR/DT/14/110 | 234509189.5
109 | July, 2014 | Award of Contract for the Canalisation of 1km DDPA Canal (Lot 1), Burutu LGA | Delta State | INTEGRO CONST. NIG. LTD. |  | Canalisation | 12 months | NDDC/EDP/UIDW/PR/DT/14/111 | 215708125
110 | July, 2014 | Award of Contract for the Canalisation of Creek at Toru Ojobo (Lot 2), Burutu LGA | Delta State | JY CONST. CO. NIG. LTD. |  | Canalisation | 12 months | NDDC/EDP/UIDW/PR/DT/14/112 | 241958125
111 | July, 2014 | Award of Contract for the Canalisation of Creek at Toru Ojobo (Lot 3), Burutu LGA | Delta State | GMG GLOBAL CONST. & DEV. NIG. LTD. |  | Canalisation | 12 months | NDDC/EDP/UIDW/PR/DT/14/113 | 240958125
112 | July, 2014 | Award of Contract for the Canalisation of Creek at Toru Ojobo (Lot 4), Burutu LGA | Delta State | WESTON CHIVAS EMPORIUM LTD. |  | Canalisation | 12 months | NDDC/EDP/UIDW/PR/DT/14/114 | 234808125
113 | July, 2014 | Award of Contract for the Canalisation of 1km DDPA Canal (Lot 1), Uvwie LGA | Delta State | JOLLY ENERGY FLEET LTD. |  | Canalisation | 12 months | NDDC/EDP/UIDW/PR/DT/14/115 | 234509189.5
114 | July, 2014 | Award of Contract for the Construction of Office Extension and Renovation of existing offices at Police Headquarters, Moscow Road, Port Harcourt | Rivers State | TECHNICS DE STOCKADE INC. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/116 | 150221464.95
115 | July, 2014 | Award of Contract for the Furnishing of the Hostel (1 No) at Federal College of Education (Technical), Omoku in Onelga LGA | Rivers State | MBONNY TECHNICAL SERVICES LTD. |  | Furnishing | 3 months | NDDC/EDP/UIDW/PR/RV/14/117 | 28345642.5
116 | July, 2014 | Award of Contract for the Construction of Internal Road, Uvwie Road leading to Ufuoma Fish Farm in Uvwie LGA | Delta State | ANI CORPORATE INT'L LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/118 | 249591213
117 | July, 2014 | Award of Contract for the Construction of Access Rad and Landing Jetty at Henshaw Town Beach in Calabar Central | Cross River State | ZENITH CONST. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/CR/14/119 | 200000000
118 | July, 2014 | Award of Contract for the Construction of Obio Edik Community Road in Bakassi LGA | Cross River State | ZENITH CONST. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/CR/14/120 | 200000000
119 | July, 2014 | Award of Contract for the Furnishing of NDDC Hostel at Federal University of Technology, Owerri | Imo State | MEIN NIGERIA LIMITED |  | Furnishing | 3 months | NDDC/EDP/UIDW/PR/IM/14/121 | 89812800
120 | July, 2014 | Award of Contract for the Erosion Remediation and Construction of Daniel Henshaw Street in Calabar South LGA | Cross River State | AMPLE DIMENSION LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/CRS/14/122 | 242694194.67
121 | July, 2014 | Award of Contract for the Construction of Ohore 1 Road, Okpe LGA | Delta State | GMG GLOBAL CONST. & DEV. NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/123 | 200000000
122 | August, 2014 | Award of Contract for the Construction of Ikot Ubok Udom-Ikot Abasi Road, Ikot Ubok in Nsit Atai LGA | Akwa Ibom State | A & J CONST. CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/124 | 244007024
123 | August, 2014 | Award of Contract for the Construction of Internal Roads at Koroma Tai LGA | Rivers State | ORBITAL RESOURCES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/125 | 249350680
124 | August, 2015 | Award of Contract for the Installation of 2 No, 500KVA, 33/0.415KV Transformer at Niger Delta Ministry | Ondo State | RECYCLED POWERED & ENERGY NIG. LTD. |  | Transformer | 3 months | NDDC/EDP/UIDW/PR/ON/14/126 | 9000000
125 | August, 2014 | Award of Contract for the Construction of Izombe-Agwa - Obokofia Road | Imo State | NIGER DELTA PROJECTS CONSORTIUM LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/127 | 795964238.19
126 | August, 2014 | Award of Contract for the Construction of C.R.A. Road, Odikirike, Elelenwo, Obio Akpor LGA | Rivers State | PABROE SYNERGY LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/128 | 250000000
127 | August, 2014 | Award of Contract for the Construction of Internal Road with Drains at Omuchiolu-Omuokiri, Omuchiolu in Ikwerre LGA | Rivers State | OX-MAT RESOURCES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/129 | 228060000
128 | August, 2014 | Award of Contract for the Construction of NDDC Prototype University Hostel block at Edwin Clark's University, Kiagbodo LGA | Delta State | NYEMARO NIGERIA LTD. |  | Prototype University | 12 months | NDDC/EDP/UIDW/PR/DT/14/130 | 750608754.81
129 | August, 2014 | Award of Contract for the Construction of Iko-Atabrikang-Akata-Opolom-Ikot Enwang-Okoroutip-Iwuochang Road with 100m (5 No. Spans x 20m) Bridge (Phase 3) | Akwa Ibom State | RAPID PACK LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/131 | 717292906
130 | August, 2014 | Award of Contract for the Construction of Iko-Atabrikang-Akata-Opolom-Ikot Enwang-Okoroutip-Iwuochang Road (5Km Pavement and Surfacing) (Phase 4) | Akwa Ibom State | TOROMIK NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/132 | 876727500
131 | August, 2014 | Award of Contract for the Construction of Iko-Atabrikang-Akata-Opolom-Ikot Enwang-Okoroutip-Iwuochang Road (2.5Km) (Phase 5) | Akwa Ibom State | ROCANI VENTURES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/133 | 905932500
132 | August, 2014 | Award of Contract for the Construction of Iko-Atabrikang-Akata-Opolom-Ikot Enwang-Okoroutip-Iwuochang Road (Culverts/Drains and Dredging) (Phase 6) | Akwa Ibom State | BOLIV LIMITED |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/134 | 943036380
133 | August, 2014 | Award of Contract for the Construction of Iko-Atabrikang-Akata-Opolom-Ikot Enwang-Okoroutip-Iwuochang Road (2.5Km) (Phase 7) | Akwa Ibom State | CHESA LIMITED |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/135 | 857257500
134 | August, 2014 | Award of Contract for the Construction of Iko-Atabrikang-Akata-Opolom-Ikot Enwang-Okoroutip-Iwuochang Road (Dredging of Sand for Road Filling) (Phase 8) | Akwa Ibom State | T. K. ENGINEERING CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/136 | 879395000
135 | August, 2014 | Award of Contract for the Construction of Iko-Atabrikang-Akata-Opolom-Ikot Enwang-Okoroutip-Iwuochang Road (Dredging of Sand for Road Filling) (Phase 9) | Akwa Ibom State | VICHE RESOURCES NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/137 | 870595000
128 | August, 2014 | Award of Contract for the Construction of Civic Centre for Displaced People at Oko-Odifulu, Oshimili LGA | Delta State | AK LESO VENTURES NIG. LTD. |  | Civic centre | 12 months | NDDC/EDP/UIDW/PR/DT/14/138 | 179530284.62
129 | August, 2014 | Award of Contract for the Construction of Internal Road Network at Sagbama in Sagbama LGA | Bayelsa State | PETOYIN DZYNS/ CONST. CONSULTANCY LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/139 | 249500000
130 | August, 2014 | Award of Contract for the Construction of Rigid Pavement at Road 18, Ohia Oda, Rumuokwuta in Obio Akpor LGA | Rivers State | LINGARY GLOBAL CONCEPT LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/140 | 248500000
131 | August, 2014 | Award of Contract for the Construction of Akengbuda Youth Road, Amagba Community, Oredo LGA | Edo State | SUPPLY & TRANSPORT INTEGRATED SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/141 | 219906394.25
132 | August, 2014 | Award of Contract for the Landscaping and Furnishing of NDDC Seconday School, Alalama in Asari Toru LGA | Rivers State | EIGMA INTEGRAL LOGISTICS & SOLUTION LTD. |  | Landscaping & Furnishing | 12 months | NDDC/EDP/UIDW/PR/RV/14/142 | 118138625
133 | August, 2014 | Award of Contract for the Supply of Speed Boats and Fibre in Port Harcourt | Rivers State | SKY PRO LIMITED |  | Speed Boats & Fibre | 12 months | NDDC/EDP/UIDW/PR/RV/14/143 | 979853587.5
133 | August, 2014 | Award of Contract for the Clearing of Waterways (Lot 1) in Ilaje LGA | Ondo State | CMCO NIG. LTD. |  | Clearing of Waterways | 12 months | NDDC/EDP/UIDW/PR/ON/14/144 | 200000000
134 | August, 2014 | Award of Contract for the Clearing of Waterways (Lot 2) in Ilaje LGA | Ondo State | MOPHYX SERVICE LTD. |  | Clearing of Waterways | 12 months | NDDC/EDP/UIDW/PR/ON/14/145 | 200000000
135 | August, 2014 | Award of Contract for the Clearing of Waterways (Lot 3) in Ilaje LGA | Ondo State | SYNTEK BUSINESS SERVICES LTD. |  | Clearing of Waterways | 12 months | NDDC/EDP/UIDW/PR/ON/14/146 | 200000000
136 | August, 2014 | Award of Contract for the Clearing of Waterways (Lot 4) in Ilaje LGA | Ondo State | KATES RESOURCES NIG. LTD. |  | Clearing of Waterways | 12 months | NDDC/EDP/UIDW/PR/ON/14/147 | 200000000
137 | August, 2014 | Award of Contract for the Clearing of Waterways (Lot 1) in Ese Odo LGA | Ondo State | GREATLIFE TELECOMS LTD. |  | Clearing of Waterways | 12 months | NDDC/EDP/UIDW/PR/ON/14/148 | 150000000
138 | August, 2014 | Award of Contract for the Clearing of Waterways (Lot 2) in Ese Odo LGA | Ondo State | GLITERING COMPUTER LTD. |  | Clearing of Waterways | 12 months | NDDC/EDP/UIDW/PR/ON/14/149 | 150000000
139 | August, 2014 | Award of Contract for the Installation of 3 nos. 500kva, 11/0.415KV Transformer at Rumunduru-Elioani Community, Chibuzor Close, Rumuibekwe and Ejezuba Street, Woji | Rivers State | K. K. KOBINA ENT. LTD. |  | Transformer | 12 months | NDDC/EDP/UIDW/PR/RV/14/150 | 13500000
140 | August, 2014 | Award of Contract for the Installation of 1 No. 500KVA, 11/0.415KV Transformer at Agip Estate Landlord Association | Rivers State | K. K. KOBINA ENT. LTD. |  | transformer | 12 months | NDDC/EDP/UIDW/PR/RV/14/151 | 4500000
141 | August, 2014 | Award of Contract for the Canalization of Siloko-Taribor Creek (Phase 1) in Odigbo LGA | Ondo State | K.F.T. UDUBOH NIG. LTD. |  | Canalisation | 12 months | NDDC/EDP/UIDW/PR/ON/14/152 | 933988000
141 | September, 2014 | Award of Contract for the Construction of Water Front Toilet blocks (Phase 2) at Abalama, Asari Toru LGA | Rivers State | FORDETOP SERVICES |  | Const. of Water Front Toilet | 12 months | NDDC/EDP/UIDW/PR/RV/14/153 | 195780772.5
142 | September, 2014 | Award of Contract for the Construction of Internal Roads (Lot 3) in Abua Central, Abua/Odual LGA | Rivers State | ACTSON INTEGRATED NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/154 | 168100025
143 | September, 2014 | Award of Contract for the Construction of Internal Roads (Lot 1) in Abua Central, Abua/Odual LGA | Rivers State | COASTAL RANGE PROJECTS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/155 | 208115325
144 | September, 2014 | Award of Contract for the Construction of Internal Roads (Lot 2) in Abua Central, Abua/Odual LGA | Rivers State | GREYPHANTOM LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/156 | 213404945
145 | September, 2014 | Award of Contract for the Construction of Oporoma/Tema/Sama/Ifoko/ Ilelema/Okpo/Abalama, Phase 1, Abalama Town, Asari Toru LGA | Rivers State | HIGHSPEC CONST. CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/157 | 233572600
146 | September, 2014 | Award of Contract for the Solar Powered Water Project at Oporoama, Asari Toru LGA | Rivers State | PHEODOR GLOBAL PROSPECTS COY. |  | Water | 12 months | NDDC/EDP/UIDW/PR/RV/14/158 | 179528523.3
147 | September, 2014 | Award of Contract for the Construction of Abalama Internal Road, Abalama (Rigid Pavement and Drains) in Asari Toru LGA | Rivers State | WILLINDA BUSINESS RESOURCES |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/159 | 213716455
148 | September, 2014 | Award of Contract for the Construction of Umutu/Akaoku Road in Ukwuani LGA | Delta State | RENNOVATE COMPANY |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/160 | 195268287.5
149 | September, 2014 | Award of Contract for the Extension of High Tension (HT) Line to NDDC Hostel, Futo and Installation of 500KVA, 11/0.415KV Transformer at Owerri | Imo State | GEOGIC GLOBAL SERVICES COY. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/161 | 8921323.16
150 | September, 2014 | Award of Contract for the Construction of Rigid Pavement Internal Road in Ido, Asari Toru LGA | Rivers State | MILESTONES GENERAL OPTIONS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/162 | 200000000
151 | September, 2014 | Award of Contract for the Construction of Umuchetu Imogu Linik Road (Phase 1) in Ikwerre LGA | Rivers State | KUFECK KUTECK SECURITY VENTURES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/163 | 200000000
152 | September, 2014 | Award of Contract for the Construction of Akpovoka Afisere Otuma Kokori Road, Ethiope East LGA | Delta State | GMG GLOBAL CONST. & DEV. CO. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/164 | 249000000
153 | September, 2014 | Award of Contract for the Rennovation of 2 No. Staff quarters of 3 bedroom each at Williams Memorial Secondary Schoo, Afugiri Umuahia | Abia State | TYARC DESIGNS |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/165 | 98601500
154 | September, 2014 | Award of Contract for the Provision of Water facilities and Access Road at Federal College of Education (Technical) at Omoku in Ogba/Egbema/Ndoni LGA | Rivers State | MANPOWER & MARINE MANAGEMENT SERVICES LTD. |  | Water | 12 months | NDDC/EDP/UIDW/PR/RV/14/166 | 45889620
155 | September, 2014 | Award of Contract for the Construction of Suzzy Agwere Road, Agwere, Ethiope East LGA | Delta State | ARC MARINE & CIVIL CONTRACTORS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/167 | 230573280
156 | September, 2014 | Award of Contract for the Construction of Atighwor Road from Agada's Compound to Old Market Road, Jesse, Ethiope West LGA | Delta State | ARC MARINE & CIVIL CONTRACTORS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/168 | 150000000
157 | September, 2014 | Award of Contract for the Installation of 3 nos, 300KVA, 33/0.415KV Transformer at Kofawe Quarters, Agbala Premier Quarters and Agbala, Igbokoda | Ondo State | RECYCLED POWERED & ENERGY NIG. LTD. |  | Transformer | 12 months | NDDC/EDP/UIDW/PR/RV/14/169 | 13500000
158 | September, 2014 | Award of Contract for the Construction of 2km link Road at Opolo, Yenagoa | Bayelsa State | FAK ENGINEERING & CONSTRUCTION |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/170 | 490000000
158 | September, 2014 | Award of Contract for the Construction of 1km Ukwu Ugiri Umunakanu-Umuopara-Umuezegwo Road, Ehime Mbano LGA | Imo State | MORTAIN NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/171 | 118727122.5
159 | September, 2014 | Award of Contract for the Construction of Concrete pavement, Road at Akenfa 1 Extension, Yenagoa LGA | Bayelsa State | KENCHEZ NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/172 | 245000000
160 | September, 2014 | Award of Contract for the Construction of Foreshore Wall/Concrete Jetty in Burutu LGA | Delta State | ASHI-RICH NIG. ENT. LTD. |  | Jetty | 12 months | NDDC/EDP/UIDW/PR/DT/14/173 | 199116047.5
161 | September, 2014 | Award of Contract for the Construction of Twins Street/Asuquo Ekpo Street/Asuquo Nyong Street, Calabar | Cross River State | FIRST NEW ERA CONSTRUCTION |  | Road | 12 months | NDDC/EDP/UIDW/PR/CR/14/174 | 230000000
162 | September, 2014 | Award of Contract for the Construction of Plot 151 Ntibi Close, Asari Eso Layout and Spur judges Totman Etoty Streety, Iwara Street, Atsu Street, Calabar | Cross River State | KAMBYKE OIL & GAS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/CR/14/175 | 248950500
163 | September, 2014 | Award of Contract for the Completion of Dinning Hall and Kitchen at Federal Girls College, Umuahia | Abia State | MAROKES PROCUREMENT & LOGISTICS LTD. |  | Completion | 12 months | NDDC/EDP/UIDW/PR/DT/14/176 | 99975174.5
164 | September, 2014 | Award of Contract for the Construction of Ayeabam-Awi Road in Akamkpa LGA | Cross River State | BAYOU LA BATRE LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/CR/14/177 | 248435000
165 | September, 2014 | Award of Contract for the Emergency Repair/ Maintenance of Ikot Akan to Ibekwe Akpan Nya road (Ikot Abasi/Abak Road) in Ikot Abasi/ Mkpat Enin LGA | Akwa Ibom State | BASSE ENGINEERING & MICHEL LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/178 | 571169585.7
165 | September, 2014 | Award of Contract for the Construction of Omadino-Okpoti-Aghiho Road, Tebu-Ugbokoa-Jakpa (Lot 1) | Delta State | JAY CONSULT LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/179 | 249080750
166 | September, 2014 | Award of Contract for the Construction of Omadino-Okpoti-Aghiho Road, Tebu-Ugbokoa-Jakpa (Lot 2) | Delta State | PAACHE CONSTRUCTION LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/180 | 248080750
167 | September, 2014 | Award of Contract for the Construction of Omadino-Okpoti-Aghiho Road, Tebu-Ugbokoa-Jakpa (Lot 3) | Delta State | WALAND SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/181 | 245679840
168 | September, 2014 | Award of Contract for the Construction of Omadino-Okpoti-Aghiho Road, Tebu-Ugbokoa-Jakpa (Lot 4) | Delta State | DEKRA INT'L SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/182 | 242980065
169 | September, 2014 | Award of Contract for the Construction of Omadino-Okpoti-Aghiho Road, Tebu-Ugbokoa-Jakpa (Lot 5) | Delta State | NEWGATE LOGISTICS |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/183 | 245980065
170 | September, 2014 | Award of Contract for the Construction of Omadino-Okpoti-Aghiho Road, Tebu-Ugbokoa-Jakpa (Lot 6) | Delta State | ISEC NIGERIA |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/184 | 248085650
171 | September, 2014 | Award of Contract for the Construction of 180m long Bridge at Adiabor-Eseku Bridge, Odukpani LGA | Cross River State | JOHN DAVIDS CONSTRUCTION LTD. |  | Bridge | 12 months | NDDC/EDP/UIDW/PR/CR/14/185 | 996406610
171 | September, 2014 | Award of Contract for the Construction of Concrete Internal Road for Futorugbene in Ekeremor LGA | Bayelsa State | ZEROCK CONSTRUCTION NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/186 | 242146921.25
172 | September, 2014 | Award of Contract for the Construction of Boys Quarters and Renovation of Commissioner of Police Official Quarters, Port Harcourt | Rivers State | KENSTHER GLOBAL SERVICES LTD. |  | Renovation | 12 months | NDDC/EDP/UIDW/PR/RV/14/187 | 33920000
173 | September, 2014 | Award of Contract for the Construction of 1.8km Road/Drainage at Police Housing Estate in Oyigbo LGA | Rivers State | BASH & BOLTS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/188 | 240000000
174 | September, 2014 | Award of Contract for the Construction of Calabar Quarters Road in Oyigbo LGA | Rivers State | CANYON-GATE NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/189 | 200000000
175 | October, 2014 | Award of Contract for the Construction of Aba Eto Road, Odiono/Isutbe, Ikot Abasi LGA | Akwa Ibom State | TOVAN INVESTMENTS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/190 | 249685760
176 | October, 2014 | Award of Contract for the Construction of Concrete Pavement at Okoloba Town, Bomadi LGA | Delta State | DASERZ CONSTRUCTION LTD. |  | Concrete Pavement | 12 months | NDDC/EDP/UIDW/PR/DT/14/191 | 240000000
177 | October, 2014 | Award of Contract for the Construction of Concrete Pavement at Catholic Church Road, Okotukutu, Off Tamic-Okitukutu, Yenagoa LGA | Bayelsa State | NEW WAY NIG. LTD. |  | Concrete Pavement | 12 months | NDDC/EDP/UIDW/PR/BY/14/192 | 240000000
178 | October, 2014 | Award of Contract for the Construction of Concrete Pavement at Toru-Apele-Biri Town, Patani LGA | Delta State | SCASPLANT NIG. LTD. |  | Concrete Pavement | 12 months | NDDC/EDP/UIDW/PR/DT/14/193 | 235000000
179 | October, 2014 | Award of Contract for the Construction of Bridge across Amaku Oba & Approach Slab at existing bridge to Ogriagbene, Bomadi LGA | Delta State | ELOHIM HF NIG. LTD. |  | Bridge | 12 months | NDDC/EDP/UIDW/PR/DT/14/194 | 249500000
180 | October, 2014 | Award of Contract for the Construction of Udung-Eyo Internal Roads, Uyenge, Mbo LGA | Akwa Ibom State | ENTINELS NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/195 | 223494488.75
181 | October, 2014 | Award of Contract for the Rehabilitation of Orerokpe Internal Roads in Okpe LGA | Delta State | QUALITY SYNERGY INVESTMENT SERVICES NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/196 | 241563924
182 | October, 2014 | Award of Contract for the Tarring of Nwaonye Street, Issele-Uku in Aniochia North LGA | Delta State | INGOWET SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/197 | 228786120
183 | October, 2014 | Award of Contract for the Construction of Egborode Waterside Road with spur to Egborode Health Centre in Ethiope LGA | Delta State | MID SEA GEOTECHNICAL SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/198 | 199715640
184 | October, 2014 | Award of Contract for the Construction of 2Km Nkwo-Egbu Umuezeala Road with Drainage in Egbuoma Community, Oguta LGA | Imo State | FRANK & GENE INT'L LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/199 | 248191125
185 | October, 2014 | Award of Contract for the Construction of Udung Ukpong Town Hall Road, Okobo LGA | Akwa Ibom State | ROYAL VIEW SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/200 | 100000000
186 | October, 2014 | Award of Contract for the Construction of Access Road to NDDC Community Centre with two side drains at Amamong, Okobo LGA | Akwa Ibom State | GREAT HOUSE INVESTMENTS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/201 | 238000000
187 | October, 2014 | Award of Contract for the Construction of Access Road to Okobo General Hospital, Amamong with two side drains at Amamong, Okobo LGA | Akwa Ibom State | GREAT HOUSE INVESTMENTS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/202 | 249500000
188 | October, 2014 | Award of Contract for the Supply of Furniture/Equipment, Library fittings and Generator House at NDDC skill acquisition Centre in Amamong, Okobo LGA | Akwa Ibom State | LIZ CAPITAL NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/203 | 70000000
189 | October, 2014 | Award of Contract for the Provision of ICT/Computers and Installation of two (2) nos 100KVA Gen Set at NDDC skills acquisition centre in Amamong, Okobo LGA | Akwa Ibom State | PENTAGON ENERGY LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/204 | 70000000
190 | October, 2014 | Award of Contract for the Construction of Enemodia Onoyake Street, Ugborikoko Road, Phase 2, Effurun LGA | Delta State | S.O. OLOTU & SONS NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/205 | 87154735.5
191 | October, 2014 | Award of Contract for the Construction of Ikot Uboh 1.3KM Road in Nsit Atai LGA | Akwa Ibom State | FINTRAD LIMITED |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/206 | 231000000
192 | July, 2014 | Award of Contract for the Construction of Concrete Pavement at Odimodi Township Road, Phase 1, Burutu LGA | Delta State | ASIGO CO. NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/207 | 249500000
193 | October, 2014 | Award of Contract for the Construction of Concrete Pavement at Torugbene, Phase 2, Burutu LGA | Delta State | SPARK SOLAR LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/208 | 249500000
194 | October, 2014 | Award of Contract for the Construction of Apodu/ Okorogbene Walkway (3km), Phase 1, Bomadi LGA | Delta State | FIRST OCEANIC GLOBAL RESOURCES LTD |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/209 | 249500000
195 | October, 2014 | Award of Contract for the Reconstruction / Maintenance of Mike Asaboro Street/ Freeborn Street, Ugborikoko DDPA, Uvwie LGA | Delta State | T.Y. TRINITY OIL FIELD SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/210 | 145000000
196 | October, 2014 | Award of Contract for the Sandfilling of NDDC Permanent site, Eastern Bye-pass, Port Harcourt LGA | Rivers State | CASDOR CONSTRUCTION LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/211 | 241618000
197 | October, 2014 | Award of Contract for the Construction of Izombe-Mgbele Oguta Road, Phase 2, Oguta LGA | Imo State | HEXA-DIS INDUSTRIAL SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/212 | 245930415
198 | October, 2014 | Award of Contract for the Construction of Edem Mbat Road, Ikot Akpan Ata Village, Ikot Abasi LGA | Akwa Ibom State | KGA INT'L SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/213 | 248000000
199 | October, 2014 | Award of Contract for the Construction of Ikot Ekpe Road in Mkpat Enin LGA | Akwa Ibom State | TPCC GENERAL CONSTRUCTION LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/214 | 249858886
200 | October, 2014 | Award of Contract for the Construction of Esuk-Atu/Imperial College Road, Satellite Town, Calabar LGA | Cross River State | LAND & SEA DYNAMIC INVESTMENTS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/CR/14/215 | 198050000
201 | October, 2014 | Award of Contract for the Furnishing of NDDC Hostel in the Federal University of Agriculture, Umudike LGA | Abia State | KENOCHIL SERVICES NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/216 | 89812800
202 | October, 2014 | Award of Contract for the Construction of Solar Powered Street Light at Okhuokhuo Isi Community in Umunmwode LGA | Edo State | MARTHYSYN INT'L LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/217 | 249000000
203 | October, 2014 | Award of Contract for the Construction of 1.2km road at Airongioba Street, Off Igun Street, Benin City LGA | Edo State | P.S. I. Int'l Coy. Ltd. |  | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/218 | 249905000
204 | October, 2014 | Award of Contract for the Construction of Agbakabingai Etiema (Nembe Link Road), Brass LGA | Bayelsa State | FRACTAL CONST. NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/219 | 249000000
205 | October, 2014 | Award of Contract for the Construction of Access Road to Stadium in Esit Eket, Eket LGA | Akwa Ibom State | E. T. DICKS NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/220 | 198500000
206 | October, 2014 | Award of Contract for the Construction of Access Road to Paramount Rulers Palace of Nsit Afai LGA | Akwa Ibom State | E. T. DICKS NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/221 | 200000000
207 | October, 2014 | Award of Contract for the Construction of Afi Iwaad Eket Road, Eket LGA | Akwa Ibom State | BEACONEX NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/222 | 240000000
208 | October, 2014 | Award of Contract for the Construction of Solar Powered Water project at Medu Quarters, Koko, Warri North LGA | Delta State | BIBEL SYNERGY LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/223 | 50000000
209 | October, 2014 | Award of Contract for the Construction of Concrete Pavement at Redeemed Glory Road, Agudama, Yenagoa LGA | Bayelsa State | OLBY SYNERGY NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/224 | 240000000
210 | October, 2014 | Award of Contract for the Construction of Agudama Road,Off Senator Oboro Road, Agudama Town, Yenagoa LGA | Bayelsa State | OLBY GLOBAL RESOURCES |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/225 | 230000000
211 | October, 2014 | Award of Contract for the Extension of 33KV Overhead line networks from Okirika to Furukuma community LGA | Delta State | KEVTRICS NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RG/14/226 | 903239253.4
212 | October, 2014 | Award of Contract for the Extension of 33KV Overhead line networks from Furukuma to Okoloba community LGA | Delta State | MODEV NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RG/14/227 | 914022502.66
213 | October, 2014 | Award of Contract for the Extension of 33KV Overhead line networks from Okoloba to Esanma community LGA | Delta State | INCOME ELECTRIX LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/228 | 907774340.68
214 | October, 2014 | Award of Contract for the Supply of special overhead line materials to Niger Delta Region to withstand harsh environment and Ultra Violet Sun Rays Fibre | Regional | KILOWATT ENGINEERING LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RG/14/229 | 950871520
215 | October, 2014 | Award of Contract for the Supply of Atomic slicing kits fibre, link insulator fibre cross-arms to Niger Delta region | Regional | SKYVIEW POWER TECHNOLOGIES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RG/14/230 | 950871520
216 | October, 2014 | Award of Contract for the Supply of Silicon Rubber Insulator with Hydrophobic properties to withstand heavy pollution index in the Niger Delta region | Regional | INCOME ELECTRIX LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RG/14/231 | 950871520
211 | October, 2014 | Award of Contract for the Maintenance of Road from Agip Gate to Eagle Island at Port Harcourt LGA | Rivers State | FEZINAT SERVICES COY. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/232 | 248307560
212 | October, 2014 | Award of Contract for the Installation of 3 nos 300KVA 33/ 0.415KV Transformers at Nkpolu, Oroworukwo Community, Port Harcourt LGA | Rivers State | ZUV CONST. COY. |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/RV/14/233 | 13500000
213 | October, 2014 | Award of Contract for the Construction of Royal Generation Avenue, Iriebe LGA | Rivers State | G & E ENGR. SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/234 | 222874419.85
214 | October, 2014 | Award of Contract for the Construction of Okirighwre-Amukpe/Shell Road, Sapele | Delta State | LEVANT CONST. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/235 | 976509228.75
214 | October, 2014 | Award of Contract for the Installation of 2 nos 500KVA, 33/0.415KV Transformer at Unity Estate, Rumukpor Autonomus Community, Obio Akpor LGA | Rivers State | TEELON LIMITED |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/RV/14/237 | 9000000
215 | October, 2014 | Award of Contract for the Construction of Umukuikor-Omumauzor-Ariaria Junction in Abia State | Abia State | BURNSVILLE INTEGRATED SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/238 | 860549885.8
216 | October, 2014 | Award of Contract for the Construction (Erosion Control) of Ekenta-Omanpe-Odeukwu Ring Road, Phase II, Imo State | Imo State | JID CONST. COY. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/239 | 961050001
215 | October, 2014 | Award of Contract for the Construction of Ohuhu-Ekwuru-Mgbokonfa Road, Umunna Mbosi Autonomus Community, Isiala Ngwa | Imo State | RIB INVESTMENT NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/240 | 192507920
216 | October, 2014 | Award of Contract for the Installation of 1 No. 300KVA, 11/0.415KV Transformer at Umuori Uratta Community, Owerri North LGA | Imo State | SOLAR HOMES LTD. |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/IM/14/241 | 4500000
217 | October, 2014 | Award of Contract for the Proposed two bedroom semi detached building for special protection unit (SPU), Mini-Okoro Police Barracks, Lot 1, Port Harcourt LGA | Rivers State | VOCATIONAL & COMMUNITY SKILLS LTD. |  | Building | 12 months | NDDC/EDP/UIDW/PR/RV/14/242 | 248719008.15
218 | October, 2014 | Award of Contract for the Proposed two bedroom semi detached building for special protection unit (SPU), Mini-Okoro Police Barracks, Lot 2, Port Harcourt LGA | Rivers State | JOVAN & JEPHPHAN PROJECT DEV. LTD. |  | Building | 12 months | NDDC/EDP/UIDW/PR/RV/14/243 | 226713749.78
219 | October, 2014 | Award of Contract for the Proposed two bedroom semi detached building for special protection unit (SPU), Mini-Okoro Police Barracks, Lot 3, Port Harcourt LGA | Rivers State | BILORITZ NIG. LTD. |  | Building | 12 months | NDDC/EDP/UIDW/PR/RV/14/244 | 246374601.75
220 | October, 2014 | Award of Contract for the Proposed two bedroom semi detached building for special protection unit (SPU), Mini-Okoro Police Barracks, Lot 4, Port Harcourt LGA | Rivers State | HUNTILLA NIG. LTD. |  | Building | 12 months | NDDC/EDP/UIDW/PR/RV/14/245 | 230734842.13
221 | October, 2014 | Award of Contract for the Proposed two bedroom semi detached building for special protection unit (SPU), Mini-Okoro Police Barracks, Lot 5, Port Harcourt LGA | Rivers State | NIGER DELTA PROJECTS CONSORTIUM LTD. |  | Building | 12 months | NDDC/EDP/UIDW/PR/RV/14/246 | 248684700
222 | October, 2014 | Award of Contract for the Proposed two bedroom semi detached building for special protection unit (SPU), Mini-Okoro Police Barracks, Lot 6, Port Harcourt LGA | Rivers State | KEM-HAB NIG. LTD. |  | Building | 12 months | NDDC/EDP/UIDW/PR/RV/14/247 | 248684700
223 | October, 2014 | Award of Contract for the Construction of Igbodo Internal Road, Ika North East LGA | Delta State | BACOY CONST. COY. NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/248 | 249450000
224 | October, 2014 | Award of Contract for the Construction of Itu Ebange Street and Spurs Ekpenyong Bassey Close, Asim Akpo Street, Inyang Otop Street Ebeme Asim Street Bishop Anam Close in Calabar Municipal LGA | Cross River State | ZENITH CONST. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/CR/14/249 | 200000000
225 | November, 2014 | Award of Contract for the Construction of Internal Concrete Road Network at Aleibiri in Ekeremor LGA | Bayelsa State | AFAKA GLOBAL SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/250 | 249500000
226 | November, 2014 | Award of Contract for the Construction of Rigid Pavement at Ebedebiri, Sagbama LGA | Bayelsa State | OGETARE VENTURES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/251 | 150000000
227 | November, 2014 | Award of Contract for the Construction of Ansaoti EXT - Akpagu Paliamentary Road in Calabar | Cross River State | ZENITH CONST. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/CR/14/252 | 240000000
228 | November, 2014 | Award of Contract for the Construction of Otovwodo Ughelli Oviri Ogor-Okpavuere Olomu Ophorigala Road in Ughelli North LGA | Delta State | S.O. OLOTU & SONS NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/253 | 198172121
229 | November, 2014 | Award of Contract for the Construction of Internal Road Network at Odi Kolomuma-Opokuma LGA | Bayelsa State | AGBEINSCO WORLDWIDE LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/254 | 247000000
230 | November, 2014 | Award of Contract for the Construction of Secondary School Road, Phase 3, Uzamere at Uhunmwode LGA | Edo State | BAYOU LA BATRE LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/255 | 245011227.5
231 | November, 2014 | Award of Contract for the Construction of Idumeze-Aja Odah Road, Ika North LGA | Delta State | ZIMOHLAVI GLOBAL RESOURCES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/256 | 237000000
232 | November, 2014 | Award of Contract for the Construction of Deeper Life Avenue-Oro Club Road, Off PHCN in Oron LGA | Akwa Ibom State | ASILADRREN ENGINEERING LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/257 | 216750000
233 | November, 2014 | Award of Contract for the Construction of Edim Inyang-Udunghwo/Esuk Udo Road, Mbo LGA | Akwa Ibom State | SILVER BELLS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/258 | 241349325
234 | November, 2014 | Award of Contract for the Sandfilling of Akwa Ibom State University Site, Lot 1, Uyo LGA | Akwa Ibom State | OSMOSERVE GLOBAL LTD. |  | Sandfilling | 12 months | NDDC/EDP/UIDW/PR/AK/14/259 | 963694147.5
235 | November, 2014 | Award of Contract for the Sandfilling of Akwa Ibom State University Site, Lot 2, Uyo LGA | Akwa Ibom State | MERRYL-FYNCH LTD. |  | Sandfilling | 12 months | NDDC/EDP/UIDW/PR/AK/14/260 | 999758025
236 | November, 2014 | Award of Contract for the Sandfilling of Akwa Ibom State University Site, Lot 3, Uyo LGA | Akwa Ibom State | MPHASIS FULCRUM LTD. |  | Sandfilling | 12 months | NDDC/EDP/UIDW/PR/AK/14/261 | 999758025
237 | November, 2014 | Award of Contract for the Construction of Oku Iboku Internal Road in Itu LGA | Akwa Ibom State | VERINI CONSTRUCTION |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/262 | 850000000
238 | November, 2014 | Award of Contract for the Construction of Eket-James Town Raod Etebi-Oruko Road Alignment Lot 1 in Esit Eket/Orue Offong LGA | Akwa Ibom State | RIB INVESTMENT NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/263 | 932303887.35
239 | November, 2014 | Award of Contract for the Construction of Eket-James Town Raod Etebi-Oruko Road Alignment Lot 2 in Esit Eket/Orue Offong LGA | Akwa Ibom State | BASSE ENGINEERING & MICHEL LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/264 | 857737591.35
234 | November, 2014 | Award of Contract for the Construction of Ayeni/Ayadi Street, Igbokoda LGA | Ondo State | LOGTECH LIMITED |  | Road | 12 months | NDDC/EDP/UIDW/PR/ON/14/265 | 149718657.25
235 | November, 2014 | Award of Contract for the Construction of Internal Road in Opume Town, Ogbia LGA | Bayelsa State | SOLOMON MAX |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/266 | 249500000
236 | November, 2014 | Award of Contract for the Construction of Bomoundi Ekpetiama/Amassoma LGA | Bayelsa State | FREDPERRY CONST. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/267 | 249965370
237 | November, 2014 | Award of Contract for the Construction of Kirikiridien Road in Abuloma with Drains, Port Harcourt LGA | Rivers State | MOHRUBENA INT'L LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/268 | 200000000
238 | November, 2014 | Award of Contract for the Construction of Uyi Aigbogun and Adjoining Streets Aigbogbun, Oredo LGA | Edo State | NORTHSEA NIGERIA |  | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/269 | 199999989.5
239 | November, 2014 | Award of Contract for the Construction of Apodu/ Okorogben Walkway in Bomadi LGA | Delta State | HERITON TRADE LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/270 | 100611055.36
240 | November, 2014 | Award of Contract for the Installation of 2 Nos 500KVA, 33/0.415KV Transformer at Ogbere Nyande Community and Okenta Alode, Eleme LGA | Rivers State | KAIZEN NIG. LTD. |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/RV/14/271 | 9000000
241 | November, 2014 | Award of Contract for the Construction of Umuru Omuma Afor Akatta Road, Oru East LGA | Imo State | JARABIC LIMITED |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/272 | 249875480
242 | November, 2014 | Award of Contract for the Construction of Solar Street Light at the University of Benin Teaching Hospital, Benin City, Oredo LGA | Edo State | SAMATT GLOBE LTD. |  | Solar Light | 12 months | NDDC/EDP/UIDW/PR/ED/14/273 | 249272074
243 | November, 2014 | Award of Contract for the Construction of Internal Road Tarring with Drains on both sides in Ilabor Community in Ika North East LGA | Delta State | HONERICH COY. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/274 | 200000000
244 | November, 2014 | Award of Contract for the Construction of Rigid Pavement at New High Court Road, Opposite Govt. Sect. Phase 2, Bomadi LGA | Delta State | SANEWSCO INT'L LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/275 | 164056552
245 | November, 2014 | Award of Contract for the Construction of Agilobi Street, Agudama in Yenagoa LGA | Bayelsa State | EBIDEINMO NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PRBY/14/276 | 98538667.7
246 | November, 2014 | Award of Contract for the Construction of Internal Road in Opume Town, Phase 2 in Ogbia LGA | Bayelsa State | TRENUR NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/277 | 249680970
247 | November, 2014 | Award of Contract for the Rehabilitation of Abonema- Obonoma Road, Akuku Toru LGA | Rivers State | DONMAT NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/278 | 233556000
248 | November, 2014 | Award of Contract for the Electrification of Opume Community in Ogbia LGA | Bayelsa State | TRENUR NIG. LTD. |  | Elect. | 12 months | NDDC/EDP/UIDW/PR/BY/14/279 | 249500000
249 | November, 2014 | Award of Contract for the Installation of Transformer at Mmbak Etoi (HT & LT), in Uyo LGA | Akwa Ibom State | ESSIENIBOK CONSULTANT |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/AK/14/280 | 30000000
250 | November, 2014 | Award of Contract for the Installation of Transformer at Anan Ikot Ekpri Nsukaram (HT & LT), in Uyo LGA | Akwa Ibom State | VIKA LIMITED |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/AK/14/281 | 30000000
251 | November, 2014 | Award of Contract for the NDDC Grassroot Empowerment Network (Gen) Community Resource Centre in Eleme LGA | Rivers State | GRASSROOT EMPOWERMENT NETWORK |  | Empowerment | 12 months | NDDC/EDP/UIDW/PR/RV/14/282 | 80585418.1
252 | November, 2014 | Award of Contract for the Construction Rigid Pavement, Phase 2 at Abalama, Ilelema, Oporoma, Okpo and Tema, Asari Toru LGA | Rivers State | ABESCO CONST. CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/283 | 232899560
253 | November, 2014 | Award of Contract for the Rural Electrification at Omuwheche New Layout and Supply of Transformer, Omuwheche, Ikwerre LGA | Rivers State | KENIAH NIG. LTD. |  | Transformer | 12 months | NDDC/EDP/UIDW/PR/RV/14/284 | 240000000
254 | November, 2014 | Award of Contract for the Construction of Road at Omumeje Obinze in Owerri West LGA | Imo State | VOCATIONAL & COMMUNITY SKILLS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/285 | 240000000
255 | November, 2014 | Award of Contract for the Construction of Imo Polytechnic Internal Road, Umuagwo Ohaji/Egbema LGA | Imo State | HEXA-DIS CONST. CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/286 | 480000000
255 | November, 2014 | Award of Contract for the Construction of Palace Road, Phase 1 Utek Ekoko Community, Ikpoba-Okha LGA | Edo State | SHEPHERD VOICE UNIVERSAL SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/287 | 249950000
256 | November, 2014 | Award of Contract for the Construction of Six (6) classroom block at Federal Girls College at Owerri Municipality LGA | Imo State | GEOGIC GLOBAL SERVICES COY. |  | Classroom block | 6 months | NDDC/EDP/UIDW/PR/IM/14/288 | 30000000
257 | November, 2014 | Award of Contract for the Construction of Iton Abat Internal Roads, Phase 2, Ikono LGA | Akwa Ibom State | SOBAI INTEGRATED SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/289 | 137326915
258 | November, 2014 | Award of Contract for the Construction of Lucky Igbenedion Street, Roland Obandor and Osaro Street, Ugiokhuen | Edo State | P.S. I. INT'L COY. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/290 | 249950000
259 | November, 2014 | Award of Contract for the Construction of Road at Amowu Street, Off Upper Sakoponba Road after Oka Market in Ikpoba-Okha LGA | Edo State | COTABS ENGINEERING LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/291 | 249000000
260 | December, 2014 | Award of Contract for the Construction of CKC Aba Junction to Saint Paul Isu Junction Road and Drains in Nwangele LGA | Imo State | GRAPIK LIMITED |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/292 | 240000000
261 | December, 2014 | Award of Contract for the Construction of Umuogbu Amato-Uriaba-Dimagu Road in Nwangele LGA | Imo State | ELKAN ZIBSON LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/293 | 246000000
262 | December, 2014 | Award of Contract for the Construction of Isibori Market Road with spur to Agiga New Layout in Ogoja LGA | Cross River State | GEOGRAPHIC TRACKING SYSTEMS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/CR/14/294 | 200000000
263 | December, 2014 | Award of Contract for the Provision of Solar Powered Street Light at Ohong Betukwel Igwo Villages, Obudu | Cross River State | NEBEN NIG. LTD. |  | Solar Light | 12 months | NDDC/EDP/UIDW/PR/CR/14/295 | 240000000
264 | December, 2014 | Award of Contract for the Construction of Okuku-Okpoma Road in Okuku Yala LGA | Cross River State | AMPLE DIMENSION LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/CR/14/296 | 200000000
265 | December, 2014 | Award of Contract for the Construction of Udayi-Akpabuyo Estate Road, Akpabuyo LGA | Cross River State | J.T.I. ORGANISATION LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/CR/14/297 | 249000000
266 | December, 2014 | Award of Contract for the Construction of Ablasang-Buya Road in Obanilikwu LGA | Cross River State | VENESSA INT'L LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/CR/14/298 | 200000000
267 | December, 2014 | Award of Contract for the Construction of Bendi/Upan/Adede Road in Obanikwu LGA | Cross River State | DEFLON OIL COY. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/CR/14/299 | 240000000
268 | December, 2014 | Award of Contract for the Provision of Solar Powered Street Light at Abakpa/Igoli/Okuku, Ogoja LGA | Cross River State | STEELCREST ENGINEERING & CONST. LTD. |  | Solar Light | 12 months | NDDC/EDP/UIDW/PR/CR/14/300 | 240000000
269 | December, 2014 | Award of Contract for the Rehabilitation of Old Obudu, Sankwala Road in Obanlikwu LGA | Cross River State | DGP RESOURCES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/CR/14/301 | 200000000
270 | December, 2014 | Award of Contract for the Rehabilitation of Bori/Kwawa/ Boua Roads, Khana LGA | Rivers State | FIPHS INFRASTRUCTURE LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/302 | 900000000
270 | December, 2014 | Award of Contract for the Construction of Ellu/ Ovrode Road, Phase II, Isoko North LGA | Delta State | SOLOTUS NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/303 | 243039225
271 | December, 2014 | Award of Contract for the Construction of Express-Ama Ogbenna-Mission-Ama Agbaraoji Ezeleke Primary School in Aba South LGA | Abia State | FLUCHON INTEGRATED SERVICES NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/304 | 249857600
272 | December, 2014 | Award of Contract for the Construction of Isuochi-Nneator Road, Phase II, Umunnochi LGA | Abia State | CRICKLEWOOD CONST. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/305 | 200000000
273 | December, 2014 | Award of Contract for the Construction of Solar Street Light at Ase Town, Ndokwa East LGA | Delta State | AKOGATE VENTURES LTD. |  | Solar Light | 12 months | NDDC/EDP/UIDW/PR/DT/14/306 | 100000000
274 | December, 2014 | Award of Contract for the Rehabilitation of Ogbakiri Junction - Tema Road, Lot 1 | Rivers State | DERICK CONST. SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/307 | 249875650
275 | December, 2014 | Award of Contract for the Rehabilitation of Ogbakiri Junction - Tema Road, Lot II | Rivers State | DESWAMP CONST. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/308 | 249875650
276 | December, 2014 | Award of Contract for the Rehabilitation of Archdeacon Crowther Memorial Girls School Road, Elelenwo, Obio Akpor LGA | Rivers State | ISNERO NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/309 | 248261037.5
277 | December, 2014 | Award of Contract for the Construction of Road 5, Okporo Estate, Elikpokwuodu, Rukpoku in Port Harcourt LGA | Rivers State | ESCOBER STEEL CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/310 | 150000000
278 | December, 2014 | Award of Contract for the Construction of Assa Township Road, (7.5km), Ukwa West/East LGA | Abia State | GRINFRAPROJECTS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/311 | 982931950
278 | December, 2014 | Award of Contract for the Construction of Concrete Landing jetty and adjoining walkway in Igo, Ilaje LGA | Ondo State | WATERDRILL LTD. |  | Landing jetty | 12 months | NDDC/EDP/UIDW/PR/ON/14/312 | 198810731
279 | December, 2014 | Award of Contract for the Construction of Owok Akpa Road at Ekpuk Inang, Ete Community, Ikot Abasi LGA | Akwa Ibom State | POINTUP LIMITED |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/313 | 249867450
280 | December, 2014 | Award of Contract for the Construction of Nslakukuri Ring Road | Rivers State | MAGRONI LIMITED |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/314 | 200000000
281 | December, 2014 | Award of Contract for the Construction of Road Network in Minima Community in Opobo/ Nkoro LGA | Rivers State | DEEPROCK INVESTMENT CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/315 | 248000000
282 | December, 2014 | Award of Contract for the Construction of Isuochi-Nneator Road, Phase I, Umunnochi LGA | Abia State | HATCHCAD NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/316 | 200000000
283 | December, 2014 | Award of Contract for the Installation of 2 Nos 500KVA Transformers and 2 Nos 500KVA Generators at Ayababiri Town, Kolokuma Clan | Bayelsa State | GORMU GENERAL ENTERPRISES |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/317 | 64552500.5
284 | December, 2014 | Award of Contract for the Construction of Obubu Internal Roads in Udu LGA | Delta State | APLAMATUSE VENTURES |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/318 | 249650452
285 | December, 2014 | Award of Contract for the Construction of Ibiaku Ikot Ukana with drains, Ikono LGA | Akwa Ibom State | KANSUANA NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/319 | 180000000
286 | December, 2014 | Award of Contract for the Construction of Gbokoda-Jakpa, Olero Creek Community, Lot 1, Warri North LGA | Delta State | CURLEW EXPRESS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/320 | 960000000
287 | December, 2014 | Award of Contract for the Construction of Gbokoda-Jakpa, Olero Creek Community, Lot 2, Warri North LGA | Delta State | PAACHE CONSTRUCTION LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/321 | 880000000
288 | December, 2014 | Award of Contract for the Construction of Gbokoda-Jakpa, Olero Creek Community, Lot 3, Warri North LGA | Delta State | WALAND SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/322 | 760000000
286 | December, 2014 | Award of Contract for the Remedial works on Ikot Akpan Abia New Road, Uyo | Akwa Ibom State | AIDEE UNIQUE SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/323 | 220000000
287 | December, 2014 | Award of Contract for the Construction of Solar Powered Street Light along NDDC Community Centre and environs, Amamong, Okobo LGA | Akwa Ibom State | PENTAGON ENERGY LTD. |  | Solar Light | 12 months | NDDC/EDP/UIDW/PR/AK/14/324 | 249995000
288 | December, 2014 | Award of Contract for the Construction of Fencing, landscaping and erosion control at NDDC community centre, Amamong, Okobo LGA | Akwa Ibom State | GREAT HOUSE INVESTMENTS LTD. |  | Fencing | 12 months | NDDC/EDP/UIDW/PR/AK/14/325 | 249890000
289 | December, 2014 | Award of Contract for the Flood/ Erosion Control work along Okopedi Oron Road, Okobo LGA | Akwa Ibom State | E-PLUS PROJECTS LTD. |  | Erosion control | 12 months | NDDC/EDP/UIDW/PR/AK/14/326 | 249995000
290 | December, 2014 | Award of Contract for the Construction of Internal Roads in Amamong, Okobo LGA | Akwa Ibom State | TRANS-SOSSA NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/327 | 249980000
291 | December, 2014 | Award of Contract for the Emergency Repair/ Maintenance of Ikot Akan to Ibekwe Akpan Nya Road (Ikot Abasi/Abak Road), Phase II, in Ikot Abasi/ Mkpat Enin LGA | Akwa Ibom State | BASSE ENGINEERING & MICHEL LTD. |  | Emergency repair | 12 months | NDDC/EDP/UIDW/PR/AK/14/328 | 415982504.35
291 | December, 2014 | Award of Contract for the Installation of 3 Nos 500KVA, 33/0.415KV Transformers for Okrika | Rivers State | AGOS INTEGRATED SERVICES LTD. |  | Transformer | 12 months | NDDC/EDP/UIDW/PR/RV/14/329 | 13500000
292 | December, 2014 | Award of Contract for the Installation of 2 Nos 500KVA, 33/0.415KV Transformers at Bolo and Ogoloma | Rivers State | LINKS GLOBAL SYNERGY LTD. |  | Transformer | 12 months | NDDC/EDP/UIDW/PR/RV/14/330 | 9000000
293 | December, 2014 | Award of Contract for the Installation of 2 Nos 5300KVA, 33/0.415KV Transformers at Ogu Town, Okrika | Rivers State | BAPS STANDARD DELIVERIES LTD. |  | Transformer | 12 months | NDDC/EDP/UIDW/PR/RV/14/331 | 9000000
294 | December, 2014 | Award of Contract for the Supply of ICT Material for Abua ACSS Library Anyu in Abua/Odual LGA | Rivers State | WANDXWORTH INT'L LTD. |  | ICT | 12 months | NDDC/EDP/UIDW/PR/RV/14/332 | 228000000
295 | December, 2014 | Award of Contract for the Supply of ICT Material for Abua Central in Abua/Odual LGA | Rivers State | MEGA GLOBAL RESOURCES |  | ICT | 12 months | NDDC/EDP/UIDW/PR/RV/14/333 | 228000000
296 | December, 2014 | Award of Contract for the Construction of Roads leading to NDDC Estate, Off Abuloma Road, Port Harcourt LGA | Rivers State | GUSTO ENGINEERING & CONST. SERV. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/335 | 129045449.5
297 | December, 2014 | Award of Contract for the Construction of Bebua Gba Via Babiabie to Kutiang in Obudu LGA | Cross River State | UD-CLEM INTEGRATED SYSTEM NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/CR/14/336 | 200000000
298 | December, 2014 | Award of Contract for the Construction of Obosso-Mbube East/Ukpa/Rebu Junction in Mbube Ogola LGA | Cross River State | KOMPA INVESTMENT COY. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/CR/14/337 | 200000000
299 | December, 2014 | Award of Contract for the Rehabilitation of Uko Akpan- Unyenge Road, Mbo LGA | Akwa Ibom State | COTABS ENGINEERING LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/338 | 400000000
299 | December, 2014 | Award of Contract for the Construction of Olokumo-Ama Road, Amassoma, Phase 1, Southern Ijaw LGA | Bayelsa State | BANKPHILLIP PROPERTIES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/339 | 100000000
300 | December, 2014 | Award of Contract for the Construction of Amassoma Internal Roads, Southern Ijaw LGA | Bayelsa State | NOBLE CAPITAL NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/340 | 249500000
301 | December, 2014 | Award of Contract for the Construction of DSP By-pass Road, Amassoma, Southern Ijaw LGA | Bayelsa State | NOBLE CAPITAL NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/341 | 240000000
302 | December, 2014 | Award of Contract for the Construction of Tebu-Gbokoda Road, Olero Creek Community (Lot 1), Warri North LGA | Delta State | WEBSTER GLOBAL VENTURES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/342 | 850000000
303 | December, 2014 | Award of Contract for the Construction of Tebu-Gbokoda Road, Olero Creek Community (Lot 2), Warri North LGA | Delta State | RISING HEIGHTS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/343 | 650000000
302 | December, 2014 | Award of Contract for the Construction of Aisher Eletou Road from Old New Port Harcourt/Aba Road in Oyigbo LGA | Rivers State | DNANLEE RESOURCES |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/344 | 249850000
303 | December, 2014 | Award of Contract for the Construction of Osian Street in Ika North East LGA | Delta State | EDEDEKU GLOBAL SERV. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/344 | 240000000
304 | December, 2014 | Award of Contract for the Construction of Cement Street in Ika North East LGA | Delta State | HONERICH COY. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/345 | 200000000
305 | December, 2014 | Award of Contract for the Tarring of Odeh Street in Ika South East LGA | Delta State | REGINALO R & N NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/346 | 180000000
306 | December, 2014 | Award of Contract for the Construction of Tebu-Gbokoda Road, Olero Creek Community (Lot 3), Warri North LGA | Delta State | RISING HEIGHTS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/347 | 650000000
306 | December, 2014 | Award of Contract for the Construction of Road 12 Connecting Road 21 and 29, Federal Housing Estate, Woji, Port Harcourt LGA | Rivers State | GINA INTEGRATED SERVICES |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/348 | 249000000
307 | December, 2014 | Award of Contract for the Construction of Agidiase-Ogbe-Isheagwu Road (Phase 1), Aniocha South LGA | Delta State | HONERICH COY. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/349 | 550000000
308 | December, 2014 | Award of Contract for the Construction of Abbi-Emu-Uno Road, Ndokwa West LGA | Delta State | SHARPSTONE CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/350 | 900000000
309 | December, 2014 | Award of Contract for the Construction of Ring Road, Umunede, Ika North East LGA | Delta State | REGINALO R & N NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/351 | 495000000
307 | December, 2014 | Award of Contract for the Construction of Akwukwu Circular Road (Umu-Opu to Ogbani), Oshimili North LGA | Delta State | HONERICH COY. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/352 | 180000000
308 | December, 2014 | Award of Contract for the Construction of Warri Internal Roads, Lot 1, (Dore Roland Road, Sand Beach Road 1 and Sand Beach Road 2) in Warri | Delta State | ARC (MARINE & CIVIL CONTRACTORS) LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/353 | 249000000
309 | December, 2014 | Award of Contract for the Construction of Asaba Internal Roads (Chris Igbenigun Street Core Area II), Lot 6 | Delta State | EWEJOBAT COMPANY |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/354 | 245500000
310 | December, 2014 | Award of Contract for the Construction of Asaba Internal Roads (WAEC Extension 4), Lot 3 | Delta State | FROT PROJECT & PROCUREMENT SERV. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/355 | 245500000
311 | December, 2014 | Award of Contract for the Construction of Asaba Internal Roads (Isidore Olele Street), Lot 5 | Delta State | FROT ENERGY SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/356 | 245500000
312 | December, 2014 | Award of Contract for the Construction of Asaba Internal Roads (WAEC Extension 1 & 3), Lot 2 | Delta State | WESTON CHIVAS EMPORIUM LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/357 | 245500000
313 | December, 2014 | Award of Contract for the Construction of Asaba Internal Roads (Chief R. Louis Odogwu Street), Lot 4 | Delta State | BULWARK CONST. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/358 | 245500000
314 | December, 2014 | Award of Contract for the Construction of Asaba Internal Roads (Lady Tonia Ojokwu Street), Lot 1 | Delta State | RICCARDO CONSTRUCTION NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/359 | 245500000
315 | December, 2014 | Award of Contract for the Construction of Warri Internal Roads, Lot 1, Emergency Maintenance Provision of Drainages Structure Repairs, Reinstatement and Pavement Strenghthening along Ekwaju Road and Shell Contractors Gate Road in Warri | Delta State | RICCARDO CONSTRUCTION NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/360 | 249000000
316 | December, 2014 | Award of Contract for the Construction of BSA Odofori Avenue Beside Open University, Bayelsa Palm Road, Yenagoa LGA | Bayelsa State | RADNITZ INTEGRATED SERV. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/361 | 240000000
317 | December, 2014 | Award of Contract for the Construction of Warri Internal Roads, Lot 2, Emergency Maintenance Provision of Drainages Structure Repairs, Reinstatement and Pavement Strenghthening along Ekwaju Road and Shell Contractors Gate Road in Warri | Delta State | RICCARDO CONSTRUCTION NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/362 | 249000000
318 | December, 2014 | Award of Contract for the Construction of Warri Internal Roads, Lot 3, Emergency Maintenance Provision of Drainages Structure Repairs, Reinstatement and Pavement Strenghthening along NPA Express Road (Dual Carriageway) in Warri | Delta State | WESTON CHIVAS EMPORIUM LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/363 | 249000000
319 | December, 2014 | Award of Contract for the Construction of Asaba Internal Roads, Lot 1 | Delta State | TRANS-CONTINENTAL NETWORK LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/364 | 249650452
320 | December, 2014 | Award of Contract for the Reclamation (Sandfilling) of Abigborodo Community, Warri North LGA (Lot 1) | Delta State | ROYAL MAID INT'L RESOURCES LTD. |  | Reclamation | 12 months | NDDC/EDP/UIDW/PR/DT/14/365 | 963000000
321 | December, 2014 | Award of Contract for the Reclamation (Sandfilling) of Abigborodo Community, Warri North LGA (Lot 2) | Delta State | CROWN TOWER INT'L RESOURCES LTD. |  | Reclamation | 12 months | NDDC/EDP/UIDW/PR/DT/14/366 | 985000000
322 | December, 2014 | Award of Contract for the Reclamation (Sandfilling) of Abigborodo Community, Warri North LGA (Lot 3) | Delta State | RINDEX ASSOCIATES |  | Reclamation | 12 months | NDDC/EDP/UIDW/PR/DT/14/367 | 985000000
323 | December, 2014 | Award of Contract for the Shore Protection at Abigborodo Community, Warri North LGA (Lot 1) | Delta State | LORICAMP ENGINEERS & CONSULTANTS |  | Shore protection | 12 months | NDDC/EDP/UIDW/PR/DT/14/368 | 800000000
324 | December, 2014 | Award of Contract for the Shore Protection at Abigborodo Community, Warri North LGA (Lot 3) | Delta State | A. I. L. INFRASTRUCTURES LTD. |  | Shore protection | 12 months | NDDC/EDP/UIDW/PR/DT/14/369 | 557648750
325 | December, 2014 | Award of Contract for the Shore Protection at Abigborodo Community, Warri North LGA (Lot 2) | Delta State | PLANET PROJECTS LTD. |  | Shore protection | 12 months | NDDC/EDP/UIDW/PR/DT/14/370 | 750000000
326 | December, 2014 | Award of Contract for the Construction of Abigborodo Community Roads, Warri North LGA (Lot 1) | Delta State | GOLD & GATE RESOURCES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/371 | 978157500
327 | December, 2014 | Award of Contract for the Construction of Abigborodo Community Roads, Warri North LGA (Lot 2) | Delta State | CEMAG GATE |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/372 | 986193750
320 | December, 2014 | Award of Contract for the Construction of Warri Internal Roads, Lot 4, Emergency Maintenance Provision of Drainages Structure Repairs, Reinstatement and Pavement Strenghthening along Secondary School Roads in Warri | Delta State | WIND-JERI INTEGRATED RESOURCES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/373 | 249000000
321 | December, 2014 | Award of Contract for the Construction of Efue Street, Oyede, Isoko North LGA | Delta State | LEZFREMOR SERVICES |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/374 | 140000000
322 | December, 2014 | Award of Contract for the Construction of Concrete Pavement/ Drain at Ocan/Miebi Street, Off Sedica Road, Enerhen, Uvwie LGA | Delta State | BRIGICON INTEGRATED SERV. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/375 | 245000000
323 | December, 2014 | Award of Contract for the Construction of Strabag Road in Ayadehe in Itu LGA | Akwa Ibom State | PAMINA ENT. NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AKS/14/376 | 200000000
324 | December, 2014 | Award of Contract for the Construction of Mbak Atai Ring Road, Edere Mbak-Ikot Enwan-Akpa Utong-Ekeng-Edem Edit Mbak Atai in Itu LGA | Akwa Ibom State | BROOKFIELD CEDAR PROPERTIES NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AKS/14/377 | 249000000
325 | December, 2014 | Award of Contract for the Construction of Abisa Beach Road/Friday Tom Inyang Street, Off Afaha Atai Road, Ikot Ibiok (200m), Ekott Street, Ukwa Estate, Off Oron Road (500m), Akrudum Street, Off Etebom Road, Etebi Idung Iwak (300m) in Eket LGA | Akwa Ibom State | UTIMANIK INTEREST LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AKS/14/378 | 248870550
326 | December, 2014 | Award of Contract for the Construction of Udo-Ajamita Road in Warri North LGA, Lot 1 | Delta State | FROT ENERGY SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/379 | 800000000
327 | December, 2014 | Award of Contract for the Construction of Tebu-Gbokoda-Udo Road, Olero Creek Community, Warri North LGA (Lot 2) | Delta State | WESTON CHIVAS EMPORIUM LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/380 | 800000000
328 | December, 2014 | Award of Contract for the Construction of Tebu-Gbokoda-Udo Road, Olero Creek Community, Warri North LGA (Lot 1) | Delta State | RICCARDO CONSTRUCTION NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/381 | 910000000
329 | December, 2014 | Award of Contract for the Construction of Udo-Ajamita Road in Warri North LGA, Lot 2 | Delta State | FROT PROJECT & PROCUREMENT SERV. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/382 | 650000000
326 | December, 2014 | Award of Contract for the Construction of Mbutu Umuojima Obuzor-Umuakpara Road, Osisioma Ngwa | Abia State | LIPPIZANER STALLION NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/383 | 249500000
327 | December, 2014 | Award of Contract for the Construction of Uzomiri Umuakali Road, Omuma LGA | Rivers State | AJ BUTLER INT'L LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/384 | 150000000
328 | December, 2014 | Award of Contract for the Construction of Internal Road Network around Otuke (Lot 2) in Ogbia LGA | Bayelsa State | ZEROCK CONST. NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/385 | 989643250
329 | December, 2014 | Award of Contract for the Construction of Internal Road Network around Otuke (Lot 1) in Ogbia LGA | Bayelsa State | ZEROCK CONST. NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/386 | 978950680
330 | December, 2014 | Award of Contract for the Construction of Internal Road Network around Otuke (Lot 3) in Ogbia LGA | Bayelsa State | ZEROCK CONST. NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/387 | 978432123
328 | December, 2014 | Award of Contract for the Construction of Ekiebong-Ubotuong Road in Mbo LGA | Akwa Ibom State | TIMARIS NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AKS/14/388 | 245000000
329 | December, 2014 | Award of Contract for the Construction of NDDC Rivers State Office Building Project, Phase 2, Port Harcourt | Rivers State | KOMESS RESOURCES NIG. LTD. |  | Building | 12 months | NDDC/EDP/UIDW/PR/RV/14/389 | 570900362.27
329 | December, 2014 | Award of Contract for the Construction of Motorized Borehole at Amaukwu, Ozaa in Ukwa West LGA | Abia State | WATERFRONT DEV. LTD. |  | Borehole | 12 months | NDDC/EDP/UIDW/PR/AB/14/390 | 100000000
330 | December, 2014 | Award of Contract for the Construction of Internal Roads, Umuekwule, Umuahia North LGA | Abia State | GLOBAL CONST. & LOGISTICS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/391 | 987435500
330 | December, 2014 | Award of Contract for the Construction of Umuarugwu Internal Roads, Ehime Mbano LGA | Imo State | BASH & BOLTS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/392 | 248000000
331 | December, 2014 | Award of Contract for the Construction of Amaji-Umuogolo-Umudogwu Road, Ehime Mbano LGA | Imo State | WESTERN DEV. CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/393 | 249000000
332 | December, 2014 | Award of Contract for the Installation of 1 No. 500KVA 33/0.415KV Transformer at Okoroutip Village, Ibeno LGA | Akwa Ibom State | E. J. JAMES CONST. WORKS LTD. |  | Transformer | 12 months | NDDC/EDP/UIDW/PR/AK/14/395 | 4500000
333 | December, 2014 | Award of Contract for the Installation of 1 No. 500KVA 11/0.415KV Transformer at Obo Atai Community, Nsit Ibom LGA | Akwa Ibom State | BLIZZCON PARTNERS NIG. LTD. |  | Transformer | 12 months | NDDC/EDP/UIDW/PR/AK/14/396 | 4500000
334 | December, 2014 | Award of Contract for the Installation of 1 No. 300KVA 33/0.415KV Transformer at Ikot Ata Udo (Ukpum Okon Community), Ikot Abasi LGA | Akwa Ibom State | CAROS ENGINEERING SERVICES LTD. |  | Transformer | 12 months | NDDC/EDP/UIDW/PR/AK/14/397 | 4500000
335 | December, 2014 | Award of Contract for the Construction of Agbowosi Street and Drainages, Warri South LGA | Delta State | ARC MARINE & CIVIL CONTRACTORS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/398 | 235000000
336 | December, 2014 | Award of Contract for the Construction of Alaka Road in Orhunworhun, Udu LGA | Delta State | PAN BAAE INV. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/399 | 100000000
337 | December, 2014 | Award of Contract for the Construction of Solar Water at Okpara Waterside, Ethiope East LGA | Delta State | SUNLEY CONST. CO. LTD. |  | Solar water | 12 months | NDDC/EDP/UIDW/PR/DT/14/400 | 52000000
338 | December, 2014 | Award of Contract for the Construction of Arthur Akpowowo Road, Ebrumede, Uvwie LGA | Delta State | ROSA VOSA NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/401 | 240000000
339 | December, 2014 | Award of Contract for the Construction of 2Km Road, Ebrumede, Uvwie LGA | Delta State | MAVIS GLOBAL CONSULT LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/402 | 250000000
340 | December, 2014 | Award of Contract for the Construction of Iyase Osowe Road, Off Infant Jesus Road, Asaba Internal Road (Lot 3) | Delta State | A & J CONST. CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/403 | 240000000
341 | December, 2014 | Award of Contract for the Construction of Idumu-Ugbo/ Owarre Road, Ute-Ukpu, Ika North East LGA | Delta State | HONERICH COY. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/404 | 200000000
342 | December, 2014 | Award of Contract for the Construction of Egborode Primary School with Gate House and Administrative Block at Okpe LGA | Delta State | TOSKAT NIG. LTD. |  | Gate house | 12 months | NDDC/EDP/UIDW/PR/DT/14/405 | 99974998.66
343 | December, 2014 | Award of Contract for the Construction of Richard Oviorho Street, Off Agbarho-Warri Road, Okukpere Near Okuokoko, Okpe LGA | Delta State | CRUSTEAM NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/406 | 160000000
344 | December, 2014 | Award of Contract for the Construction of Chuks Chimoronke Avenue, Asaba Internal Road (Lot 1) | Delta State | DERE ENGINEERING CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/407 | 248000000
345 | December, 2014 | Award of Contract for the Construction of Trem Church Road by Ibusa (Plaza), Asaba Internal Road (Lot 4) | Delta State | SEA FANCEE LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/408 | 247000000
346 | December, 2014 | Award of Contract for the Construction of Godwin Ayemi Street in Okukprere New Layout, Okuokoko, Okpe LGA | Delta State | BELCH & SOME INV. & TRUST LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/409 | 150000000
347 | December, 2014 | Award of Contract for the Construction of Obi Link by Akpanam Road and SSG Link Road - Austin Okonji Avenue, Asaba Internal Road (Lot 2) | Delta State | CAROS ENGINEERING SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/410 | 246000000
348 | December, 2014 | Award of Contract for the Canalization, Reclamation and Provision of Recreational Facilities at Idung Afangedem, Esit Eket LGA | Akwa Ibom State | TOM FLAKES NIG. LTD. |  | Canalization | 12 months | NDDC/EDP/UIDW/PR/AK/14/411 | 501248100
348 | December, 2014 | Award of Contract for the Construction of School to Land - Betem Road, Bori | Rivers State | GUSMAN LIMITED |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/412 | 245000000
349 | December, 2014 | Award of Contract for the Construction of Concrete Pavement Road, Opposite Abacha Estate, Opolo, Yenagoa LGA | Bayelsa State | PAUL & OKPIKPI NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/413 | 249500000
350 | December, 2014 | Award of Contract for the Construction of Concrete Pavement Road at La-Gold Street, Ekeki, Yenagoa LGA | Bayelsa State | EBIKEBINA NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/414 | 249500000
351 | December, 2014 | Award of Contract for the Construction of Ebikake Street, Ede-Epie, Yenagoa LGA | Bayelsa State | DEN-BI NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/415 | 249500000
352 | December, 2014 | Award of Contract for the Construction of 3Km Concrete Road with Culvert and Drainage from Beautiful Gate to Foutorugbene, Ekeremor LGA | Bayelsa State | NEX-XYNEX NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/416 | 900000000
353 | December, 2014 | Award of Contract for the Construction of Hon. Dein Benadoumene Road, Ekeke, Yenagoa LGA | Bayelsa State | ORRION TRUST INT'L LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/417 | 290000000
354 | December, 2014 | Award of Contract for the Reclamation and Sandfilling of Kurutie in Warri South West LGA | Delta State | K.F.T. UDUBOH NIG. LTD. |  | Reclamation | 12 months | NDDC/EDP/UIDW/PR/DT/14/418 | 950000000
355 | December, 2014 | Award of Contract for the Canalization of Oporoza Creek, Phase 1, Warri South LGA | Delta State | DISEK INTEGRATED GLOBAL LTD. |  | Canalization | 12 months | NDDC/EDP/UIDW/PR/DT/14/419 | 750000000
356 | December, 2014 | Award of Contract for the Canalization of Oporoza Creek, Phase 2, Warri South LGA | Delta State | PAMOCT NIG. LTD. |  | Canalization | 12 months | NDDC/EDP/UIDW/PR/DT/14/420 | 750000000
357 | December, 2014 | Award of Contract for the Reclamation and Sandfilling of Benikrukru, Lot 1, Warri South West LGA | Delta State | SWAMPGROVE NIG. LTD. |  | Reclamation | 12 months | NDDC/EDP/UIDW/PR/DT/14/421 | 950000000
358 | December, 2014 | Award of Contract for the Reclamation and Sandfilling of Benikrukru, Lot 2, Warri South West LGA | Delta State | GPDDYBEST INTEGRATED RESOURCES LTD. |  | Reclamation | 12 months | NDDC/EDP/UIDW/PR/DT/14/422 | 950000000
359 | December, 2014 | Award of Contract for the Reclamation and Sandfilling of Benikrukru, Lot 3, Warri South West LGA | Delta State | FELOKINA SERVICES NIG. LTD. |  | Reclamation | 12 months | NDDC/EDP/UIDW/PR/DT/14/423 | 950000000
360 | December, 2014 | Award of Contract for the Reclamation and Sandfilling of Benikrukru, Lot 4, Warri South West LGA | Delta State | LAYEFA GLOBAL OIL SERVICES LTD. |  | Reclamation | 12 months | NDDC/EDP/UIDW/PR/DT/14/424 | 950000000
361 | December, 2014 | Award of Contract for the Reclamation and Sandfilling of Benikrukru, Lot 5, Warri South West LGA | Delta State | JOWURUS NIG. LTD. |  | Reclamation | 12 months | NDDC/EDP/UIDW/PR/DT/14/425 | 600000000
362 | December, 2014 | Award of Contract for the Reclamation and Sandfilling of Benikrukru, Lot 6, Warri South West LGA | Delta State | KWUE NIG. LTD. |  | Reclamation | 12 months | NDDC/EDP/UIDW/PR/DT/14/426 | 600000000
363 | December, 2014 | Award of Contract for the Reclamation and Sandfilling of Kokodiagbene, Lot 1, Warri South LGA | Delta State | POWEDE NIG. LTD. |  | Reclamation | 12 months | NDDC/EDP/UIDW/PR/DT/14/427 | 750000000
364 | December, 2014 | Award of Contract for the Reclamation and Sandfilling of Kokodiagbene, Lot 2, Warri South LGA | Delta State | BENOTECH RESOURCES NIG. LTD. |  | Reclamation | 12 months | NDDC/EDP/UIDW/PR/DT/14/428 | 750000000
352 | December, 2014 | Award of Contract for the Construction of 1 no. 6 Classroom block and Staff quarters at Benikrukru Community Scondary School, Benikrukru, Warri South West LGA | Delta State | BLUEGATE ASSOCIATES LTD. |  | Classroom block | 12 months | NDDC/EDP/UIDW/PR/DT/14/429 | 199500000
353 | December, 2014 | Award of Contract for the Construction of Lecture Theature, E. K. Clark University, Kiagbodo, Burutu LGA | Delta State | WAINE INV. INTEGRATED LTD. |  | Building | 12 months | NDDC/EDP/UIDW/PR/DT/14/430 | 250000000
354 | December, 2014 | Award of Contract for the Construction of 500 Students Capacity Hostel at Western Delta University, Oghara LGA | Delta State | WEBSTER GLOBAL VENTURES LTD. |  | Building | 12 months | NDDC/EDP/UIDW/PR/DT/14/431 | 397950000
354 | December, 2014 | Award of Contract for the Installation of 1 No. 500KVA, 33/0.415KV and 1 No. 300KVA 33/0.415KV Transformer at Shower Christian High School Road, Ikwerre Ngwo, Etche LGA and Orogbom Crescent Community, Port Harcourt | Rivers State | PECANY TECHNO SOLUTIONS LTD. |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/RV/14/432 | 9000000
355 | December, 2014 | Award of Contract for the Construction of Anchor of Hope Road/Usiayor Road, Ugborikoko, Uwvie LGA | Delta State | HANWELL ENGINEERING LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/433 | 248000000
356 | December, 2014 | Award of Contract for the Construction of Tiger Crescent Road and Drains, Upper Agbarho, Ughelli South LGA | Delta State | ORBITAL RESOURCES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/434 | 250000000
357 | December, 2014 | Award of Contract for the Installation of 1 No. 300KVA 33/0.415KV Transformer at Otari Community, Abua/Odual LGA | Rivers State | SA-LINK INTEGRATED SERVICES LTD. |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/RV/14/435 | 4500000
358 | December, 2014 | Award of Contract for the Construction of Emmanuel Street, Off NTA/Apara Link Road, Obio Akpor LGA | Rivers State | SOTAK RESOURCES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/436 | 227818750
359 | December, 2014 | Award of Contract for the Installation of 4 No. 500KVA 11/0.415KV Transformer at Tombia Community, Degema LGA | Rivers State | FUBY STAR INTEGRATED SERVICES LTD. |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/RV/14/437 | 18000000
360 | December, 2014 | Award of Contract for the Shore Protection at Gio in Tai LGA | Rivers State | FIPHS INFRASTRUCTURE LTD. |  | Shore protection | 12 months | NDDC/EDP/UIDW/PR/RV/14/438 | 980000000
360 | December, 2014 | Award of Contract for the Construction of Eli Okahia Olua Internal Roads (East-West Road) at Rumuigbo, Obio Akpor LGA | Rivers State | YASMIN GLOBAL FURNITURE DEV. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/439 | 247516101
361 | December, 2014 | Award of Contract for the Construction of Pargoleens Street, Elkpokwu Town, Obio Akpor LGA | Rivers State | THE CREATOR'S CONCEPT LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/440 | 247495601
362 | December, 2014 | Award of Contract for the Construction of Cottage Hospital at Amassoma | Bayelsa State | MIKE-SPRING LOGISTICS LTD. |  | Building | 12 months | NDDC/EDP/UIDW/PR/BY/14/441 | 242500000
363 | December, 2014 | Award of Contract for the Renovation of Rivers State Police Command Armoury at Port Harcourt LGA | Rivers State | KENSTHER GLOBAL SERVICES LTD. |  | Renovation | 12 months | NDDC/EDP/UIDW/PR/RV/14/442 | 51888365.5
364 | December, 2014 | Award of Contract for the Renovation of Police Guest House, William Jumbo Street at Port Harcourt LGA | Rivers State | TECHNICS DE STOCKADE INC. |  | Renovation | 12 months | NDDC/EDP/UIDW/PR/RV/14/443 | 33910086.81
365 | December, 2014 | Award of Contract for the Construction of Solar Powered Street Light, Mereje, Okpe LGA | Delta State | INGOWET SERVICES LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/DT/14/444 | 196920573.66
366 | December, 2014 | Award of Contract for the Construction of Road with 600mm Excavation and Filling and 2 side drains at Umeri/Upper Ojekpolor Street, Boji-Boji Owa, Ika North LGA | Delta State | HONERICH COY. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/445 | 249965370
367 | December, 2014 | Award of Contract for the Construction of Kokori Internal Roads | Delta State | LAND & SEA BUSINESS SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/446 | 199188905
368 | December, 2014 | Award of Contract for the Construction of Prince Kohwo Road, Off Omo Agege Street/Court Road, Uvwie LGA | Delta State | CASH CARE LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/447 | 249950000
369 | December, 2014 | Award of Contract for the Construction of Banire Street, Akure | Ondo State | BACOY CONST. CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/ON/14/448 | 249000000
370 | December, 2014 | Award of Contract for the Construction of Road in Mopol 18, Irete in Owerri West LGA | Imo State | OTIOS & CO. NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/449 | 199595000
371 | December, 2014 | Award of Contract for the Fencing of Omuma technical Secondary School, Omuma, Oru East LGA | Imo State | PRIMEWEST PROPERTIES LTD. |  | Fencing | 12 months | NDDC/EDP/UIDW/PR/IM/14/450 | 149678500
372 | December, 2014 | Award of Contract for the Rehabilitation of Internal Roads at Imo Police Command Headquarter, Owerri Municipal LGA | Imo State | ZIEGERNETH LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/451 | 198700543
373 | December, 2014 | Award of Contract for the Bara-Kono Sandfilling and Shore Protection | Rivers State | MNY INTEGRATED SERVICES LTD. |  | Shore protection | 12 months | NDDC/EDP/UIDW/PR/RV/14/452 | 953036200
373 | December, 2014 | Award of Contract for the Construction of Yizhak Rabin School Road, Off East West Road to link New Airport Road, Rumuosi, Obio Akpor LGA | Rivers State | HOFA CONST. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/453 | 199941500
374 | December, 2014 | Award of Contract for the Dredging/Sandfilling of Olare Water Layout, Ogborikoko Community, Lot 1, Uvwie LGA | Delta State | MELITA CONST. CO. LTD. |  | Sandfilling | 12 months | NDDC/EDP/UIDW/PR/DT/14/454 | 909580911
375 | December, 2014 | Award of Contract for the Dredging/Sandfilling of Olare Water Layout, Ogborikoko Community, Lot 2, Uvwie LGA | Delta State | ASIGO CO. NIG. LTD. |  | Sandfilling | 12 months | NDDC/EDP/UIDW/PR/DT/14/455 | 899120590.15
376 | December, 2014 | Award of Contract for the Dredging/Sandfilling of Olare Water Layout, Ogborikoko Community, Lot 3, Uvwie LGA | Delta State | OMA ROCK LTD. |  | Sandfilling | 12 months | NDDC/EDP/UIDW/PR/DT/14/456 | 898980100.5
377 | December, 2014 | Award of Contract for the Dredging/Sandfilling of Olare Water Layout, Ogborikoko Community, Lot 4, Uvwie LGA | Delta State | FIRST OCEAN OIL & GAS LTD. |  | Sandfilling | 12 months | NDDC/EDP/UIDW/PR/DT/14/457 | 897750580
378 | December, 2014 | Award of Contract for the Dredging/Sandfilling of Olare Water Layout, Ogborikoko Community, Lot 5, Uvwie LGA | Delta State | MELITA CONST. CO. LTD. |  | Sandfilling | 12 months | NDDC/EDP/UIDW/PR/DT/14/458 | 899150950.8
379 | December, 2014 | Award of Contract for the Dredging/Sandfilling of Olare Water Layout, Ogborikoko Community, Lot 6, Uvwie LGA | Delta State | FIRST OCEAN OIL & GAS LTD. |  | Sandfilling | 12 months | NDDC/EDP/UIDW/PR/DT/14/459 | 887590950.95
380 | December, 2014 | Award of Contract for the Dredging/Sandfilling of Olare Water Layout, Ogborikoko Community, Lot 7, Uvwie LGA | Delta State | ASIGO CO. NIG. LTD. |  | Sandfilling | 12 months | NDDC/EDP/UIDW/PR/DT/14/460 | 897980950
381 | December, 2014 | Award of Contract for the Dredging/Sandfilling of Olare Water Layout, Ogborikoko Community, Lot 8, Uvwie LGA | Delta State | OMA ROCK LTD. |  | Sandfilling | 12 months | NDDC/EDP/UIDW/PR/DT/14/461 | 899189975.15
382 | December, 2014 | Award of Contract for the Dredging/Sandfilling of Olare Water Layout, Ogborikoko Community, Lot 9, Uvwie LGA | Delta State | FIRST OCEAN OIL & GAS LTD. |  | Sandfilling | 12 months | NDDC/EDP/UIDW/PR/DT/14/462 | 897945960.65
383 | December, 2014 | Award of Contract for the Dredging/Sandfilling of Olare Water Layout, Ogborikoko Community, Lot 10, Uvwie LGA | Delta State | FIRST OCEAN OIL & GAS LTD. |  | Sandfilling | 12 months | NDDC/EDP/UIDW/PR/DT/14/463 | 898250175
384 | December, 2014 | Award of Contract for the Dredging/Sandfilling of Olare Water Layout, Ogborikoko Community, Lot 11, Uvwie LGA | Delta State | JOUPI NIG. LTD. |  | Sandfilling | 12 months | NDDC/EDP/UIDW/PR/DT/14/464 | 909580911
374 | December, 2014 | Award of Contract for the Construction of Solar Powered Street Light, Egborode, Okpe LGA | Delta State | TOSKAT NIG. LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/DT/14/465 | 248580000
375 | December, 2014 | Award of Contract for the Construction of Abana Street Extension/ Alalibo Avenue, Old GRA, Port Harcourt | Rivers State | LYTE CONCEPTS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/466 | 247055315
376 | December, 2014 | Award of Contract for the Construction of Obi-Wali Street, NTA Mgbuoba Market Junction link Road, Obio Akpor LGA | Rivers State | AIK UNIQUE MEGA LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/467 | 186542190
377 | December, 2014 | Award of Contract for the Construction of Kings Avenue, Off Tombia Street Extension, GRA, Port Harcourt LGA | Rivers State | ACTINUM LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/468 | 247417250
378 | December, 2014 | Award of Contract for the Construction of Doxa Avenue, Of Dr. Peter Odili Road, Trans Amadi, Port Harcourt LGA | Rivers State | COMMERCE SERVICES NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/469 | 248122350
379 | December, 2014 | Award of Contract for the Construction of Solar Water Project at Kiagbodo, Burutu LGA | Delta State | FANAMA CONST. CO. LTD. |  | Solar water | 12 months | NDDC/EDP/UIDW/PR/DT/14/470 | 46950000
380 | December, 2014 | Award of Contract for the Electrification Project at Kiagbodo, Burutu LGA | Delta State | JOSAMA ENGINEERING CO. LTD. |  | Electrification | 12 months | NDDC/EDP/UIDW/PR/DT/14/471 | 99500000
381 | December, 2014 | Award of Contract for the Construction of Internal Concrete Road, Agbere, Sagbama LGA | Bayelsa State | MAYDIF ENT. NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/472 | 219436330
382 | December, 2014 | Award of Contract for the Construction of Internal Road at Effurun Army Barrack, Lot 1, Uvwie LGA | Delta State | SIRIVERE INV. NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/473 | 249350000
383 | December, 2014 | Award of Contract for the Rehabilitation of Awo-Omamma to Amiri and Nnempi Road, Lot 1 | Imo State | FRANK & GENE INT'L LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/474 | 981917416.25
384 | December, 2014 | Award of Contract for the Rehabilitation of Awo-Omamma to Amiri and Nnempi Road, Lot 2 | Imo State | CILAZ INTEGRATED SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/475 | 915425387.5
385 | December, 2014 | Award of Contract for the Rehabilitation of Awo-Omamma to Amiri and Nnempi Road, Lot 3 | Imo State | GODON DEVELOPMENT LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/476 | 983968924.75
386 | December, 2014 | Award of Contract for the Rehabilitation of Okwelle Umueshi-Isieknesi-Ntueke Road and Erosion control with Bridge (Lot 1) in Onuimo/Ideato LGA | Imo State | TIMIK ENGR. & CONST. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/477 | 983602210
387 | December, 2014 | Award of Contract for the Rehabilitation of Okwelle Umueshi-Isieknesi-Ntueke Road and Erosion control with Bridge (Lot 2) in Onuimo/Ideato LGA | Imo State | WOODSTON ENGR. & CONST. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/478 | 996989641.88
388 | December, 2014 | Award of Contract for the Rehabilitation of Okwelle Umueshi-Isieknesi-Ntueke Road and Erosion control with Bridge (Lot 3) in Onuimo/Ideato LGA | Imo State | DAYAK NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/479 | 992702584.88
389 | December, 2014 | Award of Contract for the Rehabilitation of Okwelle Umueshi-Isieknesi-Ntueke Road and Erosion control with Bridge (Lot 4) in Onuimo/Ideato LGA | Imo State | STEELCREST ENGINEERING & CONST. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/480 | 971166932.5
390 | December, 2014 | Award of Contract for the Rehabilitation of Oguta Junction, Mgbidi Umuhu/Omuma to Affor Akatta with 250 street lights (Lot 1) | Imo State | HARTON NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/481 | 512821485
391 | December, 2014 | Award of Contract for the Rehabilitation of Oguta Junction, Mgbidi Umuhu/Omuma to Affor Akatta with 250 street lights (Lot 2) | Imo State | GRAPIK LIMITED |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/482 | 481961700
392 | December, 2014 | Award of Contract for the Rehabilitation of Oguta Junction, Mgbidi Umuhu/Omuma to Affor Akatta with 250 street lights (Lot 3) | Imo State | ELKAN ZIBSON LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/483 | 934469490.88
393 | December, 2014 | Award of Contract for the Desilting of Imo Rivers in Umuahia | Abia State | TK ENGR. COY. LTD. |  | Desilting | 12 months | NDDC/EDP/UIDW/PR/AB/14/484 | 994200000
383 | December, 2014 | Award of Contract for the Construction of Internal Roads at Afor Umueze in Ehime Mbano LGA | Imo State | ZICHWOOD LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/485 | 247328750
384 | December, 2014 | Award of Contract for the Dredging/ Desilting of Imo Rivers in Onuimo and Ihitte Ubuma, Lot 1 | Imo State | N.P.G NIG. LTD. |  | Dredging | 12 months | NDDC/EDP/UIDW/PR/IM/14/486 | 994200000
384 | December, 2014 | Award of Contract for the Rehabilitation of New Haven Estate Roads, GRA, Port Harcourt | Rivers State | KANSUANA NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/487 | 99165143
385 | December, 2014 | Award of Contract for the Electrification of Community, Kolo in Ogbia LGA | Rivers State | M & E COMMUNICATIONS LTD. |  | Electrification | 12 months | NDDC/EDP/UIDW/PR/RV/14/488 | 148731223.78
386 | December, 2014 | Award of Contract for the Canalization (Tein) opening in Ogobo from Taylor Creek to Tuloba, Yenagoa LGA | Bayelsa State | PATOSKI INT'L SERV. LTD. |  | Canalization | 12 months | NDDC/EDP/UIDW/PR/BY/14/489 | 971421875
387 | December, 2014 | Award of Contract for the Canalization of (Egbebiri/Tuburu) opening in Ogobo of Obubu Creek from Taylor Creek to Orashi Rivers, Yenagoa LGA | Bayelsa State | STEVANELA INTEGRATED SERV. LTD. |  | Canalization | 12 months | NDDC/EDP/UIDW/PR/BY/14/490 | 950000000
386 | December, 2014 | Award of Contract for the Installtion of 4 nos 33 units of 500KVA transformers in Onu Omopi Community, Omerelu, Ikwerre LGA (Omele, Omike, Omuichi and Omugwere) | Rivers State | GARFIELD INTEGRATED SERVICES |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/RV/14/491 | 1800000
387 | December, 2014 | Award of Contract for the Shore Protection at Ugborodo Community (Lot 3), Warri South West LGA | Delta State | PARESA NIG. E & C LTD. |  | Shore protection | 12 months | NDDC/EDP/UIDW/PR/DT/14/492 | 770000000
388 | December, 2014 | Award of Contract for the Shore Protection at Ugborodo Community (Lot 4), Warri South West LGA | Delta State | NIGITRADE INT'L COY. LTD. |  | Shore protection | 12 months | NDDC/EDP/UIDW/PR/DT/14/493 | 814000000
389 | December, 2014 | Award of Contract for the Shore Protection at Ugborodo Community (Lot 2), Warri South West LGA | Delta State | FOXTONVILLE LTD. |  | Shore protection | 12 months | NDDC/EDP/UIDW/PR/DT/14/494 | 869000000
390 | December, 2014 | Award of Contract for the Shore Protection at Ugborodo Community (Lot 1), Warri South West LGA | Delta State | TRISAC LTD. |  | Shore protection | 12 months | NDDC/EDP/UIDW/PR/DT/14/495 | 950000000
391 | December, 2014 | Award of Contract for the Canalization/Reclamation of Ugborodo Community (Lot 1), Warri South West LGA | Delta State | HERITON TRADE LTD. |  | Canalization | 12 months | NDDC/EDP/UIDW/PR/DT/14/496 | 990000000
392 | December, 2014 | Award of Contract for the Canalization/Reclamation of Ugborodo Community (Lot 2), Warri South West LGA | Delta State | FROT PROJECT & PROCUREMENT SERV. LTD. |  | Canalization | 12 months | NDDC/EDP/UIDW/PR/DT/14/497 | 868000000
393 | December, 2014 | Award of Contract for the Canalization/Reclamation of Ugborodo Community (Lot 3), Warri South West LGA | Delta State | WESTON CHIVAS EMPORIUM LTD. |  | Canalization | 12 months | NDDC/EDP/UIDW/PR/DT/14/498 | 970000000
394 | December, 2014 | Award of Contract for the Canalization/Reclamation of Ugborodo Community (Lot 4), Warri South West LGA | Delta State | RICCARDO CONSTRUCTION NIG. LTD. |  | Canalization | 12 months | NDDC/EDP/UIDW/PR/DT/14/499 | 899000000
395 | December, 2014 | Award of Contract for the Canalization/Reclamation of Ugborodo Community (Lot 5), Warri South West LGA | Delta State | R & T CONST. LTD. |  | Canalization | 12 months | NDDC/EDP/UIDW/PR/DT/14/500 | 870000000
387 | December, 2014 | Award of Contract for the Construction of Ita Mbaba Road and environs, Shelter Afrique Estate, Uyo LGA | Akwa Ibom State | ABILITY ENGINEERING COY. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/501 | 248250639
388 | December, 2014 | Award of Contract for the Construction of Ogbesasa Street, Benin City | Edo State | YASEKA INTEGRATED CONCEPTS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/502 | 246007693
389 | December, 2014 | Award of Contract for the Provision of Safety signs, road markings and Rehabilitation of some Roads in the NDR | Regional | ASILADRREN ENGINEERING LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RG/14/503 | 943663035
389 | December, 2014 | Award of Contract for the Construction of Limit Road, Benin City, Oredo LGA | Edo State | EWOSAT INTEGRATED SERVICES |  | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/504 | 219716900
390 | December, 2014 | Award of Contract for the Installation of 2 Nos 500KVA 11/0.415KV Transformer at Eli Weligbo Community, Opposite Obio Akpor International Market | Rivers State | MACDONALD GLOBAL RESOURCES |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/RV/14/505 | 9000000
391 | December, 2014 | Award of Contract for the Installation of 1 No 500KVA 33/0.415KV and 1 No. 300KVA/ 0.415 Transformer at Yenegwe-Epie Community, Yenagoa LGA | Bayelsa State | EL-GODAMS GLOBAL SERVICES LTD. |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/BY/14/506 | 9000000
392 | December, 2014 | Award of Contract for the Construction of Idiedo Orhuworun Road linking Umunade Close, Otokutu, Ughelli South LGA | Delta State | SOLOTUS NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/507 | 99500000
393 | December, 2014 | Award of Contract for the Construction of Asaba Street Umuahia, Amuzukwu | Abia State | VIANKO OPTIMAL SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/508 | 218014085
394 | December, 2014 | Award of Contract for the Construction of Umuihie Odo-Umuanya-Ogbodi Road in Umuahia South LGA | Abia State | BESSEMBER CONST. CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/509 | 239532815
395 | December, 2014 | Award of Contract for the Construction of Internal Road Network, Federal Mdical Centre, Asaba | Delta State | LEVANT CONST. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/510 | 159150086
396 | December, 2014 | Award of Contract for the Construction of Degema-Krakrama Jetty Access Road, Asari-Toru/ Degema LGA | Rivers State | BOJACK MARINE & LOGISTICS SERV. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/512 | 187614620
397 | December, 2014 | Award of Contract for the Construction of Harold Ogbonda Street/New Layout Street, Woji Town, Obio Akpor LGA | Rivers State | PASSION BLADE SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/513 | 249348969.95
398 | December, 2014 | Award of Contract for the Construction of Otuabula II Concrete Road, Ogbia LGA | Bayelsa State | ZEDISCO INT'L INVESTMENT LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/514 | 237408140
399 | December, 2014 | Award of Contract for the Construction of Township Road Concrete Pavement at Bobougbene, Burutu LGA | Delta State | DABSKIC DREDGING & CONST. (W/A) LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/515 | 234900000
400 | December, 2014 | Award of Contract for the Construction of Rigid Pavement (Phase 3) at Abalama, Ilelema, Oporoma, Okpo and Tema, Asari Toru LGA | Rivers State | MUDSKIPPER CONST. CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/516 | 235651190
401 | December, 2014 | Award of Contract for the Construction of Road at 24th - 25th Street, DDPA Housing Estate, Effurun LGA | Delta State | CHARLECH LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/517 | 227351020.5
402 | December, 2014 | Award of Contract for the Construction of Ogbe-Eki, Dumez link Road | Delta State | JITOBS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/518 | 149000400
403 | December, 2014 | Award of Contract for the Construction of Nma O Avenue, Off Amogudu Abiriba Road | Abia State | OFATCE GLOBAL LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/520 | 198444290
404 | December, 2014 | Award of Contract for the Construction of Ohanso-Obunku Road in ukwa East LGA | Abia State | MOSHOR AFRICAN CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/521 | 238019535
405 | December, 2014 | Award of Contract for the Construction of Foundation Hotel Road with spur to Assembly of God Church, Obehie-Asa, Ukwa East LGA | Abia State | HASAPLIN CONST. CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/522 | 249758575
406 | December, 2014 | Award of Contract for the Construction of Ibiaku Ikot Ukana with Drains (Phase 2), Ikono LGA | Akwa Ibom State | KANSUANA NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/523 | 106560764.95
407 | December, 2014 | Award of Contract for the Construction of Ring Road, Umunede, Ika North East LGA | Delta State | REGINALO R & N NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/524 | 492794272.5
407 | December, 2014 | Award of Contract for the Electrification of 144 Battalion Nigerian Army, Asa | Abia State | SYLVAKIN INTEGRATED SERVICES |  | Electrification | 12 months | NDDC/EDP/UIDW/PR/AB/14/525 | 5406239.25
408 | December, 2014 | Award of Contract for the Rehabilitation of Elibrada Oduoha-Emuoha Road | Rivers State | EVOLVE INTEGRATED SERVICES |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/526 | 249875650
409 | December, 2014 | Award of Contract for the Construction of Aghalokpe/ Ajaguoyinbo Road (Lot 1), Okpe LGA | Delta State | CRUSHSTONE CONST. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/527 | 494566775
410 | December, 2014 | Award of Contract for the Sandfilling of Toru-Ndoro Town (Lot 1), Ekeremor LGA | Bayelsa State | ZEROCK CONST. NIG. LTD. |  | Sandfilling | 12 months | NDDC/EDP/UIDW/PR/BY/14/528 | 844009125
411 | December, 2014 | Award of Contract for the Sandfilling of Toru-Ndoro Town (Lot 2), Ekeremor LGA | Bayelsa State | HIGHWAYS CONST. CO. NIG. LTD. |  | Sandfilling | 12 months | NDDC/EDP/UIDW/PR/BY/14/529 | 828336000
412 | December, 2014 | Award of Contract for the Sandfilling of Toru-Ndoro Town (Lot 3), Ekeremor LGA | Bayelsa State | ZEROCK CONST. NIG. LTD. |  | Sandfilling | 12 months | NDDC/EDP/UIDW/PR/BY/14/530 | 828336000
413 | December, 2014 | Award of Contract for the Sandfilling of Toru-Ndoro Town (Lot 4), Ekeremor LGA | Bayelsa State | FRACTAL CONST. CO. NIG. LTD. |  | Sandfilling | 12 months | NDDC/EDP/UIDW/PR/BY/14/531 | 828336000
414 | December, 2014 | Award of Contract for the Sandfilling of Toru-Ndoro Town (Lot 5), Ekeremor LGA | Bayelsa State | HIGHWAYS CONST. CO. NIG. LTD. |  | Sandfilling | 12 months | NDDC/EDP/UIDW/PR/BY/14/532 | 828336000
415 | December, 2014 | Award of Contract for the Sandfilling of Toru-Ndoro Town (Lot 6), Ekeremor LGA | Bayelsa State | ZEROCK CONST. NIG. LTD. |  | Sandfilling | 12 months | NDDC/EDP/UIDW/PR/BY/14/533 | 828336000
409 | December, 2014 | Award of Contract for the Construction of Water Project at Asarama, Andoni LGA | Rivers State | JOSHERE GLOBAL NIG. LTD. |  | Water | 12 months | NDDC/EDP/UIDW/PR/RV/14/534 | 125812019.5
410 | December, 2014 | Award of Contract for the Emergency Gully Erosion Control and Construction of Road in Ikpa Town, Esit Eket LGA | Akwa Ibom State | GULF MEADOW NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/535 | 168969764
411 | December, 2014 | Award of Contract for the Installation of 1 No. 300KVA 33/0.415KV Transformer at Iquita Community, Oron LGA | Akwa Ibom State | BOND TECH NIG. |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/AK/14/536 | 4500000
412 | December, 2014 | Award of Contract for the Installation of Solar Street Light at 24th - 25th Street, DDPA Housing Estate, Ugborikoko, Uvwie LGA | Delta State | AK - LESO VENTURES |  | Solar light | 6 months | NDDC/EDP/UIDW/PR/DT/14/537 | 120000000
413 | December, 2014 | Award of Contract for the Construction of Okafor Street with spurs, Igbogene, Yenagoa LGA | Bayelsa State | MAKJOINT MARINE ENERGY LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/538 | 249309690
414 | December, 2014 | Award of Contract for the Construction of Internal Road, Kolo in Ogbia LGA | Bayelsa State | OPTIMAL STANDARD ENGR. & CONST. NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/539 | 248580000
415 | December, 2014 | Award of Contract for the Construction of Marine Road, Agoloma, Patani LGA | Delta State | ABSON NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/540 | 179213333.75
416 | December, 2014 | Award of Contract for the Supply of Electric Power and Installation of Solar Street Light along Eyo-Abasi Ebughu Road, Uboro Isong, Udung Uko LGA | Akwa Ibom State | TECHNOPAK LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/AK/14/541 | 243000000
417 | December, 2014 | Award of Contract for the Construction of Access Road at Ebekule Kingdom, Ko LGA | Bayelsa State | FEST & BEST INTERBIZ COY. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/542 | 248457060
418 | December, 2014 | Award of Contract for the Construction of Unity Road to Amiakpu Community Road, Andoni LGA | Rivers State | DIAAZ WELLSPRING RESOURCES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/543 | 845867956
418 | December, 2014 | Award of Contract for the Construction of Isiodu Road and drains in Emohua LGA | Rivers State | GAME PROJECTS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/544 | 232000000
419 | December, 2014 | Award of Contract for the Construction of Korobarezi Internal Roads, Agoloma, Patani LGA | Delta State | SBG VENTURES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/545 | 248500000
420 | December, 2014 | [5 empty] | 12 months | NDDC/EDP/UIDW/PR/DT/14/546
421 | December, 2014 | [5 empty] | 12 months | NDDC/EDP/UIDW/PR/DT/14/547
422 | December, 2014 | [5 empty] | 12 months | NDDC/EDP/UIDW/PR/DT/14/548
423 | December, 2014 | [5 empty] | 12 months | NDDC/EDP/UIDW/PR/DT/14/549
424 | December, 2014 | [5 empty] | 12 months | NDDC/EDP/UIDW/PR/DT/14/550
420 | December, 2014 | Award of Contract for the Construction of Umuchioke- Umulakwo Road, Nwangele LGA | Imo State | BRET INTEGRATED LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/551 | 239850000
421 | December, 2014 | Award of Contract for the Construction of New Government House Ring Road, Umuahia LGA | Abia State | ANDORA PLUS SERV. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/552 | 243921550
422 | December, 2014 | Award of Contract for the Dredging/Desilting of Igbo River, Mkpataku-Elua | Imo State | MIZER LOGISTICS SERVICES LTD. |  | Dredging | 12 months | NDDC/EDP/UIDW/PR/IM/14/553 | 949220780
423 | December, 2014 | Award of Contract for the Dredging/Desilting of Igbo River, Obokofia | Imo State | PACIFIC FIELDS NIG. LTD. |  | Dredging | 12 months | NDDC/EDP/UIDW/PR/IM/14/554 | 949220780
424 | December, 2014 | Award of Contract for the Dredging/Desilting of Imo River, Onuimo and Ihitte Ubuma (Lot 2) | Imo State | COTRID NIG. LTD. |  | Dredging | 12 months | NDDC/EDP/UIDW/PR/IM/14/555 | 949220780
425 | December, 2014 | Award of Contract for the Dredging of Imo River, Owerrinta | Imo State | SLOAN RIDGE LTD. |  | Dredging | 12 months | NDDC/EDP/UIDW/PR/IM/14/556 | 994815780
422 | December, 2014 | Award of Contract for the Construction of Umuduruji- Umuezealamouke, Amaigbo, Nwangele LGA | Imo State | MORTAIN NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/557 | 239850000
423 | December, 2014 | Award of Contract for the Construction of Imuwahen Avenue/Egbe Avenue, Off Gapiona Street, G.R.A, Benin City | Edo State | CHIBRONS EQUIPMENT NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/558 | 245087315
424 | December, 2014 | Award of Contract for the Construction of Umuakuchukwu Uriaba Umuezeala Afor Road and Drains in Nwangele LGA | Imo State | BURNSVILLE INTEGRATED SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/559 | 239250000
425 | December, 2014 | Award of Contract for the Construction of Road at CKC St. Paul's Isu Junction, Nwangele LGA | Imo State | STEELCREST ENGINEERING & CONST. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/560 | 244429940
426 | December, 2014 | Award of Contract for the Construction of Amukwe Dimagu Amato-Amawillie Road, Nwangele LGA | Imo State | GRAPIK LIMITED |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/561 | 244429940
427 | December, 2014 | Award of Contract for the Construction of Umuobu- Uriaba Uteke Road and Drains in Abba, Nwangele LGA | Imo State | ELKAN ZIBSON LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/562 | 244429940
428 | December, 2014 | Award of Contract for the Dredging/Desilting of Obano- Okposha Oguta Lake Waterway (Lot 1) | Imo State | EMCHAI LTD. |  | Dredging | 12 months | NDDC/EDP/UIDW/PR/IM/14/563 | 994415000
429 | December, 2014 | Award of Contract for the Dredging/Desilting of Obano- Okposha Oguta Lake Waterway (Lot 2) | Imo State | RIVERBROOK ENERGY LTD. |  | Dredging | 12 months | NDDC/EDP/UIDW/PR/IM/14/564 | 994415000
428 | December, 2014 | Construction of 2km Rigid pavement road from Okwagbe waterside Road to the main road, Okwagbe, Ughelli South LGA | Delta State | FORKEN VENTURES |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/565 | 240579550
429 | December, 2014 | Award of Contract for the Construction of Solar Powered Street Light at Ibe Street, Elekahia, Port Harcourt | Rivers State | WRIGHT INTEGRATED SERVICES |  | Solar street light | 12 months | NDDC/EDP/UIDW/PR/RV/14/566 | 247991974.52
430 | December, 2014 | Award of Contract for the Construction of Solar Powered Street Light at Elekahia, Port Harcourt | Rivers State | E S GLOBLA RESOURCES LTD. |  | Solar street light | 12 months | NDDC/EDP/UIDW/PR/RV/14/567 | 245113203.5
431 | December, 2014 | Award of Contract for the Construction of Solar Powered Street Light at Rumukalagbor, Port Harcourt | Rivers State | SKYWORTH WEST AFRICA LTD. |  | Solar street light | 12 months | NDDC/EDP/UIDW/PR/RV/14/568 | 247991974.52
432 | December, 2014 | Award of Contract for the Construction of Solar Powered Street Light at Ebubu, Eleme | Rivers State | PACIFIC FIELDS NIG. LTD. |  | Solar street light | 12 months | NDDC/EDP/UIDW/PR/RV/14/569 | 245854475
433 | December, 2014 | Award of Contract for the Construction of Solar Powered Street Light at Umuwachukwuike, Umuonyeche, Umunohu Road, Ihittee-Ubama LGA | Imo State | CHIKOVNY LTD. |  | Solar street light | 12 months | NDDC/EDP/UIDW/PR/IM/14/570 | 239500000
434 | December, 2014 | Award of Contract for the Construction of Waja Shore Protection/Nkpogu, Port Harcourt | Rivers State | SLOAN RIDGE LTD. |  | Shore Protection | 12 months | NDDC/EDP/UIDW/PR/RV/14/571 | 672397500
434 | December, 2014 | Award of Contract for the Construction of Nkpa Ring Road, Bende, LGA | Abia State | RIBBON RESOURCES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/572 | 247485440
435 | December, 2014 | Award of Contract for the Construction of Akpasak Estate Road, Uyo | Akwa Ibom State | PROXEPACK LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/573 | 248156540
436 | December, 2014 | Award of Contract for the Construction of Aghalokpe/ Ajaguoyibo Roads (Lot 2) in Okpe LGA | Delta State | EARTH METALS VENTURES |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/574 | 495130180
436 | December, 2014 | Award of Contract for the Construction of Agudama New Access Road, Yenagoa LGA | Bayelsa State | CHITEKS VENTURES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/575 | 245545940
437 | December, 2014 | Award of Contract for the Construction of Adibon Avenue, Igbogene Epie, Yenagoa LGA | Bayelsa State | OBIBI & SONS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/631 | 98744986.25
438 | December, 2014 | Award of Contract for the Reconstruction/Maintenance of NNPC Junior Staff Club Road with Drains 79th Street, Bendel Estate, Warri | Delta State | OMA ROCK LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/632 | 243419998
439 | December, 2014 | Award of Contract for the Construction of Imirigi Ring Road, Ogbia LGA | Bayelsa State | JOUPI NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/633 | 249038990
440 | December, 2014 | Award of Contract for the Reconstruction of Custom Barrack Road/Ijaw Quarters Road at Ogborikoko, Uvwie LGA | Delta State | BIBO-EBI INTEGRATED RESOURCES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/634 | 243419998
441 | December, 2014 | Award of Contract for the Construction of Asigo Road, Opposite Ovwian Grammar School, Demesi Estate in Udu LGA | Delta State | FIRST OCEAN OIL & GAS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/635 | 212572000
442 | December, 2014 | Award of Contract for the Construction of Efejuku Street/Umukoro Street/ Okpako Street and Ajiri Close, Ugolokposo in Uvwie LGA | Delta State | JULIE-MAN INT'L CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/636 | 247696565
443 | December, 2014 | Award of Contract for the Construction of Corpoers Lodge at Ogriagbene, Bomadi LGA | Delta State | FUNSMAN NIG. CO. LTD. |  | Corpers Lodge | 12 months | NDDC/EDP/UIDW/PR/DT/14/637 | 237967322
444 | December, 2014 | Award of Contract for the Construction of Cottage Hospital Emvor, Isoko North LGA | Delta State | MELITA CONST. CO. LTD. |  | Cottage Hospital | 12 months | NDDC/EDP/UIDW/PR/DT/14/638 | 218227322
445 | December, 2014 | Award of Contract for the Construction of MPP3 Road, Okurumapolo Koko, Ogbia LGA | Bayelsa State | BELEMAME NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/639 | 99694403.25
446 | December, 2014 | Award of Contract for the Construction of Okpuhu Umuahia Umuajameze Umuokpara Road, Umuahia LGA | Abia State | GINSCON CONST. CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/640 | 249214580
447 | December, 2014 | Award of Contract for the Reclamation of Ijakpa Primary School Land, Onire Ijakpa Quarters, Phase 2, Effurun, Uvwie LGA | Delta State | PEREFEPS NIG. LTD. |  | Reclamation | 12 months | NDDC/EDP/UIDW/PR/DT/14/641 | 240187250
448 | December, 2014 | Award of Contract for the Supply of Cleaner and Safer Drinking Water System in the NDDC | Regional | GREENWELL TECHNOLOGIES |  | Water System | 12 months | NDDC/EDP/UIDW/PR/RG/14/642 | 674375000
449 | December, 2014 | Award of Contract for the Canalization of Akoloba Creek, Akugbene Town (Lot 3), Bomadi LGA | Delta State | TEESET NIG. LTD. |  | Canalization | 12 months | NDDC/EDP/UIDW/PR/DT/14/643 | 941049475
450 | December, 2014 | Award of Contract for the Canalization/Reclamation of Seitoroubolou- Ekametagbene Town (Lot 1) in Bomadi LGA | Delta State | PRO'CONSULT & ENG. SERV. LTD. |  | Canalization | 12 months | NDDC/EDP/UIDW/PR/DT/14/644 | 978921875
451 | December, 2014 | Award of Contract for the Canalization of Akoloba Creek, Akugbene Town (Lot 1), Bomadi LGA | Delta State | PHILAGEF GLOBAL NIG. LTD. |  | Canalization | 12 months | NDDC/EDP/UIDW/PR/DT/14/645 | 958650625
452 | December, 2014 | Award of Contract for the Canalization of Akoloba Creek, Akugbene Town (Lot 2), Bomadi LGA | Delta State | COMPLETE UNIT LTD. |  | Canalization | 12 months | NDDC/EDP/UIDW/PR/DT/14/646 | 958650625
448 | December, 2014 | Award of Contract for the Construction of 2km Road at Kigbodo Town, Burutu LGA | Delta State | DOYE FRANK NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/647 | 249685760
449 | December, 2014 | Award of Contract for the Construction of Amaeke-Agbo Road, Umuahia LGA | Abia State | ISNERO NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/648 | 247369540
450 | December, 2014 | Award of Contract for the Construction of Umuokuzu Village Road, Umuokanne, Ohaji/Egbema LGA | Imo State | FLEETWOOD INTEGRATED SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/649 | 239840838.75
451 | December, 2014 | Award of Contract for the Construction of Roads in Mboioku Ikot Odung, Ikono LGA | Akwa Ibom State | CHINA HARBOUR ENGR. NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/650 | 239999001
452 | December, 2014 | Award of Contract for the Construction of Okpodim Road at Ulakwo, Etche LGA | Rivers State | POMARB RESOURCES NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/651 | 229562750
453 | December, 2014 | Award of Contract for the Construction of Ekezeala-Abeke Road in Isiala Mbano LGA | Imo State | GRAPIK LIMITED |  | Road | 12 months | NDDC/EDP/UIDW/PR/DIM/14/652 | 247269040
454 | December, 2014 | Award of Contract for the Construction of Umuakuchukwu Okwareke-Isu Road, Nwangele LGA | Imo State | ELKAN ZIBSON LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/653 | 245605821.25
455 | December, 2014 | Award of Contract for the Construction of Rumutanwhor/ Minita Rumuigbo Road, Ozuoba, Obio Akpor LGA | Rivers State | GOSNAG NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/654 | 239999001
456 | December, 2014 | Award of Contract for the Installation of 1 No. 300kva 33/0.415KV Transformer at Ikot Ambon Community, Obesikpo LGA | Akwa Ibom State | RSA GLOBAL RESOURCES LTD. |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/RV/14/655 | 4500000
457 | December, 2014 | Award of Contract for the Solar Powered Street Light at Oke Oka, Akoko LGA | Ondo State | YEMARK GLOBAL SERVICES |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/ON/14/656 | 249999001
458 | December, 2014 | Award of Contract for the Solar Street Light at Federal University of Technology, Akure (Phase 2), Akuru LGA | Ondo State | TEMEGS ENGR. LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/ON/14/657 | 249999001
459 | December, 2014 | Award of Contract for the Solar Street Light at Igbobini Community, Ese Odo LGA | Ondo State | DOLBAN TECHNICAL NIG. LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/ON/14/658 | 249999001
460 | December, 2014 | Award of Contract for the Solar Street Light at Beaular Street New Site, Ore, Odigbo LGA | Ondo State | FORTRESS INTER-LINK SERVICES |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/ON/14/659 | 249999001
461 | December, 2014 | Award of Contract for the Construction of Ajanuwa and Olufemisoro Street with Drains, Ondo West LGA | Ondo State | BACOY CONST. CO. NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/ON/14/660 | 249450000
462 | December, 2014 | Award of Contract for the Burutu/Forcados Pilot project for Provision of Sustainable Electricity, Lot 3 | Delta State | KEVTRICS NIG. LTD. |  | Electrification | 12 months | NDDC/EDP/UIDW/PR/DT/14/661 | 844523027.6
463 | December, 2014 | Award of Contract for the Burutu/Forcados Pilot project for Provision of Sustainable Electricity, Lot 2 | Delta State | POWERACUMEN CONSULTING LTD. |  | Electrification | 12 months | NDDC/EDP/UIDW/PR/DT/14/662 | 956252520
464 | December, 2014 | Award of Contract for the Burutu/Forcados Pilot project for Provision of Sustainable Electricity, Lot 1 | Delta State | INCOME ELECTRIX LTD. |  | Electrification | 12 months | NDDC/EDP/UIDW/PR/DT/14/663 | 998830500
462 | December, 2014 | Award of Contract for the Installation of 1 No. 300KVA 33/0.415KV Transformer at Amuzu, Oloko | Abia State | LUCHIMS CONST.CO. LTD. |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/AB/14/664 | 7227689.74
463 | December, 2014 | Award of Contract for the Construction of Iko Ekwa-Ikot Ibiok-Afaha Atai Road, Eket LGA | Akwa Ibom State | NORABLE RESOURCES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/665 | 594249705
463 | December, 2014 | Award of Contract for the Construction of Shell View Street, Rumukwurushi, Port Harcourt LGA | Rivers State | WHEED NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/666 | 159999001
464 | December, 2014 | Award of Contract for the Construction of Elimgbu-Emma-Uchay by Court Estate, Elimgbu, Port Harcourt LGA | Rivers State | JUSDISIRE NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/667 | 187909616.25
465 | December, 2014 | Award of Contract for the Extension of 33KV overhead lines from Afiesere 132/33KV Substation to Ughelli and Isiokolo Towns | Delta State | ESOP POWER LIMITED |  | Electrification | 12 months | NDDC/EDP/UIDW/PR/DT/14/668 | 845675000
466 | December, 2014 | Award of Contract for the Canalization/Reclamation of Seitoroubolou- Ekametagbene Town (Lot 2) in Bomadi LGA | Delta State | WESTON CHIVAS EMPORIUM LTD. |  | Canalization | 12 months | NDDC/EDP/UIDW/PR/DT/14/669 | 871047500
467 | December, 2014 | Award of Contract for the Construction of Roads in Ogidigben Communit Lot 1 | Delta State | LEVANT CONST. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/670 | 832292750
465 | December, 2014 | Award of Contract for the Construction of Concrete Pavement Road at Obotebe in Burutu LGA | Delta State | TAREBI VENTURES |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/672 | 229999001
466 | December, 2014 | Award of Contract for the Construction of Mobile Camp Internal Road/Ekete Inland, Ekete Community, Udu LGA | Delta State | FERGIO VENTURES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/673 | 143031375
467 | December, 2014 | Award of Contract for the Construction of Yingi/Freedom Street linking Olare layout Ijaw Quarters, Ogborikoko, Uvwie LGA | Delta State | BIBO-EBI INTEGRATED RESOURCES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/674 | 196369130
468 | December, 2014 | Award of Contract for the Construction of Roads in Ogidigben Communit Lot 2 | Delta State | HADDOCK QUEST ENGR. & CONST. NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/675 | 832292750
468 | December, 2014 | Award of Contract for the Installation of 1 No. 300KVA 33/0.415KV Transformer at Umuoru Village, Obingwa LGA | Abia State | HUMAMICH SERVICES NIG. LTD. |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/AB/14/676 | 6841984.23
469 | December, 2014 | Award of Contract for the Construction of Concrete Pavement at Police Road, Mile 11, Sagbama Town in Sagbama LGA | Bayelsa State | CEVINIKEL NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/677 | 226045195
470 | December, 2014 | Award of Contract for the Construction of Kobina Close, Off Assembly of God Church, Yenagoa LGA | Bayelsa State | TRINITY WORLD WIDE ALLIED LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/678 | 177821333
471 | December, 2014 | Award of Contract for the Construction of Concrete Landing jetty with Waiting Shed at Febugha Boat Yard, Okoroware Quarters, Ogriagbene, Bomadi LGA | Delta State | JULIE-MAN INT'L CO. LTD. |  | Landing jetty | 12 months | NDDC/EDP/UIDW/PR/DT/14/679 | 240000000
472 | December, 2014 | Award of Contract for the Installation of 1 No. 300KVA 33/0.415KV Transformer at Owaza, Ukwa West LGA | Abia State | LUCHIMS CONST.CO. LTD. |  | Transformer | 12 months | NDDC/EDP/UIDW/PR/AB/14/681 | 7625251.25
473 | December, 2014 | Award of Contract for the Construction of Okakpa/ Ohrunwhorun link Road, Off DSC Expressway, Udu LGA | Delta State | FIRST OCEAN OIL & GAS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/682 | 245785400
474 | December, 2014 | Award of Contract for the Extension of 33KV overhead line from Oghara 132/33KV substation to Western Delta University, Delta State Teaching Hospital and Koko | Delta State | CORRSERVE NIG. LTD. |  | Electrification | 12 months | NDDC/EDP/UIDW/PR/DT/14/683 | 994215993
475 | December, 2014 | Award of Contract for the Extension of 33KV overhead line from Ozoro 132/33KV substation to benefitting Communities | Delta State | MODEV NIG. LTD. |  | Electrification | 12 months | NDDC/EDP/UIDW/PR/DT/14/684 | 993279523.91
476 | December, 2014 | Award of Contract for the Extension of 33KV overhead line from Afiesere substation to Ozoro substation including a line bay (Lot 3) | Delta State | KILOWATT ENGINEERING LTD. |  | Electrification | 12 months | NDDC/EDP/UIDW/PR/DT/14/685 | 997509000
477 | December, 2014 | Award of Contract for the Extension of 33KV overhead line from Afiesere substation to Ozoro substation including a line bay (Lot 2) | Delta State | SKYVIEW POWER TECHNOLOGIES LTD. |  | Electrification | 12 months | NDDC/EDP/UIDW/PR/DT/14/686 | 997450000
478 | December, 2014 | Award of Contract for the Extension of 33KV overhead line from Afiesere substation to Ozoro substation including a line bay (Lot 1) | Delta State | INCOME ELECTRIX LTD. |  | Electrification | 12 months | NDDC/EDP/UIDW/PR/DT/14/687 | 993453744.78
479 | December, 2014 | Award of Contract for the Construction of Asaramaija-Iwokit Road, Onelga | Rivers State | HIGHWAYS CONST. CO. NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/688 | 619293530
474 | December, 2014 | Award of Contract for the Construction and Sandfilling of Road at Dimaro's Compound, Peteorugbene, Ekeremor LGA | Bayelsa State | OGBOFURUGHA NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/689 | 149440375
475 | December, 2014 | Award of Contract for the Construction of Peter Ukoh Street by God's Grace Church, Ovwian, Udu LGA | Delta State | PRETAMAKAB INTEGRATED SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/690 | 99327475
476 | December, 2014 | Award of Contract for the Construction of Foreshore Walls at Torugbene, Burutu LGA | Delta State | MELITA CONST. CO. LTD. |  | Foreshore wall | 12 months | NDDC/EDP/UIDW/PR/DT/14/691 | 239513078.15
477 | December, 2014 | Award of Contract for the Supply of Potable Water filters for the Riverine Communities | Akwa Ibom State | GREENWELL TECHNOLOGIES |  | Water System | 12 months | NDDC/EDP/UIDW/PR/AK/14/692 | 674375000
477 | December, 2014 | Award of Contract for the Construction of Comprehensive Health Centre, Oguama, Ahiazu, Mbiase LGA | Imo State | TAUBER NIG. LTD. |  | Health Centre | 12 months | NDDC/EDP/UIDW/PR/IM/14/693 | 70000000
478 | December, 2014 | Award of Contract for the Construction of Solar Powered Street Light at Oguta Agwa Ndioshimiri K. Beach, Oguta LGA | Imo State | KONSTRUCZIONE LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/IM/14/694 | 199971066
479 | December, 2014 | Award of Contract for the Construction of Ezeugo/Uga Street, Amakohia Layout, Owerri North LGA | Imo State | CILAZ INTEGRATED SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/695 | 299900000
479 | December, 2014 | Award of Contract for the Construction of Umudinma-Umuopara Road by Primary School, Eziali, Mgbidi, Orlu LGA | Imo State | FRANK & GENE ENERGY LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/696 | 199900000
480 | December, 2014 | Award of Contract for the Construction of Marine Police Station, Oguta LGA | Imo State | WEST AFRICAN TECHNOLOGICAL SERVICES LTD. |  | Marine Police station | 12 months | NDDC/EDP/UIDW/PR/IM/14/697 | 198630058.63
481 | December, 2014 | Award of Contract for the Extension of Electricity to Umuokwu New Layout/College Road, Izombe, Oguta LGA | Imo State | INDUSTRIAL DYNAMICS NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/698 | 99456483.48
482 | December, 2014 | Award of Contract for the Construction of Solar Powered Street Light at Umudike-Orie Umuobom-Amaikpa Umudike, Ideato North LGA | Imo State | AVC ENERGY LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/IM/14/699 | 199900000
483 | December, 2014 | Award of Contract for the Installation of 1 No. 500KVA 33/0.415KV Transformer at Umueze Autonomous Community, Akwete-Ndoki, Ukwa East LGA | Abia State | DINATEX ENERGY LTD. |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/AB/14/700 | 4500000
484 | December, 2014 | Award of Contract for the Construction of Rigid pavement at Sandfilled area, Ojobo Town, Burutu LGA | Delta State | MELITA CONST. CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/701 | 239031100
485 | December, 2014 | Award of Contract for the Construction of Concrete pavement Road at Preyor Road, Off Amalasa Road, Bomadi LGA | Delta State | EBIORO NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/702 | 247337990
486 | December, 2014 | Award of Contract for the Construction of Rigid pavement at Debakeme Street, urutu LGA | Delta State | GOMUSA INDUSTRIAL SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/703 | 191797605
487 | December, 2014 | Award of Contract for the Construction of Township Road Concrete Pavement/Concrete Landing jetty, Bubopagbene Town, Burutu LGA | Delta State | DABSKIC DREDGING & CONST. (W/A) LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/704 | 234849304.82
488 | December, 2014 | Award of Contract for the Construction of Barr. Ebi Angagha Street, Off Imiringi Road, Edepie, Yenagoa LGA | Bayelsa State | OKERENGIDI GLOBAL SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/705 | 149703932
489 | December, 2014 | Award of Contract for the Construction of Ughelli to Agbara Road, ughelli North LGA | Delta State | RAPHAT CORPORATE ASSOCIATES |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/706 | 249423500
490 | December, 2014 | Award of Contract for the Construction of Aladja-Isaba-Ogbe-Ojoh-Ode-Itsekiri Road/ Bridges, Phase 1, Lot 1 | Delta State | T-SILLO RESOURCES CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/707 | 789685926.65
491 | December, 2014 | Award of Contract for the Construction of Aladja-Isaba-Ogbe-Ojoh-Ode-Itsekiri Road/ Bridges, Phase 1, Lot 2 | Delta State | LAKEFIELD ENERGY SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/708 | 722857263.6
492 | December, 2014 | Award of Contract for the Construction of Aladja-Isaba-Ogbe-Ojoh-Ode-Itsekiri Road/ Bridges, Phase 1, Lot 3 | Delta State | MAJIRI NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/709 | 882763149.99
493 | December, 2014 | Award of Contract for the Construction of Aladja-Isaba-Ogbe-Ojoh-Ode-Itsekiri Road/ Bridges, Phase 1, Lot 4 | Delta State | EDY-BO INT'L LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/710 | 911071238
494 | December, 2014 | Award of Contract for the Construction of Aladja-Isaba-Ogbe-Ojoh-Ode-Itsekiri Road/ Bridges, Phase 1, Lot 5 | Delta State | LEVANT CONST. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/711 | 925907171.74
495 | December, 2014 | Award of Contract for the Construction of Aladja-Isaba-Ogbe-Ojoh-Ode-Itsekiri Road/ Bridges, Phase 1, Lot 6 | Delta State | HADDOCK QUEST ENGR. & CONST. NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/712 | 886135697.34
496 | December, 2014 | Award of Contract for the Construction of Aladja-Isaba-Ogbe-Ojoh-Ode-Itsekiri Road/ Bridges, Phase 1, Lot 7 | Delta State | GAS CONSULTING CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/713 | 940475800.09
497 | December, 2014 | Award of Contract for the Construction of Aladja-Isaba-Ogbe-Ojoh-Ode-Itsekiri Road/ Bridges, Phase 1, Lot 8 | Delta State | BULWARK CONSTRUCTION LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/714 | 879836471.86
498 | December, 2014 | Award of Contract for the Construction of Aladja-Isaba-Ogbe-Ojoh-Ode-Itsekiri Road/ Bridges, Phase 1, Lot 9 | Delta State | RICCARDO CONSTRUCTION NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/715 | 916362325
499 | December, 2014 | Award of Contract for the Construction of Aladja-Isaba-Ogbe-Ojoh-Ode-Itsekiri Road/ Bridges, Phase 1, Lot 10 | Delta State | FROT ENERGY SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/716 | 772231658.16
500 | December, 2014 | Award of Contract for the Dredging of Oniyi River, Eziama Ikeduru | Imo State | JEXSTER INVESTMENT LTD. |  | Dredging | 12 months | NDDC/EDP/UIDW/PR/im/14/717 | 849995375
490 | December, 2014 | Award of Contract for the Instalaltion of 1 No. 300KVA 33/0.415KV Transformer at Ekenna Street, Aba | Abia State | PLETHORA VENTURES |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/AB/14/718 | 4500000
491 | December, 2014 | Award of Contract for the Instalaltion of 1 No. 300KVA 33/0.415KV Transformer at Amuzukwu Ibeku Community | Abia State | HUMAMICH SERVICES NIG. LTD. |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/AB/14/719 | 4500000
492 | December, 2014 | Award of Contract for the Construction of 12 Classroom block, Assembly Hall, Fence, Laboratory block and Paving stones at St. Malachy Secondary School, Sapele, Lot 1 | Delta State | EANDER REALITY LTD. |  | Classroom block | 12 months | NDDC/EDP/UIDW/PR/DT/14/720 | 627218274.29
493 | December, 2014 | Award of Contract for the Construction of 12 Classroom block, Road and Staff quarters at St. Malachy Secondary school, Sapele, Lot 2 | Delta State | OMATODAM NIG. LTD. |  | Classroom block | 12 months | NDDC/EDP/UIDW/PR/DT/14/721 | 315137032.4
494 | December, 2014 | Award of Contract for the Construction of Shore Protection, Internal Roads and Housing Projects at Udo Community, Warri North LGA | Delta State | APLAMATUSE VENTURES |  | Shore Protection | 12 months | NDDC/EDP/UIDW/PR/DT/14/722 | 950356875
495 | December, 2014 | Award of Contract for the Construction of Ginuwa Grammar School, Gbokoda,Warri North LGA | Delta State | OCEAN EXPLORERS NIG. LTD. | last update for consultant | Building | 12 months | NDDC/EDP/UIDW/PR/DT/14/723 | 982491457.5
496 | December, 2014 | Award of Contract for the Construction of Warri Internal Roads (Ode Ugborodo), Warri South West LGA | Delta State | TRISAC NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/724 | 988070218
492 | December, 2014 | Award of Contract for the Construction of Otepe-Ovade Road 1.5km with drains, Oteweve LGA | Delta State | RICGBAN NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/725 | 201999001
493 | December, 2014 | Award of Contract for the Construction of Internal Road Network at FGC, Ikom LGA | Cross River State | SUNBIRD INVESTMENT LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/CR/14/726 | 149850421.1
494 | December, 2014 | Award of Contract for the Construction of Internal Road Network at SPCE Ntunrokim Community, Akpraobong, Ikom LGA | cross River State | WINALLY INT'L TECH. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/CR/14/727 | 199819231.31
495 | December, 2014 | Award of Contract for the Erosion Control and drainage works at Steady Flow Arangafam Knowledge Village, Nde, Ikom LGA | Cross River State | DE-PRECISE STANDING LTD. |  | Erosion control | 12 months | NDDC/EDP/UIDW/PR/CR/14/728 | 199875323
496 | December, 2014 | Award of Contract for the Construction of Eke Eziachi-Umorie Road in Orlu LGA | Imo State | MAKRICKY NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/729 | 178792992.5
497 | December, 2014 | Award of Contract for the Construction of Wilson Irene Street, Off DBS Road, Asaba, Oshimili South LGA | Delta State | UNITOP INT'L LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/730 | 199312328.67
498 | December, 2014 | Award of Contract for the Construction of Idung Atangedem-Ine Akpautong/ Atlantic Ocean Road, Lot 4, Esit Eket LGA | Akwa Ibom State | SHORELINE PROPERTIES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/731 | 989553474
499 | December, 2014 | Award of Contract for the Construction of Idung Atangedem-Ine Akpautong/ Atlantic Ocean Road, Lot 5, Esit Eket LGA | Akwa Ibom State | HAPEL NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/732 | 989553474
500 | December, 2014 | Award of Contract for the Construction of Idung Atangedem-Ine Akpautong/ Atlantic Ocean Road, Lot 6, Esit Eket LGA | Akwa Ibom State | CARLSBERG NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/733 | 993950474
501 | December, 2014 | Award of Contract for the Construction of Idung Atangedem-Ine Akpautong/ Atlantic Ocean Road, Lot 3, Esit Eket LGA | Akwa Ibom State | CRESTLINE CONST. NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/734 | 983420913.75
502 | December, 2014 | Award of Contract for the Construction of Idung Atangedem-Ine Akpautong/ Atlantic Ocean Road, Lot 2, Esit Eket LGA | Akwa Ibom State | AUTOSTRADA WORKS |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/735 | 987910763
503 | December, 2014 | Award of Contract for the Construction of Idung Atangedem-Ine Akpautong/ Atlantic Ocean Road, Lot 1, Esit Eket LGA | Akwa Ibom State | STEFANUTTI STOCKS HAPEL LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/736 | 995010763
504 | December, 2014 | Award of Contract for the Construction of Internal Roads and Drainage channels at Ugbuwangwe, Warri South LGA | Delta State | LUMAG GLOBAL NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/737 | 499028272.33
498 | December, 2014 | Award of Contract for the Construction of Ojo Street, Off Uwasota Road, Benin City LGA | Edo State | LAVENT NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/738 | 248900670
499 | December, 2014 | Award of Contract for the Installation of Solar Powered Street Light at Ayejuni Street, Off Erinje Road, Okitipupa LGA | Ondo State | ROSA DIAMENTE PROJECTS SOLUTIONS CO. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/ON/14/739 | 199999001
500 | December, 2014 | Award of Contract for the Construction of Mgbu Odudu Akpa Wede through Enyinda Int'l College Road, Ogbogoro, Obio Akpor LGA | Rivers State | MJW NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/740 | 497016431.25
500 | December, 2014 | Award of Contract for the Construction of Solar powered street light at Aleibiri Town, Phase 2, Ekeremor LGA | Bayelsa State | B2 ULTIMATE GLOBAL VENTURES |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/BY/14/741 | 220376709.58
501 | December, 2014 | Award of Contract for the Construction of Obiga Asa- Umudobia Road, Ukwa West LGA | Abia State | MJW NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/742 | 453829010.3
501 | December, 2014 | Award of Contract for the Installation of 1 No. 300KVA 11/0.415KV transformer at Ikot Etefia Ukim community, Ikot Abasi LGA | Akwa Ibom State | PROCFAM VENTURES |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/AK/14/743 | 4670325.6
502 | December, 2014 | Award of Contract for the Rehabilitation of Ogbakiri junction - Tema Road, Lot 4 | Rivers State | VALDON LOGISTICS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/744 | 983441266.96
502 | December, 2014 | Award of Contract for the Renovation and equipping of EFCC Office No. 6 Olumeni Street, Old GRA, Port Harcourt | Rivers State | EJIRON NIG. LTD. |  | Renovation | 12 months | NDDC/EDP/UIDW/PR/RV/14/745 | 210544573.05
503 | December, 2014 | Award of Contract for the Construction of Internal Road at Swall, Yenagoa LGA | Bayelsa State | STINREEN INTEGRATED SERVICES |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/746 | 225627413.7
504 | December, 2014 | Award of Contract for the Construction of Tenacious Road extension at Yenagoa LGA | Bayelsa State | EMMAEBI GLOBAL SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/747 | 225175925
505 | December, 2014 | Award of Contract for the Construction of Internal Road IN Ayakoro Town, Ogbia LGA | Bayelsa State | TAMLUX ONYINS-B NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/748 | 228002078.15
506 | December, 2014 | Award of Contract for the Solar Powered Street Light at Ekrebo Road in Isiokolo, Ethiope East LGA | Delta State | JUPITER JONES ASSOCIATES |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/749 | 186609892.85
507 | December, 2014 | Award of Contract for the Furnishing of the Prototype University Hostel at Cross River State University of Technology, Calaba LGA | Cross River State | IDEA INVESTMENT LTD. |  | Prototype University | 12 months | NDDC/EDP/UIDW/PR/CR/14/750 | 89812800
508 | December, 2014 | Award of Contract for the Provision of 132/33KV 1 No. x 40MVA Transmission substation at Afaha Ekpenedi, Esit Eket, Ibeno and Environ LGA | Akwa Ibom State | WORLDSCOPE INVEST. NIG. LTD. |  | Transformer | 12 months | NDDC/EDP/UIDW/PR/AK/14/751 | 960606375.65
508 | December, 2014 | Award of Contract for the Installation of 2 No. 500KVA, 11/0.415KV Transformer for Idoro Road Landlord Association, Uyo | Akwa Ibom State | TECHNO-TRUST ENGINEERING LTD. |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/AK/14/752 | 9000000
509 | December, 2014 | Award of Contract for the Construction of Solar Powered Street Light at Burutu Town, Burutu LGA | Delta State | JRB SOLAR INVESTMENT LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/DT/14/753 | 239999001
510 | December, 2014 | Award of Contract for the Construction of Umuduuodu-Ekiti Afor Abba Road in Nwangele LGA | Imo State | UNAG SERVICES NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/754 | 240100000
511 | December, 2014 | Award of Contract for the Construction of Debi close at Toru Ndoro, Ekeremor LGA | Bayelsa State | OKERENGIDI GLOBAL SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/755 | 234535341.5
512 | December, 2014 | Award of Contract for the Construction of Solar Powered street light at Westend Road, ugborikoko, Uvwie LGA | Delta State | SPARK SOLAR LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/DT/14/756 | 247654711
513 | December, 2014 | Award of Contract for the Installation of 3 No. 300KVA 33/0.415KV Transformer at Rumuche Emohua Akpagh, Nnata Weli Community and White House Community, Woji Town | Rivers State | SOIBIRIMAM VENTURES LTD. |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/RV/14/757 | 13500000
514 | December, 2014 | Award of Contract for the Construction of Internal Roads in Mbiabum-Ndiyan-Okpo, Ikono LGA | Akwa Ibom State | INNOVIC INTEGRATED SERV. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/758 | 398963210
514 | December, 2014 | Award of Contract for the Construction of Perimeter Fencing, Gatehouse and Installation of paving stones at Pere's Palace, Kiagbodo, Burutu LGA | Delta State | MEIN NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/759 | 106392864.6
515 | December, 2014 | Award of Contract for the Construction of Princess street/Oziegbe/Okominor street and adjoining streets, Ekpan, Uvwie LGA | Delta State | SOLOTUS NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/760 | 249250346
516 | December, 2014 | Award of Contract for the Construction of Road in Ndon Ebom linking Okobo/Oron, Uruan LGA | Akwa Ibom State | BEDANAT NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/761 | 249025613.21
517 | December, 2014 | Award of Contract for the Installation of 1 No. 300KVA 33/0.415KV Transformer at Umukalu, Ukwa West LGA | Abia State | LUCHIMS CONST.CO. LTD. |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/AB/14/762 | 6204147.97
518 | December, 2014 | Award of Contract for the Rehabilitation of Tombia Road Extension along Royal House of Grace Church, Port Harcourt LGA | Rivers State | KANSUANA NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/763 | 99822450
519 | December, 2014 | Award of Contract for the Erosion control and Bridging works at Eshi Bansan Community, Boki LGA | Rivers State | BIS 'N' INTEGRATED SERV. NIG. LTD. |  | Erosion control | 12 months | NDDC/EDP/UIDW/PR/CR/14/764 | 98581801.42
520 | December, 2014 | Award of Contract for the Construction of Solar powered street light at Isampou (Phase 3), Ekeremor LGA | Bayelsa State | B2 ULTIMATE GLOBAL VENTURES |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/BY/14/765 | 202568756.25
521 | December, 2014 | Award of Contract for the Construction of link Road between Isampou and Kalama, Kolokuma/Opokuma LGA | Bayelsa State | KENCHEZ NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/766 | 239477763.5
522 | December, 2014 | Award of Contract for the Construction of New bypass, Off Abinoko Garri market road, Mosogor Town, Ethiope West LGA LGA | Delta State | CASH CARE LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/767 | 196922712.5
523 | December, 2014 | Award of Contract for the Construction of Aragba/Okobia/ Okwelebor/Okuabude Road, Okpe LGA | Delta State | DE GOOSE DEV. & PROJECTS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/768 | 617120600
523 | December, 2014 | Award of Contract for the Construction of Rigid Pavement at Orhuworun, Udu LGA | Delta State | ROSA VOSA NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/769 | 241461050
524 | December, 2014 | Award of Contract for the Construction of Perimeter fence, Gatehouse and Generator house at Specialist Hospital, Ikom LGA | Cross River State | EMOSTRADE LTD. |  | Gate house | 12 months | NDDC/EDP/UIDW/PR/CR/14/770 | 122861911
525 | December, 2014 | Award of Contract for the Rural Electrification of Mkpat/ Orunghe Bawop Communities, Boki LGA | Cross River State | BIS 'N' JEG INTEGRATED SERV. NIG. LTD. |  | Electrification | 12 months | NDDC/EDP/UIDW/PR/CR/14/771 | 97562675.5
526 | December, 2014 | Award of Contract for the Construction of Ancillary Building at NDDC Corporate Headquarters building complex, Eastern by-pass, Port Harcourt (Lot 1) | Rivers State | MARSHLAND PROJECTS NIG. LTD. |  | Building | 12 months | NDDC/EDP/UIDW/PR/RV/14/772 | 994424652.66
527 | December, 2014 | Award of Contract for the Construction of External Civil and other works at NDDC Corporate Headquarters building complex, Eastern by-pass, Port Harcourt (Lot 2) | Rivers State | IMBE KORU & SONS NIG. LTD. |  | Building | 12 months | NDDC/EDP/UIDW/PR/RV/14/773 | 987015656.33
528 | December, 2014 | Award of Contract for the Construction of External services at NDDC Corporate Headquarters building complex, Eastern by-pass, Port Harcourt (Lot 3) | Rivers State | ALIBAR VENTURES & INV. NIG. LTD. |  | Building | 12 months | NDDC/EDP/UIDW/PR/RV/14/774 | 981978019.68
529 | December, 2014 | Award of Contract for the Itam switching station to Uyo transmission, erection of 132KV line bay to Uyo substation, 132KV DC transmission line from Ekparakwa to Ikot Ekpene and 2 x 132KV line bay extension at Ekparakwa substation - Lot 1 | Akwa Ibom State | CORRSERVE NIG. LTD. |  | Electrification | 12 months | NDDC/EDP/UIDW/PR/RV/14/775 | 997005434.25
530 | December, 2014 | Award of Contract for the Itam switching station to Uyo transmission, erection of 132KV line bay to Uyo substation, 132KV DC transmission line from Ekparakwa to Ikot Ekpene and 2 x 132KV line bay extension at Ekparakwa substation - Lot 2 | Akwa Ibom State | INCOME ELECTRIX LTD. |  | Electrification | 12 months | NDDC/EDP/UIDW/PR/RV/14/776 | 996877079.1
531 | December, 2014 | Award of Contract for the Itam switching station to Uyo transmission, erection of 132KV line bay to Uyo substation, 132KV DC transmission line from Ekparakwa to Ikot Ekpene and 2 x 132KV line bay extension at Ekparakwa substation - Lot 3 | Akwa Ibom State | KILOWATT ENGINEERING LTD. |  | Electrification | 12 months | NDDC/EDP/UIDW/PR/RV/14/777 | 995211719.25
532 | December, 2014 | Award of Contract for the Itam switching station to Uyo transmission, erection of 132KV line bay to Uyo substation, 132KV DC transmission line from Ekparakwa to Ikot Ekpene and 2 x 132KV line bay extension at Ekparakwa substation - Lot 4 | Akwa Ibom State | MODEV NIG. LTD. |  | Electrification | 12 months | NDDC/EDP/UIDW/PR/RV/14/778 | 997437736.21
533 | December, 2014 | Award of Contract for the Itam switching station to Uyo transmission, erection of 132KV line bay to Uyo substation, 132KV DC transmission line from Ekparakwa to Ikot Ekpene and 2 x 132KV line bay extension at Ekparakwa substation - Lot 5 | Akwa Ibom State | ESOP POWER LIMITED |  | Electrification | 12 months | NDDC/EDP/UIDW/PR/RV/14/779 | 998535499.92
534 | December, 2014 | Award of Contract for the Itam switching station to Uyo transmission, erection of 132KV line bay to Uyo substation, 132KV DC transmission line from Ekparakwa to Ikot Ekpene and 2 x 132KV line bay extension at Ekparakwa substation - Lot 6 | Akwa Ibom State | KEVTRICS NIG. LTD. |  | Electrification | 12 months | NDDC/EDP/UIDW/PR/RV/14/780 | 997146563.35
535 | December, 2014 | Award of Contract for the Itam switching station to Uyo transmission, erection of 132KV line bay to Uyo substation, 132KV DC transmission line from Ekparakwa to Ikot Ekpene and 2 x 132KV line bay extension at Ekparakwa substation - Lot 7 | Akwa Ibom State | POWER ACUMEN CONSULTING LTD. |  | Electrification | 12 months | NDDC/EDP/UIDW/PR/RV/14/781 | 996845189.23
536 | December, 2014 | Award of Contract for the Itam switching station to Uyo transmission, erection of 132KV line bay to Uyo substation, 132KV DC transmission line from Ekparakwa to Ikot Ekpene and 2 x 132KV line bay extension at Ekparakwa substation - Lot 8 | Akwa Ibom State | SKYVIEW POWER TECHNOLOGIES LTD. |  | Electrification | 12 months | NDDC/EDP/UIDW/PR/RV/14/782 | 997712240
537 | December, 2014 | Award of Contract for the Itam switching station to Uyo transmission, erection of 132KV line bay to Uyo substation, 132KV DC transmission line from Ekparakwa to Ikot Ekpene and 2 x 132KV line bay extension at Ekparakwa substation - Lot 9 | Akwa Ibom State | FORTRESS INTER-LINK SERVICES |  | Electrification | 12 months | NDDC/EDP/UIDW/PR/RV/14/783 | 997125103.89
538 | December, 2014 | Award of Contract for the Itam switching station to Uyo transmission, erection of 132KV line bay to Uyo substation, 132KV DC transmission line from Ekparakwa to Ikot Ekpene and 2 x 132KV line bay extension at Ekparakwa substation - Lot 10 | Akwa Ibom State | ANDAT ENERGY TECHNIQUES LTD. |  | Electrification | 12 months | NDDC/EDP/UIDW/PR/RV/14/784 | 951796692.76
526 | December, 2014 | Award of Contract for the Installation of 1 No. 500KVA 33/0.415KV Transformer at Britarch School, Amazukou Ibeku and Umuimenyi Community, Bende LGA | Abia State | OKERENGIDI GLOBAL SERVICES LTD. |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/AB/14/785 | 7060124.23
527 | December, 2014 | Award of Contract for the Construction of Internal Roads in Aduku, Sagbama LGA | Bayelsa State | GAS LINE ENGINEERING CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/by/14/786 | 243153803
528 | December, 2014 | Award of Contract for the Construction of 1Km Concrete Road at Christ the Pillar of Life Church, Off Cherubim Road, Mile 3, Port Harcourt | Rivers State | GRATEMAN STEPS INVESTMENTS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/787 | 183263759.5
529 | December, 2014 | Award of Contract for the Construction of 1Km Internal Road Network at Oruma, Ogbia LGA | Bayelsa State | DANIELLO PUOLO COY. NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/788 | 229709873
530 | December, 2014 | Award of Contract for the Construction of Road 24, Extension A Agip Estate, Obio Akpor LGA | Rivers State | EVITON GLOBAL RESOURCES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/789 | 299150190
530 | December, 2014 | Award of Contract for the Construction of 1.5km of Road 1, Extension and Road 2 Extension at Rumukparali New Layout, Obio Akpor LGA | Rivers State | WRIGHT INTEGRATED SERVICES |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/790 | 232668980
531 | December, 2014 | Award of Contract for the Provision of 2 Nos 15MVA injection substation at Uya Oron with dedicated line to Nautical College and Ibom International Airport | Akwa Ibom State | HAYMILL NIG. LTD. |  | Electrification | 12 months | NDDC/EDP/UIDW/PR/AK/14/791 | 900000000
532 | December, 2014 | Award of Contract for the Provision of 2 Nos 15MVA injection substation at Uya Oron with dedicated line to Uyo Town and Nung Udoe, Ibesikpo | Akwa Ibom State | WORLDSCOPE INVEST. NIG. LTD. |  | Electrification | 12 months | NDDC/EDP/UIDW/PR/AK/14/792 | 900000000
531 | December, 2014 | Award of Contract for the Reclamation of Ijakpa Primary School Land, Onire Ijakpa Quarter, Phase 1, Effurun in Uvwie LGA | Delta State | GETO ASSOCIATES NIG. LTD. |  | Reclamation | 12 months | NDDC/EDP/UIDW/PR/DT/14/793 | 240187250
532 | December, 2014 | Award of Contract for the Construction of Mereje/Ekoko Eroghor Road in Okpe LGA | Delta State | ARC MARINE & CIVIL CONTRACTORS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/794 | 499092080
532 | December, 2014 | Award of Contract for the Construction of Rigid Pavement on Lucky London Street, Okpe LGA | Delta State | MARA-KODY NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/795 | 249045607
533 | December, 2014 | Award of Contract for the Construction of Egbeleku, Umujaghwa Oviri Okpe to Amukpokor | Delta State | S. O. OLOTU & SONS NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/796 | 629839100
533 | December, 2014 | Award of Contract for the Construction of Edeoha Community Road with drainage | Rivers State | O'BOMA INT'L SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/797 | 195408911.75
534 | December, 2014 | Award of Contract for the Construction of Amaukwe Umudiamagu-Umuogbu Rod, Nwangele LGA | Imo State | EBIYAIFA INV. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/798 | 176469575
535 | December, 2014 | Award of Contract for the Construction of Tuomo waterfront concrete road pavement and drains, Burutu LGA | Delta State | DOYE FRANK NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/799 | 199150550
536 | December, 2014 | Award of Contract for the Construction of Ero Maho Bakery Road, Off Ekewan Road, Benin city LGA | Edo State | AMOSTER INTEGRATED SERVICES LTD. | err on ref.from here | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/800 | 145262150
537 | December, 2014 | Award of Contract for the Construction of Odu Street, Ohunmora-Oba Owan West LGA | Edo State | ARIUS WAVE OIL & GAS |  | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/801 | 195102773.75
538 | December, 2014 | Award of Contract for the Construction of Calabar - Adiabor - Creek Town road, Adiabo-Eseku to Creek town road junction axis | Cross River State | ZENITH CONST. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/CR/14/802 | 949767843
538 | December, 2014 | Award of Contract for the Rehabilitation of Upper Ekenwan Road, Benin city, Oredo LGA | Edo State | FIRST GILT LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/803 | 195897830
539 | December, 2014 | Award of Contract for the Rehabilitation of Nekpenekpen street, Benin city, Oredo LGA | Edo State | PEBBLES INT'L OIL & GAS SPECIATIES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/804 | 195897830
540 | December, 2014 | Award of Contract for the Construction of Osubi New Layout Road, Okuokoko, Okpe LGA | Delta State | WEBSTER GLOBAL VENTURES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/805 | 737995042.9
540 | December, 2014 | Award of Contract for the Construction of Umunemeze Okaiga Road, Nkwoegwu, Umuahia LGA | Abia State | OBITEX & COY. NIG. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/806 | 192129525
541 | December, 2014 | Award of Contract for the Construction of Godwin Erebor-Ogodie street, Off Country Home Motel Road, Benin city LGA | Edo State | AMASCO CONSULTANTS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/807 | 167759717.15
542 | December, 2014 | Award of Contract for the Provision of Solar Powered street light in Minimah & Iloma Communities, Opobo/Nkoro LGA | Rivers State | SOTOMINA INTEGRATED SERV. LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/RV/14/808 | 244500000
543 | December, 2014 | Award of Contract for the Construction of Omungwu Road, Ikwerre LGA | Rivers State | STREAM CONST. & EQUIPMENT LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/809 | 291726615
543 | December, 2014 | Award of Contract for the Construction of Minima Internal Road Network, Opobo/Nkoro LGA | Rivers State | T.J. OBIESIGHA MINIMAH NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/810 | 248010638
544 | December, 2014 | Award of Contract for the Construction of Aluu Internal Roads, Ikwerre LGA | Rivers State | HENCON GLOBAL LINK LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/811 | 186267500
545 | December, 2014 | Award of Contract for the Construction of Concrete road by Royal House of Grace Int'l Church, Rumueme, Obio Akpor LGA | Rivers State | STREAM CONST. & EQUIPMENT LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/812 | 190431496.25
546 | December, 2014 | Award of Contract for the Construction of Ekpegong/ Ataijong Road, Asalakiri Community, Andoni LGA | Rivers State | MALLOUS BROTHERS CONTRACTING LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/813 | 537691765.43
546 | December, 2014 | Award of Contract for the Supply of mattresses, blankets, pillows and bedspread for Nigeria Prison's services, Port Harcourt LGA | Rivers State | OROMACLIFF VENTURES |  | Supply | 6 months | NDDC/EDP/UIDW/PR/RV/14/814 | 49000000
547 | December, 2014 | Award of Contract for the Construction of Rigid Pavement at Secondary School Road, Toru-Angiama Town, Sagbama LGA | Bayelsa State | AJUHAKI LIMITED |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/815 | 357506403
548 | December, 2014 | Award of Contract for the Construction of Internal Roads in Orere Community, Lot 1, Ughelli South LGA | Delta State | DICKENS & MABEL INT'L LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/816 | 425000000
549 | December, 2014 | Award of Contract for the Construction of Internal Roads in Orere Community, Lot 2, Ughelli South LGA | Delta State | LEIGHTON SYNERGY LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/817 | 592000000
550 | December, 2014 | Award of Contract for the Construction of Internal Roads in Orere Community, Lot 3, Ughelli South LGA | Delta State | EDISON PROPERTIES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/818 | 983000000
547 | December, 2014 | Award of Contract for the Construction of Eucharistic Congress Avenue Road, Owerri Municipal LGA | Imo State | LOVIRG CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/819 | 89980000
548 | December, 2014 | Award of Contract for the Construction of Osaremwinda Street, Off Dumez Road, Ikpoba LGA | Edo State | GAPEC CONSULTANTS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/820 | 147312653.25
549 | December, 2014 | Award of Contract for the Reonstruction of Road 24 and Road 2, Federal Housing Estate, Rumueme, Port Harcourt LGA | Rivers State | CEDAR CONST. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/821 | 299650340
550 | December, 2014 | Award of Contract for the Construction of 4km Beeri Road and drains with 2 culvert in Khana LGA | Rivers State | PACEO CARRETERA NIG.LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/822 | 644932157
551 | December, 2014 | Award of Contract for the Construction of Ogoloma-Ukaya Road and drains, Rigid pavement, Andoni LGA | Rivers State | NEXT TECHNOLOGY GLOBAL SOLUTION |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/823 | 532565805
548 | December, 2014 | Award of Contract for the Construction of Awulu Market Alupa Road with drains, Eke-Eke- Awulu, Obowo LGA | Imo State | BLESSED LIFE MULTI-PURPOSE VENTURES |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/824 | 193716065
549 | December, 2014 | Award of Contract for the Construction of Nduku-Niproc Road, Arondizuogu Nduku, Ideato LGA | Imo State | POWER & ENERGY OIL TOOLS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/825 | 240091273
550 | December, 2014 | Award of Contract for the Construction of Adolor Road with drains in Egor LGA | Edo State | WINTRAKK MEGA LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/826 | 233212670
551 | December, 2014 | Award of Contract for the Construction of Esievo Lane in Enerhen, Uvwie LGA | Delta State | OILRITE ENERGY RESOURCES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/827 | 241112900
552 | December, 2014 | Award of Contract for the Construction of Glorious Street in Okuokoko in Okpe LGA | Delta State | CASH CARE LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/828 | 99573320
553 | December, 2014 | Award of Contract for the Electrification project in Okwighele community/ construction of 2 x 7.5KVA 33/11KV substation in Okpe LGA | Delta State | DOCKLOCK RESOURCES LTD. |  | Electrification | 12 months | NDDC/EDP/UIDW/PR/DT/14/829 | 238386252.4
554 | December, 2014 | Award of Contract for the Construction of Ogelegbanowei/ Raymond Street, Ogodobiri Layout, Ekpan, Uvwie LGA | Delta State | ROSA VOSA NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/830 | 228813518
555 | December, 2014 | Award of Contract for the Construction of Miller Ovedje/ Bethel Christian Oboriowo Street, Off Osubi, Okpe LGA | Delta State | DELZACK GENE INT'L LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/831 | 196327221.5
556 | December, 2014 | Award of Contract for the Rehabilitation of Technical College Road, Utagba-Ogbe-Ndokwa LGA | Delta State | PEG ULTIMATE RESOURCES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/832 | 193586937.5
557 | December, 2014 | Award of Contract for the Construction of Internal Road in Igun Ethiope East LGA | Delta State | WOKSONS INT'L LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/833 | 148301850
558 | December, 2014 | Award of Contract for the Construction of Barr. Newworld Safugha street, Off Agbamu Crescent, Effurun, UvwieLGA | Delta State | SANEWSCO INT'L LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/834 | 110051281.6
559 | December, 2014 | Award of Contract for the Construction of Regent International School Close, Off Refinery Road in UvwieLGA | Delta State | BRIDGESTONE NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/835 | 215948531.5
560 | December, 2014 | Award of Contract for the Construction of Archibong street link road, Afaha Uqua, Eket LGA | Akwa Ibom State | XXTIENCY NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/836 | 228956080
561 | December, 2014 | Award of Contract for the Construction of Anua/Ifa Ikot Okpon/Isiet Beach Road, Uyo LGA | Akwa Ibom State | MURVAL CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/837 | 899890840
561 | December, 2014 | Award of Contract for the Construction of East-West Road, Ibaka, Mbo LGA | Akwa Ibom State | V.J. & BROTHERS NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/838 | 211345800
562 | December, 2014 | Award of Contract for the Construction of Bassey Isoh road, off Aka Item road, Uyo LGA | Akwa Ibom State | TRYBES PRIME CREST CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/839 | 205000000
563 | December, 2014 | Award of Contract for the Construction of NDDC Standard Hospital at Ibiono LGA | Akwa Ibom State | EBONGSON SERVICES LTD. |  | Hospital | 12 months | NDDC/EDP/UIDW/PR/AK/14/840 | 100000000
564 | December, 2014 | Award of Contract for the Emergency rehabilitation of 33KV overhead line network from Okitipupa to Igbokoda LGA | Ondo State | STEADY ENGINEERING & CONSTRUCTION LTD. |  | Rehab. | 12 months | NDDC/EDP/UIDW/PR/ON/14/841 | 86088209.08
565 | December, 2014 | Award of Contract for the Construction of Shoreline road and bridges from Ayama-Oka-Ama Isi Ita (Phase 1 - 4km shoreline road - Lot 1 | Rivers State | FRANEZ NIG. LTD. |  | Shoreline road & Bridges | 12 months | NDDC/EDP/UIDW/PR/RV/14/842 | 941240070
566 | December, 2014 | Award of Contract for the Construction of Shoreline road and bridges from Ayama-Oka-Ama Isi Ita (Phase 1 - 650m sheet piled shoreline road - Lot 2 | Rivers State | RICCARDO CONSTRUCTION NIG. LTD. |  | Shoreline road & Bridges | 12 months | NDDC/EDP/UIDW/PR/RV/14/843 | 908772599.5
565 | December, 2014 | Award of Contract for the Construction of Toilet building at Abalama (Phase 2), Asari Toru LGA | Rivers State | BEEBEE GLOBAL VENTURES |  | Building | 12 months | NDDC/EDP/UIDW/PR/RV/14/844 | 64518544.25
566 | December, 2014 | Award of Contract for the Construction of Shoreline road and bridges from Ayama-Oka-Ama Isi Ita (Phase 1 - 325m sheet piled shoreline road - Lot 3 | Rivers State | FROT ENERGY SERVICES LTD. |  | Shoreline road & Bridges | 12 months | NDDC/EDP/UIDW/PR/RV/14/845 | 847840541.4
567 | December, 2014 | Award of Contract for the Construction of Shoreline road and bridges from Ayama-Oka-Ama Isi Ita (Phase 1 - 500m Road across swampy land and 5 x 8.7m span deck on pile bridge from Ataba Ama John - Lot 4 | Rivers State | APLAMATUSE VENTURES |  | Shoreline road & Bridges | 12 months | NDDC/EDP/UIDW/PR/RV/14/846 | 834802825.8
568 | December, 2014 | Award of Contract for the Construction of Shoreline road and bridges from Ayama-Oka-Ama Isi Ita (Phase 2 - 4km shoreline road - Lot 1 | Rivers State | RILL OIL SERVICES LTD. |  | Shoreline road & Bridges | 12 months | NDDC/EDP/UIDW/PR/RV/14/847 | 941240070
569 | December, 2014 | Award of Contract for the Construction of Shoreline road and bridges from Ayama-Oka-Ama Isi Ita (Phase 2 - 650m sheet piled shoreline road - Lot 2 | Rivers State | EMMANIQUE SERVICES LTD. |  | Shoreline road & Bridges | 12 months | NDDC/EDP/UIDW/PR/RV/14/848 | 908772599.5
570 | December, 2014 | Award of Contract for the Construction of Shoreline road and bridges from Ayama-Oka-Ama Isi Ita (Phase 2 - 3.5Km shoreline road - Lot 3 | Rivers State | RANC CONST. CO. NIG. LTD. |  | Shoreline road & Bridges | 12 months | NDDC/EDP/UIDW/PR/RV/14/849 | 831146835
571 | December, 2014 | Award of Contract for the Construction of Shoreline road and bridges from Ayama-Oka-Ama Isi Ita (Phase 2 - 600m Road and 8 x 8.75m span deck on pile bridge froma Ama John to Isita, Lot 4 | Rivers State | ATTANNU CONST. LTD. |  | Shoreline road & Bridges | 12 months | NDDC/EDP/UIDW/PR/RV/14/850 | 909239425.8
572 | December, 2014 | Award of Contract for the Construction of Ayama Mission Road and environs, Ataba, Andoni LGA | Rivers State | ATAFRANC NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/851 | 959999001
567 | December, 2014 | Award of Contract for the Construction of Okey Uzoho Street, Amakohia Layout, Owerri LGA | Imo State | UDOKA BESTMAN INT'L LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/852 | 244950000
568 | December, 2014 | Award of Contract for the Construction of Ekpo Nko Internal Roads, Ikono LGA | Akwa Ibom State | MONTMEF COY. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/853 | 499007621
568 | December, 2014 | Award of Contract for the Construction of Solar Powered water project at Nduo Eduo, Eket LGA | Akwa Ibom State | MANGROVE SWAMP CONSULT LTD. |  | Solar water | 12 months | NDDC/EDP/UIDW/PR/AK/14/854 | 99261174.95
569 | December, 2014 | Award of Contract for the Construction of Aka Ikot Udo Eno Ediene Ikono LGA | Akwa Ibom State | HARVARD INVESTMENTS & SECURITIES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/855 | 399876004.25
569 | December, 2014 | Award of Contract for the Construction of 1Km road at Block E, GRA Estate, Osongama, Uyo LGA | Akwa Ibom State | GOODNEWS TRANS CONSTRUCTION LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/856 | 105488000
570 | December, 2014 | Award of Contract for the Construction of Owen Street, Off Ikot Udoma James Town Road | Akwa Ibom State | R. E. SURUTEL LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/857 | 99080963
571 | December, 2014 | Award of Contract for the Construction of Remedial works | Akwa Ibom State | CONSECRATION LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/858 | 78402462
572 | December, 2014 | Award of Contract for the Rehabilitation of General Hospital, Ibekwe, Ikot Abasi LGA | Akwa Ibom State | WHOLEX NIG. LTD. |  | Rehab. | 12 months | NDDC/EDP/UIDW/PR/AK/14/859 | 249500000
573 | December, 2014 | Award of Contract for the Rehabilitation of Water project at Umuechem, Etche LGA | Rivers State | BIKEN GLOBAL RESOURCES LTD. |  | Water | 12 months | NDDC/EDP/UIDW/PR/RV/14/860 | 24238100
574 | December, 2014 | Award of Contract for the Installation of 1 No. 300KVA, 33/0.415KV transformer at Obuoha/Egbelu, Aba LGA | Abia State | FUBY STAR INTEGRATED SERVICES LTD. |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/AB/14/861 | 6626928.68
575 | December, 2014 | Award of Contract for the Installation of 1 No. 300KVA, 33/0.415KV transformer at Umuikukor, Asa, Ukwa WEst LGA | Abia State | FUBY STAR INTEGRATED SERVICES LTD. |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/AB/14/862 | 7605251.25
576 | December, 2014 | Award of Contract for the Construction of Ogulagha Okontu Road Network, Burutu LGA | Delta State | DE-SOLO GLOBAL RESOURCES |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/863 | 232086256.25
577 | December, 2014 | Award of Contract for the Construction of Usokun Internal Road in Degema LGA | Rivers State | SBJ UPSTREAM LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/864 | 249090173.5
578 | December, 2014 | Award of Contract for the Construction of Kokori Internal Road (Phase 2), Ethiope LGA | Delta State | RUSKAT MEDICAL INDUSTRIES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/865 | 249170980
579 | December, 2014 | Award of Contract for the Construction of Access Road linking Oloye Close/Byeziegbe street, Niger Cat | Delta State | GMG GLOBAL CONST. & DEV. CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/866 | 224196070
580 | December, 2014 | Award of Contract for the Rehabilitation of Ogbakiri Junction - Tema Road, Lot 3 | Rivers State | HIGHSPEC CONST. CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/867 | 249875650
581 | December, 2014 | Award of Contract for the Construction of Otie-Owhe to Emevor Road, Isoko North LGA | Delta State | DORSALI INVESTMENT RESOURCES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/868 | 198743680.75
582 | December, 2014 | Award of Contract for the Construction of Asphaltic road, Yeghe Gokhana LGA | Rivers State | BILLCREST NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/869 | 98623896
583 | December, 2014 | Award of Contract for the Construction of Council/Hospital Road, Patani LGA | Delta State | S. P. I. NIG. ENT. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/870 | 149865355.67
584 | December, 2014 | Award of Contract for the Construction of Arai-Obaka Concrete link road, Kolga LGA | Bayelsa State | GOJO GLOBAL RESOURCES |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/871 | 240685760
585 | December, 2014 | Award of Contract for the Construction of Adepeju Avenue, Ondo West LGA | Ondo State | BACOY CONST. CO. NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/ON/14/872 | 245612900
586 | December, 2014 | Award of Contract for the Erosion Control works at Ekeya community and Amamong, Okobo LGA | Akwa Ibom State | EWOBROS NIG. LTD. |  | Erosion control | 12 months | NDDC/EDP/UIDW/PR/AK/14/873 | 699080500
586 | December, 2014 | Award of Contract for the Installation of Solar powered street light at Atakoro/Oruko communities in Urueofong/Oruko LGA | cross River State | PROXEPACK LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/CR/14/874 | 249658560.7
587 | December, 2014 | Award of Contract for the Remedial works on Market road, Ikot Ibritam, Oruk Anam LGA | Akwa Ibom State | MANGROVE RESOURCES & LOGISTICS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/875 | 120800000
588 | December, 2014 | Award of Contract for the Installation of Solar powered street light at Ikot Okpudo, Nsit Ubium, Etinan LGA | Akwa Ibom State | UNIVERSAL ENVITEC LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/AK/14/876 | 200000000
589 | December, 2014 | Award of Contract for the Construction of Ikot Etefia-Mbiafun Nkwongo Road, Ikot Etefia, Ikono LGA | Akwa Ibom State | AGJ GLOBAL SERVICES |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/877 | 249450000
590 | December, 2014 | Award of Contract for the Construction of Aka Atan road from Aka Etinan road to Ring road | Akwa Ibom State | DUNAMIS ENGINEERING SERVICES |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/878 | 99867450
591 | December, 2014 | Award of Contract for the Installation of Solar powered street light at Busi 1 - 6 communities, Obanliku LGA | Cross River State | GRABOT NIG. LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/CR/14/879 | 249560264.5
592 | December, 2014 | Award of Contract for the Provision of Solar powered water project at Mechanic village, Ohiya, Umuahia | Abia State | MEGABIZ INTEGRATED GLOBAL NIG. LTD. |  | Solar water | 12 months | NDDC/EDP/UIDW/PR/AB/14/880 | 50000000
593 | December, 2014 | Award of Contract for the Reconstruction of Ikhi-Idumago Nta Ora road, Esan West LGA | Edo State | PETONY TECH. CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/881 | 244500000
594 | December, 2014 | Award of Contract for the Construction of Concrete pavement at Odimodi Township Road, Phase 2, Burutu LGA | Delta State | FAVOUR FIRST PROJECT LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/882 | 377242902.5
594 | December, 2014 | Award of Contract for the Construction of Chief Attan Iwuchukwu road (Amaugbara-Umukabia), Nwangele LGA | Imo State | UTILYN GLOBAL RESOURCES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/883 | 179897001
595 | December, 2014 | Award of Contract for the Installation of 1 No. 500KVA 11/0.415KV transformer at Ekurede Itsekiri community, Warri South LGA | Delta State | VECTOR OSUP GLOBAL SERVICES NIG. LTD. |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/DT/14/884 | 4500000
596 | December, 2014 | Award of Contract for the Construction of Egbelu Amaimo Internal link Road, Ikeduru LGA | Imo State | SOLERCY NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/885 | 239080776
597 | December, 2014 | Award of Contract for the Construction of Awatang-Oniong- Ikot Akpan Obioekot Nkana-Ikot Nsung road, Eastern Obolo LGA | Akwa Ibom State | USORO CONTRACTING & SUPPLIES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/886 | 698076000
597 | December, 2014 | Award of Contract for the Construction of Atai Atan Road from IBB way to Ring road, Uyo LGA | Akwa Ibom State | VIRINI NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/887 | 149500870
598 | December, 2014 | Award of Contract for the Construction of Ibiaku Ikot Udom-Eshiet-Mbiabong Edik Akrah communities, Ikono Ibiono LGA | Akwa Ibom State | CONST. & ALLIED PROJECTS CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/888 | 459080761
599 | December, 2014 | Award of Contract for the Construction of Edem Iyere-Edem Urua-Usuk Obio Edere Road, Ikono LGA | Akwa Ibom State | DAVANLA LIMITED |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/889 | 949767843
598 | December, 2014 | Award of Contract for the Rehabilitation of Water projects in AKS (various) | Akwa Ibom State | SUNAMUS NIG. LTD. |  | Water | 12 months | NDDC/EDP/UIDW/PR/AK/14/890 | 149632190
599 | December, 2014 | Award of Contract for the Construction of 2 Storey Maternity block for Pregnant women and provision of electricity services and standby generator at the University of Uyo Teaching Hospital, Uyo LGA | Akwa Ibom State | EAC CONST. LTD. |  | Building | 12 months | NDDC/EDP/UIDW/PR/AK/14/891 | 350000000
599 | December, 2014 | Award of Contract for the Installation of Solar Powered Water project at Mbon Ebre, Oruk Anam LGA | Akwa Ibom State | EKMAR VENTURES |  | Water | 12 months | NDDC/EDP/UIDW/PR/AK/14/892 | 199197800
600 | December, 2014 | Award of Contract for the Remedial works on Market road, Eket LGA (Phase 2) | Akwa Ibom State | ADY MAX NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/893 | 66813000
601 | December, 2014 | Award of Contract for the Rehabilitation of Health centre at Etip Ediene, Ikono LGA | Akwa Ibom State | CONNECTEL LTD. |  | Rehab. | 12 months | NDDC/EDP/UIDW/PR/AK/14/894 | 150000000
602 | December, 2014 | Award of Contract for the Construction of 1km road at Eket, Eket LGA | Akwa Ibom State | FOUNDATION (W.A) ENT. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/895 | 99750000
603 | December, 2014 | Award of Contract for the Remedial works on Market road, Ikot Ibritam, Oruk Anam LGA | Akwa Ibom State | MANGROVE RESOURCES & LOGISTICS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/896 | 120800000
604 | December, 2014 | Award of Contract for the Remedial works on Market road, Ikot Ibritam, Oruk Anam LGA (Phase 2) | Akwa Ibom State | QUALITY IN SERVICES INTERCONTINENTAL LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/897 | 149860360
605 | December, 2014 | Award of Contract for the Reconstruction of East West Road to Rumuagholu T-Junction, Port Harcourt | Rivers State | AGOTEZ GLOBAL SERVICES |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/898 | 230341486.25
606 | December, 2014 | Award of Contract for the Construction of Marine Road/ Rigid pavement, Patani Town, Patani LGA | Delta State | CAPSINE NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/899 | 198467532.15
607 | December, 2014 | Award of Contract for the Construction of Council/ Logistics Road, Patani LGA | Delta State | STURDY HILLS CONST. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/900 | 177664620.5
608 | December, 2014 | Award of Contract for the Construction of Oba Palace Road, Igbokoda, Ilaje LGA | Ondo State | DIVY I. T. CONSULTANTS |  | Road | 12 months | NDDC/EDP/UIDW/PR/ON/14/901 | 237249815
609 | December, 2014 | Award of Contract for the Installation of 1 No. 500KVA 33/0.415KV transformer at Government House, Umuahia LGA | Abia State | LEMANTIC & CO. CONST. NIG. LTD. |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/AB/14/902 | 7078268.23
610 | December, 2014 | Award of Contract for the Construction of Solar powered water project at Opara waterside in Ethiope East LGA | Delta State | ENVIRONMENTAL GURUS NIG. LTD. |  | Water | 12 months | NDDC/EDP/UIDW/PR/DT/14/903 | 52000000
611 | December, 2014 | Award of Contract for the Installation of 3 Nos. 300KVA 33/0.415KV transformer at OLGA | Akwa Ibom State | BERIJE TECHNICAL SERVICES |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/AK/14/904 | 13500000
612 | December, 2014 | Award of Contract for the Construction of Odionwere Street, Iguosa (1.6km), Ovia North East LGA | Edo State | DIVY I. T. CONSULTANTS |  | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/905 | 219616900
613 | December, 2014 | Award of Contract for the Renovation/Furnishing of Federal Govt. Girls College (FGGC) Clinic, Abuloma, Port Harcourt | Rivers State | IZU EASTGATE NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/906 | 55005341.25
614 | December, 2014 | Award of Contract for the Installation of 1 No. 300KVA 11/0.415KV transformer at Umungede, Isietite Oha communities, Owaza and Old Aba Road | Abia State | LAPRESSY LTD. |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/AB/14/908 | 13500000
615 | December, 2014 | Award of Contract for the Construction of Staff quarters twin storey building of 4-unit bedroom flat, Patani LGA | Delta State | DJEMPARS NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/909 | 184999001
616 | December, 2014 | Award of Contract for the Installation of 2 No. 300KVA 11/0.415KV transformer at Umulebe village, Ideato South LGA | Imo State | CAPITOLIUM VENTURES |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/IM/14/910 | 8999001
617 | December, 2014 | Award of Contract for the Construction of Iheagwa Internal roads (Phase 1), Owerri West LGA | Imo State | BESSEMBER CONST. CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/911 | 242550550
618 | December, 2014 | Award of Contract for the Installation of 1 No. 300KVA 11/0.415KV transformer at Upper Chinda/Ada George Road, Rumueme, Port Harcourt | Rivers State | FYOTEEP BUSINESS ORGANIZATION LTD. |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/RV/14/912 | 4500000
619 | December, 2014 | Award of Contract for the Construction of Nwagboso- Ntagbu-World Bank Road, Abayi, Aba | Abia State | LUCHIMS CONST.CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/913 | 144665026.25
620 | December, 2014 | Award of Contract for the Installation of 2 No. 300KVA 11/0.415KV transformer at Gba and Nyoweii villages, Bean community, Khana LGA | Rivers State | REWAMAJ NIG. LTD. |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/RV/14/914 | 9000000
621 | December, 2014 | Award of Contract for the Construction of Chief Worlu Chukwu extension roads, Rumuagholu, Port Harcourt | Rivers State | AB OHAJINETO CONCEPTS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/915 | 165622362.5
622 | December, 2014 | Award of Contract for the Construction of NDDC State office building project, Phase 2, Umuogu Isialanteke Asa | Abia State | MIGO CONSTRUCTION LTD. |  | Building | 12 months | NDDC/EDP/UIDW/PR/AB/14/916 | 532637105.46
622 | December, 2014 | Award of Contract for the Installation of 1 No. 300KVA 11/0.415KV transformer at Amaoba-Ime Amaoba Ikputu, Ikwuano | Abia State | FUBY STAR INTEGRATED SERVICES LTD. |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/AB/14/917 | 6222497.97
623 | December, 2014 | Award of Contract for the Construction of Modern Market/ link roads at Ogriagbene, Bomadi LGA | Delta State | FIRST OCEANIC GLOBAL RESOURCES LTD |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/918 | 545999001
623 | December, 2014 | Award of Contract for the Construction of Umuegwusi (Galaxy) Umuakata Road, Owaza, Ukwa West LGA | Abia State | FIRST OCEANIC GLOBAL RESOURCES LTD |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/919 | 245419797.5
624 | December, 2014 | Award of Contract for the Construction of Uzo Ekwuru Road, Ukwu Road, Phase II, Owaza, Ukwa West LGA | Abia State | LEMANTIC & CO. CONST. NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/921 | 257599550
624 | December, 2014 | Award of Contract for the Construction of Otepe-Ovade Road 1.5km with drains, Phase 2 | Delta State | A-D KEN CORPORATE ASSOCIATES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/922 | 202000000
625 | December, 2014 | Award of Contract for the Construction of Umuegwusi - Umuachara-Umueleleukwu Road, Owaza, Ukwa West LGA | Abia State | NEC CONST. & SERV. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/923 | 252060503
626 | December, 2014 | Award of Contract for the Construction of Chibuo-Egwudaelendu Ring Road, Uzuaku, Ukwa West LGA | Abia State | IMMACULATE PRINCE ENGR. WORKS NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/924 | 389368827.5
627 | December, 2014 | Award of Contract for the Construction of Umuachalaba Ekwuru Road, Ukwa West LGA | Abia State | CHRIS WILLS RESOURCES INTEGRATED LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/925 | 257599550
625 | December, 2014 | Award of Contract for the Construction of Ikatka Internal Road and drains, Ahoada East LGA | Rivers State | PIK INT'L AGENCY LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/926 | 249002367
626 | December, 2014 | Award of Contract for the Construction of Mrs Tikere Ebebi Road, Yenagoa Town, Yenagoa LGA | Bayelsa State | PEREZO PROJECTS CONST. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/927 | 242051675
627 | December, 2014 | Award of Contract for the Solar Powered street light at Ediagbon village, Egbo/Sam Agida-Kokori, Ethiope East LGA | Delta State | JUPITER JONES ASSOCIATES LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/DT/14/928 | 199999001
628 | December, 2014 | Award of Contract for the Solar Powered street light at Erusegbele/Ijgbale Street, Effurun, Uvwie LGA | Delta State | HAMALOCK NIG. LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/DT/14/929 | 249654711
629 | December, 2014 | [6 empty] | NDDC/EDP/UIDW/PR/AK/14/930
630 | December, 2014 | [6 empty] | NDDC/EDP/UIDW/PR/AK/14/931
631 | December, 2014 | [6 empty] | NDDC/EDP/UIDW/PR/AK/14/932
629 | December, 2014 | Award of Contract for the Construction of Onicha Ugbo Idumuje Unor | Delta State | A.A. AKIMO CONST. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/933 | 244767090
630 | December, 2014 | Award of Contract for the Construction of Internal Roads at Govt. Hospital, Ogriagbene, Bomadi LGA | Delta State | BOLOUPESIBO & SONS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/934 | 249690931
631 | December, 2014 | Award of Contract for the Construction of Concrete pavement of the sandfilled area, Ojobo Town | Delta State | EASTEND PET. CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/935 | 249400870
632 | December, 2014 | Award of Contract for the Construction of Rigid pavement at Gbesa Grammar School Premises, Ojobo Town, Burutu LGA | Delta State | KIFATAL CONCEPT LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/936 | 234012467
633 | December, 2014 | Award of Contract for the Construction of Egbelu-Umungede Road, Owaza, Ukwa West LGA | Abia State | FIPHS INFRASTRUCTURE LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AB/14/937 | 600008200
634 | December, 2014 | Award of Contract for the Provision of solar powered street light at Okopedi, Oron Federal Constituency, Okobo LGA | Akwa Ibom State | A.A. ONYEONORO & SONS ENT. NIG. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/AK/14/938 | 75000000
635 | December, 2014 | Award of Contract for the Construction of Civic Centre at Itu, Itu LGA | Akwa Ibom State | BOND & BOND LTD. |  | Civic centre | 12 months | NDDC/EDP/UIDW/PR/AK/14/939 | 179000000
636 | December, 2014 | Award of Contract for the Installation of Solar powered street light at Ikot Eder village, Onna LGA | Akwa Ibom State | BEMAC INVESTMENT LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/AK/14/940 | 235000000
637 | December, 2014 | Award of Contract for the Construction of Ndukpoise junction - Ikot Essien village, Nsit Ubiom LGA | Akwa Ibom State | ABOVE ENGR. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/941 | 219008900
638 | December, 2014 | Award of Contract for the Construction of Ikot Itie-Idung Road, Nsit Atai LGA | Akwa Ibom State | IMATA GLOBAL VENTURES |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/942 | 149650000
639 | December, 2014 | Award of Contract for the Construction of Internal Road in Mbioto Ekpene Ituen, Etinan LGA | Akwa Ibom State | GASSONS NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/943 | 499500000
640 | December, 2014 | Award of Contract for the Construction of Ikot Esang-Ikot Akpan Nko Atiamkpat Ikot Ese Isiet, Ikot Esang, Onna LGA | Akwa Ibom State | DUNAMIS NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/944 | 849978430
639 | December, 2014 | Award of Contract for the Construction of 1km Road with 2 side drains at Ukara Ikot Ofok Road, Essien Udium LGA | Akwa Ibom State | BACK-UP ENGINEERS LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/945 | 149778041
640 | December, 2014 | Award of Contract for the Construction of New Woji Layout, Phases 1 & 2, Woji, Obio Akpor LGA | Rivers State | DILDAY INTEGRATED SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/946 | 199883250
641 | December, 2014 | Award of Contract for the Construction of Ekrehavwie/Oguname/Ophori, Ughelli North LGA | Delta State | EXTREME ENGINEERING LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/947 | 199999001
642 | December, 2014 | Award of Contract for the Construction of |  | JUSTIO NIG. LTD. | pending for now |  | 12 months | NDDC/EDP/UIDW/PR/AK/14/948
643 | December, 2014 | Award of Contract for the Construction of Umu-Ebereke Road, Off Omusoya Road, High Tension, Oyigbo LGA | Rivers State | DIAMOND & DAVID INTEGRATED SERVICES NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/949 | 249341116
644 | December, 2014 | Award of Contract for the Construction of 1km Road with 2 side drains at Ide Ikot Udo Road, Obot Akara LGA | Akwa Ibom State | VEPAK GLOBAL INVESTMENT LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/950 | 149006870
645 | December, 2014 | Award of Contract for the Construction of 1km Road with 2 side drains at Ikot Edem Road | Akwa Ibom State | FREKEM MERCANTILE LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/951 | 149804321
646 | December, 2014 | Award of Contract for the Construction of Etim Ekpo - Ukanafun Road, Oruk Anam LGA | Akwa Ibom State | VOLTA CONST. CO. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/952 | 99156213
647 | December, 2014 | Award of Contract for the Construction of Ntiat Itam Internal Roads, Itu Ntiat, Itu LGA | Akwa Ibom State | TOPICFIELD GLOBAL LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/953 | 378143009
648 | December, 2014 | Award of Contract for the Solar Powered street light at Oku Iboku communities, Itu LGA | Akwa Ibom State | RELIANCE FACILITIES & INFRASTRUCTURES LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/AK/14/1000 | 366331742.45
649 | December, 2014 | Award of Contract for the Solar Powered street light at Abak Federal Constituency, Abak LGA | Akwa Ibom State | PEARL TRINITIES OVERSEAS LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/AK/14/1001 | 231040396.06
650 | December, 2014 | Award of Contract for the Solar Powered street light along Eyoabasi Ebughu Road, Isong Inyang-Ebughu, Mbo LGA | Akwa Ibom State | GLOBAL ADVANCED TECHNIQUES LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/AK/14/1002 | 242000000
651 | December, 2014 | Award of Contract for the Provision of Solar Powered street light at Enwang, Mbo LGA | Akwa Ibom State | VESICA INT'L TECHNOLOGIES LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/AK/14/1003 | 242000000
652 | December, 2014 | Award of Contract for the Provision of Solar Powered street light at Akamkpa Town LGA | Cross River State | LA NIG. LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/CR/14/1004 | 240814712
653 | December, 2014 | Award of Contract for the Construction of Okpanam-Ibusa link road | Delta State | MEBLEY & ASSOCIATES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/1005 | 244950000
654 | December, 2014 | Award of Contract for the Construction of Ugolo/Osubi Road | Delta State | RIC & SO TECHNICAL SERVICES LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/DT/14/1006 | 348076318
654 | December, 2014 | Award of Contract for the Construction of Austin Cosmos Road, Aboh Mbaise LGA | Imo State | STEELFORCE ENGINEERING & CONST. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/1007 | 99095950
655 | December, 2014 | Award of Contract for the Construction of Mini Stadium at the University of Uyo, Uyo LGA | Akwa Ibom State | EDINBURGH VENTURES NIG. LTD. |  | Stadium | 12 months | NDDC/EDP/UIDW/PR/AK/14/1008 | 99500000
656 | December, 2014 | Award of Contract for the Installation of Solar Powered street light at Ikot Ekpene, Phase 2, Ikot Ekpene LGA | Akwa Ibom State | MOUNTAINS & VALLEYS CONST. LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/AK/14/1009 | 230000000
657 | December, 2014 | Award of Contract for the Installation of Solar Powered street light at Umuagbai, Oyigbo LGA | Rivers State | TAMSONG NIG. LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/RV/14/1010 | 249500000
658 | December, 2014 | Award of Contract for the Installation of Solar Powered street light along Polytechnic Road, Bori/Khana LGA | Rivers State | BERIJE TECHNICAL SERVICES |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/RV/14/1011 | 89500000
659 | December, 2014 | Award of Contract for the Installation of Solar Powered street light at Akpet Central, Biase LGA | Cross River State | TECHPRO CONSULTS LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/AK/14/1012 | 74852684
660 | December, 2014 | Award of Contract for the Installation of Solar Powered street light at Okolomade, Abua/Odual LGA | Akwa Ibom State | EDINBURGH VENTURES NIG. LTD. |  | Stadium | 12 months | NDDC/EDP/UIDW/PR/RV/14/1013 | 234500000
661 | December, 2014 | Award of Contract for the Installation of Solar Powered street light at Eneka, Obio Akpor LGA | Rivers State | MEIN NIG. LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/RV/14/1014 | 219500000
662 | December, 2014 | Award of Contract for the Installation of Solar Powered street light at Ambassador Iyalla Layout, Port Harcourt | Rivers State | EBICHUS NIG. LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/RV/14/1015 | 244500000
663 | December, 2014 | Award of Contract for the Construction of Rigid pavement internal road at Amawu Street, Off Upper Sakponba Road, Okha | Edo State | DARANTS SYSTEMS LTD |  | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/1016 | 279450000
663 | December, 2014 | Award of Contract for the Construction of 2.5km Obobosa Street and adjoining three lanes, Off Omokaro Road, Ogida quarters, Benin City | Edo State | CLEAN SLATE NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/1017 | 175058355
664 | December, 2014 | Award of Contract for the Provision of Solar powered street light at Bebi Communities and Federal College of Education, Obudu, Bebi Campus, Obudu LGA | Cross River State | MIMSHAK MARINE LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/CR/14/1018 | 244999001
665 | December, 2014 | Award of Contract for the Provision of Solar powered street light at Mbak Atai Community, Itu LGA | Akwa Ibom State | KEMSON OIL NIG. LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/AK/14/1019 | 99999001
666 | December, 2014 | Award of Contract for the Provision of Solar powered street light from Afor Market to St. Mary Hospital, Ugwashi-Uku | Delta State | VALERIE VALUES NIG. LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/DT/14/1020 | 240000000
667 | December, 2014 | Award of Contract for the Construction of 3km Osaro/Roland, Obanor/Ugiokhen Street, Behind B.I.U., GRA, Benin City | Edo State | AQUA AIR GLOBAL RESOURCES NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/1021 | 238650550
668 | December, 2014 | Award of Contract for the Erosion control works at Eburutu Army Barracks, Calabar (Lot 1) | Cross River State | ZENITH CONST. LTD. |  | Erosion control | 12 months | NDDC/EDP/UIDW/PR/CR/14/1022 | 720457090
669 | December, 2014 | Award of Contract for the Erosion control works at Eburutu Army Barracks, Calabar (Lot 2) | cross River State | ZENITH CONST. LTD. |  | Erosion control | 12 months | NDDC/EDP/UIDW/PR/CR/14/1023 | 720457090
668 | December, 2014 | Award of Contract for the Construction of Solar powered street light at Bubrugbene, Burutu LGA | Delta State | DABSKIC DREDGING & CONST. (W/A) LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/DT/14/1024 | 148978760
669 | December, 2014 | Award of Contract for the Construction of Solar powered street light at Chief Frank Nweke Layout NTA, Ozuoba, Obio Akpor LGA | Rivers State | B4A INTEGRATED SERVICES |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/RV/14/1025 | 229807334
670 | December, 2014 | Award of Contract for the Construction of Bulu-Orua-Agoro Road, Sagbama LGA | Bayelsa State | ATUP ENGINEERING LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/1026 | 839528643
670 | December, 2014 | Award of Contract for the Construction of 2km Road at Yenagoa Estate, Off Abacha Road, Phase 2, Okaka/Epie, Yenagoa LGA | Bayelsa State | L. AYEJU ASSOCIATES & SUPPLY LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/BY/14/1027 | 239500000
671 | December, 2014 | Award of Contract for the Dredging for Flood control in Afaha Eket | Akwa Ibom State | RHEMALLYCX NIG. LTD. |  | Dredging | 12 months | NDDC/EDP/UIDW/PR/AK/14/1050 | 799500
672 | December, 2014 | Award of Contract for the Construction of 114 Road, Street light close in Ohia Igba Rumuapu Rukpokwu | Rivers State | QUALITY SYNERGY INVESTMENT SERVICES NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/1051 | 219550743.75
673 | December, 2014 | Award of Contract for the Solar Powered water Project at Umuogalaba Owaza, Ukwa West LGA | Abia State | RUTOCHAN GLOBAL RESOURCES |  | Solar water | 12 months | NDDC/EDP/UIDW/PR/AB/14/1051 | 49999001
674 | December, 2014 | Award of Contract for the Construction of Umuorobara Akpotu Road, Aboh Mbaise LGA | Imo State | DABCON CONST. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/1052 | 179500000
675 | December, 2014 | Award of Contract for the Installation of 1 No. 300KVA 11/0.415KV transformers at Umungede, Isietite Oha communities, Owaza and Old Aba Road | Abia State | OBODAVE INTEGRATED SERVICES LTD. |  | Transformer | 12 months | NDDC/EDP/UIDW/PR/AB/14/1052 | 6240641.97
676 | December, 2014 | Award of Contract for the Construction of Omadi Egbuoma-Ohakpu Road, Omadi Eguoma, Oguta LGA | Imo State | BENROSE GLOBAL INTEGRATED COY. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/1053 | 179446130
677 | December, 2014 | Award of Contract for the Construction of Wire Road, Ubiaa, Esan South East LGA | Edo State | JEKCONS NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/1053 | 299500000
677 | December, 2014 | Award of Contract for the Construction of Umuokwuaba Owerre Ebeiri Road in Orlu LGA | Imo State | MACSLO INT'L LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/1054 | 179500000
678 | December, 2014 | Award of Contract for the Construction of Government Girls secondary School Road in Ogbonna, Etsako Central | Edo State | VI-DONNEL INVESTMENT & CAPITAL DEV. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/1054 | 229500600
679 | December, 2014 | Award of Contract for the Construction of Umuchukwu-Anunu Umuezealagbe Road (Unity Road) in Ukukluwe Ajirija, Isiala Mbano LGA | Imo State | DATASCAN CONSULT INT'L LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/1055 | 214009800
680 | December, 2014 | Award of Contract for the Provision of Solar Powered street light at Otefe-Ovade, Ethiope West LGA | Delta State | TAGBAS TECHNICAL NIG. LTD. |  | Solar light | 12 months | NDDC/EDP/UIDW/PR/DT/14/1055 | 149750562
681 | December, 2014 | Award of Contract for the Installation of 1 No. 300KVA 11/ 0.415KV Transformer at Elipokwu-Du Okporo II, Rukpokwu, Obio Akpor LGA | Rivers State | OXBOW RESOURCES SERVICES INTEGRATED LTD. |  | Transformer | 6 months | NDDC/EDP/UIDW/PR/RV/14/1056 | 4500000
682 | December, 2014 | Award of Contract for the Construction of Hospital Road in Ovbiogie community, Orhionmwon LGA | Edo State | JEKCONS NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/ED/14/1056 | 99500000
683 | December, 2014 | Award of Contract for the Construction of Okochiri Internal Roads, Okrika LGA | Rivers State | SE-KURO NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/RV/14/1057 | 779101600
684 | December, 2014 | Award of Contract for the Construction of Ekeng Evoa Convent Street | Cross River State | SBJ UPSTREAM LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/CR/14/1058 | 395500000
685 | December, 2014 | Award of Contract for the Construction of Nze Ezeugo Street, Amakohia, Owerri North LGA | Imo State | SONGRATIS NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/1059 | 295000000
686 | December, 2014 | Award of Contract for the Construction of Mbiaya Uruan Road, Uruan LGA | Akwa Ibom State | DRILEX OIL NIG. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/AK/14/1060 | 199500000
687 | December, 2014 | Award of Contract for the Construction of Samuel Akinbolaji Oladepo Estate Road at Ondo Town, Ondo WEST LGA | Ondo State | ENITY VENTURES |  |  | 12 months | NDDC/EDP/UIDW/PR/ON/14/1062
687 | December, 2014 | Award of Contract for the Construction of Afor Amazu Amaegbu Road in Orsu LGA | Imo State | SPANISH CONST. COY. LTD. |  | Road | 12 months | NDDC/EDP/UIDW/PR/IM/14/1101 | 233500000
325152353982.1201

## NCS
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) : |  | NIGERIA CUSTOMS SERVICE
MINISTRY :
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2014 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | DRILLING OF BOREHOLE AND CONSTRUCTION OF GROUND AND OVERHEAD WATER TANK AT KATSINA ALA BORDER STATION, BENUE STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 14500000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS MASY NIG. LTD. | 2014-12-23 | 12011076 | 4 WEEKS | 2015-04-30 | 0 | 2015-05-28 | COMPLETED | 0% | NA | NIL
2 | SUPPLY AND INSTALLATION OF 60KVA SOUND PROOF PERKINS GENERATOR AT KANGIWA BORDER STATION, KEBBI STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 100000000 | OPEN | 2014-11-25 | 2014-12-18 | 14200000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS OL-YEM ASSOCIATES | 2014-12-24 | 12480200 | 5 WEEKS | 2015-06-11 | 0 | 2015-07-09 | COMPLETED | 0% | NA | NIL
3 | RENOVATION OF 2 NOS. 6-UNITS FLAT AT IFONYITEDO, OGUN STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 80000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS BUILDSTRUCT NIG. LTD. | 2014-12-23 | 55192914 | 16 WEEKS | 2015-05-18 | 0 | 2015-09-07 | ON-GOING | 0% | NA | NIL
4 | CONSTRUCTION OF FENCING AND GATE HOUSE AT PLOT 63, URATTA HOUSING ESTATE, OWERRI, IMO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 40000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ANDY JOES GROUP NIG. LTD. | 2014-12-24 | 17800200 | 8 WEEKS | 2015-03-17 | 0 | 2015-05-12 | COMPLETED | 0% | NA | NIL
5 | SUPPLY AND INSTALLATION OF 60KVA SOUND PROOF PERKINS GENERATOR AT MAJE BORDER STATION, KEBBI STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 100000000 | OPEN | 2014-11-25 | 2014-12-18 | 16500000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS M-SQUARE FURNISHING LTD. | 2014-12-24 | 9750000 | 6 WEEKS | 2015-05-28 | 0 | 2015-07-09 | COMPLETED | 0% | NA | NIL
6 | RENOVATION OF 1 NO. 30 MAN RANK AND FILE AT ABEOKUTA,OGUN STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 80000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS BABJAM NIG. LTD. | 2014-12-27 | 98292372.1 | 12 WEEKS | 2015-01-22 | 0 | 2015-04-09 | COMPLETED | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
7 | CONSTRUCTION OF RESTRUCTURED AND REMODELED 30 MAN RANK AND FILE BUILDING AT ABEOKUTA, OGUN STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 411478571.43 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ETSOLA NIG. LTD. | 2014-12-23 | 378250000 | 36 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
8 | RENOVATION OF ABANDONED GOVERNMENT WAREHOUSE BUILDING AT ABEOKUTA, OGUN STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 40000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS G IS GOOD VENTURES LTD. | 2014-12-23 | 23100150 | 6 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
9 | CONSTRUCTION OF BOY’S QUARTERS, FENCING AND LANDSCAPING OF NEWLY COMPLETED AREA COMPTROLLER’S QUARTERS, ABEOKUTA, OGUN STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 60000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS HEN-MID CONCEPT NIG. LTD | 2014-12-23 | 66143000 | 20 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
10 | RENOVATION AND FURNISHING OF COMMANDANT’S QUARTERS AT CUSTOMS TRAINING COLLEGE, IKEJA – LAGOS | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 39780120 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS CELADON SERVICES NIG. LTD. | 2014-12-23 | 39780120 | 12 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | FUNDED FROM OVERHEAD
11 | RENOVATION OF OFFICE BLOCK AT ALARI OUTSTATION, OGUN STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 40000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ENNKA ELECTRICAL AND GENERAL SERVICES NIG. LTD. | 2014-12-23 | 25400100 | 7 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
12 | RENOVATION OF OFFICE BLOCK AT IJOUN, OGUN STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 15000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS SATCHMORE BUSINESS DIMENSIONS | 2014-12-23 | 13780100 | 4 WEEKS | 2015-02-05 | 0 | 2015-03-05 | ON-GOING | 0% | NA | NIL
13 | RENOVATION OF 1 NO. 3 UNITS 2-BEDROOM FLAT AT ALARI, OGUN STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 30000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ERNYSON CONSTRUCTION AND ENGINEERING LTD. | 2014-12-23 | 31050100 | 10 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
14 | RENOVATION OF 3 NOS. 1-BEDROOM FLAT ALARI STATION, OGUN STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 45000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ORAL NIG. ENTERPRISES | 2014-12-31 | 20050000 | 8 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
15 | RENOVATION OF 1 NO. 27 MAN RANK AND FILE IDIROKO, OGUN STATE LOT ‘A’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 50000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ZOMAX NIG. LTD. | 2014-12-23 | 98918268.5 | 12 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
16 | RENOVATION OF 1 NO. 27 MAN RANK AND FILE IDIROKO, OGUN STATE LOT ‘B’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 50000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ARDEM NIG. CO. LTD. | 2014-12-23 | 99280000 | 16 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
17 | RENOVATION OF 1 NO. 27 MAN RANK AND FILE IDIROKO, OGUN STATE LOT ‘C’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 50000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS MUSTAGLASS NIG. LTD. | 2014-12-23 | 101250000 | 16 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
18 | RENOVATION OF 2 NOS. 6 UNITS 1-BEDROOM FLAT AT IDOPETU, OGUN STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 100000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS DRABBLE NIG. LTD. | 2014-12-23 | 34890500 | 12 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
19 | RENOVATION OF 2 NOS. 2-BEDROOM AND OFFICE BLOCK AT IDOPETU, OGUN STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 40000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS A&S NIG. LTD. | 2014-12-23 | 29850000 | 12 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
20 | RENOVATION OF 1 NO. 6 ROOMS BUNGALOW AT IMEKO, OGUN STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 40000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ADEFORTS NIG. LTD. | 2014-12-23 | 20140200 | 6 WEEKS | 2015-06-23 | 0 | 2015-08-04 | ON-GOING | 0% | NA | NIL | REQUEST PAYMENT OF VALUATION
21 | RENOVATION OF 1 NO. 4 ROOMS OFFICE AT ILARA, IMEKO, OGUN STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 30000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS TUNNER NIG. LTD. | 2014-12-23 | 15850000 | 4 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
22 | RENOVATION OF GOVERNMENT WAREHOUSE AND ARMOURY AT IBADAN, OYO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 80000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS SATRAD NIG LTD. | 2014-12-23 | 42850000 | 10 WEEKS | 2015-02-24 | 0 | 2015-05-05 | ON-GOING | 0% | NA | NIL
23 | RENOVATION OF MECHANICAL WORKSHOP AND CLINIC AT IBADAN, OYO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 50000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS MAXMILL LTD. | 2014-12-23 | 30150200 | 6 WEEKS | 2015-03-12 | 0 | 2015-04-23 | ON-GOING | 0% | NA | NIL
24 | RENOVATION OF CUSTOMS HOUSE, IBADAN, OYO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 400000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS S.E.A. KEN INT. LTD | 2014-12-23 | 401516000 | 24 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
25 | RENOVATION OF 6 UNITS 2-BEDROOM SEMI DETACHED AT IJOKODO, OYO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 80000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS FUNGET CONCEPT LTD. | 2014-12-23 | 74020100 | 10 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
26 | RENOVATION OF OFFICE COMPLEX, OSHOGBO, OSUN STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 80000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS JOLOW NIG. LTD. | 2014-12-23 | 46780100 | 14 WEEKS | 2015-07-01 | 0 | 2015-08-07 | ON-GOING | 0% | NA | NIL
27 | RENOVATION OF 3 NOS. 3-BEDROOM APARTMENT AT OSHOGBO, OSUN STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 60000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS A.O. OHIKHENA & ASSOCIATES NIG. LTD. | 2014-12-23 | 47106200.33 | 12 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
28 | RENOVATION OF OFFICERS MESS, SEME BADAGRY, LAGOS | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 40000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS JOLOW NIG. LTD. | 2014-12-23 | 20100150 | 5 WEEKS | 2015-07-10 | 0 | 2015-08-14 | ON-GOING | 0% | NA | NIL
29 | DRILLING OF BOREHOLE AND CONSTRUCTION OF GROUND AND OVERHEAD WATER TANK AT IJOFIN WATER SIDE OUTSTATION, OGUN STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 14150000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS TREYD ALLIANCE COMPANY LTD. | 2014-12-24 | 14750100 | 6 WEEKS | 2015-06-29 | 0 | 2015-08-10 | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
30 | DRILLING OF BOREHOLE AND CONSTRUCTION OF GROUND AND OVERHEAD WATER TANK FOR 30 MAN RANK AND FILE AT AKURE, ONDO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 14340000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ETSOLA NIG. LTD. | 2014-12-23 | 14340000 | 6 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | FUNDED FROM OVERHEAD
31 | SUPPLY AND INSTALLATION OF 350KVA SOUND PROOF GENERATOR TO TIN-CAN ISLAND AREA COMMAND | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 22000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS VISIBLE GLOBAL CONCEPT LTD. | 2014-12-24 | 27101100 | 10 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
32 | SUPPLY AND INSTALLATION OF 100KVA SOUND PROOF GENERATOR TO CUSTOMS AREA OFFICE, OSHOGBO, OSUN STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 100000000 | OPEN | 2014-11-25 | 2014-12-18 | 14200000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS MICANS NIG. LTD. | 2014-12-23 | 14100250 | 8 WEEKS | 2015-02-04 | 0 | 2015-04-01 | COMPLETED | 0% | NA | NIL
33 | SUPPLY AND INSTALLATION OF 100KVA SOUND PROOF GENERATOR TO CUSTOMS BARRACKS, IJOKODO, OYO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 100000000 | OPEN | 2014-11-25 | 2014-12-18 | 22300000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS MUSWAD GIDAD NIG. LTD. | 2014-12-24 |  | 6 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
34 | CONSTRUCTION AND SUPPLY OF 2 NOS. 13 METRE LONG MULTIROLE FAST INTERVENTION PATROL CRAFTS (BOATS) FOR ANTI-SMUGGLING ACTIVITIES ALONG THE WATER WAYS/CRACKS FOR WESTERN MARINE COMMAND, IBAFON, APAPA – LAGOS | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 1000000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS PORTPLUS LTD. | 2014-12-24 | 882150750 | 12 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
35 | CONSTRUCTION AND SUPPLY OF 2 NOS. SOLARS APPROVED RIGID INFLATABLE BOATS (RIBS) (4.5 METERS RIB WITH 6 CREW MEMBERS WITH YAMAHA ENGINE) AT WESTERN MARINE COMMAND, LAGOS STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 50500100 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS MATHAS INT. LTD. | 2014-12-23 | 50500100 | 14 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | FUNDED FROM OVERHEAD
36 | CONSTRUCTION OF RESTRUCTURED AND REMODELLED 30 MAN RANK AND FILE BUILDING AT KADUNA | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 411478571.43 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS APD VENTURES LTD. | 2014-12-23 | 380120000 | 35 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
37 | DEMOLITION/CONSTRUCTION OF 3 NOS. 2-BEDROOM FLATS AT BOSSO ESTATE, MINNA, NIGER STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 69950200 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ETSOLA NIG. LTD. | 2014-12-23 | 69950200 | 10 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | FUNDED FROM OVERHEAD
38 | CONSTRUCTION OF 16 MAN RANK AND FILE AT YAURI, KEBBI STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 183333333.34 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ZOHA ENT. NIG. LTD. | 2014-12-23 | 201250100 | 24 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
39 | CONSTRUCTION OF 16 MAN RANK AND FILE AT BAGUDO, KEBBI STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 183333333.34 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS RESOLUTION NIG. LTD. NO. 16, JAMARE CLOSE, GARKI II, ABUJA | 2014-12-23 | 200180100 | 20 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
40 | CONSTRUCTION OF 16 MAN RANK AND FILE AT SHINKAFI, ZAMFARA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 183333333.34 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS MAC-WOMS NIGERIA LTD. | 2014-12-23 | 199980200 | 22 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
41 | CONSTRUCTION OF PERIMETER FENCE, GATE AND GATE HOUSE AT ILLELA BORDER STATION, SOKOTO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 140000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS MUSWAD GIDAD NIG. LTD. | 2014-12-24 | 60120100 | 10 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
42 | CONSTRUCTION OF PERIMETER FENCE, GATE AND GATE HOUSE RAFIN DUMA BORDER SOKOTO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 100000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS JOLOW NIG. LTD. | 2014-12-24 | 52571420.3 | 12 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
43 | CONSTRUCTION OF MINI PETROLEUM FILLING STATION AT F.O.U. ZONE ‘B’ KADUNA, ZAIRA ROAD, KADUNA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 29875000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS BROADLINE GENERAL CONTRACT SERVICES LTD. | 2014-12-24 | 29875000 | 12 WEEKS | 2015-03-09 | 0 | 2015-06-01 | COMPLETED | 0% | NA | NIL | PROJECT WAS FUNDED UNDER OVERHEAD
44 | RE-ROOFING AND RENOVATION OF OFFICE COMPLEX AT F.O.U. ZONE ‘B’, KADUNA – ZARIA ROAD, KADUNA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 100145529.27 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS AL-MUSTAKBAR GLOBAL SERVICES LTD. | 2014-12-24 | 100145529.27 | 14 WEEKS | 2015-05-28 | 0 | 2015-09-03 | ON-GOING | 0% | NA | NIL | PROJECT WAS FUNDED FROM MAINTENACE BUDJET
45 | RENOVATION AND UPGRADING OF GOVERNMENT WAREHOUSE AT MINNA, NIGER STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 26850100 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS BROADLINE GENERAL CONTRACT SERV. LTD. | 2014-12-24 | 26850100 | 8 WEEKS | 2015-04-20 | 0 | 2015-06-15 | COMPLETED | 0% | NA | NIL | PROJECT WAS FUNDED FROM MAINTENACE BUDJET
46 | RENOVATION OF 3 NOS. 3-BEDROOM FLAT AT BOSSO ESTATE, MINNA, NIGER STATE LOT ‘A’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 37070250 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ABABIA VENTURES LTD. | 2014-12-24 | 37070250 | 10 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | PROJECT WAS FUNDED FROM MAINTENACE BUDJET
47 | RENOVATION OF 3 NOS. 3-BEDROOM FLAT AT BOSSO ESTATE, MINNA, NIGER STATE LOT ‘B’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 33010200 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS UZO NWOSU NIG. LTD. | 2014-12-23 | 33010200 | 10 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | PROJECT WAS FUNDED FROM MAINTENACE BUDJET
48 | RENOVATION OF 3 NOS. 3-BEDROOM FLAT AT BOSSO ESTATE, MINNA, NIGER STATE LOT ‘C’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 32920100 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS MUAK INT’L LTD. | 2014-12-23 | 32920100 | 12 WEEKS | 2015-03-12 | 0 | 2015-06-04 | COMPLETED | 0% | NA | NIL | PROJECT WAS FUNDED FROM MAINTENACE BUDJET
49 | RENOVATION OF OFFICE AND BAGGAGE HALL AT KONGOLAM, KATSINA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 34250000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS MERIT ITER LTD. | 2014-12-23 | 34250000 | 8 WEEKS | 2014-06-18 | 0 | 2015-08-13 | ON-GOING | 0% | NA | NIL | PROJECT WAS FUNDED FROM MAINTENACE BUDJET
50 | RENOVATION OF OC STATION QUARTERS (4-BEDROOM FLAT), BLOCK L (INTELLIGENT UNIT), BLOCK A (OFFICERS RECREATION CENTRE) AND BLOCK H (6 UNITS OF 2-BEDROOM FLATS) AT KONGOLAM, KATSINA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 60000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS OVIVI VENTURES LTD. | 2014-12-23 | 48010200 | 14 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
51 | RENOVATION OF BLOCK F (10 UNITS OF 1-BEDROOM FLATS) AND BLOCK G (6 UNITS OF 2-BEDROOM FLATS) AT KONGOLAM, KATSINA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 60000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS VISIBLE GLOBAL CONCEPT LTD. | 2014-12-24 | 58200000 | 16 WEEKS | 2015-02-05 | 0 | 2015-05-21 | COMPLETED | 0% | NA | NIL
52 | RENOVATION OF 4 NOS. 3-BEDROOM WITH FENCING AND GATE HOUSE AT PHASE II LOKOGOMA, LOKOJA, KOGI STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 48750000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS GALLAHAMS TECHNOLOGIES LTD. | 2014-12-23 | 48750000 | 12 WEEKS | 2015-06-11 | 0 | 2015-09-03 | ON-GOING | 0% | NA | NIL | PROJECT WAS FUNDED FROM OVERHEAD
53 | RENOVATION OF OFFICERS MESS AT CHIKANDA, KWARA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 45000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS STARGATE ENGINEERING & CONSTRUCTION LTD. | 2014-12-23 | 20850100 | 4 WEEKS | 2015-04-28 | 0 | 2015-05-26 | COMPLETED | 0% | NA | NIL
54 | RENOVATION OF BURNT OFFICERS IN CHARGE QUARTERS AT CHIKANDA, KWARA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 60000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS HALLERULUSSEE NIG. LTD. | 2014-12-23 | 30294550.1 | 12 WEEKS | 2015-07-06 | 0 | 2015-09-28 | ON-GOING | 0% | NA | NIL
55 | RENOVATION OF INDOOR SPORTS AND RECREATION HALL AT CHIKANDA, KWARA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 70000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS MERIT ITER LTD. | 2014-12-23 | 19250200 | 8 WEEKS | 10/07/20115 | 0 | 2015-09-04 | ON-GOING | 0% | NA | NIL
56 | RENOVATION OF ABANDONED BARRACKS ACCOMMODATION AT CHIKANDA, KWARA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 80000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | NASRAELI COMPANY LTD. | 2014-12-23 | 29120100 | 10 WEEKS | 2015-07-03 | 0 | 2015-07-11 | ON-GOING | 0% | NA | NIL
57 | RENOVATION OF GOVERNMENT WAREHOUSE, SOKOTO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 50000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ABDULWAHAB MEMORIAL NIG. LTD. | 2014-12-23 | 22535075.8 | 10 WEEKS | 2015-05-27 | 0 | 2015-07-06 | ON-GOING | 0% | NA | NIL
58 | RENOVATION OF CUSTOMS HOUSE, SOKOTO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 150000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS RIL-RUMS NIG. LTD. | 2014-12-23 | 85350200 | 18 WEEKS | 2015-03-05 | 0 | 2015-07-02 | ON-GOING | 0% | NA | NIL
59 | RENOVATION OF MECHANICAL WORKSHOP, SOKOTO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 45000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS SALPA NIG. LTD. | 2014-12-24 | 23100000 | 8 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
60 | RENOVATION OF 1 NO. 6 UNITS 2-BEDROOM FLAT AT GWIWA, SOKOTO STATE LOT ‘A’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 32240000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS NATIJAH INVESTMENT LTD. | 2014-12-23 | 32240000 | 8 WEEKS | 2015-06-29 | 0 | 2015-08-28 | ON-GOING | 0% | NA | NIL | PROJECT WAS FUNDED FROM OVERHEAD
61 | RENOVATION OF 1 NO. 6 UNITS 2-BEDROOM FLAT AT GWIWA, SOKOTO STATE LOT ‘B’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 33050750 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ASF ALLIANCE LTD. | 2014-12-24 | 33050750 | 5 WEEKS | 2015-07-04 | 0 | 2015-07-01 | ON-GOING | 0% | NA | NIL | PROJECT WAS FUNDED FROM OVERHEAD
62 | RENOVATION OF 1 NO. 6 UNITS 2-BEDROOM FLAT AT GWIWA, SOKOTO STATE LOT ‘C’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 32280100 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ABSAD INTEGRATED SERVICES LTD. | 2014-12-24 | 32280100 | 6 WEEKS | 2015-03-30 | 0 | 2015-05-11 | COMPLETED | 0% | NA | NIL | PROJECT WAS FUNDED FROM OVERHEAD
63 | RENOVATION OF BARRACKS AT RAFIN DUMA BORDER STATION, SOKOTO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 20580000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS SAFAL WORLDWIDE | 2014-12-24 | 20580000 | 6 WEEKS | 2015-05-29 | 0 | 2015-07-03 | COMPLETED | 0% | NA | NIL | PROJECT WAS FUNDED FROM OVERHEAD
64 | RENOVATION OF OLD CUSTOMS HOUSE, GUSAU AND CONVERSION TO BARRACKS ACCOMMODATION, ZAMFARA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 100000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS DSI PLUS LTD. | 2014-12-23 | 64120100 | 18 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
65 | RENOVATION OF CUSTOMS HOUSE AT BIRNIN KEBBI, KEBBI STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 100000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ANKAMU NIG. LTD. | 2014-12-23 | 54130000 | 12 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
66 | RENOVATION OF MINI OFFICE AT MAJE, BORDER STATION, KEBBI STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 26666666.67 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ABDULWAHAB MEMORIAL NIG. LTD. | 2014-12-24 | 17100000 | 5 WEEKS | 2015-06-30 | 0 | 2015-08-04 | ON-GOING | 0% | NA | NIL
67 | RENOVATION OF MINI OFFICE AT BAGUDO BORDER STATION, KEBBI STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 26666666.67 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS MULTIPURPOSE GENERAL CONTRACTOR LTD. | 2014-12-23 | 19980100 | 5 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
68 | RENOVATION OF MINI OFFICE AT YAURI BORDER STATION, KEBBI STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 26666666.67 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS BIRZAMFY ENT. LTD. | 2014-12-24 | 19250100 | 6 WEEKS | 2015-07-16 | 0 | 2015-08-27 | ON-GOING | 0% | NA | NIL
69 | RENOVATION OF 1 NOS. 4 UNITS 1-BEDROOM FLAT AT MAJE BORDER STATION, KEBBI STATE LOT ‘A’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 80000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS POINTED PINNACLE INTEGRATED SERVICES LTD. | 2014-12-23 | 24120100 | 4 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | COMPLETED | 0% | NA | NIL
70 | RENOVATION OF 1 NOS. 4 UNITS 1-BEDROOM FLAT AT MAJE BORDER STATION, KEBBI STATE LOT ‘B’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 27130120 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS MARUTEE NIG. LTD. | 2014-12-23 | 27130120 | 8 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | PROJECT WAS FUNDED FROM OVERHEAD
71 | RENOVATION OF BARRACKS AT BAGUDO BORDER STATION, KEBBI STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 50000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS MARUTEE NIG. LTD. | 2014-12-23 | 25550100 | 6 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
72 | RENOVATION OF 1 NOS. 6 UNITS 2-BEDROOM SEMI DETACHED AT YAURI, KEBBI STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 33101250 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS FADAHAMA GLOBAL INVESTMENT LTD. | 2014-12-23 | 33101250 | 10 WEEKS | 2005-06-03 | 0 | 2015-08-12 | ON-GOING | 0% | NA | NIL | PROJECT WAS FUNDED FROM OVERHEAD
73 | DRILLING OF BOREHOLE AND CONSTRUCTION OF GROUND AND OVERHEAD WATER TANK AT RAFIN DUMA, SOKOTO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 17000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS HASH INVESTMENT & SERVICES LTD. | 2014-12-24 | 14750010 | 8 WEEKS | 2015-06-29 | 0 | 2015-08-24 | ON-GOING | 0% | NA | NIL
74 | DRILLING OF BOREHOLE AND CONSTRUCTION OF GROUND AND OVERHEAD WATER TANK AT MAJE BORDER, KEBBI STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 17000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS YTEK INVEST. & AGRO ALLIED LTD. | 2014-12-24 | 15100000 | 6 WEEKS | 2015-06-25 | 0 | 2015-08-06 | ON-GOING | 0% | NA | NIL
75 | DRILLING OF BOREHOLE AND CONSTRUCTION OF GROUND AND OVERHEAD WATER TANK AT GUSAU, ZAMFARA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 16500000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS NAMINA GLOBAL SERVICE LTD. | 2014-12-23 | 14340000 | 6 WEEKS | 2015-06-19 | 0 | 2015-08-06 | ON-GOING | 0% | NA | NIL
76 | SUPPLY AND INSTALLATION OF 60KVA SOUND PROOF PERKINS GENERATOR AT DOLEKAINA BORDER STATION, KEBBI STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 100000000 | OPEN | 2014-11-25 | 2014-12-18 | 14200000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ADAF BML NIG. LTD. | 2014-12-24 | 9560000 | 5 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
77 | SUPPLY AND INSTALLATION OF 60KVA SOUND PROOF PERKINS GENERATOR AT LOLO DOLEKAINA BORDER STATION, KEBBI STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 100000000 | OPEN | 2014-11-25 | 2014-12-18 | 16500000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS VENTHCLOE VENTURES LTD. | 2014-12-24 | 10570100 | 6 WEEKS | 2015-03-16 | 0 | 2015-04-27 | COMPLETED | 0% | NA | NIL
78 | SUPPLY AND INSTALLATION OF 100KVA SOUND PROOF PERKINS GENERATOR AT CUSTOMS HOUSE, SOKOTO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 100000000 | OPEN | 2014-11-25 | 2014-12-18 | 16500000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS DALINGA LTD. | 2014-12-24 | 14250100 | 6 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
79 | SUPPLY AND INSTALLATION OF 60KVA SOUND PROOF PERKINS GENERATOR AT RAFIN DUMA BORDER STATION, SOKOTO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 100000000 | OPEN | 2014-11-25 | 2014-12-18 | 16500000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ENNKA ELECTRICAL AND GENERAL SERVICES NIG. LTD. | 2014-12-24 | 9720100 | 4 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
80 | SUPPLY AND INSTALLATION OF 60KVA SOUND PROOF PERKINS GENERATOR AT CUSTOMS OFFICE, GUSAU, ZAMFARA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 100000000 | OPEN | 2014-11-25 | 2014-12-18 | 14200000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ALMOND REALITY LTD. | 2014-12-24 | 9870000 | 5 WEEKS | 2015-03-03 | 0 | 2015-04-07 | COMPLETED | 0% | NA | NIL
81 | SUPPLY AND INSTALLATION OF 100KVA SOUND PROOF PERKINS GENERATOR AT CUSTOMS BARRACKS, GWIWA, SOKOTO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 100000000 | OPEN | 2014-11-25 | 2014-12-18 | 16500000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS. BLUE HEIGHT TRIPLE INTEGRATED SERVICES LTD. | 2014-12-23 | 14100200 | 6 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
82 | CONSTRUCTION OF RESTRUCTURED AND REMODELLED 30 MAN RANK AND FILE BUILDING AT WARRI, DELTA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 411478571.43 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS UZO NWOSU NIG. LTD. | 2014-12-23 | 382200000 | 40 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
83 | CONSTRUCTION OF PARADE GROUND AT CUSTOMS TRAINING COLLEGE, KANO | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 10000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS SCHRAMM GLOBAL SERVICES LTD. | 2014-12-24 | 18950000 | 10 WEEKS | 2015-01-22 | 0 | 2015-04-02 | COMPLETED | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
84 | CONSTRUCTION OF GROUND AND OVERHEAD WATER TANK AND CONSTRUCTION OF GENERATOR HOUSE SHINKAFI BORDER STATION, ZAMFARA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 8522673.5 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS SAAB COMMERCIAL NIG. LTD. | 2014-12-23 | 8522673.5 | 4 WEEKS | 2015-04-03 | 0 | 01/05/20`5 | COMPLETED | 0% | NA | NIL | FUNDED FROM OVERHEAD
85 | CONSTRUCTION OF 16 MAN RANK AND FILE AT SAPELE, DELTA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 120000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS MDC GLOBAL CONCEPT LTD. | 2014-12-23 | 188500521 | 16 WEEKS | 2015-06-12 | 0 | 2015-10-02 | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
86 | CONSTRUCTION OF 16 MAN RANK AND FILE AT YENEGOA, BAYELSA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 180000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS TECH & SONS LTD. | 2014-12-23 | 218750000 | 30 WEEKS | 2015-04-11 | 0 | 2015-11-07 | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
87 | CONSTRUCTION, LANDSCAPING AND FURNISHING OF AREA CONTROLLER’S QUARTERS AT MILE 4 BARRACKS, PORT HARCOURT, RIVERS STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 220000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS APD VENTURES LTD. | 2014-12-23 | 219850100 | 24 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
88 | CONSTRUCTION, LANDSCAPING AND FURNISHING OF ZONAL COORDINATOR’S QUARTERS AT MILE 4 BARRACKS, PORT HARCOURT, RIVERS STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 260000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS RICHARD VAL ENTERPRISES LTD. | 2014-12-23 | 259200100 | 24 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
89 | DEMOLITION AND RECONSTRUCTION OF 30 MAN RANK AND FILE AT NSUKKA ROAD BARRACKS MILE ONE, PORT HARCOURT, RIVERS STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 370000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS MIEKEMI SERVICES. | 2014-12-24 | 436850000 | 32 WEEKS | 2015-04-16 | 0 | 2015-11-26 | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
90 | REHABILITATION OF 30 MAN RANK AND FILE WARRI, DELTA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 50000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ZOOKAS NIG. LTD. | 2014-12-24 | 52850100 | 32 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
91 | FENCING OF ARMOURY BUILDING, PORT HARCOURT, RIVERS STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 30000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS EBONITE NIG. LTD. | 2014-12-23 | 16350100 | 4 WEEKS | 2015-07-16 | 0 | 2015-08-13 | ON-GOING | 0% | NA | NIL
92 | FENCING OF CUSTOMS LAND AT YENEGOA, BAYELSA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 300000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS JAMI SERVICES LTD. | 2014-12-24 | 275311943.33 | 14 WEEKS | 2015-06-16 | 0 | 2015-10-06 | ON-GOING | 0% | NA | NIL
93 | CONSTRUCTION OF BARRACKS FENCE WITH 3 GATE HOUSES AND CONSTRUCTION OF PERIMETER FENCE FOR AREA CONTROLLER’S RESIDENCE WITH 1 GATE HOUSE AT ENUGU STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 46150100 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS REFINED GOLDEN ABM NIG. LTD. | 2014-12-24 | 46150100 | 10 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | FUNDED FROM OVERHEAD
94 | CONSTRUCTION OF FENCING AND GATE HOUSE AT PLOT 61, URATTA HOUSING ESTATE, OWERRI, IMO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 40000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS NASMOHA NIG. LTD. | 2014-12-24 | 17290100 | 6 WEEKS | 2015-07-06 | 0 | 2015-08-17 | ON-GOING | 0% | NA | NIL
95 | CONSTRUCTION OF FENCING AND GATE HOUSE AT PLOT 64, URATTA HOUSING ESTATE, OWERRI, IMO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 40000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS BABJAM NIG. LTD. | 2014-12-23 | 16890200 | 8 WEEKS | 2015-05-06 | 0 | 2015-07-01 | COMPLETED | 0% | NA | NIL
96 | CONSTRUCTION OF FENCING AND GATE HOUSE AT PLOT 67, URATTA HOUSING ESTATE, OWERRI, IMO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 40000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS DE-SAM BUSOBAY VENTURES | 2014-12-23 | 17890250 | 7 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
97 | PERIMETER SURVEY OF NIGERIA CUSTOMS SERVICE LAND AT ELEME, PH, RIVERS STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 10526250 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS DAVEZO NIG. LTD. | 2014-12-24 | 10526250 | 5 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | FUNDED FROM OVERHEAD
98 | RENOVATION OF OFFICE BLOCK AT AHOADA, BAYELSA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 40000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS VASHIJ NIG. LTD. | 2014-12-23 | 21200400 | 8 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
99 | RENOVATION OF CUSTOMS OFFICE, IKANG-BAKASSI, AKWA IBOM STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 40000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS UGONDECHS INT’L LTD. | 2014-12-24 | 20996000 | 15 WEEKS | 2015-07-07 | 0 | 2015-10-13 | ON-GOING | 0% | NA | NIL
100 | RENOVATION OF CUSTOMS OFFICE AT ORON OUTSTATION, AKWA IBOM STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 45000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS BARHAMU GLOBAL SERVICES LTD. | 2014-12-23 | 21216000 | 14 WEEKS | 2015-05-21 | 0 | 2015-08-27 | ON-GOING | 0% | NA | NIL
101 | RENOVATION OF 1 NO. 3-BEDRROM FLATS AT ORON OUTSTATION, AKWA IBOM STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 30000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS SAVIMSAJ NIG. LTD. | 2014-12-24 | 25950100 | 14 WEEKS | 2015-03-25 | 0 | 2015-06-22 | COMPLETED | 0% | NA | NIL
102 | RENOVATION OF MFUM OFFICE, CROSS RIVER STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 80000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ARMUSAN NIG. LTD. | 2014-12-23 | 22140000 | 10 WEEKS | 2015-06-24 | 0 | 2015-09-02 | ON-GOING | 0% | NA | NIL
103 | RENOVATION OF 2 NOS. 3-BEDROOM FLAT AT CUSTOMS BARRACKS, CALABAR, CROSS RIVER STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 38000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS UGONDECHS INT’L LTD. | 2014-12-24 | 31002200 | 10 WEEKS | 2015-07-07 | 0 | 2015-09-15 | ON-GOING | 0% | NA | NIL | FUNDED FROM OVERHEAD
104 | RENOVATION OF 2 NOS. 3-BEDROOM FLATS AT MFUM BORDER STATION, CROSS RIVER STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 60000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ADE-JOY NIG. LTD. | 2014-12-23 | 25010100 | 8 WEEKS | 2015-07-14 | 0 | 2015-09-08 | ON-GOING | 0% | NA | NIL
105 | RENOVATION OF CUSTOMS OFFICE WITH CANTEEN AT SAPELE, DELTA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 50000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ABDUL AHMED NIG. ENTERPRISES | 2014-12-23 | 51250100 | 12 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
106 | RENOVATION OF AREA CONTROLLER’S RESIDENCE AT OWERRI, IMO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 50000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS PONIAL INTER GLOBAL INVEST. LTD. | 2014-12-23 | 45915800 | 12 WEEKS | 2015-04-02 | 0 | 2015-06-25 | COMPLETED | 0% | NA | NIL
107 | RENOVATION OF 4-BEDROOM DUPLEX AT EGBEARADA HOUSING ESTATE, OWERRI, IMO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 80000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS AVIVA ENGINEERING NIG. LTD. | 2014-12-24 | 48010000 | 10 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
108 | RENOVATION OF 2-BEDROOM FLAT AT EGBEARADA HOUSING ESTATE, OWERRI, IMO STATE LOT ‘A’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 25000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS AJEF APE NIG. LTD. | 2014-12-24 | 13950000 | 6 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
109 | RENOVATION OF 2-BEDROOM FLAT AT EGBEARADA HOUSING ESTATE, OWERRI, IMO STATE LOT ‘B’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 25000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS YARBAKHAT COMPANY LTD. | 2014-12-24 | 13905200 | 8 WEEKS | 2015-06-23 | 0 | 2015-08-10 | ON-GOING | 0% | NA | NIL
110 | RENOVATION OF 3-BEDROOM FLAT AT EGBEARADA HOUSING ESTATE, OWERRI, IMO STATE LOT ‘A’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 30000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ADMAIR AGENCY NIG. LTD. | 2014-12-24 | 16950000 | 5 WEEKS | 2015-05-14 | 0 | 2015-06-18 | COMPLETED | 0% | NA | NIL
111 | FLAT AT EGBEARADA HOUSING ESTATE, OWERRI, IMO STATE LOT ‘B’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 30000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS TABES CONCEPT INT’L LTD. | 2014-12-24 | 17010000 | 6 WEEKS | 2015-05-15 | 0 | 2015-06-26 | COMPLETED | 0% | NA | NIL
112 | RENOVATION OF 5-BEDROOM FLAT AT PLOT 61, URATTA HOUSING ESTATE, OWERRI, IMO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 60000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS TONIADANICZ INT. LTD. | 2014-12-23 | 32405231.25 | 10 WEEKS | 2015-04-24 | 0 | 2015-06-05 | COMPLETED | 0% | NA | NIL
113 | RENOVATION OF 5-BEDROOM FLAT AT PLOT 63, URATTA HOUSING ESTATE, OWERRI, IMO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 60000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ABLE MATTERS NIG. LTD. | 2014-12-23 | 33180000 | 12 WEEKS | 2015-03-04 | 0 | 2015-05-27 | COMPLETED | 0% | NA | NIL
114 | RENOVATION OF 5-BEDROOM FLAT AT PLOT 64, URATTA HOUSING ESTATE, OWERRI, IMO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 60000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS TAM TAM PROJECT LTD. | 2014-12-24 | 32850000 | 10 WEEKS | 2015-03-27 | 0 | 2015-06-05 | COMPLETED | 0% | NA | NIL
115 | RENOVATION OF 5-BEDROOM FLAT AT PLOT 67, URATTA HOUSING ESTATE, OWERRI, IMO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 60000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ADEFORTS NIG. LTD. | 2014-12-24 | 32750000 | 8 WEEKS | 2015-06-08 | 0 | 2015-06-03 | ON-GOING | 0% | NA | NIL | REQUEST PAYMENT OF VALUATION
116 | RENOVATION OF OC’S RESIDENCE AT ONITSHA, ANAMBRA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 30000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS KEVMAUR NIG. LTD. | 2014-12-24 | 34280900 | 8 WEEKS | 2015-06-22 | 0 | 2015-08-17 | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
117 | RENOVATION OF 2-BEDROOM TWIN INTERMEDIATE STAFF QUARTERS AT ONITSHA, ANAMBRA STATE LOT ‘A’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 15000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS A.O. OHIKHENA & ASSOCIATE NIG. LTD. | 2014-12-24 | 28010000 | 10 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
118 | RENOVATION OF 2-BEDROOM TWIN INTERMEDIATE STAFF QUARTERS AT ONITSHA, ANAMBRA STATE LOT ‘B’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 15000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ABDUL AHMED NIG. ENTERPRISES | 2014-12-23 | 28500000 | 10 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
119 | RENOVATION OF 2-BEDROOM TWIN INTERMEDIATE STAFF QUARTERS AT ONITSHA, ANAMBRA STATE LOT ‘C’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 15000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS CHESEE NIG. LTD. | 2014-12-24 | 27950100 | 14 WEEKS | 2015-06-30 | 0 | 2015-08-25 | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
120 | RENOVATION OF 2-BEDROOM TWIN INTERMEDIATE STAFF QUARTERS AT ENUGU. LOT ‘A’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 30000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ALADEMOLA NIG. ENTERPRISES | 2014-12-24 | 28050000 | 10 WEEKS | 2015-07-16 | 0 | 2015-09-24 | ON-GOING | 0% | NA | NIL
121 | RENOVATION OF 2-BEDROOM TWIN INTERMEDIATE STAFF QUARTERS AT ENUGU. LOT ‘B’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 30000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ANDY JOES GROUP NIG. LTD. | 2014-12-24 | 28050000 | 12 WEEKS | 2015-04-22 | 0 | 2015-07-15 | COMPLETED | 0% | NA | NIL
122 | RENOVATION OF 2-BEDROOM TWIN INTERMEDIATE STAFF QUARTERS AT ENUGU. LOT ‘C’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 30000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS MERIT KAY NIG. LTD. | 2014-12-24 | 26050000 | 10 WEEKS | 2015-04-29 | 0 | 2015-07-08 | COMPLETED | 0% | NA | NIL
123 | RENOVATION OF BLOCK OF 6 NOS. 1-BEDROOM INTERMEDIATE STAFF QUARTERS AT ENUGU STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 52000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS JEFLOK ENGINEERING COMPANY LTD. | 2014-12-24 | 49980150 | 10 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | FUNDED FROM OVERHEAD
124 | RENOVATION OF DEPUTY COMPTROLLER’S QUARTERS AT WARRI, DELTA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 41000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS REFINED GOLDEN ABM NIG. LTD. | 2014-12-24 | 39750000 | 14 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | FUNDED FROM OVERHEAD
125 | DRILLING OF BOREHOLE AND CONSTRUCTION OF GROUND AND OVERHEAD WATER TANK AT SAPELE, DELTA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 13740000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS HILEPAH SKY INT’L LTD. | 2014-12-24 | 14690100 | 6 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
126 | DRILLING OF BOREHOLE AND CONSTRUCTION OF GROUND AND OVERHEAD WATER TANK AT FOU ZONE ‘C’ OWERRI, IMO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 17000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS RESOLUTION NIG. LTD. | 2014-12-23 | 14870000 | 6 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
127 | DRILLING OF BOREHOLE AND CONSTRUCTION OF GROUND AND OVERHEAD WATER TANK AT BARTHUST QUARTERS, PORT HARCOURT, RIVERS STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 13850000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ANCHORTECH CONCEPT LTD. | 2014-12-23 | 13895200 | 5 WEEKS | 2015-05-26 | 0 | 2015-06-30 | COMPLETED | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
128 | DRILLING OF BOREHOLE AND CONSTRUCTION OF GROUND AND OVERHEAD WATER TANK WITH WATER TREATMENT PLANT GENERATOR AND GENERATOR HOUSE, YENEGOA, BAYELSA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 46300000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS FIBOW & ENVT. ENGR. CONSULT LTD. | 2014-12-24 | 47091348.34 | 8 WEEKS | 2015-07-15 | 0 | 2015-09-09 | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
129 | DRILLING OF BOREHOLE AND CONSTRUCTION OF GROUND AND OVERHEAD WATER TANK AT CUSTOMS AREA OFFICE, CALABAR, CROSS RIVER STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 14780000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS GEORGE MINING & EXPLORATION NIG. LTD. | 2014-12-24 | 13905200 | 8 WEEKS | 2015-06-25 | 0 | 2015-08-20 | ON-GOING | 0% | NA | NIL
130 | SUPPLY AND INSTALLATION OF 1 NO. 250KVA SOUND PROOF PERKINS GENERATOR TO CUSTOMS OFFICE, WARRI, DELTA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 100000000 | OPEN | 2014-11-25 | 2014-12-18 | 16200000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS SUWANG INTEGRATED SERVICES LTD. | 2014-12-24 | 21270000 | 8 WEEKS | 2015-07-13 | 0 | 2015-09-07 | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
131 | SUPPLY AND INSTALLATION OF 1 NO. 60KVA SOUND PROOF PERKINS GENERATOR TO SAPELE OFFICE, DELTA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 100000000 | OPEN | 2014-11-25 | 2014-12-18 | 16200000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS CROWN RESOURCES DEV. COMPANY LTD | 2014-12-24 | 9810730 | 4 WEEKS | 2015-04-14 | 0 | 2015-05-12 | COMPLETED | 0% | NA | NIL
132 | SUPPLY AND INSTALLATION OF 1 NO. 100KVA SOUND PROOF PERKINS GENERATOR TO FOU ZONE ‘C’ OWERRI, IMO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 100000000 | OPEN | 2014-11-25 | 2014-12-18 | 14160000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS EPITOME DE-LACLASSE VENTURES LTD. | 2014-12-23 | 14160000 | 4 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
133 | CONNECTION OF CUSTOMS HOUSE AREA II COMMAND, ONNE – PH TO NATIONAL GRID | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 41010100 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS HAJEDOC NIG. LTD. | 2014-12-24 | 41010100 | 8 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
134 | SUPPLY AND INSTALLATION OF 1 NO. 80KVA SOUND PROOF PERKINS GENERATOR TO CUSTOMS OFFICE, CALABAR, CROSS RIVER STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 100000000 | OPEN | 2014-11-25 | 2014-12-18 | 12010200 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS MUSWAD GIDAD NIG. LTD. | 2014-12-23 | 12010200 | 5 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
135 | SUPPLY AND INSTALLATION OF 2 NOS. 300KVA TRANSFORMER TO FOU ZONE ‘C’ OWERRI, IMO STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 100000000 | OPEN | 2014-11-25 | 2014-12-18 | 20000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS MAC-WOMS NIGERIA LTD. | 2014-12-23 | 17980000 | 6 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
136 | COMPLETION AND FURNISHING OF MEDICAL CLINIC AND DOCTOR’S QUARTERS INCLUDING LANDSCAPING AT BAUCHI, STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 100000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS MASY NIG. LTD. | 2014-12-23 | 29850000 | 10 WEEKS | 2015-03-27 | 0 | 2015-06-06 | COMPLETED | 0% | NA | NIL
137 | CONSTRUCTION OF PERIMETER FENCE AND PROVISION OF OTHER INFRASTRUCTURE AT GOMBE OUTSTATION BARRACKS, GOMBE STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 81780000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS FARINDOKI CONSTRUCTION NIG. LTD. | 2014-12-24 | 81780000 | 8 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | FUNDED FROM OVERHEAD
138 | RENOVATION OF 2 NOS. 3-BEDROOM SENIOR STAFF QUARTERS WITH BOYS QUARTERS AT RUWAN ZAFI, BORNO STATE. LOT ‘A’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 33340000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS USILADI NIG. LTD. | 2014-12-24 | 33840000 | 14 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
139 | RENOVATION OF 2 NOS. 3-BEDROOM SENIOR STAFF QUARTERS WITH BOYS QUARTERS AT RUWAN ZAFI, BORNO STATE. LOT ‘B’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 33340000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS PARADIGM TECH SERVICE LTD. | 2014-12-24 | 33150000 | 18 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
140 | RENOVATION OF 2 NOS. 3-BEDROOM SENIOR STAFF QUARTERS WITH BOYS QUARTERS AT RUWAN ZAFI, BORNO STATE. LOT ‘C’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 33340000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS NVITAGRACE NIG. LTD. | 2014-12-24 | 34820000 | 14 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
141 | RENOVATION OF 2 NOS. 3-BEDROOM SENIOR STAFF QUARTERS WITH BOYS QUARTERS AT RUWAN ZAFI, BORNO STATE. LOT ‘D’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 33340000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS SHET SCIENTIFICS NIG. LTD. | 2014-12-24 | 32140100 | 18 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
142 | RENOVATION OF 2 NOS. 3-BEDROOM SENIOR STAFF QUARTERS WITH BOYS QUARTERS AT RUWAN ZAFI, BORNO STATE. LOT ‘E’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 33340000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS. KAZAK MEGA LINKS LTD. | 2014-12-24 | 32980000 | 16 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
143 | RENOVATION OF 2 NOS. 3-BEDROOM SENIOR STAFF QUARTERS WITH BOYS QUARTERS AT RUWAN ZAFI, BORNO STATE. LOT ‘F’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 33340000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS ARMUSAN NIG. LTD. | 2014-12-24 | 33050100 | 14 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
144 | RENOVATION OF 2 NOS. 3-BEDROOM SENIOR STAFF QUARTERS WITH BOYS QUARTERS AT RUWAN ZAFI, BORNO STATE. LOT ‘G’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 33340000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS TRIPLE ICON NIG. LTD. | 2014-12-24 | 32650000 | 12 WEEKS | 2015-03-24 | 0 | 2015-06-02 | COMPLETED | 0% | NA | NIL
145 | RENOVATION OF 2 NOS. 3-BEDROOM SENIOR STAFF QUARTERS WITH BOYS QUARTERS AT RUWAN ZAFI, BORNO STATE. LOT ‘H’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 33340000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS LOLAKO NIG. LTD. | 2014-12-24 | 32750000 | 16 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
146 | RENOVATION OF 2 NOS. 3-BEDROOM SENIOR STAFF QUARTERS WITH BOYS QUARTERS AT RUWAN ZAFI, BORNO STATE. LOT ‘I’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 33340000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS KIRANUWA GLOBAL INVESTMENT | 2014-12-24 | 33250000 | 14 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
147 | RENOVATION OF 2 NOS. 2-BEDROOM FLATS WITH BQ AND 1 NO. INTERMEDIATE STAFF QUARTERS AT AHMADU BELLO WAY, JIMETA, ADAMAWA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 60000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS AB INTERBIZ NIG. LTD. | 2014-12-23 | 49250200 | 16 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
148 | RENOVATION OF 2 NOS. 2 UNIT 2-BEDROOM FLAT AT YOLA, ADAMAWA. LOT ‘A’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 17500000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS VAJILI NIG. LTD. | 2014-12-24 | 26750100 | 14 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
149 | RENOVATION OF 2 NOS. 2 UNIT 2-BEDROOM FLAT AT YOLA, ADAMAWA. LOT ‘B’ | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 17500000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS JAMBEL CONSTRUCTION LTD. | 2014-12-24 | 26101200 | 10 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
150 | RENOVATION OF CUSTOMS OFFICE AND BARRACKS AT GEMBU, TARABA STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 100000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS 2KINGS INTEGRATED CONSTR. SERVICES LTD. | 2014-12-24 | 28320000 | 12 WEEKS | 2015-04-23 | 0 | 2015-07-16 | COMPLETED | 0% | NA | NIL
151 | RENOVATION AND FURNISHING OF AREA CONTROLLER’S QUARTERS INCLUDING LANDSCAPING AT BAUCHI STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 60000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS GWWIL COMM LTD. | 2014-12-24 | 56950000 | 12 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
152 | RENOVATION AND FURNISHING OF ZONAL COORDINATOR QUARTERS INCLUDING 2 NOS. BQ AND CAR PARK AT BAUCHI | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 100000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS. AMASH GLOBAL CONCEPT LTD. | 2014-12-24 | 44250100.2 | 16 WEEKS | 2015-05-14 | 0 | 2015-09-03 | ON-GOING | 0% | NA | NIL | #VALUE!
153 | RENOVATION AND FURNISHING OF 4-BEDROOM SSQ, MODIFICATION OF EXISTING FENCE AND LANDSCAPING INCLUDING BQ, ALGADAMA BARRACKS, JOS, PLATEAU | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 40000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS LARTMAS INVESTMENT LTD. | 2014-12-24 | 53270105 | 14 WEEKS | 2015-06-25 | 0 | 2015-10-01 | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
154 | RENOVATION OF 2 NOS. TWIN 2-BEDROOM FLAT AT MIANGO ROAD, CUSTOMS BARRCKS, JOS PLATEAU STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 60000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS SUWANG INT’L SERVICES LTD. | 2015-05-24 | 28280100 | 12 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
155 | RENOVATION OF 3 NOS. TWIN 2-BEDROOM FLAT AT MIANGO ROAD, CUSTOMS BARRCKS, JOS PLATEAU STATE B, D & E | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 90000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS JIDDARI LTD. | 2014-12-23 | 38140200 | 6 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
156 | RENOVATION OF 1 NO. 30 MAN RANK AND FILE AT CUSTOMS BARRACKS MAKURDI, BENUE STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 60000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS LARTMAS INVESTMENT LTD. | 2014-12-24 | 99980000 | 14 WEEKS | 2015-06-25 | 0 | 2015-10-01 | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
157 | DRILLING OF BOREHOLE AND CONSTRUCTION OF GROUND AND OVERHEAD WATER TANK AT DEPUTY COMPTROLLER’S QUARTERS, JALINGO, TARABA. | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 17500000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS GOGO CONSTRUCTION CO. LTD. | 2014-12-24 | 17890000 | 6 WEEKS | 2015-06-29 | 0 | 2015-08-10 | ON-GOING | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
158 | DRILLING OF BOREHOLE AND CONSTRUCTION OF GROUND AND OVERHEAD WATER TANKS AT BAUCHI | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 14500000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS NORTHPOLE OIL & GAS RESOURCES LTD. | 2014-12-24 | 14650000 | 6 WEEKS | 2015-05-12 | 0 | 2015-06-23 | COMPLETED | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
159 | SUPPLY AND INSTALLATION OF 1 NO. 27KVA SOUND PROOF PERKINS GENERATOR TO ASST. COMPTROLLER GENERAL (ZONAL COORDINATOR, ZONE ‘D’) BAUCHI STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 100000000 | OPEN | 2014-11-25 | 2014-12-18 | 14200000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS. NORTHPOLE OIL & GAS RESOURCES LTD. | 2014-12-24 | 5650000 | 4 WEEKS | 2015-05-12 | 0 | 2015-06-09 | COMPLETED | 0% | NA | NIL
160 | SUPPLY AND INSTALLATION OF 1 NO. 100KVA SOUND PROOF PERKINS GENERATOR TO CUSTOMS BARRACKS, DOGON DUTSE, JOS – PLATEAU STATE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 100000000 | OPEN | 2014-11-25 | 2014-12-18 | 16500000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS DALINGA LTD. | 2014-12-23 | 14790500 | 6 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
161 | FENCING OF NCS NEWLY ACQUIRED LAND AT FCT COMMAND, ABUJA | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 300000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS TRIAD ASSOCIATES | 2014-12-24 | 180417283 | 20 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
162 | CONSTRUCTION OF ADDITIONAL WORKS I.E. INTRODUCTION OF FRENCH DRAINS, SAP LAX RX-770 FOR SURFACE HARDNER WATER PROOF, REDUCE LEVEL EXCAVATION ALONG HANGER TAXIWAY ETC AND UPGRADING/AMENDMENT TO CGC OFFICE AT NCS HANGER PROJECT AT NNAMDI AZIKWE INT’L AIRPORT, ABUJA | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 140000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS STAR PLAZA ENTERPRISES LTD. | 2014-12-24 | 134700000 | 18 WEEKS | 2015-02-13 | 0 | 2015-06-12 | COMPLETED | 0% | NA | NIL
163 | CONSTRUCTION OF BITUMEN ROAD TO CONNECT NCS HANGER PROJECT TO MAIN TAXI WAY AT NNAMDI AZIKWE INT’L AIRPORT, ABUJA | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 260000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS STAR PLAZA ENTERPRISES LTD. | 2014-12-24 | 259823386.88 | 34 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
164 | LANDSCAPING AND HORTICULTURAL WORKS, STORM WATER DRAINAGE, AND RESTRUCTURING OF FALLEN OFF FENCE AT CUSTOMS SERVICE BARRACKS, KARU – ABUJA | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 51980000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS KONTEMPORARY KONCEPTS LTD. | 2014-12-24 | 51980000 | 14 WEEKS | 2015-03-05 | 0 | 2015-06-11 | COMPLETED | 0% | NA | NIL | FUNDED FROM OVERHEAD
165 | RENOVATION OF NEWLY CONVERTED OFFICE TO BARRACKS INCLUDING FENCING AND SUPPLY AND INSTALLATION OF 27KVA GENERATOR AT GWAGWALADA, ABUJA | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 80000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS DASAL VENTURES LTD. | 2014-12-24 | 46980000 | 7 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
166 | REHABILITATION AND UPGRADING OF EXISTING SITE OFFICE INCLUDING MANUAL LAUNDRY FACILITY, WATER TREATMENT PLANT, VERANDER LINKS TO EXISTING HOSPITAL METAL GRILLE WORKS AND PURCHASE/INSTALLATION OF DEDICATED UPS SYSTEM AND AVR FOR CUSTOMS HOSPITAL, KARU – ABUJA | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 100000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS KABAB VENTURES LTD. | 2014-12-24 | 55120900 | 34 WEEKS | 2015-04-21 | 0 | 2015-12-15 | ON-GOING | 0% | NA | NIL
167 | DRILLING OF BOREHOLE AND CONSTRUCTION OF GROUND AND OVERHEAD WATER TANK INCLUDING RETICULATION AT SSQ, KUJE – ABUJA | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 1000000000 | OPEN | 2014-11-25 | 2014-12-18 | 17205200 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS AMIR CREATIONS LTD. | 2014-12-24 |  | 6 WEEKS | 2015-05-18 | 0 | 2015-06-29 | COMPLETED | 0% | NA | NIL | FUNDED FROM OVERHEAD
168 | SUPPLY AND INSTALLATION OF 2 NOS. 500KVA SOUND PROOF PERKINS GENERATOR TO CUSTOMS MEDICAL CENTRE, KARU – ABUJA | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 100000000 | OPEN | 2014-11-25 | 2014-12-18 | 100000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS LARTMAS INVESTMENT LTD. | 2014-12-23 | 64100000 | 8 WEEKS | GONE TO SITE WHILE AWAITNG MOBILIZATION FEE | 0 |  | ON-GOING | 0% | NA | NIL
169 | SUPPLY, INSTALLATION AND ACTIVATION OF 3000 UNITS GSM DESKTOP PHONES AND 20 BLACKBERRY PORSCHE (CARBON) HANDSETS FOR EFFECTIVE ANTI-SMUGGLING STRATEGY FOR NIGERIA CUSTOM SERVICE | PUNCH (26-05-2014); DAILYSUN (26-05-2014); LEADERSHIP (27-05-2014); DAILY TRUST (27/05/2014) | 100000000 | OPEN | 2014-11-25 | 2014-12-18 | 450000000 | NA | 2014-12-22 | LEAST BEST EVALUATED TENDER | MESSRS FREEDOM PRODUCTS INTERNATIONAL LTD. | 2014-12-24 | 452100000 | 10 WEEKS | 2014-04-10 | 0 | 2015-06-19 | COMPLETED | 0% | NA | NIL | ROLLED OVER TO 2015 BUDGET
| TOTAL | [11 empty] | 10590213178.9

## NBET
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) : |  | Nigerian Bulk Electricity Trading Plc
MINISTRY :
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/03/2015 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/03/2015 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | Supply of ICT Equipment- Volume License HP Servers, APC , UPS. | 01.08.2014- Daily Trust,Thisday,the Guardian and Abuja Enquirer. | PTB | NCB | 01.08.2014 | 10.11.2014 | 15000000 | NA | 11.11.2014 | Omniswift Limited | Omniswift Limited | 14.11.2014 | 13977600 | 3 months |  | 13977600 |  | Completed | 100 | NA | NA | Completed
2 | Supply of Desktop Computers and Laptops | 01.08.2014- Daily Trust,Thisday,the Guardian and Abuja Enquirer. | PTB | NCB | 12.12.2014 | 15.12.2014 | 45000000 | NA | 11.11.204 | Auspoint Limited | Auspoint Limited | 14.11.2014 | 36876000 | 3 months |  | 36876000 |  | Completed | 100 | NA | NA | Completed
3 | Supply of office furniture, equipment and accessories | 01.08.2014- Daily Trust,Thisday,the Guardian and Abuja Enquirer. | PTB | NCB | 02.03.2015 | 02.03.2016 | 35000000 | NA | 13.02.2015 | Versatile Resources Limited | Versatile Resources Limited | 26.03.2015 | 31503764 | 8 weeks |  | 31503764 |  | Completed | 100 |  | NA | Completed
4 | Project management/monitoring Project Vehicles | 01.08.2014- Daily Trust,Thisday,the Guardian and Abuja Enquirer. | PTB | NCB | 13.02.2015 | 13.02.2015 | 80000000 | NA | 04.03.2015 | Kojo Motors | Kojo motors | 13.04.2015 | 48444444 | 8 weeks |  | 48444444 |  | Completed | 100 |  | NA | Completed
| TOTAL | [11 empty] | 50853600

## NITT
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) : |  | NIGERIAN INSTITUTE OF TRANSPORT TECHNOLOGY
MINISTRY : |  | MINISTRY OF TRANSPORT TECHNOLOGY
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) 2014 | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2014 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | Supply and Installation of Security Equipment | 22/04/13 Daily Trust, Guardian &FTJ | IMTB | Open Competitive Bidding | 29/07/2013 | August, 2013 | 45452393 | N/A | 27/08/2013 | 74095497 | Umobehn Nig. Ltd. | 2013-03-09 | 74095497 | 4 Weeks | 26/09/2013 | 44878522.45 | 2013-03-10 | Ongoing | 61% | NA | NA
2 | Upgrading of Water Supply System | 22/04/13 Daily Trust, Guardian &FTJ | IMTB | Open Competitive Bidding | 29/07/2013 | August, 2013 | 44289228 | N/A | 27/08/2013 | 141851409.3 | Umobehn Nig. Ltd. | 2013-03-09 | 141851409.3 | 12 Weeks | 26/09/2013 | 99295986.51 | 2013-03-12 | Ongoing | 70% | NA | NA
3 | Supply and Installation of Intercom Equipment/Facilities | 22/04/13 Daily Trust, Guardian &FTJ | IMTB | Open Competitive Bidding | 29/07/2013 | August, 2013 |  | N/A | 27/08/2013 | 8900003 | Transtime Nig. Ltd | 2013-04-09 | 8900003 | 4 Weeks | 20/12/2013 | 4485000 | 30/10/2013 | Completed | 100% | NA | NA
4 | Dedicated Power Supply 33/11 KVA Power line | 14/07/2014 Daily Trust, Guardian&FTJ | IMTB | Open Competitive Bidding | 25/08/2014 | September, 2014 | 105000000 | N/A | 24/10/2014 | 95971800 | Elektron Nig. Ltd. | 31/10/2014 | 95971800 | Four months | None | Nil | 28/02/2015 | Ongoing | 40% | NA | NA
5 | Feasibility Studies, Consultancy and Design of New office Block for 2 new created Departments | 14/07/2014 Daily Trust, Guardian & FTJ | IMTB | Open Competitive Bidding | 25/08/2014 | September, 2014 | 50326439 | N/A | 24/10/2014 | 20056337.39 | Tera Consults Limited and others | 31/10/2014 | 20056337.39 | Four months | None | Nil | 21/12/2014 | Ongoing | 100% | NA | NA
6 | Rehabilitation of Registrar's Official Residence | 14/07/2014 Daily Trust, Guardian & FTJ | IMTB | Open Competitive Bidding | 25/08/2014 | September, 2014 | 100000000 | N/A | 24/10/2014 | 8930864.75 | Bazuf Worldwide Services Ltd. | 31/10/2014 | 8930864.75 | 3 Weeks | None | Nil | 31/12/2014 | Ongoing | 80% | NA | NA
7 | Rehabilitation of Senior Staff Quarters Block A1 | 14/07/2014 Daily Trust, Guardian & FTJ | IMTB | Open Competitive Bidding | 25/08/2014 | September, 2014 | 100000000 | N/A | 24/10/2014 | 16249149.35 | Safaz Intergrated Services Ltd. | 31/10/2014 | 16249149.35 | 6 Weeks | None | Nil | 31/12/2014 | Ongoing | 80% | NA | NA
8 | Rehabilitation of junior Staff Quarters Block B8 | 14/07/2014 Daily Trust, Guardian & FTJ | IMTB | Open Competitive Bidding | 25/08/2014 | August, 2014 | 100000000 | N/A | 24/10/2014 | 9879886.95 | Alhaji Sarki Mailemu Global Links Nig.Ltd. | 31/10/2014 | 9879886.95 | 6 Weeks | None | Nil | 31/12/2014 | Completed | 100% | NA | NA
9 | NITT Outreach Learning Programme Portharcourt Annex | 12/04/2010 Daily Trust, Guardian & FTJ | IMTB | Open Competitive Bidding | 2010-09-07 | December, 2010 | 305650879 | N/A | 2010-03-12 | 110590199.14 | Globamak Developers Ltd. | 2010-07-12 | 110590199.14 | 30 Weeks | None | 50062184.55 | 30/08/2012 | Ongoing | 65% | NA | NA
10 | NITT Outreach Learning Centre Lagos Annex | 12/04/2010 Daily Trust, Guardian & FTJ | IMTB | Open Competitive Bidding | 2010-09-07 | August, 2010 | 305650879 | N/A | 28/08/2010 | 144574408.35 | Kyas Ltd. | 2010-03-08 | 144574408.35 | 17 Weeks | 24/08/2010 | 109193737.6 | 30/06/2014 | Ongoing | 85% | 17/03/2014 | NA
11 | Purchase of Library Books | 14/07/2014 Daily Trust, Guardian&FTJ | IMTB | Open Competitive Bidding | 25/08/2014 | September, 2014 | 50000000 | N/A | 2014-01-09 | 48597546.18 | Maccat Nig. Ltd | 2014-10-09 | 48597546.18 | 6 Weeks | 30/10/2014 | 7289631.92 | 30/12/2014 | Ongoing | 20% | NA | NA
12 | Equipping of TTC | 12/04/2010 Daily Trust, Guardian & FTJ | IMTB | Open Competitive Bidding | 2010-09-07 | August, 2010 | 302117578 | N/A | 28/08/2010 | 237607477.66 | Cyrilpet Ventures Ltd and Others | 2012-08-11 | 3633148642.07 | 3Months | 06/10/2012 and Others | 276806250 | 31/01/2013 | Ongoing | 60% | NA | NA
| TOTAL | [11 empty] | 199685584.62

## NPA
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) : |  | NIGERIAN PORTS AUTHORITY
MINISTRY : |  | TRANSPORT
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [10 empty] | CONTRACT AWARD | [6 empty] | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | RECURRENT / CAPITAL EXPENDITURE | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | COMPANY' ADDRESS | DATE OF CONTRACT AWARD | ACTUAL EXPEDITURE (NGN) (CONTRACT VALUE) | ACTUAL EXPEDITURE (NGN) (CONTRACT VALUE) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 24/10/2014 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS % of Completion | REMARKS
1 | Consultancy & professional Services for the Establishment of Command Control Communication & intelligence centre for NPA | CAPITAL EXPENDITURE | N/A | MTB | Direct Procurement | Sept. 2013 | N/A | 1717853000 | BPP 19/2/14 | MTB 5/5/14 | No | Galaxy Backbone PLC | 61, Adetokunbo Crescent, Wuse 2, Abuja. +234-9-4612481, - 2 | 27/5/14 | 86198978.91 |  | 14 months | 2014-06-01 | 56029282.28 | Aug. 2014 | 75% | Project On-going
2 | Establishment of Command Control Communication and Intelligence centre for the Ports | CAPITAL EXPENDITURE | N/A | FEC | Selective Tendering BPP No Objection Certification | 16/10/12 |  | 1717853000 | BPP 2/7/12 |  | Yes | Stampford International Liited | Plot 745, Kade Street, Off Aminu Kano Crescent, Wuse 2, Abuja | 26/7/13 | 2397315867 |  | 14 months | 15/5/14 | 1797986900.25 | July, 2015 | 75% | Project On-going
3 | Design, Construction & commissioning of one Executive Passenger Boat | CAPITAL EXPENDITURE | 17/9/12 | FEC | Competitive Bidding | 30/10/12 |  | 106750000 | N/A | 2014-05-05 | Yes | Mutuall Commitment Nig. Ltd. | 6, Atbana Street, Wuse 2, Abuja FCT. 0803 470 0993 0803 321 0348 | 20/5/14 |  | $4,818,822.00 | 9 months |  |  |  |  | Awaiting FEC approval
4 | Design, Construction & commissioning of Marine Vessels - Two (2Nos) Pilot Cutters. | CAPITAL EXPENDITURE | 17/9/12 | FEC | Competitive Bidding | 30/10/12 |  | 300000000 | N/A | 2014-05-05 | Yes | Mutuall Commitment Nig. Ltd. | 6, Atbana Street, Wuse 2, Abuja FCT. 0803 470 0993 0803 321 0348 | 20/5/14 |  | $6,281,562.00 | 14 months |  | 0 |  |  | Awaiting FEC approval
5 | Consultancy Services for the Dredging of Esravos - Warri- Aladja- Koko Channel in Warri Pilotage District, Delta State. | CAPITAL EXPENDITURE |  | FEC | Competitive Bidding |  |  | Lumpsum 1,000,000,000 | N/A |  |  | Aim Consultants Limited | Plot 267A Etim Inyang Crescent | 24/2/14 | 274990038.27 |  |  |  | 41248505.74 |  |  | On-Going
6 | Commissioning of Consultancy Services for the Financial Audit of Port & Cargo Handling Terminal, Tin-Can Island Port Complex | RECURRENT EXPENDITURE |  |  | Competitive Bidding |  |  | 1300000 |  | 2013-10-12 | Yes | Segun Aremu & Co | Plot 9, Barnawa Close, Challawa GRA, Barnawa, Kaduna. 0803 409 1167 0803 306 6142 | 29/1/14 | 19422500 |  | 3 months |  | 12624625
7 | Drilling of Borehole & Water Treatment Plant at Fire Service Station, LPC, Apapa | RECURRENT EXPENDITURE |  |  | Competitive Bidding |  |  | lumpsum 181,914 |  |  |  | Royal Diadem Consult | 12, Seguela Street, Wuse 2, Abuja, FCT. 0803 706 5878 | 16/1/14 | 17114769 |  | 8 weeks
8 | Drilling of Borehole & Water Treatment Plant at FederalLighter Terminal (FLT) Onne Port, Rivers State. | RECURRENT EXPENDITURE |  |  | Competitive Bidding |  |  | lumpsum 181,914 |  |  |  | Carnia Limited | 6B, Bendel Close, Off bishop Aboyade Cole Street. Victoria Island, Lagos. 0808 299 2090 | 2014-07-02 | 17330500 |  | 8 weeks |  | 15715612.5 |  |  | On Going
9 | Expansion and Rehabilitation of Tin Can Island Port Service Lane, Tin Can , Lagos | CAPITAL EXPENDITURE |  | 2014-02-05 | Competitive Bidding |  |  | 400,000,000( Provisionally) |  | MTB |  | Messrs Deux Project Limited | 261A Corporate Drive, Dolphin Estate, Ikoyi, Lagos. +234 706 106 1154 | 27/5/14 | 812993241.51 |  | 12 months |  | 121948987 |  | 15% | On-Going
10 | Rehabilitation of Fire Service/Harbours Building at FLT, Onne Port Complex | CAPITAL EXPENDITURE |  |  | Competitive Bidding | [6 empty] | Akiz International Limted | 1, Calabar Close, Garki, Abuja. 0818 690 1012 | 2014-03-02 | 20304208 |  | 90 days |  | 18412221.89
11 | SUPPLY OF KASPERSKY ENTERPRISE ANTIVIRUS APPLICATION | CAPITAL EXPENDITURE | 23/10/13 | PTB | Competitive bidding | 13/11/13 | Dec, 13 | Lumpsum 1,000,400,000 | N/A | 20/1/14 | Yes | Messrs. Kwod Systems Company Limited | 11, Ugbeje Aki Street, Maryland Lagos. 08025922513; 07039171205 | 28/2/14 | 19845000 |  | 60days |  | N19,845,000.00 |  | 100% | Job completed
12 | MAINTENANCE CORROSSION COATING OF THE SHEET PILES AT CALABAR PORT | RECURRENT EXPENDITURE | 29/7/13 | PTB | Competitive bidding | 2013-12-09 | Dec, 13 | 320719000 | N/A | 20/1/14 | Yes | Messrs. Gojopal Nigeria Limited | 19A, Colorado Close, Ministers Hill, Maitama, Abuja. 08022900909 | 2014-05-02 | 41466180 |  | 8 weeks | 2014-04-01 | 39392871 |  | 100% | Job completed
13 | PROVISION OF PORT AND TERMINALS SFOH ENLIGHTENMENT AND MOBILIZATION AT LAGOS PORT COMPLEX | CAPITAL EXPENDITURE | 23/10/13 | PTB | Competitive bidding | 27/11/13 | Dec, 13 | Lumpsum 1,414,191,000 | N/A | 20/1/14 | Yes | Messrs Avalon International Nigeria Limited | Plot 1700, Violet Young Close, Off Adetokunbo Ademola Street, Victoria Island, Lagos | 24/1/14 | 17500000 |  | 3 weeks |  | 17500000 |  | 100% | Job completed
14 | PROVISION OF PORT AND TERMINALS SFOH ENLIGHTENMENT AND MOBILIZATION AT TIN CAN ISLAND PORT COMPLEX | CAPITAL EXPENDITURE | 23/10/13 | PTB | Competitive bidding | 27/11/13 | Dec, 13 | Lumpsum 1,414,191,000 | N/A | 20/1/14 | Yes | Messrs Macadams Baking Systems Nigeria Limited | Ojuolape House, Plot 9, Block C. CBD, Aluasa, Ikeja, Lagos | 24/1/14 | 17500000 |  | 3 weeks |  | 17500000 |  | 100% | Job completed
15 | PROVISION OF PORT AND TERMINALS SFOH ENLIGHTENMENT AND MOBILIZATION AT RIVERS PORT COMPLEX | CAPITAL EXPENDITURE | 23/10/13 | PTB | Competitive bidding | 27/11/13 | Dec, 13 | Lumpsum 1,414,191,000 | N/A | 20/1/14 | Yes | Messrs Panat Nigeria Limited | Ojuolape House, Plot 9, Block C. P.M.B. 21013, Aluasa | 24/1/14 | 17500000 |  | 3 weeks |  | 17500000 |  | 100% | Job completed
16 | PROVISION OF PORT AND TERMINALS SFOH ENLIGHTENMENT AND MOBILIZATION AT CALABAR PORT COMPLEX | CAPITAL EXPENDITURE | 23/10/13 | PTB | Competitive bidding | 27/11/13 | Dec, 13 | Lumpsum 1,414,191,000 | N/A | 20/1/14 | Yes | Messrs Safety Centre International Limited | Opp. Port Harcourt Int'l Airport Hotel, Omagwa, PH, Rivers State. 0802300 2275 | 24/1/14 | 17500000 |  | 3 weeks |  | 17500000 |  | 100% | Job completed
17 | PROVISION OF PORT AND TERMINALS SFOH ENLIGHTENMENT AND MOBILIZATION AT ONNE PORT | CAPITAL EXPENDITURE | 23/10/13 | PTB | Competitive bidding | 27/11/13 | Dec, 13 | Lumpsum 1,414,191,000 | N/A | 20/1/14 | Yes | Messrs Intertec Engineering Nigeria Limited | Opp. Port Harcourt Int'l Airport Hotel, Omagwa, PH, Rivers State. 07033993001 | 24/1/14 | 17500000 |  | 3 weeks |  | 17500000 |  | 100% | Job completed
18 | PROVISION OF PORT AND TERMINALS SFOH ENLIGHTENMENT AND MOBILIZATION AT DELTA PORT COMPLEX | CAPITAL EXPENDITURE | 23/10/13 | PTB | Competitive bidding | 27/11/13 | Dec, 13 | Lumpsum 1,414,191,000 | N/A | 20/1/14 | Yes | Messrs The SAO Group | Ojuolape House, Plot 9, Aluasa, Ikeja, Lagos. 08033904106 | 24/1/14 | 17500000 |  | 3 weeks |  | 17500000 |  | 100% | Job completed
19 | DEPLOYMENT OF PAY DIRECT PAYMENT SOLUTION BY INTERSWITCH LTD FOR NPA | CAPITAL EXPENDITURE |  | PTB | Repeat Procurement |  |  | Lumpsum 1,000,400,000 | N/A |  | Yes | Messrs Interswitch Limited | Plot1648C, Oko-Awo Close. Victoria Island, Lagos 07040303058 | 28/1/14 | 4725000 |  | 1 month |  | 5165862.05 |  | 100% | N4,725,000.00 has been paid on the Equipment . Now a fee of 1.5% is paid on the Bank Lodgement so far.
20 | CONSTRUCTION OF REINFORCED CONCRETE PAVEMENT AT MARINE DOCKYARD, CALABAR PORT | RECURRENT EXPENDITURE | 27/8/13 | PTB | Competitive bidding | 27/11/13 | Nov, 13 | 200000000 | N/A | 20/1/14 | Yes | Messrs Hamif Projects & Services Limited | No. 24, Bujumbune Street, Wuse 2, Abuja. 08091122099 | 2014-05-02 | 19462800 |  | 2 months |  | 18489660 |  | 100% | Job completed
21 | PRINTING AND SUPPLY OF SHIP ENTRY NOTICE FORM “B” | RECURRENT EXPENDITURE | 13/9/13 | PTB | Competitive bidding | 28/10/13 | Nov, 13 | lumpsum 223102000 | N/A | 20/1/14 | Yes | Messrs Dami Ventures | 61, Mafoluku Rd. Mafoluku- Oshodi 08023180182 | 30/1/14 | 7875000 |  | 4 weeks. |  | 7875000 |  | 100% | Job completed
22 | RENEWAL OF EXTRA AWARENESS CAMPAIGN FOR NIGERIAN PORTS AUTHORITY ON NTA INTERNATIONAL NETWORK | RECURRENT EXPENDITURE |  | PTB | Renewal of Contract |  | 2013-06-12 | lumpsum 282,915,000 | N/A | 20/1/14 | Yes | Messrs Florish Ventures | 6, Awoseyin Street, Shomolu, Lagos. 08033120691 | 28/1/14 | 19580550 |  | 13 weeks |  | 19580550 |  | 100% | Job completed
23 | RE-ROOFING, RENOVATION AND EXTERNAL WORKS OF MAGISTRATE COURT BUILDING, LAGOS PORT COMPLEX, APAPA | RECURRENT EXPENDITURE | 21/10/13 | PTB | Competitive bidding | 28/10/13 | Nov, 13 | Lumpsum 205,619,000 | N/A | 20/1/14 | Yes | Messrs Lende Ventures Limited | Suites 1 & 2 CFA Plaza Adjacent School of Nursing Gate, Jekadafari, Gombe, Gombe State. 08055060100 | 28/1/14 | 9914427.07 |  | 4 weeks |  | 9421705.71 |  | 100% | Job completed
24 | CONSTRUCTION OF WATER TREATMENT PLANT, BUILDING AND PROVISION OF WATER STORAGE TANK AT FIRE SERVICE STATION, NPA HEADQUARTERS, MARINA –LAGOS | RECURRENT EXPENDITURE | 25/11/13 | PTB | Competitive bidding | 30/12/13 | Jan,14 | Lumpsum 205,619,000 | N/A | 20/1/14 | Yes | Messrs Tob Drill Limited | Plot33, Mobolaji Johnson Avenue, Oregun Industrial Layout, Ikeja, Lagos. 01-7615403; 08033158566 | 2014-05-02 | 9426003.4 |  | 8 weeks |  | 8547671.27 |  | 100%
25 | RE-ROOFING, GENERAL RENOVATION OF MARINE POLICE STATION AND EXTERNAL WORKS AT ELEGBATA, MARINA – LAGOS | RECURRENT EXPENDITURE | 26/8/13 | PTB | Competitive bidding | 2013-12-12 | Jan,14 | Lumpsum 205,619,000 | N/A | 20/1/14 | Yes | Messrs Amstek Investment Concept Limited | 16B, Ijaiye Road, Ogba, Lagos. 08101755534 | 24/1/14 | 9650416.6 |  | 4 weeks. |  | 8751173.24
26 | RENOVATION/PROVISION OF PUBLIC ADDRESS SYSTEM, CONFERENCE TABLE AND EXECUTIVE CHAIRS AT CONFERENCE ROOM, NO 1, JOSEPH STREET, LAGOS | RECURRENT EXPENDITURE | 23/10/13 | PTB | Competitive bidding | 30/12/13 | Jan,14 | Lumpsum 205,619,000 | N/A | 20/1/14 | Yes | Messrs JBAF Investments Limited | No. 7, Port-Novo Street, Wuse 2, FCT. Abuja. 08078545812; 08069593623 | 30/1/14 | 9210000 |  | 8 weeks |  | 8749500 |  | 100%
27 | RE-ROOFING AND REHABILITATION OF ADMINISTRATION BLOCK EXTENSION OCCUPIED BY INDUSTRIAL RELATIONS, TRAINING AND TWO HOUSE UNIONS AT NEW PORT, WARRI | RECURRENT EXPENDITURE | 27/9/13 | PTB | Competitive bidding | 30/12/13 | Jan,14 | Lumpsum 205,619,000 | N/A | 20/1/14 | Yes | Messrs June Investment Nigeria Limited | Plot33, Mobolaji Johnson Avenue, Oregun Industrial Layout, Ikeja, Lagos. 08023203601 | 2014-05-02 | 19455765 |  | 180 days |  | 17359663.5
28 | UPGRADING OF POWER SUPPLY TO ENGINEERING YARD AND ITS ENVIRONS, FLT, ONNE | RECURRENT EXPENDITURE | 20/12/3 | PTB | Competitive bidding | 30/12/13 | Jan,14 | Lumpsum 205,619,000 | N/A | 20/1/14 | Yes | Messrs Volton Logistics Services Limited | 41, Bello dandago Rd, Kano. 08033305274 | 2014-03-02 | 8372175 |  | 8 weeks |  | 7953566.25 |  | 100%
29 | MAINTENANCE AND SERVICING OF ELECTRICAL POWER DISTRIBUTION NETWORK EQUIPMENT AND DEVICES AT RIVERS PORT, PORT HARCOURT | RECURRENT EXPENDITURE | 2012-07-12 | PTB | Competitive bidding | 2014-03-01 | Jan,14 | 100000000 | N/A | 20/1/14 | Yes | Messrs Exact Services Limited | 30/32 Creek Road (2nd Floor) P.O.Box. 1000, Apapa, Lagos. 01-4817663; 01-3200490 08037209660 | 31/1/14 | 15044400 |  | one (1) year |  | 3761100 |  | 45%
30 | THE MAINTENANCE AND SERVICING OF ELECTRICAL POWER DISTRIBUTION NETWORK EQUIPMENT AND DEVICES AT ONNE PORT, PORT HARCOURT | RECURRENT EXPENDITURE | 2012-07-12 | PTB | Competitive bidding | 2014-03-01 | Jan,14 | 100000000 | N/A | 20/1/14 | Yes | Messrs Excel Capital Limited | 30/32 Creek Road (2nd Floor) P.O.Box. 1000, Apapa, Lagos. 08039333399 | 31/1/14 | 14070000 |  | 1 year |  |  |  | 45%
31 | CONSULTANCY SERVICES FOR THE AUDIT OF ENL TERMINAL, APAPA | RECURRENT EXPENDITURE | 2013-07-10 | PTB | Competitive bidding | 21/10/13 | Dec, 13 | 655000000 | N/A | 20/1/14 | Yes | Messrs Bayco Consulting | 6A, Amudalat Ajiun Street, Ikota Royal Estate. Behind Zenith Bank. Opp. Mega Chicken, Lekki Epe Expressway, Ikota, Lagos 08033416065 |  | 18574000 |  | (3) months |  | 12073100
32 | RECOMMENDATION FOR ACTUARIAL VALUATION OF THE AUTHORITY’S PENSIONS AND GRATUITY SCHEMES AS AT 31ST DECEMBER, 2012 & 2013 | RECURRENT EXPENDITURE |  | PTB | Renewal of Contract |  |  | Lumpsum 1,000,400,000 | N/A | 20/1/14 |  | Messrs Alexander Forbes Consulting Actuaries Nigeria Limited | 2nd Floor. Rio Plaza, 235 Muri Okunola Street, Victoria Island | 29/1/14 | 6000000 |  | 1 month |  | 6000000 |  | 100% | Job completed
33 | COMPUTERIZATION OF NPA SYSTEMS: RENEWAL OF SUPPORT AND SUPERVISORY SERVICES FOR SAGE PASTEL EVOLUTION FOR 2013 TO 2014 | CAPITAL EXPENDITURE |  | PTB | Renewal of Contract |  |  | lumpsum 2,510,810,000.00 | N/A | 20/1/14 |  | Messrs Ade-Odiachi & Co | Robert Ade-Odiachi Shippers Plaza, 4 Park Lane, Apapa, Lagos. 0709 800 3989 | 2014-05-02 | 17640000 |  | 12 months |  | 17640000 |  | 100% | Job completed
34 | SUPPLY OF 66,000 LITRES OF AGO (DIESEL) FOR NIGERIAN PORTS AUTHORITY HEADQUARTERS & NO 1 JOSEPH STREET, MARINA – LAGOS | RECURRENT EXPENDITURE |  | PTB | Competitive bidding (National Shopping) |  | 24/1/14 | Lumpsum 693,253,000 | N/A | 2014-11-03 | Yes | Messrs First Fortune Energy Co. Limited | 63, Kofo Abayomi Avenue, Apapa, Lagos. 01-9500980, 08062852233 | 28/1/14 | 11921250 |  | 1 week |  | 11921250 |  | 100% | Job completed
35 | BARTHYMETRIC SURVEY OF CALABAR CHANNEL | CAPITAL EXPENDITURE |  | PTB | Competitive bidding |  |  |  | N/A | 20/1/14 | Yes | Messrs Survicom Services Nigeria Limited | 62, ObiWali Road, Rumuigbo, PH | 27/1/14 | 49960000 |  | 1 month |  | 49960000 |  | 100% | Job completed
36 | SUPPLY OF OFFICE FURNITURE FOR PORT-HARCOURT PORT COMPLEX | CAPITAL EXPENDITURE |  | PTB | Competitive bidding |  |  | lumpsum 584,500,000 | N/A |  | Yes | Messrs Mog Holding Limited | 103, Allen Avenue, Ikeja, Lagos. 08033018324 | 21/1/14 | 47973400 |  | 2 weeks |  | 47972400 |  | 100% | Job completed
37 | REQUEST FOR SUPPLY OF 330 NOS PEPPER SPRAY | RECURRENT EXPENDITURE | 2013-06-12 | PTB | Competitive bidding | 30/12/13 | Jan,14 | Lumpsum 119,904.000 | N/A | 2014-06-03 | Yes | Messrs Monarch Imagination Limited | Suite A9, Doly Plaza Plot 1073, Adetokunbo Ademola Crescent, Wuse 2, Abuja. 08159369137 | 17/3/14 | 8835750 |  | 8 weeks |  | 8835750 |  | 100% | Job completed
38 | SUPPLY OF PERSONAL PROTECTIVE EQUIPMENT (PPE) FOR ENVIRONMENT DEPARTMENT, HEADQURTERS | CAPITAL EXPENDITURE | 23/10/13 | PTB | Competitive bidding | 30/12/13 | Jan,14 | lumpsum 1,414,191,000 | N/A | 2014-06-03 | Yes | Messrs Tripple ‘A’ Precision Services Limited | Dammje Shopping Complex, Jos Road Lafia, Nassarawa State. 0802 556 6265 0803 688 1106 | 20/3/14 | 9300000.75 |  | 10 weeks |  | 9300000.75 |  | 100% | Job completed
39 | SUPPLY OF POWER FROM FEEDER PILLAR (I) TO AN EXISTING FEEDER PILLAR (II) AT ENGINEERING WORKYARD AND EXTENSION OF POWER SUPPLY UNDER WATER CONTROL PANEL AT KLT I | RECURRENT EXPENDITURE | 2013-02-12 | PTB | Competitive bidding | 30/12/13 | Jan,14 | Lumpsum 111,773,000 | N/A | 2014-06-03 | Yes | Messrs Inland Chips Limited | B1, TOB Plaza, Ayodele Fanioki Avenue, Magodo, Isheri, Lagos. 08023203601 | 17/3/14 | 9225750 |  | 2 months |  | 8764462.5 |  | 20%
40 | REHABILITATION OF TOILETS AND REFELTING OF LEAKING ROOF OF WING ‘B’ OF THE ADMINISTRATION BUILDING, NEW PORT, WARRI | RECURRENT EXPENDITURE | 26/8/13 | PTB | Competitive bidding | 2014-03-01 | Jan,14 | Lumpsum 205,619,000 | N/A | 2014-06-03 | Yes | Messrs Akpufu Integrated Services Nigeria Limited | No. 1, Kudang Street, Off Monrovian Crescent Wuse 2, Abuja. 0808 693 5483 | 20/3/14 | 14144592 |  | 9 weeks |  | 0
41 | RENOVATION OF NPA ACCOMMODATION FOR NAVAL TASKFORCE, FOT, ONNE | RECURRENT EXPENDITURE | 20/11/13 | PTB | Competitive bidding | 2014-03-01 | Jan,14 | Lumpsum 205,619,000 | N/A | 2014-11-03 | Yes | Messrs Tropical Investment Nigeria Limited | No 104 Hadejia Road, Yankaba Qtrs. Kano. 0803 504 6500 | 20/3/14 | 8983590 |  | 8 weeks |  | 7636051.5
42 | REPLACEMENT OF OBSOLETE FITTING/REACTIVATION OF 12M PERIMETER SECURITY LIGHTING SYSTEM FROM DOCKYARD MAIN ACCESS ROAD TO DOCKYARD MANAGER’S OFFICE, PORT-HARCOURT | RECURRENT EXPENDITURE |  | PTB | Competitive bidding |  |  | ` | N/A | 2014-06-03 | Yes | Messrs Sule Adini Nigeria Limited |  | 30/3/14 | 9900450 |  | (4) weeks |  | 9404977.5 |  | 100%
43 | RENOVATION WORKS AT FIRE SERVICE STATION BLOCK, NEW PORT, WARRI | RECURRENT EXPENDITURE | 23/10/13 | PTB | Competitive bidding | 2013-11-11 | Jan,14 | Lumpsum 205,619,000 | N/A | 2014-06-03 | Yes | Messrs Deina Integrated Concept Limited | No 16, Buba Ardo Road, Jalingo, Taraba State. 0812 317 3477 | 17/3/14 | 9410467 |  | 10 weeks |  | 8939943.65 |  | 100%
44 | MAINTENANCE OF 500KVA (SOUND PROOF), 300KVA AND 250KVA GENERATORS AT ONNE PORT | RECURRENT EXPENDITURE | 17/5/13 | PTB | Competitive bidding | 30/12/13 | Jan,14 | Lumpsum 135,000,000 | N/A | 2014-06-03 | Yes | Messrs Excel Capita Limited | 30/32 Creek Road (2nd Floor) Apapa, Lagos. 01-481 7663, 01-320 0490 | 17/3/14 | 13818000 |  | 1 year |  |  |  | 45%
45 | MAINTENANCE AND SERVICING OF ELECTRICAL POWER DISTRIBUTION NETWORK AT WARRI PORT, DELTA STATE | RECURRENT EXPENDITURE | 17/5/13 | PTB | Competitive bidding | 2014-03-01 | Jan,14 | Lumpsum 135,000,000 | N/A | 2014-06-03 | Yes | Messrs Testmate Holdings | Plot 20C, Akin Ogunlewe Street , Victoria Island. Lagos. | 17/3/14 | 15682900 |  | 1 year |  |  |  | 45%
46 | MAINTENANCE AND SERVICING OF ELECTRICAL POWER DISTRIBUTION NETWORK AND DEVICES AT CALABAR PORT COMPLEX | RECURRENT EXPENDITURE | 17/5/13 | PTB | Competitive bidding | 2014-03-01 | Jan,14 | Lumpsum 135,000,000 | N/A | 2014-06-03 | Yes | Messrs Exact Services Limited | 30/32 Creek Road (2nd Floor) Apapa, Lagos. 01-481 7663, 01-320 0490 | 17/3/14 | 15044400 |  | 1 year |  | 0 |  | 45%
47 | MAINTENANCE OF 250KVA PERKINS (SUBSTATION 6) 250KVA PERKINS (BEHIND CPE’S BLOCK), 300KVA & 250KVA PERKINS (DOCKYARD), 250KVA AND 110 KVA GENERATORS IN PORT-HARCOURT | RECURRENT EXPENDITURE | 17/5/13 | PTB | Competitive bidding | 30/12/13 | Jan,14 | Lumpsum 135,000,000 | N/A | 2014-06-03 | Yes | Messrs Testmate Holdings | Plot 20C, Akin Ogunlewe Street , Victoria Island. Lagos. | 17/3/14 | 20106400 |  | 1 year |  |  |  | 45%
48 | MAINTENANCE OF 500KVA PERKINS (SOUND PROOF) 250KVA PERKINS (SOUND PROOF) AND 40KVA GENERATORS AT CALABAR PORT COMPLEX | RECURRENT EXPENDITURE |  | PTB | Competitive bidding | 30/12/13 | 2014-06-03 | lumpsum 44,000,000 | N/A | 2014-06-03 | Yes | Tuma Enterprises Limited | Tuma Enterprises Power & Ind. Engr. Services, 51B, Tony Eromosol Street Parkview, Ikoyi, Lagos. | 17/3/14 | 16821000 |  | 1 year |  |  |  | 45%
49 | SUPPLY OF 7NOS BREATHING APPARATUS SET FOR FIRE SERVICE DEPARTMENT | CAPITAL EXPENDITURE | 2013-10-10 | PTB | Competitive bidding | 2014-03-01 | Jan,14 | lumpsum 1,414,191,000 | N/A | 2014-06-03 | Yes | Messrs TZI Energy & Industry Services Limited | 12E Golden Park Estate Lekki-Aja Expressway, Lagos. 0803 454 7344, 0803 310 1388 | 17/3/14 | 19005000 |  | 4weeks |  | 19005000 |  | 100% | Job completed
50 | MAINTENANCE OF 810KVA PERKINS (SOUND PROOF), 500KVA PERKINS (SOUND PROOF) AND 100KVA GENERATORS AT DELTA PORT COMPLEX, WARRI | RECURRENT EXPENDITURE |  | PTB | Competitive bidding |  |  | lumpsum 44,000,000 | N/A | 2014-06-03 | Yes | Tuma Enterprises Limited | Tuma Enterprises Power & Ind. Engr. Services, 51B, Tony Eromosol Street Parkview, Ikoyi, Lagos. | 17/3/14 | 15842400 |  | 1 year |  |  |  | 25% | On-going
51 | RENOVATION OF DOCKYARD STORES AT RIVERS PORT, PORT-HARCOURT | RECURRENT EXPENDITURE | 21/11/13 | PTB | Competitive bidding | 2013-12-12 | Jan,14 | lumpsum 205,619,000 | N/A | 2014-06-03 | Yes | Messrs Benejaf International Limited | 150, East/West Road. Nkpolu, Rumuigbo. PH. Rivers State. 0815 597 5700 0815 597 5701 | 17/3/14 | 7005110.85 |  | 3 weeks |  | 6654855.31 |  | 100% | Job completed
52 | RENOVATION OF NPA ADMINISTRATION BUILDING AT FEDERAL LIGHTER TERMINAL, ONNE | RECURRENT EXPENDITURE | 29/11/13 | PTB | Competitive bidding | 2013-12-12 | Jan,14 | lumpsum 205,619,000 | N/A | 2014-06-03 | Yes | Messrs AB & PEE Engineering Services Limited | No. 1B, Lander Close, Off LiverPool Road, Apapa, Lagos | 17/3/14 | 19888550 |  | 2 weeks |  | 18035298.75 |  | 100% | Job completed
53 | SMS AND CRIME CONTROL SECURITY SYSTEM FOR NPA SECURITY PERSONNEL | RECURRENT EXPENDITURE | 20/12/13 | PTB | Competitive bidding | 30/12/13 | Jan,14 | 119904000 | N/A | 2014-06-03 | Yes | Messrs Anxan Global Investments Limited | Suite 4, Plot 80, Area A Extension Nyanyan FCT, Abuja. 0803 305 5763, 0802 321 8685 | 17/3/14 | 19500000 |  | 8 weeks |  | 19500000 |  | 100% | Job completed
54 | CONSTRUCTION OF 150MM CONCRETE PAVEMENT AND OTHER EXTERNAL WORKS AT THE FIRE SERVICE STATION, FEDERAL OCEAN TERMINAL, ONNE PORT | RECURRENT EXPENDITURE | 29/11/13 | PTB | Competitive bidding | 30/12/13 | Jan,14 | lumpsum 205,619,000 | N/A | 2014-06-03 | Yes | Messrs Mafadens Corporation Limited | No. 4, Randle Road, Apapa, Lagos. 0803 303 1712, 0803 453 8271 | 17/3/14 | 20575390 |  | 3 months |  | 18658137.75 |  | 80%
55 | RECONSTRUCTION AND REHABILITATION OF DILAPIDATED PUBLIC TOILET 1 AND BURNT TOILET BLOCK 2 AT NPA TRAILER PARK, NEW PORT WARRI | RECURRENT EXPENDITURE | 26/8/13 | PTB | Competitive bidding | 2014-09-01 | Jan,14 | lumpsum 205,619,000 | N/A | 2014-06-03 | Yes | Messrs Tiamiyu-Ade Nigeria Limited | Block 14, Plot 6, Kalejaiye Daisi Street, Magodo, G.R.A. Phase 1, Isheri - Lagos. 0803 315 8566 | 17/3/14 | 7218948 |  | 5 weeks
56 | SUPPLY OF FULL CHEMICAL SUITS AND FALL ARRESTORS | CAPITAL EXPENDITURE | 23/10/13 | PTB | Competitive bidding | 30/12/13 | Jan,14 | lumpsum 413,710,000 | N/A | 2014-06-03 | Yes | Messrs Nabas Global Resources | Suite 001, Ground Floor FMBN Building, Plot 266 Tafawa Balewa Way CBD, Abuja, FCT. 0803 225 1509, 0806 441 9119 | 18/3/15 | 10372320 |  | 2 weeks |  | 10372320 |  | 100% | Job completed
57 | SUPPLY OF UNIFORMS, PROTECTIVE GEAR AND OTHER ITEMS FOR FIRE SERVICE, SECURITY AND DRIVERS | RECURRENT EXPENDITURE |  | PTB | Competitive bidding | 2013-12-12 | Jan,14 | lumpsum 46,537,000 | N/A | 2014-06-03 | Yes | Messrs Labim Investment Limited | 6, Oyenubi Street, Oworonshoki, Lagos. 0802 309 6526 | 17/3/14 | 19968963 |  | 3 months |  | 0
58 | CONSTRUCTION OF TWO (2) TOILETS, RENOVATION OF 550KVA POWER HOUSE AND SIX (6NOS) TOILETS AT FUEL DUMP, CALABAR PORT | RECURRENT EXPENDITURE | 2013-10-10 | PTB | Competitive bidding | 2012-04-12 | Jan,14 | lumpsum 205,619,000 | N/A | 2014-06-03 | Yes | Messrs South Stream Energy Nigeria Limited | 12A Olarewaju Ninalowo Crescent, Lekki Phase 1, Lagos. 0805 618 4474 | 17/3/14 | 10852590 |  | 90 Days |  | 1627888.5 |  | 15% APG
59 | RENOVATION OF NIGERIAN PORTS POLICE (AREA COMMANDER’S OFFICE) WESTERN PORTS COMMAND, LAGOS PORT COMPLEX | RECURRENT EXPENDITURE | 27/9/13 | PTB | Competitive bidding | 30/12/13 | Jan,14 | lumpsum 205,619,000 | N/A | 2014-06-03 | Yes | Messrs Polar Business Solution Limited | 10, Fakeye Street Obawole, Iju, Lagos. | 17/3/14 | 14351232 |  | 6 weeks |  | 13633756.85 |  | 100% | Job Completed
60 | REACTIVATION OF POLES SECURITY LIGHT ALONG PORT ACCESS ROAD BETWEEN MAIN GATE AND QUAYS CUSTOM OFFICE, CALABAR PORT | RECURRENT EXPENDITURE | 2013-10-10 | PTB | Competitive bidding | 2014-03-01 | Jan,14 | lumpsum 111,773,000 | N/A | 2014-06-03 | Yes | Messrs Amugate Integrated Services | 7, Off Green Villa/Dimrose Street Boro Expressway, Yenogoa, Bayelsa State. 0803 688 7882; 0809 990 7080 | 17/3/14 | 15439000.72 |  | 5 weeks |  | 14667050
61 | REHABILITATION OF MAGISTRATE COURT BUILDING AT KIRIKIRI LIGHTER TERMINAL, PHASE I | RECURRENT EXPENDITURE | 23/10/13 | PTB | Competitive bidding | 30/12/13 | Jan,14 | lumpsum 205,619,000 | N/A | 2014-06-03 | Yes | Messrs Merit Branzuk Energy Limited | Suite 1, First Floor, Izon Warri House,, Central Business District Abuja. 0803 918 1435, 0816 163 0100 | 17/3/14 | 11994087.16 |  | 4 weeks
62 | PRINTING AND SUPPLY OF SAFETY SIGNAGES WITHIN WESTERN PORTS OPERATIONAL AREA | CAPITAL EXPENDITURE | 2013-12-08 | PTB | Competitive bidding | 26/9/13 | Nov,13 | lumpsum 1,414,191,000 | N/A | 2014-06-03 | Yes | Messrs Emjay Global Impex Limited | 54, Adeshiyan Street, Off Ilupeju By-Pass, Lagos 0802 325 9600 | 17/3/14 | 14231699 |  | 30 days |  | 14231699 |  | 100% | Job completed
63 | CONSULTANCY SERVICES FOR THE AUDIT OF INTELS TERMINAL B, WARRI NEW PORT | RECURRENT EXPENDITURE |  | PTB | Competitive bidding |  | Dec, 13 | 4000123000 | N/A | 2014-06-03 | Yes | Messrs William Adeyemi & Co | 42, Mambo Street, Wuse Zone 2, Abuja. 0802 033 8822, 0804 611 8583 | 20/3/14 | 19200000 |  | 3 months |  | 12480000
64 | PROVISION OF ALTERNATE BROADBAND INTERNET BANDWIDTH FOR THE AUTHORITY’S HEADQUARTERS | CAPITAL EXPENDITURE | 2013-04-12 | PTB | Competitive bidding | 2014-06-01 | Jan,14 | Lumpsum 1,000,400,000 | N/A | 2014-11-03 | Yes | Messrs Atorj Technology & Cyberspace Limited | 33, Saka Tinubu Street, Victoria Island, Lagos. 0806 206 4340 0704 496 7548 | 26/3/14 | 19687500 |  | 8 weeks |  | 19687500 |  | 100% | Job completed
65 | SUPPLY OF 66,000 LITRES OF AGO (DIESEL) FOR NIGERIAN PORTS AUTHORITY HEADQUARTERS AND NO. 1 JOSEPH STREET, MARINA, LAGOS | RECURRENT EXPENDITURE |  | PTB | Competitive bidding |  | Jan, 2014 | 693253000 | N/A | 2014-11-03 | Yes | Messrs First Fortune Global Energy Co. Limited | 63, Kofo Abayomi Avenue, Apapa, +234-1-950 980 | 18/3/14 | 12375000 |  | 1 week |  | N12,375,000.00 |  | 100% | Job completed
66 | REPLACEMENT AND RE-ROUTING OF FAULTY SECTION OF HT CABLE BETWEEN SUB-STATION A & B ON RING 1 OF HT NETWORK AT DELTA PORT, WARRI | CAPITAL EXPENDITURE | 2013-03-06 | PTB | Competitive bidding | 18/7/14 | Feb, 2014 | 70000000 | N/A | 2014-11-03 | Yes | Messrs MB Integrated Electrical & Data Services Limited | 2nd Floor Tosland Plaza, 1, Warehouse Road, Apapa, Lagos. 0805 626 4876 0705 577 0665 | 20/3/14 | 44503200 |  | 30 days |  | 42278040 |  | 20%
67 | CONSTRUCTION OF HEALTH CENTRE AT BALANGA/BILIRI LOCAL GOVERNMENT AREA, GOMBE STATE (CORPORATE SOCIAL RESPONSIBILITY) | CAPITAL EXPENDITURE |  | PTB | Competitive bidding | 13/11/13 | Nov,13 | 185250000 | N/A | 2014-11-03 | yes | Messrs Musasa Medical Equipment Limited | 5, Nasarawa Quarters, Gombe, Gombe State. 0803 698 0996 | 20/3/14 | 20830638 |  | 6 months |  | 19789106.1
68 | PROVISION/INSTALLATION OF WATER HYDRANT AT PORT-HARCOURT | RECURRENT EXPENDITURE | 26/8/13 | PTB | Competitive bidding | 2013-07-10 | Jan,14 | 205619000 | N/A | 2014-11-03 | Yes | Messrs Imanil Haq Nigeria Limited | D71, Kabuga Housing, Kano State. 0806 089 5506 0809 094 2431 | 21/3/14 | 7934850 |  | 8 weeks |  | 7538106.5975 |  | 100%
69 | GENERAL RENOVATION AND PAINTING OF NPA BUILDING AT WARRI PORT COMPLEX | RECURRENT EXPENDITURE | 26/8/13 | PTB | Competitive bidding | 2013-07-10 | Jan,14 | 205619000 | N/A | 2014-11-03 | Yes | Messrs Gold Leng Investment Limited | 4, Ibadan street, Behind Shopping Complex, Jimeta, Yola. 0803 729 1460 0803 351 6367 | 21/3/14 | 31433351.4 |  | 10 weeks |  | 0
70 | SUPPLY AND INSTALLATION OF CISCO SWITCHES FOR DELTA PORTS | CAPITAL EXPENDITURE | 29/11/13 | PTB | Competitive bidding | 2014-06-02 | Feb, 2014 | Lumpsum 1000400000 | N/A | 2014-11-03 | yes | Messrs Panat Nigeria Limited | Ojuolape House, Plot 9, Block C. CBD. Aluasa, Ikeja, Lagos. 0803 390 4106 | 21/3/14 | 19600000 |  | 6 weeks |  | 19600000 |  | 100% | Job completed
71 | EVALUATION REPORT ON FINANCIAL BIDS FOR SUPPLY OF OFFICE EQUIPMENT FOR PORT-HARCOURT PORT COMPLEX | CAPITAL EXPENDITURE | 17/6/13 | PTB | Competitive bidding | 30/7/13 | Nov,13 | 637164000 | N/A | 2014-11-03 | Yes | Messrs Wood Affairs Nigeria Limited | 322, Adetokunbo Ademola Crescent, Wuse 2, Abuja. 0803 778 6261 | 18/3/14 | 21219791.25 |  | 2 weeks |  | 21219791.25 |  | 100% | Job completed
72 | SUPPLY OF FIVE (5 NOS) EARLY WARNING FIRE ALARM SYSTEMS FOR FIRE SERVICE DEPARTMENT | CAPITAL EXPENDITURE | 2014-10-01 | PTB | Competitive bidding | 2014-10-02 | Feb, 2014 | lumpsum 1,088,450,000 | N/A | 2014-11-03 | Yes | Messrs Umuoga Ventures Limited | 11A, Agarawu Street, Lagos Island. 0704 073 1950 0805 682 5095 | 18/3/14 | 19950000 |  | 3 weeks |  | 19950000 |  | 0%
73 | SUPPLY AND INSTALLATION OF CISCO SWITCHES FOR CALABAR PORT | CAPITAL EXPENDITURE | 29/11/13 | PTB | Competitive bidding | 2014-06-02 | Feb, 2014 | Lumpsum 1000400000 | N/A | 2014-11-03 | yes | Messrs Panat Nigeria Limited | Ojuolape House, Plot 9, Block C. CBD. Aluasa, Ikeja, Lagos. 0803 322 6549 | 21/3/14 | 19600000 |  | 6 weeks |  | 19600000 |  | 100% | Job completed
74 | ESTABLISHMENT OF RADIO LINK BETWEEN NPA AND CUSTOM OFFICES | CAPITAL EXPENDITURE | 14/12/13 | PTB | Competitive bidding | 2014-06-02 | Feb, 2014 | Lumpsum 1000400000 | N/A | 2014-11-03 | yes | Messrs Leaderitte Nigeria Limited | 34, Gwagwalada Road, Kuje. Abuja. | 26/3/14 | 18480395 |  | 4 weeks |  | 18480395 |  | 100% | Job completed
75 | DESIGN, DEVELOPMENT AND DEPLOYMENT OF INTRANET PORTAL FOR NIGERIAN PORTS AUTHORITY | CAPITAL EXPENDITURE | 14/12/13 | PTB | Competitive bidding | 2014-06-02 | Feb, 2014 | Lumpsum 1000400000 | N/A | 2014-11-03 | yes | Messrs Lahmah Universal Concept | 7, Uruguan Crescent Wuse 2, FCT. Abuja 0803 024 4381 | 26/3/14 | 18375000 |  | 9 weeks |  | 17456250 |  | 100% | Job completed
76 | SUPPLY OF LICENSED MICROSOFT WINDOWS 8 PROFESSIONAL FOR HEADQUARTERS, MARINA | CAPITAL EXPENDITURE |  | PTB | Competitive bidding | 2014-06-02 | Feb, 2014 | Lumpsum 1000400000 | N/A | 2014-11-03 | yes | Messrs Norden Global Resources Limited | Plot 192, Phase 1, Kubwa , Abuja. 0809 802 4381 | 26/3/14 | 16537500 |  | 5 weeks |  | 16537500 |  | 100% | Job completed
77 | SUPPLY OF TWO (2 NOS) ANGUS FIRE PORTABLE PUMPS 1300RPM (PETROL TYPE) | CAPITAL EXPENDITURE |  | PTB | Competitive bidding | 2014-10-02 | Feb, 2014 | lumpsum 1,088,450,000 | N/A | 2014-11-03 | Yes | Messrs Ojoma Integrated Services Limited | Suite2, 1st Floor Behind Eterna Filling Station, Utako, Abuja. 0703 434 6363 | 21/3/14 | 15750000 |  | 28 days |  | 15750000 |  | 100% | Job completed
78 | SUPPLY OF ONE HUNDRED (100) BEDS AND BEDDINGS FOR FIRE SERVICE DEPARTMENT | CAPITAL EXPENDITURE |  | PTB | Competitive bidding | 2014-10-02 | Feb, 2014 | lumpsum 1,088,450,000 | N/A | 2014-11-03 | Yes | Messrs Forte-Centris International Limited | 15A, Arusha Crescent, Off Nouakchott Street, Wuse Zone 1, Abuja. 0802 941 6090 0809 234 9792 | 18/3/14 | 13383399 |  | 6 weeks |  | 13383399 |  | 0%
79 | SUPPLY AND INSTALLATION OF CISCO SWITCHES FOR WESTERN ZONE | CAPITAL EXPENDITURE | 14/12/13 | PTB | Competitive bidding | 2014-06-02 | Feb, 2014 | Lumpsum 1000400000 | N/A | 2014-11-03 | Yes | Messrs Avalon Intercontinental Nigeria Limited | Plot 1700, Violet Yough Close, Off adetokunbo Ademola Street, Victoria, Island, Lagos | 25/3/14 | 19746173 |  | 6) weeks |  | 19746173 |  | 100% | Job completed
80 | SUPPLY AND INSTALLATION OF CISCO SWITCHES FOR TIN CAN ISLAND PORT COMPLEX | CAPITAL EXPENDITURE | 2013-09-12 | PTB | Competitive bidding | 2014-06-02 | Feb, 2014 | Lumpsum 1000400000 | N/A | 2014-11-03 | Yes | Messrs Avalon Intercontinental Nigeria Limited | Plot 1700, Violet Yough Close, Off adetokunbo Ademola Street, Victoria, Island, Lagos | 25/3/14 | 19746000 |  | 6) weeks |  | 19746000 |  | 100% | Job completed
81 | SUPPLY AND INSTALLATION OF CISCO SWITCHES FOR RIVERS PORT | CAPITAL EXPENDITURE | 2013-09-12 | PTB | Competitive bidding | 2014-06-02 | Feb, 2014 | Lumpsum 1000400000 | N/A | 2014-11-03 | Yes | Messrs Intertec Engineering Nigeria Limited | Ojuolape House, Plot 9, Block C. CBD. Aluasa, Ikeja, Lagos | 21/3/14 | 19700000 |  | 6) weeks |  | 19700000 |  | 100% | Job completed
82 | SUPPLY AND INSTALLATION OF CISCO SWITCHES FOR ONNE PORT | CAPITAL EXPENDITURE | 2013-09-12 | PTB | Competitive bidding | 2014-06-02 | Feb, 2014 | Lumpsum 1000400000 | N/A | 2014-11-03 | Yes | Messrs Panat Nigeria Limited | Ojuolape House, Plot 9, Block C. CBD. Aluasa, Ikeja, Lagos. 0803 322 6549 | 21/3/14 | 19600000 |  | 6 weeks |  | 19600000 |  | 100% | Job completed
83 | SUPPLY AND INSTALLATION OF CISCO SWITCHES FOR LAGOS PORT COMPLEX | CAPITAL EXPENDITURE | 2013-09-12 | PTB | Competitive bidding | 2014-06-02 | Feb, 2014 | Lumpsum 1000400000 | N/A | 2014-11-03 | Yes | Messrs Avalon Intercontinental Nigeria Limited | Plot 1700, Violet Yough Close, Off adetokunbo Ademola Street, Victoria, Island, Lagos | 25/3/14 | 19746173 |  | 6 weeks |  | 19746173 |  | 100% | Job completed
84 | SUPPLY AND INSTALLATION OF CISCO SWITCHES FOR JOSEPH STREET | CAPITAL EXPENDITURE | 14/12/13 | PTB | Competitive bidding | 2014-06-02 | Feb, 2014 | Lumpsum 1000400000 | N/A | 2014-11-03 | Yes | Messrs Intertec Engineering Nigeria Limited | Ojuolape House, Plot 9, Block C. CBD. Aluasa, Ikeja, Lagos | 21/3/14 | 19700000 |  | 6 weeks |  | 19700000 |  | 100% | Job completed
85 | SUPPLY AND INSTALLATION OF CISCO SWITCHES FOR EASTERN ZONE | CAPITAL EXPENDITURE | 14/12/13 | PTB | Competitive bidding | 2014-06-02 | Feb, 2014 | Lumpsum 1000400000 | N/A | 2014-11-03 | Yes | Messrs Intertec Engineering Nigeria Limited | Ojuolape House, Plot 9, Block C. CBD. Aluasa, Ikeja, Lagos | 21/3/14 | 19700000 |  | 6 weeks |  | 19700000 |  | 100% | Job completed
86 | SUPPLY OF THREE HUNDRED (300 NOS) THREE-IN-ONE SHOCK BATONS FOR SECURITY DEPARTMENT | RECURRENT EXPENDITURE | 14/11/13 | PTB | Competitive bidding | 2014-07-02 | Feb, 2014 | Lumpsum 119,904.000 | N/A | 2014-11-03 | Yes | Messrs Muststand International | 11, New Market Road, Opp. Union Bank, Gombe State. 0806 157 2366 0703 318 4249 | 20/3/14 | 10080000 |  | (3) weeks |  | 10080000 |  | 100% | Job completed
87 | SUPPLY AND INSTALLATION OF INVERTERS AT ICT SERVER ROOM, STERLING TOWERS | CAPITAL EXPENDITURE | 14/12/13 | PTB | Competitive bidding | 2014-06-02 | Feb, 2014 | Lumpsum 1000400000 | N/A | 2014-11-03 | Yes | Messrs Kwod Systems Company Limited | 11, Ugbeje Aki Street, Maryland, Lagos. 0802 502 2513 | 26/3/14 | 18900000 |  | 4 weeks |  | 18900000 |  | 100% | Job completed
88 | SUPPLY AND DEVELOPMENT OF ICT TROUBLESHOOTING, SUPPORT AND NETWORK MONITORING APPLICATION | CAPITAL EXPENDITURE | 14/12/13 | PTB | Competitive bidding | 2014-06-02 | Feb, 2014 | Lumpsum 1000400000 | N/A | 2014-11-03 | Yes | Messrs Satco Nigeria Limited | 240, Hadejia Road, Kano. | 26/3/14 | 16275000 |  | 5 weeks |  | 16275000 |  | 100% | Job completed
89 | SUPPLY, CONFIGURATION AND DEPLOYMENT OF LICENSED MICROSOFT WINDOWS 2012 SERVER | CAPITAL EXPENDITURE | 14/12/13 | PTB | Competitive bidding | 2014-06-02 | Feb, 2014 | Lumpsum 1000400000 | N/A | 2014-11-03 | yes | Messrs Calmness and Prime Ventures | 30, Mosumola Street, Aguda Surulere, Lagos. 0809 501 9443 | 26/3/14 | 19698000 |  | 6 weeks |  | 19698000
90 | SUPPLY AND INSTALLATION OF WALK-THROUGH METAL DETECTOR FOR LPC AND TCIPC | RECURRENT EXPENDITURE | 2014-09-01 | PTB | Competitive bidding | 2014-07-02 | Feb, 2014 | Lumpsum 119,904.000 | N/A | 2014-11-03 | Yes | Messrs Vicston Ventures Limited | 16, Sule Abore Street, Ojodu, Berger, Lagos | 20/3/14 | 13000000 |  | 8 weeks |  | 13000000 |  | 100% | Job completed
91 | PURCHASE OF PEGASYS INJECTION FOR HEPATITIS B POSITIVE NPA EMPLOYEES REQUIRING TREATMENT | RECURRENT EXPENDITURE |  | PTB | Direct Procurement |  | Feb, 2014 | Lumpsum 219,002,000 | N/A | 2014-11-03 | Yes | Messrs World-Wide Ventures Limited | 13, Fatai Atere Way. Matori, Lagos. 0805 529 9649 | 17/3/14 | 43452000 |  | 4 weeks |  | 43452000 |  | 100% | Job completed
92 | ILLUMINATION AND REACTIVATION OF SECURITY LIGHTENING POLES FROM NPA MAIN GATE TO COSTAIN ROADWAY, RIVERS PORT | RECURRENT EXPENDITURE | 2013-02-12 | PTB | Competitive bidding | 2014-07-02 | Feb, 2014 | Lumpsum 205619000 | N/A | 2014-11-03 | Yes | Messrs Anna Royal Limited | 8, Nwadialo Close, Opp. Flour Mills Estste. Satelite Town, Lagos. 0803 310 9687 | 21/5/14 | 5298825 |  | 5 weeks
93 | SINKING OF BOREHOLE AT SHIPPING AGENCY BUILDING MANAGED BY SEAVIEW PROPERTIES | RECURRENT EXPENDITURE |  | PTB | Competitive bidding | 2014-10-01 | Feb, 2014 | Lumpsum 205619000 | N/A | 2014-11-03 | Yes | Messrs Habas Integrated Concept Limited | Northside Apartment, BLK 2. FLT. 2. 6, Nguru Close, Off Emeka Anyaoku Crescent. Garki Area 2, Abuja. | 20/3/14 | 10991400 |  | 4 weeks
94 | RENOVATION OF POLICE STATION IN CALABAR PORT | RECURRENT EXPENDITURE |  | PTB | Competitive bidding | 2014-10-01 | Feb, 2014 | Lumpsum 205619000 | N/A | 2014-11-03 | Yes | Messrs Scallini Nigeria Limited | 5, Lifeline Close, Off Oludi street, GRA Phase 1, Port Harcourt, Rivers State. 0803 322 7513 | 20/3/14 | 9972177 |  | 12 weeks |  | 9972177 |  | 100%
95 | CONSTRUCTION OF PROTOTYPE BLOCKS OF CLASS ROOMS AT BICHI, KANO STATE | CAPITAL EXPENDITURE |  | PTB | Competitive bidding | 2014-10-01 | Feb, 2014 | Lumpsum 185,250,000.00 | N/A | 2014-11-03 | Yes | Messrs A.G.B. Radda Company Nigeria Limited | 38, Ado Bayero Road Kano State. 0803 316 2696 | 17/3/14 | 20830638.62 |  | 6 months |  | 20830638.62 |  | 100% | Job completed
96 | CONSTRUCTION OF PROTOTYPE BLOCKS OF CLASS ROOMS AT BOMO SCHOOL, PLATEAU STATE | CAPITAL EXPENDITURE |  | PTB | Competitive bidding | 2014-10-02 | Feb, 2014 | Lumpsum 185,250,000.00 | N/A | 2014-11-03 | Yes | Messrs Ingona Company Limited | Plot 81, 321 Road, Gwarimpa Estate, FCT. Abuja. 0803 314 4161 0805 273 4779 | 17/3/14 | 20999205 |  | 6 months |  | 19949244.75 |  | 100% | Job completed
97 | PRINTING OF FIRE SERVICE LOG BOOK (5,000 copies of fire Service Log Book, 500 copies of Fire Service Certificate of Compliance) | RECURRENT EXPENDITURE |  | PTB | Competitive bidding | 2014-10-01 | Feb, 2014 | Lumpsum 223,102,000 | N/A | 2014-11-03 | Yes | Messrs Art Thonade Engineering (Nig) Limited | 4, Irepo Street, Oke-Ira, Ogba, Ikeja 01-7730556. | 18/3/14 | 8006250 |  | 4 weeks |  | 8006250 |  | 100% | Job completed
98 | SUPPLY AND INSTALLATION OF 800AMPS 4 – WAY FEEDER PILLAR AT TERMINAL MANAGER’S PREMISES. kLT | RECURRENT EXPENDITURE |  | PTB | Competitive bidding | 2014-07-02 | Feb, 2014 | Lumpsum 111,773,000 | N/A | 2014-11-03 | Yes | Messrs Dafal Mani Nigeria Limited | 256A, Minna Main Mkt. Minna, Niger State. 0803 333 5421 | 20/3/14 | 6848100 |  | 4 weeks
99 | SUPPLY AND IMPLEMENTATION OF HELPDESK APPLICATION /INFRASTRUCTURE | CAPITAL EXPENDITURE | 2013-03-06 | PTB | Competitive bidding | 17/7/13 | Dec, 13 | Lumpsum 1000400000 | N/A | 2014-11-03 | yes | Messrs Telematics System Limited | 207, Herbert Macauley Street, Sabo, Yaba, Lagos | 22/5/14 | 19550000 |  | 8 weeks |  | 19550000 |  | 100% | Job completed
100 | SUPPLY OF HARDWARE AND NET ACCESSORIES | CAPITAL EXPENDITURE | 14/12/13 | PTB | Competitive bidding | 2013-07-02 | Feb, 2014 | Lumpsum 1000400000 | N/A | 2014-11-03 | Yes | Messrs Mazufan Contracting Agency Limited | F6, Yoruba Road, Kawo, Kaduna. | 26/3/14 | 18186000 |  | 28 days |  | 18186000 |  | 100% | Job completed
101 | SUPPLY OF TONERS FOR NIGERIAN PORTS AUTHORITY | CAPITAL EXPENDITURE | 14/12/13 | PTB | Competitive bidding | 2013-07-02 | Feb, 2014 | Lumpsum 1000400000 | N/A | 2014-11-03 | yes | Messrs Faloplus Ventures | 12, Bamgbopa street, Abule Ijesha, Yaba, Lagos. 0701 732 4688 0812 579 9077 | 26/3/14 | 19582500 |  | 9 weeks |  | 19582500 |  | 100% | Job completed
102 | SUPPLY AND DEVELOPMENT OF BACKUP AND DISASTER RECOVERY INFRASTRUCTURE FOR NIGERIAN PORTS AUTHORITY | CAPITAL EXPENDITURE | 14/12/13 | PTB | Competitive bidding | 2013-07-02 | Feb, 2014 | Lumpsum 1000400000 | N/A | 2014-11-03 | Yes | Messrs Atorj Technologies/Cyberspace | 33, Saka Tinubu Street, Victoria Island, Lagos. 0806 206 4340 0704 496 7548 | 26/3/14 | 18525000 |  | 8 weeks |  | 18525000 |  | 100% | Job completed
103 | REHABILITATION OF 12M SECURITY LIGHTING SYSTEMS WITHIN DREDGING/POLLUTION CONTROL DEPARTMENT, DOCKYARD, RIVERS PORT | RECURRENT EXPENDITURE | 2013-02-12 | PTB | Competitive bidding | 2013-07-02 | Feb, 2014 | Lumpsum 205619000 | N/A | 2014-11-03 | Yes | Messrs Dayot Global Investment Limited | 2, Abayomi Kiyomi Street, Off Rafiu Babatunde, Tinubu Road. Amuwo Odofin. 0803 302 0789, 0703 195 4820 | 21/3/14 | 8399685 |  | 6 weeks
104 | PRINTING AND SUPPLY OF FORM E.1 TO NPA HEADQUARTERS | RECURRENT EXPENDITURE |  | PTB | Competitive bidding |  |  | 212049000 | N/A | 2014-11-03 | Yes | Messrs Queens Bridge | Plot 23A, Alhaji Tokan Street, Alaka Estate Surulere, Lagos. 0803 718 0422 0803 307 2202 | 20/3/14 | 5512500 |  | 3 weeks |  |  |  | 100% | Job completed
105 | SUPPLY AND INSTALLATION OF STREET LIGHTING ALONG ACCESS ROAD FROM NPA GATE TO FIRST ROUND ABOUT AT KIRIKIRI LIGHTER TERMINAL, LAGOS | RECURRENT EXPENDITURE | 2013-02-12 | PTB | Competitive bidding | 2013-07-02 | Feb, 2014 | Lumpsum 111,773,000 | N/A | 2014-11-03 | yes | Messrs Dayot Global Investment Limited | 2, Abayomi Kiyomi Street, Off Rafiu Babatunde, Tinubu Road. Amuwo Odofin. 0803 302 0789, 0703 195 4820 | 2014-11-04 | 7091700 |  | 6 weeks
106 | CONSULTANCY SERVICES FOR THE AUDIT OF INTELS TERMINAL, FOT, ONNE | RECURRENT EXPENDITURE |  | PTB | Competitive bidding |  | January, 2014 |  | N/A | 2014-11-03 | Yes | Messrs Ben Ugwu & Co | Suite 203/205 Anbeez Plazs, 15, Ndola Crescent Zone 5, Abuja. 0803 720 2120 0807 737 8537 | 20/3/14 | 20160000 |  | 3 months |  |  |  |  | Job completed
107 | SUPPLY OF OFFICE FURNITURE FOR PORT AUTHORITY POLICE – EASTERN COMMAND | CAPITAL EXPENDITURE |  | PTB |  |  |  | lumpsum 584,500,000 | N/A | 2014-11-03 | Yes | Messrs Mog Holdings Limited | 4A Herbert Macauley Crescent GRA, Ikeja. Lagos. 0803 301 8324 | 14/3/14 | 14621775 |  | 4 weeks |  | 14621775 |  | 100% | Job completed
108 | SUPPLY OF 66,000 LITRES OF AGO (DIESEL) FOR NIGERIAN PORTS AUTHORITY HEADQUARTERS AND NO. 1 JOSEPH STREET, MARINA, LAGOS | RECURRENT EXPENDITURE |  | PTB | Competitive bidding |  | Feb,13 | Lumpsum 693,253,000 | N/A | 2014-11-03 | Yes | Messrs Umisal Nigeria Limited | Flat 5, No. 4 Abaji Close, Oyo Street, Area 2 Garki, Abuja. 081 545 4529 0809 783 3847 | 17/3/14 | 10494000 |  | 1 week |  | 10494000 |  | 100% | Job completed
109 | MONTHLY END USER SUPPORT AND MAINTENANCE OF INFORMATION SYSTEMS (IS) FOR NPA HEADQUARTERS, MARINA, LAGOS – REQUEST FOR RENEWAL OF CONTRACT | CAPITAL EXPENDITURE |  | PTB | Renewal Procurement |  |  | Lumpsum 1000400000 | N/A | 2014-11-03 | Yes | Messrs Project Wheel Engineering Limited | 47, Payne Crescent, Apapa, Lagos. 0803 821 6666 0809 821 6666 | 20/3/14 | 3450000 | 3450000 | 12 Months |  | 3,450,000.00 9months |  | 100% | Job completed
110 | REQUEST FOR RENEWAL OF FOURTH QUARTER MEDIA ENLIGHTENMENT PROGRAMMES ON SELECTED RADIO STATIONS | CAPITAL EXPENDITURE |  | PTB | Renewal Procurement |  | Feb,13 | Lumpsum 207,679,000 |  | 2014-11-03 |  | Messrs Gentle Bash Global Investment Limited | No. 38, Asmau Yakubu Street, Giginyu Qtrs, Kano, Kano State. 064938880, 08030706087, 08051042633 |  | 9970000 |  |  |  | 9970000 |  | 100% | Job completed
111 | DIRECT PROCUREMENT OF SIX (6 NOS) OF VARIOUS CATERPILLAR SOUND PROOF GENERATORS | CAPITAL EXPENDITURE |  | MTB | Direct Procurement |  | Feb,13 | 100000000 |  | 2014-11-03 |  | Messrs Mantrac Nigeria Limited | 2, Billingsway (Off Secretariat Road) Oregun Industrial Estate. Ikeja, Lagos |  | 97563024.15 |  | 40 days |  | 87936523.8
112 | RENOVATION OF FIRE SERVICE BUILDING AT CALABAR | RECURRENT EXPENDITURE |  | PTB | Competitive bidding | 26/11/13 | Nov,13 | Lumpsum 205619000 | N/A | 2014-11-03 | Yes | Messrs Oladua Ventures Limited | 31A, Bashorun Road, Ibadan, Oyo State. 02-8102879 | 21/3/14 | 11577797 |  | 4weeks |  | 11577797
113 | PROVISION OF PHCN CONTROL MINIMUM OCB WITH 12KV, 630A ISOLATOR PANEL, SUPPLY/INSTALLATION OF 11KV PANELS INCLUSIVE OF TERMINATION KITS IN DELTA PORT, WARRI | CAPITAL EXPENDITURE | 2013-03-06 | PTB | Competitive bidding | 17/7/13 | Dec, 13 | Lumpsum 145,000,000 | N/A | 2014-11-03 | Yes | Messrs Eraskonergy Nigeria Limited | 3, Uche Street, Off Stadium Road, Port Harcourt. +234-84-361479 | 27/3/14 | 46830000 |  | 12 weeks
114 | REHABILITATION OF DILAPIDATED NPA LIGHT HOUSE, PILOT QUARTERS & OTHER FACILITIES AT ESCRAVOS | CAPITAL EXPENDITURE | 26/8/13 | PTB | Competitive bidding | 2013-07-10 | Nov,13 | 100000000 | N/A | 2014-11-03 | yes | Messrs Jeckons Nigeria Limited | KM 5. refinery Road, Ekpan, Warri, Delta State. 0803 707 9030 0807 573 8518 | 20/3/14 | 26026331.63 |  | 12 weeks
115 | CONSTRUCTION AND SUPPLY OF ONE (1 NO) 35 METERS FAST ASSAULT PATROL CRAFT | CAPITAL EXPENDITURE |  | FEC | Direct Procurement |  | Feb, 2014 | lumpsum 1,075,000,000 | 2 July, 2013 | 2014-11-03 | Yes | Messrs Global Spectrum Energy Service Limited | 49A, Christ Maduka Street Lekki Phase 1, Lagos Tel: 0803 408 1116; 0705 111 6039 |  | 2197645080 |  | four (4) months |  |  |  |  | Procurement Process on-going
116 | CONSTRUCTION AND SUPPLY OF TWO (2 NOs) 12 METERS SECURITY PATROL BOATS (WATER FRONT PATROL) | CAPITAL EXPENDITURE |  | FEC | Direct Procurement |  | Feb, 2014 | lumpsum 1,075,000,000 | 2 July, 2013 | 2014-11-03 |  | Messrs ES Shipbuilding |  |  |  | $4,147,500.00 | 6 weeks |  |  |  |  | Procurement Process on-going
117 | CONSTRUCTION AND SUPPLY OF TWO (2 NOs) UNDER LIFT RECOVERY/TOWING TRUCK | CAPITAL EXPENDITURE |  | FEC | Direct Procurement |  | Feb, 2014 | lumpsum 1,075,000,000 | 2 July, 2013 | 2014-11-03 |  | Messrs IBT Associates Nigeria Limited |  |  | 180000000 |  | four (4) months |  |  |  |  | Procurement Process on-going
118 | CONSTRUCTION AND SUPPLY OF TWO (2 NOS) 9 METERS SECURITY PATROL BOATS (WATER FRONT PATROL) | CAPITAL EXPENDITURE |  | FEC | Direct Procurement | 14/10/14 | Feb, 2014 | lumpsum 1,075,000,000 | 2 July, 2013 | 2014-11-03 |  | Messrs TH Marine Limited |  |  |  | $3,654,420.00 | 6 weeks |  |  |  |  | Procurement Process on-going
119 | SUPPLY OF COLLAPSIBLE SECURITY/SPEED BARRIERS | CAPITAL EXPENDITURE |  | FEC | Direct Procurement |  | Feb, 2014 | lumpsum 10,000,000 | 2 July, 2013 | 2014-11-03 |  | Messrs Nachi Munak Technical Co. Limited | 23, Payne Crescent Apapa, Lagos |  | 10500000 |  | 3 Months |  | 10500000 |  | 100% | Procurement Process on-going
120 | SUPPLY OF FIREMAN SHIP BOOK 1 – 12 AND PART A – C (10 SETS) | CAPITAL EXPENDITURE | 21/1/14 | PTB | Competitive bidding | 2014-11-02 | Feb, 2014 | lumpsum 1,088,450,000 | N/A | 2014-11-03 | Yes | Messrs Tripple K Investment Limited | 21A, Sultan Road, Ext. Nasarawa, Kano State. 0803 638 3813 | 20/3/14 | 19737795 |  | 18 weeks |  | 19737795 |  | 100% | Job completed
121 | CONSULTANCY SERVICES ON INVENTORIZATION STUDY OF COMMUNITY DEVELOPMENT PROJECTS IN 2012 AND ITS IMPACT | RECURRENT EXPENDITURE |  |  | Competitive bidding |  |  | lumpsum 1,250,000,000.00 | N/A | 2014-11-03 | Yes | Messrs Admobile Media Limited | No 10, Oweh Stree Jibowu, Lagos. 0703 678 3411 | 18/3/14 | 16686377.5 |  | 10 weeks |  | 16686377.5 |  | 100% | Job completed
122 | CONSULTANCY SERVICES ON NEEDS ASSESSMENT OF NIGERIAN PORTS AUTHORITY HOST COMMUNITIES | RECURRENT EXPENDITURE |  |  | Competitive bidding |  |  | lumpsum 1,250,000,000.00 | N/A | 2014-11-03 | Yes | Messrs GR8 Measure Media Network Limited | 15B, Sowemimo Street GRA, Ikeja, Lagos. 0706 449 6516 | 18/3/14 | 19115822.25 |  | 10 weeks |  | 19115822.25 |  | 100% | Job completed
123 | CONSULTANCY SERVICES FOR THE AUDIT OF JULIUS BERGER TERMINAL, WARRI PORT | RECURRENT EXPENDITURE |  |  | Competitive bidding |  |  |  | N/A | 2014-11-03 | Yes | Messrs Sada Idris & Co | 2n Floor, FMB. Building, Central Business District, Abuja. 0803 788 2878 | 20/3/14 | 20336925 |  | 3 months |  | 13219001.2556
124 | SUPPLY AND INSTALLATION OF SECURITY SCANNING EQUIPMENT (X-RAY) IN LAGOS PORT COMPLEX | CAPITAL EXPENDITURE |  | FEC | Direct Procurement |  | Feb, 2014 | lumpsum 1,075,000,000 | 2 July, 2013 | 2014-11-03 |  | Messrs Edward Greens Global Limited |  |  |  | $6,290,812.50 | 6 months |  |  |  |  | Procurement Process on-going
125 | PROVISION OF OFFICE FURNITURE AT NPA CLINIC, BODE THOMAS, SURULERE | CAPITAL EXPENDITURE |  | PTB | Direct Procurement |  |  | lumpsum 584,500,000 | N/A | 2014-11-03 | Yes | Messrs Mog Holdings Limited | 4A Herbert Macauley Crescent GRA, Ikeja. Lagos. 0803 301 8324 | 14/3/14 | 19730550 |  | 4 weeks |  | 19730550 |  | 100%
126 | Reactivation/Extension of Security Lighting system opposite Administrative Block entrance to Wharf Gate, Onne Port | CAPITAL EXPENDITURE |  | PTB | Competitive bidding |  |  |  | N/A |  | Yes | Messrs Joimtec Nig. Limited | 5th Avenue, P Close, House 5. Festac Town, Lagos. 0805 117 8505 0803 724 2738 | 20/3/14 | 6976278.75 |  | 3 months |  | 19730550 |  | 100%
127 | MAINTENANCE AND SERVICING OF ELECTRICAL POWER DISTRIBUTION NETWORK AND DEVICES AT LAGOS PORT COMPLEX, APAPA | RECURRENT EXPENDITURE | 17/5/13 | PTB | Competitive bidding | 2014-03-01 | Jan,14 | Lumpsum 135,000,000 | N/A | 2014-06-03 | Yes | Messrs Exact Services Limited | 30/32 Creek Road (2nd Floor) Apapa, Lagos. 01-481 7663, 01-320 0490 | 17/3/14 | 19647600 |  | 1 year |  |  |  | 45%
128 | BRANDING AND STANDARDIZATION OF NPA LETTER HEAD PAPERS | RECURRENT EXPENDITURE |  | PTB | Competitive bidding |  |  | Lumpsum 212,049,000 | N/A | 19/3/14 | Yes | Messrs Zotok Limited | 1, Raimi Adedokun Lane, By Gbagada General Hospital, Lagos TelL 0802 082 2933; 0702 860 2146 | 30/3/14 | 14200000 |  | 4 weeks |  | 14200000 |  | 100% | Job completed
129 | EXTENSION OF WATER FROM FLT2 TO BRAWAL OIL TERMINAL AT FLT, ONNE PORT | CAPITAL EXPENDITURE | 2013-09-09 | PTB | Competitive bidding | 18/10/13 | Jan, 14 |  | N/A | 19/3/14 | Yes | Messrs Land and Water Partnership Limited | 12, Keffi Road , Barnawa, GRA. Kaduna. Tel: 0803 337 1670; 0703 190 4139 | 30/3/14 | 36072278 |  | 12 weeks
130 | REQUEST FOR APPROVAL FOR PROVISION OF OFFICE FURNITURE AT 5TH & 6TH FLOORS, HEADQUARTERS, MARINA | CAPITAL EXPENDITURE |  | PTB | Repeat Procurement |  |  | lumpsum 584,500,000 | N/A | 19/3/14 | Yes | Messrs Mog Holdings Limited | 4A, Herbert Macaulay Crescent, GRA. Ikeja, Lagos. 0803 301 8324 | 25/3/14 | 19880050 |  | 4 weeks |  | 19880050 |  | 100% | Job completed
131 | REQUEST FOR APPROVAL FOR SUPPLY OF SUPPLEMENTARY OFFICE FURNITURE ITEMS URGENTLY NEEDED FOR USE AT DELTA PORT, WARRI | CAPITAL EXPENDITURE |  | PTB | Repeat Procurement |  |  | lumpsum 584,500,000 | N/A | 19/3/14 | Yes | Messrs Mog Holdings Limited | 4A, Herbert Macaulay Crescent, GRA. Ikeja, Lagos. 0803 301 8324 | 25/3/14 | 21897750 |  | 2 weeks |  | 21897750 |  | 100% | Job completed
132 | REQUEST FOR APPROVAL FOR PROVISION OF OFFICE FURNITURE FOR ICT GALLERY & HELP DESK OFFICE | CAPITAL EXPENDITURE |  | PTB | Repeat Procurement |  |  | lumpsum 584,500,000 | N/A |  |  | Messrs Mog Holdings Limited | 4A, Herbert Macaulay Crescent, GRA. Ikeja, Lagos. 0803 301 8324 |  | 5937750 |  | 2 weeks |  | 5937750 |  | 100% | Job completed
133 | EVALUATION REPORT OF FINANCIAL BIDS FOR SUPPLY/INSTALLATION OF 33/11KV PANEL WITH SF6 BREAKERS AT MAIN POWER STATION, LAGOS PORT COMPLEX, APAPA |  |  | MTB | Competitive bidding | 16/7/13 |  |  | N/A | 2014-05-06 | Yes | Messrs Hadabs Ventures Limited | 1B, Lander Close Off Liverpool Road, Apapa, Lagos, Tel: 0806 767 1616; 0805 212 1616 | 2014-07-07 | 60952500 |  | (7) weeks |  | 28,115,476.2 36,904,480.84
134 | APPOINTMENT OF CONSULTANT FOR THE PROVISION OF LAND SURVEY SERVICES (LAGOS AREA) | CAPITAL EXPENDITURE | 17/6/13 | PTB | Competitive bidding | 27/7/13 | 2014-03-01 |  | N/A | 19/3/14 | Yes | Messrs Soloku Development Corporation Limited | 302B, Port Harcourt Aba Expressway, Port Harcourt, Rivers State, 0803 708 2834 | 31/3/14 | 10076062.5 |  | 4 weeks
135 | APPOINTMENT OF CONSULTANT FOR THE PROVISION OF LAND SURVEY SERVICES (PORT-HARCOURT AREA) | CAPITAL EXPENDITURE | 17/6/13 | PTB | Competitive bidding | 27/7/13 | March, 2014 |  | N/A | 19/3/14 | Yes | Messrs Super-Geomatics Services Nigeria Limited | 52, Omoi-Orosi Avenue, Off Psychiatric Road, | 31/3/14 | 20395200 |  | 4 weeks |  | 20395200
136 | EVALUATION REPORT OF FINANCIAL BIDS ON PROCUREMENT OF RADIOLOGICAL, MEDICAL AND LABORATORY EQUIPMENT | CAPITAL EXPENDITURE | 23/9/13 | PTB | Competitive bidding | 28/10/2013 | March, 2014 |  | N/A | 19/3/14 | Yes | Messrs Arnold PPE West Africa Limited | 9, Karimu Kotun Street, Victoria Island, Lagos |  | 123515230 |  | 8 weeks
137 | CONSTRUCTION OF WIRE MESH TURNSTILE GATES AND CANOPY AT 1ST & 2ND GATES, TIN CAN ISLAND PORT | RECURRENT EXPENDITURE |  | PTB | Competitive bidding | 2014-10-02 |  |  | N/A | 19/3/14 | Yes | Messrs Inland Chips Limited | B1 TOP PLAZA AYODELE FANIOKI AV. MAGODO ISHERI LAGOS 08023203601 |  | 6282235.75 |  | 6 weeks
138 | CONSTRUCTION OF BLOCK OF TOILETS, GENERATOR HOUSE AND OTHER ANCILLARY WORKS AT MEDICAL CENTRE, BODE THOMAS, SURULERE, LAGOS | RECURRENT EXPENDITURE |  | PTB | Competitive bidding | 2014-10-02 | 2014-02-01 |  | N/A | 19/3/14 | Yes | Messrs June Investments Nigeria Limited | PLOT 33 MOBOLAJI JOHNSON AVENUE OREGUN IND. ALAUSA IKEJA LAGOS 08033158566 |  | 16453026.05 |  | 8 weeks
139 | PROVISION OF PRESSED STEEL WATER STORAGE TANK AT NPA CLINIC, SURULERE, LAGOS | RECURRENT EXPENDITURE |  | PTB | Competitive bidding | 2014-10-02 | 2014-02-01 |  | N/A | 19/3/14 | Yes | Messrs Sule Adini Nigeria Limited | 26 LEWIS STREET ABULE EGBA LAGOS 08055114792 |  | 15447814.8 |  | 6 weeks |  | 8844047.62
140 | SUPPLY OF SIXTY (60) NOs FIREMEN HELMETS FOR HSE DEPARTMENT | CAPITAL EXPENDITURE |  | PTB | Competitive bidding | 2014-10-02 | 2014-02-01 |  | N/A | 19/3/14 | Yes | Messrs Tejid International Limited | SUITE B 295-296 & 308 SURA BUSINESS COMPLEX, SIMPSON STREET LAGOS ISLAND 08033473524 |  | 8997750 |  | 2 weeks |  | 8997750 |  | 100% | Job completed
141 | SUPPLY OF FOUR HUNDRED (400) NOs HIGH VISIBILITY LIFE JACKET (IMO APPROVED) | CAPITAL EXPENDITURE |  | PTB | Competitive bidding | 2014-10-03 | 2014-03-01 |  | N/A | 19/3/14 | Yes | Messrs Dafal Mani Nigeria Limited | 256A MINNA MAIN MKT. MINNA NIGER STATE 08033335421 | 27/3/14 | 15960000 |  | 4 weeks |  | 15960000 |  | 100% | Job completed
142 | PRINTING AND SUPPLY OF ACCREDITED PROGRAMMES OF UNIVERSITIES INTO BOOKLETS | RECURRENT EXPENDITURE |  | PTB | Competitive bidding | 14/3/2014 | 2014-03-01 |  | N/A | 19/3/14 | Yes | Messrs Martrax Limited | 10 BENSON STREET OFF AKERELE SURULERE | 31/3/14 | 6300000 |  | 4 weeks |  |  |  | 100% | Job completed
143 | DRILLING OF INDUSTRIAL BOREHOLE AT NPA SPORTS GROUND, BODE THOMAS, SURULERE, LAGOS | RECURRENT EXPENDITURE | February, 2014 | PTB | Competitive bidding | 14/3/14 | 2014-02-01 | lumpsum 181,914 | N/A | 19/3/14 | Yes | Messrs Top Drill Limited | PLOT 33 MOBOLAJI JOHNSON AVENUE OREGUN IND. ALAUSA IKEJA LAGOS 08033158566 | 30/3/14 | 17086455 |  | 6 months |  | 11701146.25
144 | FINANCIAL BIDS FOR PROVISION/INSTALLATION OF HT UNDERGROUND CABLE NETWORK FROM SUB-STATION 5 TO CONTROL TOWER, LAGOS PORT COMPLEX, APAPA, LAGOS STATE | CAPITAL EXPENDITURE | June, 2014 | PTB | Competitive bidding | 16/7/2014 |  | 150000000 | N/A | 19/3/14 | Yes | Messrs MB Integrated Electrical & Data Services Limited | 2ND FLOOR TOSLAND PLAZA, 1 WAREHOUSE ROAD APAPA LAGOS 08056264876; 07055770665 | 30/3/14 | 35733600 |  | 30 Days |  | 33946920.53
145 | REPLACEMENT OF OBSOLETE FITTING/REACTIVATION OF 12M PERIMETER SECURITY LIGHTING SYSTEM FROM DOCKYARD MAIN ACCESS ROAD TO DOCKYARD MANAGER’S OFFICE, PORT-HARCOURT | RECURRENT EXPENDITURE |  | PTB | Competitive bidding | 10th February, 2014 | February, 2014 |  | N/A | 19/3/14 | Yes | Messrs Sule Adini Nigeria Limited | 26 LEWIS STREET ABULE EGBA LAGOS 08055114792 | 30/3/14 | 9900450 |  | 4 weeks |  | 9900450 |  | 100% | Job completed
146 | PROVISION OF AREA NETWORK AT NPA CLINIC, BODE THOMAS, SURULERE, LAGOS | CAPITAL EXPENDITURE |  | PTB | Competitive bidding | 2014-10-02 | February, 2014 |  | N/A | 19/3/14 | Yes | Messrs Akiz International Limited | 1, CALABAR CLOSE GARKI ABUJA 08186901012 | 30/3/14 | 19246500 |  | 9 weeks |  | 8948095.24
147 | GENERAL ELECTRICAL RENOVATION OF OFFICES AND WORKSHOP OF MARINE DOCKYARD, CALABAR | RECURRENT EXPENDITURE |  | PTB | Competitive bidding | 14/2/14 | February, 2014 |  | N/A | 19/3/14 | Yes | Messrs Am-Sadaq Ventures | 711 ROAD HOUSE 20 C. CLOSE FESTAC TOWN LAGOS 08029399073 | 20/3/14 | 8592728 |  | 6 weeks |  | 8873000
148 | RESTRUCTURING, UPGRADING AND RECONFIGURATION OF MICROSOFT EXCHANGE 2010 ELECTRONIC MAIL INFRASTRUCTUE/APPLICATION | CAPITAL EXPENDITURE |  | PTB | Competitive bidding | 14/2/14 | February, 2014 |  | N/A | 19/3/14 | Yes | Messrs Le Proghrammeen Solutions | SUITE F15 FEBSON MALL WUSE ZONE 4 ABUJA 08032898122; 07098820672 | 30/3/14 | 17220000 |  | 60 Days |  |  |  | 100% | Job completed
149 | DESIGN, CONSTRUCTION AND EQUIPPING OF ICT CENTRES FOR NIGERIAN PORTS AUTHORITY | CAPITAL EXPENDITURE | 29th July, 2013 | MTB | Competitive bidding | 14/2/14 | March, 2014 |  | N/A | 2014-04-07 | Yes | Messrs XPTECH Power Limited | SUITE 26 SILLA ZEKA PLAZA, 29 ADEBAYO ADEDEJI CRESCENT UTAKO ABUJA 08188056661 | 2014-07-08 | 340502127.16 |  | 90 Days |  | 170146050.6 |  | 20%
150 | PROVISION OF DIGITAL UHF RADIO COMMUNICATION FOR NPA HEADQUARTERS AND ALL PORTS | CAPITAL EXPENDITURE | 2013-03-06 | PTB | Competitive bidding | 18/7/13 | March,14 | 125000000 | N/A | 28/3/14 | yes | Messrs Viacove Limited | 29A SUEZ CANAL CRESCENT WUSE ZONE 4 ABUJA +2347063891652 | 31/3/14 | 158710814.75 |  | 21 weeks
151 | ENVIRONMENTAL AUDIT OF CALABAR CHANNEL DREDGING | CAPITAL EXPENDITURE |  | PTB | Re-Procurement | 18/2/14 | March,14 | 3000000000 | N/A | 28/3/14 | Yes | Messrs CARES Nigeria | 54 AWOLOWO ROAD IKEJA LAGOS | 24/4/14 | 48956030 |  | 6 weeks |  | 41789000
152 | SUPPLY OF ONE (1) NO. ANGUS FIRE PORTABLE PUMP (DIESEL TYPE) FOR FIRE SERVICE DEPARTMENT | CAPITAL EXPENDITURE | 2014-10-01 | PTB | Competitive bidding | 2014-10-02 | Feb,14 | lumpsum 1,088,450,000 | N/A | 28/3/14 | Yes | Messrs Benejaf International Limited | 150, EAST-WEST ROAD NKPOLU RUMUIGBO PORT | 31/3/14 | 9660000 |  | 6 weeks |  | 9660000 |  | 100% | Job completed
153 | REHABILITATION WORKS AT QUAYS CANTEEN BUILDING, TIN CAN ISLAND PORT COMPLEX | RECURRENT EXPENDITURE | 25/11/13 | PTB | Competitive bidding | 25/3/14 | March,14 | lumpsum 181,914,000 | N/A | 28/3/14 | Yes | Messrs Calmness and Prime Ventures | 30 MOSUMOLA STREET AGUDA SURULERE LAGOS | 31/3/14 | 9578678 |  | 8 weeks |  | 9099744.1 |  |  | Job completed
154 | REACTIVATION OF 18 METRES SECURITY LIGHTING POLE SYSTEMS AT MAIN GATE AREA, RIVERS PORT | RECURRENT EXPENDITURE | 2014-11-03 | PTB | Competitive bidding | 25/3/14 | March, 14 | lumpsum 48,000,000 | N/A | 28/3/14 | Yes | Messrs Zeal Services Limited | 5TH AVENUE P. CLOSE HOUSE 9 FESTAC TOWN LAGOS | 31/3/14 | 6410800 |  | 4 months |  | 6090260 |  | 100% | Job completed
155 | SUPPLY OF TWENTY (20) NOS. VEHICLE AMBER ROTATION LIGHT/ALARM FOR SECURITY DEPARTMENT | RECURRENT EXPENDITURE | 27/2/14 | PTB | Competitive bidding | 14/3/14 | March, 14 | lumpsum 119,904,000 | N/A | 28/3/14 | Yes | Messrs Rosary Project Limited | 25, ALIYU MOH'D STREET U/RIMI KADUNA 08037021380 | 31/3/14 | 3700000 |  | 2 weeks |  | 3330000
156 | RENOVATION OF DOCKYARD CANTEEN AT RIVERS PORT, PORT-HARCOURT | RECURRENT EXPENDITURE | 25/11/13 | PTB | Competitive bidding | 25/3/14 | March,14 | lumpsum 205,619,000 | N/A | 28/3/14 | Yes | Messrs Cien Dynamic Concepts Limited | PLOT 806, EMEKA ANYAOKU STREET AREA 11 GARKI ABUJA |  | 6986320 |  | 4 weeks |  | 6335322
157 | REHABILITATION OF FACILITIES AT THE ADMINISTRATION BUILDING AT NPA, SAPELE, DELTA STATE | RECURRENT EXPENDITURE | 27/9/13 | PTB | Competitive bidding | 2013-12-12 | Jan, 14 | Lumpsum 205,619,000 | N/A | 28/3/14 | Yes | Messrs Tasnafat Nigeria Limited | NO 3/4 RACE COURSE BY MM WAY KANO 08135403288, 08182725601 | 31/3/14 | 7830322.5 |  | 8 weeks |  | 3390659.25
158 | CONCRETE PAVING OF SURROUNDING AND REPAINTING OF EXTERNAL SURFACE OF CONTAINERS AND PERIMETER FENCE AT CONTAINERIZED MANAGED BY SEAVIEW PROPERTIES | RECURRENT EXPENDITURE |  | PTB | Competitive bidding | 25/3/14 | Jan, 14 | lumpsum 205,619,000 | N/A | 28/3/14 | Yes | Messrs Chesire Nigeria Limited | PLOT 41, KARU SITE EXT. BEHIND MOBILE FILLING STATION ABUJA 08033371670 | 31/3/14 | 18578714 |  | 8 weeks |  | 17649778.3
159 | CONSTRUCTION OF WATER TREATMENT PLANT AT NPA SPORTS GROUND, BODE THOMAS, SURULERE, LAGOS | RECURRENT EXPENDITURE | 2013-12-12 | PTB | Competitive bidding | 2014-10-01 | Feb, 14 | Lumpsum 205,619,000 | N/A | 28/3/14 | Yes | Messrs Alluvial Resources Limited | PLOT 33 MOBOLAJI JOHNSON AVENUE OREGUN IND. ALAUSA IKEJA LAGOS 08033158566 | 31/3/14 | 16705210.5 |  | 10) weeks |  | 14827023.1
160 | SUPPLY OF TWENTY-FIVE (25) NOS. GARRET HAND HELD METAL DETECTORS | RECURRENT EXPENDITURE | 27/2/14 | PTB | Competitive bidding | 25/3/14 | March, 14 | lumpsum 119,904,000 | N/A | 28/3/14 | Yes | Messrs A.U.B. Aluminum & Glass Sales Limited | 1583/1588 KOFAR ROAD KANO 08037034655 | 2014-08-04 | 3150000 |  | 1 year
161 | SUPPLY OF NETWORK ACCESSORIES, DEPLOYMENT AND CONFIGURATION OF NETWORKING DEVICE AT NPA HEADQUARTERS | CAPITAL EXPENDITURE | 24/1/14 | PTB | Competitive bidding | 14/2/14 | Feb,14 | lumpsum 1,000,400,000 | N/A | 19/3/14 | Yes | Messrs NYU Resources Limited | 7, URUGUAY CRESCENT WUSE 11 ABUJA 08033024384 | 31/3/14 | 18863250 |  | 60 days |  | 18863250 |  | 100% | Job completed
162 | CONSOLIDATION OF NPA’S GROUP ACCOUNTS BY SERVING JOINT AUDITORS (SIAO & MUKTARI DANGANA & CO. CHARTERED ACCOUNTANTS) | RECURRENT EXPENDITURE |  | PTB | Competitive bidding |  |  | 150000000 | N/A | 28/3/14 | Yes | Messrs SIAO & Muktari Dangana & Co. Chartered Accountants | 19 ARAROMI STREET, OFF MOLONEY STREET ONIKAN LAGOS; 18B OLU HOLLOWAY ROAD IKOYI LAGOS | 2014-06-05 | 21000000 |  | 3 months |  | 17812500
163 | Rehabilitation of NPA Clinic, Construction of Medical Laboratory Block, Drilling of Water Borehole and Overhead Tank at New Port Warri. | CAPITAL EXPENDITURE | 29/10/14 | PTB | Competitive bidding | 2013-12-12 | Jan. 2014 | lumpsum 200,000,000 | N/A | 28/3/14 | Yes | Messrs Agnelson Limited | Arapasanwo Street, Off Oluwaleyimu Street, Ikeja, Lagos 0803 720 3650 | 31/3/14 | 16937525 |  | 4 months
164 | CONSULTANCY SERVICES FOR THE PROVISION OF ENVIRONMENTAL AUDIT FOR RIVERS AND ONNE PORTS | RECURRENT EXPENDITURE | 2014-12-02 | PTB | Competitive bidding | 2014-07-03 | March, 14 | 20000000 | N/A | 16/7/14 | Yes | Messrs Jawura Environmental Services | 77, IKORODU ROAD - 1ST&2ND FLOOR - FADEYI LAGOS 08033013378; 08023313330 |  | 14941500 |  |  |  | 14259632.6
165 | Supply of 66,000 Litres of AGO (Diesel) for Nigeria Ports Authority Headquarters & 1 Joseph Street Marina Lagos | RECURRENT EXPENDITURE | National Shopping List 30/7/12 | PTB | Competitive bidding | 30/4/14 | National Shopping List 30/4/14 | lumpsum 601,491,000 | N/A | 14/7/14 | Yes | Messrs. Al-Hamary & Co. Investment Ltd | 12 OSHODU STREET OSHODI APAPA EXPRESSWAY APAPA LAGOS 08033040211; 0808289000 |  | 13985400 |  | 6 days |  | 13985400 |  | 100% | Job completed
166 | Forwarding of Report for the Conduct of Promotion | RECURRENT EXPENDITURE | Proposal submission 27/3/14 | PTB | Direct Procurement | 31/3/14 | Direct Proc. | 328455000 | N/A | 14/7/14 | Yes | Messrs. Administrative Staff College of Nigeria - ASCON | PMB 1004 TOPO BADAGRY 08037173823; 08129270746 | 24/4/14 | 18000000 |  | 1 month |  | 16200000 |  | 100% | Job completed
167 | RECRUITMENT OF CANDIDATES FOR POSITIONS IN FIRE SERVICE DEPARTMENT AUTHORITY-WIDE | Recurrent Expenditure |  | PTB | Direct Procurement |  |  |  | N/A | 14/3/14 | Yes | Messrs. West Africa Examination Council - WAEC | 21, HUSSY STREET YABA LAGOS 018961016; 08037146502 | 30/4/14 | 5490502.5 |  | 1 month |  | 1604233.34
168 | contract Award for the making of Escravos Entrance Channel with 17Nos. Medium Density “R” Class Polyethylene (MDPE) Buoys - (Request for approval for Additional Works done) | Capital Expenditure |  | PTB | Direct Procurement | 20/5/14 | Direct Proc. | 313653000 | N/A | 14/7/14 | Yes | Messrs Fomene Maritime International Limited | NO. 19 OTORHO ROAD OGHARA DELTA STATE 08034710993 | 29/6/12 | 10694968 |  | 3 weeks |  | 5763976.91
169 | REACTIVATION/IMPROVEMENT OF LIGHTING SYSTEM AROUND ALRAINE BUILDING AND ENVIRON, EASTERN PORT HEADQUARTERS, PORT-HARCOURT | Recurrent Expenditure | 15/04/14 | PTB | Competitive bidding | 27/05/14 | June, 14 | 182944000 | N/A | 2014-10-07 | Yes | Messrs Optimist Ventures | 21, CREEK ROAD APAPA LAGOS 08033432639 |  | 13641075 |  | 120 days |  | 12959021.25
170 | REACTIVATION OF LOW VOLTAGE POWER DISTRIBUTION AND LIGHTING SYSTEM OF THE POWER HOUSE, TINCAN ISLAND PORT, LAGOS | Recurrent Expenditure | 24/4/14 | PTB | Competitive bidding | 27/05/14 | June, 14 | 182944000 | N/A | 14/7/14 | Yes | Messrs Thomcom Global Links Nigeria Limited | 19 SUEZ CRESCENT IBRAHIM ABACHA ESTATE WUSE ZONE 4 ABUJA 08036062560; 08036062562 |  | 9990120 |  | 3 weeks |  | 9490614
171 | PROVISION/INSTALLATION OF ELECTRONICALLY CONTROLLED FIRE ALARM SYSTEM AT THE MAIN ADMINISTRATION BUILDING, LAGOS PORT COMPLEX, APAPA | Recurrent Expenditure | 14/3/14 | PTB | Competitive bidding | 27/05/14 | June, 14 | 109000000 | N/A | 14/7/14 | Yes | Messrs Thomcom Global Links Nigeria Limited | 19 SUEZ CRESCENT IBRAHIM ABACHA ESTATE WUSE ZONE 4 ABUJA 08036062560; 08036062562 |  | 5703075 |  |  |  | 0
172 | RECONSTRUCTION OF NIGERIAN PORTS AUTHORITY BUILDING AT PETROLEUM WHARF, APAPA, LAGOS | Recurrent Expenditure | 24/4/14 | PTB | Competitive bidding | 27/05/14 | June, 14 | 181914000 | N/A | 14/7/14 | Yes | Messrs Mustang Global Limited | NO. 2 KARIBA MISSISSIPI STREET MAITAMA ABUJA 0803304429 |  | 9700776 |  |  |  | 9215737.2
173 | REPLACEMENT OF MISSING/DAMAGED CAST IRON METAL GRATING ON THE DRAINAGE IN FRONT OF CONTROL TOWER AND BAKASSI COMPLEX ENTRANCE, LPC, APAPA | Recurrent Expenditure | 22/5/14 | PTB | Competitive bidding | 27/05/14 | June, 14 | 60323000 | N/A | 14/7/14 | Yes | Messrs Monarch Imagination Limited | KM 14, BENIN AUCHI ROAD URORA BENIN CITY 08082184085 |  | 18143601 |  | 6 weeks |  | 17236420.95
174 | REPLACEMENT OF DILAPIDATED FEEDER PILLAR AND REHABILITATION OF ELECTRICAL WIRING AND UPGRADING OF ADMINISTRATION BUILDING, KIRIKIRI PHASE 1, APAPA, LAGOS | Recurrent Expenditure | 28/3/14 | PTB | Competitive bidding | 30/4/14 | June, 14 | 182944000 | N/A | 14/7/14 | Yes | Messrs Tracross Limited | 10B DUTSE STREET WAR COLLEGE ZONE GARIMPA FCT ABUJA 07082206481; 08079786122 |  | 7788742.5 |  |  |  | 7399305.37
175 | REPLACEMENT OF OBSOLETE WINDOW BLIND AT NEW ADMINISTRATION BUILDING AND OTHER ANNEX OFFICES AT LAGOS PORT COMPLEX, APAPA | Recurrent Expenditure | 15/04/14 | PTB | Competitive bidding | 27/05/14 | June, 14 | 181914000 | N/A | 14/7/14 | Yes | Messrs Willette Services Company Limited | OLUWALEYIMU STREET OFF UNITY ROAD IKEJA LAGOS 08034388535 |  | 15376821.6 |  | 30 Days |  | 14607980.52
176 | CONSULTANCY SERVICES FOR LAND BASE GEOTECHNICAL INVESTIGATION AND TESTING FOR ESCRAVOS PORT DEVELOPMENT AND BREAKWATER REHABILITATION PROJECT AT OGIDINGBE, DELTA STATE (P.N. 3845, LOT 2) | Capital Expenditure | 30/4/14 | PTB MTB/BPP | Competitive bidding | 2014-12-05 | June, 14 | 350000000 | 26/2/14 March, 2014 | 14/7/14 | Yes | Messrs Fugro Nigeria Limited | 91, Odani Road, Off PH. Eleme Expressway, Elelenwo, PH, Rivers State 0802 290 8428, 0802 290 8427, 0808 448 5546 |  | 123570225.1 | [5 empty] | Procurement Process on-going
177 | CONSULTANCY SERVICES FOR MARINE BASE GEOTECHNICAL INVESTIGATION AND TESTING FOR ESCRAVOS PORT DEVELOPMENT AND BREAKWATER REHABILITATION PROJECT AT OGIDINGBE, DELTA STATE | Capital Expenditure | 30/4/14 | PTB MTB/BPP | Competitive bidding | 2014-12-05 | June, 14 | 350000000 | 26/2/14 March, 2014 | 14/7/14 | Yes | Messrs Fugro Nigeria Limited | 91, Odani Road, Off PH. Eleme Expressway, Elelenwo, PH, Rivers State 0802 290 8428, 0802 290 8427, 0808 448 5546 |  | 986231930.29 | [5 empty] | Procurement Process (On-going)
178 | REQUEST FOR RENEWAL OF PLATINUM SERVICE CONTRACT - Xerox Copiers | RECURRENT EXPENDITURE | Contract Renewal (Platinum Service contract) | PTB | Competitive bidding | Contract renewal | 27/6/14 | 62165000 | N/A | 14/7/14 | Yes | Messrs Xerox H.S. Nigeria Limited | 12/14FATAI ATERE WAY MATORI SCHEME OSHODI LAGOS 01-4521500 |  | 10776710.07 |  |  |  | 10776710.07
179 | SUPPLY OF 66,000 LITRES OF AGO (DIESEL) FOR NIGERIAN PORTS AUTHORITY HEADQUARTERS, 1 JOSEPH STREET AND NPA CLINIC AT BODE THOMAS, SURULERE, LAGOS | Recurrent Expenditure |  | PTB | Competitive bidding | 17/6/14 | June, 14 | 601491000 | N/A | 14/7/14 | Yes | Messrs First Fortune Global Energy Company Limited | 63, KOFO ABAYOMI AVENUE APAPA LAGOS 08023417072 |  | 13200000 |  |  |  | 13200000 |  | 100% | Job completed
180 | PROVISION OF DUE DILIGENCE SERVICES ON LEKKI PORT LFTZ ENTERPRISE | RECURRENT EXPENDITURE |  | PTB | q11 |  | 2014-06-01 | 200000000 | N/A | 14/7/14 | Yes | Messrs KPMG Advisory Services | KPMG TOWER, BISHOP ABOYADE COLE STREET VICTORIA ISLAND LAGOS +234-1-2806020; 07069721470 | 20/6/14 | 35000000 |  | 3 weeks |  | 14000000
181 | SUPPLY AND INSTALLATION OF VINLY FLOORS CARPET AT NPA CLINIC, BODE THOMAS, SURULERE, LAGOS | Recurrent Expenditure | 24/3/14 | PTB | Competitive bidding | 30/4/14 | May, 2014 | 39658000 | N/A | 15/7/14 | Yes | Messrs Retrop Limited | 120, HERBERT MACAULAY STREET EBUTE META LAGOS 08025369885; 08025369997 |  | 12215724.9 |  | 23/weeks |  | 12215724.9
182 | STRUCTURED CABLING OF LOCAL AREA NETWORK AND PROVISION OF INTERNET ACCESS FOR ABUJA LIAISON OFFICE | Capital Expenditure | 2013-02-11 | PTB | Competitive bidding | 30/12/13 | JANUARY, 14 | 2510810000 | N/A | 2014-10-07 | Yes | Messrs Project Wheel Engineering Limited | 47, PAYNE CRESCENT APAPA LAGOS 08038216666; 08098216666 |  | 19350000 |  |  |  | 19350000
183 | RECONSTRUCTION OF DAMAGED HEAVY DUTY METAL GATE AT KIRIKIRI LIGHTER TERMINAL, PHASE I & II | Recurrent Expenditure | 25/12/13 | PTB | Competitive bidding | 21/1/14 | May, 2014 | 181914000 | N/A | 16/7/14 | Yes | Messrs Tom-Cat Services Limited | 48, ELESHIN STREET OBALENDE LAGOS 08053534616 |  | 6980792.28 |  | 8 weeks |  | 6631752.67 |  | 100%
184 | SUPPLY OF OFFICE EQUIPMENT FOR USE IN LAGOS PORT COMPLEX | Capital Expenditure | 2014-03-04 | PTB | Competitive bidding | 30/4/14 | June, 2014 | 62165000 | N/A | 16/7/14 | Yes | Messrs Yamek Nigeria Limited | ASO ESTATE B. CLOSE HOUSE 4 KARU ABUJA 08055464727 |  | 5326125 |  | 4 weeks |  | 5326125
185 | RECONSTRUCTION OF EXISTING PERIMETER BLOCKWALL FENCE AND RAISING OF THE ENTIRE FENCE AT NPA CLINIC, SPORTS GROUND PREMISES, BODE THOMAS, SURULERE | Recurrent Expenditure | 16/5/14 | PTB | Competitive bidding | 2014-12-06 | July,2014 | 22 | N/A | 16/7/14 | Yes | Messrs Mahaj Nigeria Limited | 12B SULAIMAN BARAU STREET SULEJA NIGER STATE 07035082310 |  | 19602861.14
186 | SUPPLY OF OFFICE EQUIPMENT FOR USE IN EASTERN PORT HEADQUARTERS | Capital Expenditure | 2014-05-06 | PTB | Competitive bidding | 2014-02-07 | July, 2014 | 62165000 | N/A | 16/7/14 | Yes | Messrs Brightstone Nigeria Limited | 23, MATADI STREET, WUSE 111 ABUJA, 08037728795; 08133096709 |  | 9644250
187 | Supply of 2 Nos. Breathing Apparatus recharging machines | RECURRENT EXPENDITURE | 2013-02-10 | PTB | Competitive bidding | 13/11/13 | May, 2014 | 7500000 | N/A | 22/5/14 | Yes | Messrs. Ojoma Integrated Services Ltd | Suite 2, 1st Floor Maram Plaza, Eke Yusuf Close, Behind Etema Filling Station |  | 15750000 |  | 8 weeks
188 | SUPPLY OF OFFICE EQUIPMENT FOR USE IN NPA CLINIC | Capital Expenditure | 2014-03-07 | PTB | Competitive bidding | 30/4/14 | June, 2014 | 62,165,000,00 | N/A | 16/7/14 | Yes | Messrs Back ‘O’ Wall Global Limited | 21, CHURCH STREET, OFF OPEBI ROAD IKEJA LAGOS, 08023260006 |  | 4794457 |  | 4 weeks |  |  |  | 100% | Job completed
189 | SUPPLY OF OFFICE EQUIPMENT FOR USE IN TIN CAN ISLAND PORT | Capital Expenditure | 2014-03-04 | PTB | Competitive bidding | 30/4/14 | July, 2014 | 62165000 | N/A | 2014-04-08 | Yes | Messrs Aurora Pathfinder Limited | 21, BISHOP CROWTHER STREET SURULERE LAGOS 08035378839 |  | 2739240 |  | 4 weeks |  | 2739240
190 | SUPPLY OF OFFICE EQUIPMENT FOR USE IN ONNE PORT | Capital Expenditure | 2014-03-04 | PTB | Competitive bidding |  | July, 2014 | 62165000 | N/A | 2014-04-08 | Yes | Messrs Martrax Limited | 10 BENSON STREET OFF AKERELE ROAD SURULERE LAGOS 07025400061 | 2014-07-08 | 9749565 |  | 4 weeks |  | 9749565
191 | PROVISION OF CONSULTANCY SERVICES FOR 3D PRESENTATION OF OFFICE FURNITURE AND EQUIPMENT LAYOUT FOR OFFICES AT NPA HQ, 26/28, MARINA, LAGOS |  | 16/5/14 | PTB | Competitive bidding | 2014-12-06 | July, 2014 | 62165000 | N/A | 2014-04-08 | Yes | Messrs Ika Space Limited | ABIKE SULEIMAN STREET LPI LAGOS 08066376518 | 16/09/14 | 18196500 |  | 4 months |  | 18196500
192 | RESTORATION OF TELEPHONE SERVICES TO DELTA PORT, WARRI (TRANSFER, INSTALLATION AND UPGRADING OF CORAL FLEXI-COM 5000 PABX) | Recurrent Expenditure | 16/5/14 | PTB | Competitive bidding | 2014-12-06 | July, 2014 | 89160000 | N/A | 2014-04-08 | Yes | Messrs Odia Sympathronics (Nig.) Enterprises | AMAZING GRACE COMPLEX, 157 MUSHIN ROAD ILLE IWE LETTA B/STOP ISOLO LAGOS 08023147074; 08071209791 | 2014-07-08 | 19905648 |  | 8 weeks
193 | REQUEST FOR APPROVAL IN RESPECT OF RE-CALIBRATION OF SAFETY DEVICES (FORTY-TWO (42) NOS PORTABLE RADIATION DETECTORS) AND CERTIFICATION OF TEN (10) OFFICERS ON THE USE OF RADIATION MONITORING DEVICES |  |  | PTB | Competitive bidding |  |  |  | N/A | 2014-04-08 | Yes | Messrs Ebonite Nigeria Limited | 14, ADENIYI JONES AVENUE IKEJA LAGOS 08055503004 | 12-0-14 | 7775688.31 |  | 6 weeks
194 | PERIMETER BLOCK FENCING OF NPA POLICE QUARTERS, NEW PORT, WARRI, DELTA STATE | Recurrent Expenditure | 2014-03-07 | PTB | Competitive bidding | 30/7/14 | July, 2014 | 600000000 | N/A | 2014-04-08 | Yes | Messrs Oma-Alagbokun Nigeria Limited | TRAILER PARK, BESIDE JOMALIC OFFICE NEW PORT WARRI 08053301257; 08138971691 | 2014-07-08 | 12366094.4 |  | 6 weeks |  | 11213799.24 |  | 100%
195 | REHABILITATION OF NPA MAGISTRATE COURT BUILDING AND SERVICE INFRASTRUCTURE, NEW PORT COMPLEX, WARRI | Recurrent Expenditure | 18/6/2014 | PTB | Competitive bidding | 30/7/14 | July, 2014 | 587633905 | N/A | 2014-04-08 | Yes | Messrs Kizzy Business Enterprises | NO. 65 EKUREDE ITSEKIRI, WARRI, DELTA STATE 08089920706 | 2014-07-08 | 9601641.5 |  | 6 weeks |  | 8706943.09
196 | EQUIPMENT SUPPORT FOR HP SERVERS AND STORAGE (REPLACEMENT OF COMPONENTS, PARTS AND APPLICATIONS) | Capital Expenditure | 16/4/14 | PTB | Competitive bidding | 27/5/14 | 2014-07-14 | 247669000 | N/A | 29/8/14 | Yes | Messrs Afritech Multi Concept Limited | 27B, ROYAL PALM DRIVE OSBORNE FORESHORE 11 IKOYI LAGOS 08025022513 |  | 19930050 |  |  |  | 19930050
197 | PROVISION AND INSTALLATION OF LOW TENSION PANEL/REDISTRIBUTION OF LOADS AROUND MARKETING BUILDING/ENVIRONS, ONNE PORT COMPLEX | Recurrent Expenditure | 16/7/14 | PTB | Competitive bidding | 2014-12-08 | 2014-08-01 | 182944000 | N/A | 28/8/14 | Yes | Messrs Exact Hallmark Services Limited | 55, FLAT 1, KOSOFE ROAD DOLPHIN ESTSTE IKOYI 08033798112, 08026803412 |  | 8000055 |  | (4) weeks |  | 7600025.25
198 | SUPPLY OF 66,000 LITRES OF AGO (DIESEL) FOR NPA HEADQUARTERS, 1 JOSEPH STREET AND NPA CLINIC AT BODE THOMAS, SURULERE, LAGOS | Recurrent Expenditure |  | PTB | Competitive bidding |  |  | 601491000 | N/A | 29/8/14 | Yes | Messrs First Fortune Global Energy Co. Limited | 63, KOFO ABAYOMI AVENUE APAPA LAGOS 08023417072 |  | 13200000 |  |  |  | 13200000
199 | PROVOSION AND INSTALLATION OF 1600 AMPS LT PANELS WITH VARIOUS CONTROL DEVICES AT EASTERN PORTS HEADQUARTERS, PORT HARCOURT | Recurrent Expenditure | 30/4/14 | PTB | Competitive bidding | 27/5/14 | JULY, 2014 | 128944000 | N/A | 29/8/14 | Yes | Messrs Calmness and Prime Ventures | 30, MOSUMOLA STREET AGUDA SURULERE LAGOS 08095019443 |  | 15840300 |  | (120) days |  | 15048285 |  | 100%
200 | CONSTRUCTION OF ENGINE BAY AT FIRE SERVICE STATION, FEDERAL LIGHTER TERMINAL, ONNE PORT COMPLEX | Recurrent Expenditure | 2014-03-07 | PTB | Competitive bidding | 30/7/14 | JULY, 2014 | 600000000 | N/A | 29/8/14 | Yes | Messrs Hamlix Nigeria Limited | SHOP 66, SHY SHOPPING PLAZA BUK ROAD OPP GADON KAYA KANO 08033499025 |  | 11269385.6
201 | REHABILITATION OF NIGERIAN PORTS AUTHORITY’S CORPORATE HEADQUARTERS FIRE SERVICE STATION ALONG MARINA, LAGOS | Recurrent Expenditure | 2014-03-07 | PTB | Competitive bidding | 30/7/14 | JULY, 2014 | 181914000 | N/A | 29/8/14 | Yes | Tom-Cat Services Limited | 48, ELSHIN STREET OBALENDE LAGOS 08053534616 | 16/9/14 | 12618144 |  | 4 weeks
202 | CONSULTANCY FOR THE PROVISION OF ADVISORY SERVICES ON PORT DEVELOPMENT – IBAKA DEEP SEA PORT, AKWA IBOM STATE (INDIVIDUAL CONSULTANT) |  | 2014-03-07 | PTB | Competitive bidding | 30/7/14 | August,2014 | 200000000 | N/A | 29/8/14 | Yes | Messrs C.A. Borha | CAPTAIN HOUSE, 34, AJE STREET YABA LAGOS 08066376518 |  | 18300000 |  | January – December, 2013 |  | 18300000
203 | DRILLING OF BOREHOLE AND PROVISION OF WATER TREATMENT PLANT AT NO. 12B PARK LANE, APAPA, LAGOS | Recurrent Expenditure | 16/5/14 | PTB | Competitive bidding | 2014-12-06 | August,2014 | 181914050 | N/A | 29/8/14 | Yes | Messrs Shenim Ventures Limited | 32, ALI AKILU ROAD 2ND FLOOR SUITE 10 KADUNA 08037878984 | 16-09-14 | 19741050 |  | (3) weeks
204 | SUPPLY OF TWENTY (20) NOS OPERATIONAL DOGS FOR USE OF PORT AUTHORITY POLICE, WESTERN COMMAND | Recurrent Expenditure | 30/7/14 | PTB | Competitive bidding | 26/8/14 |  | 125422000 | N/A | 29/8/14 | Yes | Messrs Leke Concept Limited | 1, ADEGBEYENI STREET BEHIND ALADE MKT. ADJACENT IKEJA MEDICAL CENTRE, OFF ALLEN AVENUE LAGOS 08033467707 |  | 13387500 |  | (6) weeks |  | 12431500
205 | GENERAL CLEANING AND HOUSE KEEPING OF RELOCATED MEDICAL DEPARTMENT AND ITS ENVIRONS AT NPA SPORTS GROUND, BODE THOMAS |  |  | PTB | Competitive bidding |  |  | 219945000 | N/A | 2013-09-09 | Yes | Messrs Seaview Properties Limited | NO. 1 JOSEPH STREET, MARINA LAGOS |  | 2329013.25 |  | (12) months effective from October 2013 – September 2014 |  | 101716552.16
206 | COMPLETION OF EIGHT (8) STOREY ADMINISTRATION BUILDING (CONSTRUCTION OF OUTSTANDING THREE (3) OFFICE FLOORS) AT LAGOS PORT COMPLEX, APAPA – PUBLIC NOTICE NO. 3844 | Capital Expenditure | 18/11/14 | MTB | Competitive Bidding | 2014-10-12 | Sept. 2014 | 250000000 |  | 15/9/14 | Yes | Messrs A & K Construction Limited | Behind Setraco Building, Plot 527, Shehu Yaradua Way, Abuja. 0807 939 9443, 0803 358 3224 |  | 997491733.39 |  | 24 weeks |  |  |  | Procurement Process ongoing
207 | SUPPLY OF OFFICE EQUIPMENT FOR USE IN WESTERN PORTS | Capital Expenditure | 19/3/14 | PTB | Competitive Bidding | 30/4/14 | 2014-07-01 | 238452000 | N/A | 12/3/2014 15/9/2014 | Yes | Messrs Peakant Limited | 4, OYEWO CLOSE OREGUN IKEJA LAGOS 07032732399, 08027805901 |  | 4628846.25 |  | 4 weeks |  | 4628846.25
208 | PRINTING OF IFRS CHART OF ACCOUNTS FOR THE AUTHORITY AND ORACLE FINANCIALS | Recurrent Expenditure | 2014-02-05 | PTB | Competitive Bidding | 2014-12-06 | Aug. 2014 | 212049000 | N/A | 15/9/2014 | Yes | Messrs QBPR Nigeria Limited | 23A ALHAJI TOKAN STREET, ALAKA ESTATE SURULERE LAGOS 08033072202, 08035254837 |  | 3150000 |  | 2 weeks |  | 3150000 |  | 100%
209 | RENEWAL OF LICENSE FOR SAGE PASTEL EVOLUTION FOR MAY 2014 – APRIL 2015 | Recurrent Expenditure |  | PTB | Renewal of Contract | Renewal | Renewal | 2510810000 | N/A | 14/9/14 |  | Messrs Robert Ade-odiachi & Co. Limited | SHIIPERS PLAZA, 4 PARK LANE APAPA LAGOS 07098003989 | 22/9/14 | 8366550 |  | I year |  | 8366550 |  | 100%
210 | PROVISION OF ELECTRONIC ARCHIVING SYSTEM FOR PROCUREMENT DEPARTMENT | Capital Expenditure | 21/5/14 | PTB | Competitive Bidding | 18/6/14 | 2014-07-01 | 575000000 | N/A | 15/9/14 | Yes | Messrs NEET Nigeria Limited | 43, AKIN ADESOLA STREET VICTORIA ISLAND LAGOS | 24/9/14 | 19999418.25 |  | 3 months
211 | SUPPLY OF FOAM CONCENTRATE (HEADQUARTERS, MARINA) | Recurrent Expenditure | 2014-05-07 | PTB | Competitive Bidding | 26/8/14 | Sept. 2014 | 15000000 | N/A | 15/9/14 | Yes | Messrs Pasturage Vert Limited | 133, AGREY ROAD PORT HARCOURT 08033412773 | 23/9/14 | 14850000 |  | 4 weeks
212 | SUPPLY OF KITCHEN EQUIPMENT FOR CALABAR PORT | Recurrent Expenditure | 2014-05-07 | PTB | Competitive Bidding | 26/8/14 | Aug. 2014 | 8291000000 | N/A | 15/9/14 | Yes | Messrs Ark Thonade Engineering Limited | 4, IREPO STREET OKE-IRA OGBA LAGOS 08081143844 |  | 4536000 |  |  |  | 3635835
213 | SUPPLY OF FIFTY (50) NOS MOBILE BARRIER FOR SECURITY DEPARTMENT | Recurrent Expenditure | 18/6/14 | PTB | Competitive Bidding | 30/7/14 | 2014-07-01 | 262500000 | N/A | 2014-12-09 | Yes | Messrs Platinum Synergy Limited | SUITE A, 12 AMMA CENTRE ABUJA 08065736000 | 22/9/14 | 12481875 |  | 120 days
214 | Sunken MT BAJIMA in Port Harcourt |  | 14/7/14 | MTB | Emergency Procurement |  |  |  | N/A | 14/9/14 | Yes | Messrs Oceantech Nigeria Limited | 5, ELDER ANTHONY OWABIE STREET OFF EPIRIKO/EEO ROAD BY WIMPY JUNCTION PORTHARCOURT | 22/9/14 | 39810750 |  | 4 weeks |  | 37820212.5
215 | Sunken ML SAKWA, PC SHELLENG and PB KABBA |  |  | MTB | Emergency Procurement |  |  |  | N/A | 14/9/14 | Yes | Messrs Aviva Quartet Limited | PLOT 29 FURO EPIMORE STREET, LEKKI PHASE 1 LAGOS, 08022222099 | 22/9/14 | 15015000
216 | SUPPLY OF 66,000 LITRES OF AGO (DIESEL) FOR NIGERIAN PORTS AUTHORITY HEADQUARTERS, NO. 1 JOSEPH STREET AND NPA CLINIC AT BODE THOMAS, SURULERE, LAGOS | Recurrent Expenditure |  | PTB | Competitive bidding |  | Sept. 2014 | 601491000 |  |  | Yes | Messrs. Umsal Nig. Ltd. | Flat 5, No. 4 Abaji Close, Oyo Street. Area 2 Garki, Abuja. 0803 361 6747 | 13/11/2014 | 13860000 |  | 4 weeks
217 | PRINTING OF ANNUAL PERFORMANCE APPRAISAL REPORT BOOKLETS | Recurrent Expenditure |  | PTB | Competitive Bidding | [5 empty] | Yes | Messrs Achievement & Knowledge Development | 3, Dada Akapo Street, Orile, Oshodi, Lagos Tel: 0803 370 7106 | 14/11/14 | 8195250 |  | 4 weeks |  |  |  | 100%
218 | CONSTRUCTION OF REINFORCED CONCRETE DISCHARGE SEWER FROM NPA SPORTS GROUND PREMISES TO COKER-AGUDA CANAL, SURULERE, LAGOS | Recurrent Expenditure | 2014-01-07 | PTB | Competitive Bidding | 2014-12-08 | Aug. 2014 | 181914000 |  |  | Yes | Messrs Strabic Construction Limited | 48, Adefemi Taire Street, Omole, Ikeja, Lagos Tel: 0803 328 3214 | 2014-11-11 | 15864857.8 |  | 5weeks |  | 17421128.93
219 | SUPPLY OF SEVENTY-NINE (79) UNITS OF 3KVA SMART ON-LINE UNINTERRUPTED POWER SUPPLY (UPS) | Recurrent Expenditure | 2014-08-08 | PTB | Competitive Bidding | 19/9/14 |  | 238452000 |  |  | Yes | Messrs Welzi International Limited | Suite 60, Area 7 Shopping Complex, FCT, Abuja Tel: 0803 331 1622 | 13/11/2014 | 18912600 |  | 42days |  | 18912600
220 | SUPPLY OF ONE HUNDRED AND TEN (110) NOS NEW TYRES FOR ALL FIRE SERVICE TRUCKS | Recurrent Expenditure |  | PTB | Competitive Bidding | [5 empty] | Yes | Messrs Astel Limited | 28A, Berkley Street, Onikan, Lagos State Tel: 0805 939 2749 | 13/11/2014 | 15939000 |  | 4weeks |  | 15939000
221 | SUPPLY OF 15,000 LITRES OF FOAM CONCENTRATE FOR USE IN FIRE SERVICE DEPARTMENT, CALABAR PORT COMPLEX | Recurrent Expenditure | 2014-08-08 | PTB | Competitive Bidding | 19/9/14 | Oct. 2014 | 675000000 |  |  | Yes | Messrs Monarch Imaginations Limited | Flat 5, No. 4 Abaji Close, Oyo State. Area 2 Garki, Abuja. 0809 783 3847, 081 545 4529 | 2014-12-11 | 16225095 |  | 6weeks |  | 16225095
222 | SUPPLY OF FORTY-FIVE (45) UNITS MOTOR BATTERIES IN PORT HARCOURT | Recurrent Expenditure |  | PTB | Competitive Bidding | [5 empty] | Yes | Messrs Amicent Nigeria Limited | 66 Campbell Street Beside, Wetern House, Lagos Island Tel: 0802 290 2446 | 2014-12-11 | 4520000 |  | 4weeks |  | 4520000
223 | SUPPLY OF FORTY-FIVE (45) UNITS MOTOR BATTERIES IN LAGOS PORT COMPLEX |  |  | PTB | Competitive Bidding | [5 empty] | Yes | Messrs Tom-Cat Services Limited | 48, Eleshin Street, Obalende, Lagos. 0805 353 4616 | 13/11/2014 | 4803750 |  | 4weeks |  | 4803750
224 | SUPPLY OF 15,000 LITRES OF FOAM CONCENTRATE FOR USE IN FIRE SERVICE DEPARTMENT, RIVERS PORT, PORT HARCOURT | Recurrent Expenditure |  | PTB | Competitive Bidding | [5 empty] | Yes | Messrs Laura Veta Limited | 6,Rehohoth Drive GRA Phase 11, Off Country Home Road. Benin-City 0802 312 4313; 0805 614 1182 | 2014-12-11 | 14880000 |  | 4weeks
225 | SUPPLY OF OFFICE EQUIPMENT FOR USE AT CALABAR PORT | Capital Expenditure | 19/3/14 | PTB | Competitive Bidding | 30/4/14 | Oct. 2014 | 62165000 |  |  | Yes | Messrs Brimwell Innovation Limited | 4, Ayo Oguntuga Street, Magodo GRA, Lagos, Tel: 0802 724 8878 | 13/11/2014 | 7159845 |  | 4weeks |  | 7159845
226 | SUPPLY AND INSTALLATION OF SECURITY ALARM/INTRUDER DETECTION SYSTEM WITH ALTERNATIVE POWER SUPPLY FOR PERIMETER PROTECTION OF CAR PARK, CORPORATE HEADQUARTERS, MARINA | Recurrent Expenditure | 2014-08-08 | PTB | Competitive Bidding | 18/9/2014 | Oct. 2014 | 262500000 |  |  | Yes | Messrs Laditech Ventures | 96/129 Okota Road, Okota, Lagos Tel: 0802 943 7316 | 13/11/2014 | 5759250 |  | 60 days |  |  |  |  | Procurement Process (on-going)
227 | SUPPLY OF OPERATIONAL EQUIPMENT FOR SECURITY DEPARTMENT | Capital Expenditure | 2014-08-08 | PTB | Competitive Bidding | 19/9/14 | Oct. 2014 | 262500000 |  |  | Yes | Messrs. STI Limited | 346, Herbert Macaulay Street, Yaba Lagos. Tel: 0802 317 0942; 0805 748 2520 | 13/11/2014 | 9555000 |  | 28 days |  | 9555000
228 | CONSTRUCTION OF REINFORCED CONCRETE PAVEMENT BETWEEN THE EXISTING LAWN TENNIS AND BASKETBALL COURTS, NPA SPORTS GROUND, SURULERE, LAGOS | Recurrent Expenditure | 18/6/14 | PTB | Competitive Bidding | 30/7/14 | Oct. 2014 | 60323000 |  |  | Yes | Messrs Strabic Construction Limited | 48, Adefemi Taire Street, Omole, Ikeja, Lagos Tel: 0803 328 3214 | 2014-11-11 | 19211270
229 | RECRUITMENT OF CANDIDATES FOR POSITIONS IN FIRE SERVICE DEPARTMENT AUTHORITY-WIDE | ` |  | PTB | Repeat Procurement |  |  |  | N/A | 28/10/14 | Yes | Messrs. West Africa Examination Council - WAEC | 21, HUSSY STREET YABA LAGOS 018961016; 08037146502 | 14/11/14 | 6774755 |  | 1 month |  |  |  |  | On-Going
230 | PROPOSAL TO CARRY OUT DIVING INSPECTION ON IDENTIFIED WRECKS ALONG CALABAR PILOTAGE DISTRICT |  |  | PTB | Repeat Procurement | [5 empty] | Yes | Messrs Humber Marine Wercks Co. Ltd. | 10, Adeola Ajayi Street, Off Murtala Mohammed Int'l Airport Road, Ikeja. Lagos |  | 48510000 |  |  |  | 31531500 |  |  | Procurement Process (on-going)
231 | MOBILIZATION AND SENSITIZATION ON THE EBOLA VIRUS DISEASE (EVD) AND OTHER COMMUNICABLE DISEASES IN LPC AND TCIPC |  |  | PTB | Competitive Bidding | [5 empty] | Yes | Messrs Zeal Services Limited | 5th Avenue, P. Close, House 9, Festac Town, Lagos | 13/11/2014 | 18976650 |  | 3 months |  | 18976650
232 | Construction of Health Care Cenre in Kopmur/Bokos, Plateau State (Corporate Social Responsibility) | Capital Expenditure | 2014-08-08 | PTB | Competitive Bidding | 19/9/14 | Oct.2014 | 1250000000 |  |  | Yes | Messrs La-Chateau Ventures Nigeria Limited | Plot 413, Jos Street, Area 11, Garki, Abuja. Tel: 0814 444 00951 | 18/11/14 | 20630823 |  | 4 months |  | 20630823
233 | Supply of 16,000 Litres of Foam Concentrate to FireService Department in Delta Port Complex, Warri | Recurrent Expenditure | 2014-07-07 | PTB | Competitive Bidding | 2014-08-09 | Oct. 2014 | 675000000 |  |  | Yes | Messrs J-Nissi Nigeria Limited | 2, Urubi Street (Iyaro) 4th floor, Benin-city, Edo State | 17/11/2014 | 19140000 |  | 2 weeks |  | 19140000
234 | Second Quarter Supply of Drugs for NPA Headquarters Clinic | Recurrent Expenditure | 2014-05-09 | PTB | Competitive Bidding | 17/10/14 | Oct. 2014 | 350000000 |  |  | Yes | Messrs Ishara Pharmaceuticals Limited | 1, Muhammadu Buhari Way, Shopping Complex, Kaduna. 062-248804 | 14/11/14 | 19735363.2 |  | 2 weeks
235 | Supply of Office Furniture at Lagos Port Complex, Apapa | Capital Expenditure | 14/7/14 | PTB | Competitive Bidding | 27/8/14 | Oct. 2013 | 584500000 |  | 2014-10-11 | Yes | Messrs Eliz Blessing Enterprises | 4A, Herbert Macauley Crescent, GRA Ikeja, Lagos. 0708 718 2254 | 19/12/14 | 45160500 |  | 4 weeks |  | 45160500
236 | Supply of Office Furniture at Tin-Can Port Complex, Apapa | Capital Expenditure | 14/7/14 | PTB | Competitive Bidding | 27/8/14 | Oct. 2013 | 584500000 |  | 2014-10-11 | Yes | Messrs Anuoluwapo and Company | 6, Mojidi Street, Ikeja Lagos 0708 71 2254 0803 320 3497 | 19/12/14 | 47890500 |  | 4 weeks |  | 45160500
237 | Supply of Office Furniture at Eastern Ports Zonal Headquarters, Port Harcourt | Capital Expenditure | 14/7/14 | PTB | Competitive Bidding | 27/8/14 | Oct. 2013 | 584500000 |  |  | Yes | Messrs MOG Holdings Limited | 4A, Herbert Macaulay Crescent, GRA Ikeja Lagos. 08033018324. | 2014-11-11 | 49308000 |  | 2 weeks |  | 47890500
238 | Supply and Installation of Computer Hardware and Accessories for Onne Port, Onne, Rivers | Recurrent Expenditure | 15/8/14 | PTB | Competitive Bidding | 26/9/14 | Oct. 2014 | 2510810000 |  |  | Yes | Messrs Nachi Munak Tech. Co. Limited | 23, Payne Crescent Apap, Lagos | 14/11/2014 | 19976250 |  | 4 weeks |  | 49308000
239 | Supply and Installation of Computer Hardware and Accessories for Lagos Port Complex | Recurrent Expenditure | 29/8/14 | PTB | Competitive Bidding | 2014-10-10 | Oct. 2014 | 2510810000 |  |  | Yes | Messrs Acalibo and Company Limited |  |  | 19927450.2 |  |  |  | 19976250
240 | Supply and Installation of Computer Hardware and Accessories for Eastern Port Headquarters | Recurrent Expenditure | 2014-11-09 | PTB | Competitive Bidding | 23/10/2014 | Oct. 2014 | 2510810000 |  |  | Yes | Messrs Labonll Nigeria Limited | Builders, Civil Engineers, General Contractors. No. 1, MacDonald Street, Off Egerton Road, Calabar, Cross River State 0803 341 4944 |  | 18690000 |  | 3 weeks |  | 19927450.2
241 | Supply and Installation of Computer Hardware and Accessories for Tin-Can Island Port Complex, Apapa | Recurrent Expenditure | 2014-11-09 | PTB | Competitive Bidding | 23/10/2014 | Oct. 2014 | 2510810000 |  |  | Yes | Messrs Tebold Promotions and Services Limited | Plot 9, Flat 27, Professor Lelvin Akingbehin, Lekki Phase 1, Lagos |  | 19950000 |  | 4 weeks |  | 18690000
242 | Supply and Installation of Computer Hardware and Accessories for Rivers Port Complex, Port Harcourt | Recurrent Expenditure | 2014-11-09 | PTB | Competitive Bidding | 23/10/2014 | Oct. 2014 | 2510810000 |  |  | Yes | Messrs Metro Resources Limited | 6, lle-lfe Street, Area 8, Garki, Abuja. |  | 19897500 |  | 4 weeks |  | 19950000
243 | Design and Implementation of Electric Document Management System for NPA | Recurrent Expenditure | 2014-11-09 | PTB | Competitive Bidding | 23/10/2014 | Oct. 2014 | 2510810000 |  |  | Yes | Messrs Afritech Multi Concepts Limited | 27B Royal Palm Drive Osborne Foreshore II Ikoyi, Lagos 0818 601 8983 | 18/11/2014 | 19976250 |  | 6 months |  | 19897500
244 | Design and Implementation of Online Automation process for Sen-Web Based Distribution Application | Recurrent Expenditure | 2014-11-09 | PTB | Competitive Bidding | 23/10/2014 | Oct. 2014 | 2510810000 |  |  | Yes | Messrs OK Computers/Afritech Multi Concepts Limited | 6, Balarabe Musa Crescent, V/I Lagos. | 17/11/2014 | 19719000 |  | 6 months |  | 19719000
245 | Development and Production of Information usage Policy Document for NPA | Recurrent Expenditure | 2014-11-09 | PTB | Competitive Bidding | 23/10/2014 | Oct. 2014 | 2510810000 |  |  | Yes | Messrs FS Day Resources Limited | Area 11, Garki, Abuja 080 536 9795 |  | 19840500 |  | 4 weeks
246 | Third Quarter Supply of Medicines for NPA Headquarters Clinic | Recurrent Expenditure | 2014-11-09 | PTB | Competitive Bidding | 23/10/2014 | Oct. 2014 | 2510810000 |  |  | Yes | Messrs Remedia Pharmacy Services Limited | 69,Kofo Abayomi Avenue, Apapa, Lagos 0808 822 6324 |  | 19834501.28
247 | Renovation work at Bungalow Annex at 1, Joseph Street, Lagos | Capital Expenditure | 21/5/14 | PTB | Competitive Bidding | 2014-02-07 | 2014-07-01 | 181914000 |  |  | Yes | Messrs Benejaf International Limited | 150, East-West Road, Nkpolu Rumigbo, Port Harcourt, Rivers State. 081 558 75700 |  | 19926637.85 |  | 12 weeks |  | 19926637.85
248 | Re- painting and Decoration of the External Surface of Main Building Car Park Fence, renovation and Re-painting of fallen Fence at 1, Joseph Street, Lagos | Capital Expenditure | 21/5/14 | PTB | Competitive Bidding | 2014-02-07 | 2014-07-01 | 181914000 |  |  | Yes | Messrs Auxty Limited | Shop 1, 115, Ikota Shopping Complex, Victoria Garden City, Lagos. 0802 323v7652 0702 642 4970 |  | 9867365 |  | 4 weeks
249 | Internal and External Painting of Administration Building, Lagos Port Complex, Apapa | Capital Expenditure | 2014-11-09 | PTB | Competitive Bidding | 23/10/2014 | Oct. 2014 | 181914000 |  |  | Yes | Messrs Dafal Mani Limited | 256A, Minna Main Market, Minna, Niger State 0803 333 5421 |  | 11138545 |  | 10 weeks |  | 10632247.95
250 | Construction of Gate House, Concrete Sign Post, Metal Gate andSeptic Tank/Soak-Away Pits at the Main Entrance of Rivers Port Complex, Port Harcourt | Capital Expenditure | 2014-11-09 | PTB | Competitive Bidding | 23/10/2014 | Oct. 2014 | 600000000 |  | 2014-10-11 | Yes | Messrs Tantamount Nigeria Limited | 2, Awori Street, Ile Epo Alh. B/Stop, Egbeda Lagos. 0803 330 6658, | 19/12/14 | 10689399 |  | 3 months
251 | Supply of Safety Working Tools for Accident Investigation, Reporting and Documentation | Recurrent Expenditure | 2014-11-09 | PTB | Competitive Bidding | 23/10/2014 | Oct. 2014 | 525000000 |  |  | Yes | Messrs Quick Projects Limited | 17B, Allen Avenue, Ikeja, Lagos. 0803 300 1234 |  | 16415700 |  | 3 months |  | 16268700
252 | Supply of Back-up Spare Parts for Two (2) Nos Twenty (20) Tons Sino Tow Trucks | Recurrent Expenditure | 29/8/14 | PTB | Competitive Bidding | 2014-10-10 | Oct. 2014 | 525000000 |  |  | Yes | Messrs Excel Global Engineering Limited | 23, Suez Crescent Ibrahim Abacha Estate, Wuse Zone 4, Abuja |  | 16968630 |  | 4 months |  | 16120198.5
253 | Water Rescue Safety Kits and Swimming Compliance Certification for Safety and Occupational Health Officers | Recurrent Expenditure | 15/8/14 | PTB | Competitive Bidding | 26/9/14 | Oct. 2014 | 525000000 |  |  | Yes | Messrs Gold Leng Investment Limited | 4, Ibadan Street, Behind Shopping Complex, Jimeta, Yola, Adamawa State. 0803 343 2639 |  | 19828200 |  | 4 weeks |  | 18400000
254 | Supply of Sixty (60)Nos New Tyres for Utility Vans (Eastern Port Area) | Recurrent Expenditure | 29/8/14 | PTB | Competitive Bidding | 2014-10-10 | Oct. 2014 | 675000000 |  |  | Yes | Messrs Multigate Associate International Limited | 25, Oduduwa Street, Ikate Surulere, Lagos. 0802 309 9269 | 14th, November, 2014 | 14490000 |  | 4 weeks |  | 14490000
255 | Supply of Foam Concentrate for Fire Service at Lagos Port Complex, Apapa | Recurrent Expenditure | 2014-11-09 | PTB | Competitive Bidding | 23/10/14 | Oct. 2014 | 675000000 |  |  | Yes | Messrs Sukeem Nigeria Limited | 4, Akpogunma Street, Kilo Bus-Stop, Surulere Lagos | 17th, November, 2014 | 14765625 |  | 8 weeks
256 | Appointment of Consultant for the Valuation of Nigerian Ports Authority's Assets (Lands and Buildings) - Lagos Ports Area | Capital Expenditure | 16/6/14 | PTB | Competitive Bidding | 2014-09-07 | Oct. 2014 | 200000000 |  |  | Yes | Messrs Etudo and Company | 217A, Igbosere Road, Lafiagi, Lagos. 01-4544687 | 13th, November, 2014 | 17172500 |  |  |  | 6869000 |  | 100%
257 | Appointment of Consultant for the Valuation of Nigerian Ports Authority's Assets (Lands and Buildings) -Rivers Ports Area | Capital Expenditure | 16/6/14 | PTB | Competitive Bidding | 2014-09-07 | Oct. 2014 | 200000000 |  |  | Yes | Messrs Judo Onuoha and Company | Suite 2, 11 Williams Plaza, Plot511 herbert Macualay Way, Wuse Zone 4. Abuja. 0809 677 9145 0805 732 3896 | 13th, November, 2014 | 18711000
258 | Appointment of Consultant for the Valuation of Nigerian Ports Authority's Assets (Lands and Buildings) - Warri Ports Area | Capital Expenditure | 16/6/14 | PTB | Competitive Bidding | 2014-09-07 | Oct. 2014 | 200000000 |  |  | Yes | Messrs Ezeh Ezeh and Company | 3rd floor, Gateway Plaza, Plot 208, Z. Maimalari Street, Abuja. 0808 718 7125 0706 638 6768 | 13th, November, 2014 | 9331875
259 | Appointment of Consultant for the Valuation of Nigerian Ports Authority's Assets (Lands and Buildings) - Calabar Ports Area | Capital Expenditure | 20/8/14 | PTB | Competitive Bidding | 2014-09-07 | Oct. 2014 | 200000000 |  |  | Yes | Messrs I. Idi and Partners | 6A, Ahmadu Bello Way, Ali Akilu House, Kaduna 0803 714 2757 | 14th, November, 2014 | 9881157.32
260 | Upgraing of Power Supply System from Sub-Station 2 to Administration Building at Lagos Port Complex, Apapa | Capital Expenditure | 14/7/14 | PTB | Competitive Bidding | 2014-01-09 | Oct. 2014 | 50000000 |  |  | Yes | Messrs Beam Energy Limited | Plot 390 George Crescent, Off WEMPCO Rd. Ogba Lagos, 0814559370, 08023076849 | 18th November, 2014 | 20544761.65 |  | 12 weeks
261 | Supply of Three (3) Nos fire Portable Pumps for use in Fire Service Department, Corporate Headquarters | Recurrent Expenditure | 16/7/14 | PTB | Competitive Bidding | 27/8/14 | Oct. 2014 | 15000000 |  |  | Yes | Messrs Mafadens Corporations Limited | 4, Randle Road, Apapa, Lagos. 0803 453 8271 0803 303 1712 | 18th, November, 2014 | 15750000 |  | 60 days |  | 15000000
262 | SUPPLY OF 66,000 LITRES OF AGO (DIESEL) FOR NIGERIAN PORTS AUTHORITY HEADQUARTERS, NO. 1 JOSEPH STREET AND NPA CLINIC AT BODE THOMAS, SURULERE, LAGOS | Recurrent Expenditure | 18/9/14 | PTB | Competitive Bidding | 30/10/14 | Oct. 2014 | 601491000 |  |  | Yes | Messrs Tam Tam Project Limited | Suite C433, Ikeja Plaza, Mobolaji Bank, Anthony Way, Ikeja, Lagos 0803 451 7535 0809 234 8766 | 11, November, 2014 | 13167100 |  |  |  | 13860000
263 | Supply of PRP Powder for Bio-Remediation in the Environment Unit of Health , Safety and Environment (HSE) |  |  | PTB | Competitive Bidding |  | Oct. 2014 | 525000000 |  |  | Yes | Messrs Agnelson Limited | 1, Arapasanya street, Off oluwaleyimu street, Ikeja Lagos | 17th November, 2014 | 19971000 |  | 6 weeks
264 | Consultancy Services for the Forensic Cleaning and Consolidation of NPA;s Account within the Network of First City Monument Bank | Recurrent Expenditure | 19/9/14 | PTB | Competitive Bidding | 31/10/14 | Nov. 2014 | 150000000 |  | 25/11/14 | Yes | Messrs FFA Professionals | 116, Akowonjo Road Egbeda, Lagos 0802 315 7072, 0805 209 0313 | 2014-11-12 | 7500000 |  | 2 months |  | 7500000
265 | Consultancy Services for the Forensic Cleaning and Consolidation of NPA;s Account within the Network of Guaranty Trust Bank PLC | Recurrent Expenditure | 19/9/14 | PTB | Competitive Bidding | 31/10/14 | Nov. 2014 | 150000000 |  | 25/11/14 | Yes | Messrs Deen A Mosudi & Co | Suite 21B, Block B, Sabondale Shopping Complex, Plot 526, Obafemi Awolowo Way, Jabi District, Abuja. 0802 700 7930, 0803 645 9132 | 2014-11-12 | 7499625 |  | 2 months |  | 2999850
266 | Consultancy Services for the Forensic Cleaning and Consolidation of NPA;s Account within the Network of Unity Bank PLC | Recurrent Expenditure | 19/9/14 | PTB | Competitive Bidding | 31/10/14 | Nov. 2014 | 150000000 |  | 25/11/14 | Yes | Messrs Olabode Akande & Co | 3rd Floor Lamlat House, 270, Ikorodu Road, Obanikoro Lagos 0803 309 5806, 0705 940 0265 | 2014-11-12 | 7558950 |  | 2 months
267 | Consultancy Services for the Forensic Cleaning and Consolidation of NPA;s Account within the Network of Keystone Bank PLC | Recurrent Expenditure | 19/9/14 | PTB | Competitive Bidding | 31/10/14 | Nov. 2014 | 150000000 |  | 25/11/14 | Yes | Messrs Segun Aremu & Co | Plot 9, Barnawa Close, Challawa GRA Challawa Kaduna 0803 306 6142 062 886320 | 2014-11-12 | 7455000 |  | 2 months
268 | Consultancy Services for the Forensic Cleaning and Consolidation of NPA;s Account within the Network of Fidelity Bank PLC | Recurrent Expenditure | 19/9/14 | PTB | Competitive Bidding | 31/10/14 | Nov. 2014 | 150000000 |  | 25/11/14 | Yes | Messrs Oluwasiji Ayetan | 20, Lyson Chemical Avenue, Off Idiroko Road, Ota Ogun State. 0802 501 3404, 0802 290 0336 | 2014-11-12 | 7500000 |  | 2 months
269 | Consultancy Services for the Forensic Cleaning and Consolidation of NPA;s Account within the Network of Wema Bank | Recurrent Expenditure | 19/9/14 | PTB | Competitive Bidding | 31/10/14 | Nov. 2014 | 150000000 |  | 25/11/14 | Yes | Messrs Eagle Professional Partners | 22, Bida Road (Wema Bank Building) CBD, Kaduna. 0818 200 4336 0802 843 0798 | 2014-11-12 | 7455000 |  | 2 months |  | 2982000
270 | Consultancy Services for the Forensic Cleaning and Consolidation of NPA;s Account within the Network of First Bank PLC | Recurrent Expenditure | 19/9/14 | PTB | Competitive Bidding | 31/10/14 | Nov. 2014 | 150000000 |  | 25/11/14 | Yes | Messrs Korede Odulaja & Co | 72, Ijikoyejo Street, Ijeshatedo, Surulere, Lagos | 2014-11-12 | 7035000 |  | 2 months |  | 7349370
271 | Consultancy Services for the Forensic Cleaning and Consolidation of NPA;s Account within the Network of City Bank | Recurrent Expenditure | 19/9/14 | PTB | Competitive Bidding | 31/10/14 | Nov. 2014 | 150000000 |  | 25/11/14 | Yes | Messrs Yomi Isafiade & Associates | 66, Clampbell Street, Lagos Island. 0703 938 7193, 0802 290 2446 | 2014-11-12 | 7455000 |  | 2 months |  | 2982000
272 | Consultancy Services for the Forensic Cleaning and Consolidation of NPA;s Account within the Network of Sterling Bank | Recurrent Expenditure | 19/9/14 | PTB | Competitive Bidding | 31/10/14 | Nov. 2014 | 150000000 |  | 25/11/14 | Yes | Messrs Rosewater Partners | 5, Shagamu Avenue, Off Association Avenue, Ilupeju Lagos. 01- 2718643 - 4 | 2014-11-12 | 7354767 |  | 2 months
273 | Supply of 88 Nos. New Tyres for all All Fire Services Trucks (Eastern Port Area) |  |  | PTB | Competitive Bidding |  |  | Lumpsum 1,088,450,000 |  | 25/11/14 | Yes | Messrs. Sailnak Nigeria Limited | 31, Cater Street, Off Moloney Ebute-Metta, Lagos. 0806 647 3717 | 2014-11-12 | 12381600 |  | 4 weeks |  | 12381600
274 | Connection of 11KV Power Supply to Dockyard at Calabar Port Complex | Recurrent Expenditure | 2014-04-08 | PTB | Competitive Bidding | 15/9/14 | Nov. 2014 | 182944000 |  | 25/11/14 | Yes | Messrs. Larelek Ultimate Limited | Plot 12, CIPM Road, Alausa, Ikeja, Lagos. 0803 328 3214 01-8930475 | 2014-11-12 | 19142550 |  | 2 weeks
275 | Transfer & Installation of Two (2) Nos.1500 KVA Generators from NPA Corporate Headquarters to Tin-Can Island Port and Onne Port Complex | Recurrent Expenditure | 24/9/14 | PTB | Competitive Bidding | 2014-05-11 | Nov. 2014 | 182944000 |  | 25/11/14 | Yes | Messrs. Larelek Ultimate Limited | Plot 12, CIPM Road, Alausa, Ikeja, Lagos. 0803 328 3214 01-8930475 | 2014-11-12 | 9664200 |  | 2 weeks
276 | Construction of Access Control, Concrete Sign Post 2, Gate House, 2 Septic Tanks & 2 Soak-away Pits at the Entrance of Rivers Port, Port-Harcourt | Capital Expenditure | 24/9/14 | PTB | Competitive Bidding | 2014-05-11 | Nov. 2014 | 181914000 |  | 25/11/14 | Yes | Messrs. Larelek Ultimate Limited | Plot 12, CIPM Road, Alausa, Ikeja, Lagos. 0803 328 3214 01-8930475 | 2014-11-12 | 11607205.5 |  | 2 months
277 | Supply of Operation al Vehicles for the Port Authority Police Western Command. | Recurrent Expenditure | 14/7/14 | PTB | Competitive Bidding | 25/8/14 | Nov. 2014 | 278047000 |  | 25/11/14 | Yes | Messrs. R. T. Briscoe Nig. Limited | 18, Fatai Atere Way, Matori, Lagos. 01 - 2790 757, 270 3477 | 2014-11-12 | 40792500 |  | 1 week |  | 40792500
278 | Supply & Installation of Computer Hardware & Accessories for NPA, Delta Port Complex, Warri, Delta Port | Recurrent Expenditure | 2014-11-09 | PTB | Competitive Bidding | 23/10/2014 | Nov. 2014 | 2510810000 |  | 25/11/14 | Yes | Messrs. Tripple Vision Limited | 374, Kurmawa, Kano State | 2014-11-12 | 19687500 |  | 4 weeks |  | 19687500
279 | Deployment of Desk SMS, DATA/Voice Communication Application & Infrastructure | Recurrent Expenditure | 24/9/2014 | PTB | Competitive Bidding | 2014-05-11 | Nov. 2014 | 2510810000 |  | 25/11/14 | Yes | Messrs. Specserve Limited | 20, Ibrahim Crescent, Awoyaya, Ajah, Lagos 0802 880 5766 | 2014-11-12 | 17801795.5 |  | 6 weeks |  | 17801795.5
280 | Supply of Tools & Equipment for Lagos Dockyard | Recurrent Expenditure | 25/8/14 | PTB | Competitive Bidding | 2014-09-10 | Nov. 2014 | 255000000 |  | 25/11/14 | Yes | Messrs. Sunola Investment Limited | 42, S. A. Latinwo Street, Gudu District, Abuja. 0802 380 0316 | 16/12/14 | 22152165 |  | 6 weeks
281 | Supply of Tools & Equipment for Warri Dockyard | Recurrent Expenditure | 25/8/14 | PTB | Competitive Bidding | 2014-09-10 | Nov. 2014 | 255000000 |  | 25/11/14 | Yes | Messrs. Bru-Voks Integrated Concepts Limited | 101, Refinery Road Effurun, Delta State | 16/12/14 | 35683000 |  | 90 days |  | 35683000
282 | Supply of Tools & Equipment for Onne Dockyard | Recurrent Expenditure | 25/8/14 | PTB | Competitive Bidding | 2014-09-10 | Nov. 2014 | 255000000 |  | 25/11/14 | Yes | Messrs. Fingers Nigeria Limited | 16A, Buma Road, Apapa Lagos. 0803 329 9921, 0802 835 1169 | 16/12/14 | 34731875.85 |  | 90 days |  | 34731875.85
283 | Supply of Personal Protective Equipment for Environment Department | Recurrent Expenditure | 25/8/14 | PTB | Competitive Bidding | 2014-09-10 | Nov. 2014 | 525000000 |  | 25/11/14 | Yes | Messrs. International Energy Services Limited | Energy House, 9A, Awolowo Road, Ikoyi, Lagos. 01-4615636 01- 4630183 | 2014-11-12 | 9045784.14 |  | 2 weeks
284 | Replacement of 5 Nos Faulty Galvanized Steel Gates (Double Swing ) and Ancillary Works at the Main Entrance Gate, Lagos Port Complex, Apapa. | Capital Expenditure | 2014-02-06 | PTB | Competitive Bidding | 14/7/14 | Nov. 2014 | 181914000 |  | 25/11/14 | Yes | Messrs. Samade Investment Nigeria Limited | 23, Ebenezer Akintunji, Ikotun Lagos 0803 720 8013 | 2014-11-12 | 11984700 |  | 3 months
285 | Consultancy Services for Construction of NPA Administration Building at Abuja Civil/Structural Services. | Capital Expenditure | 18/11/14 | PTB | Competitive Bidding | 2014-10-12 | Dec. 2014 | 500000000 |  |  | Yes | Messrs. Jofa and Partners | Suite 33, Garki II Shopping Complex, Opposite City, Mohammed Buhari Way, Garki, Abuja 0803 314 2266 |  | 12952108.31
286 | Supply of Safety and Occupational Health Equipment for Public Enlightenment and Hazardous Material Handling | Recurrent Expenditure | 28/7/14 | PTB | Competitive Bidding | 2014-09-08 | Nov. 2014 | 525000000 |  | 23/12/14 | Yes | Messrs. King and Cole International Limited | 18,Joseph Waya Close, National Assembly Qtrs. Zone B. Apo Abuja. 0803 396 0665 0806 803 6986 | 24/12/14 | 41962725 |  | 10 weeks
287 | Supply of Personal Protective Equipment for Fire Service Department | Recurrent Expenditure | 28/7/14 | PTB | Competitive Bidding | 2014-08-09 | Nov. 2014 | 675000000 |  |  | Yes | Messrs. Value Asset Nigeria Limited | Block 11, Flat 8, Baruma Estate, Wuse, Abuja. 0818 134 7118 |  | 84609000 |  | 4 weeks
288 | Reactivation of 18M High Mast Security Lights at Common User Areas in Calabar Port | Capital Expenditure | 14/7/14 | PTB | Competitive Bidding | 2014-01-09 | Oct. 2014 | 48000000 |  | 19/12/14 | Yes | Messrs. Marvel Nigeria Limited | 45, Lawani Street, Off University Road, Yaba Lagos. 0703 416 5610 0805 329 8722 | 24/12/14 | 24708600 |  | 4 weeks
289 | Reactivation of 18M High Mast Security Lights at Common User Areas in Rivers Port | Capital Expenditure | 2014-08-09 | PTB | Competitive Bidding | 21/10/14 | Nov. 2014 | 48000000 |  | 19/12/14 | Yes | Messrs. International Energy Services Limited | Energy House, 9A, Awolowo Road, Ikoyi, Lagos. 01-4615636 | 24/12/14 | 13461525 |  | 6 weeks
290 | Maintenance and Corrosion Protection of the Recessed Sheet Pile Wall at Kirikiri Lighter Terminal, Phase 11, Tin-Can Island Port, Lagos | Capital Expenditure | 2014-08-09 | PTB | Competitive Bidding | 21/10/14 | Nov. 2014 | 143735000 |  | 19/12/14 | Yes | Messrs. Drilex Oil Nigeria Limited | KM 5, Refinery Road, Effurun, Delta Port 0807 787 1895 0808 669 5518 | 24/12/14 | 47407500 |  | 24 weeks |  | 47407500
291 | General Renovation of Administration Buildingat Calabar Port Complex | Capital Expenditure | 14/7/14 | PTB | Competitive Bidding | 28/8/14 | Oct. 2014 | 600000000 |  | 19/12/14 | Yes | Messrs.Immanil Haq Nigeria Limited | D71, Kabuga Housing, Kano State. 0806 089 5506, 0809 094 2431 | 24/12/14 | 76256502 |  | 6 months |  | 0
292 | General Renovation of Alraine Warehouse Converted to Officers for Rivers Port | Capital Expenditure | 14/7/14 | PTB | Competitive Bidding | 28/8/14 | Nov. 2014 | 60000000 |  | 19/12/14 | Yes | Messrs. Tunal Resources Limited | Suite 16E &17E, Sobandole Plaza Awolowo Way, Jabi Abuja. 0802 334 5647, 0702 544 9837 | 24/12/14 | 65720974 |  | 120 days
293 | Rehabilitation of Internal Road at Kirikiri Lighter Termina IIl (KLT II), Lagos | Capital Expenditure | 2014-08-08 | PTB | Competitive Bidding | 21/10/14 | Dec. 2014 |  |  | 19/12/14 | Yes | Messrs. Avalon International Nigeria Limited | Plot 1700, Violet Yough Close, Lagos 08141374382 | 24/12/14 | 247940220 |  | 2 months |  | 235543209 |  | 100%
294 | The Imperative of Weekly Nes Magazine Programme to Highlight the activities, Contributions and achievements of NPA to the Nigerian Economy | Recurrent Expenditure |  | PTB | Competitive Bidding |  |  | 282915000 |  |  | Yes | Messrs. First World Media Services | 5, Biaduo Street, Off Keffi Street, Off Awolowo Road, Ikoyi, Lagos. 0706 464 8212 0802 369 7999 |  | 27148875 |  | 13 weeks |  | 27148875
295 | Consultancy Services for the Forensic Cleansing and Consolidation of the Authority's Accounts within the Network of Eco Bank | Recurrent Expenditure | 2014-02-10 | PTB | Competitive Bidding | 13/11/14 | Dec. 2014 | 150000000 |  | 19/12/14 | Yes | Messrs. Ade Adewuyi & Co | Block 11, Suite 22, Sura Shoppoing Complex, Simpson Street, Lagos Island 01 892 1962 | 24/12/14 | 7485000 |  | 2 months
296 | Consultancy Services for the Forensic Cleansing and Consolidation of the Authority's Accounts within the Network of Diamond Bank PLC | Recurrent Expenditure | 2014-02-10 | PTB | Competitive Bidding | 13/11/14 | Dec. 2014 | 150000000 |  | 19/12/14 | Yes | Messrs. Ahmed Idris & Co | 18, Zaria Road Kano, 0805 665 6018, 0818 697 5569 | 24/12/14 | 7498450 |  | 2 months
297 | Consultancy Services for the Forensic Cleansing and Consolidation of the Authority's Accounts within the Network of Stanbic IBTC Bank | Recurrent Expenditure | 19/9/14 | PTB | Competitive Bidding | 31/10/14 | Dec. 2014 | 150000000 |  | 19/12/14 | Yes | Messrs. Oyerinde Oke & Co | 9/11, Tayo Joseph Street, Off Alaja Road, Ayoba Ipaja, Lagos 0802 309 3065, 0802 832 8522 | 24/12/14 | 7497000 |  | 2 months
298 | Consultancy Services for the Forensic Cleansing and Consolidation of the Authority's Accounts within the Network of Skye Bank PLC | Recurrent Expenditure | 19/9/14 | PTB | Competitive Bidding | 31/10/14 | Dec. 2014 | 150000000 |  | 19/12/14 | Yes | Messrs. Onyeluka Nwanze & Associates | 3rd Floor, Foreshore Towers 2A, Osborn Road, Ikoyi Lagos. 01-2690460, 2701718- 9 | 24/12/14 | 7501725 |  | 2 months
299 | Consultancy Services for the Forensic Cleansing and Consolidation of the Authority's Accounts within the Network of Mainstreet Bank |  |  | PTB | Competitive Bidding |  |  |  |  | 19/12/14 | Yes | Messrs. Adedayo Arowolo & Co | 68, Shyllon Street, Off Ikorodu Road, Ilupeju Lagos 0803 304 8989 | 24/12/14 | 7413000 |  | 2 months
300 | Consultancy Services for the Forensic Cleansing and Consolidation of the Authority's Accounts within the Network of Access Bank PLC | Recurrent Expenditure | 19/9/14 | PTB | Competitive Bidding | 31/10/14 | Nov. 2014 | 150000000 |  | 19/12/14 | Yes | Messrs. Remi Oyedeji & Co | 5A, Obasekunmade Road, Off Mallo Filling Station, Ikorodu Lagos 0802 313 5940, 0802 302 7565 | 24/12/14 | 7500000 |  | 2 months
301 | Consultancy Services for the Forensic Cleansing and Consolidation of the Authority's Accounts within the Network of Zenith Bank PLC | Recurrent Expenditure | 2014-02-10 | PTB | Competitive Bidding | 13/11/14 | Nov. 2014 | 150000000 |  | 19/12/14 | Yes | Messrs. Ahmed Tijjani & Co | 23, Ibrahim Taiwo Road, Kano State 0806 605 5711 0802 357 5573 | 24/12/12 | 7471800 |  | 2 months
302 | Consultancy Services for the Forensic Cleansing and Consolidation of the Authority's Accounts within the Network of UBA PLC | Recurrent Expenditure | 2014-02-10 | PTB | Competitive Bidding | 13/11/2014 | Nov. 2014 | 150000000 |  | 19/12/14 | Yes | Messrs. Adeniyi Anifowose & Co | Ola-Iya House, Oyebola Street, Off Safurat Benson Street, Ikorodu Lagos 0803 302 4394 0802 312 9642 | 24/12/14 | 7500000 |  | 2 months
303 | Consultancy Services for the Forensic Cleansing and Consolidation of the Authority's Accounts within the Network of Enterprise Bank PLC | Recurrent Expenditure | 2014-08-10 | PTB | Competitive Bidding | 2014-09-12 | Dec. 2014 | 150000000 |  | 19/12/14 | Yes | Messrs. Ahmed Zakari & Co | 175B, Isale Eko Avenue, Dolphine Estate, Ikoyi Lagos 01 743 1279, 01 743 1280 | 24/12/14 | 7304000 |  | 2 months
304 | Upgrading and Optimization of Server Room, Onne | Recurrent Expenditure |  | PTB | Competitive Bidding |  |  |  |  | 23/12/14 | Yes | Messrs. Intertec Engineering Nigeria Limited | Ojuolape House Plot 9, Block c, CBD. Off Agidingbi Road, Alausa Ikeja. 01-554650 | 24/12/14 | 19813500 |  | 1 month |  | 19813500
305 | Supply of Surveillance and Monitoring Equipment for Tank Farms in Calabar Port | Recurrent Expenditure |  | PTB | Competitive Bidding |  |  |  |  | 22/12/14 | Yes | Messrs. Leke Concept Limited | 1, Adegbeyeni Street, Behind Alade Mkt. Ikeja, Lagos 0803 346 7707 | 24/12/14 | 19283670 |  | 8 weeks
306 | Supply of Souvenir (West-Point Freezer WBQ309) for Long Service Award for Human Resources Division | Recurrent Expenditure | 21/10/14 | PTB | Competitive Bidding | 2014-02-12 | Dec. 2014 | 283451000 |  | 19/12/14 | Yes | Messrs. O. J. Kings Company Limited | 63, Sanya Street, Aguda, Surulere, Lagos. 0909 924 1560 | 24/12/14 | 4498200 |  | 120 days
307 | Supply of Souvenir (Samsung Double Door Fridge RS 21 HF TPN) for Long Service Award for Human Resources Division | Recurrent Expenditure | 21/10/14 | PTB | Competitive Bidding | 2014-02-12 | Dec. 2014 | 283451000 |  | 19/12/14 | Yes | Messrs Tino Electronics | Legacy Place, 3rd R/About, Lekki Expressway, Lagos 0803 921 5321, 0709 503 8214, 0802 290 2969 | 24/12/14 | 4107600 |  | 120 days
308 | Construction of WireMesh Canopy and Turnstile Gate Entrance at Kirikiri Lighter Terminal, Phase I & II Gate Entrance, Apapa, Lagos. | Capital Expenditure | 2014-02-10 | PTB | Competitive Bidding | 13/11/14 | Nov. 2014 | 181914000 |  | 19/12/14 | Yes | Messrs. Fa'ida Fasha Ventures | 41, Park Lane, Apapa Lagos 0803 293 9073 | 24/12/14 | 11373450 |  | 7 weeks |  | 11373450
309 | General Renovation of Anchorage Canteen, Rivers Port, Port harcourt | Recurrent Expenditure | 24/9/14 | PTB | Competitive Bidding | 23/10/2014 | Nov. 2014 | 600000000 |  |  | Yes | Messrs. Moskelly services Limited | Shop 1A, Aridman Press, by State Civil Service Commission, Okene/Kabba Road, Lokoja. Kogi Stae 0702 544 2308 |  | 5163894 |  | 6 weeks
310 | Construction of Office Blocks/Re-Roofing of Statistics Offices Behind Administration Block, Federal Lighter Terminal, Onne Port Complex | Recurrent Expenditure | 2014-08-08 | PTB | Competitive Bidding | 19/9/14 | Nov. 2014 | 600000000 |  |  | Yes | Messrs. Lahmah Universal Concept Limited | 7, Uruguan Crescent Wuse II, Abuja |  | 18163808.3 |  | 8 weeks |  | 16471271.62
311 | General Renovation/Re-Roofing of NPA Clinic at Bonny | Recurrent Expenditure | 24/9/14 | PTB | Competitive Bidding | 2014-05-11 | Nov. 2014 | 600000000 |  | 19/12/14 | Yes | Messrs. Laralek Ultimate Limited | Plot 12, CIPM Road, Alausa, Ikeja, Lagos. 0803 328 3214 01-8930475 | 24/12/14 | 9903619 |  | 3 months
312 | Reconstruction of failed Concrete pavement at carpark area, Engineering premises, Federal Lighter Terminal, Onne Port Complex | Recurrent Expenditure | 24/9/14 | PTB | Competitive Bidding | 2014-05-11 | Nov. 2014 | 600000000 |  | 19/12/14 | Yes | Messrs. Prime Engineering Construction Limited | Plot 10, Block, 70 Taiye Olowu Street, Lagos 0805 271 4496, 0806 922 7436 | 24/12/14 | 8808296.41 |  | 60 days |  | 8367881.59
313 | Provision of Pedestrian guide Rails with Security shed at the Maingate (West Wing) and Security enhancement through Vehicular and Pedestrian control at New administrative Building, LPC, Apapa, Lagos | Recurrent Expenditure | 17/9/14 | PTB | Competitive Bidding | 2014-05-11 | Nov. 2014 | 600000000 |  | 22/12/14 | Yes | Messrs. Strabic Construction Limited | 48, Adefemi Taire Street, Omole, Ikeja, Lagos Tel: 0803 328 3214 0805 818 7755 | 24/12/14 | 19497200 |  | 2 months
314 | Disconnection, Dismantling, Packaging and Removal of Flexicom 5000 PABX from Telephone exchange room to a Temporary Location at the Headquarters Building, Marina | Recurrent Expenditure | 21/10/14 | PTB | Competitive Bidding | 2014-02-12 | Dec. 2014 | 89160000 |  | 22/12/14 | Yes | Messrs. Odia Sympathronics Nigeria Enterprises Limited | Amazing Grace Complex, 157, Mushin Road Ile- Iwe Metta B/Stop, Isolo Lagos 0802 314 7074, 0807 120 9791 | 24/12/14 | 6510000 |  | 2 weeks |  | 6510000
315 | Supply of Fire Service Uniform and Uniform Accouterment for Onne Port Complex | Recurrent Expenditure | 29/10/14 | PTB | Competitive Bidding | 2014-09-12 | Dec. 2014 | 675000000 |  | 22/12/14 | Yes | Messrs. Jushix Maritime Services Limited | 29, Burma Road, Apapa Lagos 0803 321 2027 | 24/12/14 | 14983500 |  | 6 weeks
316 | Provision of Secrity Lighting System behind Engineering Canteen Building and Environs, Federal Lighter Terminal, Onne Port Complex | Recurrent Expenditure | 20/10/14 | PTB | Competitive Bidding | 2014-01-12 | Dec. 2014 | 182944000 |  | 22/12/14 | Yes | Messrs. Somkai Nigeria Limited | Plot 3, Sirraso Crescent, Wuse Zone 7, Abuja FCT. 0802 901 8182, 0802 314 5171 | 24/12/14 | 9769200 |  | 1 month |  | 9280740
317 | Supply of Fire Service Uniform and Uniform Accouterment for Lagos Port Complex | Recurrent Expenditure | 20/10/14 | PTB | Competitive Bidding | 2014-01-12 | Dec. 2014 | 675000000 |  | 22/12/14 | Yes | Messrs. Moskelly services Limited | Shop 1A, Aridman Press, by State Civil Service Commission, Okene/Kabba Road, Lokoja. Kogi Stae 0702 544 2308 | 24/12/14 | 18202275 |  | 3 weeks
318 | Supply of Fire Service Uniform and Uniform Accouterment for Tin-Can Island Port Complex | Recurrent Expenditure | 21/10/14 | PTB | Competitive Bidding | 2014-02-12 | Dec. 2014 | 675000000 |  | 22/12/14 | Yes | Messrs. Visible Construction Limited | 20, Hakeen Balogun Street, Ikeja Lagos. 01-8117100 | 24/12/14 | 16953085 |  | 4 weeks
319 | Supply of Fire Service Uniform Accouterment for Delta Ports, Warri | Recurrent Expenditure | 21/10/14 | PTB | Competitive Bidding | 2014-02-12 | Dec. 2014 | 675000000 |  | 22/12/14 | Yes | Messrs. Tinn and Zaytoun Investment Limited | 8, Abbey Street, Onipanu Lagos. 0708 337 9575 | 24/12/14 | 13707750 |  | 4 weeks
320 | Supply of Touch Free and Instant Dispensers with Hand Sanitizer and Refills for NPA Offices in Maina, Sterling Towers, Campbell & Joseph Street, Clinic | Recurrent Expenditure | 24/9/14 | PTB | Competitive Bidding | 2014-05-11 | Nov. 2014 | 525000000 |  | 22/12/14 | Yes | Messrs. Alto-Danyaya Nigeria Limited | 29, Adebola Street, Surulere, Lagos 0803 343 2639 | 24/12/14 | 7035000 |  | 1 week |  | 7035000
321 | Printing and Supply of Audit Witnessing, Project Monitoring and Query Forms | Recurrent Expenditure | 20/10/14 | PTB | Competitive Bidding | 2014-01-12 | Dec. 2014 | 212049000 |  | 24/12/14 | Yes | Messrs. Benvic Limited | 33, Bamgbose Street, Lagos Island. 0803 345 871 |  | 4987500 |  | 8 weeks |  | 4987500
322 | Printing and Supply of Servicom Stickers, Projector and Printer | Recurrent Expenditure | 2014-08-07 | PTB | Competitive Bidding | 19/8/14 | Dec. 2014 | 212049000 |  | 22/12/14 | Yes | Messrs. Am-Sadaq Ventures | 711, Road 20C Close, FESTAC Town, Lagos 0803 343 2639 | 24/12/14 | 3685500 |  | 4 weeks |  | 3685500
323 | Printing and Supply of various types of Envelopes for NPA | Recurrent Expenditure | 2014-02-10 | PTB | Competitive Bidding | 13/11/14 | Dec. 2014 | 212049000 |  | 22/12/14 | Yes | Messrs. Zotok Limited | 1, Raimi Adedokun Lane, By Gbagada General Hospital, Lagos. 0702 860 2146 | 24/12/14 | 12025125 |  | 2 months |  | 12025125
324 | Supply of outboard Engines for Police Boats 1 & 2 | Recurrent Expenditure | 2014-02-10 | PTB | Competitive Bidding | 13/11/14 | Nov. 2014 | 25218000 |  | 22/12/14 | Yes | Messrs Saturn Integrated Services Limited | Suite 305/307 Kano House, 73 Ralph Shodeinde Street CBD Abuja. 0807 070 1104 | 24/12/14 | 11376056 |  | 2 months
325 | Supply and Installation of Security Speed Breakers (Calming Ramps) at the Entrance/Exit gates of various Ports | Recurrent Expenditure | 2014-02-10 | PTB | Competitive Bidding | 13/11/14 | Dec. 2014 | 125422000 |  | 22/12/14 | Yes | Messrs. Tafor Universal Limited | Plot 48, Suite 7 Kasope Road, Ikoyi Lagos. 0703 381 4211, 0807 204 6658 | 24/12/14 | 12906750 |  | 2 months |  | 12906750
326 | Supply of Surveillance and Monitoring Equipment for Safety of Tank Farms in Delta Port, Warri | Recurrent Expenditure | 20/10/14 | PTB | Competitive Bidding | 2014-01-12 | Dec. 2014 | 525000000 |  | 22/12/14 | Yes | Messrs. Sofets Enterprises | 34 Ibikunle Avenue , Bodija, Ibadan 0803 371 5962 | 24/12/14 | 12471900 |  | 10 weeks |  | 12471900
327 | Supply of 45 Nos New Tyres for Utility Vans (Western Port Area) | Recurrent Expenditure | 2014-02-10 | PTB | Competitive Bidding | 13/11/14 | Dec. 2014 | 675000000 |  | 22/12/14 | Yes | Messrs. Belaham Building Services | 122 Buk Road, Kano 0704 542 3898 | 24/12/14 | 12836250 |  | 4 weeks |  | 12836250
328 | Supply and Deployment of Microsoft Licenses to Nigerian Ports Authority, Western Zone | Recurrent Expenditure | 28/10/14 | PTB | Competitive Bidding | 2014-09-12 | Dec. 2014 | 2510810000 |  | 22/12/14 | Yes | Messrs. Sharp Realtors Limited | 2, Akingbola Street, Oregun, Ikeja Lagos, 0819 154 2209 | 24/12/14 | 19980000 |  | 4 weeks |  | 19980000
329 | Supply and Deployment of Microsoft Licenses to Nigerian Ports Authority, Calabar Port | Recurrent Expenditure | 28/10/14 | PTB | Competitive Bidding | 2014-09-12 | Dec. 2014 | 2510810000 |  | 22/12/14 | Yes | Messrs. Stonewall Ventures Limited | 1st Floor Nwoura Plaza 3, Dar Es-Salam Street, Wuse II, Abuja. 0803 787 5359 | 24/12/14 | 19530000 |  | 4 weeks |  | 19530000
330 | Provision of 3MBS/3MBS internet Access for NPA, Calabar Port Complex | Recurrent Expenditure | 20/10/14 | PTB | Competitive Bidding | 2014-01-12 | Dec. 2014 | 2510810000 |  | 22/12/14 | Yes | Messrs. Afritech Multiconcept Limited | 27B Royal Palm Drive Osborne Foreshore II Ikoyi, Lagos 0818 601 8983 | 24/12/14 | 12980000 |  | 4 weeks |  | 12980000
331 | Supply of Branded Hand Crafted Leather Carpet and Puff Set | Recurrent Expenditure | 21/10/14 | PTB | Competitive Bidding | 2014-02-12 | Dec. 2014 | 283451000 |  | 22/12/14 | Yes | Messrs. Tracross Limited | 10B Dutse Street. War College Zone, Gwarinpa FCT. Abuja 0708 220 6481 0807 978 6122 | 24/12/14 | 18522000 |  | 4 weeks |  | 18522000
332 | Supply of Souvenir (Branded Plaques) to NPA | Recurrent Expenditure | 2014-02-10 | PTB | Competitive Bidding | 13/11/2014 | Dec. 2014 | 283451000 |  | 22/12/14 | Yes | Resources Smith Limited | Plot 46B Kumai Crescent Off Aminu Kano Street Wuse II Abuja. 0806 548 5888, 0804 313 9333 | 24/12/14 | 4011000 |  | 4 weeks |  | 4011000
333 | Supply of Branded Umbrellas for NPA | Recurrent Expenditure | 21/10/14 | PTB | Competitive Bidding | 2014-02-12 | Dec. 2014 | 283451000 |  | 22/12/14 | Yes | Messrs. Commodity Exchange (Worldwide) Nigeria Limited | Amaka Shopping Mall 29, Shipolu Street, Onipanu, Lagos 0805 116 2688 | 24/12/14 | 9468375 |  | 4 weeks |  | 9468375
334 | Engagement of a Consultant for Upgrading/Re-designation/Conversion of Employees | Recurrent Expenditure |  | PTB | Competitive Bidding |  |  | 328455000 |  | 19/12/14 | Yes | Messrs. Administrative Staff College of Nigeria (ASCON) | PMB 1004 Topo-Badagry, Lagos State 0803 717 3823 0912 927 0746 | 24/12/14 | 4450000 |  | 2 weeks |  | 4450000
335 | Engagement of additional personnel for the monthly end user support and maintenance of information systems (IS) for NPA - Request for extension of contract | Recurrent Expenditure | 2014-03-11 | PTB | Competitive Bidding | Renewal |  | 2510810000 |  | 22/12/14 | Yes | Messrs. Project Wheel Engineering Limited | 47, Payne Crescent, Apapa, Lagos 0803 821 6666 0809 821 6666 | 24/12/14 | 48600000 |  | 3 months |  | 48600000
336 | Provision of Consultancy Services on Strategy Implementation for Organisational Development Phase 1 | Recurrent Expenditure |  | PTB | Competitive Bidding |  |  | 328455 |  | 22/12/14 | Yes | Messrs. A. T. Metzger | 114, Herbert Macauley Street, Ebute Metta, East, Lagos 0802 295 1553 0809 231 4020 | 28/1/14 | 19959240 |  | 4 months |  | 19959240 | 100%
337 | Inventorisation Study on Community Development Projects in 2013 and its Impact (Commissioning of Consultancy Services) | Capital Expenditure | 2014-11-11 | PTB | Competitive Bidding | 23/12/14 | Jan. 2015 | 30200000 |  | 2015-05-02 | Yes | Messrs. Admobile Media Ltd. | 10, Oweh Street, Jibowu, Lagos. 0704 368 9110 | 13/2/15 | 18686377.5 |  | 6 weeks |  | 18686377.5 |  |  | Pay a License Fee of $20,000.00 to NPA & subsequently pay an annual renewal fees of $10,000.00
338 | Supply of Safety Equipment for Enforcement of Minimum Standard for Trucks operating in the Ports - LPC & TCIPC | Recurrent Expenditure | 20/10/14 The Guardian & Leadership, Federal Tenders Journal & NPA website (2/11/14) | PTB | Competitive Bidding | 2014-01-12 | Jan. 2015 | 525000000 |  | 2015-05-02 | Yes | Messrs Nikcarl Associates Limited | 19/21, Taiwo Soremenkun Street, Canal Estate, Okoko, Lagos. 0803 302 5917 | 13/2/15 | 37065000 |  | 8 weeks
339 | Sensitization & Awareness on Environmental Sustainability in Marine Environment for Delta Port, Warri | Recurrent Expenditure | 22/10/14 | PTB | Competitive Bidding | 2014-03-12 | Jan. 2015 | 525000000 |  | 2015-05-02 | Yes | Messrs. Chikorie Enterprises | 5th Avenue, L. Close, House 1, Festac Town, Lagos. 0802 930 1341, 0805 590 8765 | 13/2/15 | 19456500 |  | 4 weeks
340 | Sensitization & Awareness on Environmental Sustainability in Marine Environment for Rivers Port, Port Harcourt. | Recurrent Expenditure | 2014-03-12 | PTB | Competitive Bidding | 14/1/15 | Jan. 2015 | 575000000 |  | 2015-05-02 | Yes | Messrs. Chikorie Enterprises | 5th Avenue, L Close, House 1, Festac Town, Lagos. 0802 930 1341, 0805 590 8765 | 13/2/15 | 19461750 |  | 4 weeks
341 | Procurement of 1 No. Coastal Monitoring Station S4 current Meter and S4 ADWI Wave Measuring Equipment for Delta Pilotage District, Warri. | Recurrent Expenditure | 2014-03-12 | PTB | Competitive Bidding | 14/1/15 | Jan. 2015 | 87500000 |  | 2015-05-02 | Yes | Messrs. Tyse Limited | KM 13, Lekki Epe Expressway, Opp. 2nd Toll Plaza, Lagos. 0802 316 3747 | 13/2/15 | 19425000 |  | 12 weeks
342 | Sensitization & Awareness on Environmental Sustainability in Marine Environment for Onne Port | Recurrent Expenditure | 2014-01-12 | PTB | Competitive Bidding | 14/1/15 | Jan. 2015 | 525000000 |  | 2015-05-02 | Yes | Messrs. Tyse Limited | KM 13, Lekki Epe Expressway, Opp. 2nd Toll Plaza, Lagos. 0802 316 3747 | 13/2/15 | 19472250 |  | 4 weeks
343 | Sensitization & Awareness on Environmental Sustainability in Marine Environment for Calabar Port. | Recurrent Expenditure | 2014-03-12 | PTB | Competitive Bidding | 14/1/15 | Jan. 2015 | 525000000 |  | 2015-05-02 | Yes | Messrs. Tyse Limited | KM 13, Lekki Epe Expressway, Opp. 2nd Toll Plaza, Lagos. 0802 316 3747 | 13/2/15 | 19498500 |  | 4 weeks
344 | Supply Teledyne RD-ADCP Instrument for Lagos Pilotage | Recurrent Expenditure | 2014-03-12 | PTB | Competitive Bidding | 14/1/15 | Jan. 2015 |  |  | 2015-05-02 | Yes | Messrs. Tyse Limited | KM 13, Lekki Epe Expressway, Opp. 2nd Toll Plaza, Lagos. 0802 316 3747 | 13/2/15 | 19750000 |  | 4 weeks
345 | Upgrading of Power Supply Cable from Sub-Station 6 to Eastern Ports Headquarters building, Rivers Port Complex, Port Harcourt | Recurrent Expenditure | 21/5/14 | PTB | Competitive Bidding | 2014-02-07 | Aug. 2014 | 182944000 |  | 2015-05-02 | Yes | Messrs. Tymol Nigeria Limited | Plot 33, Mobolaji Johnson Avenue, Oregun Industrial Layout, Alausa, Ikeja, Lagos. 0803 315 8566 | 13/2/15 | 15540000 |  | 6 weeks |  | 15540000
346 | Provision and Installation of Primary nad Secondary Telephone Cable Network serving the Control Tower, Harbours Department, Lagos Port Compex, Apapa | Recurrent Expenditure | 21/5/14 | PTB | Competitive Bidding | 2014-02-07 | Oct. 2014 | 89160000 |  | 2015-05-02 | Yes | Messrs. Tiamiyu-Ade Nigeria Limited | Block 14, Plot 6, Kalejaiye Daisi Street, Magodo, GRA, Phase 1, Isheri-Lagos 0803 315 8566 | 13/5/15 | 7812525 |  | 5 weeks
347 | Reactivation of Electrical Installation in Eastern Ports Headquarters, Port Harcourt. | Recurrent Expenditure | 21/5/14 | PTB | Competitive Bidding | 2014-02-07 | Oct. 2014 | 182944000 |  | 2015-05-02 | yes | Messrs. Artic Concept Limited | Plot 33, Mobolaji Johnson Avenue, Oregun Industrial Layout, Alausa, Ikeja, Lagos. 0803 315 8566 01-761 5403 | 13/2/15 | 15796809.09 |  | 5 weeks |  | 15006968.64
348 | Supply of Toners and Computer Accessories for Abuja Liaison Office | Recurrent Expenditure | 3/12/14 NPA Website and Notice board | PTB | Competitive Bidding | 14/1/15 | Jan. 2015 | 2510810000 |  | 2015-05-02 | Yes | Messrs. Jaagee Nigeria Limited | 88, Jaagee House, KM 6, Ibadan-Ife Express Road, Olode, Ibadan 0802 318 9657 | 13/2/15 | 12496050 |  | 3 weeks
349 | Procurement of 1 No. Coastal Monitoring Station S4 current Meter and S4 ADWI Wave Measuring Equipment for ort Harcourt/Bonny Pilotage District, Port Harcourt. | Recurrent Expenditure | 2014-10-12 | PTB | Competitive Bidding | 14/1/14 | Jan. 2015 | 87500000 |  | 2015-05-02 | Yes | Messrs Chikorie Enterprises | 5th Avenue, L Close, House 1, Festac Town, Lagos. 0802 930 1341, 0805 590 8765 | 13/2/15 | 19425000 |  | 12 weeks
350 | Supply Teledyne RD-ADCP Instrument for Port Harcourt Pilotage | Recurrent Expenditure | 16/11/14 | PTB | Competitive Bidding | 27/1/15 | Feb. 2015 | 122500000 |  | 2015-05-02 | Yes | Messrs. Tyse Limited | KM 13, Lekki Epe Expressway, Opp. 2nd Toll Plaza, Lagos. 0802 316 3747 | 13/2/15 | 19700000 |  | 4 weeks
351 | Supply of Six (6 Nos) Protective Storage Cabins for the Environment Department | Recurrent Expenditure | 2014-11-11 | PTB | Competitive Bidding | 23/12/14 | Jan. 2015 | 525000000 |  | 2015-03-02 | Yes | Messrs. Infrastructure Tech. Services Limited | 53, Oyemekun Road, Ogba, Lagos 0806 398 6961 | 13/2/15 | 17860500 |  | 8 weeks
352 | Construction of Clinic Building by Nigerian Ports Authority at Majiya Tuare, LGA, Jigawa | Capital Expenditure | 19/12/14 | PTB | Competitive Building | 30/1/15 | Jan. 2015 | 1250000000 |  | 2015-05-02 | Yes | Messrs. Mazufah | F6, Yoruba Road, Kawo, Kaduna. 0803 930 7024 | 13/2/15 | 27300000 |  | 4 months
353 | Rehabilitation of Historical Library Centre in Kano (CSR) | Capital Expenditure | 19/12/14 | PTB | Competitive Bidding | 30/1/15 | Jan. 2015 | 1250000000 |  | 2015-05-02 | Yes | Messrs. Nordeen Global Resources Limited | Plot 192, Phase 1, Kubwa, Abuja. 0809 802 4381 | 13/2/15 | 19500000 |  | 5 weeks
354 | Supply of Fire Service Uniforms & Uniform Accoutrement for Calabar Port Complex | Recurrent Expenditure | 16/12/14 | PTB | Competitive Bidding | 27/1/15 | Feb. 2015 | 675000000 |  | 2015-05-02 | Yes | Messrs. Mahaj Nig. Limited | 12B, Suliman Barau, Sulija, Niger State. 0805 210 6005, 0803 315 5842 | 13/2/15 | 15127875 |  | 4 weeks
355 | Relocation of Calabar Radio/Signal Station | Capital Expenditure | 22/9/14 Guardian & Daily Trust 5/10/14 Federal Tenders Journal (FTJ) | PTB | Competitive Bidding | 17/11/14 | Jan. 2015 | 200000000 |  | 2015-05-02 | Yes | Messrs. Snotec Facilities Enginerring Ltd. | R15, A Crescent, Citec Estate, Airport Road Bye-Pass Abuja 0806 648 2258, 0802 380 0316 | 13/2/15 | 31991820 |  | 6 weeks
356 | Consultancy Services for the Conduct of Personnel Audit | Recurrent Expenditure | 22/9/14 | PTB | Competitive Bidding | 17/11/14 | Dec. 2014 | 328455000 |  | 2015-05-02 | Yes | Messrs. Dyna Consult Ltd. | 4, Gbolahan Mudashiru Street, Ikoyi, Lagos | 13/2/15 | 19834000 |  | 4 weeks |  | 19834000
357 | Supply of Pollution Clean Up Remediation Tools | Recurrent Expenditure | 19/12/14 | PTB | Competitive Bidding | 30/1/15 | Feb. 2015 | 525000000 |  | 2015-05-02 | Yes | Messrs. Cobuva Renaissance Ltd. | 17, Ramotu Street, Okokomaiko, Lagos 0803 724 2738 | 13/2/15 | 7497403.451 |  | 4 weeks |  | 7497403.45
358 | Supply of Surveillance & Monitoring Equipment for Safety of Tank Farm in Lagos Port Complex | Recurrent Expenditure | 16/12/14 | PTB | Competitive Bidding | 27/1/15 | Feb. 2015 | 525000000 |  | 2015-05-02 | Yes | Messrs. Pad Gabza Global Resources Ltd. | 102, Samphino Road, Kpansia-Epie, Yenagoa, Bayelsa State. 0803 543 3155 | 13/2/15 | 13804665 |  | 4 weeks
359 | Supply of Spare Parts for MT Otuoke | Recurrent Expenditure | 16/12/14 | PTB | Competitive Bidding | 27/1/15 | Feb. 2015 | 355000000 |  | 2015-05-02 | Yes | Messrs. Cobuva Renaissance Ltd. | 17, Ramotu Street, Okokomaiko, Lagos 0803 724 2738 | 13/2/15 | 7484400 |  | 2 months |  | 7497403.45
360 | Supply and Installation of Computer Hardware & Accessories for NPA | Recurrent Expenditure | 2014-08-09 | FEC | Competitive Bidding | 23/9/14/ 9/1/15 | Jan. 2015 | 2510810000 |  |  | Yes | Messrs. Tripple Vision Limited | 60B, Mississippi Street, Maitama, Abuja 0803 059 1059, 0815 562 7414 |  | 324757604.14 |  | 6 weeks
361 | Provision of Some Radio Transmission Equipment as CSR intervention on selected Federal Radio Corporation of Nigeria (FRCN) Stations (Positive FM, Akure | Recurrent Expenditure | 2014-11-11 | PTB | Competitive Bidding | 23/12/14 | Jan. 2015 | 1250000000 |  | 2015-05-02 | Yes | Messrs. Amicent Nigeria Limited | 66, Clampbell Street, Lagos Island. 0703 938 7193, 0802 290 2446 | 13/2/15 | 28392000 |  | 4 weeks
362 | Provision of 2MBS/2MBS Internet Access for NPA, Eastern Zone | Recurrent Expenditure | 2014-11-11 | PTB | Competitive Bidding | 23/12/14 | Jan. 2015 | 2510810000 |  | 2015-05-02 | Yes | Messrs. Kwod System Company Limited | 11, Ugbaje Aki Street, Maryland, Lagos. 0802 592 2513 | 13/2/15 | 11917500 |  | 30 days |  | 11917500
363 | Upgrade and Optimization of Server Room, Rivers Port, Port Harcourt | Recurrent Expenditure | 2014-11-11 | PTB | Competitive Bidding | 23/12/14 | Jan. 2015 | 2510810000 |  | 2015-05-02 | Yes | Messrs. SAO Machinery Ltd | Plot 9, Ojulape House, Block C, CBD, Alausa, Ikeja, Lagos. 0803 217 6003 0816 888 7228 0807 387 2344 | 13/2/15 | 19650750 |  | 8 weeks |  | 19650750
364 | Supply of Toners and Computer Accessories for NPA, Headquarters | Recurrent Expenditure | 2014-11-11 | PTB | Competitive Bidding | 23/12/14 | Jan. 2015 | 2510810000 |  | 2015-05-02 | Yes | Messrs. Mcquintus Ltd. | 1,Agbreh Road, Off Allen AveB/Stop, Ikeja, Lagos. 01- 7741408 01- 8042594 0704 043 7247 | 13/2/15 | 19720000 |  | 30 days |  | 19720000
365 | Design and Implementation of Application Software to pull eletronic manifest information from Customs NCIS System and Convert to Reusable format | Recurrent Expenditure | 2014-11-11 | PTB | Competitive Bidding | 23/12/14 | Jan. 2015 | 2510810000 |  | 2015-05-02 | Yes | Messrs. Olvic Nigeria Ltd | 25, Emina Crescent, Off Toyin Street, Ikeja, Lagos 0808 493 9826 0806 336 0288 | 13/2/15 | 19687500 |  | 4 weeks
366 | Consultancy Services for the Forensic Cleansing and Consolidation of NPA'S Accounts within the Network of Heritage Bank PLC | Recurrent Expenditure | 20/10/14 | PTB | Competitive Bidding | 2014-01-12 | Dec. 2014 | 150000000 |  |  | Yes | Messrs. Karim & Associates Ltd | 10, Old Jos Road Opposite Congo Campus ABU, Zaria, Kaduna State. 0806 776 6436 0805 777 7085 |  | 7869750 |  | 2 months
367 | Provision of 3MBS/3MBS Internet Access for NPA, Rivers Ports. | Recurrent Expenditure | 2014-05-11 | PTB | Competitive Bidding | 17/12/14 | Jan. 2015 | 2510810000 |  | 2015-05-02 | Yes | Messrs. Kwod System Company Limited | 11, Ugbaje Aki Street, Maryland, Lagos. 0802 592 2513 | 13/2/15 | 11917500 |  | 30 days
368 | Consultancy Services for the Forensic Cleansing and Consolidation of NPA'S Accounts within the Network of Union Bank | Recurrent Expenditure | 19/9/14 | PTB | Competitive Bidding | 31/10/14 | Dec. 2014 | 150000000 |  | 2015-05-02 | Yes | Messrs. Suleiman Mohammed & Co | 1A, Airport Road, Opposite Ahmadiya Line Junction, P.O. Box 10653, Kano. 0803 614 2221 0805 501 2952 | 13/2/15 | 7495000 |  | 2 months
369 | Proposaed Construction of Fence Wall for NPA at Cadastral Zone, Abuja | Capital Expenditure | 2014-12-11 | PTB | Competitive Bidding | 24/12/14 | Jan. 2015 | 181914000 |  | 2015-05-02 | Yes | Messrs. Admo T Global Services Ltd. | House H 8, Road 62, FHA Estate, Lugbe Abuja. 0806 972 5147 0803 435 9329 | 13/2/15 | 13761429 |  | 2 months
370 | Supply of Fire Service Uniforms & Uniform Accoutrement for Rivers Port | Recurrent Expenditure | 2014-03-12 | PTB | Competitive Bidding | 14/1/15 | Jan. 2015 | 675000000 |  | 2015-05-02 | Yes | Messrs. Ground Level Services Limited | B288, Wunti Street, Bauchi, Bauchi State. 0709 821 1857 | 13/2/15 | 15200300 |  | 8 weeks
371 | Supply and Installation of Computer Hardware and Accessories for Western Ports.- | Recurrent Expenditure | 2014-12-11 | PTB | Competitive Bidding | 22/12/14 | Jan. 2015 | 2510810000 |  | 2015-05-02 | Yes | Messrs. Hanwell Engineering Limited | 37, Ribadu Road, SW. Ikoyi, Ikoyi. 0817 171 7735 0808 601 4694 | 13/2/15 | 19992682 |  | 3 weeks
372 | Procurement of 1 No. Coastal Monitoring Station S4 Current Meter & S4 ADWi Wave Measuring Equipment for Lagos Pilotage District | Recurrent Expenditure | 2015-03-12 | PTB | Competitive Bidding | 14/1/15 | Jan. 2015 | 87500000 |  | 2015-05-02 | Yes | Messrs. Intertrade Treasuress Ltd | 26,Ali Kareem Akande Street, Olodi Apapa, Lagos 0703 434 6363 | 13/2/15 | 19549687.5 |  | 12 weeks
373 | Consultancy Services for the Construction of NPA Administrative Building at Abuja - Mech./Electrical Engineering Services | Capital Expenditure | 29/10/14 | PTB | Competitive Bidding | 2014-10-12 | Dec. 2014 | 500000000 |  | 2015-05-02 | Yes | Messrs. Elens Konsult. | 10, Tinubu Close, Off Coker Road, Palmgrove Estate, Lagos. 01-8441481 0803 322 5459 | 13/2/15 | 49800000 |  | 2 months
374 | Supply of Toners and Computer Accessories for Eastern Ports | Recurrent Expenditure | 2014-11-11 | PTB | Competitive Bidding | 23/12/14 | Jan. 2015 | 2510810000 |  | 2015-05-02 | Yes | Messrs. Jebster Nigeria Ltd. | D Wing, 2nd Floor Elephant Cement House, CBD, Alausa, Ikeja, Lagos. 0805 428 0075 0805 427 9961 | 13/2/15 | 14840700 |  | 4 weeks
375 | Sensitization & Awareness on Environmental Sustainability in Marine Environment for Lagos Port Complex, Apapa. | Recurrent Expenditure | 2014-03-12 | PTB | Competitive Bidding | 14/1/15 | Jan. 2015 | 675000000 |  | 2015-05-02 | Yes | Messrs. Avalon Intercontinental Nig. Ltd | Plot 1700, Violet Yough Close, Lagos, Off Adetokunbo Ademola Street, V/Island, Lagos. 08141374382 | 13/2/15 | 19509000 |  | 4 weeks |  | 19845000
376 | Sensitization & Awareness on Environmental Sustainability in Marine Environment for TCIPC, Apapa | Recurrent Expenditure | 2014-03-12 | PTB | Competitive Bidding | 14/1/15 | Jan. 2015 | 525000000 |  | 2015-05-02 | Yes | Messrs. INT Technology Partners Ltd. | Ojuolope House Plot 9, Block c, CBD.Alausa, Ikeja, Lagos. 0817 563 8210 | 13/2/15 | 19674900 |  | 4 weeks |  | 19740000
377 | Supply of Licensed Microsoft Software for NPA, Headquarters. | Recurrent Expenditure | 2014-11-11 | PTB | Competitive Bidding | 23/12/14 | Jan. 2015 | 2510810000 |  | 2015-05-02 | Yes | Messrs. Calmness & Prime Ventures | No. 30 Mosumola Street, Aguda, Surulere, Lagos. 0809 501 9443 | 13/2/15 | 19687500 |  | 4 weeks |  | 19687500
378 | Supply of Fire Service Uniforms and Uniform Accouterment for Headquarters | Recurrent Expenditure | 2014-03-12 | PTB | Competitive Bidding | 14/1/15 | Jan. 2015 | 675000000 |  | 2015-05-02 | Yes | Messrs. Saturn Inter Limited | Suite 305/307 Kano House, 73 Ralph Shodeinde Street CBD Abuja. 0807 070 1104 0803 343 1267 | 13/2/15 | 15525825 |  | 30 days
379 | Supply of Tonners and Computer Accessories at Rivers Ports, Port Harcourt | Recurrent Expenditure | 2014-11-11 | PTB | Competitive Bidding | 23/12/14 | Jan. 2015 | 2510810000 |  | 2015-05-02 | Yes | Messrs. SAO Machinery Ltd | Ojuolope House Plot 9, Block c, CBD.Alausa, Ikeja, Lagos. 0816 888 7228 0803 217 6003 0807 387 2344 | 13/2/15 | 19703250 |  | 6 weeks
380 | Rehabilitation of Acess Road Entrance/Exit to the Terminal B' (ECM Terminal) NPA, Calabar | Capital Expenditure | 14/7/14 | PTB | Competitive Bidding | 28/8/14 | Jan. 2015 | 60000000 |  | 2015-04-02 | Yes | Messrs. Bid Engineering Ltd. | 18, Moloney Street, Lagos 01-2630975 | 13/2/15 | 48842200 |  | 12 weeks
381 | Supply of Licensed Microsoft Software for NPA, Delta Ports | Recurrent Expenditure | 2014-11-11 | PTB | Competitive Bidding | 23/12/14 | Jan. 2015 | 2510810000 |  | 2015-05-02 | Yes | Messrs. Multicadre Limited | 22 Dauda Oyeniran Street, Egan, Igando, Lagos | 13/2/15 | 19921114.5 |  | 4 weeks
382 | Supply of Surveillance and Monitoring Equipment for Safety of Tank Farms in TCIPC,Apapa. | Recurrent Expenditure | 2014-03-12 | PTB | Competitive Bidding | 14/1/15 | Jan. 2015 | 575000000 |  | 2015-05-02 | Yes | Messrs. Alhaji M-T Umaru Limited | 73, Allen Avenue, Ikeja, Lagos 0809 990 7539 01-8417635 | 13/2/15 | 14378800 |  | 12 weeks |  | 14378800
383 | Provision of Mobile Internet Service and One year Subscription for 100 people in selected department | Recurrent Expenditure | 2014-11-11 | PTB | Competitive Bidding | 23/12/14 | Jan. 2015 | 2510810000 |  | 2015-05-02 | Yes | Messrs. Enhance Information Systems Technology | 21, Victoria Ironsi Crescent, Gwarimpa Housing Estate, Abuja. 0807 091 71205 | 13/2/15 | 19950000 |  | 4 weeks |  | 19950000
384 | Upgrade of Board Band Internet Connectivity from 4MBS to 10MBS for NPA, Headquarters, Marina, Lagos | Recurrent Expenditure | 2014-11-11 | PTB | Competitive Bidding | 23/12/14 | Jan. 2015 | 2510810000 |  | 2015-05-02 | Yes | Messrs. Enhance Information Systems Technology | 21, Victoria Ironsi Crescent, Gwarimpa Housing Estate, Abuja. 0807 091 71205 | 13/2/15 | 19845000 |  | 4 weeks |  | 19845000
385 | Supply of Microsoft Licence System centre for NPA, Headquarters. | Recurrent Expenditure | 2014-05-11 | PTB | Competitive Bidding | 17/12/14 | Dec. 2014 | 2510810000 |  | 2015-05-02 | Yes | Messrs. Mazufah Contracting Agency Limited | F6, Yoruba Road, Kawo, Kaduna. 0802 502 2513 0703 917 1205 | 13/2/15 | 20343750 |  | 4 weeks
386 | Provision of Offline/Online Back Up to NPA, Headquarters | Recurrent Expenditure | 2014-05-11 | PTB | Competitive Bidding | 17/12/14 | Dec. 2014 | 2510810000 |  | 2015-05-02 | Yes | Messrs. Mazufah Contracting Agency Limited | F6, Yoruba Road, Kawo, Kaduna. 0802 502 2513 0703 917 1205 | 13/2/15 | 19425000 |  | 4 days
387 | Supply of Hard Suction Pipes | Recurrent Expenditure | 20/10/14 | PTB | Competitive Bidding | 2014-01-12 | Jan. 2015 | 525000000 |  | 23/12/14 | Yes | Messrs. King and Cole International Limited | 18,Joseph Waya Close, National Assembly Qtrs. Zone B. Apo Abuja. 0803 396 0665 0806 803 6986 | 24/12/14 | 10945000 |  | 8 weeks
388 | Supply of Licensed Microsoft Software for Eastern Port | Recurrent Expenditure | 2014-11-11 | PTB | Competitive Bidding | 23/12/14 | Jan. 2015 | 2510810000 |  |  | Yes | Messrs. Aurora Pathfinder Limited | 52B, Kudirat Abiola Way, Oregun, Ikeja. 0805 021 7988 0803 537 8839 |  | 19988734.5 |  | 4 weeks |  | 19988734.5
389 | Provision of 3MBS/3MBS Internet Access for NPA, Delta Ports. | Recurrent Expenditure | 2014-03-12 | PTB | Competitive Bidding | 14/1/15 | Jan. 2015 | 2510810000 |  | 2015-05-02 | Yes | Messrs. Peakant Limited | 70, Alhaji Abbas Street, Ogudu, Ojota, Lagos. 0802 212 7175 0803 396 2485 |  | 12995146.5 |  | 4 weeks
| TOTAL | [13 empty] | 15529427715.621 | 3450000

## PETMF
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) : |  | PETROLEUM EQUALISATION FUND (MANAGEMENT) BOARD
MINISTRY : |  | MINISTRY OF PETROLEUM RESOURCES
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2013 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | SUPPLY OF OFFICE EQUIPMENT | NA | AO | SHOPPING | N/A | NA | 1291500 | NA | 17/06/2014 | ZIRCON INVEST | ZIRCON INVEST | 17/06/2014 | 1291500 | 2 WEEKS | 18/06/2014 | 1291500 | 31/06/14 | COMPLETED | 100% | NA | NA | COMPLETED
2 | SUPPLY OF 6 NOS GUBABI 4X4 FIREPROOF CABINET | NA | AO | SHOPPING | NA | NA | 2242800 | NA | 2014-05-08 | OCEANSIZE VENTURES LTD. | OCEANCIZE VENTURES LTD. | 2014-05-08 | 2242800 | 2 WEEKS | 2014-05-08 | 2242800 | 19/08/14 | COMPLETED | 100% | NA | NA | COMPLETED
3 | RAISED FLOOR FOR ICT INFRASTRUCTURE | 07/03/2014 NOTICE BOARD | PTB | NCB | 2014-03-06 | 2014-06-06 | 8090709.38 | NA | 24/07/2014 | BARAFATIN LTD | BARAFATIN LTD | 24/07/2014 | 8090709.38 | 8 WEEKS | 25/07/2014 | 8090709.38 | 18/09/14 | COMPLETED | 100% | NA | NA | COMPLETED
4 | SUPPLY OF OFFICE EQUIPMENT/RENOVATION | NA | AO | SHOPPING | NA | NA | 2146200 | NA | 15/07/2014 | GREENWICH INT'L. LTD. | GREENWICH INT'L LTD. | 15/07/2014 | 2146200 | 3 WEEKS | 15/07/2014 | 2146200 | 2014-05-08 | COMPLETED | 100% | NA | NA | COMPLETED
5 | PRINTING OF TRANSPORTATION EQUALISATION SCHEME AT A GLANCE IN FULL DIGITAL COLOR | NA | AO | SHOPPING | NA | NA | 315000 | NA | 2014-10-12 | WOLSAK NIGERIA LIMITED | WOLSAK NIGERIA LIMITED | 2014-10-12 | 315000 | 1 WEEK | 2014-10-12 | 315000 | 17/12/2014 | COMPLETED | 100% | NA | NA | COMPLETED
5 | SUPPLY OF OFFICE EQUIPMENT /RENOVATION | NA | AO | SHOPPING | NA | NA | 1190647.5 | NA | 21/11/2014 | EVERGREEN CONSTRUCTION | EVERGREEN CONSTRUCTION | 21/11/2014 | 1190647.5 | 3 WEEKS | 24/11/2014 | 1190647.5 | 2014-05-12 | COMPLETED | 100% | NA | NA | COMPLETED
6 | SUPPLY OF 50 ROLLS OF THERMAL PAPER | NA | AO | SHOPPING | NA | NA | 2480625 | NA | 20/11/2014 | O.A. INT'L COMPANY | O.A. INT'L COMPANY | 20/11/2014 | 2480625 | 2 WEEKS | 20/11/2014 | 2480625 | 2014-05-12 | COMPLETED | 100% | NA | NA | COMPLETED
7 | CONSTRUCTION OF SECURITY BARRICADE | NA | AO | SHOPPING | NA | NA | 2303175 | NA | 15/12/2014 | ARBITRAGE RESSOURCES MGT | ARBITRAGE RESOURCES MGT | 15/12/2014 | 2303175 | 1 WEEK | 15/12/2014 | 2303175 | 22/12/14 | COMPLETED | 100% | NA | NA | COMPLETED
8 | CONSTRUCTION OF 2 NOS CAR PORT | NA | AO | SHOPPING | NA | NA | 2493225 | NA | 17/12/2014 | GAPRIS RESOURCES LTD | GAPRIS RESOURCES LTD | 17/12/2014 | 2493225 | 1 WEEK | 17/12/2014 | 2493225 | 24/12/14 | COMPLETED | 100% | NA | NA | COMPLETED
9 | SUPPLY OF 45 NOS FILING CABINET | NA | AO | SHOPPING | NA | NA | 2296350 | NA | 15/12/2014 | DIAMOND BITS INT'L LTD. | DIAMOND BITS INT'L LTD. | 15/12/2014 | 2296350 | 1 WEEK | 15/12/2014 | 2296350 | 22/12/14 | COMPLETED | 100% | NA | NA | COMPLETED
10 | PARTITIONING NEW HEAD OFFICE | 03/02/14 DAILY TRUST,04/02/14 THISDAY & FED TENDERS JOURNAL | PTB | NCB | 2014-04-03 | 31/03/2014 | 187290680.85 | NA | 17/04/2014 | AMPLIFIED NIGERIA LTD. | AMPLIFIED NIGERIA LTD. | 17/04/2014 | 187290680.85 | 12 WEEKS | 17/04/2014 | 187290680.85 | 2014-10-07 | COMPLETED | 100% | NA | NA | COMPLETED
11 | SUPPLY OF 50 NOS AIRWICK FRESHMATIC MACHINE & 100 NOS AIRWICK FRESHMATIC REFILL | NA | AO | SHOPPING | NA | NA | 525000 | NA | 2014-03-04 | ALPHA-BARO COMPANY | ALPHA-BARO COMPANY | 2014-03-04 | 525000 | 3 WEEKS | 2014-03-04 | 525000 | 24/04/2014 | COMPLETED | 100% | NA | NA | COMPLETED
12 | BLOCK WORK & PAINTING NEW HEAD OFFICE | 28/02/14 DAILY TRUST,THISDAY, & FEDERAL TENDERS JOURNAL | PTB | NCB | 24/04/2014 | 16/05/2014 | 20111910 | NA | 28/05/2014 | PRIMARX GLOBAL DIMENSION | PRIMARX GLOBAL DIMENSION | 28/05/2014 | 20111910 | 8 WEEKS | 30/05/2014 | 20111910 | 23/07/14 | COMPLETED | 100% | NA | NA | COMPLETED
13 | PROCUREMENT OF STORE ITEMS | NA | AO | SHOPPING | NA | NA | 1491210 | NA | 24/07/2014 | JAMBEY CONCEPTS | JAMBEY CONCEPTS | 24/07/2014 | 1491210 | 3 WEEKS | 24/07/2014 | 1491210 | 15/08/2014 | COMPLETED | 100% | NA | NA | COMPLETED
14 | ELECTRICAL WORKS NEW HEAD OFFICE | 28/02/2014 DAILY TRUST, THISDAY & FEDERAL TENDERS JOURNAL | PTB | NCB | 2014-06-05 | 22/05/2014 | 13177143 | NA | 28/05/2014 | TAJMUS & CO NIGERIA LTD. | TAJMUS & CO NIGERIA LTD. | 28/05/2014 | 13177143 | 6 WEEKS | 30/05/2014 | 13177143 | 2014-09-07 | COMPLETED | 100% | NA | NA | COMPLETED
15 | AIR CONDITIONING/ INSTALLATION NEW HEAD OFFICE | 28/02/2014 DAILY TRUST, THISDAY & FEDERAL TENDERS JOURNAL | PTB | NCB | 2014-06-05 | 21/05/2014 | 39273911.25 | NA | 28/05/2014 | PENTAGON SYSTEMS LTD. | PENTAGON SYSTEMS LTD. | 28/05/2014 | 39273911.25 | 5 WEEKS | 2014-03-06 | 39273911.25 | 2014-02-07 | COMPLETED | 100% | NA | NA | COMPLETED
16 | INSTALLATION OF SECURITY EQUIPMENTS NEW HEAD OFFICE | NA | PTB | DP (SECURITY) | NA | NA | 56515514.5 | NA | 20/06/2014 | PETRONICS ENGINEERING SERVICES LTD. | PETRONICS ENGINEERING SERVICES LTD. | 20/06/2014 | 56515514.5 | 12 WEEKS | 20/06/2014 | 56515514.5 | 2014-12-09 | COMPLETED | 100% | NA | NA | COMPLETED
17 | MICROSOFT LICENSE | NA | AO | SHOPPING | NA | NA | 1203904.83 | NA | 2014-04-09 | SIDMACH TECHNOLOGIES LIMITED | SIDMACH TECHNOLOGIES LIMITED | 2014-04-09 | 1203904.83 | 2 WEEKS | 2014-04-09 | 1203904.83 | 18/09/14 | COMPLETED | 100% | NA | NA | COMPLETED
18 | PROVISION OF LOCAL AREA NETWORK NEW HEAD OFFICE | 28/02/2014 DAILY TRUST, THISDAY & FEDERAL TENDERS JOURNAL | PTB | NCB | 2014-06-08 | 15/08/2014 | 76265209.71 | NA | 2014-09-09 | BACKBONE CONNECTIVITY NETWORK LTD. | BACKBONE CONNECTIVITY NETWORK LTD. | 2014-11-09 | 76265209.71 | 8 WEEKS | 2014-11-09 | 76265209.71 | 2014-06-11 | COMPLETED | 100% | NA | NA | COMPLETED
19 | PROVISION OF SOLAR POWER BACKUP | 28/02/2014 DAILY TRUST, THISDAY & FEDERAL TENDERS JOURNAL | PTB | NCB | 24/06/2014 | 2014-09-07 | 78000000 | NA | 2014-09-09 | RENECON ENERGY LTD. | RENECON ENERGY LTD. | 2014-11-09 | 78000000 | 8 WEEKS | 2014-11-09 | 78000000 | 2014-06-11 | COMPLETED | 100% | NA | NA | COMPLETED
20 | PROVISION OF BACKUP POWER SYSTEMS | 28/02/2014 DAILY TRUST, THISDAY & FEDERAL TENDERS JOURNAL | PTB | NCB | 2014-06-08 | 15/08/2014 | 50204700 | NA | 2014-09-09 | MICRO PRODUCTS LIMITED | MICRO PRODUCTS LIMITED | 2014-09-09 | 50204700 | 8 WEEKS | 2014-09-09 | 50204700 | 2014-04-11 | COMPLETED | 100% | NA | NA | COMPLETED
21 | SUPPLY OF 1 NO 12KVA FIRMAN GENERATING SET (DIESEL ENGINE WITH LABOUR & TRANSPORT COST TO IBADAN OFFICE | NA | AO | SHOPPING | NA | NA | 1584047.5 | NA | 2014-05-11 | OLEX EMPIRE LIMITED | OLEX EMPIRE LIMITED | 2014-05-11 | 1584047.5 | 3 WEEKS | 2014-05-11 | 1584047.5 | 28/11/2014 | COMPLETED | 100% | NA | NA | COMPLETED
22
23 | PROVISION OF KITCHEN EQUIPMENT/INSTALLATION NEW HEAD OFFICE | 18/06/2014 THISDAY,19/06/14 PUNCH & FTJ | PTB | NCB | 15/07/2014 | 29/09/2014 | 10385396.39 | NA | 2014-02-10 | WESTWOOD DEVELOPERS INT'L LTD. | WESTWOOD DEVELOPERS INT'L. LTD. | 2014-02-10 | 10385396.39 | 10 WEEKS | 2014-02-10 | 10385396.39 | 2014-11-12 | COMPLETED | 100% | NA | NA | COMPLETED
24 | ADDITIONAL ELECTRICAL WORKS NEW HEAD OFFICE | NA | PTB | NA | NA | NA | 5157894.81 | NA | 31/10/2014 | TAJMUS & CO NIGERIA LTD. | TAJMUS & CO NIGERIA LTD. | 31/10/2014 | 5157894.81 | 2 WEEKS | 31/10/2014 | 5157894.81 | 14/11/14 | COMPLETED | 100% | NA | NA | COMPLETED
25 | PROVISION OF KITCHEN EQUIPMENT/INSTALLATION NEW HEAD OFFICE | NA | AO | SHOPPING | NA | NA | 2419672 | NA | 27/11/2014 | GOLDEN BIRD INVESTMENT LIMITED | GOLDENBIRD INVESTMENT LIMITED | 27/11/2014 | 2419672 | 2 WEEKS | 24/11/2014 | 2419672 | 2014-11-12 | COMPLETED | 100% | NA | NA | COMPLETED
26 | ADDITIONAL ELECTRICAL WORKS NEW HEAD OFFICE | NA | PTB | NA | NA | NA | 3255000 | NA | 21/11/2014 | TAJMUS & CO NIGERIA LTD. | TAJMUS & CO NIGERIA LTD. | 27/11/2014 | 3255000 | 2 WEEKS | 27/11/2014 | 3255000 | 2014-11-12 | COMPLETED | 100% | NA | NA | COMPLETED
27
28 | RENOVATION/REPLACEMENT OF TOILET FITTINGS NEW HEAD OFFICE | NA | AO | NS | NA | NA | 1885560 | NA | 15/12/2014 | WITTY WATERWAYS CONSULT | WITTY WATERWAYS CONSULT | 15/12/2014 | 1885560 | 2 WEEKS | 15/12/2014 | 1885560 | 29/12/14 | COMPLETED | 100% | NA | NA | COMPLETED
29 | SUPPLY OF ICT SERVERS | NA | AO | SHOPPING | NA | NA | 245000 | NA | 2014-06-08 | BUSINESS COMMUNICATIONS LIMITED | BUSINESS COMMUNICATIONS LIMITED | 2014-06-08 | 245000 | 2 WEEKS | 2014-06-08 | 245000 | 20/08/2014 | COMPLETED | 100% | NA | NA | COMPLETED
30 | PROVISION OF FIRE DETECTION & ALARM SYSTEMS | NA | PTB | FFS (GOVT. AGENCY) | NA | NA | 3154200 | NA | 23/05/2014 | FEDERAL FIRE SERVICE | FEDERAL FIRE SERVICE | 23/05/2014 | 3154200 | 5 WEEKS | 23/05/2014 | 3154200 | 27/06/14 | COMPLETED | 100% | NA | NA | COMPLETED
31 | RENOVATION OF GOMBE DEPOT OFFICE | NA | AO | SHOPPING | NA | NA | 1435455 | NA | 2014-06-11 | HARRY INTEGRATED SERVICES | HARRY INTEGRATED SERVICES | 2014-06-11 | 1435455 | 4 WEEKS | 2014-06-11 | 1435455 | 2014-08-12 | COMPLETED | 100% | NA | NA | COMPLETED
32 | ADDITIONAL SECURITY WORKS NEW HEAD OFFICE | NA | AO | NA | NA | NA | 1498875 | NA | 15/12/2014 | ARBITRAGE RESSOURCES MGT | ARBITRAGE RESOURCES MGT | 15/12/2014 | 1498875 | 2 WEEKS | 15/12/2014 | 1498875 | 29/12/14 | COMPLETED | 100% | NA | NA | COMPLETED
33 | DATA CENTRE ACCESSORIES | NA | AO | SURVEY | NA | NA | 347130 | NA | 23/01/2014 | BRIDGEUP NIGERIA LIMITED | BRIDGEUP NIGERIA LIMITED | 23/01/2014 | 347130 | 2 WEEKS | 23/01/2014 | 247130 | 2014-07-02 | COMPLETED | 100% | NA | NA | COMPLETED
34 | PUBLIC PERCEPTION OF PEFMB (PUBLIC OPINION POLL) | 12/06/2014 GUARDIAN,12/06/2014 THISDAY & FTJ | PTB | NCB | 2014-06-08 | 29/09/2014 | 35000000 | NA | 2014-02-10 | CEDRON NIGERIA LIMITED | CEDRON NIGERIA LIMITED | 2014-02-10 | 35000000 | 12 WEEKS | 2014-02-10 | 35000000 | 31/12/2014 | COMPLETED | 100% | NA | NA | COMPLETED
35 | SUPPLY OF 20 NOS C-WAY DOUBLE DOOR WATER DISPENSER | NA | AO | SURVEY | NA | NA | 1234800 | NA | 2014-10-11 | NURISAB NIGERIA ENTERPRISES | NURISAB NIGERIA ENERPRISES | 2014-10-11 | 1234800 | 3 WEEKS | 2014-10-11 | 1234800 | 28/11/2014 | COMPLETED | 100% | NA | NA | COMPLETED
36 | PUBLIC ADDRESS SYSTEM NEW HEAD OFFICE | NA | AO | SHOPPING | NA | NA | 1946500 | NA | 24/12/2014 | JONABEST GLOBAL NIGERIA | JONABEST GLOBAL NIGERIA | 24/12/2014 | 1946500 | 1 WEEK | 24/12/2014 | 1946500 | 31/12/2014 | COMPLETED | 100% | NA | NA | COMPLETED
37 | RENOVATION OF ENUGU ZONAL OFFICE | NA | AO | NCB | NA | NA | 796142 | NA | 2014-05-12 | SANTY ENERGY RESOURCES LTD | SANTY ENERGY RESOURCES LTD | 2014-05-12 | 796142 | 1 WEEK | 2014-05-12 | 796142 | 15/12/2014 | COMPLETED | 100% | NA | NA | COMPLETED
38 | SUPPLY OF CRECHE ITEMS NEW HEAD OFFICE | NA | AO | SHOPPING | NA | NA | 1025010 | NA | 24/12/2014 | SEQUOIA INVESTMENT LIMITED | SEQUOIA INVESTMENT LIMITED | 24/12/2014 | 1025010 | 1 WEEK | 24/12/2014 | 1025010 | 31/12/2014 | COMPLETED | 100% | NA | NA | COMPLETED
39 | PURCHASE OF 4 NOS BRIDGESTONE TYRES 285/65/R17 | NA | AO | SURVEY | NA | NA | 350700 | NA | 2014-10-11 | DAWNWATCH LIMITED | DAWNWATCH LIMITED | 2014-10-11 | 350700 | 1 WEEK | 2014-10-11 | 350700 | 17/11/2014 | COMPLETED | 100% | NA | NA | COMPLETED
40 | FUMIGATION OF NEW HEAD OFFICE | NA | AO | SURVEY | NA | NA | 969300 | NA | 23/12/2014 | LENKOSNOW NIGERIA LIMITED | LENKOSNOW NIGERIA LIMITED | 23/12/2014 | 969300 | 1 WEEK | 23/12/2014 | 969300 | 31/12/2014 | COMPLETED | 100% | NA | NA | COMPLETED
41 | CONSUMABLES FOR COMPUTERS & PRINTERS | NA | AO | SHOPPING | NA | NA | 1428000 | NA | 2014-03-10 | MYLOID SYSTEMS | MYLOID SYSTEMS | 2014-03-10 | 1428000 | 4 WEEKS | 2014-03-10 | 1428000 | 31/10/2014 | COMPLETED | 100% | NA | NA | COMPLETED
42 | RENOVATION & SUPPLY OF OFFICE EQUIPMENT TO IBADAN DEPOT OFFICE | NA | AO | SURVEY | NA | NA | 373190.48 | NA | 2014-05-12 | THE CARDINAL VIRTUES LIMITED | THE CARDINAL VIRTUES LIMITED | 2014-05-12 | 373190.48 | 2 WEEKS | 2014-05-12 | 373190.48 | 15/12/2014 | COMPLETED | 100% | NA | NA | COMPLETED
43 | DOCUMENTARY ON PROJECT AQUILA | 12/06/2014 GUARDIAN,12/06/2014 THISDAY & FTJ | PTB | NCB | 2014-06-08 | 29/09/2014 | 33770000 | NA | 2014-02-10 | FUEL COMMUNICATIONS LIMITED | FUEL COMMUNICATIONS LIMITED | 2014-02-10 | 33770000 | 12 WEEKS | 2014-02-10 | 33770000 | 31/12/2014 | ON-GOING | 10000% | NA | NA | ONGOING
44 | SUPPLY OF GOOD YEAR TYRES 225/50R17-9V (12 NOS) AND 255/60R 18-112V (8 NOS) | NA | AO | SHOPPING | NA | NA | 1332450 | NA | 18/08/2014 | MODE TECHNICAL GLOBAL | MODE TECHNICAL GLOBAL | 18/08/2014 | 1332450 | 1 WEEK | 18/08/2014 | 1332450 | 25/08/2014 | COMPLETED | 100% | NA | NA | COMPLETED
45 | REPAIR & CALIBRATION OF INJECTOR NOZZLES ON 150KVA GENERATING SET | NA | AO | SURVEY | NA | NA | 120600 | NA | 2014-12-12 | TOPCLASS GENERATORS LIMITED | TOPCLASS GENERATORS LIMITED | 2014-12-12 | 120600 | 1 WEEK | 2014-12-12 | 120600 | 19/12/2014 | COMPLETED | 100% | NA | NA | COMPLETED
46 | MODULAR DOOR SIGNS, MODULAR DIRECTIONAL SIGNS WITH MATERIALS | NA | AO | SURVEY | NA | NA | 2497000 | NA | 2014-12-12 | BAGGIO VISUAL CONCEPT | BAGGIO VISUAL CONCEPT | 2014-12-12 | 2497000 | 1 WEEK | 2014-12-12 | 2497000 | 19/12/2014 | COMPLETED | 100% | NA | NA | COMPLETED
47 | PEPLACEMENT OF CEILING AT GOMBE DEPOT OFFICE (ADDITIONAL WORK) | NA | AO | NA | NA | NA | 85890 | NA | 2014-11-12 | HARRY INTEGRATED SERVICES | HARRY INTEGRATED SERVICES | 2014-11-12 | 85890 | 1 WEEK | 2014-11-12 | 85890 | 17/12/2014 | COMPLETED | 100% | NA | NA | COMPLETED
48 | SUPPLY OF 300GB 10K SAS DRIVE 3 NOS | NA | AO | SHOPPING | NA | NA | 204750 | NA | 18/03/2014 | BRIDGEUP NIGERIA LIMITED | BRIDGEUP NIGERIA LIMITED | 18/03/2014 | 204750 | 4 WEEKS | 18/03/2014 | 204750 | 14/04/2014 | COMPLETED | 100% | NA | NA | COMPLETED
49 | INSTALLATION, SERVICING AND REPLACEMENT OF PARTS ON 100KVA GEN SET AT LAGOS OFFICE | NA | AO | SURVEY | NA | NA | 445410 | NA | 29/01/2014 | TOPCLASS GENERATORS LIMITED | TOPCLASS GENERATING LIMITED | 29/01/2014 | 445410 | 2 WEEKS | 29/01/2014 | 445410 | 2014-07-02 | COMPLETED | 100% | NA | NA | COMPLETED
50 | SUPPLY OF 5,000 COPIES OF 60 LEAVES AQUILA BRANDED EXERCISE BOOKS | NA | AO | SHOPPING | NA | NA | 500000 | NA | 2014-02-04 | WOLSAK NIGERIA LIMITED | WOLSAK NIGERIA LIMITED | 2014-02-04 | 500000 | 3 WEEKS | 2014-02-04 | 500000 | 24/04/2014 | COMPLETED | 100% | NA | NA | COMPLETED
51 | SUPPLY OF HP TONERS (HP 05A 30 NOS, 312A BLACK 2 NOS, 312A CYAN 2 NOS, 312A YELLOW 2 NOS, 312A MAGENTA 2 NOS | NA | AO | SURVEY | NA | NA | 535815 | NA | 2014-05-12 | DE-LAWTECH COMPUTERS | DE-LAWTECH COMPUTERS | 2014-05-12 | 535815 | 2 WEEKS | 2014-05-12 | 535815 | 2014-12-12 | COMPLETED | 100% | NA | NA | COMPLETED
52 | RENOVATION OF GUSAU DEPOT OFFICE | NA | AO | SHOPPING | NA | NA | 1291500 | NA | 18/06/2014 | ZIRCON INVESTMENT LIMITED | ZIRCON INVESTMENT LIMITED | 18/06/2014 | 1291500 | 3 WEEKS | 18/06/2014 | 1291500 | 2014-04-07 | COMPLETED | 100% | NA | NA | COMPLETED
53 | GENERATOR MAINTENANCE & REPLACEMENT OF PARTS | NA | AO | SURVEY | NA | NA | 626052 | NA | 18/09/2014 | TOPTECH ENGINEERING LIMITED | TOPTECH ENGINEERING LIMITED | 18/09/2014 | 626052 | 2 WEEKS | 18/09/2014 | 626052 | 30/09/2014 | COMPLETED | 100% | NA | NA | COMPLETED
54 | PURCHASE OF 3 NOS NOKIA HANDSETS | NA | AO | SHOPPING | NA | NA | 45900 | NA | 27/11/2014 | OKSINO P GLOBAL VENTURES | OKSINO P GLOBAL VENTURES | 27/11/2014 | 45900 | 1 WEEK | 27/11/2014 | 45900 | 2014-02-12 | COMPLETED | 100% | NA | NA | COMPLETED
55 | SUPPLY OF 3.0HP,5.0HP SURFACE PUMPS & PLUMBING FITTINGS FOR INSTALLATION | NA | AO | SURVEY | NA | NA | 951300 | NA | 24/11/2014 | WITTY WATERWAYS CONSULT | WITTY WATERWAYS CONSULT | 24/11/2014 | 951300 | 3 WEEKS | 24/11/2014 | 951300 | 2014-12-12 | COMPLETED | 100% | NA | NA | COMPLETED
56 | CONSUMABLES FOR COMPUTERS & PRINTERS | NA | AO | SHOPPING | NA | NA | 2108793 | NA | 31/03/2014 | BONITECH COMPUTERS LIMITED | BONITECH COMPUTERS LIMITED | 31/03/2014 | 2108793 | 2 WEEKS | 31/03/2014 | 2108793 | 14/04/2014 | COMPLETED | 100% | NA | NA | COMPLETED
57 | SUPPLY OF 4 NOS BRIDGESTONE TYRES 255/70/R15 | NA | AO | SURVEY | NA | NA | 176400 | NA | 29/01/2014 | EMMAKIN GLOBAL VENTURES | EMMAKIN GLOBAL VENTURES | 29/01/2014 | 176400 | 2 WEEKS | 29/01/2014 | 176400 | 2014-10-02 | COMPLETED | 100% | NA | NA | COMPLETED
58 | PROCUREMENT OF INTERMEC DEVICES | NA | AO | DP | NA | NA | 1009108.28 | NA | 16/07/2014 | ALLIED COMPUTERS | ALLIED COMPUTERS | 16/07/2014 | 1009108.28 | 6 WEEKS | 16/07/2014 | 1009108.28 | 27/08/2014 | COMPLETED | 100% | NA | NA | COMPLETED
59 | FUMIGATION OF OFFICE BUILDING | NA | AO | SURVEY | NA | NA | 231000 | NA | 2014-11-02 | LENKOSNOW NIGERIA LIMITED | LENKOSNOW NIGERIA LIMITED | 2014-11-02 | 231000 | 1 WEEK | 2014-11-02 | 231000 | 17/02/2014 | COMPLETED | 100% | NA | NA | COMPLETED
60 | SUPPLY OF OFFICE EQUIPMENT AT MAIDUGURI DEPOT OFFICE | NA | AO | SHOPPING | NA | NA | 783405 | NA | 2014-01-09 | GREMLIN SYNERGY LIMITED | GREMLIN SYNERGY LIMITED | 2014-01-09 | 783405 | 4 WEEKS | 2014-01-09 | 783405 | 2014-01-10 | COMPLETED | 100% | NA | NA | COMPLETED
61 | SERVICING OF SMOKE DETECTORS AND FIRE ALARM SYSTEMS | NA | AO | SURVEY | NA | NA | 95000 | NA | 14/02/2014 | PROSTALLERS NIGERIA LIMITED | PROSTALLERS NIGERIA LIMITED | 14/02/2014 | 95000 | 1 WEEK | 14/02/2014 | 95000 | 21/02/2014 | COMPLETED | 100% | NA | NA | COMPLETED
62 | MATERIALS AT TAGGING SITES | N | AO | SHOPPING | NA | NA | 941062.5 | NA | 2014-05-09 | FINSDAC NIGERIA LIMITED | FINSDAC NIGERIA LIMITED | 2014-05-09 | 941062.5 | 1 WEEK | 2014-05-09 | 941062.5 | 2014-12-09 | COMPLETED | 100% | NA | NA | COMPLETED
63 | PRINTING OF AQUILA FLIERS FOR PUBLICITY | NA | AO | SURVEY | NA | NA | 121000 | NA | 17/02/2014 | SHEPHERD CONCEPT LIMITED | SHEPHERD CONCEPT LIMITED | 17/02/2014 | 121000 | 2 WEEKS | 17/02/2014 | 121000 | 2014-07-03 | COMPLETED | 100% | NA | NA | COMPLETED
64 | 400 YARDS WATER HOSES | NA | AO | SURVEY | NA | NA | 141750 | NA | 18/02/2014 | EMMAKIN GLOBAL VENTURES | EMMAKIN GLOBAL VENTURES | 18/02/2014 | 141750 | 1 WEEK | 18/02/2014 | 141750 | 25/02/2014 | COMPLETED | 100% | NA | NA | COMPLETED
65 | DATA CENTRE ACCESSORIES | NA | AO | SHOPPING | NA | NA | 1092000 | NA | 30/09/2014 | SIGNAL ALLIANCE | SIGNAL ALLIANCE | 30/09/2014 | 1092000 | 4 WEEKS | 30/09/2014 | 1092000 | 30/10/2014 | COMPLETED | 100% | NA | NA | COMPLETED
66 | TECHNOWINDOWS SOFTWARE FOR CREATING & DRIVING MARKING MACHINE AND DATAMATRIX 2D CODE (12 NOS) | NA | AO | SURVEY | NA | NA | 1349250 | NA | 20/02/2014 | DIGITAL INSIGHT TECH & TELECOMS | DIGITAL INSIGHT & TELECOMS | 20/02/2014 | 1349250 | 2 WEEKS | 20/02/2014 | 1349250 | 2014-06-03 | COMPLETED | 100% | NA | NA | COMPLETED
67 | RENEWAL OF HP SERVERS INFRASTRUCTURE SUPPORT FOR ONE YEAR | NA | AO | DP | NA | NA | 1666012.32 | NA | 26/11/2014 | HEWLETT-PACKARD NIGERIA LTD | HEWLETT-PACKARD NIGERIA LTD | 26/11/2014 | 1666012.32 | 1 WEEK | 26/11/2014 | 1666012.32 | 2014-05-12 | COMPLETED | 100% | NA | NA | COMPLETED
68 | SURGE PROTECTORS (150 NOS) WITH ACCESSORIES | NA | AO | SHOPPING | NA | NA | 1073772 | NA | 18/07/2014 | NOSSTORK INVESTMENT LIMITED | NOSTORK INVESTMENT LIMITED | 18/07/2014 | 1073772 | 6 WEEKS | 18/07/2014 | 1073772 | 29/08/2014 | COMPLETED | 100% | NA | NA | COMPLETED
69 | 5 NOS HP 80A TONER CART | NA | AO | SURVEY | NA | NA | 82687.5 | NA | 20/02/2014 | JETLINK LIMITED | JETLINK LIMITED | 20/02/2014 | 82687.5 | 1 WEEK | 20/02/2014 | 82687.5 | 24/02/2014 | COMPLETED | 100% | NA | NA | COMPLETED
70 | PROCUREMENT OF 25 NOS FILING CABINETS (FIRE FORCE BRAND) | NN | AO | SHOPPING | NA | NA | 956812.5 | NA | 25/08/2014 | GOLDENBIRD INVESTMENT LIMITED | GOLDENBIRD INVESTMENT LIMITED | 25/08/2014 | 956812.5 | 5 WEEKS | 25/08/2014 | 956812.5 | 22/09/2014 | COMPLETED | 100% | NA | NA | COMPLETED
71 | REPLACEMENT OF WOODEN TILES | NA | AO | SURVEY | NA | NA | 108267.6 | NA | 2014-04-03 | ISAAC ROGERS NIGERIA LTD | ISAAC ROGERS NIGERIA LTD | 2014-04-03 | 108267.6 | 1 WEEK | 2014-04-03 | 108267.6 | 2014-12-03 | COMPLETED | 100% | NA | NA | COMPLETED
72 | SUPPLY OF HIGH QUALITY AQUILA -BRANDED SANDHU T-SHIRTS (700 NOS) | NA | AO | SURVEY | NA | NA | 2094750 | NA | 14/03/2014 | LILIES INTERNATIONAL | LILIES INTERNATIONAL | 14/03/2014 | 2094750 | 4 WEEKS | 14/03/2014 | 2094750 | 2014-11-04 | COMPLETED | 100% | NA | NA | COMPLETED
73 | SUPPLY AND REPLACEMENT OF 100A DRYCELL BATTERY ON 350KVA 2 NOS | NA | AO | SURVEY | NA | NA | 59850 | NA | 2014-04-12 | TOPCLASS GENERATORS LIMITED | TOPCLASS GENERATORS LIMITED | 2014-04-12 | 59850 | 1 WEEK | 2014-04-12 | 59850 | 2014-11-12 | COMPLETED | 100% | NA | NA | COMPLETED
74 | PACKING BOX CARTONS (2FTX2FTX1 (1/2) (1,000 UNITS) | NA | AO | SURVEY | NA | NA | 1885000 | NA | 24/11/2014 | KIWI TECH & ICT SERVICES LTD | KIWI TECH & ICT SERVICES LTD | 24/11/2014 | 1885000 | 2 WEEKS | 24/11/2014 | 1885000 | 2014-08-12 | COMPLETED | 100% | NA | NA | COMPLETED
75 | SUPPLY OF 13 NOS BOBRICK AUTOMATIC HAND DRIERS | NA | AO | SURVEY | NA | NA | 1576575 | NA | 20/11/2014 | MAFUNAB VENTURES | MAFUNAB VENTURES | 20/11/2014 | 1576575 | 3 WEEKS | 20/11/2014 | 1576575 | 2014-04-12 | COMPLETED | 100% | NA | NA | COMPLETED
76 | SUPPLY OF IDENTITY CARD MATERIALS | NA | AO | SURVEY | NA | NA | 630000 | NA | 13/11/2014 | PRESTIGE WORLD | PRESTIGE WORLD | 13/11/2014 | 630000 | 4 WEEKS | 13/11/2014 | 630000 | 13/12/2014 | COMPLETED | 100% | NA | NA | COMPLETED
77 | SUPPLY OF 30 NOS OPTICAL MOUSE, 1 CARTON OF SCHNEIDER BLACK MARKER & 1 CARTON OF SCHNEIDER RED MARKER | NA | AO | SURVEY | NA | NA | 226537.5 | NA | 2014-10-11 | UNOJODIC VENTURES NIGERIA | UNOJODIC VENTURES NIGERIA | 2014-10-11 | 226537.5 | 2 WEEKS | 2014-10-11 | 226537.5 | 24/11/2014 | COMPLETED | 100% | NA | NA | COMPLETED
78 | RENOVATION WORK AT ENUGU DEPOT | NA | AO | SHOPPING | NA | NA | 1307202.7 | NA | 2014-10-11 | ABETO ENGINEERING COMPANY | ABETO ENGINEERING COMPANY | 2014-10-11 | 1307202.7 | 1 WEEK | 2014-10-11 | 1307202.7 | 17/11/2014 | COMPLETED | 100% | NA | NA | COMPLETED
79 | RELOCATION OF TAGGING EXERCISE TO KADUNA REFINERY | NA | AO | SHOPPING | NA | NA | 341250 | NA | 18/08/2014 | QUADRANT GLOBAL CONCEPT | QUADRANT GLOBAL CONCEPT | 18/08/2014 | 341250 | 6 WEEKS | 18/08/2014 | 341250 | 30/10/2014 | COMPLETED | 100% | NA | NA | COMPLETED
| TOTAL | [11 empty] | 685865442.1

## PTDF
PTDF PROCUREMENT INVENTORY FOR 2014
PROCURING ENTITY (MDA) :
MINISTRY : |  | PETROLEUM TECHNOLOGY DEVELOPMENT FUND
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [5 empty] | CONTRACT AWARD
S/N | CONTRACT DESCRIPTION | APPROVAL THRESHOLD | PROCUREMENT METHOD | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | EXPECTED COMPLETION DATE | PROJECT STATUS | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
ADMIN. & HR
1 | Printing of Nigerian Mining & Geosciences Society (NMGS) Publication | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | FullHouse Consulting Limited | 18-03-14 | 3025000 | 4 weeks | 18-03-14 | 27-03-14 | N/A | N/A | N/A
2 | Printing of PTDF Research Report | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | Direct Digital Prints Limited | 20-03-14 | 3306397.55 | 4 weeks | 20-03-14 | 22-02-14 | N/A | N/A | N/A
3 | Purchase of book on ''Oil & Gas Exploitationin Nigeria'' | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | Engr Dogara Bijimi | 20-03-14 | 500000 | 4 weeks | 20-03-14 | 26-03-14 | N/A | N/A | N/A
4 | Printing of the January, 2014 edition of the Petroleum Technology Journal (PTDJ) | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | Yaliam Press Limited | 25-04-14 | 1548255 | 4 weeks | 25-04-14 | 27-05-14 | N/A | N/A | N/A
5 | Production of specialized stationeries for the office of the Executive Secretary | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | Prince Prints Limited | 23-05-14 | 324450 | 4 weeks | 23-05-14 | 27-05-14 | N/A | N/A | N/A
6 | Printing & supply of letter headed paper & white official conqourer envelops | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | Fedic Nkwo Ventures Printing & Signage | 15-4-14 | 1333500 | 4 weeks | 15-03-14 |  | N/A | N/A | N/A
7 | Replacement of faulty parts of sharp Photocopier domiciled at the Executive Secretary's office | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | Electro-Hall Sharp | 29-07-14 | 67042.5 | 4 weeks | 29-07-14 |  | N/A | N/A | N/A
8 | Printing & Supply of programme of event and book of abstract | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | Yaliam Press Limited | 18-03-14 | 450000 | 4 weeks | 18-03-14 |  | N/A | N/A | N/A
9 | Printing of the july, 2014 edition of Petroleum Technology Journal (PTDJ) | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | Yaliam Press Limited |  | 1876290 | 4 weeks |  |  | N/A | N/A | N/A
10 | Printing of complimentary cards on digital imaging | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | Yaliam Press Limited | 22-10-14 | 87825 | 4 weeks | 22-10-14 |  | N/A | N/A | N/A
11 | Supply of PTDF specially produced stationeries | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | Prince Prints Limited |  | 3591000 | 4 weeks |  |  | N/A | N/A | N/A
12 | Production of supply of Nigeria centenary Commemorative lapel-pins | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | Chilaks Nig Ltd | 28-10-14 | 1008000 | 4 weeks | 28-10-14 |  | N/A | N/A | N/A
13 | Printing of customized PTDF shirts, polos and other accessories for Nigerian students in Norway | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | AVL-RYL Ventures Nigeria Limited | 31-10-14 | 3564000 | 4 weeks | 31-10-14 |  | N/A | N/A | N/A
14 | Supply of 2 units of Toyota Corolla 1.8 & 1 unit Toyota coaster bus to PTDF office complex | TENDERS BOARD | single sourcing | N/A | N/A | N/A | Elizade Nigeria ltd | 27-02-14 | 22777778 | 4 weeks | 27-02-14 | 28-02-14 | N/A | N/A | N/A
15 | supply of 6 units of honda accord cars to PTDF office complex | TENDERS BOARD | single sourcing | N/A | N/A | N/A | T.H.P | 27-02-14 | 40633344 | 4 weeks | 27-02-14 | 28-02-14 | N/A | N/A | N/A
16 | Supply of 4 units of VW Passat 2.0 | TENDERS BOARD | single sourcing | N/A | N/A | N/A | Circular Automobile company ltd |  | 35700000 | 4 weeks |  |  | N/A | N/A | N/A
17 | Supply of 2 units of Toyota Land cruiser VX-V8 5.7 litres petrol engine, 1 unit of Toyota Avensis 2.0 litres petrol engine & 1 unit Toyota hilux | TENDERS BOARD | single sourcing | N/A | N/A | N/A | Circular Automobile company ltd |  | 61369000 | 4 weeks |  |  | N/A | N/A | N/A
18 | Supply of capital items | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | Chandon office & homes limited |  | 1375132.5 | 4 weeks |  |  | N/A | N/A | N/A
19 | Purchase & supply of capital items for university endowment programme | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | Chandon office & homes limited | 15-05-14 | 2000000 | 4 weeks | 15-05-14 |  | N/A | N/A | N/A
20 | Spply of 15,000 litres of diesel | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | First Project Global services ltd | 25-09-14 | 2709000 | 4 weeks | 25-09-14 |  | N/A | N/A | N/A
21 | Installation of toilet extractor fans | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | Akin Olalere Nigeria limited |  | 595455 | 4 weeks |  |  | N/A | N/A | N/A
22 | Supply of fire extinguisher balls | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | Homesource continental ltd |  | 4370625 | 4 weeks |  |  | N/A | N/A | N/A
23 | Supply of office furniture | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | Chandon office & homes limited |  | 2772220 | 4 weeks |  |  | N/A | N/A | N/A
24 | Supply and installation of Cisco Router at PTDF office complex | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | CNI Technologies | 30-01-14 | 519750 |  | 30-01-14 |  | N/A | N/A | N/A
25 | Supply and installation of Power backup system batteries at PTDF office complex | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A |  | 30-01-14 | 1200000 | 4 weeks | 30-01-14 |  | N/A | N/A | N/A
26 | Equipping the office of the Executive Secretary with various items | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | First Project Global services ltd | 24-07-14 | 9967600 | 4 weeks | 24-07-14 | 24-07-14 | N/A | N/A | N/A
STRATEGIC PLANNING & RESEARCH
27 | Disbursement of Endowned Chair | N/A | single sourcing |  | N/A | N/A | 8 Endowned Universities |  | 136376864 | 5 YEARS |  |  | N/A | N/A | N/A
28 | Endowned Facilitation | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | Endowned Universities |  | 6349392 | 5 YEARS |  |  | N/A | N/A | N/A
29 | Annual Oil & Gas Research Grant Competition | TENDERS BOARD | single sourcing | N/A | N/A | N/A | PTDF |  | 39818572.95 | YEARLY |  |  | N/A | N/A | N/A
30 | PTDF Knowledge Sharing Programme | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | PTDF |  | 5450800 | YEARLY |  |  | N/A | N/A | N/A
31 | Printing of Journal | TENDERS BOARD | single sourcing | N/A | N/A | N/A | Admin & HR department takes charge |  | 13924545 | BI-ANNUALLY |  |  | N/A | N/A | N/A
32 | PTDF(oil and Gas Conference/Seminar Local &International | TENDERS BOARD | single sourcing | N/A | N/A | N/A | PTDF |  | 87765306.88 | YEARLY |  |  | N/A | N/A | N/A
33 | Conferences/Seminar for Stakeholder | TENDERS BOARD | single sourcing | N/A | N/A | N/A | PTDF |  | 79294515 | YEARLY |  |  | N/A | N/A | N/A
34 | Professional Associations | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | PTDF |  | 5820000 | YEARLY |  |  | N/A | N/A | N/A
35 | Local Tour | TENDERS BOARD | single sourcing | N/A | N/A | N/A | PTDF |  | 48440505 | YEARLY |  |  | N/A | N/A | N/A
36 | Petroleum Statistics | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | PTDF |  | 5400000 | YEARLY |  |  | N/A | N/A | N/A
37 | PTDF Annual Workshop | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | PTDF |  | 3036300 | YEARLY |  |  | N/A | N/A | N/A
38 | Library and Reference Books | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | PTDF |  | 1320500 | YEARLY |  |  | N/A | N/A | N/A
39 | Books and Journals for Upgraded Universities | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | PTDF |  | 1022500 | YEARLY |  |  | N/A | N/A | N/A
TRAINING DIVISION
40 | University Lecturers Skills Enhancement Training Programme and Spain for Dual Vocational Training | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | New Castle University, United Kingdom and Grenoble Ecole De Management, France | SEPT. 2014 | 6232050 | 1 Week | 2014-10-09 | 17-09-14 | N/A | N/A | N/A
41 | PTDF Technology Enhancement Training & Learning Programme (TETLP) | N/A | single sourcing | N/A | N/A | N/A | Safwaz Nigeria Limited & Semeantic Systems and Messrs on-booarding Impact Consultancy | 2014-05-01 | 118920000 | 3 Weeks | 6TH-10TH MAY (NC), 13TH-17TH MAY (NE,SW), 20TH-24TH MAY 2014 (NW,SE & SS ZONE) | 24-05-2014 | N/A | N/A | N/A
42 | INDUSTRY TRAINING: Direrctorate Cadre of the Ministry of Petroleum Resources on Technical Training in Oil and Gas titled ' The International Oil and Gas Industry Risks and challenges Developing Forward Looking Perspectives for the Petroleum Industry' held in dubai. | N/A | single sourcing | N/A | N/A | N/A | Petrowise Solutions Limited. Pti CONSULTANCY SERVICE LTD | MARCH 2014 - DECEMBER 2014 | 7638050 | 1WK - 2WKS | 17-03-14 | 21-03-14 TO 20-12-14 | N/A | N/A | N/A
43 | Data Management in Oil and Gas Forecasting, Rick and Reliaility Analysis for Members of the Consultative committee on petroleum statistics (CCPS) at PTI Effrurun Delta State | EXECUTIVE SECRETARY | single sourcing | N/A | N/A | N/A | PTDF | DEC. 2014 | 3861300 | 2 WEEKS | 2014-09-12 | 20-12-14 | N/A | N/A | N/A
EDUCATION DIVISION
44 | Oversea Scholarship Scheme (OSS) | TENDERS BOARD | N/A |  | N/A | N/A | Cinfores | OCT. 2014 | 14025000 | 1 YEAR | OCT. 2014 | ONGOING | N/A | N/A | N/A
45 | Oversea Scholarship Scheme (OSS) | EXECUTIVE SECRETARY | N/A | N/A | N/A | N/A | Cinfores |  | 1870000 | 1 YEAR |  |  | N/A | N/A | N/A
46 | Oversea Scholarship Scheme (OSS) | TENDERS BOARD | N/A | N/A | N/A | N/A | Cinfores | NOV. 2014 | 12525000 | 1 YEAR | NOV. 2014 |  | N/A | N/A | N/A
47 | Oversea Scholarship Scheme (OSS) | EXECUTIVE SECRETARY | N/A | N/A | N/A | N/A | Attached | 24-04-2014 | 4800000 | 1 YEAR | 18-05-2014 |  | N/A | N/A | N/A
48 | Oversea Scholarship Scheme (OSS) | EXECUTIVE SECRETARY | N/A | N/A | N/A | N/A | N/A |  | 991900 |  |  |  | N/A | N/A | N/A
49 | Oversea Scholarship Scheme (OSS) | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | FBN PLC | 2014 |  | 1 YEAR | 2014 |  | N/A | N/A | N/A
LEGAL AND SECRETARIAL SERVICES
50 | Recertification fee of PTDF office Headquater | TENDERS BOARD | N/A | N/A | N/A |  | Kolapo Adabale & Co | 21-02-2007 | 31,440,00.00 | 23-04-14 | 21-02-2007 |  | N/A | N/A | N/A
UPSTREAM DIVISION
51 | GEOSCIENCES TRAINING PROGRAM | EXECUTIVE SECRETARY |  | N/A | N/A |  | DANVIC CONCEPTS INTERNATONAL Nigeria ltd | NOV. 23-2011 | 6720000 | 1 weeK | 2014-03-06 |  | N/A | N/A | N/A
52 | POST TRAINING ATTACHMENT PROGRAM | EXECUTIVE SECRETARY |  | N/A | N/A |  | Enidee Global Services | 30-03-2009 | 1557140 | 6 MONTHS IN BATCHES |  | STILL IN PROGRESS | N/A | N/A | N/A
FINANCE & ACCOUNT
53 | Tax Audut Exercise | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | FIRS team |  | 60000 |  | 20-02-14 |  | N/A | N/A | N/A
54 | Tax Audut Exercise | TENDERS BOARD | N/A | N/A | N/A |  | Frankby Consult | 20-02-14 | 15750000 | 4 MONTHS | 27-03-14 | 15-07-14 | N/A | N/A | N/A
55 | Transparency Audt | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | NEITI Team |  | 70000 |  | 19-06-14 |  | N/A | N/A | N/A
56 | Tax Audut Exercise | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | FIRS team |  | 12000 |  | 15-07-14 |  | N/A | N/A | N/A
57 | Annual Audit(Financials) | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | Sada Idris & Co |  | 1814000 |  | 25-10-14 |  | N/A | N/A | N/A
58 | Management Consultancy | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | Damab ltd | 2014-01-11 | 9450000 | 1 MONTH | 2014-01-11 | 30-11-14 | N/A | N/A | N/A
59 | Annual Audit(Financials) | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | Sada Idris & Co | 22-07-14 | 6000000 |  | 21-10-14 | 29-11-14 | N/A | N/A | N/A
60 | consultancy | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | Olaboye Shuaibu & Co | 2012-09-08 | 6375000 |  | 14-08-12 | 27-08-14 | N/A | N/A | N/A
61 | Software Renewal | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | Compucare ltd |  | 3538500 |  | 14-02-14 |  | N/A | N/A | N/A
62 | Software Expenses | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | N/A |  | 210000 |  | 25-02-14 |  | N/A | N/A | N/A
63 | Software Renewal | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | Compucare ltd |  | 1878975 |  | 2014-12-12 |  | N/A | N/A | N/A
| PRESS & ER | [11 empty] | N/A | N/A | N/A
64 | BALANCE OF PRODUCTION AND AIRING OF IHR HAUS INTERACTIVE PROGRAM | TENDERS BOARD | N/A | N/A | N/A |  | VISION MEDIA SERVICES LTD |  | 15282590 |  |  |  | N/A | N/A | N/A
65 | ADVERT AND PHOTO/VIDEO COVERAGE FOR COMMISSIONING OF ICT CENTRES IN LAGOS | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | SHALLOM JJ VENTURES |  | 101700 |  |  |  | N/A | N/A | N/A
66 | JOURNALIST/PHOTOGRAPH AND VIDEO COVERAGE FOR PRESENTATION OF CERTIFICATE TO DEPT GRADUANDS | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | SHALLOM JJ VENTURES |  | 160000 |  |  |  | N/A | N/A | N/A
67 | NTA COVERING OF COMMISSIONING/HANDOVER OF ICT CENTRES | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | NTA |  | 603000 |  |  |  | N/A | N/A | N/A
68 | UKO-NWAFOR'S OBITUARY ANNOUNCEMENTS | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | GUARDIAN NEWSPAPER |  | 619500 |  |  |  | N/A | N/A | N/A
69 | REFUND FOR COVERAGE OF INDUCTION PROGRAM FOR HELICOPTER TRAINEES IN SOUTH AFRICA | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | Sstudio 115 integrated services ltd |  | 200000 |  |  |  | N/A | N/A | N/A
70 | production of monthly newsletter | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | prints espress ltd |  | 236250 |  |  |  | N/A | N/A | N/A
71 | PURCHASE OF PUBLICATION "AGE OF GOODLUCK" | EXECUTIVE SECRETARY | N/A | N/A |  |  | GASKIA MEDIA |  | 30000 |  |  |  | N/A | N/A | N/A
72 | ADVERT FOR 2013/2014 OSS APPLICATION | EXECUTIVE SECRETARY |  |  | N/A |  | GUARDIAN NEWSPAPER |  | 175331 |  |  |  | N/A | N/A | N/A
73 | ADVERT FOR 2013/2014 OSS APPLICATION | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | MEDIA TRUST |  | 143521 |  |  |  | N/A | N/A | N/A
74 | ADVERT FOR 2013/2014 OSS APPLICATION | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | VANGUARD MEDIA LTD |  | 136000 |  |  |  | N/A | N/A | N/A
75 | PRINTING OF 21 PHOTOS OF HELICOPTER PILOTING TRAINING | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | HEZRONE PHOTO STUDIO |  | 16800 |  |  |  | N/A | N/A | N/A
76 | PETROLEUM INDUSTRY REVIEW 2012 | EXECUTIVE SECRETARY | N/A | N/A | N/A |  |  |  | 5000000
77 | PRODUCTION OF PTDF FLIER AND FOLDER | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | PRINTS EXPRESS LTD |  | 483000 |  |  |  | N/A | N/A | N/A
78 | PRINTING OF PHOTOS AND PURCHASE OF CONSUMABLES BY P & ER | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | HEZRONE PHOTO STUDIO |  | 53100 |  |  |  | N/A | N/A | N/A
79 | PRODUCTION OF PTDF FLIERS | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | PRINTS EXPRESS LTD |  | 483000 |  |  |  | N/A | N/A | N/A
80 | COVERAGE OF KAR ACADEMY GRAD IN COTONOU | EXECUTIVE SECRETARY |  | N/A | N/A |  | NTA |  | 95625 |  |  |  | N/A | N/A | N/A
81 | ADVERT PLACEMENT FOR CALL FOR RESEARCH PROPOSALS | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | GUARDIAN |  | 508722 |  |  |  | N/A | N/A | N/A
82 | ADVERT PLACEMENT | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | SHODEVO LTD |  | 1715728 |  |  |  | N/A | N/A | N/A
83 | VIDEO COVERAGE/PHOTO | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | JAY JAY SHALLOM VENTURES |  | 55000 |  |  |  | N/A | N/A | N/A
84 | PAYMENT OF INDEBTEDNESS | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | UPPER REACH LTD |  | 3090000 |  |  |  | N/A | N/A | N/A
85 | ES VISIT TO UK | EXECUTIVE SECRETARY | N/A | N/A |  |  | REFUND BY HEAD PRESS & ER |  | 270000 |  |  |  | N/A | N/A | N/A
86 | ADVERT PLACEMENT FOR OSS APTITUDE TEST | EXECUTIVE SECRETARY | N/A |  | N/A |  | GUARDIAN |  | 173331 |  |  |  | N/A | N/A | N/A
87 | ADVERT PLACEMENT FOR OSS APTITUDE TEST | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | SHODEVO LTD |  | 558563 |  |  |  | N/A | N/A | N/A
88 | LOGISTICS IN FACILITATING SIGNING OF MOU WITH UNITAR | EXECUTIVE SECRETARY |  | N/A | N/A |  |  |  | 200000 |  |  |  | N/A | N/A | N/A
89 | PRESS COVERAGE AT THE KAR ACADEMY COTONOU GRADUATION | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | ESTACODE |  | 420750 |  |  |  | N/A | N/A | N/A
90 | PRESS COVERAGE AT THE KAR ACADEMY COTONOU GRADUATION | EXECUTIVE SECRETARY | N/A | N/A |  |  | ESTACODE |  | 231720 |  |  |  | N/A | N/A | N/A
91 | PHOTO AND VIDEO COVERAGE | EXECUTIVE SECRETARY | N/A |  | N/A |  | JAY JAY SHALOM VENTURES |  | 100000 |  |  |  | N/A | N/A | N/A
92 | ES POTRAIT | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | JAY JAY SHALOM VENTURES |  | 75000 |  |  |  | N/A | N/A | N/A
93 | MEDIA COVERAGE OF MINISTERIAL PLATFORM & PUBLICITY | EXECUTIVE SECRETARY | N/A | N/A | N/A |  |  |  | 660000 |  |  |  | N/A | N/A | N/A
94 | ES INSPECTION VIST PROJECTS IN P/H | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | PER DIEM AND MEDIA COVERAGE |  | 170200 |  |  |  | N/A | N/A | N/A
95 | CANVAS PHOTOGRAPH OF ES | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | JULIA DIGITAL |  | 250000 |  |  |  | N/A | N/A | N/A
96 | 2014/15 SCHOLARSHIP ADVERT | EXECUTIVE SECRETARY |  | N/A | N/A |  | GUARDIAN |  | 508722 |  |  |  | N/A | N/A | N/A
97 | 2014/15 SCHOLARSHIP ADVERT | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | SHODEVO LTD |  | 1466876.25 |  |  |  | N/A | N/A | N/A
98 | PRESS COVERAGE OF SENATE COMMITTEE ON PETROLEUM VISIT | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | JAY JAY SHALOM VENTURES |  | 400000 |  |  |  | N/A | N/A | N/A
99 | COVERAGE OF KOGI GOVERNMENT VIST | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | NTA |  | 905000 |  |  |  | N/A | N/A | N/A
100 | CONGRATULATORY MESSA TO NIGERIA AT 53 | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | SHODEVO LTD |  | 619500 |  |  |  | N/A | N/A | N/A
101 | CONGRATULATORY MESSA TO NIGERIA AT 53 | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | GUARDIAN |  | 385875 |  |  |  | N/A | N/A | N/A
102 | CONGRATULATORY MESSA TO NIGERIA AT 53 | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | NEWS DIRECT GLOBAL CONSEPTS |  | 385875 |  |  |  | N/A | N/A | N/A
103 | LOGISTICS FOR ANTI-CRRUPTION WEEK MEDIA COVERAGE | EXECUTIVE SECRETARY | N/A | N/A | N/A |  |  |  | 200000 |  |  |  | N/A | N/A | N/A
104 | COVERAGE FOR HLICOPTER PILOTING SCHOLARS IN SOUTH AFRICA | EXECUTIVE SECRETARY |  | N/A | N/A |  | PRESS AND NTA |  | 721875 |  |  |  | N/A | N/A | N/A
105 | COVERAGE OF NIGERIAN CONTENT 2013 ROADSHOW AT BAYELSA | EXECUTIVE SECRETARY | N/A | N/A | N/A |  | JAY JAY SHALOM VENTURES |  | 182000 |  |  |  | N/A | N/A | N/A
ICU
106 | 3 YEAR B.Sc POGRAMMES IN DIFFERENT OIL AND GAS RELATED FIELD | N/A | N/A | N/A | N/A |  | LINTON UNIVERSITY COLEGE, MALAYSIA. | FEB. 2012 | 235888562.06 | 1 YEAR 6 MONTHS | FEB. 2012 | 2015-04-01 | N/A | N/A | N/A
107 | 12 MONTH INTENSIVE AUTOMOBILE, ICT, WELDING, PHYSICS, DESIGNS, ECONOMICS AND LANGUAGE TRAINING | TENDERS BOARD | N/A | N/A | N/A |  | KING AMACHREE ROYAL ACADEMY COTONOU, BENIN REPUBLIC | 2012-05-01 | 29251430 | 1 YEAR | 2012-05-01 | 2014-04-01 | N/A | N/A | N/A
108 | 18 MONTH HELICOPTER PILOTING AND AIR SURVEILLANCE TRAINING | N/A | N/A | N/A | N/A |  | HOVER DYNAMICS TRAINING CENTRE, MIDRAND, SOUTH AFRICA | FEB. 2013 | 398233160 | 1 YEAR 6 MONTHS | FEB. 2013 | 2014-08-01 | N/A | N/A | N/A
109 | 4 YEARS B.Sc PROGRAMMES IN PETROLEUM ENGINEERING | TENDERS BOARD | N/A | N/A | N/A |  | GUANGZHOU CITY CONSTRUCTION COLLEGE. GUANGDON UNIVERSITY OF PETROCHEMICAL TECHNOLOGY, CHINA | 2013-07-01 | 78153900 | 4 YEARS | 2013-07-01 | 2018-07-01 | N/A | N/A | N/A
|  |  |  | N/A | N/A
| PROTOCOL |  | N/A
110 | VISAS | N/A | N/A | N/A | N/A |  | REQUESTS |  | 21735000
111 | TICKETS | N/A | N/A | N/A | N/A |  | AGENTS |  | 247500000
112 | EVENT MANAGEMENT | N/A | N/A | N/A | N/A |  | INVITATION REQUEST |  | 43380000
ICT
113 | UPGRADE OF PTDF WEB | EXECUTIVE SECRETARY |  | N/A | N/A |  | USOFT COMPUTERS | DEC. 2014 | 1417500
114 | SUPPLY OF ESET ANTIVIRUS | EXECUTIVE SECRETARY |  | N/A | N/A |  | J.B COMPUTERS | NOV. 2014 | 1625000
| TOTAL | [7 empty] | 1960249086.69

## REA
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) : |  | RURAL ELECTRIFICATION AGENCY
MINISTRY : |  | FEDERAL MINISTRY OF POWER
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY PTB/AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/03/2015 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2014 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | Electrification Of Aba- Alfa, Araromi And Babaode In Ayiba Lga In Oyo State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 25433665 |  | 15/10/2014 | YES | TOLUYAN INTEGRATED SERVICES LTD. | 15/10/2014 | 21684536.85 | 6 WEEKS |  | 18327666.06 | 6months | completed as per 2014 budget | 40 | N/A | N/A
2 | Electrification Of Ikere In Iseyin Lga, Oyo State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 51179040 |  | 15/10/2014 | YES | SHAFANA ENTERPRISES LTD. | 15/10/2014 | 48592975.73 | 6 WEEKS |  | 39390287.61 | 6months | completed as per 2014 budget | 40 | N/A | N/A
3 | Electrification Of Akinwunmi/Osuogun In Iseyin Lga, Oyo State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 32130599 |  | 15/10/2014 | YES | HABITAT & BUILDING CONCEPT LTD. | 15/10/2014 | 26443907.3 | 6 WEEKS |  |  | 6months | completed as per 2014 budget | 40 | N/A | N/A
4 | Electrification Of Ibaragun / Robinyan In Ifo Lga, Ogun State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 32373000 |  | 15/10/2014 | YES | BONUS RESOURCES & INVESTMENT LIMITED | 15/10/2014 | 27233506.5 | 6 WEEKS |  | 23444495.91 | 6months | completed as per 2014 budget | 40 | N/A | N/A
5 | Installation Of 2x7.5mva, 33/11kv And 11kv Panel In Injection Substation At Nkwoagu And Repairs Of Outgoing Feeder In Abia State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 69300000 |  | 15/10/2014 | YES | ONE COMPLET SOLUTION | 15/10/2014 | 59919140 | 10 WEEKS |  | 52977600 | 6months | completed as per 2014 budget | 100 | N/A | N/A
6 | Electrification Of Umunevo-Amagunze/Njiagu Ihuokpara In Enugu State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 37125000 |  | 15/10/2014 | YES | KEWPOWER ENGINEERING CO. LTD. | 15/10/2014 | 33307447.16 | 6 WEEKS |  |  | 6months | Awaiting commissioning | 95 | N/A | N/A
7 | Electrification Improvement In Umuada, Obunaoru And Other Communities In Ngodoukwu In Abia State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 24750000 |  | 15/10/2014 | YES | IJALLA ENGINEERING SERVICES LTD. | 15/10/2014 | 23888766.97 | 6 WEEKS |  | 10748395.07 | 6months | Awaiting commissioning | 95 | N/A | N/A
8 | Electrification Of Ohuhu -Nsulu And Umugo In Isiala Ngwa North Lga In Abia | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 24750000 |  | 15/10/2014 | YES | SABA INTEGRATED RESOURCES LTD | 15/10/2014 | 21910983.93 | 6 WEEKS |  | 2404264.4 | 6months | substation level | 85 | N/A | N/A
9 | Electrification Project At Amagunze Extension 1 In Enugu State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 21072150 |  | 15/10/2014 | YES | EM-PLAN INTERATED LIMITED | 15/10/2014 | 19838354.4 | 4 WEEKS |  | 14962497.89 | 6months | The award was for pole erection only | 95 | N/A | N/A
10 | Electrification Of Fota - Riji - Duwa - Yan - Dingam In Gombi Lga, Adamawa State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 29700000 |  | 15/10/2014 | YES | ELFIN RESOURCE LTD. | 15/10/2014 | 28782798 | 6 WEEKS |  | 15327100.8 | 6months | The award was for pole erection only | 90 | N/A | N/A
11 | Tenah (Gaya Daku, Gartanu, Sikalmi and Kuva Gaya) ITC/TDN | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 14850000 |  | 15/10/2014 | YES | BENGIN & ASSOCIATES LTD. | 15/10/2014 | 12225742 | 4 WEEKS |  |  | 6months | The award was for pole erection only | 90 | N/A | N/A
12 | Zigayirma, Kwaakah, Mullah & Jabba In Hong Lga, Adamawa State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 39600000 |  | 15/10/2014 | YES | McMITCHELL NIG. LTD | 15/10/2014 | 34943120.3 | 6 WEEKS |  |  | 6months | The award was for pole erection only | 40 | N/A | N/A
13 | Rehabilitation of Ngamdu - Gotala and Electrification of Dabira, Kaga LGA, Borno State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 34650000 |  | 15/10/2014 | YES | KAMA INTERGRATED SERVICES LTD. | 15/10/2014 | 32184002.35 | 6 WEEKS |  | 27012857.99 | 6months | completed | 90 | N/A | N/A
14 | Electrification Of Marguba, Kaga Lga, Borno State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 24750000 |  | 15/10/2014 | YES | UGAMA TECHNICAL & SUPPLY COMPANY LTD. | 15/10/2014 | 22764020 | 6 WEEKS |  |  | 6months | --- | -- | N/A | N/A
15 | Electrification Of Malumeri, Damboa Lga, Borno State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 22275000 |  | 15/10/2014 | YES | LUCENT VENTURES LTD. | 15/10/2014 | 21842338.13 | 6 WEEKS |  |  | 6months | yet to be moblised to site | --- | N/A | N/A
16 | Electrification Of Dongon, Gogadi&Kwaredauiel I Zaru Lga In Kebbi State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 39600000 |  | 15/10/2014 | YES | PASONS LIMITED | 15/10/2014 | 34171822.2 | 6 WEEKS |  | 14468676.75 | 6months | completed awaiting commisionning | 100 | N/A | N/A
17 | Electrification Of Kunyai - Marsa - Rikawanzangonkataf Lga Kaduna State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 24750000 |  | 15/10/2014 | YES | LOKO RESOURCES LTD. | 15/10/2014 | 21335874.1 | 6 WEEKS |  | 3640532.16 | 6months | completed | 95 | N/A | N/A
18 | Electrification Of Kamantan - Lenak - Tudun Wada - Kaform - Kagal - Hurgyam - Angwanlaushi - Nassarawa - Kar,Men - Idung - Kanzir - Tapyeri - Hwukyanzangonkataf Lga Kaduna State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 34650000 |  | 15/10/2014 | YES | NAICE CONTRACTS & LOGISTICS LIMITED | 15/10/2014 | 31843580.5 | 6 WEEKS |  | 26844096.02 | 6months | completed | 100 | N/A | N/A
19 | Electrification Of Zonkwa – Kamantan Zangonkataf Lga Kaduna State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 19800000 |  | 15/10/2014 | YES | SHAGAYA GLOBAL SERVICES LTD. | 15/10/2014 | 18953151.15 | 4 WEEKS |  | 8060239.44 | 6months | completed | 100 | N/A | N/A
20 | Electrification Of Ajokoipee Community In Oyun L.G.A, Kwara State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 29700000 |  | 15/10/2014 | YES | JAYCOOT VENTURES LTD. | 15/10/2014 | 27643585 | 6 WEEKS |  |  | 6months | contractor yet to report to zone | 0 | N/A | N/A
21 | Electrification Of Apata - Aje, Owode Jankare,And Alagbon Villages In Asa Lga Of Kwara State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 19800000 |  | 15/10/2014 | YES | DOUBLE Y & O VENTURES LIMITED | 15/10/2014 | 16130763.65 | 4 WEEKS |  | 13648552.83 | 6months | completed awating testing | 94 | N/A | N/A
22 | Electrification Of Oke - Ode / Aireke/ Igbo - Ote, Kereaje- Dikko / Sani - Koro / Eleyele/ Igbaja -Ogele / Magboa&Labaka Extension In Ifelodun Lga, Kwara State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 34650000 |  | 15/10/2014 | YES | LIBERTY (OVERSEA) BROTHERS LTD. | 15/10/2014 | 32919716.21 | 6 WEEKS |  | 14329297.77 | 6months | completed awating testing | 96.7 | N/A | N/A
23 | Electrification Of Alalubosa In Ilorin South Lga, Kwara State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 12375000 |  | 15/10/2014 | YES | EMICO INTERNATIONAL LTD. | 15/10/2014 | 8631152.5 | 4 WEEKS |  |  | 6months | completed awating testing | 100 | N/A | N/A
24 | Electrification Of Gbade - Nakare In Nassarawa State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 14850000 |  | 15/10/2014 | YES | JOETEX GLOBAL VENTURES NIG. LTD | 15/10/2014 | 13640524.9 | 4 WEEKS |  | 11046220.22 | 6months | completed awating testing | 89.9 | N/A | N/A
25 | Electrification Of Fusa - Maijuju - Zandi In Plateau State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 29700000 |  | 15/10/2014 | YES | ERICA DAWN INTL. LTD. | 15/10/2014 | 25862980 | 6 WEEKS |  | 2645365.4 | 6months | contractor on site | 25.2 | N/A | N/A
26 | Electrification Of Hiktup - Kobwang - Mper In Plateau State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 14850000 |  | 15/10/2014 | YES | MOAT GLOBAL CONCEPT NIG LTD. | 15/10/2014 | 11403400 | 4 WEEKS |  | 9816840 | 6months | completed awaiting testing | 99.9 | N/A | N/A
27 | Electrification Of Lungu In Fct | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 24750000 |  | 15/10/2014 | YES | BROWNNY GOLD LIMITED | 15/10/2014 | 21383675 | 6 WEEKS |  | 17571627 | 6months | completed awaiting testing | 99.9 | N/A | N/A
28 | Electrification Of Mpape (Paipe), Fct, Abuja | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 24750000 |  | 15/10/2014 | YES | OMOTOSHO & SONS (NIG) LTD. | 15/10/2014 | 23236182.8 | 6 WEEKS |  | 9532082.64 | 6months | completed awaiting testing | 91.1 | N/A | N/A
29 | Electrification Of Dakin Biyu In Fct | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 29700000 |  | 15/10/2014 | YES | LALUCO CONTRACTORS NIGERIA LIMITED | 15/10/2014 | 27762276.5 | 6 WEEKS |  | 23899698 | 6months | completed awaiting testing | 95.7 | N/A | N/A
30 | Extension Of Electricity To Some Communities In Niger State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 59400000 |  | 15/10/2014 | YES | SHAREVIGO ENGINEERING CO. (NIG) LTD. | 15/10/2014 | 52039277.74 | 10 WEEKS |  | 7805891.67 | 6months | ongoing | 72.6 | N/A | N/A
31 | Electrification Of Pupa Akin Community In Kwara State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 12375000 |  | 15/10/2014 | YES | TOLKINS VENTURES NIG LTD. | 15/10/2014 | 9417500.65 | 4 WEEKS |  |  | 6months | completed awaiting testing | 86.1 | N/A | N/A
32 | Electrification Of Ojegbe Village, Iyakomoboru Community, Oju Lga, Benue State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 12375000 |  | 15/10/2014 | YES | JAFIL ENGINEERING LTD. | 15/10/2014 | 12078450 | 4 WEEKS |  |  | 6months | completed | 95 | N/A | N/A
33 | Electrification Of Harge - Shikaan In Katsina - Ala Lga, Benue State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 14850000 |  | 15/10/2014 | YES | AYOLEX INVESTMENT LTD. | 15/10/2014 | 12903913.1 | 4 WEEKS |  |  | 6months | pole erection in progress | 40.1 | N/A | N/A
34 | Electrification Of Kyado - Mbajir, Katsinaala Lga, Benue State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 12375000 |  | 15/10/2014 | YES | GENEROSITY VENTURE LTD. | 15/10/2014 | 11135408.01 | 4 WEEKS |  |  | 6months | contractor on site | 0 | N/A | N/A
35 | Electrification Of Adikpo - Sati Mbabanu, Kwande Lga, Benue State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 9900000 |  | 15/10/2014 | YES | BEACON CREATIVE IDEAS LTD | 15/10/2014 | 8554068 | 4 WEEKS |  |  | 6months | contractor yet to be taken to site | 0 | N/A | N/A
36 | Ikot Akpan Sung Installation Of Transformers And Construction Of (Ht/Lt) Lines In Akwa Ibom State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 10439280 |  | 15/10/2014 | YES | TEMPS ENGINEERING LIMITED | 15/10/2014 | 8562233 | 4 WEEKS |  |  | 6months | yet to report to site | 0 | N/A | N/A
37 | Electrification Of Ikot Ide Apakpan In Akwa Ibom State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 19800000 |  | 15/10/2014 | YES | GAFA NIG. LTD. | 15/10/2014 | 18415496.25 | 4 WEEKS |  |  | 6months | sub station level | 85 | N/A | N/A
38 | Electrification Of Mbiokporo 2 In Nsit Ibom Lga, Akwa Ibom | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 19800000 |  | 15/10/2014 | YES | MENTOR ELECTRICAL INVESTMENT LIMITED | 15/10/2014 | 17868907.07 | 4 WEEKS |  |  | 6months | sub station level | 85 | N/A | N/A
39 | Electrification Of Urohi - Oke Communities In Esan West Lga, Edo State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 26042696 |  | 15/10/2014 | YES | MA'AMA NIGERIA LIMITED | 15/10/2014 | 23082888.58 | 6 WEEKS |  | 9930233.12 | 6months | sub station level | 85 | N/A | N/A
40 | Electrification Of Agi - Izekor Communities In Igueben Lga, Edo State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 21640051 |  | 15/10/2014 | YES | SOLABIG NIG. LTD. | 15/10/2014 | 19826806.17 | 4 WEEKS |  | 8163955.34 | 6months | awaiting commissioning | 100 | N/A | N/A
41 | Electrification Of Rural Communities In Esan Central Esan West And Igueben Lga (Oyomo Quarters, Okuemen, Oraede And Isibhelua Village), Edo State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 24750000 |  | 15/10/2014 | YES | OCEAN SANDS PROSPECTING NIGERIA LIMITED | 15/10/2014 | 21976918.6 | 6 WEEKS |  | 18806877.54 | 6months | awaiting commissioning | 100 | N/A | N/A
42 | Electrification Of Nkpara Ndem Village In Ikom Lga, Cross River State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 14850000 |  | 15/10/2014 | YES | SUNEX NIGERIAL LIMITED | 15/10/2014 | 13831008.03 | 4 WEEKS |  |  | 6months | yet to report to site | 0 | N/A | N/A
43 | Electrification Of Okosura Village In Ikom Lga In Cross River State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 19800000 |  | 15/10/2014 | YES | ASIA AFRICA TRADING COMPANY | 15/10/2014 | 17984195.65 | 4 WEEKS |  | 15463666.35 | 6months | sub station level | 85 | N/A | N/A
44 | Rural Electrification Of Okoroba Ext. In Ogbia Lga, Bayelsa State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 27981480 |  | 15/10/2014 | YES | ELECTROMAX ENGINEERING SERVICES LTD. | 15/10/2014 | 25274700 | 6 WEEKS |  |  | 6months | route acess in complete | 0 | N/A | N/A
45 | Rehabilitation Of Otoabagi-Oluokpokiti-Opune-Otungidi 33kv Line And Installation Of Distribution Transformers, Bayelsa State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 33135623 |  | 15/10/2014 | YES | EDDY SUCCESS GLOBAL RESOURCES LTD. | 15/10/2014 | 31989090 | 6 WEEKS |  |  | 6months | just mobilized | 0 | N/A | N/A
46 | Rural Electrification Of Elebele-Oruna-Emeya, Bayelsa State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 22976664 |  | 15/10/2014 | YES | POWER SYSTEMS ENGINEERING SERVICES LTD. | 15/10/2014 | 19635024.1 | 4 WEEKS |  | 8259843.08 | 6months | Awaiting commissioning | 100 | N/A | N/A
47 | Rural Electrification Of Igwuruta Ali Community In Rivers | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 21610761 |  | 15/10/2014 | YES | MID-RIDGE NIG. LTD. | 15/10/2014 | 16578372.4 | 4 WEEKS |  |  | 6months | sub station level | 90 | N/A | N/A
48 | Radiation Of 37km Of 33kv Line For Power Improvement In Ika North East/South Lga In Delta State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 30012087 |  | 15/10/2014 | YES | C.R. KING INTERNATIONAL LTD. | 15/10/2014 | 24151322.5 | 6 WEEKS |  |  | 6months | pole erection | 20 | N/A | N/A
49 | Construction And Rehabilitation Of Angiama-Oporoma And Oporama Hospital-Onyoma-Ekowa North-Ekianbiri-Peremabiri And Peremabiri School. 48km 33kv Line In Bayelsa State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 65774992 |  | 15/10/2014 | YES | MAIN INFRASTRUCTURE LTD. | 15/10/2014 | 54639562.34 | 10 WEEKS |  | 34330052.08 | 6months | complete | 100 | N/A | N/A
50 | Construction Of Angiamaotuan-Umbugbene-Ogbonguene-Egbe Pulugbere-Aketi-Ondewari-Korokosei-Ikeinyabiri-Olugbobiri-Kebiri-Awigbene-Osiama-Isoni-Azia-Kasama. 38km 33kvitc Line In Bayelsa State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 91203929 |  | 15/10/2014 | YES | SONSAC CONTRACTORS LTD. | 15/10/2014 | 72137440.2 | 10 WEEKS |  | 50411234.11 | 6months | complete | 100 | N/A | N/A
51 | Construction And Rehabilitation Of Agiama-Angiama-Ludonu-Agidigbene-Eniwari-Ofonibiri-Opuama-Opolobugo-Diebu-Peremabiri-Bio Aguabiri-Aguabiri-Igebiri-Obeleli-Anyama-Oweikorogha-Ikbiriamasoma. 42km 33kv Itc In Bayelsa State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 100865618 |  | 15/10/2014 | YES | HARJOKES LTD. | 15/10/2014 | 84536500 | 10 WEEKS |  | 72308610 | 6months | completed | 100 | N/A | N/A
52 | Rural Electrification Of Obulu Okiti Community, Delta State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 49500000 |  | 15/10/2014 | YES | POTI GLOBAL SERVICES LIMITED | 15/10/2014 | 44977653.07 | 6 WEEKS |  | 29602562.71 | 6months | sub station | 90 | N/A | N/A
53 | Provision And Installation Of Solar Street Light In 25 Communities In Niger State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 99000000 |  | 15/10/2014 | YES | MINDLINK INTERNATIONAL LTD. | 15/10/2014 | 71087250 | 10 WEEKS |  |  | 6months |  |  | N/A | N/A
54 | Solar Street Light At Akpuoga / Onuogba / Obinagu / Uguruoma / Nchatancha In Nike Lga, Enugu State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 29700000 |  | 15/10/2014 | YES | AUGNIS NIGERIA GRP LTD. | 15/10/2014 | 23232300 | 6 WEEKS |  |  | 6months | mobilized to site | 10 | N/A | N/A
55 | Solar Street Light At Udi Community, Enugu State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 44550000 |  | 15/10/2014 | YES | SPEC-ON GLOBAL LINKS LTD. | 15/10/2014 | 37512200 | 6 WEEKS |  |  | 6months | complete | 100 | N/A | N/A
56 | Solar Street Light At Nneke Ano And Ugwu Ogo, Enugu State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 24750000 |  | 15/10/2014 | YES | KIMEX MULTICONCEPT NIG. LTD. | 15/10/2014 | 18546912.5 | 4 WEEKS |  | 7983236.25 | 6months | complete | 100 | N/A | N/A
57 | Solar Street Light At Esut Communities In Agbani, Enugu State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 29700000 |  | 15/10/2014 | YES | TAYLO NIG. LTD. | 15/10/2014 | 24124370 | 6 WEEKS |  | 20751228 | 6months | complete | 100 | N/A | N/A
58 | Solar Street Light At Amaechi Awkunanaw In Enugu South Lga, Enugu State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 39600000 |  | 15/10/2014 | YES | TIGER ASPECT SERVICES LIMITED | 15/10/2014 | 33156110 | 6 WEEKS |  | 28543086 | 6months | complete | 100 | N/A | N/A
59 | Provision And Installation Of Solar Street Light In Oboroke, Okehi Lga, Kogi State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 14850000 |  | 15/10/2014 | YES | SIOUX ENERGIS LTD. | 15/10/2014 | 14843975.75 | 4 WEEKS |  |  | 6months | complete and in use | 100 | N/A | N/A
60 | Electrfication Of Township Distribution Network In Eniwari / Oporoma / Fonibiri / Kainyabiri / Opuama Communities, Bayelsa | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 39600000 |  | 15/10/2014 | YES | MACJONES NIG. LTD. | 15/10/2014 | 36070349.73 | 6 WEEKS |  |  | 6months | completed | 100 | N/A | N/A
61 | Solar Street Light At Akwuke/Akwuke-Uwani/Isikwe Communities, Enugu State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 14850000 |  | 15/10/2014 | YES | GABAYA NIGERIA LTD. | 15/10/2014 | 13787350 | 4 WEEKS |  |  | 6months | completed | 100 | N/A | N/A
62 | Provision Of Solar Street Light At Ishiagu In Ebonyi State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 29700000 |  | 15/10/2014 | YES | NASA GLOBAL RESOURCES SERVICES LTD. | 15/10/2014 | 23423400 | 6 WEEKS |  | 10540530 | 6months | completed | 100 | N/A | N/A
63 | Procurement And Installation Of 18nos 300 Kva Transformers At Kiru, Kano State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 42075000 |  | 15/10/2014 | YES | AWAL INVESTMENTS LTD. | 15/10/2014 | 41224128.2 | 6 WEEKS |  | 40954490.31 | 6months | completed tested and awaiting commissioning | 100 | N/A | N/A
64 | Procurement And Installation Of 15nos 300 Kva Transformers At Bebeji, Kano | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 37125000 |  | 15/10/2014 | YES | GARKADAN ENGINEERING & CONSTRUCTION CO. LIMITED | 15/10/2014 | 37123048.8 | 6 WEEKS |  | 31354497.9 | 6months | completed tested and awaiting commissioning | 100 | N/A | N/A
65 | Provision Of Solar Street Light At Ethiope And Abraka, Delta State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 49500000 |  | 15/10/2014 | YES | EPHDEINO NIGERIA LIMITED | 15/10/2014 | 48300000 | 6 WEEKS |  | 26136000 | 6months | completed | 95 | N/A | N/A
66 | Provision And Installation Of Solar Powered Street Lights In Selected Towns (Ogbomosho North/South Orire, Mbaitoti Ikeduru, Kabba Bunu, Ahoada East Odual, Obio Akpor, Ogbia, Abak Ibano, Nsukka Igboeje), Oyo State | 16/06/2014 (Daily Trust, Federal Tender Journal & Thisday) | PTB | NCB | 2014-04-08 | 2014-10-11 | 198000000 |  | 15/10/2014 | YES | DIZZAT ENGINEERING COMPANY LTD. | 15/10/2014 | 175769000 | 10 WEEKS |  | 26365350 | 6months | project completed | 100 | N/A | N/A
67 | Electrification Of West Itam Itu And Uyo Communities In Akwa Ibom North-East Senatorial District, Akwa Ibom | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 80000000 |  | 15/10/2014 | YES | FOSAB GLOBAL ENERGY SERVICES LTD. | 2014-09-12 | 66837756.2 | 10 WEEKS |  |  | 6months | yet to report to site |  | N/A | N/A
68 | Electrification Of Ikeje To Ogane Igah In Olamaboro Lga, Kogi State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 40000000 |  | 2014-09-12 | YES | OMEX CONCEPT LTD. | 2014-09-12 | 33568849 | 6 WEEKS |  |  | 6months | contractor working on site | 0 | N/A | N/A
69 | Rural Electrification From Abejikolo To Bagana In Omala Lga, Kogi State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 40000000 |  | 15/10/2014 | YES | OMOPHICO ENGINEERING WORK LTD. | 2014-09-12 | 31999036.93 | 6 WEEKS |  | 10911270.75 | 6months | stringing on progress | 68.19 | N/A | N/A
70 | Construction Of 14 Span Of Lt Line At Odoefie, Ilodu, Odosubugbawa And Ihimeren In Ikenne L. G. A. Of Ogun State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | MD/CEO | NCB | 17/09/2014 | 2014-10-11 | 2000000 |  | 2014-09-12 | YES | MULTIBIZ ADEBUNMI NIG. LTD. | 2014-09-12 | 1952427.45 | 2 WEEKS |  |  | 6months | base casting for transformer | 50 | N/A | N/A
71 | Power Improvement At Aninri/Awgu/Oji River Lgas, Enugu State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 20000000 |  | 2014-09-12 | YES | GENIC VENTURES LTD. | 2014-09-12 | 16625347.6 | 4 WEEKS |  |  | 6months | base casting for transformer | 50 | N/A | N/A
72 | Completion Of Electricity Project From Kola-Theble-Kerau-Dumna Zebru & Dumna Dutse, Adamawa State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 70000000 |  | 15/10/2014 | YES | NWESCO NIGERIA LIMITED | 2014-09-12 | 60944760.6 | 10 WEEKS |  | 14023618.83 | 6months | sub station level | 60 | N/A | N/A
73 | Extension Of Electricity Line From Silli To Dangir, Adamawa State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 30000000 |  | 2014-09-12 | YES | AFRIJANGO INTER. COMPANY LTD. | 2014-09-12 | 24787136.04 | 6 WEEKS |  |  | 6months | stringing level | 65 | N/A | N/A
74 | Rural Electrification In Bunga Town, Birnin Kebbi, Kebbi State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 30000000 |  | 15/10/2014 | YES | SABA INTEGRAYED RESOURCES LTD. | 2014-09-12 | 25284179.45 | 6 WEEKS |  | 4008286.81 | 6months | completed awaiting testing | 95 | N/A | N/A
75 | Construction Of Line From Maje, Anaba, Libale, Kampanin Jibrin, Kashin Alura And Rigolo To Be Connected From Nasko, Magam In Niger North Senatorial District, Niger State. | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 15/10/2014 | YES | DENDION LOGISTICS SERVICES LTD. | 2014-09-12 | 17453410.4015 | 4 WEEKS |  |  | 6months | contractor yet to be mobilized to site | 0 | N/A | N/A
76 | Power Improvement And Purchase Of Transformers In Otukpo Lga, Benue State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 15/10/2014 | YES | MOAT GLOBAL CONCEPT NIG. LTD. | 2014-09-12 | 16795154.4955 | 4 WEEKS |  |  | 6months | completed awaiting testing | 82.1 | N/A | N/A
77 | Provision Of 132kv Transformer Station At Gbugbu Town In Edu Lga Of Kwara State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 15/10/2014 | YES | BILISARAT NIGERIA LIMITED | 2014-09-12 | 16304928.05 | 4 WEEKS |  |  | 6months | contractor has been taken to site | 0 | N/A | N/A
78 | Electrification Of Agwa-Oguta, Umuabiahu Mgbidi, Ofeahia And Ibiasoegbe Oru West Lga, Imo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 2014-09-12 | YES | COASTLINE PROJECTS LTD. | 2014-09-12 | 16160996.81 | 4 WEEKS |  |  | 6months | yet to be moblised to site | 0 | N/A | N/A
79 | Provision Of Solar Street Light In Imo East Senatorial District, Imo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 2014-09-12 | YES | PROPERTY GUIDE INT'L LTD. | 2014-09-12 | 14232400 | 4 WEEKS |  |  | 6months | completed | 100 | N/A | N/A
80 | Provision Of Solar Powered Street Lights At Gulani Lga, Gujiba Lga, Busari Lga, Turmuwa Lga, Geidam Lga And Yunusari Lga In Yobe East Senatorial District, Yobe State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 2014-09-12 | YES | SMARCO GLOBAL INVESTMENT LIMITED | 2014-09-12 | 16295500 | 4 WEEKS |  |  | 6months | completed | 90 | N/A | N/A
81 | Etinan- Itu Rural Electrification Project, Akwa Ibom State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 15/10/2014 | YES | HIZ ENTITY LTD. | 2014-09-12 | 17449463.57 | 4 WEEKS |  |  | 6months | sub station level | 85 | N/A | N/A
82 | Electrification Of Kafaje & Borno Kici Towns In Fune Lga Of Yobe State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 2014-09-12 | YES | SAND AND SO NIGERIA LIMITED | 2014-09-12 | 17207945.91 | 4 WEEKS |  |  | 6months | yet to be moblised to site |  | N/A | N/A
83 | Provision Of 500kva Transformer In Edo North Senatorial District, Edo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 2014-09-12 | YES | ELECTRIC DISTRIBUTION AND MARKETING SERVICES LTD. | 2014-09-12 | 18979772.5 | 4 WEEKS |  |  | 6months | awaiting commissioning | 100 | N/A | N/A
84 | Supply And Installation Of 15 Units Of 500kva Transformers In Jigawa South-West Senetorial District, Jigawa State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 2014-09-12 | YES | MATERIAL MANAGERS LIMITED | 2014-09-12 | 16100922.12 | 4 WEEKS |  |  | 6months | contractor yet to be mobilized to site | 0 | N/A | N/A
85 | Supply & Installation Of 4nos. 500kva Transformer In Tofa & Rimin Gado Lgas, Kano State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 2014-09-12 | YES | MCMITCHELL NIGERIA LIMITED | 2014-09-12 | 16789518.15 | 4 WEEKS |  |  | 6months | contractor yet to be mobilized to site |  | N/A | N/A
86 | Construction Of Electricity Projects At Onwekka Community, Ikwo Lga, Ebonyi Central Senatorial District, Ebonyi State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 2014-09-12 | YES | KDD CONCEPTS & RESOURCES LTD. | 2014-09-12 | 13315541.11 | 4 WEEKS |  |  | 6months | stringing level | 75 | N/A | N/A
87 | Electrification Of Bokkos, Bokkos-Mars-Daffo In Plateau State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 2014-09-12 | YES | PARTENGOFF NIG. LTD. | 2014-09-12 | 14228060 | 4 WEEKS |  |  | 6months | contractor has been taken to site | 0 | N/A | N/A
88 | Electrification Of Umuoba Anam To Nzam In Anambra State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 28603240 |  | 2014-09-12 | YES | CARDINAL ORIENTED CONNECTIONS LIMITED | 2014-09-12 | 16230029.2925 | 4 WEEKS |  |  | 6months | mobilized to site | 10 | N/A | N/A
89 | Solar Street Light In Selected 15 Towns In Anambra State. | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 2014-09-12 | YES | XCESS STRENGHT NIG. LTD. | 2014-09-12 | 15323750 | 4 WEEKS |  |  | 6months | completed | 100 | N/A | N/A
90 | Construction Of 11kv Control Room At Kaura Namoda In Zamfara State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 2014-09-12 | YES | DTS TRANSFORMER ELECTRIC IND. LTD. | 2014-09-12 | 16488843.75 | 4 WEEKS |  |  | 6months | completed according to year 2014 | 95 | N/A | N/A
91 | Construction And Installation Of 500kva Transformer At Imagbodo Street, Off Eweka Street, Off Ihama Road, Benin City | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 6930000 |  | 2014-09-12 | YES | NAGSAM GLOBAL LINKS MAGNETS LTD. | 2014-09-12 | 6848324.18 | 4 WEEKS |  | 2947705 | 6months | completed | 100 | N/A | N/A
92 | Provision Of Street Light At Opoji, Edenu And Ugbegun In Esan Central Lga, Edo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 39600000 |  | 2014-09-12 | YES | SOLABIG NIG. LTD. | 2014-09-12 | 27145800 | 6 WEEKS |  |  | 6months | completed | 100 | N/A | N/A
93 | Provision Of Solar Street Light At Ebutte Ujiogba, Udo In Esan West Lga, Edo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 49500000 |  | 2014-09-12 | YES | BAVISCO ENERGY LIMITED | 2014-09-12 | 35952400 | 6 WEEKS |  | 16178580 | 6months | completed | 100 | N/A | N/A
94 | Electrification Of Kawo Burus, Makadi Farau/Kawo Magarya In Garko Lga, Kano State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 15/10/2014 | YES | INTER-TECH CONSULTS NIG. LTD. | 2014-09-12 | 14950230 | 4 WEEKS |  |  | 6months | contractor yet to be mobilized to site | 0 | N/A | N/A
95 | Provision / Installation Of Solar Street Light At Orlu / Orsu / Oru East Fed. Constituency, Imo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 24750000 |  | 16/3/2015 | YES | RENEWABLE SOURCE ESTATE LTD | 16/3/2015 | 17866400 | 4 WEEKS |  |  | 6months |  |  | N/A | N/A
96 | Rural Electrification Project In Gwaram Fed. Const. Jigawa State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 2014-09-10 | YES | PACIFIC SE NIGERIA LTD. | 16/3/2015 | 16249159.77 | 6 WEEKS |  |  | 6months | completed as per 2014 appropiation budget | 95 | N/A | N/A
97 | Procurement And Installation Of 2nos. 300kva 33/0.415kv Transformers Atago -Isona, Onyiangi Omodereri Layout And Ile Ajana, Ajabata Oyo East Fed. Constituency, Oyo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 9900000 |  | 2014-09-10 | YES | TOBEDDY CONCEPTS (NIG.) LTD. | 16/3/2015 | 7814869.85 | 4 WEEKS |  |  | 6months | contractor yet to be mobilized to site |  | N/A | N/A
98 | Provision Of 1n0, 200kva Transformer @Sharan Rose Nursery School (After Army Barrack) Okitipupa L.G.A. Ondo State. | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 4950000 |  | 2014-09-10 | YES | PERFECT CONCEPT ENGINEERING NIG. LTD. | 16/3/2015 | 4769160.4 | 4 WEEKS |  |  | 6months | contractor yet to be mobilized to site |  | N/A | N/A
99 | Provision Of Solar Street Light At Eniwari Towns, Southers Ijaw Lga, (Construction Of 33kv Line From Angiama Substation Through Eniwari To Opuama In S/Ijaw), Bayelsa State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 39600000 |  | 2014-09-10 | YES | MATINI ENGINEERING & CONSTRUCTION LTD. | 16/3/2015 | 27614400 | 6 WEEKS |  |  | 6months | completed | 100 | N/A | N/A
100 | Rural Electrification At Kamaru/Tsam (Chawai) Chiefdom Of Kauru Lga, Kaduna State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 2014-09-10 | YES | SHAGAYA GLOBAL SERVICES LTD. | 16/3/2015 | 15842574.75 | 4 WEEKS |  |  | 6months | completed awaiting commisionning | 100 | N/A | N/A
101 | Electrification Of 3nos Step-Down Transformer At Akoku Uno-Ukabi, Delta State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 9900000 |  | 15/10/2014 | YES | SCOOP MULTILINKS LIMITED | 16/3/2015 | 7832492.45 | 4 WEEKS |  |  | 6months | just mobilized in 2015 | 0 | N/A | N/A
102 | Installation Of 3nos 500kva Transformers At Ilesa South/East/West Atakumosa East, Osun State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 14850000 |  | 2014-09-12 | YES | EZMATOL CONSTRUCTION LTD. | 16/3/2015 | 11087749.15 | 4 WEEKS |  |  | 6months | contractor yet to be mobilized to site |  | N/A | N/A
103 | Solar Street Light At Ukpolofiedo, Awonegbe, Osomegbe, Agballa, Iyeazamah & Abumeare In Agbede All In Etsako West Lga, Edo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 2014-09-12 | YES | BLACK CONSTRUCTION LIMITED | 16/3/2015 | 15384600 | 4 WEEKS |  | 6923070 | 6months | completed | 100 | N/A | N/A
104 | Solar Street Light At Atirkyase & Mbagba, Ushongo, Benue State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 15/10/2014 | YES | BASE MARK CONSTRUCTION LTD. | 16/3/2015 | 18755584.6 | 4 WEEKS |  |  | 6months | completed | 82.6 | N/A | N/A
105 | Extension Of Electricity Supply To Ge-Mbayan To Adikpo-Mbaagwa, Benue State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 15/10/2014 | YES | OMOTOSHO & SONS NIG. LTD. | 16/3/2015 | 16613663.6 | 4 WEEKS |  |  | 6months | completed | 86.1 | N/A | N/A
106 | Provision/Installation Of 300 Kva & 500 Kva Transformers At Amuwo Odofin, Lagos State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 59400000 |  | 2014-09-12 | YES | RASIMTOH NIGERIA LIMITED | 16/3/2015 | 50203572 | 10 WEEKS |  |  | 6months | project completed tested and certified | 100 | N/A | N/A
107 | Provision Of Solar Street Light At Atakampa Urban, Cross River State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 13860000 |  | 2014-09-12 | YES | ACCENT INDUSTRIAL PROJECTS LTD. | 16/3/2015 | 13752200 | 4 WEEKS |  |  | 6months | completed | 100 | N/A | N/A
108 | 15nos. Of Solar Street Light At Fagunwa ,Ijapo Housing Estate And Oba Afunbiowo Estate , Idanre Rd. Akure South Lga Ondo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 9900000 |  | 2014-09-12 | YES | INFRAWATCH LTD | 16/3/2015 | 9798000 | 4 WEEKS |  |  | 6months | completed | 100 | N/A | N/A
109 | Provision Of Solar Street Light At Aniocha Oshimili Fed Constituency, Delta State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 49500000 |  | 2014-09-12 | YES | SHAFANA ENTERPRISES LTD. | 16/3/2015 | 39853000 | 6 WEEKS |  |  | 6months | completed | 100 | N/A | N/A
110 | Electrification Of Kurebe In Shiroro, Niger State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 2014-09-12 | YES | DUKON MULTI SERVICES LTD. | 16/3/2015 | 18488198.468 | 6 WEEKS |  |  | 6months | contractorhas been taken to site | 0 | N/A | N/A
111 | Provison Of 15nos. Of Solar Street Light At Eruwa , Lanlate In Ibarapa East Lga @ Ido Lga , Oyo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 9900000 |  | 2014-09-12 | YES | FATLAN INTER-BIZ NIGERIA LIMITED | 16/3/2015 | 9798000 | 4 WEEKS |  |  | 6months | contractor yet to be mobilized to site |  | N/A | N/A
112 | Provision Of Solar Street Light At Ilorin East/Ilorin South, Kwara State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | MD/CEO | NCB | 17/09/2014 | 2014-10-11 | 4950000 |  | 2014-09-12 | YES | ARCHIVISUAL SOLUTIONS LTD. | 16/3/2015 | 4802325.25 | 2 WEEKS |  |  | 6months | completed | 86.8 | N/A | N/A
113 | Provision & Installation Of Solar Street Light At Isoko North/South Federal Constituency, Delta State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 49500000 |  | 15/10/2014 | YES | MUDKA ENGINEERING WORKS LIMITED | 16/3/2015 | 36553000 | 2 WEEKS |  | 16448850 | 6months | awaiting commissioning | 100 | N/A | N/A
114 | Electrification Of Tahoss- Tigi, Barkin Ladi/ Riyom In Plateau State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 2014-09-12 | YES | FACCO IND. LTD. | 16/3/2015 | 16967790 | 4 WEEKS |  |  | 6months | contractor on site | 0 | N/A | N/A
115 | Procurement And Installation Of Transformers In Jankasa / Unguwar Rimi, Madamai, Adu / Ashin & Kajim / Randiam Towns, Kaduna State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 2014-09-12 | YES | FOXTROT O & G COMPANY NIGERIA LTD. | 16/3/2015 | 16410143 | 4 WEEKS |  |  | 6months | contractor mobilized to site | 10 | N/A | N/A
116 | Procurement And Installation Of 1nos. 300kva 33/0.415kv Transformer Alubata & Ologuneru In Ido Lga Oyo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | MD/CEO | NCB | 17/09/2014 | 2014-10-11 | 4950000 |  | 2014-09-12 | YES | KANNYKOY UNIQUE MULTI PURPOSE LTD. | 16/3/2015 | 4538778.6 | 2 WEEKS |  |  | 6months | completed as per 2014 appropiation budget | 100 | N/A | N/A
117 | Construction of 5nos. 300kva Relief Sub-Stations At Ilorin East/Ilorin South, Kwara State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 9900000 |  | 2014-09-12 | YES | SWASH INTEGRATED PROJECTS LTD. | 16/3/2015 | 8608641.46 | 4 WEEKS |  |  | 6months | completed as per 2014 appropiation budget | 97.1 | N/A | N/A
118 | Procurement & Installation Of 500kva Transformers At Aborerin, Sango & New Eruwa In Ibarapa East, Lga, Oyo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | MD/CEO | NCB | 17/09/2014 | 2014-10-11 | 4950000 |  | 2014-09-12 | YES | CARSUL LIMITED | 16/3/2015 | 4479483.45 | 2 WEEKS |  |  | 6months | completed as per 2014 | 100 | N/A | N/A
119 | Procurement And Installation Of 300kva Transformers At Nsadop (Boki), State Housing Ikom, Cross River State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 14850000 |  | 2014-09-12 | YES | BISOK INTEGRATED LIMITED | 16/3/2015 | 11975084.55 | 4 WEEKS |  | 5254506 | 6months | completed | 100 | N/A | N/A
120 | Installation Of 5 Nos 300/500kva Transformers At Bende Lga, Abia State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 2014-09-12 | YES | OKIYI INVESTMENTS NIG. LTD. | 16/3/2015 | 18154014.66 | 4 WEEKS |  | 7709811.69 | 6months | awaiting commissioning | 95 | N/A | N/A
121 | Procurement/Installation Of 3nos.500kva Transformers At Ojo Federal Constituency, Lagos State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 2014-09-12 | YES | JANEL INTERNATIONAL NIG. LTD. | 16/3/2015 | 19076748.55 | 4 WEEKS |  |  | 6months | completed as per 2014 budget | 100 | N/A | N/A
122 | Electrification Of Kawo In Rafi Lga, Niger State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 2014-09-12 | YES | KILOMAKER LTD. | 16/3/2015 | 17476109.64 | 4 WEEKS |  |  | 6months | contractor yet to be mobilized | 0 | N/A | N/A
123 | Procurment & Installation Of 3nos 300kva Transformers At Ozoro, Isoko Lga, Delta State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 9900000 |  | 15/10/2014 | YES | COX.A INTEGRATED LIMITED | 16/3/2015 | 8223944.63 | 4 WEEKS |  |  | 6months | completed | 100 | N/A | N/A
124 | Electrification Of Loko Community, Nasarawa State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 2014-09-12 | YES | UNI CHRIS NIG. LTD. | 16/3/2015 | 16282661.85 | 4 WEEKS |  | 7008621.52 | 6months | completed | 86.1 | N/A | N/A
125 | Supply Of 7.5mva 33/11kv Transformer To Ubth Benin, Edo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 39600000 |  | 15/10/2014 | YES | PHILAB GEN. MERCHANT LIMITED | 16/3/2015 | 34258425.25 | 4 WEEKS |  | 30832582.73 | 6months | awaiting testing | 100 | N/A | N/A
126 | Procurement And Installation Of 3nos 300kva, 33/0.415kv Transformers At Orhuwhorun/Owhrode In Udu Lga, Delta State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 9900000 |  | 15/10/2014 | YES | SCOOP ELECTRIC LIMITED | 16/3/2015 | 8105298.9 | 4 WEEKS |  |  | 6months | just mobilized | 0 | N/A | N/A
127 | Procurement/Installation Of 7nos 300kva Transformers At Eguare Udo, Egbesan, Idumeka, Idumogo, Egbiki,Afuda, Idumotalor, Idumotutu, Union Bank Rd, Igueben, Lga, Edo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 39600000 |  | 2014-09-12 | YES | OPEN DOOR SYSTEMS INTERNATIONAL LTD. | 16/3/2015 | 32719708.58 | 6 WEEKS |  | 14721382.54 | 6months | awaiting test | 100 | N/A | N/A
128 | Completion Of Ndukwe Rural Electrification At Afikpo North Lga, Ebonyi State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 2014-09-12 | YES | SAAC VENTURES LIMITED | 16/3/2015 | 19293538.96 | 4 WEEKS |  |  | 6months | awaiting commissioning | 95 | N/A | N/A
129 | Procurement & Installation Of 4nos 300/500kva Transformers At Obingwa / Osisioma / Ugwunagbe Federal Constituency, Abia State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 2014-09-12 | YES | PUNNOCC NIGERIA LTD. | 16/3/2015 | 14597835.16 | 4 WEEKS |  |  | 6months | substation level | 85 | N/A | N/A
130 | Rural Electrification At Gidan Madi And Tungar Tsaoro In Tangaza Lga Of Sokoto State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 15/10/2014 | YES | SENATORCH LTD. | 16/3/2015 | 15922560.98 | 4 WEEKS |  |  | 6months | contracting yet to be mobilized | 0 | N/A | N/A
131 | Construction Of Injection Substation At Ewu, Edo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 2014-09-12 | YES | UTSOTA ENERGY LTD. | 16/3/2015 | 19403272.65 | 4 WEEKS |  |  | 6months | just mobilized | 0 | N/A | N/A
132 | Electrification Of Muye Town, Lapai Lga In Niger State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 9900000 |  | 15/10/2014 | YES | HENOCHIM INVESTMENTS LTD. | 16/3/2015 | 7850550.9 | 4 WEEKS |  |  | 6months | sub station in progress | 67.2 | N/A | N/A
133 | Electrification Of Uzea Community Emu To Orowa And Ewoiki To Ebun Village Uromi, Edo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 39600000 |  | 2014-09-12 | YES | GALAZY CONCRETE WORKS LTD. | 16/3/2015 | 31413690.95 | 6 WEEKS |  |  | 6months | pole erection completed | 40 | N/A | N/A
134 | Procurement/Installation Of 3 Nos 300kva Transformers To Replace Faulty Ones In Edenu,Agua, Idunwele, Ikhilor, Ikekato, Idumadi, Eko-Iyiobhebhe Procurement & Installation Of 10nos 300kva Transformers To Replace Faulty Ones In Edenu, Agua, Idunwele, Ikhilor, Ikekato, Idumabi, Eko-Iyiobhebhe, Ikinago-Opoji, Ikiewanlen, Opoji Esan Central Lga, Edo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 49500000 |  | 2014-09-12 | YES | LENDE VENTURES LIMITED | 16/3/2015 | 42598619 | 6 WEEKS |  |  | 6months | stringing and substation | 75 | N/A | N/A
135 | Procurement & Installation Of 5ookva/33/.415kv @ Phase II, Behind Redeem Church, Kogi State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 7920000 |  | 2014-09-12 | YES | MOSBA-PJ GLOBAL LIMITED | 16/3/2015 | 5335106 | 6 WEEKS |  |  | 6months | completed awaiting testing | 82.9 | N/A | N/A
136 | Provision Of Solar Street Light Across Port Harcourt Federal Constituency II, Rivers State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 25700000 |  | 15/10/2014 | YES | MONNEX GLOBAL RESOURCES LIMITED | 16/3/2015 | 18018000 | 6 WEEKS |  | 8108100 | 6months | completed | 100 | N/A | N/A
137 | Construction Of 22 Span Of Lt Line At Jalugun Area In Inisha, Odo-Otin L. G. A. Osun State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | MD/CEO | NCB | 17/09/2014 | 2014-10-11 | 2970000 |  | 15/10/2014 | YES | AIMS 4MAHAQ INTERBIZ LTD. | 16/3/2015 | 2913521.55 | 2 WEEKS |  |  | 6months | contractor yet to be mobilized to site |  | N/A | N/A
138 | Procurement & Installation Of 5nos 300kva Transformers At Kayama & Odi In Kolokuma Lga Of Bayelsa State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 14850000 |  | 2014-09-12 | YES | OLKON INTERNATIONAL LTD. | 16/3/2015 | 12068753.11 | 4 WEEKS |  |  | 6months | sub station in progress | 90 | N/A | N/A
139 | Provision & Installation Of 3nos 300kva Transformers In Ohagi/Egbema-Oguta-Oru West, Imo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 9900000 |  | 2014-09-12 | YES | FROBEN CONSTRUCTION SERV. LTD. | 16/3/2015 | 9849024.35 | 4 WEEKS |  |  | 6months | substation level | 85 | N/A | N/A
140 | Provision Of Solar Street Light At Olugbobiri, Oporoma Town, Southern Ijaw Lga, Bayelsa State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 2014-09-12 | YES | BREM INTERNATIONAL LTD. | 16/3/2015 | 15708000 | 4 WEEKS |  |  | 6months | just mobilized | 10 | N/A | N/A
141 | Procurement & Installation Of 5 Nos 300kva Transformers At Minjibiri/Ungogo Federal Constituency, Kano State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 14850000 |  | 2014-09-12 | YES | AISHRUK GLOBAL INVESTMENT LTD. | 16/3/2015 | 11451113.937 | 4 WEEKS |  |  | 6months | contractor yet to be mobilized to site | 0 | N/A | N/A
142 | Provision Of Transformers/Material & Grid Extension At Udi/Ezeagu Fed. Constituency, Enugu State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 9900000 |  | 2014-09-12 | YES | SILVERBRUSH CONSULTS LTD. | 16/3/2015 | 9629259.21 | 4 WEEKS |  |  | 6months | contractor yet to be mobilized to site | 0 | N/A | N/A
143 | Electrification Of Nyivu Village In Donga Lga, Taraba State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 15/10/2014 | YES | ARGENTUM SUPREMO VENTURE NIGERIA LTD. | 16/3/2015 | 19206921.19 | 4 WEEKS |  |  | 6months | completed awaiting test | 90 | N/A | N/A
144 | Solar Street Light At Nkwerre/Isu/Nwangele Njaba Federal Const. Imo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 9900000 |  | 2014-09-12 | YES | MACEN J LIMITED | 16/3/2015 | 9388600 | 4 WEEKS |  |  | 6months | completed awaiting test | 100 | N/A | N/A
145 | Rural Electrification In Tokulo - Kaima Village, Bwari Lga, Fct | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 9900000 |  | 15/10/2014 | YES | STRAIGHT STREET INTERNATIONAL LIMITED | 16/3/2015 | 8095589.52 | 4 WEEKS |  |  | 6months | ongong | 40 | N/A | N/A
146 | Rural Electrification In Piko-Galuwyi-Kute Villages, Bwari, Fct | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 14850000 |  | 15/10/2014 | YES | LATSUL ENGR. LTD. | 16/3/2015 | 14092365.4315 | 4 WEEKS |  |  | 6months | completed | 68.1 | N/A | N/A
147 | Provision Of 3nos 300kva Transformers At St Maria Ave. Off Power Line Boji Owa,Prof. Ebie Strt.,Agbor. Idumu-Obior Qtr Igbodo And Ewuru Agbor, Delta State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 9900000 |  | 15/10/2014 | YES | KENDEIBERT RESOURCE NIG. LTD. | 16/3/2015 | 7813400.15 | 4 WEEKS |  |  | 6months | yet to report |  | N/A | N/A
148 | Provision & Installation Of Transformers In Edati Town & Mokwa Town, Niger State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 14850000 |  | 15/10/2014 | YES | SLEDGE CONSULTING LIMITED | 16/3/2015 | 10817704.8 | 4 WEEKS |  |  | 6months | completed and energized | 99.9 | N/A | N/A
149 | Solar Street Light At For Mbaya Buruku Fed. Constituency, Benue State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 2014-09-12 | YES | LIKEPOLES CONSULT ENGINEERING SERVICES LTD. | 16/3/2015 | 15614700 | 4 WEEKS |  |  | 6months | contractor on site | 0 | N/A | N/A
150 | Provision Of 5nos 300kva Transformers At Ogbomoso North South & Orire Federal Constituency, Oyo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 15/10/2014 | YES | EL NASSER VENTURES LTD. | 16/3/2015 | 15318632.5 | 4 WEEKS |  |  | 6months | completed as per2014 bdget | 60 | N/A | N/A
151 | Rural Electrification In Orire Lga, Oyo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 9900000 |  | 15/10/2014 | YES | BOAS DESTINY INT. LTD. | 16/3/2015 | 9861170.08 | 4 WEEKS |  |  | 6months |  |  | N/A | N/A
152 | Procurement And Installation Of 3nos. 500kva 11/0.415kv Transformers For Irepodun & Co. Fed. Constituency, Osun State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 16830000 |  | 15/10/2014 | YES | JAJI M. M. NIG. LTD. | 16/3/2015 | 14774087.95 | 4 WEEKS |  |  | 6months | contractor yet to be mobilized to site |  | N/A | N/A
153 | Provision Of 5nos 200kva Transformers At Ekoi, Ikot, Nyoho, Ibam, Ukot In Ini Lga, Akwa Ibom State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 9900000 |  | 15/10/2014 | YES | BRIGANTE LTD. | 16/3/2015 | 8257204.7 | 4 WEEKS |  |  | 6months | completed | 100 | N/A | N/A
154 | Rural Electrification Of Ogugu Community In Olamaboro Lga, Kogi State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 15/10/2014 | YES | BIYAYA NIGERIA LTD. | 16/3/2015 | 17666342.55 | 4 WEEKS |  |  | 6months | stringing completed | 61.8 | N/A | N/A
155 | Electrification of Angwan Adamu, Rugan Fulani, Angwan Amos /Azunu And Ado Extension By Kugbaru Rd Ado Karu Lga Of Nasarawa State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 9900000 |  | 15/10/2014 | YES | SCHOTTEK ENG. CO. NIG. LTD. | 16/3/2015 | 9862534.55 | 4 WEEKS |  |  | 6months | completed and energized | 85.6 | N/A | N/A
156 | Installation of Transformers inNkaramoche Iramogu, Iheagwu, Owerri West Lga And Naze, Umuakau In Owerri North Lga, Imo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 15/10/2014 | YES | MICH, HI-TECH NIG. LTD. | 16/3/2015 | 15097896.21 | 4 WEEKS |  |  | 6months | awaiting commissioning | 95 | N/A | N/A
157 | Electrification Of Ogbe-Orji Community, Illa, Delta State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 14850000 |  | 15/10/2014 | YES | ENFIN ELECTRIQUE LTD. | 16/3/2015 | 11964051.45 | 4 WEEKS |  |  | 6months | awaiting commissioning | 95 | N/A | N/A
158 | Electrification And Installation Of Transformers In Azuisha Ndubia-Igbagu, Okpokoroko Ndubia-Igbagu, Azufia Ndubia, Igbagu In Izzi, Ebonyi State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 9900000 |  | 2014-09-12 | YES | FABIYKE INTERGRATED SERVICES LTD. | 16/3/2015 | 9468821.32 | 4 WEEKS |  |  | 6months | completed as per 2014 budget | 100 | N/A | N/A
159 | Provision Of 10nos Solar Street Light At Umuanyaku Ikperejere In Ihite Ugboma Lga, Imo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 9900000 |  | 2014-09-12 | YES | ENJAIZ TECHNOLOGY NIG. LTD | 16/3/2015 | 9837100 | 4 WEEKS |  |  | 6months | completed | 100 | N/A | N/A
160 | Electrification Of Ukpologwu, Oshimili North Lga Of Delta State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 14850000 |  | 2014-09-12 | YES | BORIKAN TECHNICAL SERVICES LTD | 16/3/2015 | 11066231.94 | 4 WEEKS |  |  | 6months | completed | 100 | N/A | N/A
161 | Installation Of Transformers At Omuoda Aluu New Layout Port Harcourt, Rivers State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 9900000 |  | 2014-09-12 | YES | DURUKE LTD | 16/3/2015 | 8124898.925 | 4 WEEKS |  |  | 6months | yet to report | 0 | N/A | N/A
162 | Provision Of Solar Street Light At Udi Kolokuma/Opokuma Lga, Bayelsa State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 9900000 |  | 2014-09-12 | YES | TARIOK NIG. LTD | 16/3/2015 | 8265400 | 4 WEEKS |  |  | 6months | completed | 100 | N/A | N/A
163 | Solar/Rural Electrification At Eruere, Avibiosi-Okpohumi Road, Avibiosi Town In Owan West Lga, Edo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 2014-09-12 | YES | PYRICH ENGINEERING LTD. | 16/3/2015 | 15384600 | 4 WEEKS |  |  | 6months | completed | 100 | N/A | N/A
164 | Provision Of Solar Street Light At Emonyoku - Achaja Olamaboro Lga, Kogi State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 14850000 |  | 15/10/2014 | YES | TENAB INTERNATIONAL LTD. | 16/3/2015 | 11962150.5 | 4 WEEKS |  |  | 6months | contractor yet to report to zone | 0 | N/A | N/A
165 | Procurement And Installation Of 5nos 500kva At Efekpe Imane Olamaboro Lga, Kogi State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 24750000 |  | 15/10/2014 | YES | NEW MOON NIGERIA LTD. | 16/3/2015 | 24412059.976 | 6 WEEKS |  |  | 6months | completed awaiting testing | 86.1 | N/A | N/A
166 | Provision Of Solar Street Light At Gwanda Village In Kurmi Lga, Taraba State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 9900000 |  | 15/10/2014 | YES | GENEROSITY VENTURE LTD. | 16/3/2015 | 8461700 | 4 WEEKS |  | 3642210 | 6months | completed in service | 100 | N/A | N/A
167 | Rural Electrification Of Tyekv - Apeinumv Yandev Gboko, Benue State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 19800000 |  | 15/10/2014 | YES | MAN -JONNIE RESOURCES NIG. LTD. | 16/3/2015 | 17617710.2 | 4 WEEKS |  | 7583275.26 | 6months | completed | 86.1 | N/A | N/A
168 | Electrification Of Alifeti- Oba, Iga- Ologbeche L.G.A In Benue State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 25000000 |  | 2014-09-12 | YES | CC-WEST GLOBAL SERVICES LTD. | 16/3/2015 | 21082722.3 | 6 WEEKS |  |  | 6months | completed | 86.1 | N/A | N/A
169 | Electrification Of Ojagbama Adoka, Otukpo L.G.A In Benue State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 25000000 |  | 15/10/2014 | YES | BENGIN & ASSOCIATES LIMITED | 16/3/2015 | 21548557.4 | 6 WEEKS |  | 18550497.24 | 6months | completed | 95.6 | N/A | N/A
170 | Supply Of 10no. 500kva Transformers For Rural Electrification In Benue North West Senatorial District, Benue State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 50000000 |  | 15/10/2014 | YES | DIZZAT ENGINEERING COMPANY LTD. | 16/3/2015 | 40186566 | 6 WEEKS |  |  | 6months | sub station in progress | 46.1 | N/A | N/A
171 | Electrification of Agbolo/Gbayi/Kuji/Shape/Tumtum/Wana Small Towns Electrification Projects In Niger East Senatorial District, Niger State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 80000000 |  | 15/10/2014 | YES | DORNY SERVICES NIG. LTD. | 16/3/2015 | 66581156.4125 | 10 WEEKS |  | 21253493.94 | 6months | stringing inprogress | 55.7 | N/A | N/A
172 | Power Supply And Installation Of 300kva 33/0.415kv Trans. In Majinga Town In Magama Lga In Niger North Senatorial District | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 7057378 |  | 15/10/2014 | YES | ANTRACOM LIMITED | 16/3/2015 | 6865664.68 | 4 WEEKS |  |  | 6months | sub station in progress | 56.3 | N/A | N/A
173 | Power Supply And Installation Of 300kva 33/0.415kv Trans. In Libele Town In Magama Lga In Niger North Senatorial District | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 11865108 |  | 2014-09-12 | YES | DUMACO BEST PROPERTIES LTD. | 16/3/2015 | 9218020.49 | 4 WEEKS |  |  | 6months | contractor yet to report to zone | 0 | N/A | N/A
174 | Power Supply And Installation Of 300kva 33/0.415kv Trans. In Nasko Town In Magama Lga In Niger North Senatorial District. | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 8383000 |  | 2014-09-12 | YES | LEAD RESOURCES LTD. | 16/3/2015 | 8109804.6 | 4 WEEKS |  |  | 6months | completed awaiting testing | 86.1 | N/A | N/A
175 | Power Supply And Installation Of 300kva 33/0.415kv Trans. In Gwagwade Town In Magama Lga In Niger North Senatorial District, Niger State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 12035860 |  | 15/10/2014 | YES | THINK HOME NIG. LTD. | 16/3/2015 | 10618525 | 4 WEEKS |  |  | 6months | completed awaiting testing | 86.1 | N/A | N/A
176 | Power Supply And Installation Of 300kva 33/0.415kv Transformer In Rijau Magajiya Town In Magama Lga In Niger North Senatorial District | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 13800000 |  | 2014-09-12 | YES | BEACON CREATIVE IDEAS LTD. | 16/3/2015 | 10400021.09 | 4 WEEKS |  |  | 6months | contractor yet to be taken to site | 0 | N/A | N/A
177 | Construction Of Rural Electrification To Emifari Via Kusogi, Katcha Lga, Niger State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 20000000 |  | 2014-09-12 | YES | SULE SAGMACK NIG. LTD. | 16/3/2015 | 15423560.65 | 4 WEEKS |  | 2313534.1 | 6months | stringing in progess | 44.6 | N/A | N/A
178 | Electrification In Nasarawa Eggon To Arikya In Nasarawa North Senatorial District, Nasarawa State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 45000000 |  | 15/10/2014 | YES | EPHDEINO NIG. LTD. | 16/3/2015 | 32886996.66 | 6 WEEKS |  |  | 6months | contractor has been to site | 0 | N/A | N/A
179 | Supply And Installation Of 5 Units Of 500kva Transformers At Kabba-Bunu/Ijumu, Kogi State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 20000000 |  | 15/10/2014 | YES | AABOWA & COMPANY NIG. LTD. | 16/3/2015 | 19527075.762 | 6 WEEKS |  |  | 6months | contractor has been to site | 0 | N/A | N/A
180 | Installation Of 500kva And 2nos 300kva Transformer At Arochukwu/Ohafia, Abia State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 10000000 |  | 2014-09-12 | YES | PULSAR TECHNOLOGY CONSTRUCTIONS & BUILDERS NIG. LTD. | 16/3/2015 | 7707983.1 | 4 WEEKS |  | 6546532.41 | 6months | completed | 100 | N/A | N/A
181 | Rural Electrification Project At Ohoazara / Onicha / Ivo Communities, Ebonyi State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 20000000 |  | 2014-09-12 | YES | CARLIN CONCEPT INTER. LTD. | 16/3/2015 | 15390362.03 | 4 WEEKS |  | 11052627.3 | 6months | completed | 100 | N/A | N/A
182 | Procurement Of 8nos 300kva Transformers In Ehime-Mbano, Ihitte, Uboma/Obowo Federal Constituency, Imo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 15000000 |  | 30/3/2015 | YES | DISMAS INTEGRATED SERVICE LTD | 30/3/2015 | 13176884 | 4 WEEKS |  |  | 6months |  |  | N/A | N/A
183 | Procurement Of 12nos 300kva Transformers In Mbaitoli And Ikeduru Lgas, Imo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 30000000 |  | 2014-09-10 | YES | FINKOLIS INTERNATIONAL CO. LTD. | 30/3/2015 | 23585998 | 6 WEEKS |  |  | 6months | awaiting commissioning | 95 | N/A | N/A
184 | Rural Electrification At Kayeri-Kafaje And Kafaje Town In Yobe South Senatorial District, Yobe State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 68535628 |  | 2014-09-10 | YES | BABADIDI TRESURES LTD. | 30/3/2015 | 63399178 | 10 WEEKS |  | 54038827.8 | 6months | completed | 90 | N/A | N/A
185 | Rural Electrification At Borno Kichi Town In Yobe South Senatorial District | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 51464372 |  | 2014-09-10 | YES | J. BERACHAH GLOBAL LTD. | 30/3/2015 | 42245620.3 | 6 WEEKS |  | 21718594.8 | 6months | stringing level | 60 | N/A | N/A
186 | Supply Of Aluminium Conductor & Installation Tools, Kirfi Lga, Bauchi State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 10000000 |  | 2014-09-10 | YES | ADMASOL IN-DEPTH TECHNOLOGIES LTD. | 30/3/2015 | 7907065.695 | 4 WEEKS |  |  | 6months | yet to mobilize | 0 | N/A | N/A
187 | Procurement And Installation Of Transformers At Bayo /Biu / Kwaya Kusar / Shani Federal Constituency Of Borno State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 20000000 |  | 15/10/2014 | YES | MOPPAN NIG. LTD. | 30/3/2015 | 19928490.07 | 4 WEEKS |  |  | 6months | s/s and material supplied | 70 | N/A | N/A
188 | Supply & Installation 500kva Transformer And Connection To National Grid At Odeda Lga , Ogun Central Senatorial District, Ogun State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | MD/CEO | NCB | 17/09/2014 | 2014-10-11 | 7500000 |  | 15/10/2014 | YES | OBOCH GLOBAL RESOURCES LIMITED | 30/3/2015 | 4962595 | 2 WEEKS |  |  | 6months | completed as per 2014 appropiation budget | 100 | N/A | N/A
189 | Supply And Installation Of 500kva Transformer And Connection To National Grid At Ifo Lga, Ogun Central Senatorial District, Ogun State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | MD/CEO | NCB | 17/09/2014 | 2014-10-11 | 7500000 |  | 15/10/2014 | YES | TRANSEZ NIG. LTD. | 30/3/2015 | 4962595 | 2 WEEKS |  |  | 6months | completed as per 2014 appropiation budget | 100 | N/A | N/A
190 | Supply & Installation 500kva Transformer & Connection To National Grid Ewekoro Lga, Ogun Central Senatorial District, Ogun State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 7500000 |  | 15/10/2014 | YES | MELDAT INT. INVESTMENT LTD. | 30/3/2015 | 7431346 | 4 WEEKS |  |  | 6months | completed as per 2014 appropiation budget | 100 | N/A | N/A
191 | Supply And Installation 500kva Transformer And Connection To National Grid In Abeokuta South Lga, Ogun Central Senatorial District, Ogun State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 7500000 |  | 15/10/2014 | YES | KLYDE RESOURCES LTD. | 30/3/2015 | 6143035.5 | 4 WEEKS |  |  | 6months | completed as per 2014 appropiation budget | 100 | N/A | N/A
192 | Supply & Installation 500kva Transformer And Connection To National Grid In Obafemi Owode Lga Ogun Central Senatorial District, Ogun State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 7500000 |  | 15/10/2014 | YES | ABIGA INTEGRATED CONCEPT LTD. | 30/3/2015 | 6133571 | 4 WEEKS |  |  | 6months | completed as per 2014 appropiation budget | 100 | N/A | N/A
193 | 2 N0s. 300kva Transformers In Ifo And Ewekoro Federal Constituency, Ogun State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 10000000 |  | 15/10/2014 | YES | ULTIMO SUSTANTIVO NIG. LTD. | 30/3/2015 | 7808168.8 | 4 WEEKS |  |  | 6months | contractor yet to mobilize | 0 | N/A | N/A
194 | Provision Of Solar Street Light Across Lagos Island Federal Constituency 1, Lagos State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 13000000 |  | 2014-09-10 | YES | BRINAX GLOBAL SERVICES LTD. | 30/3/2015 | 10979625 | 4 WEEKS |  | 9452025 | 6months | completed as per 2014 appropiation budget | 100 | N/A | N/A
195 | Power Improvement At Arolu, Surulere Lga, Oyo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 26234500 |  | 15/10/2014 | YES | TOPFAT GLOBAL LINKS LTD. | 30/3/2015 | 20416134.58 | 6 WEEKS |  |  | 6months | completed as per 2014 appropiation budget | 60 | N/A | N/A
196 | Power Improvement At Igbo-Ile Via Ogbomosho, Surulere Lga, Oyo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 10501000 |  | 2014-09-12 | YES | GALA VENTURES (NIG) LTD. | 30/3/2015 | 8360081.4 | 4 WEEKS |  | 7424052.39 | 6months | completed as per 2014 appropiation budget | 100 | N/A | N/A
197 | Supply Of 6nos 500kva Transformers To Egbeda/Ona-Ara Lgas, Oyo State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 36000000 |  | 15/10/2014 | YES | BINTAYAH GLOBAL RESOURCES SERVICES LTD. | 30/3/2015 | 29624293.25 | 6 WEEKS |  | 26598107.93 | 6months | completed as per 2014 appropiation budget | 60 | N/A | N/A
198 | Procurement Of Lines/Cables And Transformers At Dan-Musa L.G.A, Katsina State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 25000000 |  | 2014-09-12 | YES | MARCO-KINGS ENGINEERING NIG. LTD. | 30/3/2015 | 20095155.2 | 6 WEEKS |  |  | 6months | contractor mobilized to site | 0 | N/A | N/A
199 | Procurement Of Lines And Transformers At Lambar Rimi-Bisau-Bora In Batagrawa Lga, Katsina State | 14/07/2014 (Daily Trust, Daily Sun & Federal Tender Journal) | PTB | NCB | 17/09/2014 | 2014-10-11 | 30000000 |  | 2014-09-12 | YES | YARMTY NIG. LTD. | 30/3/2015 | 24473682.45 | 6 WEEKS |  |  | 6months | contractor mobilized to site | 0 | N/A | N/A
200 | Construction Of 33kva Line At Market -Buturkai Makera Ward In Katsina State | 22/09/2014 (Daily Trust & Federal Tender Journal) | MD/CEO | NCB | 2014-12-11 | 2014-10-11 | 4950000 |  | 2014-12-12 | YES | U.U. POWER MULTI CONCEPTS RESOURCES LTD. | 2014-12-12 | 3828246.56 | 2 WEEKS |  |  | 6months | contractor mobilized to site | 0 | N/A | N/A
201 | Electrification Sabon Gida-Danbushiya-Danhonu, Kaduna State | 22/09/2014 (Daily Trust & Federal Tender Journal) | PTB | NCB | 2014-12-11 | 2014-10-11 | 49500000 |  | 2014-12-12 | YES | KINPATINO PROJECTS LTD. | 2014-12-12 | 45445868.54 | 6 WEEKS |  |  | 6months | mobilized to site |  | N/A | N/A
202 | Completion Of Ongoing Lga Sub-Stations Reinforcement At Idemili South, Idemili North, Njikoka, Awka South, Awka North, Dunukoffia And Anaocha In Anambra State | 22/09/2014 (Daily Trust & Federal Tender Journal) | PTB | NCB | 2014-12-11 | 2014-10-11 | 128700000 |  | 2014-12-12 | YES | I.U.K. INTERNATIONAL CO. LTD. | 2014-12-12 | 107060544.65 | 10 WEEKS |  |  | 6months | substation level | 85 | N/A | N/A
203 | Construction And Installation Of Solar Powered Street Light In Anambra South Senatorial District, Anambra State | 22/09/2014 (Daily Trust & Federal Tender Journal) | PTB | NCB | 2014-12-11 | 2014-10-11 | 19800000 |  | 2014-12-12 | YES | SONSAC CONTRACTORS LTD. | 2014-12-12 | 16002480 | 4 WEEKS |  | 13776048 | 6months | completed | 100 | N/A | N/A
204 | Rural Electrification Of Ogboza Amanator Autonomous Community In Imo State | 22/09/2014 (Daily Trust & Federal Tender Journal) | PTB | NCB | 2014-12-11 | 2014-10-11 | 23409429 |  | 2014-12-12 | YES | A.C. CHARLES INT'L CO. LTD. | 2014-12-12 | 22597833.5 | 6 WEEKS |  |  | 6months | line rehabilitation in progress | 80 | N/A | N/A
205 | Installation Of Transformers At Agwa Amuda To Ezi Ogwu In Amachi, Afikpo North Lga, Ebonyi State | 22/09/2014 (Daily Trust & Federal Tender Journal) | PTB | NCB | 2014-12-11 | 2014-10-11 | 9900000 |  | 2014-12-12 | YES | C.L. INFRA INTERNATIONAL LTD. | 2014-12-12 | 7404611.83 | 4 WEEKS |  |  | 6months | route surveying | 20 | N/A | N/A
206 | Power Rehabilitation and Upgrading of 220KVA Transformers at Umuezeala Nsu in Ehime Mbano, Isiala LGA, Imo State | 22/09/2014 (Daily Trust & Federal Tender Journal) | PTB | NCB | 2014-12-11 | 2014-10-11 | 99000000 |  | 2014-12-12 | YES | BRENT INVESTMENT LTD. | 2014-12-12 | 87121700.98 | 10 WEEKS |  | 2000000 | 6months | awaiting commissioning | 95 | N/A | N/A
207 | Purchase & Installation Of 500kva/300kva Transformer At Isoko /South Federal Constituency, Delta State | 22/09/2014 (Daily Trust & Federal Tender Journal) | PTB | NCB | 2014-12-11 | 2014-10-11 | 49500000 |  | 2014-12-12 | YES | COMDAVIS ELECTRICAL ENTER. LTD. | 2014-12-12 | 45125161.65 | 6 WEEKS |  |  | 6months | just mobilized |  | N/A | N/A
208 | Construction Of Solar Street Light At Uruepken, Ujoelen, Udumebo & Illeh At Essan West Lga In Edo State | 22/09/2014 (Daily Trust & Federal Tender Journal) | PTB | NCB | 2014-12-11 | 2014-10-11 | 29700000 |  | 2014-12-12 | YES | UPDATE LIMITED | 2014-12-12 | 21044100 | 6 WEEKS |  |  | 6months | completed | 100 | N/A | N/A
209 | Electrification of Atugbe to Okoromi, Edo State | 22/09/2014 (Daily Trust & Federal Tender Journal) | PTB | NCB | 2014-12-11 | 2014-10-11 | 9900000 |  | 2014-12-12 | YES | DAMSAL (NIG.) LIMITED | 2014-12-12 | 7694004.85 | 4 WEEKS |  |  | 6months | yet to report to site | 0 | N/A | N/A
210 | Completion Of Solar Street Light At Okhafunovor/ Sabo Qtrs & Others In Imiegba Town, Etsako Isa, Edo State | 22/09/2014 (Daily Trust & Federal Tender Journal) | PTB | NCB | 2014-12-11 | 2014-10-11 | 19800000 |  | 2014-12-12 | YES | JULZ VENTURES (NIG.) LTD. | 2014-12-12 | 13602600 | 4 WEEKS |  |  | 6months | completed | 100 | N/A | N/A
211 | Electrification Of Onigbogi, Osun State | 22/09/2014 (Daily Trust & Federal Tender Journal) | PTB | NCB | 2014-12-11 | 2014-10-11 | 29336143 |  | 2014-12-12 | YES | PEROS & ASSOCIATES NIGERIA LIMITED | 2014-12-12 | 25763954.85 | 6 WEEKS |  | 11075818.89 | 6months | work in progress | 60 | N/A | N/A
212 | Connection Of Electricity Form Mararaba -Gayama -Sabo-Gida Tukwa-Didan-Baissa-Gwanda To National Grid In Taraba State | 22/09/2014 (Daily Trust & Federal Tender Journal) | PTB | NCB | 2014-12-11 | 2014-10-11 | 19800000 |  | 2014-12-12 | YES | VINENESS GLOBAL CONCEPT LTD. | 2014-12-12 | 17102927.19 | 4 WEEKS |  |  | 6months | pole erectoin in progress | 20 | N/A | N/A
213 | Electrification Of Zanyon Teajey, Kaduna State | 22/09/2014 (Daily Trust & Federal Tender Journal) | PTB | NCB | 2014-12-11 | 2014-10-11 | 27329671 |  | 2014-12-12 | YES | TOLUYAN INTEGRATED SERVICES LTD. | 2014-12-12 | 21071450.26 | 6 WEEKS |  |  | 6months | contractor yet to mobilize | 0 | N/A | N/A
214 | Balance To Complete Electrification Of Banghai, Bachit, Keng 'A' & 'B' Fang, Gwon Lwa, Vwak Lwa, Batuk Fang, Shonong 'A' & 'B', Compass And Sharubutu Towns In Riyom Lga Of Plateau State (Bachit) | NA | PTB | Restrictive Tender | 2015-12-03 | 26/2/2015 | 34650000 | 26/2/2015 | 16/3/2015 | YES | MOAT GLOBAL CONCEPTS LTD. | 16/3/2015 | 33221235.42 | 6 WEEKS |  | 9816840 | 6months | completed awaiting testing | 99.9 | N/A | N/A
215 | Electrification Of Ogodo Alata Community In Asa Lga, Kwara State | NA | PTB | Restrictive Tender | 2015-12-03 | 26/2/2015 | 19305000 | 26/2/2015 | 16/3/2015 | YES | HONEY ORSAMONI NIGERIA LIMITED | 16/3/2015 | 17985913.64 | 4 WEEKS |  |  | 6months |  |  | N/A | N/A
216 | Electrification Of Abavo / Ahilagu /Oki / Bojiboji/ Agbor Obi / Emuhu/ Udumebah/ Otolokpo Communities In Ika North East, Lga, Delta State | NA | PTB | Restrictive Tender | 2015-12-03 | 26/2/2015 | 69300000 | 26/2/2015 | 16/3/2015 | YES | PHOENIX HEIRS CONCEPT LIMITED | 16/3/2015 | 59514136.45 | 10 WEEKS |  |  | 6months |  |  | N/A | N/A
217 | Construction Of Solar Street Light At Kayama, Kolokuma Opokuma Lga, Rivers State | NA | PTB | Restrictive Tender | 2015-12-03 | 26/2/2015 | 19800000 | 26/2/2015 | 16/3/2015 | YES | JRB SOLAR INVESTMENT LIMITED | 16/3/2015 | 17805150 | 4 WEEKS |  |  | 6months |  |  | N/A | N/A
218 | Procurement And Installation Of 2nos 300kva Transformers At Peresima Polo Okrika, Rivers State | NA | PTB | Restrictive Tender | 2015-12-03 | 26/2/2015 | 5940000 | 26/2/2015 | 16/3/2015 | YES | FOMRAT INDUSTRIES LIMITED | 16/3/2015 | 5137535.3 | 4 WEEKS |  |  | 6months |  |  | N/A | N/A
219 | Provision Of Solar Street @ Guni In Munya Lga, Niger State | NA | PTB | Restrictive Tender | 2015-12-03 | 26/2/2015 | 9900000 | 26/2/2015 | 16/3/2015 | YES | JRB SOLAR INVESTMENT LIMITED | 16/3/2015 | 7100100 | 4 WEEKS |  |  | 6months |  |  | N/A | N/A
220 | Construction Of 33kva Line Fadumawa-Bahirawa Kurfi B Ward, Katsina State | NA | PTB | Restrictive Tender | 2015-12-03 | 26/2/2015 | 9900000 | 26/2/2015 | 16/3/2015 | YES | EKSATO ENGINEERING SERVICES NIG. LTD. | 16/3/2015 | 8126084 | 4 WEEKS |  |  | 6months |  |  | N/A | N/A
221 | Electrification Of Chibani In Munya Lga, Niger State | NA | PTB | Restrictive Tender | 2015-12-03 | 26/2/2015 | 9900000 | 26/2/2015 | 16/3/2015 | YES | ZYLAB TECHNOLOGIES NIG. LTD. | 16/3/2015 | 8208436.95 | 4 WEEKS |  |  | 6months | sub station/stringing on progress | 86.1 | N/A | N/A
222 | Procurement / Installation Of 5 Nos 500kva Transformers At Shiroro Rafi & Munya Lga, Niger State | NA | PTB | Restrictive Tender | 2015-12-03 | 26/2/2015 | 9900000 | 26/2/2015 | 16/3/2015 | YES | NIELS & STANLEY ENERGY SERVICES AND CONSULTING | 16/3/2015 | 8844080.36 | 4 WEEKS |  |  | 6months |  |  | N/A | N/A
223 | Procurement And Installation Of 300kva Transformer At Ekpedo Akoko Edo, Edo State | NA | PTB | Restrictive Tender | 2015-12-03 | 26/2/2015 | 6930000 | 26/2/2015 | 16/3/2015 | YES | DUE DONS NIG. LIMITED | 16/3/2015 | 5785815.03 | 4 WEEKS |  |  | 6months |  |  | N/A | N/A
224 | Construction Of Solar Street Light At Ekpedo Akoko Edo, Edo State | NA | PTB | Restrictive Tender | 2015-12-03 | 26/2/2015 | 6930000 | 26/2/2015 | 16/3/2015 | YES | DUE DONS NIG. LIMITED | 16/3/2015 | 6048900 | 4 WEEKS |  |  | 6months |  |  | N/A | N/A
225 | Provision And Instl. Of Solar Street Light @ Emenegate In Ogugu Olamaboro Lga, Kogi State | NA | PTB | Restrictive Tender | 2015-12-03 | 26/2/2015 | 9900000 | 26/2/2015 | 16/3/2015 | YES | TOLUYAN INTERGRATED SER. LTD | 16/3/2015 | 7072500 | 4 WEEKS |  |  | 6months |  |  | N/A | N/A
226 | Provision Of 3no. Transformers At Army Barracks Takum Lga Taraba State | NA | PTB | Restrictive Tender | 2015-12-03 | 26/2/2015 | 9900000 | 26/2/2015 | 16/3/2015 | YES | WARAMS SERVICES LTD. | 16/3/2015 | 8982542.37 | 4 WEEKS |  |  | 6months |  |  | N/A | N/A
227 | Provision Of 300kva Transformer At Road A7 Citec Estate, Mbora, Abuja | NA | MD/CEO | Restrictive Tender | 2015-12-03 | 26/2/2015 | 4950000 | 26/2/2015 | 16/3/2015 | YES | EKSATO ENGINEERING SERVICES NIG. LTD. | 16/3/2015 | 3860504 | 2 WEEKS |  |  | 6months |  |  | N/A | N/A
228 | Power Supply And Installation Of 200kva 11/0.445kv Trans. In Usubu Kontagora Lga In Niger North Senatorial District, Niger State | NA | PTB | Restrictive Tender | 2015-12-03 | 26/2/2015 | 6134233 | 26/2/2015 | 16/3/2015 | YES | FOMRAT INDUSTRIES LIMITED | 16/3/2015 | 5747865.14 | 4 WEEKS |  |  | 6months | completedawaiting testing | 72.6 | N/A | N/A
229 | Power Supply And Installation Of 300kva 33/0.415kv Trans. In Tungan Magajiya Town In Magama Lga In Niger North Senatorial District, Niger State | NA | PTB | Restrictive Tender | 2015-12-03 | 26/2/2015 | 7500000 | 26/2/2015 | 16/3/2015 | YES | WARAMS SERVICES LTD. | 16/3/2015 | 6612890.05 | 4 WEEKS |  |  | 6months |  |  | N/A | N/A
230 | Supply And Installation Of 1no. 500kva 11/0.415kv Trans. At Abeokuta North L.G.A., Ogun State | NA | PTB | Restrictive Tender | 2015-12-03 | 26/2/2015 | 7500000 | 26/2/2015 | 16/3/2015 | YES | FANO (NIG.) LTD. | 16/3/2015 | 6006008.4 | 4 WEEKS |  |  | 6months |  |  | N/A | N/A
231 | Network Extension Of Enyibichiri/Echialike, Ebonyi State | NA | PTB | Restrictive Tender | 2015-12-03 | 26/2/2015 | 23473377 | 26/2/2015 | 16/3/2015 | YES | KEW POWER ENGINEERING CO. LTD. | 16/3/2015 | 20332081.65 | 4 WEEKS |  |  | 6months |  |  | N/A | N/A
232 | Extension Of Electricity From Mada To Iggah Burum In Nasarawa State | NA | PTB | Restrictive Tender | 2015-12-03 | 26/2/2015 | 59400000 | 26/2/2015 | 16/3/2015 | YES | BRAMWELL ELECTRICAL NIG. LTD. | 16/3/2015 | 43914127.7 | 6 WEEKS |  |  | 6months |  |  | N/A | N/A
233 | Electrification Of Dengi Bashar In Plateau State | NA | PTB | Restrictive Tender | 2015-12-03 | 26/2/2015 | 27700000 | 26/2/2015 | 16/3/2015 | YES | SAGAOLA MINING AND ENGINEERING (NIG) LTD. | 16/3/2015 | 24333533.72 | 6 WEEKS |  |  | 6months |  |  | N/A | N/A
| TOTAL | [11 empty] | 5038055902.7465

## SEC
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) : |  | SECURITIES & EXCHANGE COMMISSION
MINISTRY : |  | FINANCE
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [5 empty] | CONTRACT AWARD |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | APPROVAL THRESHOLD | PROCUREMENT METHOD | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY MTB | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | AMOUNT PAID AS AT 31/12/2014 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | REMARKS
1 | Supply of 2 Nos Peugoet Expert TEEPEE VEHICLES | TENDERS BOARD | SELECTIVE TENDERING | 100000000 | 2013-12-11 | 14/5/2014 | PAN Ltd | 21/05/2014 | 14575890 | 5 DAYS (UPON RECEPT OF AWARD LETTER) | 14575890 | may, 2015 | completed | Delivered and paid
2 | Supply of one (1) 23 seater, petrol engine airconditioned bus | TENDERS BOARD | SELECTIVE TENDERING | 100000000 | 2013-12-11 | 14/5/2014 | innosson vehic;le manufacturing co. ltd. | 21/5/2014 | 7400000 | 5 DAYS (UPON RECEPT OF AWARD LETTER | 7400000 | may, 2015 | completed
| TOTAL | [7 empty] | 21975890

## POWER
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) : |  | FEDERAL MINISTRY OF POWER
MINISTRY : |  | FEDERAL MINISTRY OF POWER
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD | [5 empty] | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) |  | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2014 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | Revision of Contract for the Design, Manufacture, Supply, Erection and Commissioning of 33KV Switchgear at Kolo Creek | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB |  |  |  | N/A | MTB/June 2014 (TCN) | YES | Meesrs LS Industrial Services Ltd |  | 257707602.62 | 744127.64 |  |  |  |  | ONGOING |  | NIL | NIL
2 | Revision of contract for the Design, Manufacture, Supply, Erection and Commissioning of 1x90MVA-132/33KV Substation oat Gbarantou | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB |  |  |  | N/A | MTB/June 2014 (TCN) | YES | Messrs Income Electrix Ltd |  | 230623305.98 | 3665162.33 |  |  |  |  | ONGOING |  | NIL | NIL
3 | Supply and Installation of Communication Equipment on Security Patrol Vehicles at the Zungeru Hydroelectric Power Project | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB |  |  |  | N/A | MTB/June 2014 (TCN) | YES | Messrs Care Tech Auto Enterprises |  | 20191500 | [5 empty] | ONGOING |  | NIL | NIL
4 | Conduct of Power Sector Stakeholders Research on the Post Reform Progress | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB |  |  |  | N/A | MTB/ June 2014 | YES | Messrs Crystal Research & Marketing Services Ltd | June 18, 2014 | 15750000 |  | 8 Weeks | September 1, 2014 | 7875000 | October, 2014 | Completed | Completed | N/A | N/A | Project completed. Awaiting balance
5 | Production, Design and Mounting of Bill Boards at 7 Locations for the on-going National Power Sector Apprenticeship Scheme (NAPSAS). | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB |  |  |  | N/A | MTB/ July 2014 | YES | MessrsWittengeisen& Walter Ltd |  | 14437500 | [5 empty] | ONGOING |  | NIL | NIL
6 | Engineering,Design,Manufacture,Supply, Commissioning and Protection/Control and Tariff Metering Scheme Equipment for Ibom Power-Alscon 132kv D/C Transmission Line at Alscon Power Plant: For evacuation of over 200MW stranded power to grid network | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB |  |  |  | N/A | MTB/ July 2014 (For TCN) | YES | MessrsMojec International Ltd |  | 724686470.99 | [5 empty] | ONGOING |  | NIL | NIL
7 | Rehabilitation of 12nos. collapsed towers of Sapele-Aladja 330KV Line | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB |  |  |  | N/A | MTB/ July 2014 | YES | MessrsEnergo (Nig) Ltd |  | 269371952.58 | [5 empty] | ONGOING |  | NIL | NIL
8 | Engagement of an external Legal Advisory Service (Coal to Power) for NBET | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB |  |  |  | N/A | MTB/ July 2014 (For NBET) | YES | MessrsKocharr& Company and Administrative Staff College of India and Vigor Law Firm |  | 96646230.8 | [5 empty] | ONGOING |  | NIL | NIL
9 | Construction and Installation of 10KM of 33KV Lines and Associated 2x15MVA, 33/11KV Substation at Ibuzor | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB |  |  |  | N/A | MTB/ August 2014 | YES | Messrs Power Control & Appliances Limited |  | 325792191 | [5 empty] | ONGOING |  | NIL | NIL
10 | Additional works on the Rural Electrification of Agyna-Sabon Tasha in Kwali Area Council, Abuja. | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB |  |  |  | N/A | MTB/ August 2014 | YES | Messr Remarks Associated Engineering Consultancy Ltd |  | 12672164.64 |  |  | June 2014 |  |  | Completed | 100% | NIL | NIL
11 | Procurement of 10nos. Innoson Pick-Up Van 4x4 D/C | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB |  |  |  | N/A | MTB/ August 2014 | YES | MessrsInnoson Vehicle manufacturing Company Ltd |  | 50400000 | [5 empty] | ONGOING |  | NIL | NIL
12 | Payment for the let/lease of an Office space within SHM Office Complex along Kado/MabushiExpressway,Abuja,FCT | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB |  |  |  | N/A | MTB/ August 2014 | YES | MessrsNawa Properties Ltd |  | 9980000 | [5 empty] | ONGOING |  | NIL | NIL
13 | Town hall meeting in 12 locations of the Country for a public awareness campaign on the Power Sector Reform Project | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB |  |  |  | N/A | MTB/ August 2014 | YES | MessrsPatike Communication Limited |  | 59820000 | [5 empty] | ONGOING |  | NIL | NIL
14 | Procurement of 2nos. Large sized Bill Boards to show case giant strides in the Nation’s Power Sector | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB |  |  |  | N/A | MTB/ August 2014 | YES | MessrsGaskia Media Limited |  | 15000000 | [5 empty] | ONGOING |  | NIL | NIL
15 | Appointment of Consultants for Consultancy Services for the Recruitment of Manpower in the 6 Geo political zones of the Country and the Lead Consultant for the National Power Sector Apprenticeship Scheme as follows: LOT 1: North-Central Zone LOT 2 : North-East Zone LOT 3 : North-West Zone LOT 4 : South-East Zone LOT 5 : South-South Zone LOT 6 : South-West Zone Lead Consultant | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB |  |  |  | N/A | MTB/ September, 2014 | YES | a. MessrsGreen Consult Ltd b. Messrs I-Path Hub Ltd c. Messrs Infosofia consulting Ltd d. Bridgegap Investment Ltd e. Messrs Febi Consult Ltd f. Messrs Datanics Engineering Ltd g. Messrs Wittengeisen & Walter Ltd |  | 163000679.4 | [5 empty] | ONGOING |  | NIL | NIL
16 | Let/Lease of an office space within SHM Office Complex along Kado/Mabushi Express way for NAPSAS | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB |  |  |  | N/A | MTB/ September, 2014 | YES | MessrsNawa Properties Ltd |  | 10299200 | [5 empty] | ONGOING |  | NIL | NIL
17 | Clearing of 1390 Hectares Resettlement sites for relocation of the Communities affected by the Zungeru Hydroelectricity Power Project | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ September, 2014 | YES | Messrs Global Legend Integrated Concept Ltd |  | 520000000 | [5 empty] | ONGOING |  | NIL | NIL
18 | Construction of Sustainable off – grid solar power system for the Electrification of selected communities in FCT | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, |  |  | 2014-08-01 | [13 empty] | ONGOING |  | NIL | NIL
a | Durumi Community | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs Schneider Electric Nig Ltd |  | 228255351.01 |  |  | SEPTEMBER, 2013 |  |  | COMPLETED | 100% | NIL | NIL
b | Waru Community | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs Lordezetech Int Ltd. |  | 238375254 |  |  | SEPTEMBER, 2013 |  |  | COMPLETED | 100% | NIL | NIL
c | Shape Community | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs Lordezetech Int Ltd |  | 218895296.88 |  |  | SEPTEMBER, 2013 |  |  | ONGOING |  | NIL | NIL
d | Sherepe Community | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs Golden Grid Solution Inc / M – Raid Global Nig Ltd. |  | 148187393.14 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
19 | Procurement and Installation of Security Services and Critical Assets Protection (Transmission of Surveillance Systems Application) | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  | 594000000 | N/A | MTB/October 2014 | YES | Messers Momas Systems Nigeria Ltd |  | 548010000 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
20 | Upgrading and Improvement of Electricity Supply at Langtang North and Langtang South Federal Constituencies in Plateau State. | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs Roodag Nigeria Ltd |  | 22725130 | [5 empty] | ONGOING |  | NIL | NIL
21 | Production of A Video Documentary on 215MW Kaduna Power Plant Project. | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB |  |  |  | N/A | MTB/October 2014 | YES | Messrs HTP Media Production and Communications. |  | 18193660.5 | [5 empty] | ONGOING |  | NIL | NIL
22 | Procurement and installation of Security Services and Critical Assets Protection (Supply and Installation Inverters at Federal Ministry of Power Headquarters) Federal Secretariat Complex, Abuja Under The Protection of Critical Assets. | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB |  |  |  | N/A | MTB/October 2014 | YES | Messrs 4Prestige Prime Gate Services Limited. |  | 87850000 | [5 empty] | ONGOING |  | NIL | NIL
23 | Supply of Project Vehicles as Follows: 2NOS. Nissan Pick – Up NP300,2.4L, Double Cabin, 4WD AX. 1No. Mitsubishi canter, 3.9ltr | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB |  |  |  | N/A | MTB/October 2014 | YES | Messrs Stallion NMN Ltd Messrs Lanre Shittu |  | 20364450 | [5 empty] | ONGOING |  | NIL | NIL
24 | Rehabilitation and Upgrading of Electricity Supply Network in Kiagbodo Community and University Environs in Delta State. | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB |  |  |  | N/A | MTB/October 2014 | YES | Messrs Power Control and Appliances |  | 26754945 | [5 empty] | ONGOING |  | NIL | NIL
25 | Production and Supply of 6.750NOS Branded Polo Shirts. 6.750NOS Caps, 6.750NOS Jotters, 6,750NOS Pan and Bags For National Power Sector Apprenticeship Scheme (NAPSAS) | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB |  |  |  | N/A | MTB/October 2014 | YES | Messrs Network Strategy Ltd. |  | 60750000 | [5 empty] | ONGOING |  | NIL | NIL
26 | Consultancy Services on Upgrading of Accounting System Facilities in The Department Of Finance and Account, Federal Ministry Of Power. | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  | 49500000 | N/A | MTB/October 2014 | YES | Messrs Data Easy Systems Ltd. |  | 41050000 | [5 empty] | ONGOING |  | NIL | NIL
27 | Consultancy Services and Supervision of The Construction of Hydropower Dams Project in Five Location | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB |  |  |  |  | MTB/October 2014 | [9 empty] | ONGOING |  | NIL | NIL
a | . Asejire Hydropower Dam | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs Quaint Nig Ltd |  | 86932411 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
b | . Zobe Hydropower Dam | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs Goli – Hans Int’l Ltd |  | 87063299.9 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
c | . Owena Hydropower Dam | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs Northcroft Nig Ltd |  | 79989783.3 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
d | . Onipanu Hydropower Dam | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs Helbert Nig Ltd |  | 78998896.4 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
e | . Gimi Hydropower Dam | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs Nathados Ventures Ltd |  | 77618920.1 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
28 | Construction Of Hydropower Dams On Five Locations. Asejire Hydropower Dam | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs Newbay Engr Ltd |  | 243595832.56 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
29 | . Zobe Hydropower Dam | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs Fosab Int’L Ltd |  | 321565603.68 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
30 | . Owena Hydropower Dam | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs IESG Nig Ltd. |  | 265909694.45 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
31 | . Onipanu Hydropower Dam | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs Tralat Nig Ltd |  | 255063273.5 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
32 | . Gimi Hydropower Dam | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs Powersys Integrated Sys Ltd |  | 316872143.42 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
33 | Additional Works On Rural Electrification Of Gawu Village, Doigan Ruwa in Abaji Area Council, FCT Abuja | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  | 39600000 | N/A | MTB/October 2014 | YES | Messrs Sonsac Contractor Ltd |  | 35349167.33 |  |  | 2014-10-01 |  |  | ONGOING |  | NIL | NIL
34 | Additional works On Rural Electrification Of Sabon Gari, Bwari – Kuchibuyi, Byazhin in Bwari Area Council, FCT Abuja. | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  | 39600000 | N/A | MTB/October 2014 | YES | Messrs Black Const. Ltd |  | 38370613.44 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
35 | Engagement Of Transaction Advisor For The Development Of Hydropower Dams Comprising Of 10MW Oyan Dam In Ogun State, 6MW Ikere Gorge Dam In Oyo State And 450KW Owena Dam In Ondo State. | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs Hebert Nigeria Ltd |  | 76109093.88 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
36 | Conduct Of Business Cluster Survey (BCS | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs No 1 Polls Ltd | 2014-11-14 | 17850000 |  | 4 MONTHS | 2015-03-01 | NIL | 2015-06-01 | ONGOING | NIL | N/A | N/A | Awaiting payment of 50%
37 | Conduct Of Business Cluster Survey (BCS | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs Utsola Energy Ltd | 2014-11-14 | 17850000 |  | 4 MONTHS | 2015-03-01 | NIL | 2015-06-01 | ONGOING | NIL | N/A | N/A | Awaiting payment of 50%
38 | Implementation Of Executive Dashboard Solution (Directive Tracking System) For Office Of The Honourable Minister And Permanent Secretary, Federal Ministry Of Power. | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs Softtrust Technologies Ltd |  | 14750000 | [5 empty] | ONGOING |  | NIL | NIL
39 | Upgrading And Improvement Of Data Centre At The Power Holding Company Of Nigeria (PHCN) Building At Maitama For federal Ministry Of Power. | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs Zinox Computers Ltd |  | 54951690 | [5 empty] | ONGOING |  | NIL | NIL
40 | Construction Of Ishiagu Electricity Distribution Network | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs Nathan Christopher Const. Ltd |  | 302305001 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
41 | Power Improvement In Ewatto, Esan South East LGA In Edo State. | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs Kinpatino Projects Ltd |  | 86934452.25 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
42 | Power Improvement At Ita – Oshin Abeokuta North LGA, Ojokodo Ajitadun Abeokuta North And Amolaso Community Abeokuta South LGA In Ogun State | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs Dawn Mara Int’I Ltd |  | 38118022 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
43 | Construstion Of Interconnecting Roads Between The Resettlement Sites Of The Communities to Be Displaced By The Zungeru Hydro Electric Power Project: | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  |  | MTB/October 2014 | [9 empty] | ONGOING |  | NIL | NIL
44 | · LOT 1 – Construction Of 18KMS Laterite Road From Maikago – Kango Riyo – Walako – Jagindin Lawo - Lawo | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs Redak Nigeria Ltd |  | 895400000 | [5 empty] | ONGOING |  | NIL | NIL
45 | · LOT 2 – Construction Of 14KMS Laterite Road From Gidan Danbuki – Burmi – Agbegbe - Ashiwe | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs Valleren Nigeria Ltd |  | 890368000 | [5 empty] | ONGOING |  | NIL | NIL
46 | Consultancy Services For Socio Economic And Environmental Impact Study Hydropower Plant in Two Location. | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  |  | MTB/October 2014 | [9 empty] | ONGOING |  | NIL | NIL
a | . LOT A | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs I.B. Global Resources Ltd |  | 74560432.35 | [5 empty] | ONGOING |  | NIL | NIL
b | . LOT B | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs Open Door System Int’L Ltd |  | 72500100.5 | [5 empty] | ONGOING |  | NIL | NIL
47 | Overhauling Of 4NOS. Elevator At PHCN Building Maitama Abuja. | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB |  |  |  | N/A |  | YES | Messrs BYCO Energy And Petroleum Resources |  | 27300000 | [5 empty] | ONGOING |  | NIL | NIL
48 | External Painting Of PHCN Building in Maitama Abuja. | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB |  |  |  | N/A | MTB/October 2014 | YES | Messrs Berger Paint Nig PLC. |  | 16027948 | [5 empty] | ONGOING |  | NIL | NIL
49 | · Supply Of 1NO. Innoson IVM 5000, 15 Seater Bus, Petrol Engine, 2.4L Utility Bus | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB |  |  |  | N/A | MTB/October 2014 | YES | Messrs Innoson Vehicle Man. Co. Ltd. |  | 4410000 | [5 empty] | ONGOING |  | NIL | NIL
50 | · 5NOS. IVM – Carrier 4WD Petrol Engine With Air Conditioner. | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB |  |  |  | N/A | MTB/October 2014 | YES | Messrs Innoson Vehicle Man. Co. Ltd |  | 26200000 | [5 empty] | ONGOING |  | NIL | NIL
51 | For Security Services And Critical Asset Protection. | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  |  | MTB/October 2014 | [9 empty] | ONGOING |  | NIL | NIL
52 | · Supply And Installation Of Bollard. | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October | YES | Messrs Natty Joe Ventures |  | 52999093.88 | [5 empty] | ONGOING |  | NIL | NIL
53 | · Construction Of Electric Fence And Hand Held Bomb Detector. | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October | YES | Double Platinum Group |  | 33371089.5 | [5 empty] | ONGOING |  | NIL | NIL
54 | · Security Access Control | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs ASM Technology Ltd |  | 66062338.68 | [5 empty] | ONGOING |  | NIL | NIL
55 | · Supply & Installation Of Walkthrough Metal Detector & Baggage Scanner | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/October 2014 | YES | Messrs Aviastrat Limited. |  | 25447433.38 | [5 empty] | ONGOING |  | NIL | NIL
56 | LOT B7 1MW Solar Power Plant at Shagari Town in Soloto State | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/November 22014 | YES | Messrs Solar Force Nigeria Limited |  | 105739142 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
57 | LOT B9 Supply and installation of 3 units of KVA Transformer in Akerebiata Area Ilorin East LGA, Muhyideen Road Illorin South, Kwara | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  | 15000000 | N/A | MTB/November 22014 | YES | Messrs Setonji Ojugbele Elect Power Works Nigeria Limited |  | 11785853.2 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
58 | LOT B10 Provision of Ten (10) Nos 500KVA 33/0.415 Transformers with accessories at Abeokuta North, Obafemi Owode and Odeda LGA, Ogun State | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  | 20000000 | N/A | MTB/November 22014 | YES | Messrs De-El Shaddai Prestige Nigeria Limited |  | 17298382.8 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
59 | LOT B13 Electrification of Kubchi, Baaje and Multe Village of Danboa LGA | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  | 100000000 | N/A | MTB/November 22014 | YES | Messrs Musty Electrical company Limited |  | 98209734.93 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
60 | LOT B18 Construction of Solar Sreet Light in Ikwa West, Abia State | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  | 29700000 | N/A | MTB/November 22014 | YES | Messrs East Equipment and Co. Limited |  | 24757200 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
61 | LoT B18 Constuction of 500KVA Transformer relief substation and connection to National grid at Karu district, Jos South LGA Plateau State | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  | 6800000 | N/A | MTB/November 22014 | YES | Messrs Ogon Asun Co. Limited |  | 6190195.28 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
62 | LOT B19 Transformer projects and installation of solar streetlight in Ageva, Etahi, GRA, Idare/Idogido, Idiche, Idoji, Idozumi, Inike, Obehirra, Okeneba, Okengwe, and Ozuwaya | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  | 29700000 | N/A | MTB/November 22014 | YES | Messrs Lejit Nigeria Limited |  | 19842000 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
63 | LOT B21 Electrification of Ijakoro-Zhiko/Papsa Village in Bwari LGA (6JM) | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  | 39600000 | N/A | MTB/November 22014 | YES | Messrs MTC Nigeria Limited |  | 31805691.02 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
64 | LOT B 22 Electricfication of Kwara to YEBU Leda, Kwali Area Council, FCT | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  | 19800000 | N/A | MTB/November 22014 | YES | MessrsVinez Projects and Investment Limited |  | 16612152.5 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
65 | LOT B23 Electrification of Paiko-Ibwa, Gwagwalada Area Council, FCT | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  | 12870000 | N/A | MTB/November 22014 | YES | Messrs Zetex Ventures Limited |  | 10404179.38 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
66 | LOT 24 Electrification of Apo to Taku Shara, Amac FCT, Abuja | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  | 19800000 | N/A | MTB/November 22014 | YES | Messrs Jaal Engineering Services Limited |  | 12814308.55 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
| ELECTRIFY NIGERIA (LIGHT UP NIGERIA) In The Following Locations | [5 empty] | 1089000000 | [11 empty] | ONGOING |  | NIL | NIL
67 | NEKE UNO, ENUGU STATE | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs Sonsac Contractors Limited |  | 117659691 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
68 | Katsit Daji, Kaduna Stae | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs Brown Obolity & Company Limited |  | 118446229.86 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
69 | Aztateumini, Abia | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs Techno International Limited |  | 129201055.01 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
70 | Ubogu, Obuno, Akpugo, Nkanu West Lga, Enugu State | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs Ayolex Investment Li Mited |  | 122201979.38 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
71 | Modu Ganari (Police College Maiduguri) | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs AIA International Limited |  | 124668454.6 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
72 | Dagwarga, Sokoto | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs Black Construction Limited |  | 128575462.5 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
73 | Biliri, Gombe State | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs Demfad Engineering Nigeria Company Limited |  | 129607816 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
74 | Odoralamo, Ogun State | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs Egja Meceng Nigeria Li Mited |  | 129370518.45 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
75 | Otuaba, Bayelsa State | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs Binowell Integrated Services Limited |  | 129316803.16 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
76 | Udi Town, Enugu State | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs Mindlink International Limited |  | 129607053.16 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
77 | Eniwari, Bayelsa State | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs Bensam Nigeria Limited |  | 113365812 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
78 | Nta Maduguri, Borno State | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs Hi-Test Nigeria Limited |  | 127776111.3 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
79 | Umudimagu, Imo State | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs XYZ Engineering Services Limited |  | 118464229.81 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
80 | Oguru, Ogun State | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs Somerset Cap Mark Trust |  | 124350360 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
81 | Alau (University Of Maiduguri) | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs MSH Marine Services Limited |  | 122658454.6 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
82 | Ajegunle Village, Abeokuta | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs Kalaks Investment Nigeria Limited |  | 123776687.6 |  |  | APG NOT PAID |  |  | ONGOING |  | NIL | NIL
83 | Engagment Of Consultant For Ict Projects As Follows: |  |  |  | 2014-08-01 | [13 empty] | ONGOING |  | NIL | NIL
84 | Lead Consultant | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs Trydell Consulting limited |  | 12000000 | [5 empty] | ONGOING |  | NIL | NIL
85 | DEVELOPMENT OF N IGERIA POWER SECTOR INFORMATION SYSTEM (PSMIS ) | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  | 14850000 | N/A | MTB/ December 2014 | YES | Messrs Achor Dataware solutions Limited |  | 20455375 | [5 empty] | ONGOING |  | NIL | NIL
86 | CONDUCT OF POWER INFRASTRUTURE CENCUS | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  | 14850000 | N/A | MTB/ December 2014 | YES | Messrs Geosoft Solutions Limited |  | 11200000 | [5 empty] | ONGOING |  | NIL | NIL
87 | DEVELOPMENT OF INFORMATION RESOURSES CENTRE (IRC) VIRTAL LIBRARY (VR) | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  | 19800000 | N/A | MTB/ December 2014 | YES | Messrs Finesse Integrated Technology Llimited |  | 24197605 | [5 empty] | ONGOING |  | NIL | NIL
88 | INSTALLATION OF VIDEO CONFERENCING SYSTEM | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  | 25273499 | N/A | MTB/ December 2014 | YES | Messrs Hospitrends Cunsulting Limited |  | 21704657.51 | [5 empty] | ONGOING |  | NIL | NIL
89 | DASHBOARD PROJECT MONITORING SYSTEM | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  | 19800000 | N/A | MTB/ December 2014 | YES | Messrs Quaint Global Energy Solutions Limited |  | 13192566 | [5 empty] | ONGOING |  | NIL | NIL
90 | ENGAGEMENT OF CONSULTANT FOR TECHNICAL CAPACITY BUILDINGFOR PPP & IPPS PROJECTS | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  | 14850000 | N/A | MTB/ December 2014 | YES | Messrs Quaint Global Energy Solutions Limited | 2014-12-04 | 8212050.05 |  | 2 MONTHS |  |  |  | ONGOING |  | NIL | NIL
91 | ENGAGEMENT OF CONSULTANT FOR ESTABLISMENT OF COMPUTERISED RECORDS & E-REGISTRY | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  | 49500000 | N/A | MTB/ December 2014 | YES | Messrs Hallowgate Telecom Services Limited |  | 23283750 | [5 empty] | ONGOING |  | NIL | NIL
92 | WORKSHOP ON ESTABLISHMENT OF COMPUTERISED RECORDS & REGISTRY | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs Tagged Technology Limited |  | 15200150 | [5 empty] | ONGOING |  | NIL | NIL
93 | Power Improvement In Boji-Boji Agbor And Aliagwai Communities In Ika South LGA Of Delta State | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs Genco Excel Services Limited |  | 154915856 | [5 empty] | ONGOING |  | NIL | NIL
94 | Design, Supply And Installation Of 3 X 1.5million Liters Fuel Storage Tanks, Associated Interconnection And Pumps For The 215MW Kaduna Power Plant Project | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs Arewa Metal Containers Ltd |  | 556300275.01 | [5 empty] | ONGOING |  | NIL | NIL
95 | Consultancy Services on Enumeration and Valuation of properties at Mambilla Hydroelectric Power Project in ten (10) locations | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014,
96 | Enumeration and Valuation of Tlrow Takun-Kastina-Ala and Buruku LGAs | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs Amakiri Associates |  | 83352000 | [5 empty] | ONGOING |  | NIL | NIL
97 | Enumeration and Valuation of Tlrow Bali,Ussa, Gassol LGAs | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs Ora Egbunike and Associate |  | 83352000 | [5 empty] | ONGOING |  | NIL | NIL
98 | Enumeration and Valuation of Tlrow Donga LGA, Mararaba Majot 330KVA Substation | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs Adamu Mohammed and Partners |  | 83352000 | [5 empty] | ONGOING |  | NIL | NIL
99 | Enumeration and Valuation of TLROW Gboko, Tarka, Markudi LGAs & Apir 330KVA Substation | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs Dan Odiete & Co. |  | 87814000 | [5 empty] | ONGOING |  | NIL | NIL
100 | Enumeration and Valuation of TLROW Ardo Kola, Jalingo LGAs 330KVA Substation | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs Mohammed & Co |  | 87814000 | [5 empty] | ONGOING |  | NIL | NIL
101 | Enumeration and Valuation of Sabon Gida, Akanwe, TLROW Portyard, Abong – Mararaba 330KVA Substation | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs Obi-Anioke & Co |  | 87814000 | [5 empty] | ONGOING |  | NIL | NIL
102 | Enumeration and Valuation of Sumsum tunnel intake, Nghu Dam, Power House, Switch & Api Weir and all interconnecting tunnels | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs Eze Eze & Co |  | 98451000 | [5 empty] | ONGOING |  | NIL | NIL
103 | Enumeration and Valuation of Old Gembu Dam Axis, Leme, Kamkam, Tambuwa & Kusuku River flooding Area, Nya Dam Axia & Sumsum Dam | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs Iboro Ige Adaba & Associates |  | 98451000 | [5 empty] | ONGOING |  | NIL | NIL
104 | Enumeration and Valuation of Right Bank of Donga River in Gembu Dam Axis Reservoir | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs Frank Maluze and Associates |  | 98451000 | [5 empty] | ONGOING |  | NIL | NIL
105 | Enumeration and Valuation of Right Bank of Donga River in Gembu Dam Axis Reservoir | Federal Tender Journal, Monday June 30-Sunday July 13, 2014, Nigeria Pilot of Thursday June 19, 2014, | MTB | NCB | 2014-08-01 |  |  | N/A | MTB/ December 2014 | YES | Messrs George Nzei & Co |  | 98451000 | [5 empty] | ONGOING |  | NIL | NIL
| TOTAL | [11 empty] | 13249104455.7 | 4409289.97 | 167.5 | CBN RATE @ 31st Dec. 2014
738556069.975
[12 empty] | G/TOTAL | 13987660525.675

## WDC
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) : |  | NATIONAL CENTRE FOR WOMEN DEVELOPMENT
MINISTRY : |  | FEDERAL MINISTRY FOR WOMEN AFFAIRS & SOCIAL DEVELOPMENT
FINANCIAL YEAR : 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2013 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2013 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | Construction of Skills acquisition Centre at Ngodo in Ummuneochi LGA of Abia State | 22nd July, 2013 | Tenders Board | NCB | 5th August,2013 | 25-26 Sept, 2013 | 2013/2014 | NA | 27 Aug.,2013 |  | Macbeck International Ltd. | 6 Nov. 2013 | 25454867 | Ongoing |  | Nil | Ongoing | Works | 20% | NA | NA | Ongoing
2 | Equiping of Multi- Production Plants Eket and Women War Memorial Ikot Abasi, Akwa Ibom State | 22nd July, 2013 | Tenders Board | NCB | 5 August, 2013 | 27 August, 2013 | 2013/2014 | NA | 27 Aug.,2013 |  | Votary Covenate Technology Limited | 3 Sept,2013 |  | Ongoing | 11 Dec. 2013 | 9464325 | Ongoing | Goods | 20% | NA | NA | Ongoing
3 | Equiping of Cassava cottage Industry with machines at Nkporo I Ohafia LGA Abia State | 22nd July, 2013 | Tenders Board | NCB | 5th August,2013 | 25 -26 Sept,2013 | 2013/2014 | NA | 27 Aug.,2013 |  | Tramasco Nig. Ltd. | 6th Nov. 2013 | 17000000 | Ongoing | 11th Dec. 2013 | Nil | Ongoing | Goods | Completed | NA | NA | Ongoing
4 | Construction of Mini Fish Processing Plant at Mbo, Akwa Ibom State | 22nd July, 2013 | Tenders Board | NCB | 5th August,2013 | 27th August,2013 | 2013/2014 | NA | 27 Aug.,2013 |  | Fastrack Investment Company Ltd. | 3rd Sept.2013 | 64453867 | Ongoing | 4th Sept.2013 | 22,299.321.6 | Ongoing | Works | Completed | NA | NA | Ongoing
5 | Construction of Mini Fish Processing Plant at Ibeno LGA, Akwa Ibom State | 22nd July, 2013 | Tenders Board | NCB | 5th August,2013 | 27th August,2013 | 2013/2014 | NA | 27 Aug.,2013 |  | M/S Pacific Hills International Ltd | 3rd Sept.2013 | 63095500 | Ongoing |  | 59730148 | Ongoing | Works | Completed | NA | NA | Ongoing
6 | Replacement of Central Air Condition system for the Main Auditotium | 25th June, 2012 | Tender Board | NCB | 17th July, 2012 | 11th Oct. 2012 | 2012/2013/2014 | NA | 11th Oct.2012 |  | M/S Samab Nig.Ltd | 23rd Oct. 2012 | 44255000 | Ongoing | 23rd Oct, 2012 | 30978500 | Ongoing | works | Ongoing | NA | NA | Ongoing
7 | Construction of Women war and Development Centre in Ikot Abasi | 25th June, 2012 | Tender Board | NCB | 17th July, 2012 | 11th Oct. 2012 | 2012/2013 | NA | 11th Oct.2012 |  | M/S Crystar Nig. Ltd | 23rd Oct. 2012 |  | Ongoing | 23rd Oct, 2012 | 60000000 | Ongoing | Work | Ongoing | NA | NA | Ongoing
8 | Palm Oil processing Mill in Esit Eket LGA, Akwa Ibom State | 22nd July, 2013 | Tender Board | NCB | 17th July, 2012 | 11th Oct. 2012 | 2012/2013 | NA | 11th Oct.2012 |  | Anisef Intergated ltd | 23d Oct. 2012 | 37500000 | Ongoing | 23rd Oct, 2012 | 12000000 | Ongoing | Work | Ongoing | NA | NA | Ongoing
9 | Cassava cottage Industry at Nkporo I Ohafia LGA Abia State | 22nd July, 2013 | Tenders Board | NCB | 5 | 27th August,2013 | 2013/2014 | NA | 27th Aug.2013 |  | Tramasco Nig. Ltd | 6th Nov. 2013 | 17350000 | Ongoing | 11th Dec.2014 | 16523809 | Ongoing | Works |  | NA | NA | Ongong
10 | Repair of fire Guted Building , Dora Akunyili Block | 22nd July, 2013 | Tender Board | NCB | 5th August,2013 | 27th August,2013 | 2013/2014 | NA | 25th April, 2014 |  | Solidmark Associates Ltd | 28th May, 2014 | 33000000 | Ongoing | 29th May,2014 |  | Ongoing | Work | Ongoing | NA | NA | Ongion
11 | Rehabilitation of Nigerian Women Hall of Fame | 22nd July, 2013 | Tenders Board | NCB | 24th Sep. 2013 | 27th August,2013 | 2013/2014 | NA | 27 Aug.,2013 |  | Dream Technologies and Logistic Limited | 3rd Sept.2013 | 12507760 | Ongoing | 4th Sept.2013 | 12507760 | Ongoing | Works | Ongoing | NA | NA | Ongoing
12 | Research, Documentation on relevant Gender issues including the National Gender Data Bank, Activation of Women Development Centres (WDCs) in Nigeria and Gender/ICT Training for Women for Sustainable National Development | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 33000000 | Ongoing | NA | NA | Ongoing | Training Programme | Ongoing | NA | NA | Ongoing
13 | Reactivation of Women Development Centre and Gender Vocational/ICT Training of Women at Ebonyi South Senatorial District | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 113312292 | Ongoing | NA | NA | Ongoing | Training Programme | Ongoing | NA | NA | Ongoing
14 | Women Empowerment programme in Zamfara West Senatorial District, Zamfara State | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 15000000 | Ongoing | NA | NA | Ongoing | Training Programme | Ongoing | NA | NA | Ongoing
15 | Women Development Centre at Alimosho LGA, Lagos West Senatorial District, Lagos State | 22nd July, 2013 | Tender Board | NCB | 5th August,2013 | 27th August,2013 | 2013/2014 | NA | 27th Aug.2013 |  | Stable Tech.Ltd | 3rd Sept.2013 | 104745328.39 | Ongoing | 3rd Sept,2013 | Nil | Ongoing | Works | Ongoing | NA | NA | Ongoing
16 | Collation of Sex Disagregated Data on involvement/participation of Nigerian Women in Politics from 1999 -date in collaboration with the National Bureau of Statistics | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 25000000 | Ongoing | NA | NA | Ongoing | Training Programme | Ongoing | NA | NA | Ongoing
17 | Collation of Data on Mortality in Nigeria (update on 2007 Indices) | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 15000000 | Ongoing | NA | NA | Ongoing | Training Programme | Ongoing | NA | NA | Ongoing
| TOTAL | [11 empty] | 620674614.39

## NCPC
PROCUREMENT RECORDS (SERVICES)
PROCURING ENTITY (MDA) : |  | NIGERIA CHRISTIAN PILGRIM COMMISSION
MINISTRY : |  | PRESIDENCY
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (US $) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014 (US $) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2013 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | AIRLIFT OF NIGERIAN CHRISTIAN PILGRIMS TO & FROM ISRAEL, ROME AND GREECE | DAILY TRUST, THE PUNCH, FEDERAL TENDERS JOURNAL AND NCPC WEBSITE ON TUESDAY, 25TH FEBRUARY, 2014 | (SGF)FEC | INTERNATIONAL COMPETITIVE BIDDING | 2014-04-17 | 2014-05-05 | FROM STATES CHRISTIAN WELFARE BOARDS | N/A | 2014-07-07 | YES | ATLAS JET | 2014-08-01 | 5253740 | 3 MONTHS | OCTOBER, 2014 | 5253740 | 2014-12-31 | COMPLETED | 100 | N/A | N/A
2 | GROUNDHANDLING OF NIGERIAN CHRISTIAN PILGRIMS IN ISRAEL, ROME AND GREECE | DAILY TRUST, THE PUNCH, FEDERAL TENDERS JOURNAL AND NCPC WEBSITE ON TUESDAY, 25TH FEBRUARY, 2014 | PARASTATAL TENDER BOARD | INTERNATIONAL COMPETITIVE BIDDING | 2014-04-17 | 2014-05-05 | FROM STATES CHRISTIAN WELFARE BOARDS | N/A | 2014-05-15 | AWARDED TO 6 NO. GROUND HANDLERS | TAILOR MADE; TABAR TOURS; SUNWAY TOURS; JERUSALEM T&T; ASIA/RUBICON; PROMOTLINE | 2014-08-01 | 11616020 | 3 MONTHS | OCTOBER, 2014 | 11616020 | 2014-12-31 | COMPLETED | 100 | N/A | N/A
16869760
PROCUREMENT RECORDS (GOODS)
| PROCURING ENTITY (MDA) : | NIGERIA CHRISTIAN PILGRIM COMMISSION
| MINISTRY : | PRESIDENCY
| FINANCIAL YEAR : | 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2013 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | SUPPLY OF OFFICE FURNITURE AT THE HEADQUARTERS OFFICE COMPLEX | 17/04/14, NCPC NOTICE BOARD | PARASTATAL TENDER BOARD | NATIONAL COMPETITIVE BIDDING | 2014-04-30 | 2014-05-14 | CAPITAL | N/A | 2014-05-14 | YES | MESSRS. FORTRESS PROJECTS LTD | 2014-05-28 | 5775900 | 14 DAYS | N/A | 5198310 | 2014-06-11 | COMPLETED | 100 | N/A | N/A
2 | PROVISION OF LOCAL AREA NETWORK (LAN) TO THE NEW BUILDING OF THE COMMISSION | 30/07/14, NCPC NOTICE BOARD | PARASTATAL TENDER BOARD | NATIONAL COMPETITIVE BIDDING | 2014-08-14 | 2014-08-19 | CAPITAL | N/A | 2014-08-19 | YES | MESSRS. DYNAMIC COMPUTER RESOURCE CENTRE LTD. | 2014-08-22 | 1812540.68 | 14 DAYS | N/A | 1631286.61 | 2014-09-05 | COMPLETED | 100 | N/A | N/A
3 | SUPPLY OF OFFICE EQUIPMENT | 1/08/14, NCPC NOTICE BOARD | ACCOUNTING OFFICER | NATIONAL COMPETITIVE BIDDING | 2014-08-15 | 2014-08-23 | CAPITAL | N/A | 2014-08-23 | YES | MESSRS. ALLMEG INVESTMENT LTD | 2014-08-25 | 939225 | 14 DAYS | N/A | 845302.5 | 2014-09-08 | COMPLETED | 100 | N/A | N/A
4 | SUPPLY OF OFFICE FURNITURE | 1/08/14, NCPC NOTICE BOARD | PARASTATAL TENDER BOARD | NATIONAL COMPETITIVE BIDDING | 2014-08-15 | 2014-08-23 | CAPITAL | N/A | 2014-08-23 | YES | MESSRS. CASTELLO INTERIORS LTD | 2014-08-25 | 4029900 | 14 DAYS | N/A | 3626910 | 2014-09-08 | COMPLETED | 100 | N/A | N/A
5 | SUPPLY OF OPERATIONAL VEHICLE (PEUGEOT 508) | 1/08/14, NCPC NOTICE BOARD | PARASTATAL TENDER BOARD | NATIONAL COMPETITIVE BIDDING | 2014-08-15 | 2014-08-23 | CAPITAL | N/A | 2014-08-23 | YES | MESSRS. A.S.D MOTORS NIG.LTD | 2014-08-25 | 9484000 | 14 DAYS | N/A | 8535600 | 2014-09-08 | COMPLETED | 100 | N/A | N/A
6 | SUPPLY AND INSTALLATION OF OFFICE WOODEN BLINDS AND CURTAINS | 9/09/14, NCPC NOTICE BOARD | ACCOUNTING OFFICER | NATIONAL COMPETITIVE BIDDING | 2014-09-09 | 2014-09-23 | CAPITAL | N/A | 2014-09-25 | YES | MESSRS. STEB GLOBAL | 2014-09-29 | 2344755 | 14 DAYS | N/A | 2110279.5 | 2014-10-13 | COMPLETED | 100 | N/A | N/A
7 | ADDITIONAL SUPPLY OF OFFICE FURNITURE | 6/10/14, NCPC NOTICE BOARD | ACCOUNTING OFFICER | NATIONAL COMPETITIVE BIDDING | 2014-10-06 | 2014-10-20 | CAPITAL | N/A | 2014-10-22 | YES | MESSRS. FORTRESS PROJECTS LTD | 2014-10-24 | 2366600 | 14 DAYS | N/A | 2129940 | 2014-11-07 | COMPLETED | 100 | N/A | N/A
8 | INSTALLATION OF MOTORIZED SLIDING GATE | 21/10/14, NCPC NOTICE BOARD | PARASTATAL TENDER BOARD | NATIONAL COMPETITIVE BIDDING | 2014-10-21 | 2014-11-04 | CAPITAL | N/A | 2014-11-06 | YES | MESSRS. AFE VENTURES LTD | 2014-11-07 | 3889820 | 14 DAYS | N/A | 3500838 | 2014-11-21 | COMPLETED | 100 | N/A | N/A
9 | SUPPLY OF 17HP DESKTOP COMPUTERS | 5/11/14, NCPC NOTICE BOARD | ACCOUNTING OFFICER | NATIONAL COMPETITIVE BIDDING | 2014-11-05 | 2014-11-19 | CAPITAL | N/A | 2014-11-21 | YES | MESSRS. DLAMAZ GLOBAL RESOURCES LTD | 2014-11-24 | 2142000 | 14 DAYS | N/A | 1927800 | 2014-12-08 | COMPLETED | 100 | N/A | N/A
10 | SUPPLY OF OFFICE FURNITURES TO FIVE ZONAL OFFICES | 7/11/14, NCPC NOTICE BOARD | PARASTATAL TENDER BOARD | NATIONAL COMPETITIVE BIDDING | 2014-11-07 | 2014-11-21 | CAPITAL | N/A | 2014-11-24 | YES | MESSRS. FORTRESS PROJECTS LTD | 2014-11-26 | 5021225 | 14 DAYS | N/A | 4519102.5 | 2014-12-10 | COMPLETED | 100 | N/A | N/A
37805965.68
[13 empty] | 2825684800 | 167.5 | CBN RATE @ 31st Dec. 2014
[12 empty] | G/TOTAL | 2863490765.68

## NTA
PROCUREMENT RCORDS FOR 2014 FINANCIAL YEAR
NIGERIAN TELEVISION AUTHORITY
S/N | PROJECT DESCRIPTION | DATE OF BOM APPROVAL | DATE OF TENDER’S BOARD APPROVAL | CONTRACT AWARD INFORMATION | CONTRACT AMOUNT | EXPECTED DATE OF DELIVERY | ACTUAL DATE OF DELIVERY | MODE OF PAYMENT
1 | Supply of Studio Equipment for NTA 24 & NTA N/W News | 2014-01-05 | 27/5/2014 | Deechez Broadcast Ltd. | 6860601.8 | 2014-04-07 | Completed | E – Payment
2 | Supply of One 200 W HPA For NTA Ibadan. | 21/4/2014 | 27/5/2014 | Royal Telecomm International | 6380000 | 25/7/2014 | Completed | E – Payment
3 | NTA Headquarters Website Development | 2014-11-03 | 27/5/2014 | Rubik Technologies Ltd | 5500000 | 2014-05-07 | Completed | E – Payment
4 | Supply of Microwave Link Equipment for NTA Lagos and Abuja Stations | 28/3/2014 | 23/7/2014 | Royal Telecomm International | 33600000 | 30/8/2014 | Completed | E – Payment
5 | Supply of 3 Digital Studio Cameras for NTA Network News | 30/4/2014 | 27/5/2014 | Cedar Broadcast Ware House | 45845953.23 | 2014-04-07 | Completed | E – Payment
6 | Upgrade of Equipment for NTA Jos Digital switchover | 18/6/2014 | 2014-04-07 | C2S Nigeria Ltd | 5000000 | 2014-11-08 | Completed | E – Payment
7 | Supply of Equipment Upgrade For NTA News 24 | 2014-10-07 | 23/7/2014 | Mukmubis Nig. Ltd. | 26665612 | 30/8/2014 | Completed | E – Payment
8 | Equipment for NTA Port Harcourt Network Centre | 28/6/2014 | 23/7/2014 | Deechez Broadcast LTD | 3998400 | 30/8/2014 | Completed | E – Payment
9 | Supply of Professional Camcorders and Editing Systems | 13/6/2014 | 2014-04-07 | Deechez Broadcast Ltd | 42304500 | 2014-11-08 | Completed
E – Payment
10 | Supply of two Sonny Cameras For Production of Jingle | 2014-12-04 |  | KONTAKT, NIGERIA, UK, SINGAPORE | 2337000 |  | Completed | E – Payment
11 | Supply of Non Linear Editing System for Sports Light Documentary Series | 30/4/2014 | 2014-07-05 | Kontakt Nigeria Ltd Electronic Dealers Pelefman Ltd | 1165000 |  | Completed | E – Payment
12 | Supply of One Camera GY-HM650HD to Cover power link In Presidency | 25/2/2014 | 27/2/2014 | Deechez Broadcast Ltd | 2130000 | 2014-07-04 | Completed | E – Payment
13 | Supply Of Dehydrator to NTA Keffi | 20/5/2014 | 27/5/2014 | MACHIN TELECOM COP.LTD | 997000 |  | Completed | E – Payment
14 | Supply of One JVC Camera to VPS Office | 13/3/2014 | 26/4/2014 | Deechez Broadcast Ltd | 2480800 | 2014-07-04 | Completed | E – Payment
15 | Supply of One HPA From CPI International (Canada) | 21/4/2014 | 27/5/2014 | Communication & Power Industries | 6878000 |  |  | E – Payment
16 | Supply of Transmitter Spare Parts for NTA Kaltungo |  |  | TUFASCO NIG. LTD | 10715518 | 2014-03-03 | Completed | E – Payment
17 | Upgrade of DSNG Vans | 27/10/2014 | 28/10/2014 | Marutee Nigeria Ltd | 32776000 | 2014-05-12 | Completed | E – Payment
18 | Supply of Professional Camcorders and Standard Editing Systems | 2014-01-11 | 18/11/2014 | Gallahams Technologies Ltd | 31597500 | 31/12/2014 | Completed | E – Payment
19 | Supply of Broadcast Equipment for NTA Kaltungo | 26/11/2014 | 25/11/2014 | Deechez Broadcast Ltd | 34594917 | 31/12/2014 | Completed | E – Payment
20 | Supply of studio Equipment for NTA Nsukka | 26/11/2014 | 25/11/2014 | JEMJOH Nigeria Ltd | 25970000 | 31/12/2014 | Completed | E – Payment
21 | Furnishing of Admin & Boardroom Complex at NTA Owerri | 26/11/2014 | 25/11/2014 | Executive Building Project Ltd | 29800000 | 31/12/2014 | Completed | E – Payment
22 | Supply of NTA Transmitter Equipment | 26/11/2014 | 25/11/2014 | Mukmubis Nigeria Ltd | 20110000 | 31/12/2014 | Completed | E – Payment
23 | Renovation Work at NTA Potiskum Studio | 13/11/2014 | 18/11/2014 | Executive Building Project Ltd | 19210070 | 28/12/2014 | Completed | E – Payment
24 | Development of Enterprise Resource Planning Solution for Admin and Finance | 2014-07-11 | 18/11/2014 | Rubik Technologies Ltd | 19273000 | 25/12/2014 | Completed | E – Payment
25 | Supply of Equalizer Assembly | 28/2/2014 | 30/7/2014 | Sohas Ventures Nigeria Ltd | 2500000 | 28/8/2014 | Completed | E – Payment
26 | Supply of Vision Mixer for Live streaming | 13/11/2014 | 2014-06-11 | C2S Nigeria Ltd | 1743340 | 15/12/2014 | Completed | E – Payment
27 | Supply of 4 VZC-6964A4,5850-6650 MHZ HPAs | 18/10/2014 | 13/11/2014 | Communication and Power Industries (CPI) | 31046400 | 31/1/2015 | Completed | E – Payment
28 | Supply of MSX32HD/SD Matrix | 28/11/2014 | 2014-05-12 | Cedar Broadcast Ware House | 2843484 | 2015-05-01 | Completed | E – Payment
GRAND TOTAL |  |  |  |  | 454323096.03

## PPRA
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) : |  | PETROLEUM PRODUCTS PRICING REGULATORY AGENCY (PPPRA)
MINISTRY : |  | MINISTRY OF PETROLEUM RESOURCES
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION |  | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2014 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | CONTRACT AWRAD FOR SITE CLEARING AND EARTHWORK FOR PPPRA CAR PARK |  | TENDER BOARD | TENDERING | 2014-02-27 |  | 24800345 | NOT APPLICABLE | NOT APPLICABLE | YES | BEAN TOWN NIG. LTD | 2014-01-27 | 23139532.5 | 1 MONTH | NOT APPLICABLE | 23139532.5 | 2014-02-27 | Completed | 100% | NOT APPLICABLE | NOT APPLICABLE
2 | CONTACT AWARD FOR ENGAGEMENT AS A TAX CONSULTANT |  | TENDER BOARD | TENDERING | 2014-02-17 |  | 18527532.1 | NOT APPLICABLE | NOT APPLICABLE | YES | W. E. AKHIBI & CO | 2014-01-27 | 11466000 | 3 WEEKS | NOT APPLICABLE | 11466000 | 2014-02-17 | Completed | 100% | NOT APPLICABLE | NOT APPLICABLE
3 | CONTRACT AWARD FOR THE PARTITIONING OF 5TH FLOOR |  | TENDER BOARD | TENDERING | 2013-12-30 | 2013-12-30 | 29057827 | NOT APPLICABLE | NOT APPLICABLE | YES | INTERIOR WOODWORKS LTD | 2014-02-17 | 28716600 | 6 MONTHS | NOT APPLICABLE | 28716600 | 2014-07-17 | Completed | 100% | NOT APPLICABLE | NOT APPLICABLE
4 | CONTRACT AWARD FOR THE PARTITIONING OF GROUND FLOOR |  | TENDER BOARD | TENDERING | 2013-12-30 | 2013-12-30 | 18968534 | NOT APPLICABLE | NOT APPLICABLE | YES | ITEX FURNITURE | 2014-03-18 | 18032850 | 4 MONTHS | NOT APPLICABLE |  | 2014-07-18 | CANCELLED |  | NOT APPLICABLE | NOT APPLICABLE
5 | CONTRACT AWARD FOR THE PURCHASE OF A TOYOTA LANDCRUISER VXR-VX |  | TENDER BOARD |  |  |  | 25502500 | NOT APPLICABLE | NOT APPLICABLE | YES | ELIZADE NIG PLC | 2014-07-29 | 23888889 | 2 WEEKS | NOT APPLICABLE | 23888889 | 2014-09-12 | Completed | 100% | NOT APPLICABLE | NOT APPLICABLE
6 | CONTRACT AWARD FOR THE SUPPLY OF COMPUTER CONSUMABLES |  | TENDER BOARD | TENDERING | 2014-05-08 |  | 2600454 | NOT APPLICABLE | NOT APPLICABLE | YES | REDWINGS NIG LTD | 2014-10-14 | 2158905 | 2 WEEKS | NOT APPLICABLE | 2158905 | 2014-10-28 | Completed | 100% | NOT APPLICABLE | NOT APPLICABLE
7 | CONTRACT AWARD FOR THE SUPPLY OF COMPUTERS AND ACCESSORIES |  | TENDER BOARD | TENDERING | 2014-05-08 |  | 4121110.27 | NOT APPLICABLE | NOT APPLICABLE | YES | REDWINGS NIG LTD | 2014-10-08 | 3825150 | 2 WEEKS | NOT APPLICABLE | 3825150 | 2014-10-22 | Completed | 100% | NOT APPLICABLE | NOT APPLICABLE
8 | CONTRACT AWARD FOR THE SUPPLY OF OF AN OFFICIAL VEHICLE (TOYOTA AVENSUS) TO PPPRA |  | TENDER BOARD |  |  |  | 10020134 | NOT APPLICABLE | NOT APPLICABLE | YES | LANRE SHITU MOTORS NIG LTD | 2014-10-08 | 9889000 | 3 WEEKS | NOT APPLICABLE | 9889000 | 2014-10-29 | Completed | 100% | NOT APPLICABLE | NOT APPLICABLE
9 | RENEWAL OF CONTRACT FOR INTEGRATED SOLUTIONS FOR ICT INFRASTRUCTURE AND ICT STAFF CAPACITY DEVELOPMENT |  | TENDER BOARD | TENDERING | 2015-01-08 |  | 27115465.5 | NOT APPLICABLE | NOT APPLICABLE | YES | MANAGEMENT EDGE LIMITED | 2014-10-08 | 26160465.6 | 2 MONTHS | NOT APPLICABLE | 26160465.6 | 2014-12-08 | Completed | 100% | NOT APPLICABLE | NOT APPLICABLE
10 | RENEWAL OF CONTRACT FOR INTEGRATED SOLUTIONS FOR ICT INFRASTRUCTURE AND ICT STAFF CAPACITY DEVELOPMENT |  | TENDER BOARD | TENDERING | 2015-01-12 |  | 27115465.5 | NOT APPLICABLE | NOT APPLICABLE | YES | MANAGEMENT EDGE LIMITED | 2014-10-10 | 26160465.6 | 2 MONTHS | NOT APPLICABLE | 26160465.6 | 2014-12-12 | Completed | 100% | NOT APPLICABLE | NOT APPLICABLE
11 | CONTRACT AWARD FOR THE RECONSTRUCTION OF THE PPPRA'S WEBSITE |  | TENDER BOARD | TENDERING | 2015-06-01 |  | 2800435 | NOT APPLICABLE | NOT APPLICABLE | YES | ALMAT ENGINEERING LTD | 2014-10-30 | 2720000 | 6 MONTHS | NOT APPLICABLE | 2720000 | 2015-04-30 | Completed | 100% | NOT APPLICABLE | NOT APPLICABLE
12 | CONTRACT AWARD FOR THE 2014 SALLAH GIFTS FOR SOME STAKEHOLDER'S OF THE AGENCY |  | TENDER BOARD | SELECTIVE |  |  | 7002105 | NOT APPLICABLE | NOT APPLICABLE | YES | HALIWUKS ENTERPRISE | 2014-09-30 | 6904050 | 1 WEEK | NOT APPLICABLE | 6904050 | 2014-10-06 | Completed | 100% | NOT APPLICABLE | NOT APPLICABLE
13 | CONTRACT AWARD FOR THE 2014 CHRISTMAS GIFTS FOR SOME STAKEHOLDER'S OF THE AGENCY |  | TENDER BOARD | SELECTIVE |  |  | 13230590 | NOT APPLICABLE | NOT APPLICABLE | YES | HALIWUKS ENTERPRISE | 2014-12-17 | 13051950 | 1 WEEK | NOT APPLICABLE | 13051950 | 2014-12-24 | Completed | 100% | NOT APPLICABLE | NOT APPLICABLE
14 | RENEWAL OF LIFT MAINTENANCE CONTRACT WITH CFAO EQUIPMENT NIGERIA LIMITED |  | TENDER BOARD | RENEWAL |  |  | 4151956 | NOT APPLICABLE | NOT APPLICABLE | YES | CFAO EQUIPMENT NIG LTD | 2014-10-30 | 4051555.2 | 1 YEAR | NOT APPLICABLE | 4051555 |  | Completed | 100% | NOT APPLICABLE | NOT APPLICABLE
15 | EXTENSION OF CONTRACT BETWEEN TSY-LIMITED AND PPPRA |  | TENDER BOARD | RENEWAL |  |  | 1528740 | NOT APPLICABLE | NOT APPLICABLE | YES | TSY LTD | 2014-10-30 | 1347000 | 8 MONTHS | NOT APPLICABLE | 1347000 |  | Completed | 100% | NOT APPLICABLE | NOT APPLICABLE
16 | CONTRACT AWARD FOR COMBINED INSURANCE POLICY BETWEEN STANDARD ALLIANCE INSURANCE PLC AND PPPRA |  | TENDER BOARD | RENEWAL |  |  | 61672433.75 | NOT APPLICABLE | NOT APPLICABLE | YES | STANDARD ALLIANCE INSURANCE PLC |  | 33710993.96 | 1 YEAR | NOT APPLICABLE | 33710993.96 |  | Completed | 100% | NOT APPLICABLE | NOT APPLICABLE
17 | RENEWAL OF CLEANING SERVICES CONTRACT WITH KLEENOL NIGERIA LIMITED |  | TENDER BOARD | RENEWAL |  |  | 12000000 | NOT APPLICABLE | NOT APPLICABLE | YES | KLEENOL NIG LTD |  | 10795104 | 1 YEAR | NOT APPLICABLE | 10795104 |  | Completed | 100% | NOT APPLICABLE | NOT APPLICABLE
18 | RENEWAL OF MAINTENANCE OF A GENERATOR CONTRACT WITH CUMMINS WEST AFRICA LIMITED (HEADOFFICE) |  | TENDER BOARD | RENEWAL |  |  | 5459344.45 | NOT APPLICABLE | NOT APPLICABLE | YES | CUMMINS WEST AFRICA LTD |  | 3963643.4 | 30 DAYS | NOT APPLICABLE | 3963643.4 |  | Completed | 100% | NOT APPLICABLE | NOT APPLICABLE
19 | RENEWAL OF MAINTENANCE OF A GENERATOR CONTRACT WITH JMG LIMITED (PH ZONAL OFFICE) |  | TENDER BOARD | TENDERING |  |  | 300125 | NOT APPLICABLE | NOT APPLICABLE | YES | JMG LTD |  | 241605 | 1 YEAR | NOT APPLICABLE | 241605 |  | Completed | 100% | NOT APPLICABLE | NOT APPLICABLE
20 | RENEWAL OF SECURITY GUARDS CONTRACT WITH KINGS GUARDS NIGERIA LIMITED |  | TENDER BOARD | RENEWAL |  |  | 30234730.9 | NOT APPLICABLE | NOT APPLICABLE | YES | KINGS GUARD |  | 18660000 | 1 YEAR | NOT APPLICABLE | 18660000 |  | Completed | 100% | NOT APPLICABLE | NOT APPLICABLE
21 | CONTRACT AWARD FOR THE INSTALLATION OF CYBEROAM NETWORK SECURITY |  | TENDER BOARD | TENDERING | 2014-03-26 |  | 2151031 | NOT APPLICABLE | NOT APPLICABLE | YES | ELECTRONET NIG LTD | 2014-10-10 | 2101061 | 2 MONTHS | NOT APPLICABLE | 2101061 | 2014-12-10 | Completed | 100% | NOT APPLICABLE | NOT APPLICABLE
| TOTAL | [11 empty] | 270984820.26

## NITDA
PROCUREMENT RECORDS 2014
PROCURING ENTITY (MDA) : |  | NATIONAL INFORMATION TECHNOLOGY DEVELOPMENT AGENCY (NITDA)
MINISTRY : |  | FEDERAL MINISTRY OF COMMUNICATION TECHNOLOGY
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [8 empty] | CONTRACT AWARD |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY TB | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/06/2015 (NGN) | PROJECT STATUS | % OF COMPLETION AS AT 31/06/2015 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | UPGRADE OF CISCO REGIONAL ACADEMY/MULTI-MEDIA TRAINING CENTRE TO A FULL-FLEDGED NITDA ACADEMY | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 50000000 | 16th December, 2014 | 11th December, 2014 | AS Technologies, TF3, 3rd Floor, Metro Plaza. Abuja. | May 05,2015 | 45547500 |  |  |  |  | None | 0
2 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | ILAMOSI GLOBAL RESOURCES NIGERIA LIMITED 20 IBM Haruna Street, Utako, Abuja. 09034965842,08030308862 | 17th December, 2014 | 24000000 | 23/2/2015 | 22,800,000.00 | COMPLETED | 100% | None | 0
3 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | AM-PM GLOBAL NETWORK LIMITED 10 Durban Street, Wuse 2, Abuja. 08036305762. | 17th December, 2014 | 24000000 | 20/2/2015 | 3,600,000.00 | COMPLETED | 100% | None | 0
4 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | BELSUN & HISS NIGERIA LIMITED Block E, Flat 6, Hillview estate, Gaduwa District, Abuja.08036308762 | 16th December, 2014 | 24000000 | 20/2/2015 | 22,800,000.00 | COMPLETED | 100% | None | 0
5 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | PASTURAGE VERT LIMITED 1 Tigris Close, Imanyi Estate, Maitama, Abuja | 17th December, 2014 | 24000000 | 2015-12-02 | 22,800,000.00 | COMPLETED | 100% | None | 0
6 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | EURORICA CONCEPT LIMITED Plot 213a, Muri-Okunola Street, Victoria Island, Lagos State | 16th December, 2014 | 24000000 | 2015-12-02 | 22,800,000.00 | COMPLETED | 100% | None | 0
7 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | MAGEL RESORT LIMITED 30 Emoyal Street, Port Harcourt, Rivers State. | 16th December, 2014 | 24000000 | 2015-12-02 | 22,800,000.00 | COMPLETED | 100% | None | 0
8 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | MABELT CONSTRUCTION COMPANY LIMITED 30 Emoyal Street, Port Harcourt, Rivers State | 16th December, 2014 | 24000000 | 2015-12-02 | 22,800,000.00 | COMPLETED | 100% | None | 0
9 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | COBASI INTEGRATED SERVICES LIMITED No 14, Abekuta Street, Area 8, Garki, Abuja. 08061377287,08066307300 | 17th December, 2014 | 24000000 | 20/2/2015 | 22,800,000.00 | COMPLETED | 100% | None | 0
10 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | STAR POINT CONSTRUCTION COMPANY LIMITED 13 Chuba Okadigbo Street, Gudu, Abuja. | 17th December, 2014 | 24000000 | 20/2/2015 | 3,600,000.00 | COMPLETED | 100% | None | 0
11 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | SYSNET LIMITED Plot 3, Agbeke Balogun Close, Off Church Street, Agidinge, Ikeja, Lagos State. 08033192098. | 17th December, 2014 | 24000000 | 14/4/2015 | 3,600,000.00 | WORK IN PROGESS | 15% | None | 0
12 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | SWITCH TOWERS INTERNATIONAL LIMITED 4 Hillside Estate, Gwarinpa.Abuja.07068628328,08035535132 | 17th December, 2014 | 24000000 |  | 22,800,000.00 | COMPLETED | 100% | None | 0
13 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | PEFGAN NIGERIA LIMITED 5B Edward Nnaji Street, New Heaven, Enugu. | 17th December, 2014 | 24000000 | 20/2/2015 | 3,600,000.00 | COMPLETED | 100% | None | 0
14 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | PABROE SYNERGY LIMITED | 17th December, 2014 | 24000000 |  | 22,800,000.00 | COMPLETED | 100% | None | 0
15 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | THREE FAVOURS CONSTRUCTION COMPANY LIMITED 22 GRA West Enugu, Enugu State. | 17th December, 2014 | 24000000 | 20/2/2015 | 3,600,000.00 | COMPLETED | 100% | None | 0
16 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | PASTURAGE VERT LIMITED 1 Tigris Close, Imanyi Estate, Maitama, Abuja | 16th December, 2014 | 24000000 | 2015-12-02 | 22,800,000.00 | COMPLETED | 100% | None | 0
17 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | EURORICA CONCEPT LIMITED Plot 213a, Muri-Okunola Street, Victoria Island, Lagos State | 16th December, 2014 | 24000000 | 2015-12-02 | 22,800,000.00 | COMPLETED | 100% | None | 0
18 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | MAGEL RESORT LIMITED 30 Emoyal Street, Port Harcourt, Rivers State. | 16th December, 2014 | 24000000 | 2015-12-02 | 22,800,000.00 | COMPLETED | 100% | None | 0
19 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | MABELT CONSTRUCTION COMPANY LIMITED 30 Emoyal Street, Port Harcourt, Rivers State | 16th December, 2014 | 24000000 | 2015-12-02 | 22,800,000.00 | COMPLETED | 100% | None | 0
20 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | TERRY-TONYE VENTURE House 19, 1a Road, FHA Lugbe, Abuja. 08063958054. | 17th December, 2014 | 24000000 | 27/2/2015 | 22,800,000.00 | COMPLETED | 100% | None | 0
21 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | MATS MULTI RESOURCES LIMITED 49 Transformer Road, Agudama, Yenagoa, Bayelsa State. 08130336011. | 17th December, 2014 | 24000000 | 27/2/2015 | 22,800,000.00 | COMPLETED | 100% | None | 0
22 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | DSJ INVESTMENT LIMITED Plot 36, Ibaka Street, TMC Estate, Port-Harcourt. Rivres State. 07038675613. | 17th December, 2014 | 24000000 |  | 22,800,000.00 | COMPLETED | 100% | None | 0
23 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | EMICO INTERNATIONAL LIMITED Block 5, Flat 7, Garborone Street, Wuse Zone 2, Abuja. 08032868560. | 17th December, 2014 | 24000000 | 20/2/2015 | 22,800,000.00 | COMPLETED | 100% | None | 0
24 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | KRUSH CONSTRUCTION LIMITED Plot 148, 3rd Avenue, Gwarimpa 08186881461 | 17th December, 2014 | 24000000 |  | 22,800,000.00 | COMPLETED | 100% | None | 0
25 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | INTERMEL SOLUTION LIMITED Suite 36 A & b, Maitama Shopping Complex, 5/7 Limpopo Street, Maitama, Abuja. 08036200946. | 17th December, 2014 | 24000000 | 2015-08-03 | 22,800,000.00 | COMPLETED | 100% | None | 0
26 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | PISL-PULOLGBOGI SERVICES LIMITED E300 Ikota Shopping Complex, VGC Lekki, Lagos. | 17th December, 2014 | 24000000 |  | 22,800,000.00 | COMPLETED | 100% | None | 0
27 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | ZINOX TECHOLOGIES LIMITED 20, Port-Harcourt Crescent, Off Gimbiya Street, Area 11, Garki Abuja. 08030773454. | 17th December, 2014 | 24000000 | 2015-01-04 | 3,600,000.00 | WORK IN PROGESS | 85% | None | 0
28 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | KEAP AND COMPANY LIMITED No 633 Akin Adeshola Street, Victoria Island, Lagos. 08032921022. | 17th December, 2014 | 24000000 | 24/2/2015 | 22,800,000.00 | COMPLETED | 100% | None | 0
29 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | THEREMOS INTERNATIONAL LIMITED 33 Parakou Crescent, Wuse 11, Abuja. 07038675613,08036518086 | 17th December, 2014 | 24000000 |  |  | COMPLETED | 100% | None | 0
30 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | PASTURAGE VERT LIMITED 1 Tigris Close, Imanyi Estate, Maitama, Abuja | 16th December, 2014 | 24000000 | 2015-12-02 | 22,800,000.00 | COMPLETED | 100% | None | 0
31 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | EURORICA CONCEPT LIMITED Plot 213a, Muri-Okunola Street, Victoria Island, Lagos State | 16th December, 2014 | 24000000 | 2015-12-02 | 22,800,000.00 | COMPLETED | 100% | None | 0
32 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | MAGEL RESORT LIMITED 30 Emoyal Street, Port Harcourt, Rivers State. | 16th December, 2014 | 24000000 | 2015-12-02 | 22,800,000.00 | COMPLETED | 100% | None | 0
33 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | MABELT CONSTRUCTION COMPANY LIMITED 30 Emoyal Street, Port Harcourt, Rivers State | 16th December, 2014 | 24000000 | 2015-12-02 | 22,800,000.00 | COMPLETED | 100% | None | 0
34 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | EXIT 40 NIGERIA LIMITED No 7 Baltic Crescent, maitama, Abuja. | 17th December, 2014 | 24000000 | 26/1/2015 | 22,800,000.00 | COMPLETED | 100% | None | 0
35 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | LIZTOM NIGERIA LIMITED Block 13, Apartment 14, Lukulu Street, Zone 3, Wuse, Abuja. | 17th December, 2014 | 24000000 | 26/1/2015 | 22,800,000.00 | COMPLETED | 100% | None | 0
36 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | OMADEM INT. NETWORK LIMITED Suite 11 and 12 Mangal Plaza, Area 11, Abuja. | 17th December, 2014 | 24000000 | 26/1/2015 | 22,800,000.00 | COMPLETED | 100% | None | 0
37 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | OPEGLO CONSULT NIGERIA LIMITED Block 7, Flat 17, Mano Street, Off Lukulu Street, Zone 3, Abuja. 08033164294. | 17th December, 2014 | 24000000 |  | 22,800,000.00 | COMPLETED | 100% | None | 0
38 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | VISION MULTIMEDIA PROJECT LIMITED Suite 37,Mega Plaza Oni and Sons, Ring Road, Ibadan. 08033164294 | 17th December, 2014 | 24000000 |  | 22,800,000.00 | COMPLETED | 100% | None | 0
39 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | PASTURAGE VERT LIMITED 1 Tigris Close, Imanyi Estate, Maitama, Abuja | 16th December, 2014 | 24000000 | 26/1/2015 | 22,800,000.00 | COMPLETED | 100% | None | 0
40 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | EURORICA CONCEPT LIMITED Plot 213a, Muri-Okunola Street, Victoria Island, Lagos State | 16th December, 2014 | 24000000 | 26/1/2015 | 22,800,000.00 | COMPLETED | 100% | None | 0
41 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | MAGEL RESORT LIMITED 30 Emoyal Street, Port Harcourt, Rivers State. | 16th December, 2014 | 24000000 | 26/1/2015 | 22,800,000.00 | COMPLETED | 100% | None | 0
42 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | MABELT CONSTRUCTION COMPANY LIMITED 30 Emoyal Street, Port Harcourt, Rivers State | 16th December, 2014 | 24000000 | 26/1/2015 | 22,800,000.00 | COMPLETED | 100% | None | 0
43 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | BUSINESS COMMUNICATION NIGERIA LIMITED Horizon Plaza, Plot 2420, Kashim Ibrahim way, off Herbert Macaulay way, Wuse, Abuja. 08033164294. | 17th December, 2014 | 24000000 | 26/1/2015 | 22,800,000.00 | COMPLETED | 100% | None | 0
44 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | MAITOP GLOBAL LINKS NIGERIA LIMITED 1 Block 1, Shop 4, NYSC Close, Area 3, Garki, Abuja. 08033164294. | 17th December, 2014 | 24000000 | 26/1/2015 | 22,800,000.00 | COMPLETED | 100% | None | 0
45 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | Waves Communication Limited No 7 Baltic Crescent, Maitama, Abuja | 17th December, 2014 | 24000000 | 26/1/2015 | 22,800,000.00 | COMPLETED | 100% | None | 0
46 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | MOXO PROPERTY DEVELOPMENT COMPANY LIMITED 74B Norman Williams Street, S.W Ikoyi, Lagos. 08033164294. | 17th December, 2014 | 24000000 | 26/1/2015 | 22,800,000.00 | COMPLETED | 100% | None | 0
47 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | PASTURAGE VERT LIMITED 1 Tigris Close, Imanyi Estate, Maitama, Abuja | 16th December, 2014 | 24000000 | 26/1/2015 | 22,800,000.00 | COMPLETED | 100% | None | 0
48 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | EURORICA CONCEPT LIMITED Plot 213a, Muri-Okunola Street, Victoria Island, Lagos State | 16th December, 2014 | 24000000 | 26/1/2015 | 22,800,000.00 | COMPLETED | 100% | None | 0
49 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | MAGEL RESORT LIMITED 30 Emoyal Street, Port Harcourt, Rivers State. | 16th December, 2014 | 24000000 | 26/1/2015 | 22,800,000.00 | COMPLETED | 100% | None | 0
50 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | MABELT CONSTRUCTION COMPANY LIMITED 30 Emoyal Street, Port Harcourt, Rivers State | 16th December, 2014 | 24000000 | 26/1/2015 | 22,800,000.00 | COMPLETED | 100% | None | 0
51 | ESTABLISHMENT OF KNOWLEDGE ACCESS VENUE (KAV) WITH INTERNET BANDWIDTH | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 24000000 | 16th December, 2014 | 11th December, 2014 | THREE FAVOURS CONSTRUCTION COMPANY 22 GRA, West Enugu, Enugu. | 17th December, 2014 | 24000000 | 20/2/2015 | 3,600,000.00 | COMPLETED | 100% | None | 0
52 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | APET VENTURES LIMITED 253 Mbiama/Yenagoa Road, Opp NDDC, Amarata, Bayelsa State.08036679428 | 17th December, 2014 | 4500000 |  |  | COMPLETED | 100% | None | 0
53 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | ADVANCE DATA SERVICES LIMITED 34 Usuma Street, Maitama, Abuja. 08059585486. | 17th December, 2014 | 4500000 |  | 4500000 | COMPLETED | 100% | None | 0
54 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | Seamark Gold IT Limited, Plot 873 Shetima Mungora Crescent, Behind Julius Berger, Utako Abuja. | 17th December, 2014 | 4500000 |  |  | WORK IN PROGESS | 15% | None | 0
| E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | BIBI SHOKAARE NIGERIA LIMITED No 1 Orupabo Lane, Marine Base Estate, Port-Harcourt, Rivers State. 08079872255. | 17th December, 2014 | 4500000 |  |  | COMPLETED | 100% | None | 0
55 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | KOLUMBI INN LIMITED No 10B Owen Crescent off ladoke, Akintola Bonaval, Abuja. 08035388485. | 17th December, 2014 | 4500000 |  |  | COMPLETED | 100% | None | 0
56 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | SQUIRREL MULTI-SERVICES Shop B10 Sherif Plaza, Aminu Kano Crescent ,Wuse 11,abuja. 08032905422 | 17th December, 2014 | 4500000 |  |  | COMPLETED | 100% | None | 0
57 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | ADVANCE DATA SERVICES LIMITED 34 Usuma Street, Maitama, Abuja. 08059585486. | 17th December, 2014 | 4500000 |  | 4500000 | COMPLETED | 100% | None | 0
58 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | HASOB INEGRATED SERVICES Bassan Plaza Central Business District, Abuja. 07063321242. | 17th December, 2014 | 4500000 | 2015-01-04 | 675,000.00 | WORK IN PROGESS | 15% | None | 0
59 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | Ctrend Links Limited, Plot 740 Obafemi Awolowo Way, B16 TFIN Plaza, Utako, Abuja. | 17th December, 2014 | 4500000 |  |  | WORK IN PROGESS | 15% | None | 0
60 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | ANGEL KELV NIGERIA LIMITED No 55, Church Hill Road, Port-Harcourt, Rivers State. 08036308762. | 17th December, 2014 | 4500000 |  |  | COMPLETED | 100% | None | 0
61 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | CEDEE INTERNATIONAL COMPANY No 1 Orupabo Lane, Marine Base Estate, Port-Harcourt, Rivers State. 08033112539. | 17th December, 2014 | 4500000 |  |  | COMPLETED | 100% | None | 0
62 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | Seamark Gold IT Limited, Plot 873 Shetima Mungora Crescent, Behind Julius Berger, Utako Abuja. | 17th December, 2014 | 4500000 |  |  | WORK IN PROGESS | 15% | None | 0
63 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | ADVANCE DATA SERVICES LIMITED 34 Usuma Street, Maitama, Abuja. 08059585486. | 17th December, 2014 | 4500000 |  | 4,500,000.00 | COMPLETED | 100% | None | 0
64 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | GG AND MP INTEGRATED CONCEPT No 10 Durban Street,Wuse 2,Abuja. 08036208762 | 17th December, 2014 | 4500000 |  |  | COMPLETED | 100% | None | 0
65 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | NES INTERNATIONAL LIMITED 23 Suleiman Barau, Villa Estate,Abuja.08030857146 | 17th December, 2014 | 4500000 | 2015-09-03 | 675,000.00 | SOME ISSUE TO RESOLVE |  | None | 0
| E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | MERIT BRANZUK ENERGY LIMITED 11 Maotse Tung, Off Jimmy Carter, Asokoro, Abuja. 08051925009. | 17th December, 2014 | 4500000 |  |  | COMPLETED | 100% | None | 0
66 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | PIKACHI INTEGRATED CONCEPT Plot 904 Cadestral Zone B5, Ekukkunam Street, Utako District FCT, Abuja. 08035603434 | 17th December, 2014 | 4500000 |  |  | COMPLETED | 100% | None | 0
67 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | ADVANCE DATA SERVICES LIMITED 34 Usuma Street, Maitama, Abuja. 08059585486. | 17th December, 2014 | 4500000 |  | 4,500,000.00 | COMPLETED | 100% | None | 0
68 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | MILLENIUM INTEGRATED LIMITED | 17th December, 2014 | 4500000 |  |  | WORK IN PROGESS | 15% | None | 0
69 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | ADVANCE DATA SERVICES LIMITED 34 Usuma Street, Maitama, Abuja. 08059585486. | 17th December, 2014 | 4500000 |  | 4,500,000.00 | COMPLETED | 100% | None | 0
70 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | ARIBOSOR VENTURES LIMITED No 9 Police Road, Phase 4, Kubwa, Abuja. 08083244642. | 17th December, 2014 | 4500000 | 24/2/2015 | 4,500,000.00 | WORK IN PROGESS | 15% | None | 0
71 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | K AND M INDUSTRIES LIMITED 16 Potts Johnson Street, Port-Harcourt, Rivers State. | 17th December, 2014 | 4500000 | 25/3/2015 | 4,500,000.00 | COMPLETED | 100% | None | 0
72 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | ADVANCE DATA SERVICES LIMITED 34 Usuma Street, Maitama, Abuja. 08059585486. | 17th December, 2014 | 4500000 |  | 4,500,000.00 | COMPLETED | 100% | None | 0
73 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | PASSION 2 PROFIT RESOURCES LIMITED 30 Stadium Road, Port-Harcourt, Rivers State. 08098053511. | 17th December, 2014 | 4500000 |  |  | COMPLETED | 100% | None | 0
74 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | SAAT CONSULTING 1 Rimi Street Maitama, Abuja. | 17th December, 2014 | 4500000 |  |  | COMPLETED | 100% | None | 0
75 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | Seamark Gold IT Limited, Plot 873 Shetima Mungora Crescent, Behind Julius Berger, Utako Abuja. | 17th December, 2014 | 4500000 |  |  | WORK IN PROGESS | 15% | None | 0
76 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | WILFRED ENGINEERING LIMITED 3 Amaging Grace plaza Bayelsa Court Faces Estate, Abuja. 08075806111 | 17th December, 2014 | 4500000 |  |  | COMPLETED | 100% | None | 0
77 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | ADVANCE DATA SERVICES LIMITED 34 Usuma Street, Maitama, Abuja. 08059585486. | 17th December, 2014 | 4500000 |  | 4,500,000.00 | COMPLETED | 100% | None | 0
78 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | ZOUDON GLOBAL SERVICES LIMITED 2, Bori Street Port-Harcourt. 07038675613. | 17th December, 2014 | 4500000 |  |  | COMPLETED | 100% | None | 0
79 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | ADVANCE DATA SERVICES LIMITED 34 Usuma Street, Maitama, Abuja. 08059585486. | 17th December, 2014 | 4500000 |  | 4,500,000.00 | COMPLETED | 100% | None | 0
80 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | WEBDIGIT MULTICOMMUNICATIONS LIMITED 3rd Floor, AP Plaza, Adetokunbo Ademola Crescent, Wuse 11, Abuja. 08036518086. | 17th December, 2014 | 4500000 |  | 4,500,000.00 | COMPLETED | 100% | None | 0
81 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | HALLOWGATE TELECOM SERVICES CO7 International Plaza, Wuse Zone 3, Abuja. 08075806111. | 17th December, 2014 | 4500000 |  |  | COMPLETED | 100% | None | 0
82 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | ROPSON SYSTEM LIMITED No 32, Adeniyi Close, Ijoka Road, Akure, Ondo State. 0803313229. | 17th December, 2014 | 4500000 |  |  | COMPLETED | 100% | None | 0
83 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | ADVANCE DATA SERVICES LIMITED 34 Usuma Street, Maitama, Abuja. 08059585486. | 17th December, 2014 | 4500000 |  | 4,500,000.00 | COMPLETED | 100% | None | 0
84 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | REALTECH COMPUTERS LIMITED Suite 1 and 2 First Floor Matz Plaza Junction Road, Kaduna State. | 17th December, 2014 | 4500000 |  |  | COMPLETED | 100% | None | 0
85 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | ADVANCE DATA SERVICES LIMITED 34 Usuma Street, Maitama, Abuja. 08059585486. | 17th December, 2014 | 4500000 |  | 4,500,000.00 | COMPLETED | 100% | None | 0
86 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | ROYAL PEAK LIMITED No 18, Ascon Camp, Lower Usman Dan, Abuja. 08053877799. | 17th December, 2014 | 4500000 |  |  | COMPLETED | 10% | None | 0
| E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | CLAXO GLOBAL LIMITED No 10B Owen Crescent Off Ladoke, Akintola Bonaval, Abuja. 08035388485. | 17th December, 2014 | 4500000 |  |  | WORK IN PROGESS | 15% | None | 0
87 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | ADVANCE DATA SERVICES LIMITED 34 Usuma Street, Maitama, Abuja. 08059585486. | 17th December, 2014 | 4500000 |  | 4,500,000.00 | COMPLETED | 100% | None | 0
88 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | NECH AND WORLD LIMITED No 2 Masuku Close, Off Durban Street, Ademola Adetokunbo Crescent, Wuse 11, Abuja. 07059055861. | 17th December, 2014 | 4500000 |  |  | WORK IN PROGESS | 15% | None | 0
89 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | ADVANCE DATA SERVICES LIMITED 34 Usuma Street, Maitama, Abuja. 08059585486. | 17th December, 2014 | 4500000 |  | 4,500,000.00 | COMPLETED | 100% | None | 0
90 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | NECH AND WORLD LIMITED No 2 Masuku Close, Off Durban Street, Ademola Adetokunbo Crescent, Wuse 11, Abuja. 07059055861. | 17th December, 2014 | 4500000 | 2015-05-03 | 675,000.00 | WORK IN PROGESS | 15% | None | 0
91 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | Ctrend Links Limited, Plot 740 Obafemi Awolowo Way, B16 TFIN Plaza, Utako, Abuja. | 17th December, 2014 | 4500000 |  |  | WORK IN PROGESS | 15% | None | 0
92 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | MOB AND NECH CONSTRUCTION NIG LIMITED No 2 Masuku Close, Off Durban Street, Ademole Adetokunbo Crescent, Wuse 11,abuja 07059055861 | 17th December, 2014 | 4500000 |  | 675,000.00 | WORK IN PROGESS | 15% | None | 0
93 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | ADVANCE DATA SERVICES LIMITED 34 Usuma Street, Maitama, Abuja. 08059585486. | 17th December, 2014 | 4500000 |  | 4500000 | COMPLETED | 100% | None | 0
94 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | MACDANPEE GLOBAL NIGERIA LIMITED No 4, Lagos Close, Gwarinpa Estate, Abuja. 08133715990. | 17th December, 2014 | 4500000 |  | 4500000 | COMPLETED | 100% | None | 0
95 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | MOB AND NECH CONSTRUCTION NIG LIMITED No 2 Masuku Close, Off Durban Street, Ademole Adetokunbo Crescent, Wuse 11,abuja 07059055861 | 17th December, 2014 | 4500000 | 2015-05-03 | 675,000.00 |  |  | None | 0
96 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | ADVANCE DATA SERVICES LIMITED 34 Usuma Street, Maitama, Abuja. 08059585486. | 17th December, 2014 | 4500000 |  | 4500000 | COMPLETED | 100% | None | 0
97 | E-LEARNING SOLUTION FOR KNOWLEDGE ACCESS VENUES (KAV) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 4500000 | 16th December, 2014 | 11th December, 2014 | ADVANCE DATA SERVICES LIMITED 34 Usuma Street, Maitama, Abuja. 08059585486. | 17th December, 2014 | 4500000 |  | 4500000 | COMPLETED | 100% | None | 0
98 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | TONIRISA INTERNATIONAL LIMITED No 13 Constitution Avenue, Gaduwa Estate, Apo, Abuja.08062651015 | 17th December, 2014 | 15000000 | 13/2/2015 | 14,250,000.00 | COMPLETED | 100% | None | 0
99 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | PASTURAGE VERT LIMITED 1 Tigris Close, Imanyi Estate, Maitama, Abuja | 17th December, 2014 | 15000000 | 2015-12-02 | 14,250,000.00 | COMPLETED | 100% | None | 0
100 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | EURORICA CONCEPT LIMITED Plot 213a, Muri-Okunola Street, Victoria Island, Lagos State | 17th December, 2014 | 15000000 | 2015-12-02 | 14,250,000.00 | COMPLETED | 100% | None | 0
101 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | MAGEL RESORT LIMITED 30 Emoyal Street, Port Harcourt, Rivers State. | 17th December, 2014 | 15000000 | 2015-12-02 | 14,250,000.00 | COMPLETED | 100% | None | 0
102 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | MABELT CONSTRUCTION COMPANY LIMITED 30 Emoyal Street, Port Harcourt, Rivers State | 17th December, 2014 | 15000000 | 2015-12-02 | 14,250,000.00 | COMPLETED | 100% | None | 0
103 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | AM-PM GLOBAL NETWORK LIMITED 10 Duban Street, Wuse 2, Abuja. 08036308762, 08035239938 | 17th December, 2014 | 15000000 | 23/2/2015 | 14,250,000.00 | COMPLETED | 100% | None | 0
104 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | BERGHAUS LIMITED 32A Jimmy Carter Street, Asokoro, Abuja. 07051207586. | 17th December, 2014 | 15000000 | 24/2/2015 | 2,250,000.00 | WORK IN PROGESS | 15% | None | 0
105 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | MICRO PRODUCTS LIMITED 5A Abdou Diouf Street, Asokoro, Abuja. 07051207586. | 17th December, 2014 | 15000000 | 27/2/2015 | 2,250,000.00 | WORK IN PROGESS | 15% | None | 0
106 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | MARV-YOBS NIGERIA LIMITED | 17th December, 2014 | 15000000 |  | 14,250,000.00 | COMPLETED | 100% | None | 0
107 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | AERO SYSTEMS AND TECHNOLOGIES LIMITED 7 Durban Street, Wuse 2, Abuja 08066020333 | 17th December, 2014 | 15000000 |  | 14,250,000.00 | COMPLETED | 100% | None | 0
108 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | PASTURAGE VERT LIMITED 1 Tigris Close, Imanyi Estate, Maitama, Abuja | 17th December, 2014 | 15000000 | 2015-12-02 | 14,250,000.00 | COMPLETED | 100% | None | 0
109 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | EURORICA CONCEPT LIMITED Plot 213a, Muri-Okunola Street, Victoria Island, Lagos State | 17th December, 2014 | 15000000 | 2015-12-02 | 14,250,000.00 | COMPLETED | 100% | None | 0
110 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | MAGEL RESORT LIMITED 30 Emoyal Street, Port Harcourt, Rivers State. | 17th December, 2014 | 15000000 | 2015-12-02 | 14,250,000.00 | COMPLETED | 100% | None | 0
111 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | MABELT CONSTRUCTION COMPANY LIMITED 30 Emoyal Street, Port Harcourt, Rivers State | 17th December, 2014 | 15000000 | 2015-12-02 | 14,250,000.00 | COMPLETED | 100% | None | 0
112 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | BARKING HAM NIGERIA LIMITED No 20 Malali Low Cost, Kaduna State.08066307300 | 17th December, 2014 | 15000000 |  | 14,250,000.00 | COMPLETED | 100% | None | 0
113 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | TOP CHOICE GLOBAL RESOURCES Shop A1 Area 7, shopping Complex, garki, Auja. 08037973900, 08030308762 | 17th December, 2014 | 15000000 | 20/2/2015 | 14,250,000.00 | COMPLETED | 100% | None | 0
114 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | PASTURAGE VERT LIMITED 1 Tigris Close, Imanyi Estate, Maitama, Abuja | 17th December, 2014 | 15000000 | 2015-12-02 | 14,250,000.00 | COMPLETED | 100% | None | 0
115 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | EURORICA CONCEPT LIMITED Plot 213a, Muri-Okunola Street, Victoria Island, Lagos State | 17th December, 2014 | 15000000 | 2015-12-02 | 14,250,000.00 | COMPLETED | 100% | None | 0
116 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | MAGEL RESORT LIMITED 30 Emoyal Street, Port Harcourt, Rivers State. | 17th December, 2014 | 15000000 | 2015-12-02 | 14,250,000.00 | COMPLETED | 100% | None | 0
117 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | MABELT CONSTRUCTION COMPANY LIMITED 30 Emoyal Street, Port Harcourt, Rivers State | 17th December, 2014 | 15000000 | 2015-12-02 | 14,250,000.00 | COMPLETED | 100% | None | 0
118 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | DIVINE OASIS INTERNATIONAL LIMITED No 2 Rumola Road, Suite 11, Port-Harcourt, Rivers State. 08036308762. | 17th December, 2014 | 15000000 | 20/2/2015 | 14,250,000.00 | COMPLETED | 100% | None | 0
119 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | ISOSCELES LIMITED | 17th December, 2014 | 15000000 | 23/3/2015 | 14,250,000.00 | WORK IN PROGESS | 15% | None | 0
120 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | SEGPAMOR GLOBAL SYNERGY LIMITED Goodluck District, Maitama Extension, Maitama, Abuja. 08033112539. | 17th December, 2014 | 15000000 | 2015-09-03 | 14,250,000.00 | COMPLETED | 100% | None | 0
121 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | PRIVITEK GLOBAL SERVICES LIMITED 80/81 Oba polo, Okrika, Rivers State. 08036741892,08035239938 | 17th December, 2014 | 15000000 | 20/2/2015 | 14,250,000.00 | COMPLETED | 100% | None | 0
122 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | PASTURAGE VERT LIMITED 1 Tigris Close, Imanyi Estate, Maitama, Abuja | 17th December, 2014 | 15000000 | 2015-12-02 | 14,250,000.00 | COMPLETED | 100% | None | 0
123 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | EURORICA CONCEPT LIMITED Plot 213a, Muri-Okunola Street, Victoria Island, Lagos State | 17th December, 2014 | 15000000 | 2015-12-02 | 14,250,000.00 | COMPLETED | 100% | None | 0
124 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | MAGEL RESORT LIMITED 30 Emoyal Street, Port Harcourt, Rivers State. | 17th December, 2014 | 15000000 | 2015-12-02 | 14,250,000.00 | COMPLETED | 100% | None | 0
125 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | MABELT CONSTRUCTION COMPANY LIMITED 30 Emoyal Street, Port Harcourt, Rivers State | 17th December, 2014 | 15000000 | 2015-12-02 | 14,250,000.00 | COMPLETED | 100% | None | 0
126 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | TARIOK NIGERIA LIMITED Plot 125 T.O.S Douglas Crescent ,Opp Games Village Gate, Kaura District, Abuja.08033224331 | 17th December, 2014 | 15000000 | 13/2/2015 | 14,250,000.00 | COMPLETED | 100% | None | 0
127 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | ALAMARTS PRODUCTION LIMITED 74 Bende Street, Port-Harcourt, Rivers State. 08033408976,08031308762 | 17th December, 2014 | 15000000 | 20/2/2015 | 2,250,000.00 | COMPLETED | 100% | None | 0
128 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | GOAL GETTERS LOGISTICS LIMITED House 110, Zone E, Apo Resettlement, Abuja.08085210255 | 17th December, 2014 | 15000000 | 17/2/2015 | 14,250,000.00 | COMPLETED | 100% | None | 0
129 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | CANAIMA INTERNATIONAL LIMITED 6 R.B Dikko Street, Area 11,Garki ,Abuja. 08036214908 | 17th December, 2014 | 15000000 | 13/2/2015 | 14,250,000.00 | COMPLETED | 100% | None | 0
130 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | CROWN AND REED LIMITED No 5 Op Fengesi Road, Utako, Abuja. 08036045972. | 17th December, 2014 | 15000000 | 27/2/2015 | 2,250,000.00 | COMPLETED | 100% | None | 0
131 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | YUJAE NIGERIA LIMITED 18 Jesse Jackson Street, Asokoro, Abuja. 08063363474. | 17th December, 2014 | 15000000 |  |  | WORK IN PROGESS | 15% | None | 0
132 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | NET SOLUTIONS LIMITED 9A Oluwole Street, Lekki Phase 1, Lagos State. 07033318468. | 17th December, 2014 | 15000000 | 27/2/2015 | 2,250,000.00 | WORK IN PROGESS | 15% | None | 0
133 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | PASTURAGE VERT LIMITED 1 Tigris Close, Imanyi Estate, Maitama, Abuja | 17th December, 2014 | 15000000 | 2015-12-02 | 14,250,000.00 | COMPLETED | 100% | None | 0
134 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | EURORICA CONCEPT LIMITED Plot 213a, Muri-Okunola Street, Victoria Island, Lagos State | 17th December, 2014 | 15000000 | 2015-12-02 | 14,250,000.00 | COMPLETED | 100% | None | 0
135 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | MAGEL RESORT LIMITED 30 Emoyal Street, Port Harcourt, Rivers State. | 17th December, 2014 | 15000000 | 2015-12-02 | 14,250,000.00 | COMPLETED | 100% | None | 0
136 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | MABELT CONSTRUCTION COMPANY LIMITED 30 Emoyal Street, Port Harcourt, Rivers State | 17th December, 2014 | 15000000 | 2015-12-02 | 14,250,000.00 | COMPLETED | 100% | None | 0
137 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | OPEGLO CONSULT NIGERIA LIMITED Block 7, Flat 17, Mano Street, Off Lukulu Street, Zone 3, Abuja. 08033164294. | 17th December, 2014 | 15000000 |  | 14,250,000.00 | COMPLETED | 100% | None | 0
138 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | LAVIMO GLOBAL SERVICES LIMITED Suite 125, 2nd Floor Befs Plaza, Abuja. 0816842185 | 17th December, 2014 | 15000000 | 27/2/2015 | 14,250,000.00 | COMPLETED | 100% | None | 0
139 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | BUSINESS COMMUNICATION NIGERIA LIMITED Horizon Plaza, Plot 2420, kashim Ibrahim way, Off Herbert Macaulay way, Wuse, Abuja. 08033164294. | 17th December, 2014 | 15000000 |  | 14,250,000.00 |  |  | None | 0
140 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | DAVDAN MULTICONCEPTS LIMITED No 20 Block T9 Complex, Adetokunbo Ademola Str., Wuse 11, Abuja. 08033164294. | 17th December, 2014 | 15000000 |  | 14,250,000.00 | WORK IN PROGESS | 15% | None | 0
141 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | MENORAH RESOURCES INTERNATIONAL LIMITED Commercial Plot A, 2nd Avenue, Industrial Layout, Agbara, Lagos. 08033164294. | 17th December, 2014 | 15000000 |  | 14,250,000.00 | WORK IN PROGESS | 15% | None | 0
142 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | ALSEIJAZ LIMITED No 9 Hargeysa Street, Zone 5, Abuja. 08093043668. | 17th December, 2014 | 15000000 |  | 14,250,000.00 | COMPLETED | 100% | None | 0
143 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | STAR POINTS CONSTRUCTION COMPANY 13 Chuba Okadigbo Street, Apo Quarters, Gudu District, Abuja. | 17th December, 2014 | 15000000 | 20/2/2015 | 2,250,000.00 | COMPLETED | 100% | None | 0
144 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | DMK GLOBAL ALLIANZE COMPANY LIMITED No 30 Agui Ironsi, Coscharis Estate, Maitama Abuja 08083244642 | 17th December, 2014 | 15000000 | 20/2/2015 | 14,250,000.00 | COMPLETED | 100% | None | 0
145 | COMMUNITY ACCESS CENTERS (CAC) | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 15000000 | 16th December, 2014 | 11th December, 2014 | Vision Multi Media Project Limited Suite 37, Mega Plaza, Oni and Sons ring Road, Ibadan, Oyo State.08033164294 | 17th December, 2014 | 15000000 |  | 14,250,000.00 | COMPLETED | 100% | None | 0
146 | STAKEHOLDER REVIEWS OF MINIMUM STANDARDS ON IT INFRASTRUCTUR, IT IN PUBIC UTILITIES, COMPUTER ASSEMBLY, COMPUTER PRODUCT AND IT IN BUILDING CONSTRUCTION | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 20000000 | 16th December, 2014 | 11th December, 2014 | QUICKENING INTEGRATED SERVICES LIMITED 15, Takwa Crescent, Wuse 11, Abuja. 08069155777. | 17th December, 2014 | 19978000 |  | 19978000 | COMPLETED | 100% | None | 0
147 | IMPLEMENTATION OF REGULAORY GUIDELINES ON IT IN SCHOOLS | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 20000000 | 16th December, 2014 | 11th December, 2014 | QUICKENING INTEGRATED SERVICES LIMITED 15, Takwa Crescent, Wuse 11, Abuja. 08069155777. | 17th December, 2014 | 14550000 |  | 14550000 | COMPLETED | 100% | None | 0
148 | SPECIAL PUBLIC PRIVATE PARTNESHIP (PPP) TELEVISION PROGRAM ON INFORMATION TECHNOLOGY DEVELOPMENT AND INITIATIVES AND POSSIBLE OPPORTUNITIES | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 50000000 | 16th December, 2014 | 11th December, 2014 | CENTRIL MEDIA LIMITED No 14, Thaba Tseka Street, Off Ademola/Adetokunbo Crescent, British Village, Wuse 2, Abuja. 08037517132. | 17th December, 2014 | 47990000 | 2015-08-03 | 28,794,000.00 |  |  | None | 0
149 | PROVISION OF INTERNET BANDWIDTH FOR SUSTAINING EXISTING RITC SITES | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 100000000 | 16th December, 2014 | 11th December, 2014 | GRACELAND GLOBAL LEGENDS LIMITED No 20 Democracy Crescent, Gaduwa Estate, Abuja. 08033310178. | 17th December, 2014 | 98000000 |  | 98000000 |  |  | None | 0
150 | COUNTRYWIDE ICT SECTOR BASED RISK ANALYSIS | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 20000000 | 16th December, 2014 | 11th December, 2014 | SIDMACH TECHNOLOGIES NIGERIA LIMITED 13 Town Planner way Ilepeju, Lagos. | 17th December, 2014 | 19767302.26 |  |  | WORK IN PROGESS | 50% | None | 0
151 | UPGRADE AND MAINTENANCE OF COMPEDIUM OF ICT COMPANIES PORTAL | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 20000000 | 16th December, 2014 | 11th December, 2014 | TINITOP TECHNOLOGIES LIMITED | 17th December, 2014 | 18110000 |  |  |  |  | None | 0
152 | PROVISION OF WIDE AREA NETWORK | Monday, September 8,2014 Dailytrust and The Guardian | N5 Million and above but less than N250 Million | NCB | 21st October,2014 | 2nd November,2014 | 200000000 | 16th December, 2014 | 11th December, 2014 | BRIGHT SUN NETWORKS LIMITED 23 Cairo Street, Wuse 11, Abuja. | 17th December, 2014 | 206250000 | 20/2/2015 | 30,937,500.00 |  |  | None | 0
153 | PROVISION OF WIDE AREA NETWORK | Monday, September 8,2014 Dailytrust and The Guardian | N5 Million and above but less than N250 Million | NCB | 21st October,2014 | 2nd November,2014 | 200000000 | 16th December, 2014 | 11th December, 2014 | QUADSTER NIGERIA LIMITED No 7 Baltic Crescent, off Danube Street, Maitama, Abuja. | 17th December, 2014 | 206250000 | 26/1/2015 | 206250000 |  |  | None | 0
154 | PROVISION OF WIDE AREA NETWORK | Monday, September 8,2014 Dailytrust and The Guardian | N5 Million and above but less than N250 Million | NCB | 21st October,2014 | 2nd November,2014 | 200000000 | 16th December, 2014 | 11th December, 2014 | WAVES COMMUNICATION LIMITED No 7 Baltic Crescent, Maitama, Abuja. | 17th December, 2014 | 206250000 | 26/1/2015 | 206250000 |  |  | None | 0
156 | PROVISION OF WIDE AREA NETWORK | Monday, September 8,2014 Dailytrust and The Guardian | N5 Million and above but less than N250 Million | NCB | 21st October,2014 | 2nd November,2014 | 200000000 | 16th December, 2014 | 11th December, 2014 | MICROBAN STANDARD COMMUNICATIONS LIMITED 39, Usuma Street, Maitama. Abuja. 08093043668. | 17th December, 2014 | 206250000 |  | 206250000 |  |  | None | 0
157 | PROVISION OF WIDE AREA NETWORK | Monday, September 8,2014 Dailytrust and The Guardian | N5 Million and above but less than N250 Million | NCB | 21st October,2014 | 2nd November,2014 | 200000000 | 16th December, 2014 | 11th December, 2014 | SOUTH POINT CONSULTANCY LIMITED No 10 Lobito Crescent, Wuse 11, Abuja. | 17th December, 2014 | 206250000 | 20/2/2015 | 30,937,500.00 |  |  | None | 0
158 | PROVISION OF 2 UNITS OF MULTIPLE USER VIRTUAL LIBRARY | Monday, September 8,2014 Dailytrust and The Guardian | N5 Million and above but less than N250 Million | NCB | 21st October,2014 | 2nd November,2014 | 200000000 | 16th December, 2014 | 11th December, 2014 | WAVES COMMUNICATION LIMITED No 7 Baltic Crescent, Maitama, Abuja. | 17th December, 2014 | 190000000 | 26/1/2015 | 190000000 | COMPLETED | 100% | None | 0
159 | PROVISION OF 2 UNITS OF MULTIPLE USER VIRTUAL LIBRARY | Monday, September 8,2014 Dailytrust and The Guardian | N5 Million and above but less than N250 Million | NCB | 21st October,2014 | 2nd November,2014 | 200000000 | 16th December, 2014 | 11th December, 2014 | THREE FAVOURS CONSTRUCTION COMPANY LIMITED 22 GRA West Enugu, Enugu State. | 17th December, 2014 | 190000000 | 20/2/2015 | 28,500,000.00 | COMPLETED | 100% | None | 0
160 | NITDA PROJECT/PROGRAM MONITORING AND EVALUATION | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 80000000 | 16th December, 2014 | 11th December, 2014 | Tanidom Technical Company Limited No 1 mohamed Kokori Close, Gwarinpa, Abuja.0703142126 | 22nd January,2015 | 78427000 |  | 78427000 | COMPLETED | 100% | None | 0
161 | DEVELOPMENT OF HOLOGRAM AND MACHINE READABLE BARCODE FOR IT PRODUCTS CERTIFICATION | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 20000000 | 16th December, 2014 | 11th December, 2014 | Empirebuilder Technologies Limited 13 Anambra Crescent, Off Nile St, Ministers hill, Maitama, Abuja | 17th December, 2014 | 18900500 |  | 18900500 | COMPLETED | 100% | None | 0
162 | COMPLIANCE FRAMEWORK AND IMPLEMENTATION OF GUIDELINES FOR NIGERIAN CONTENT DEVELOPMENT IN ICT | Monday, September 8,2014 Dailytrust and The Guardian | N2.50 Million and above but lessthan N50 million | NCB | 21st October,2014 | 2nd November,2014 | 50000000 | 16th December, 2014 | 11th December, 2014 | Alteq (ICT) Limited, No 12 Kolda Street, Wuse II. Abuja. | 17th December, 2014 | 48500500 |  | 48, 500,500.00 | COMPLETED | 100% | None | 0
| TOTAL | [10 empty] | 3915973302.26

## OAGOF
PROCUREMENT RECORDS
PROCURING ENTITY (MDA): |  |  |  | OAGF
MINISTRY: |  | FEDERAL MINISTRY OF FINANCE
FINANCIAL YEAR: |  |  | 2014
|  |  |  | BASIC DATA | [8 empty] | CONTRACT AWARD | [5 empty] | CONTRACT IMPLEMENTATION
S/N | CONTRACT | DATE ADVERT | APPROVAL | PROCURE- | BID | BIDS |  | DATE OF | APPROVAL | AWARDED |  | DATE OF | CONTRACT |  | DATE OF | AMOUNT | EXPECTED |  | % OF | DATE OF
| DESCRIPTION | PUBLISHED | THRESHOLD | MENT | OPENING | EVALUATION | BUDGETARY | CERTIFICATION | DATE BY | TO LEAST | CONTRACTOR | CONTRACT | VALUE | CONTRACT | COMMENCEMENT | PAID AS AT | COMPLETION | PROJECT | COMPLETION | VARIATION | VARIATION
|  | AND MEDIA |  | METHOD | DATE | REPORT | PROVISION | OF NO | AO/MTB/ | TENDERER |  | AWARD | (NGN) | PERIOD | (PHYSICAL | 31/12/13 | DATE | STATUS | AT 31/12/13 | APPROVAL | AMOUNT | REMARKS
[6 empty] | DATE | NGN | OBJECTION | FEC | [5 empty] | MOBILISATION) | (NGN) |  |  | (NGN) | IF ANY | (NGN)
1 | Construction | The Nation | [8 empty] | Alliance | 2011-04-07 | N120,555,
| of new FPO | 31/5/11 | MTB | NCB |  |  |  |  | 28/6/11 |  | Development |  | 487.5 | 24 weeks |  | 45175235.23 | 24 weeks |  | 35%
| Gusau | FTJ & L/Ship | [8 empty] | Company
2 | Construction | The Nation | [8 empty] | Coxmartinz
| of new FPO | 31/5/11 | MTB | NCB |  |  |  |  | 28/6/11 |  | Engineerin g | 2011-04-07 | N121,685, | 24 weeks |  | 34288814.45 | 24 weeks |  | 40%
| Uyo | FTJ & L/Ship | [8 empty] | Services |  | 978
3 | Construction | The Nation | [8 empty] | Jamec West
| of new FPO | 31/5/11 | MTB | NCB |  |  |  |  | 28/6/11 |  | Africa Ltd | 2011-04-07 | N121,478, | 24 weeks |  | 12500000 | 24 weeks |  | 65%
| Umuahia | FTJ & L/Ship | [10 empty] | 893.23
4 | Construction | The Nation | [8 empty] | Dogon Ruwa
| of new FPO | 31/5/11 | MTB | NCB |  |  |  |  | 28/6/11 |  | Nig. Ltd | 2011-04-07 | N120,746, | 24 weeks |  | 26112026.46 | 24 weeks |  | 25%
| Bauchi | FTJ & L/Ship | [10 empty] | 843.07
5 | Construction | [9 empty] | Sahab Solid
| of new FPO | 2010-12-07 | MTB | NCB |  |  |  |  | 2010-03-09 |  | Construction | 2010-06-09 | N81,779, | 24 weeks |  | 61117153.05 | 24 weeks |  | 73%
| Lafia | [9 empty] | Ltd |  | 523
6 | Rehabilitation | The Nation | [8 empty] | Kaoldesh
| of FPO Kano | 31/5/11 | MTB | NCB |  |  |  |  | 28/6/11 |  | Nigeria Ltd | 2011-04-07 | N20,102, | 6 weeks |  | 8238262.74 | 6 weeks |  | 95%
|  | FTJ & L/Ship | [10 empty] | 707.01
7 | Rehabilitation | The Nation | [8 empty] | Prestige
| of FPO Dutse | 31/5/2011 | MTB | NCB |  |  |  |  | 28/6/11 |  | Nigeria Ltd | 2011-04-07 | N20,441, | 6 weeks |  | 19243515.91 | 6 weeks |  | 100%
|  | FTJ & L/Ship | [10 empty] | 867.96
8 | Rehabilitation | The Nation | [8 empty] | TAAD
| of FPO Akure | 31/5/2011 | MTB | NCB |  |  |  |  | 28/6/11 |  | Construction | 2011-04-07 | N20,931, | 6 weeks |  | 8363330.27 | 6 weeks |  | 55%
|  | FTJ & L/Ship | [8 empty] | Co. Ltd |  | 823.5
9 | Furnishing of | The Nation | [8 empty] | Timsi Global
| FPO Yenagoa | 31/5/2011 | MTB | NCB |  |  |  |  | 28/6/11 |  | Resources | 2011-04-07 | N17,261, | 3 weeks |  | 9163649.41 | 3 weeks |  | 95%
|  | FTJ & L/Ship | [8 empty] | Ltd |  | 296.5
10 | Provision of | The Nation | [8 empty] | Abumado
| Bore Hole at | Leadership | [8 empty] | Investment
| FPOs Awka, | 31/5/2011 | MTB | NCB |  |  |  |  | 28/6/11 |  | Ltd | 2011-04-07 | N14,450, | 6 weeks |  | 7980000 | 6 weeks |  | 60%
| Calabar and | & FTJ | [10 empty] | 0
Yenagoa
11 | Rehabilitation | [9 empty] | Hollamarc
| of Fence, Gate | [9 empty] | Integrated
| House, and | 31/5/2011 | MTB | NCB |  |  |  |  | 28/6/11 |  | Service | 2011-04-07 | N12,000, | 6 weeks |  | 11399998.98 | 6 weeks |  | 100%
| Kerbs round | [11 empty] | 0
OAGF Block A
12 | Construction | The Nation | [8 empty] | Essence |  | N121,008,
| of new FPO | 25/6/2012 | MTB | NCB | 2012-09-07 |  |  |  | 2012-07-08 |  | Development | 28/8/12 | 150.38 | 32 weeks |  | 66326963.09 | 32 weeks |  | 60%
| Dutse | FTJ & L/Ship | [8 empty] | Company
13 | Upgrading of | [9 empty] | Biyi Concept
| Internal | [9 empty] | Ventures
| Facilities | 25/6/2012 | MTB | NCB | 2012-09-07 |  |  |  | 2012-07-08 |  | Ltd | 28/8/12 | N74,076, | 6 weeks |  | 58402947.44 | 8 weeks |  | 95%
| within Treasury | [11 empty] | 526.81
House
14 | Rehabilitation | The Nation | [8 empty] | Ayoka
| of FPO | 25/6/2012 | MTB | NCB | 2012-09-07 |  |  |  | 2012-07-08 |  | Company | 28/8/12 | N18,787, | 6 weeks |  | 16373803.69 | 6 weeks |  | 100%
| Oshogbo | FTJ & L/Ship | [8 empty] | Ltd |  | 476.75
15 | Rehabilitation | The Nation | [8 empty] | Coxmartinz
| of FPO | 25/6/2012 | MTB | NCB | 2012-09-07 | [5 empty] | Engr. Services | 28/8/12 | N21,196, | 6 weeks |  | 15839354.51 | 6 weeks |  | 95%
| Calabar | FTJ & L/Ship | [8 empty] | Ltd |  | 35
16 | Rehabilitation | The Nation | [8 empty] | Tadam Engr.
| of FPO | 25/6/2012 | MTB | NCB | 2012-09-07 |  |  |  | 2012-07-08 |  | Services | 28/8/12 | N18,532, | 6 weeks |  | 16766971.5 | 6 weeks |  | 98%
| Abakaliki | FTJ & L/Ship | [8 empty] | Ltd |  | 48.5
17 | Installation
| of Public | [9 empty] | Julius Berger
| Address | == | MTB | NCB |  |  |  |  | 23/3/2010 |  | Nigeria Plc | 24/3/10 | N59,396, | 1 week |  | 8909401.08 | 1 week |  | 100%
| Systems in the | [11 empty] | 7.25
AGF's Confe.
Room
| TOTAL | [11 empty] | 0 | NO CONTRACT WAS AWARDED IN 2014

## COPYRIGTH
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) : |  | NIGERIAN COPYRIGHT COMMISSION
MINISTRY : |  | FEDERAL MINISTRY OF JUSTICE
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2014 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | Purchase of Teaching/Learning Aid 8 Nos. Desktops 8 No. Printer 2 Nos. Photocopiers |  | Below N50 Million | NCB | 2014-06-20 | 2014-06-24 | N6,080,000 | NIL | NIL | No | Viable Solutions International Company | 2014-10-27 | 6080000 | 14 Days | 2014-10-27 | N6,080,000 | 2014-11-19 | Completed Completed | Completed Completed | NIL | NIL | NIL
2 | Purchase of Library Books and Equipment 16 Copies of various Specialized IP Books for UYO Zonal Office 16 Copies of various Specialized IP Books for PORT HARCOURT Zonal Office |  | Below 2.5M | Shopping | 14/07/14 14/07/14 | 14/07/14 14/07/14 | N2,026,668 N2,026,665 | NIL | NIL | Yes Yes | Printers Collective Limited Leadmedia Limited | 15/07/14 15/07/14 | 4053333 | 14 Days 14 Days | 16/07/14 18/07/14 | N2,026,668 N2,026,665 | 5-08-14 2-08-14 | Completed Completed | Completed Completed | NIL | NIL | NIL
3 | Purchase of Security Equipment Purchase of: 45 pieces of Spy Pen 45 pieces of Spy Glasses 97 Pieces of Handcuffs 45 Pieces of Stun Devices 126 cans of Pepper Spray 300 pieces of High Visibility Vest |  | Below N50 Million | NCB | 2014-06-20 | 2014-06-20 | N3,526,666 | NIL | NIL | Yes | Micton Solution International Limited | 2014-10-27 | 3526666 | 14 Days | NIL | N3,526,666 | 2014-11-19 | Completed | Completed | NIL | NIL | NIL
4 | Construction / Provision of Infrastructure Construction/ Design of 20ft x 10ft Billboard in Lagos Construction/ Design of 20ft x 10ft Billboard in Port Harcourt |  | Below N50 Million | NCB | 20/6/2014 20/6/2014 | 24/6/2014 24/6/2014 | N17,633,333 | NIL | NIL | Yes Yes | Kaibora Style Limited Viable Solutions International Company | 17/7/14 27/10/14 | 9111111 | 90 Days 90 Days | 17/7/14 28/10/14 | N4,850,000 N4,261,111 | 30-09-14 2-12-14 | Completed | Completed | NIL | NIL | NIL
5 | Rehabilitation/ Repairs of Office Building Rehabilitation of Lagos Office Building |  | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL
6 | Research and Development Publication and dissemination of Survey of Public Perception of the Nigerian Copyright Commission’s Results to Stakeholders |  | Below 2.5M | Shopping | 2014-07-31 | 2014-08-06 | N24,588,994 | NIL | NIL | Yes | PromisedLand Concepts | 2014-10-23 | 2400000 | 14 Days | 2014-10-24 | N2,400,000 | 2014-10-31 | Completed | Completed | NIL | NIL | NIL
| TOTAL | [11 empty] | 25171110

## NAPTIP
BUREAU OF PUBLIC PROCUREMENT
PROCUREMENT RECORDS
MINISTRY |  | JUSTICE
PROCUREMENT ENTITY (MDA) |  | NATIONAL AGENCY FOR THE PROHIBITION OF FTRAFFIC IN PERSONS (NAPTIP)
FINANCIAL YEAR |  | 2014
BASIC DATA | [7 empty] | CONTRACT AWARD | [8 empty] | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION INCLUDE QUANTITY FOR GOODS | CONTRACT TYPE | ADVERTISEMENT DATE AND MEDIA | APPROVAL AUTHORITY | PROCUREMENT METHOD | BID OPENING DATE | DATE OF COMPLETION OF FINANCIAL / TECHNICAL BID EVALUATION REPORT | RECOMMENDED CONTRACTOR | DATE OF CERTIFICATE OF NO OBJECTION (If Applicable) | APPROVAL DATE BY ATB / PCC | DATE OF CONTACT AWARD | AWARD TO LOWEST TENDERER | CONTRACT PERIOD | CONTRACT EXTENSION PERIOD | CONTRACT VALUE N | BUDGETARY PROVISION N | DATE OF CONTRACT COMMENCEMENT | DATE OF COMMENCEMENT | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | DATE OF VARIATION APPROVAL | AMOUNT OF VARIATION N | AMOUNT PAID AS AT DATE N | EXPECTED COMPLETION DATE | %TAGE OF COMPLETION AS AT DATE | REMARKS
1 | Renovation and Repairs of | Capital | July 28th, | ATB Tendering | Tendering September | Sept. 8th | Oct. 10th | Apex Global | N/A | Oct. 20th | Oct. 30th | Yes | Immediate | N/A | 10849545 | 10,849,545:00 | Immediate | Immediate Immediate N/A | Immediate | N/A | N/A | Fully Paid | Within Time | Fully Compl-
| the Agency headquarter's |  | 2014 |  |  | 2014 | 2014 | Co.Ltd. |  | 2014 | 2014 | [11 empty] | Frame | eted
building.
ii. Rehabilitation and Repairs
of the shelter facilities
2 | Furnishing of offices of the | Capital | July 28th, | ATB | Tendering | Sept. 8th | Oct. 10th, | Scoop Secu- | N/A | Oct. 20th, | Oct. 30th, | Yes | Immediate | N/A | 3000480 | 3,000,480:00 | Immediate | Immediate | Immediate | N/A | N/A | Fully Paid | Within Time | Fully Com-
| Agency's Headquarters in |  | 2014 |  |  | 2014 | 2014 | rity Ltd. |  | 2014 | 2014 | [11 empty] | Frame | pleted
Abuja
3 | Furnishing of the Agency's | Capital | July 28th, | ATB | Tendering | Sept. 8th, | Oct. 10th, | Scoop Secu- | N/A | Oct. 20th, | Oct. 30th, | Yes | Immediate | N/A | 3000900 | 3,000,900:00 | Immediate | Immediate | Immediate | N/A | N/A | Fully Paid | Within Time | Fully Com-
| Makurdi Command Offices |  | 2014 |  |  | 2014 | 2014 | rity Ltd |  | 2014 | 2014 | [11 empty] | Frame | pleted
ii. Provision of equipment and
kitchen utensils to cater for
the feeding of suspects and
victims of Human Trafficking
at the Agency's shelter facility
at Makurdi Command
4 | Provision & Installation of | Capital | July 28th, | ATB | Tendering | Sept. 8th, | Oct. 10th, | Scoop Secu- | N/A | Oct. 20th, | Oct. 30th, | Yes | Immediate | N/A | 2000000 | 2,000,000:00 | Immediate | Immediate | Immediate | N/A | N/A | Fully Paid | Within Time | Fully Com-
| security/surveillanceequip- |  | 2014 |  |  | 2014 | 2014 | rity Ltd |  | 2014 | 2014 | [11 empty] | Frame | pleted
ment at the Agency's Makurdi
Command
5 | Purchase & Installation of | Capital | July 28th, | ATB | Tendering | Sept. 8th, | Oct. 10th, | Scoop Secu- | N/A | Oct. 20th, | Oct. 30th, | Yes | Immediate | N/A | 3996500 | 3,996,500:00 | Immediate | Immediate | Immediate | N/A | N/A | Fully Paid | Within Time | Fully Com-
| Computers & IT Communica- |  | 2014 |  |  | 2014 | 2014 | rity Ltd |  | 2014 | 2014 | [11 empty] | Frame | pleted
tion equipment at Makurdi
Command
ii. Purchase of computer prin-
ters for Makurdi Command
iii. Provision of first-aid kits
and Primary Health tools for
the Agency shelter facility in
Makurdi Command
6 | Purchase of photocoping | Capital | July 28th, | ATB | Tendering | Sept. 8th, | Oct. 10th, | Bonaby | N/A | Oct. 20th, | Oct. 30th, | Yes | Immediate | N/A | 1995000 | 1,995,000:00 | Immediate | Immediate | Immediate | N/A | N/A | Fully Paid | Within Time | Fully Com-
| machines for the following |  | 2014 |  |  | 2014 | 2014 | Ventures |  | 2014 | 2014 | [11 empty] | Frame | pleted
Zonal Commands:- Makurdi,
Enugu and Sokoto.
7 | Furnishing of the Agency's | Capital | July 28th, | ATB | Tendering | Sept. 8th, | Oct. 10th, | Bonaby | N/A | Oct. 20th, | Oct. 30th, | Yes | Immediate | N/A | 3383122 | 3,383,122:00 | Immediate | Immediate | Immediate | N/A | N/A | Fully Paid | Within Time | Fully Com-
| Offices at Benin Command |  | 2014 |  |  | 2014 | 2014 | Ventures |  | 2014 | 2014 | [11 empty] | Frame | pleted
ii. Renovation/Repairs of Age-
ncy's Benin Command Office
iii.Rehabilitation/Repairs of
the Agency's shelter facility
at Benin Zonal Command
8 | Furnishing of the Agency's | Capital | July 28th, | ATB | Tendering | Sept. 8th, | Oct. 10th, | Bonaby | N/A | Oct. 20th, | Oct. 30th, | Yes | Immediate | N/A | 2995252.5 | 2,995,252:50 | Immediate | Immediate | Immediate | N/A | N/A | Fully Paid | Within Time | Fully Com-
| Kano Command Offices |  | 2014 |  |  | 2014 | 2014 | Ventures |  | 2014 | 2014 | [11 empty] | Frame | pleted
ii.Renovation/Repairs of Age-
ncy's Kano Command Office
iii.Rehabilitation/Repairs of
the Agency's shelter facility
at Kano Zonal Command
9 | Furnishing of the Agency's Offices at Lagos Command ii.Renovation/Repairs of the Agency's Lagos Command iii.Rehabilitation/Repairs of the Agency Shelter facility at Lagos Zonal Command. | Capital | July 28th | ATB | Tendering | Sept. 8th,2014 | Oct. 10th,2014 | Bonaby Ventures | N/A | Oct. 20th,2014 | Oct. 30th,2014 | Yes | Immediate | N/A | 3987994 | 3,987,994:00 | Immediate | Immediate | Immediate | N/A | N/A | Fully Paid | Within Time Frame | Fully Completed
| TOTAL | [13 empty] | 35208793.5

## COLE
PERFORMANCE REPORT ON 2014 CAPITAL BUDGET
Name of Ministry: COUNCIL OF LEGAL EDUCATION Sector: Year: 2014
S/N | PROJECT DETAILS |  |  |  | DETAILS |  |  |  | PHYSICAL IMPLEMENTATION DETAILS
| Project/Programme Title | Project/Programme Description/Objectives | Name of Contractor | Project Location/Commencement Date | Project Total Cost/Completion Date | Project/programme Financial Commitment since inception | Appropriation for 2014 | Amount Released Year-to-Date | Key Performance Indicators/Deliverables for 2014 | Total Utilised in the year | Actual Performance in year
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 10 | 11 | 12 | 14
1 | Purchase of Library Books & Periodicals | To stock the Library with relevant materials for teaching and learning |  | Abuja HQ | 10000000 | Nil | 10000000 | Nil | Nil | 0 | Nil
2 | Purchase of Library Books & Periodicals | To stock the Library with relevant materials for teaching and learning |  | Yola Campus | 10500000 | Nil | 10500000 | Nil | Nil | 0 | Nil
3 | Purchase of Library Books & Periodicals | To stock the Library with relevant materials for teaching and learning |  | Bayelsa Campus | 9635701 | Nil | 9635701 | Nil | Nil | 0 | Nil
4 | Completion of Perimeter Fencing | To provide security for students and staff | 1.Alasan Ahmed & Sons Ltd. 2.Starmax Expertise Services Ltd. 3.Bakuisi Nig.Ltd. 4.Ofure Tech. Co. Ltd | Kano Campus, August 10,2014 | 45000000 | 20000000 | 20000000 | 20000000 | Provision of security for students and staff | 20000000 | Partial fencing of the campus
5 | Perimeter Fencing | To provide security for students and staff | Nuhson PakLand Nig. Ltd | Yola Campus, July 7,2014 | 63000000 | 23000000 | 23000000 | 23000000 | Provision of security for students and staff | 23000000 | Partial fencing of the campus
6 | Perimeter Fencing | To provide security for students and staff | Asaka Services Ltd | Yenagoa Campus, December 15,2014 | 45000000 | 12989874 | 20000000 | 12989874 | Provision of security for students and staff | 12989874 | Partial fencing of the campus
7 | Virtual Library | To provide an ultra modern Library for research & learning |  | Abuja HQ | 15000000 | Nil | 60000000 | Nil | Nil | 0 | Nil
8 | Completion of Library Complex | To provide an ultra modern Library for research & learning |  | Enugu Campus | 45000000 | Nil | 30000000 | Nil | Nil | 0 | Nil
9 | Completion of another Wing of Students Hoste | To provide accommodation for students | Quoin Design & Build Ltd | Lagos Campus, December 15,2014 | 206067446.4 | 86067446.4 | 20000000 | 20000000 | Accommodation of students in one wing of the students Hostel complex | 19120850 | Partial Completion of one wing of the students Hostel complex
| TOTAL |  | 6: 449203147.4

## NDLEA
NATIONAL DRUG LAW ENFORCEMENT AGENCY
2014 PROCUREMENT PERFORMANCE
S/N | PROJECT TITTLE | GOAL | OBJECTIVES | ACTIVITIES | INPUT | TIME FRAME | EXPECTED OUTCOME | MONITORING & EVALUATION INDICATORS | WHO IS RESPONSIBLE | BUDGET | RELEASES FOR 2014 | PERFORMANCE
1 | Renovation of National Headquarters | Conducive environment | To enhance efficiency at the National Headquarters | Manson, carpentary, plumbing, electrical works. | Strict supervision to ensure standardization | 10 weeks | Excellent work | Site Engineers & monitoring team from NHQ | Project & Maintenance Unit | 30000000
2 | Procurement of Arms and Ammunition | To ensure adequate security and facilities | To enhance operation | Grading, testing, engraving | Strict supervision to ensure standardization | 8 weeks | Serviceable | Armourer at the NHQ & Internal Auditors | Armoury | 60639747 | 60109513 | 60109513
3 | Operational Vehicles | Effectively comb the nook and cranny of the nation | To improve operational logistics | Vehicle Registration & Licensing,Installation of Siren | Strict supervision to ensure standardization | 3 weeks | Maintainable vehicles | Transport/Workshop team from NHQ | Workshop/Transport Unit | 36000000 | 9217413 | 9217413
4 | Renovation of Rivers State Command | Conducive environment. | To improve work environment and enhance performances | Manson, carpentary, plumbing, electrical works. | Strict supervision to ensure standardization | 10 weeks | Excellent works | Site Engineers & monitoring team from NHQ | Project & Maintenance Unit | 10000000
5 | Renovation of Jigawa State Command | Conducive environment. | To improve work environment and enhance performances | Manson, carpentary, plumbing, electrical works. | Strict supervision to ensure standardization | 10 weeks | Excellent works | Site Engineers & monitoring team from NHQ | Project & Maintenance Unit | 10000000
6 | Renovation of Osun State Command | Conducive environment. | To improve work environment and enhance performances | Manson, carpentary, plumbing, electrical works. | Strict supervision to ensure standardization | 10 weeks | Excellent works | Site Engineers & monitoring team from NHQ | Project & Maintenance Unit | 16760015
7 | Renovation of Anambra Command | Conducive environment. | To improve work environment and enhance performances | Manson, carpentary, plumbing, electrical works. | Strict supervision to ensure standardization | 10 weeks | Excellent works | Site Engineers & monitoring team from NHQ | Project & Maintenance Unit | 10000000
8 | Renovation of Delta State Command | Conducive environment. | To improve work environment and enhance performances | Manson, carpentary, plumbing, electrical works. | Strict supervision to ensure standardization | 10 weeks | Excellent works | Site Engineers & monitoring team from NHQ | Project & Maintenance Unit | 10000000
| Total | [8 empty] | 183399762 | 69326926 | 69326926

## LAC
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) : |  | LEGAL AID COUNCIL
MINISTRY : |  | JUSTICE
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2014 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | Estab. Of Legal Aid Centres In LGA Ogbia, Bayelsa | 3/06/2014 NOTICE BOARD | Director General | NATIONAL SHOPPING | 2014-06-24 | 2014-06-30 | 2094750 | NA | 2014-06-30 | HCC Integrated Projects Nig. Ltd. | HCC Integrated Projects Nig. Ltd. | 2014-06-30 | 2094750 | 3 weeks |  | 2094750 |  | COMPLETED | 100%
2 | Estab. Of Legal Aid Centres In LGA - Otuocha, Anambra | 3/06/2014 NOTICE BOARD | Director General | NATIONAL SHOPPING | 2014-06-24 | 2014-06-30 | 2447550 | NA | 2014-06-30 | Jal Falcom Ltd | Jal Falcom Ltd | 2014-06-30 | 2447550 | 3 weeks |  | 2447550 |  | COMPLETED | 100%
3 | Estab. Of Legal Aid Centres In LGA Badagry, Lagos | 3/06/2014 NOTICE BOARD | Director General | NATIONAL SHOPPING | 2014-06-24 | 2014-06-30 | 2414475 | NA | 2014-06-30 | Timeline Ventures Ltd | Timeline Ventures Ltd | 2014-06-30 | 2414475 | 3 weeks |  | 2414475 |  | COMPLETED | 100%
4 | Estab. Of Legal Aid Centres In LGA Erinile, Kwara | 3/06/2014 NOTICE BOARD | Director General | NATIONAL SHOPPING | 2014-06-24 | 2014-06-30 | 2454165 |  | 2014-06-30 | Ephphatha Universal Systems Ltd | Ephphatha Universal Systems Ltd | 2014-06-30 | 2454165 | 3 weeks |  | 2454165 |  | COMPLETED | 100%
5 | Estab. Of Legal Aid Centres In LGA Ikom, Cross River | 3/10/2014 NOTICE BOARD | Director General | NATIONAL SHOPPING | 2014-10-17 | 2014-10-20 | 2088450 | NA | 2014-10-20 | Godafon Enterprises | Godafon Enterprises | 2014-10-20 | 2088450 | 3 weeks |  | 2088450 |  | COMPLETED | 100%
6 | Estab. Of Legal Aid Centres In LGA - Eket, Akwa Ibom | 3/10/2014 NOTICE BOARD | Director General | NATIONAL SHOPPING | 2014-10-17 | 2014-10-20 | 2096850 | NA | 2014-10-20 | Creative Best Turn-Key Project Ltd | Creative Best Turn-Key Project Ltd | 2014-10-20 | 2096850 | 3 weeks |  | 2096850 |  | COMPLETED | 100%
7 | Estab. Of Legal Aid Centres In LGA -Ungogo, Kano | 3/10/2014 NOTICE BOARD | Director General | NATIONAL SHOPPING | 2014-10-17 | 2014-10-20 | 2119425 | NA | 2014-10-20 | Design - Aid Consult | Design - Aid Consult | 2014-10-20 | 2119425 | 3 weeks |  | 2119425 |  | COMPLETED | 100%
8 | Estab. Of Legal Aid Centres In LGA- Warri, Delta | 3/06/2014 NOTICE BOARD | Director General | NATIONAL SHOPPING | 2014-06-24 | 2014-07-02 | 2089500 | NA | 2014-07-02 | Creative Best Turn-Key Project Ltd | Creative Best Turn-Key Project Ltd | 2014-07-02 | 2089500 | 3 weeks |  | 2089500 |  | COMPLETED | 100%
9 | Estab. Of Legal Aid Centres In LGA -Owo, Ondo | 3/06/2014 NOTICE BOARD | Director General | NATIONAL SHOPPING | 2014-06-24 | 2014-07-02 | 2292150 | NA | 2014-07-02 | Godafon Enterprises | Godafon Enterprises | 2014-07-02 | 2292150 | 3 weeks |  | 2292150 |  | COMPLETED | 100%
10 | Library Equipment - Computers, Printers, Photocopiers | 3/10/2014 NOTICE BOARD | Director General | NATIONAL SHOPPING | 2014-10-17 | 2014-10-20 | 2494275 | NA | 2014-10-20 | Ephphatha Universal Systems Ltd | Ephphatha Universal Systems Ltd | 2014-10-20 | 2494275 | 3 weeks |  | 2494275 |  | COMPLETED | 100%
11 | Supply of Law books | 10/03/ 2014 NOTICE BOARD | Director General | NATIONAL SHOPPING | 2014-03-24 | 2014-03-25 | 1410000 | NA | 2014-03-25 | Pen & Pages Ltd | Pen & Pages Ltd | 2014-03-25 | 1410000 | 3 weeks |  | 1410000 |  | COMPLETED | 100%
12 | Supply of legalapedia (law report) | 3/10/2014 NOTICE BOARD | Director General | NATIONAL SHOPPING | 2014-10-17 | 2014-10-20 | 2488500 | NA | 2014-10-20 | Jal Falcom Ltd | Jal Falcom Ltd | 2014-10-20 | 2488500 | 3 weeks |  | 2488500 |  | COMPLETED | 100%
13 | Supply of Law books | 3/10/2014 NOTICE BOARD | Director General | NATIONAL SHOPPING | 2014-10-17 | 2014-10-20 | 1496000 | NA | 2014-10-20 | Vidul Ventures Ltd | Vidul Ventures Ltd | 2014-10-20 | 1496000 | 3 weeks |  | 1496000 |  | COMPLETED | 100%
14 | Supply of Law books (Report) | 3/10/2014 NOTICE BOARD | Director General | NATIONAL SHOPPING | 2014-10-17 | 2014-10-20 | 2486400 | NA | 2014-10-20 | Jal Falcom Ltd | Jal Falcom Ltd | 2014-10-20 | 2486400 | 3 weeks |  | 2486400 |  | COMPLETED | 100%
15 | Supply of Library equipment | 3/10/2014 NOTICE BOARD | Director General | NATIONAL SHOPPING | 2014-10-17 | 2014-10-20 | 2489550 | NA | 2014-10-20 | Ephphatha Universal Systems Ltd | Ephphatha Universal Systems Ltd | 2014-10-20 | 2489550 | 3 weeks |  | 2489550 |  | COMPLETED | 100%
16 | Rehabilitation/ Repairs of Office BuildingState Office - Sokoto, Sokoto | 10/06/2014NOTICE BOARD | Director General | NATIONAL SHOPPING | 2014-06-24 | 2014-07-02 | 2436000 | NA | 2014-07-02 | Timeline Ventures Ltd | Timeline Ventures Ltd | 2014-07-02 | 2436000 | 3 weeks |  | 2436000 |  | COMPLETED | 100%
17 | Rehabilitation/ Repairs of Office Building State Office - Gusau, Zamfara | 10/06/2014NOTICE BOARD | Director General | NATIONAL SHOPPING | 2014-06-24 | 2014-07-02 | 2444610 | NA | 2014-07-02 | Ephphatha Universal Systems Ltd | Ephphatha Universal Systems Ltd | 2014-07-02 | 2444610 | 3 weeks |  | 2444610 |  | COMPLETED | 100%
18 | Rehabilitation/ Repairs of Office BuildingState Office, - Birin Kebbi, Kebbi | 10/06/2014NOTICE BOARD | Director General | NATIONAL SHOPPING | 2014-06-24 | 2014-07-02 | 2446500 | NA | 2014-07-02 | Godafon Enterprises | Godafon Enterprises | 2014-07-02 | 2446500 | 3 weeks |  | 2446500 |  | COMPLETED | 100%
19 | Rehabilitation/ Repairs of Office BuildingState Office - Umuahia | 10/06/2014NOTICE BOARD | Director General | NATIONAL SHOPPING | 2014-06-24 | 2014-06-30 | 2448600 | NA | 2014-06-30 | Pen & Pages Ltd | Pen & Pages Ltd | 2014-06-30 | 2448600 | 3 weeks |  | 2448600 |  | COMPLETED | 100%
20 | Rehabilitation/ Repairs of Office Building State Office - Ilorin | 10/06/2014NOTICE BOARD | Director General | NATIONAL SHOPPING | 2014-06-24 | 2014-06-30 | 2403450 | NA | 2014-06-30 | Vidul Ventures Ltd | Vidul Ventures Ltd | 2014-06-30 | 2403450 | 3 weeks |  | 2403450 |  | COMPLETED | 100%
21 | Purchase and installation of ID process machine and accessories | 1/09/2014 NOTICE BOARD | Director General | NATIONAL SHOPPING | 2014-09-15 | 2014-09-16 | 998865 | NA | 2014-09-16 | Livewell Global Services Ltd | Livewell Global Services Ltd | 2014-09-16 | 998865 | 3 weeks |  | 998865 |  | COMPLETED | 100%
22 | Supply and Installation of Servers(2) | 3/10/2014 NOTICE BOARD | Director General | NATIONAL SHOPPING | 2014-10-17 | 2014-10-20 | 2475000 | NA | 2014-10-20 | Entcomm Ltd | Entcomm Ltd | 2014-10-20 | 2475000 | 3 weeks |  | 2475000 |  | COMPLETED | 100%
23 | Human Resources Data Base Sofware | 3/10/2014 NOTICE BOARD | Director General | NATIONAL SHOPPING | 2014-10-17 | 2014-10-20 | 2450000 | NA | 2014-10-20 | Entcomm Ltd | Entcomm Ltd | 2014-10-20 | 2450000 | 3 weeks |  | 2450000 |  | COMPLETED | 100%
24 | Networking of New Head quarters Offices | 3/10/2014 NOTICE BOARD | Director General | NATIONAL SHOPPING | 2014-10-17 | 2014-10-20 | 2000000 | NA | 2014-10-20 | Entcomm Ltd | Entcomm Ltd | 2014-10-20 | 2000000 | 3 weeks |  | 2000000 |  | COMPLETED | 100%
| TOTAL | [11 empty] | 53065065

## NLRC
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) : |  | NIGERIAN LAW REFORM COMMISSION
MINISTRY : |  | JUSTICE
FINANCIAL YEAR : 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2014 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | Procurement and installation of Digital Library Infrastructure | Notice board,21/8/14 | Parastatal Tenders Board | Competitive Bidding | 2014-10-09 | 2014-10-09 | 9480000 | N/A | 2014-11-12 | Yes | Cursor IP | 2014-12-09 | 9480000 | 1 Year | 13/9/2014 | 18005250 | 31/12/2015 | On-Going | 70%
2 | Acquisition and installation of stores inventory control system | Notice board,21/8/14 | Parastatal Tenders Board | Competitive Bidding | 2014-10-09 | 2014-10-09 | 4975000 | N/A | 2014-11-09 | Yes | Arch.Vic Resources ltd | 2014-12-09 | 4975000 | 1 Year | 13/9/2014 | 4975000 | 31/12/2015 | On-Going | 50%
3 | Purchase of Office Furniture | 2014-03-11 | Parastatal Tenders Board | Competitive Bidding | 2014-10-12 | 2014-10-12 | 8950000 | N/A | 2014-11-12 | Yes | Pisyogies limited | 15/12/14 | 6953080 | 1 Year | 16/12/14 | 6953080 | 31/12/14 | On-Going | 70%
4 | Purchase of Computer Printer | 18/3/14 | Accounting Officer | Shopping | 16/3/2014 |  | 500000 | N/A | 17/3/14 | Yes | Mutoy Adekunle & Co | 20/3/14 | 500000 | 1 year | 30/3/14 | 500000 | 31/12/14 | Completed | 100%
5 | Purchase of Photocopying Machines | 21/8/14 | Parastatal Tenders Board | Competitive Bidding | 2014-10-09 | 2014-10-09 | 3500000 | N/A | 2014-11-09 | Yes | L & Bee Integrated concepts | 2014-12-09 | 3500000 | 1 Year | 25/9/14 | 3500000 | 31/12/14 | Completed | 100%
6 | Purchase of Shredding machines | 20/3/14 | Accounting Officer | Shopping | 20/3/14 | 20/3/14 | 400000 | N/A | 20/3/14 | Yes | Tomjioke Resources ltd | 20/3/14 | 400000 | 1 Year | 30/3/14 | 400000 | 31/12/14 | Completed | 100%
7 | Purchase of Scanner & Binding machines | 18/3/14 | Accounting Officer | Shopping | 18/3/14 | 18/3/14 | 750000 | N/A | 17/3/14 | Yes | Mutoy Adekunle & Co | 18/3/14 | 750000 | 1 Year | 30/3/14 | 750000 | 31/12/14 | Completed | 100%
8 | Purchase of Library Books | 2014-03-03 | Parastatal Tenders Board | Competitive Bidding | 20/3/14 | 20/3/14 | 3329474 | N/A | 31/3/14 | Yes | Yinks Int'l Enterprise | 31/3/14 | 2854500 | 1 Year | 2014-02-04 | 2854500 | 31/12/14 | On-Going | 30%
9 | Purchase of sporting/Gaming Equipments | 21/8/14 | Parastatal Tenders Board | Competitive Bidding | 2014-10-09 | 2014-10-09 | 3000399 | N/A | 2014-11-09 | Yes | LookAlike sports ltd | 2014-12-09 | 3000399 | 1 Year | 18/9/14 | 2545573 | 31/12/14 | Completed | 100%
| TOTAL | [11 empty] | 32412979

## BORBDA
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) : |  | BENIN-OWENA RIVER BASIN DEVELOPMENT AUTHORITY, KM 24, BENIN-SAPELE ROAD, OBAYANTOR, BENIN CITY
MINISTRY : |  | FEDERAL MINISTRY OF WATER RESOURCES
FINANCIAL YEAR : |  | FY2014 CAPITAL PROJECTS
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2014 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | OWENA SMALL HYDRO POWER PROJECT | [5 empty] | 20000000
a. | Construction of Small Hydro Power Facilities at Owena Dam | 30/06/2014 | PTB | OPEN | 21/08/14 | 28/11/2011 |  | NIL | NIL | YES | DTEC Nigeria Limited | 2011-01-09 | 404751861.36 | 31/12/14 | 2011-05-09 | 18218928.44 | 15/12/14 | ON-GOING | 70 | NIL | NIL
2 | OKHUNWON SMALL HYDRO POWER PROJECT | [5 empty] | 20000000
a. | Construction of Small Hydro Power Facilities at Okhunwon, Edo State. | 30/06/2014 | PTB | OPEN | 21/08/14 | 28/11/2011 |  | NIL | NIL | YES | DTEC Nigeria Limited | 30/11/2011 | 156220610.12 | 31/12/14 | 2011-05-12 | 13290758.58 | 15/12/14 | ON-GOING | 70 | NIL | NIL
3 | ITAPAJI DAM SMALL HYDRO POWER | [5 empty] | 16000000
a. | Construction of Itapaji Small Hydro Power Project | 30/06/2014 | PTB | OPEN | 21/08/14 | 26/11/2013 |  | NIL | NIL | YES | DTEC Nigeria Limited | 27/09/13 | 54389500 | 31/12/14 | 29/09/13 | 2792953.5 | 15/12/14 | ON-GOING | 60 | NIL | NIL
4 | ILLAH-EBU IRRIGATION PROJECT | [5 empty] | 38000000
a. | Construction of Farm Access Road at Illah-Ebu Irrigation project | 30/06/2014 | PTB | OPEN | 21/08/14 | 2012-09-10 |  | NIL | NIL | YES | Crest Line Services Limited | 2012-10-10 |  | 31/12/14 | 18/10/2012 | 38000000 | 15/12/14 | ON-GOING | 100 | NIL | NIL
5 | ILLUSHI-EGA-ORIA IRRIGATION PROJECT | [5 empty] | 34000000
a. | Supply of 33,000 litres of diesel for Illushi Ega/Oria Irrigation Project. (Balance payment) | 30/06/2014 | PTB | OPEN | 21/08/14 | 2013-06-06 |  | NIL | NIL | YES | Aiyanyo Aigbekaen & Co. | 2013-06-06 | 7796250 | 31/12/13 | 2013-07-06 | 331931.25 | 15/12/14 | COMPLETED | 100 | NIL | NIL
b. | Construction/Renovation Works at Illushi-Ega-Oria Irrigation Project | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/2014 |  | NIL | NIL | YES | Uniworld Integrated Services Limited | 20/10/14 | 28195733.06 | 31/12/14 | 28/10/14 | 5472335.4 | 15/12/14 | ON-GOING |  | NIL | NIL
c. | Rehabilitation of Access Road at Illushi-Ega-Oria Irrigation Project | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/2014 |  | NIL | NIL | YES | Uniworld Integrated Services Limited | 20/10/14 | 5472335.4 | 31/12/14 | 20/10/14 |  | 15/12/14 | COMPLETED | 100 | NIL | NIL
6 | AISEGBA DAM AND IRRIGATION PROJECT | [5 empty] | 12000000
a. | Rehabilitation of Access Road at Aisegba Dam |  | PTB | OPEN |  | 16/10/2014 |  | NIL | NIL | YES | Richamen Ventures | 23/12/14 | 4958814 | 31/12/14 | 23/12/14 |  | 15/12/14 | COMPLETED | 100 | NIL | NIL
b. | Clearing/Desilting of Reservoir at Aisegba Dam |  | PTB | OPEN |  | 16/10/2014 |  | NIL | NIL | YES | Mudiamen Concepts Nigeria Ltd | 23/12/14 | 3675000 | 31/12/14 | 23/12/14 |  | 15/12/14 | COMPLETED | 100 | NIL | NIL
7 | IJU/ITAOGBOLU IRRIGATION PROJECT | [5 empty] | 20000000
a. | Construction Works at Iju/Itaogbolu Project | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/2014 |  | NIL | NIL | YES | Expro Light Nigeria Limited | 20/10/14 | 51689715 | 31/12/14 | 30/10/14 |  | 15/12/14 | ON-GOING |  | NIL | NIL
8 | AYO-ILUDUN/ISAN IRRIGATION AND DAM PROJECT | [5 empty] | 2000000
9 | ERUSU/ARIGIDI AKOKO EARTH DAM & IRRIGATION PROJECT | [5 empty] | 50000000
a. | Part payment for the supervision of Construction of Irrigation Facilities at Erusu Arigidi Earth Dam. | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/2014 |  | NIL | NIL | YES | FIC Consultant Limited | 20/10/14 | 2811492 | 31/12/14 |  | 2811492 | 15/12/14 | COMPLETED | 100 | NIL | NIL
b. | Procurement of Toyota 2.7L Petrol Engine Project Vehicle | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/2014 |  | NIL | NIL | YES | Kojo Motors Limited | 20/10/14 | 13594736.84 | 31/12/14 | 29/09/14 | 13594736.84 | 15/12/14 | COMPLETED | 100 | NIL | NIL
c. | Rehabilitation of Access Road to Erusu Arigidi Irrigation Project Site, Akoko North-West LGA, Ondo State. | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/2014 |  | NIL | NIL | YES | Richamen Ventures | 20/10/14 | 4028928.75 | 31/12/14 | 29/09/14 | 4028928.75 | 15/12/14 | COMPLETED | 100 | NIL | NIL
d. | Premium payment for the Comprehensive Insurance of Toyota 2.7L Petrol Engine Project Vehicle. | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/2014 |  | NIL | NIL | YES | Lasaco Assurance Plc. | 20/10/14 | 685174.72 | 31/12/14 | 29/09/14 | 685174.72 | 15/12/14 | COMPLETED | 100 | NIL | NIL
e. | Construction of Downstream Irrigation Works at Erusu-Arigidi in Akoko North West LGA, Ondo State | 30/06/2014 | PTB |  | 21/08/14 | 16/10/2014 |  | NIL | NIL | YES | Lecone Limited | 20/10/14 | 14657704.44 | 31/12/14 |  | 14657704.44 | 15/12/14 | COMPLETED |  | NIL | NIL
10 | CONSTRUCTION OF 6NO. PRODUCTIVE BOREHOLE AT ANIOCHA NORTH/SOUTH/OSHIMILI NORTH LGA | [5 empty] | 9500000
a. | Construction of 6Nos. Productive Borehole at Aniocha North/South/Oshimili North LGA. | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/2014 |  | NIL | NIL | YES | Runola Nigeria Limited | 27/09/13 | 9250075.17 | 31/12/13 | 28/09/13 | 9250075.17 | 15/12/14 | COMPLETED | 100 | NIL | NIL
11 | CONSTRUCTION OF 1NO. MOTORISED BOREHOLE AT ABARO (ABAVO), IKA SOUTH LGA | [5 empty] | 15000000 | [9 empty] | 15/12/14
a. | Construction of 1No. Motorised Borehole at Abavo (Abavo), Ika South LGA. | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/2014 |  | NIL | NIL | YES | Andison Charifort & Company Limited | 27/09/13 | 14816969.78 | 31/12/13 | 30/09/13 | 14369217.12 | 15/12/14 | COMPLETED | 100 | NIL | NIL
12 | CONSTRUCTION OF 1NO. BOREHOLE AT ETUA-OLIOGO, NDOKWA WEST AND IBREDE, NDOKWA EAST LGA |  |  |  | 21/08/14 | 16/10/2014 | 10000000
a. | Construction of 1No. Motorised Borehole at Ibrede, Ndokwa East LGA, Delta State. | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/2014 |  | NIL | NIL | YES | Wepco Consultant (Nigeria) Limited | 27/09/13 | 5000000 | 31/12/13 | 27/09/13 | 5246362.78 | 15/12/14 | COMPLETED | 100 | NIL | NIL
b. | Construction of 1No. Hand-Aiger Drilled Borehole at Ibrede, Ndokwa East LGA, Delta State. | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/2014 |  | NIL | NIL | YES | Reginalo R & N Nigeria Limited | 27/09/13 | 4500000 | 31/12/13 | 29/09/13 | 4374091.57 | 15/12/14 | COMPLETED | 100 | NIL | NIL
13 | CONSTRUCTION OF MOTORISED BOREHOLE AT EJEME-ANIOGOR, ANIOCHA SOUTH LGA | [5 empty] | 7500000
a. | Construction of Boreholes at 10 Federal Constituencies, Delta State. | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/2014 |  | NIL | NIL | YES | Spec System Limited | 20/10/14 | 7500000 | 31/12/13 | 30/09/13 | 7500000 | 15/12/14 | COMPLETED | 100 | NIL | NIL
14 | CONSTRUCTION OF 5NOS BOREHOLES IN AKURE NORTH/SOUTH FEDERAL CONSTITUENCY, ONDO STATE |  |  |  |  | 16/10/2014 | 5000000
a. | Completion of a Borehole and Construction of Overhead Steel Tank and Control House at Isinigbo, Akure North LGA, Ondo State. | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/2014 |  | NIL | NIL | YES | Prefape (NIG) Limited | 2014-12-11 | 4972731.23 | 31/12/14 | 2014-12-11 | 2936921.15 | 15/12/14 | COMPLETED | 100 | NIL | NIL
15 | COMPLETION OF IMIEGBA WATER SCHEME, EDO STATE |  |  |  | 21/08/14 | 16/10/14 | 30000000
a. | Construction of Imiegba Water Scheme, Etsako LGA, Edo State. | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Solia International Limited | 20/10/14 | 18319287 | 31/12/14 | 20/10/14 | 18319287 | 15/12/14 | COMPLETED | 100 | NIL | NIL
16 | SOLAR STREET LIGHTS IN SELECTED COMMUNITIES, ETSAKO FEDERAL CONSTITUENCY, EDO STATE |  |  |  | 21/08/14 | 16/10/14 | 30000000
a. | Construction of Solar Street Light in Selected Communities, Etsako Federal Constituency, Edo State | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Gaze Options Limited | 20/10/14 | 27536040 | 31/12/14 | 20/10/14 | 25464199.95 | 15/12/14 | COMPLETED | 100 | NIL | NIL
| Edo State |  | PTB |  | 21/08/14 | 16/10/14 |  | NIL | NIL | YES |  | 20/10/14 |  | 31/12/14 |  |  | 15/12/14
17 | MOTORISED BOREHOLE AT SAKPONBA ROAD/AREWA COMMUNITY, EDO STATE |  |  |  |  | 16/10/14 | 10000000
a. | Construction of 1No. Motorised Borehole at Sakponba Road/Arewa Community, Benin City | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Geonorm Associates Company Limited | 20/10/14 | 10000000 | 31/12/14 | 20/10/14 | 9223855.25 | 15/12/14 | COMPLETED | 100 | NIL | NIL
18 | UNDERGROUND WATER DEVELOPMENT |  |  |  |  | 16/10/14 | 8000000 | NIL
a. | Construction of 1No. Motorised Borehole at Agenebode, Etsako East LGA, Edo State. | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Keemdek Nigeria Limited | 20/10/14 | 11094543.1 | 31/12/14 | 2014-04-11 |  | 15/12/14 | ON-GOING |  | NIL | NIL
b. | Construction of 1No. Motorised Borehole at Agenebode, Etsako East LGA, Edo State. | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Kowope Associates Nigeria Limited | 20/10/14 | 11094543.1 | 31/12/14 | 2014-04-11 |  | 15/12/14 | ON-GOING |  | NIL | NIL
19 | ERIO-EKITI EARTH DAM PROJECT | [5 empty] | 20000000
20 | OWENA MULTI PURPOSE DAM IRRIGATION PROJECT | [5 empty] | 16000000
a. | Completion of Clearing Works at Owena Multipurpose Dam | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Messrs. Awomob Ventures | 20/10/14 | 1401281.91 | 31/12/14 | 23/06/2014 | 1401281.91 | 15/12/14 | COMPLETED | 100 | NIL | NIL
b. | Clearing of Irrigable Area at the Owena Dam Irrigation Project, Ondo State. | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Dipfen Nigeria Limited | 20/10/14 | 11060280 | 31/12/14 | 2014-08-12 |  | 15/12/14 | ON-GOING |  | NIL | NIL
21 | UKHUN-ERHA IRRIGATION PROJECT | [5 empty] | 2000000
22 | UKPOKE IRRIGATION PROJECT |  |  |  | 21/08/14 | 16/10/14 | 65000000 |  |  | YES | [6 empty] | 15/12/14
a. | Construction of Infrastructure at Ukpoke Irrigation Project |  | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Oweni Nigeria Limited | 20/10/14 | 64895366.97 | 31/12/14 | 2014-06-08 | 58626584.75 | 15/12/14 | COMPLETED | 100 | NIL | NIL
23 | ADO-EKITI/OSIN IRRIGATION PROJECT | [5 empty] | 24000000
a. | Construction of Ado-Ekiti/Osin Irrigation Project, Ikole LGA, Ekiti State. | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | North South Oaks Engineering Nigeria Limited. | 20/10/14 | 204850800 | 31/12/14 | 15/03/12 | 22000000 | 15/12/14 | ON-GOING | 100 | NIL | NIL
b. | Supervision of Ado-Ekiti/Osin Irrigation Project, Ikole LGA, Ekiti State. | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | FIC Consultant Limited | 20/10/14 | 2000000 | 31/12/14 |  | 2000000 | 15/12/14 | COMPLETED | 100 | NIL | NIL
24 | EWULU IRRIGATION PROJECT | [5 empty] | 4000000
25 | ISUA IRRIGATION PROJECT | [5 empty] | 4000000
26 | APOMU RIVER DAM ILARA MONKIN | [5 empty] | 54820561
a. | Studies and Design of Aponmu River Dam, Akure South LGA, Ondo State | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | FIC Consultant Limited | 20/10/14 | 15754725 | 31/12/14 |  | 3150948 | 15/12/14 | ON-GOING | 100
b. | Construction of Aponmu River Dam project, Akure South LGA; Ondo State | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Uniworld Integrated Services Limited | 2015-12-01 | 693788582.88 |  | 15/12/15 |  |  | ON-GOING | 15 | NIL | NIL
27 | SOLAR POWERED BOREHOLES IN EKITI NORTH FEDERAL CONSTITUENCY 1 | [5 empty] | 15989330
a. | Construction of 1No. Solar Powered Borehole at Ekiti North Federal Constituency 1, Ekiti State | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Cabod Nigeria Limited | 20/10/14 | 7994665 | 31/12/14 | 20/10/14 |  | 15/12/14 | COMPLETED |  | NIL | NIL
b. | Construction of 1No. Solar Powered Borehole at Ekiti North Federal Constituency 1, Ekiti State | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Sunrain Resources Limited | 20/10/14 | 7994665 | 31/12/14 | 20/10/14 |  | 15/12/14 | COMPLETED | 100 | NIL | NIL
28 | WATER SUPPLY SCHEME IN FUGA/NORTH-IBIE (IMIEGBA) FEDERAL CONSTITUENCY ONGOING EDO STATE | [5 empty] | 16750727
a. | Construction of Water Supply Scheme at Imiegba | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Solia International Limited. | 20/10/14 | 16750727 | 31/12/14 | 27/09/13 |  | 15/12/14 | COMPLETED | 100 | NIL | NIL
29 | PROVISION OF SOLAR POWERED BOREHOLES AT 1, OHONMONINE QUARTERS (ORONYA) AOMA LULEHA, OWAN WEST LGA 2, ARBIOSI OLD SITE-UNUOKHE AOMA, OWAN WEST LGA | [5 empty] | 15000000
a. | Construction of 1No. Motorised Borehole at Old Site-Unuokhe Aoma, Avbiosi-Uzebba, Owan West LGA, Edo State | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Mid-South Development & Investment Limited | 20/10/14 | 22786417.5 | 31/12/14 | 25/07/14 | 15000000 | 15/12/14 | COMPLETED | 100 | NIL | NIL
30 | MINI WATER SUPPLY SCHEME WITH 50,000 LITRES CAPACITY OVERHEAD TANK, POWER HOUSE WITH 2NOS. 25KVA GENERATOR AND 2KM DISTRIBUTION NETWORK IN IKINAGO-OPOJI, ESAN CENTRAL LGA EDO STATE. | [5 empty] | 22841900
31 | REHABILITATION OF IGBOTAKO (LOWOMA) WATER SUPPLY SCHEME, IGBOTAKO, OKITIPUPA LGA, ONDO STATE | [5 empty] | 40000000
a. | Rehabilitation of Igbotako (LOWOLOMO) Water Supply Scheme, Igbotako, Okitipupa LGA, Ondo State. | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Lerick Nigeria Limited | 20/10/14 | 40000000 | 31/12/14 | 2014-12-11 |  | 15/12/14 | ON-GOING | 100 | NIL | NIL
32 | REHABILITATION OF ALAGBAKA WATER SUPPLY SCHEME, AKURE NORTH LGA, ONDO STATE | [5 empty] | 60000000
a. | Rehabilitation of Alagbaka Water Supply Scheme, Akure North LGA; Ondo State | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | First Seromatic Ventures Limited | 20/10/14 | 60000000 | 31/12/14 | 28/10/2014 | 60000000 | 15/12/14 | ON-GOING | 100 | NIL | NIL
33 | HEADQUARTERS DEVELOPMENT: CONSTRUCTION OF 1KM ACCESS ROAD IN PREMISES OF THE HEADQUARTERS AT OBAYANTOR, BENIN CITY, EDO STATE | [5 empty] | 40000000
a. | Construction of Access Road within the Premises of the Headquarters’ Complex at Obayantor, Benin City, Edo State | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Pafemo Nigeria Limited | 20/10/14 | 39340455 | 31/12/14 | 28/10/2014 |  | 15/12/14 | ON-GOING | 50 | NIL | NIL
34 | SOLAR POWERED BOREHOLE AT NO. 26 TANIMOWO STREET, UGBE, ONDO | [5 empty] | 10000000
a. | Rehabilitation of Access Road to Ugbe Solar Borehole Project | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Richamen Ventures | 20/10/14 | 2499918.75 | 31/12/14 | 13/10/2014 | 2499918.75 | 15/12/14 | COMPLETED | 100 | NIL | NIL
b. | Construction of 1No. Solar Powered Borehole at No. 26, Tanimowo Street, Ugbe, Ikare-Akoko, Ondo State | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Benchase Allied Resources Limited | 20/10/14 | 7348477.54 | 31/12/14 | 20/10/2014 |  | 15/12/14 | COMPLETED | 100 | NIL | NIL
35 | CONSTRUCTION OF SOLAR POWERED BOREHOLES AT PALM RUBBER, SAKA FIMUDILI WARD 1 ONDO WEST LGA AND IGBOTU-APOI ESE ODO LGA ONDO STATE. | [5 empty] | 20000000
a. | Construction of 2Nos.Solar Powerd Boreholes at Palm Rubber Saka Fimudili Ward 1, Ondo West LGA; and Igbotu-Apoi Ese Odo LGA, Ondo State. | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Lerick Nigeria Limited | 20/10/14 | 18809925.75 | 31/12/14 | 28/10/2014 | 9090909.08 | 15/12/14 | COMPLETED | 100 | NIL | NIL
36 | CONSTRUCTION OF SOLAR POWERED BOREHOLES AT OBAGBE EEMO COMPOUND, ILORO QUARTERS, OWODE ROAD, EFON ALAAYE, EFON LGA, EKITI STATE. | [5 empty] | 10000000
a. | Construction of 1No. Solar Powered Borehole at Obagbe Elemo Compound, Iloro Quarters, Owode Road, Efon Alaaye, Efon LGA; Ekiti State. | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Franghile (Nig) Agency | 20/10/14 |  | 31/12/14 | 28/10/2014 |  | 15/12/14 | COMPLETED | 100 | NIL | NIL
37 | PROVISION OF WATER BOREHOLE AT RONKE OLABODE STREET IN GRA, IJEBU QUARTERS, OWO, ONDO STATE | [5 empty] | 10000000
a. | Rehabilitation of Access Road to the Solar Powered Borehole Project at Ronke Olabode Street, Owo | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Richamen Ventures | 20/10/14 | 2100000 | 31/12/14 | 13/10/2014 |  | 15/12/14 | COMPLETED | 100 | NIL | NIL
b. | Construction of 1No. Solar Powered Borehole at Ronke Olabode Street in GRA, Ijebu Quarters, Owo, Ondo State | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Global Dayzee Multilinks Limited | 20/10/14 | 7870504.95 | 31/12/14 | 20/10/2014 |  | 15/12/14 | ON-GOING |  | NIL | NIL
38 | 3NOS. HANDPUMPS BOREHOLES AT EPINMI TEACHERS COLLEGE, ONDO STATE | [5 empty] | 10000000
a. | Construction of 3Nnos. Motorised Boreholes equipped with Handpumps at Epinmi Teachers College, Ondo State | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Franghile (Nig) Agency | 20/10/14 | 4712400 | 31/12/14 | 20/10/2014 |  | 15/12/14 | COMPLETED | 100 | NIL | NIL
b. | Rehabilitation of Water Scheme at African Church, Unity School, Epinmi-Akoko, Ondo | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Frantos Engineering Service Limited | 20/10/14 | 3582022.5 | 31/12/14 | 2014-12-11 |  | 15/12/14 | COMPLETED | 100 | NIL | NIL
39 | CONSTRUCTION OF SOLAR POWERED BOREHOLE AT ALISIMIE, IKA SOUTH LGA, DELTA STATE | [5 empty] | 20000000
a. | Construction of 1No. Solar Powered Borehole at Alisimie, Ika South LGA, Delta State | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Bee-Harris Construction Nigeria Limited | 20/10/14 | 17436893.71 | 31/12/14 | 28/10/2014 |  | 15/12/14 | COMPLETED | 100 | NIL | NIL
40 | NSADOP WATER SUPPLY SCHEME IN BOKI LGA |  |  |  | 21/08/14 | 16/10/14 | 5329777 |  |  | YES | [6 empty] | 15/12/14 |  |  | NIL | NIL
a. | Construction of 1No. Productive Borehole equipped with Solar Powered Submersible pump in Boki LGA, Cross River State. | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Ogun-Asu Company Limited | 20/10/14 | 4350535.35 | 31/12/14 | 2014-03-12 |  | 15/12/14 | ON-GOING | 0 | NIL | NIL
41 | CONSTRUCTION OF MOTORISED BOREHOLES AT DELE OKAFOR AGBOR | [5 empty] | 8000000
a. | Completion of Motorised Borehole at 7, Dele Okafor Street, Agbor, Delta State. | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Agada Foundations Limited | 20/10/14 | 4771402.02 | 31/12/14 | 2012-03-12 | 4771402.02 | 15/12/14 | COMPLETED | 100 | NIL | NIL
42 | SOLAR POWERED BOREHOLES AT THE FOLLOWING LOCATIONS: 1, ONIPARAGA 2. ARAROMI OBU 3. ILE-OLUJI 4. AJUREE ILE-OLUJI/OKEIGBO/ODIGBO FED. CONST. | [5 empty] | 15989330
43 | PURCHASE OF VARIOUS SKILL ACQUISATION EMPOWERMENT MATERIALS (BLOCK MOULDING MACHINES, MOTOCYCLES AND REGRIGERATORS) IN AKOKO EDO FED. CONST. | [5 empty] | 15989330
a. | Supply of Various Skill Acquisition Empowerment Materials (Block Moulding Machines, Motorcycles and Refrigerators) in Akoko-Edo Fed. Const.; Edo State | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Bengail Integrated Services Limited | 20/10/14 | 15386437.5 | 31/12/14 | 20/10/2014 | 15386437.5 | 15/12/14 | COMPLETED | 100 | NIL | NIL
44 | SOLAR POWERED BOREHOLE AT IDANRE ROAD, BESIDE OPEN UNIVERSITY, AKURE | [5 empty] | 10000000
a. | Rehabilitation of Access Road to the Solar Powered Borehole Project at Idanre Road, Akure. | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Andison Charifot & Company Limited | 20/10/14 | 2493750 | 31/12/14 | 13/10/2014 | 2493750 | 15/12/14 | COMPLETED | 100 | NIL | NIL
b. | Construction of 1No. Solar Powered Borehole at Idanre Road, Beside Open University, Akure, Ondo State. | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Needs Technologies Limited | 20/10/14 | 7498530.27 | 31/12/14 | 20/10/2014 |  | 15/12/14 | COMPLETED |  | NIL | NIL
45 | CONSTRUCTION OF ELEMI/UREJE RIVER DAM IN ADO-EKITI | [5 empty] | 83753634
a. | Study and Design of Elemi/Ureje River Dam, Ekiti State (Lot A2) | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | AAP & Partners | 20/10/14 | 22100000 | 31/12/14 | 16/09/2014 |  | 15/12/14 | COMPLETED | 100 | NIL | NIL
b. | Construction of Elemi/Ureje River Dam Project, Ado-Ekiti, Ekiti State | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Shon Nigeria Limited | 2015-12-01 | 460987116.45 |  | 15/01/15 |  |  |  | 15 | NIL | NIL
46 | EARTH DAM AT ERHURUN IN AKOKO EDO FEDERAL CONSTITUENCY | [5 empty] | 15227934
a. | Study and Design of Erhurun River Dam, Akoko-Edo LGA, Edo State | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | FIC Consultants Limited | 20/10/14 | 14927850 | 31/12/14 | 16/09/2014 | 2985570 | 15/12/14 | COMPLETED | 100 | NIL | NIL
47 | OYE IRRIGATION PROJECT | [5 empty] | 8000000
48 | EWOHIMI WATER SCHEME | [5 empty] | 8000000
a. | Rehabilitation of Ewohimi Water Supply Scheme, Esan South-East LGA, Edo State | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Tomline Industrial Company Limited | 20/10/14 | 503,497,417.00. | 31/12/14 | 15/03/12 | 7710885 | 15/12/14 | ON-GOING |  | NIL | NIL
49 | ENA RIVER WATER SCHEME, VIA UBIAJA, ESAN-SOUTH EAST LGA, EDO STATE. | [5 empty] | 2000000
a. | Construction of Ella Water Supply Scheme, Via Ubiaja, Esan South East LGA, Edo State | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Belvine Limited | 20/10/14 | 507,652,897.50. | 31/12/14 | 15/03/12 | 2000000 | 15/12/14 | ON-GOING |  | NIL | NIL
50 | RETICULATION OF NORTHERN ISHAN WATER SUPPLY SCHEME | [5 empty] | 2000000
a. | The Reticulation/Extension of Northern Ishan Water Supply Scheme. | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Dadim Integrated Concept Limited | 20/10/14 | 168841501.86 | 31/12/14 | 2012-02-10 | 2000000 | 15/12/14 | ON-GOING |  | NIL | NIL
51 | AGBEDE WATER SCHEME | [5 empty] | 10000000
a. | Construction of Water Treatment Plant at Agbede Water Scheme | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | C & G Tropicana (CTROL) Limited | 20/10/14 | 10000000 | 31/12/14 | 20/12/2012 | 10000000 | 15/12/14 | ON-GOING |  | NIL | NIL
52 | AYETORO EKITI SPRING WATER DEVELOPMENT | [5 empty] | 2000000
a. | Supply of Diesel Ayetoro Ekiti Spring Water Development | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Sopharm Ventures | 20/10/14 | 1900800 | 31/12/14 | 21/11/2014 | 1990800 | 15/12/14 | COMPLETED | 100 | NIL | NIL
53 | IWOROKO EKITI SPRING WATER DEVELOPMENT | [5 empty] | 2800000
a. | Rehabilitation/Connection Works at Iworoko Spring Water Project, Iworoko-Ekiti, Ekiti State. | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | BOA Associates | 20/10/14 | 1985130 | 31/12/14 | 21/11/2014 | 1985130 | 15/12/14 | COMPLETED | 100 | NIL | NIL
54 | ELETI (OTUN) SPRING WATER DEVELOPMENT | [5 empty] | 2800000 |  |  | YES
a. | Rehabilitation/Connection Works at Eleti Spring Water Project, Otun – Ekiti, Ekiti State. | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Ibi-Faruk Ventures Limited | 20/10/14 | 1995745.5 | 31/12/14 | 21/11/2014 | 1995745.5 | 15/12/14 | COMPLETED | 100 | NIL | NIL
55 | AFAO EKITI SPRING WATER DEVELOPMENT | [5 empty] | 2000000
a. | Reactivation of Afao-Ekiti Spring Water Development, Ekiti State. | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Plannet Gold Limited | 20/10/14 | 1946574 | 31/12/14 | 21/11/2014 | 1946574 | 15/12/14 | COMPLETED | 100 | NIL | NIL
56 | ERO DAM IRRIGATION PROJECT | [5 empty] | 2000000
57 | REHABILITATION OF PLANT AND EQUIPMENT | [5 empty] | 14000000
a. | Supply of btyres: 205 R16 (8Nos.), 195 R14 (8Nos.) and 235/65R17 (3Nos.) | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Osphil International | 20/10/14 | 713181 | 31/12/14 | 15/01/2014 | 713181 | 15/12/14 | COMPLETED | 100 | NIL | NIL
b. | Rehabilitation of Accidented Vehicle Parts Replacement and other Works | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Kojo Auto Service Centre | 20/10/14 | 1186057.5 | 31/12/14 | 24/02/2014 | 1186057.5 | 15/12/14 | COMPLETED | 100 | NIL | NIL
c. | Replacement of Brand New Engine, Drining Shaft, Radiator Unit, Battery, Manifold Air Distributor and B.S.M (Built In-System Interface). | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Unibright Motors Nigeria Limited | 20/10/14 | 1332878 | 31/12/14 | 24/02/2014 | 1332878 | 15/12/14 | COMPLETED | 100 | NIL | NIL
d. | The Rehabilitation Of Tractors, Ploughs And Harrows | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Mosano Link International Limited | 20/10/14 | 5000000 | 31/12/14 | 23/08/2012 | 5000000 | 15/12/14 | COMPLETED | 100 | NIL | NIL
e. | Repairs of Vehciles; FG03-D25, FG45-D25 and FG46-D25 | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Uyi Technical Motors | 20/10/14 | 443250 | 31/12/14 | 24/02/2014 |  | 15/12/14 | COMPLETED | 100 | NIL | NIL
f. | Supply of tyres for project vehicles | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Messrs. Emmatem Trust Nigeria Limited | 20/10/14 | 984897.38 | 31/12/14 | 24/02/2014 |  | 15/12/14 | COMPLETED | 100 | NIL | NIL
g. | Repair of FG17-D25, FG23-D25, FG105-D25 | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Sunny Aichenede Motors | 20/10/14 | 1125565.5 | 31/12/14 | 24/02/2014 | 1125565.5 | 15/12/14 | COMPLETED | 100 | NIL | NIL
h. | Repairs of Toyota Prado | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Kojo Motors Limited | 20/10/14 | 523218 | 31/12/14 | 24/02/2014 | 413218 | 15/12/14 | COMPLETED | 100 | NIL | NIL
i. | Repairs of Vehicle (FG03-D25) | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Uyi Technical Motors | 20/10/14 | 190890 | 31/12/14 | 24/02/2014 | 190890 | 15/12/14 | COMPLETED | 100 | NIL | NIL
j. | Overhauling of 60KVA Generating Set at the Central Road Office | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Messrs. Robert Generator | 20/10/14 | 955500 | 31/12/14 | 24/02/2014 | 955500 | 15/12/14 | COMPLETED | 100 | NIL | NIL
58 | HYDROMETEROLOGICAL NETWORK AND PLANNING | [5 empty] | 8400000
59 | MONITORING AND EVALUATION OF WATER RELATED PROJECT | [5 empty] | 4000000
a. | Monitoring and Oversignt function, Federal House of Representatives | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Mid-South Development & Investment Limited | 20/10/14 | 2499999.92 | 31/12/14 | 13/10/2014 | 2499999.92 | 15/12/14 | COMPLETED | 100 | NIL | NIL
60 | REVITALIZATION OF RBDA | [5 empty] | 4000000
61 | HEADQUARTERS DEVELOPMENT | [5 empty] | 10000000
a. | Survey works at Authority’s Land Obayantor (Final Payment) | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Evbosa & Associates | 20/10/14 | 2867877 | 31/12/14 | 2012-09-08 | 2867877 | 15/12/14 | COMPLETED | 100 | NIL | NIL
b. | Installation of Feeder Pillars, Earthing Materials, etc on Transformer (500KVA) in Obayantor | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Dele-Osaretin Nigeria Limited | 20/10/14 | 2450000 | 31/12/14 | 2012-07-12 | 2450000 | 15/12/14 | COMPLETED | 100 | NIL | NIL
c. | Pest Control at the Headquarters’ Complex, Central Road Office, Area Offices and Liaison Office, Abuja. | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Omo-Adoni C. Odihiri Nig. Ent. | 20/10/14 | 992250 | 31/12/14 | 25/07/2014 | 992250 | 15/12/14 | COMPLETED | 100 | NIL | NIL
d. | Installation of 11KVA Line Isolation Switch and Fencing of the Transformer/Feeder Pillar (Substation)/Making fire trace around the Substation/Additional Light Around the Substation, Power House, Oil Mill, Workshop, Estate and the entire Headquarters Premises | 30/06/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Dele-Osaretin Nigeria Limited | 20/10/14 | 3103070.78 | 31/12/14 | 28/010/2014 |  | 15/12/14 | COMPLETED | 100 | NIL | NIL
|  |  | PTB |  | 21/08/14 | 16/10/14 |  | NIL | NIL | YES |  | 20/10/14 |  | 31/12/14 |  |  | 15/12/14
62 | CONTRUCTION/COMPLETION OF IDANRE WATER SUPPLY SCHEME, TOWNSHIP DISTRIBUTION IN IDANRE AND ALADE TOWNSHIP EXTENSION SCHEME IN ONDO CENTRAL SENATORIAL DISTRICT, ONDO STATE. | [5 empty] | 90000000 |  |  | YES | [6 empty] | 15/12/14
a. | Construction of Idanre Regional Water Scheme, Ondo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Pacesetter Global Technology Limited | 20/10/14 | 39600000 | 31/12/14 | 27/09/2013 | 39600000 | 15/12/14 | ON-GOING | 100 | NIL | NIL
63 | CONSTRUCTION OF SOLAR POWERED BOREHOLE IN AJEGUNLE, OKEIGBO, ILE-OLUJI/OKEIGBO LGA, ONDO SOUTH SENATORIAL DISTRICT, ONDO STATE (ON-GOING) | [5 empty] | 5000000
a. | Completion of 1No. Motorised borehole at Ajegunle, Okeigbo, Ile-Oluji/Okeigbo LGA, Ondo South Senatorial District, Ondo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Plannet Gold Limited | 20/10/14 | 5520644.57 | 31/12/14 | 2014-12-11 | 5256441.06 | 15/12/14 | COMPLETED | 100 | NIL | NIL
64 | CONSTRUCTION OF SOLAR POWERED BOREHOLE IN AJEGUNLE,IGODAN-LISA/OKUNMU, OKITIPUPA LGA, ONDO SOUTH SENATORIAL DISTRICT, ONDO STATE |  |  |  | 21/08/14 | 16/10/14 | 10000000 |  |  | YES | [6 empty] | 15/12/14
a. | Construction of 1No. Solar Powered Borehole at Ajegunle, Igodan-Lisa/Okunmu, Okitipupa LGA, Ondo South Senatorial District, Ondo State. | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | VOS Construction Company Nigeria Limited | 20/10/14 | 9859804.19 | 31/12/14 | 2014-12-11 | 3893286.35 | 15/12/14 | COMPLETED | 100 | NIL | NIL
65 | CONSTRUCTION OF SOLAR POWERED BOREHOLE IN EBIDO STREET, IGBOTU, ESE-ODO LGA, ONDO SOUTH SENATORIAL DISTRICT, ONDO STATE | [5 empty] | 10000000
a. | Construction of 1No. Solar Powered Borehole at Ebido Street, Igbotu, Ese-Odo LGA; Ondo South Senatorial District, Ondo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Lerick Nigeria Limited | 20/10/14 | 10000000 | 31/12/14 | 28/10/2014 |  | 15/12/14 | COMPLETED | 100 | NIL | NIL
66 | CONSTRUCTION OF SOLAR POWERED BOREHOLE OPPOSITE CHIEF KEHINDE FASONU ARAROMI-OBU, ODIGBO LGA, ONDO SOUTH SENATORIAL DISTRICT, ONDO STATE. | [5 empty] | 10000000
a. | Construction of 1No. Solar Powered Borehole Opposite Chief Kehinde Fasonu Araromi-Obu, Odigbo LGA, Ondo South Senatorial District, Ondo State. | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | First Seromatic Ventures Limited | 20/10/14 | 10000000 | 31/12/14 | 28/10/2014 |  | 15/12/14 | ON-GOING | 100 | NIL | NIL
67 | CONSTRUCTION OF SOLAR POWERED BOREHOLE IN BROADS ST. AJAGBA, IRELE LGA, ONDO SOUTH SENATORIAL DISTRICT, ONDO STATE. |  | PTB |  | 21/08/14 | 16/10/14 |  | NIL | NIL | YES |  | 20/10/14 |  | 31/12/14 |  |  | 15/12/14
10000000
a. | Construction of 1No. Solar Powered Borehole in Broads Street, Ajagba, Irele LGA, Ondo South Senatorial District, Ondo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | H. E. Paneko Nigeria Company Limited | 20/10/14 | 9490641.93 | 31/12/14 | 28/10/2014 |  | 15/12/14 | ON-GOING |  | NIL | NIL
68 | PROVISION OF 1NO. OF MOTORISED BOREHOLE AT IGUN STREET, OREDO LGA, EDO STATE. | [5 empty] | 10000000
a. | Construction of 1No. Motorised Borehole at Igun Street, Benin City, Oredo LGA, Edo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | ED-Famos Nigeria Limited | 20/10/14 | 9813909.11 | 31/12/14 | 28/10/2014 |  | 15/12/14 | ON-GOING |  | NIL | NIL
69 | PROVISION OF 10NOS. OF MOTORISED BOREHOLES ORHIONMWON/UHUNMWODE LGA, EDO STATE | [5 empty] | 110000000
a. | Construction of 1No. Motorised Borehole at Ehiozevbaru, Uhunwonde LGA; Edo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Mosano Link International Limited | 20/10/14 | 10465794.57 | 31/12/14 | 28/10/2014 |  | 15/12/14 | COMPLETED |  | NIL | NIL
b. | Construction of 1No. Motorised Borehole at Ute-Oheze, Orhionmwon LGA; Edo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Glokins Interbiz & Partners Limited | 20/10/14 | 10465794.57 | 31/12/14 | 28/10/2014 |  | 15/12/14 | COMPLETED | 100 | NIL | NIL
c. | Construction of 1No. Motorised Borehole at Evbuohenoba, Orhionmwon LGA; Edo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Gaze Options Limited | 20/10/14 | 10465794.57 | 31/12/14 | 28/10/2014 | 9610171.2 | 15/12/14 | COMPLETED | 100 | NIL | NIL
d. | Construction of 1No. Motorised Borehole at Igbogiri, Uhunwonde LGA; Edo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Math Ehis Nigeria Limited | 20/10/14 | 10465794.57 | 31/12/14 | 28/10/2014 |  | 15/12/14 | COMPLETED | 100 | NIL | NIL
e. | Construction of 3Nos. Motorised Boreholes at Ehor, Ogan, Urhonigbe, Orhionmwon/Uhunmwonde LGA; Edo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Solia International Limited | 20/10/14 | 36601881 | 31/12/14 | 28/10/2014 | 33508062 | 15/12/14 | COMPLETED | 100 | NIL | NIL
f. | Construction of 1No. Motorised Borehole at Idumodi-Igbanke, Orhionmwon LGA; Edo State. | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Anstek Nigeria Limited | 20/10/14 | 18300940.5 | 31/12/14 | 28/10/2014 | 16754031 | 15/12/14 | COMPLETED | 100 | NIL | NIL
70 | PROVISION OF 3NOS. MOTORISED SOLAR POWERED BOREHOLES WITH TEN DISPENSING PUMPS | [5 empty] | 27000000
a. | Construction of 3Nos. motorized Solar Powered Boreholes with Ten Dispensing Pumps at Akoko-Edo LGA, Edo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | C & G Vertex Limited | 20/10/14 | 27000000 | 31/12/14 | 20/10/2014 |  | 15/12/14 | ON-GOING |  | NIL | NIL
71 | COMPLETION OF FUGAR WATER SCHEME (2012 OUTSTANDING) AT FUGAR-ETSAKO CENTRAL-EDO STATE | [5 empty] | 22000000
72 | CONSTRUCTION OF INDUSTRIAL BOREHOLE FITTED WITH 10HP, 45METER CUBE TANK AND 20KVA GENERATOR IN AFOWA-ETSAKO WEST LGA, EDO STATE. | [5 empty] | 19000000
a. | Construction of Industrial Borehole Fitted with 10HP, 45Meter Cube Tank and 20KVA Generator In Afowa-Etsako West LGA, Edo State |  | PTB |  | 21/08/14 | 16/10/14 |  | NIL | NIL | YES |  | 20/10/14 |  | 31/12/14 |  |  | 15/12/14
|  |  | PTB |  | 21/08/14 | 16/10/14 |  | NIL | NIL | YES |  | 20/10/14 |  | 31/12/14 |  |  | 15/12/14
|  |  | PTB |  | 21/08/14 | 16/10/14 |  | NIL | NIL | YES |  | 20/10/14 |  | 31/12/14 |  |  | 15/12/14
|  | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Riths Global ventures Limited | 20/10/14 | 18944635.71 | 31/12/14 | 28/10/2014 |  | 15/12/14 | COMPLETED |  | NIL | NIL
73 | MOTORISED BOREHOLE IN UTEKON COMMUNITY OF OVIA NORTH EAST LGA, EDO STATE | [5 empty] | 10000000
a. | Construction of 1No. Motorised Borehole at Utekon Community of Ovia North East LGA, Edo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Vankus Nigeria Enterprises | 20/10/14 | 9970068.57 | 31/12/14 | 28/10/2014 | 9159511.2 | 15/12/14 | COMPLETED | 100 | NIL | NIL
74 | COMPLETION OF ELECTRICITY PROJECT AT ODIGHI-AGBANIKAKA OF OVIA NORTH EAST LGA, EDO STATE | [5 empty] | 30000000
a. | The Extension of Electricity from Uhiere to Agbanikaka including the installation of 2Nos. 300KVA Transformers in Owan and Agbanikaka, Ovia North East LGA, Edo State. | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | M/S Sam & Sam International Limited | 20/10/14 | 28459441.08 | 31/12/14 | 2014-06-08 | 28459441.08 | 15/12/14 | COMPLETED | 100 | NIL | NIL
75 | PROVISION OF 7NOS. MOTORISED BOREHOLE EQUIPPED WITH SOLAR PUMP IN UGBUEZI, UHONMORA, UZEBBA, IGHERA-OTUO, AKE, IMAKHIZE-OTUO, IGUE-ISALE OWAN EAST/WEST LGA, EDO STATE. | [5 empty] | 63000000
a. | Construction of 3Nos. Motorised Boreholes equipped with Solar Pump at Ighera-Otuo, Ake, Imakhize-Otuo, Igue-Isale Owan East LGA, Edo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Mid-South Development & Investment Limited | 20/10/14 | 23999456.25 | 31/12/14 | 2014-06-08 | 22057875 | 15/12/14 | COMPLETED | 100 | NIL | NIL
b. | Construction of 2Nos. Motorised Boreholes Equipped with Solar Pump at Ugbubezi, Uhonmora and Uzebba, Owan West LGA, Edo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Mid-South Development & Investment Limited | 20/10/14 | 37889271.43 | 31/12/14 | 2014-06-08 | 34678417.2 | 15/12/14 | COMPLETED | 100 | NIL | NIL
c. | Furnishing of Project Offices | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Chasodia (Nig) Limited | 20/10/14 | 999999 | 31/12/14 | 2014-03-12 | 999999 | 15/12/14 | COMPLETED | 100 | NIL | NIL
d. | Repair of Toyota Hilux (FG33-D25) Project Vehicle | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Olajide Oluwambe Mechnical Workshop | 20/10/14 | 106576 | 31/12/14 | 2014-03-12 |  | 15/12/14 | COMPLETED | 100 | NIL | NIL
76 | PROVISION OF 2NOS. MOTORISED BOREHOLE EQUIPPED WITH SOLAR PUMP (DEEP SEDIMENTARY) IN UOKHA AND IVBIARO-OTUO, OWAN EAST/WEST LGA, EDO STATE. | [5 empty] | 48000000
a. | Construction of 2Nos. Motorised Boreholes Equipped with Solar Pump at Uokha and Ivbiaro-Otuo, Owan East/West LGa, Edo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Mid-South Development & Investment Limited | 20/10/14 | 36601880.71 | 31/12/14 | 20/10/2014 | 33508060.95 | 15/12/14 | COMPLETED | 100 | NIL | NIL
77 | PROVISION OF 20NOS. HANDPUMP BOREHOLES @ N1,700,000 EKITI SOUTH WEST/IKERE/ISE-ORUN, EKITI STATE. | [5 empty] | 34500000
a. | Construction of 4Nos. Productive Boreholes Equipped with Handpumps at Ekiti South West/Ikere/Ise-Orun, Ekiti State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Ovuos Global Resources Limited | 20/10/14 | 6120000 | 31/12/14 | 20/10/2014 |  | 15/12/14 | COMPLETED |  | NIL | NIL
b. | Construction of 4Nos. Productive Boreholes Equipped with Handpumps at Ekiti South West/Ikere/Ise-Orun, Ekiti State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Folag Investment Limited | 20/10/14 | 6120000 | 31/12/14 | 20/10/2014 | 5814000 | 15/12/14 | COMPLETED |  | NIL | NIL
c. | Construction of 4Nos. Productive Boreholes Equipped with Handpumps at Ekiti South West/Ikere/Ise-Orun, Ekiti State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Logkeg Engineering Limited | 20/10/14 | 6120000 | 31/12/14 | 20/10/2014 |  | 15/12/14 | COMPLETED |  | NIL | NIL
d. | Construction of 4Nos. Productive Boreholes Equipped with Handpumps at Ekiti South West/Ikere/Ise-Orun, Ekiti State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Agunos Nigeria Limited | 20/10/14 | 6120000 | 31/12/14 | 20/10/2014 | 5856000 | 15/12/14 | COMPLETED |  | NIL | NIL
e. | Construction of 4Nos. Productive Boreholes Equipped with Handpumps at Ekiti South West/Ikere/Ise-Orun, Ekiti State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | O & O Technical Company Limited | 20/10/14 | 6120000 | 31/12/14 | 20/10/2014 | 5856000 | 15/12/14 | COMPLETED | 100 | NIL | NIL
f. | Replacement of Tyres, Wheel Balancing and Alignment for FG-38-D25 and FG-34-D25 project vehicles. | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Emmatem Trust Nigeria Enterprises | 20/10/14 | 597450 | 31/12/14 | 2014-03-12 | 597450 | 15/12/14 | COMPLETED | 100 | NIL | NIL
g. | Renovation and Reconstruction Works | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Bramex Development Company Limited. | 20/10/14 | 2446500 | 31/12/14 | 15/12/2014 | 2446500 | 15/12/14 | COMPLETED | 100 | NIL | NIL
78 | CONSTRUCTION OF WEIR ON UGBOGBOSUN RIVER & PIPPING OF WATER TO THE RESERVOIR IN OKEEMO COMMUNITY, EKITI SOUTH WEST, EKITI STATE | [5 empty] | 10000000
a. | Construction of Weir on Ugbogbosun River & Piping of Water to the Reservoir in Okemo Community, Ekiti South West, Ekiti State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Zenflux Resources Limited | 20/10/14 | 10000000 | 31/12/14 | 28/10/2014 |  | 15/12/14 | COMPLETED |  | NIL | NIL
79 | SOLAR POWERED BOREHOLE AT OFI RIVER AREA IGBARA-IDO ROAD, ADIN, EKITI SOUTH WEST, EKITI STATE. | [5 empty] | 10000000
a. | Construction of 1No. Solar Powered Borehole at Ofi River Area Igbara-Ido Road, Adin, Ekiti South West, Ekiti State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Mobol Ventures | 20/10/14 | 7639651.64 | 31/12/14 | 28/10/2014 |  | 15/12/14 | COMPLETED | 100 | NIL | NIL
b. | Completion of 1No. Borehole at Iju-Osun Palace, Irele LGA, Ondo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Sunday Odes Enterprises | 20/10/14 |  | 31/12/14 | 18/11/2014 | 2209725 | 15/12/14 | COMPLETED | 100 | NIL | NIL
80 | REFURBISHING OF OLD BOREHOLE AT IJUKU, ILAWE, EKITI S.W/IKERE/ISE-ORUN, EKITI STATE | [5 empty] | 10000000
a. | Refurbishing of Old Borehole at Ijuku, Ilawe, Ekiti S.W/Ikere/Ise-Orun, Ekiti State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Dan & Ani Limited | 20/10/14 | 8436304.8 | 31/12/14 | 28/12/2014 |  | 15/12/14 | COMPLETED |  | NIL | NIL
b. | The Supply of Mowers & String Trimmers | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Micro-Project Development Management Limited | 20/10/14 | 1525650 | 31/12/14 | 21/11/2014 | 1525650 | 15/12/14 | COMPLETED | 100 | NIL | NIL
81 | COMPLETION OF ONGOING SOLAR POWERED BOREHOLE IN THE PALACE OF OLOGBOTUN, EKITI SOUTH WEST/IKERE/ISE-ORUN, EKITI STATE. | [5 empty] | 1000000
82 | PROVISION OF 6 UNITS OF HANDPUMP BOREHOLES @ N1.4M EACH TO THE FOLLOWING LOCATIONS |  |  |  | 21/08/14 | 16/10/14 | 8400000 | NIL | NIL | YES |  | 20/10/14 |  | 31/12/14 |  |  | 15/12/14
| PROVISION OF ONGOING SOLAR POWERED BOREHOLE IN THE PALCE OF OLOGBOTUN, EKITI SOUTH WEST/IKERE/ISE-ORUN, EKITI STATE(i) IRO QUARTERS, IYIN EKITI, IREPODUN-IFELODUN LG, (ii) OKE AGBE 1, IREPODUN IFELODUN LG (iii) IROPORA, IREPODUN-IFELODUN LG (iv) IGBO ASO, ADO EKITI LGA (v) BAWA AREA, ADO EKITI LG. (vi) OKE ALA, ADO EKITI LGA, EKITI STATE | [5 empty] | 8400000
a. | Construction of 2Nos. Productive Boreholes Equipped with Handpumps at Irepodun-Ifelodun/Ado- Ekiti LGAs, Ekiti State. | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Michael Jacobs Limited | 20/10/14 | 2788800 | 31/12/14 | 20/10/2014 | 2670360 | 15/12/14 | COMPLETED | 100 | NIL | NIL
b. | Construction of 2Nos. Productive Boreholes Equipped with Handpumps at Irepodun-Ifelodun/Ado- Ekiti LGAs, Ekiti State. | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Cabod Nigeria Limited | 20/10/14 | 2788800 | 31/12/14 | 20/10/2014 | 2670360 | 15/12/14 | COMPLETED |  | NIL | NIL
c. | Construction of 1No. Productive Borehole Equipped with Handpumps at Irepodun-Ifelodun/Ado- Ekiti LGAs, Ekiti State. | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | BOA Associates | 20/10/14 | 1394400 | 31/12/14 | 20/10/2014 | 1328000 | 15/12/14 | COMPLETED |  | NIL | NIL
83 | PROVISION OF TWO PANEL BOREHOLES EACH @ N3.6M TO THE FOLLOWING LOCATIONS; ONALA, ADO EKITI LG AND OKELAWE QUARTERS IN IREPODUN-IFELODUN LGA, EKITI STATE | [5 empty] | 7200000
a. | Construction of 2Nos. Productive Boreholes Equipped with Handpumps at the Following Locations: Onala, Ado Ekiti LG and Okelawe Quarters in Irepodun-Ifelodun LGA, Ekiti State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Anstek Nigeria Limited | 20/10/14 | 3192000 | 31/12/14 | 20/10/2014 | 3053400 | 15/12/14 | COMPLETED | 100 | NIL | NIL
b. | Construction of 2Nos. Productive Boreholes Equipped with Handpumps at the Following Locations: Onala, Ado Ekiti LG and Okelawe Quarters in Irepodun-Ifelodun LGA, Ekiti State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Michael Jacobs Limited | 20/10/14 | 3192000 | 31/12/14 | 20/10/2014 | 2984000 | 15/12/14 | COMPLETED | 100 | NIL | NIL
84 | SIX (6) SOLAR POWERED MOTORISED BOREHOLES TO ONDO EAST/WEST LGAs ONDO STATE | [5 empty] | 48000000
a. | Construction of 2Nos. Solar Motorised Boreholes at Ondo East/West LGas, Ondo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Nikvic Companion Limited | 20/10/14 | 15979905.32 | 31/12/14 | 20/10/2014 | 13791044.01 | 15/12/14 | COMPLETED | 100 | NIL | NIL
b. | Construction of 1No. Solar Motorised Borehole at Ondo East/West LGas, Ondo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Peacefos Product Limited | 20/10/14 | 7989952.66 | 31/12/14 | 20/10/2014 |  | 15/12/14 | COMPLETED |  | NIL | NIL
c. | Construction of 1No. Motorised Borehole at Ondo West LGA, Ondo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Svetoteknika Nigeria Limited | 20/10/14 | 6358309.23 | 31/12/14 | 27/09/2013 | 6358309.23 | 15/12/14 | COMPLETED | 100 | NIL | NIL
d. | Construction of 1No. Mini Water Supply Scheme at Laye, Ondo West LGA, Ondo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Smace Nigeria Limited | 20/10/14 | 9847405.48 | 31/12/14 | 27/09/2013 | 9847405.48 | 15/12/14 | COMPLETED | 100 | NIL | NIL
85 | SOLAR POWERED BOREHOLE WITH STANDARD OVERHEAD TANK FOR AKOKO SOUTH WEST, ONDO STATE | [5 empty] | 6500000
a. | Construction of 1No. Solar Powered Borehole with Standard Overhead Tank at Akoko South West, Ondo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Bizerve Nigeria Limited | 20/10/14 | 6500000 | 31/12/14 | 28/10/2014 |  | 15/12/14 | COMPLETED |  | NIL | NIL
86 | SOLAR POWERED BOREHOLE WITH STANDARD OVERHEAD TANK FOR AKOKO SOUTH EAST | [5 empty] | 6500000
a. | Construction of 1No. Solar Powered Borehole with Standard Overhead Tank at Akoko South East, Ondo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Toniparkers & Associates | 20/10/14 | 6500000 | 31/12/14 | 28/10/2014 |  | 15/12/14 | ON-GOING |  | NIL | NIL
87 | ELECTRIFICATION FROM ABUDU THROUGH OBAGIE NOHEZE-AMAS VILLAGE-OVBIUWA-AKUGBE TO IGUODODO IN ORHIONMWON LGA AND EHIOZEVBARU TO IGUAVBIANMWEN IN UHUMWONDE LGA, EDO STATE. | [5 empty] | 140000000
a. | Electrification Works from Abudu Through Obagie Nohezie-Amas Village-Ovbiuwa-Akugbe to Iguododo in orhionmwon LGA and Ehiozevbaru to Iguavbianmwen in Uhunmwonde LGA, Edo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Helma Engineering Consultants Limited | 20/10/14 | 138557872.68 | 31/12/14 | 28/10/2014 | 76050174.64 | 15/12/14 | COMPLETED | 100 | NIL | NIL
b. | Construction of Signpost at the Authority’s Landed property | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Fayoban Ventures | 20/10/14 | 1092448 | 31/12/14 | 2014-12-11 | 1092448 | 15/12/14 | COMPLETED | 100 | NIL | NIL
c. | Repairs of KIA Sportage (FG45-D25) Project Vehcile | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Olajide Oluwambe Workshop | 20/10/14 | 343140 | 31/12/14 | 15/12/2014 | 343140 | 15/12/14 | COMPLETED | 100 | NIL | NIL
88 | SOLAR POWERED BOREHOLE AT OZA VILLAGE IN ORHIONMWON LGA, EDO STATE | [5 empty] | 13000000
a. | Construction of 1No. Solar Powered Borehole at Oza Village, Orhionmwon LGA, Edo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Helma Engineering Consultants Limited | 20/10/14 | 8963635 | 31/12/14 | 27/09/2013 | 8963635 | 15/12/14 | COMPLETED | 100 | NIL | NIL
b. | Furnishing of Offices | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Bet-Idah Global Resources Limited | 20/10/14 | 2487450 | 31/12/14 | 23/11/2013 | 2487450 | 15/12/14 | COMPLETED | 100 | NIL | NIL
89 | MOTORISED BOREHOLE IN OVIA FEDERAL CONSTITUENCY, EDO STATE. | [5 empty] | 12000000
a. | Construction of 1No. Motorised Borehole at Ovia Federal Constituency, Edo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Mikesede Generation (Nig) Limited | 20/10/14 | 10437319.2 | 31/12/14 | 28/10/2014 | 456394.46 | 15/12/14 | COMPLETED | 100 | NIL | NIL
90 | MOTORISED BOREHOLE IN AZAMA COMMUNITY OFF WIRE ROAD, BENIN CITY, OREDO FEDERAL CONSTITUENCY, EDO STATE. | [5 empty] | 12000000
a. | Construction of 1No. Motorised Borehole at Azama Community Off Wire Road, Benin City, Oredo Federal Constituency, Edo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Soibi Contracting Limited | 20/10/14 | 10125145.8 | 31/12/14 | 28/10/2014 | 10072240.5 | 15/12/14 | COMPLETED | 100 | NIL | NIL
91 | MOTORISED BOREHOLE, EQUIPPED WITH SOLAR PUMP IN WARD 8, OWAN WEST LGA, EDO STATE. | [5 empty] | 12000000
a. | Construction of Motorised Borehole, Equipped with Solar Pump at Ward 8, Owan West LGA, Edo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Glocal Integrated Services Limited | 20/10/14 | 12000000 | 31/12/14 | 28/10/2014 | 11403554.4 | 15/12/14 | COMPLETED | 100 | NIL | NIL
92 | MOTORISED BOREHOLE AT UBIERUMU (WARD II) UROMI, ESAN NORTH EAST LGA, EDO STATE. | [5 empty] | 12000000
a. | Construction of 1No. Motorised Borehole at Ubierumu (Ward II) Uromi, Esan North East LGA, Edo State | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Integrated Techno Dynamics Limited | 20/10/14 | 12000000 | 31/12/14 | 28/10/2014 |  | 15/12/14 | ON-GOING | 0 | NIL | NIL
93 | REHABILITATION OF WATER SCHEME AT THE FEDERAL COLLEGE OF AGRICULTURE, AKURE. | [5 empty] | 100000000
a. | Rehabilitation of Water Scheme at the Federal College of Agriculture, Akure | 28/07/2014 | PTB | OPEN | 21/08/14 | 16/10/14 |  | NIL | NIL | YES | Complete Bright Engineers and Services Limited | 20/10/14 | 100000000 | 31/12/14 | 28/10/2014 |  | 15/12/14 | ON-GOING | 50 | NIL | NIL
93 | [12 empty] | 3672350630.7

## ICPC
BUREAU OF PUBLIC PROCUREMENT
MINISTRY: ICPC
FINANCIAL YEAR: 2012 | L YEAR:
|  | BASIC DATA | [9 empty] | CONTRACT AWARD
S/N | CONTRACT DESCRIPTION | CONTRACT TYPE | ADVERTISEMENT | APPROVAL AUTHORITY | PROCUREMENT METHOD | BID OPENING DATE | DATE OF COMPLETION
| Including Quantity of Goods) |  | DATES AND MEDIA |  |  |  | OF FINANCIAL /TECHNICAL EVALUATION | RECOMMENDED CONTRACTOR | DATE OF CERTIFICATE | APPROVAL DATE | DATE OF CONTRACT | AWARDED TO LOWEST | CONTRACT PERIOD | CONTRACT EXTENSION | CONTRACT VALUE | BUDGETARY PROVISION | DATE OF CONTRACT | DATE OF COMMENCEMENT | DATE OF VARIATION | AMOUNT OF VARIATION | AMOUNT PAID AS | EXPECTED COMPLETION DATE | % OF COMPLETION | REMARKS
[7 empty] | REPORT |  | OF NO OBJECTION | BY AO/PTB/MTB/FEC | AWARD | TENDERER |  | PERIOD | (N) | (N) | COMMENCEMENT | (PHYSICAL MOBILIZATION) | APPROVAL |  | AT DATE |  | AS AT DATE
IF APPLICABLE
1 | Construction of 40 Bed room | Works | July 15,2013 | Tenders Board | National Competitive | 26th Aug. 2013 | 11th Nov. 2013 | Rofasy Nig ltd | N/A | 12th Nov. 2013 | 15th Nov. 2013 | Yes | 32weeks | Nil | 146343361.5 | 132,897,643.00Funds for Academy | 09th Dec. 2013 | 09th Dec. 2013 | N/A | N/A | N66,184,977.57 in 2014 | 11th Aug 2014 | 100%
| Hostel Block at the Academy |  |  |  | Bidding(NCB)
2 | Supply and Installation of 2 | purchase of goods | Same as above | Accounting Officer | REQUEST FOR PROPOSAL(NS) | N/A | N/A | Sambiz Nig Ltd | N/A | 14th May,2013 | 6th May ,2013 | Yes | 1 Week | Nil | 345000 | 132951778 | 27th May 2014 | N/A | N/A | N/A | 345000 | 14th June,2014 | 100%
Nos Split Unit A/C at ACAN
3 | Technical Adviser | Services | N/A | Accounting Officer | Single source(SS) | N/A | N/A | Engr Odili Okeke | N/A | 19th Dec. 2013 | N/A | N/A | 32 weeks | Nil | 3000000 | Funds for Academy | N/A | N/A | N/A | N/A | 1715000 in 2014 | 2013-08-01 | 100%
| on Hostel Project | [14 empty] | is also for this
4 | CCECC NIG LTD | Works | Part of outstanding balance paid for a projects completed in 2011 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 6000000 | Already completed

## FMoYD
Federal Ministry of Youth Development
S/No | Project Title | Contractor | PROCUREMENT METHOD | Approval type/Date | Date Awarded | Contract Sum | Contract Duration | Implementation Level % | Remarks
1 | Supply of 300Nos Kasea Motorcycles, Binji, Sokoto State | M/s Arfat Multi Resources Ltd | NCB | MTB 06/11/14 | 24/11/14 | 48138240 | 4Weeks | 100% | Completed
2 | Supply of 300Nos Kasea Motorcycles, Silame LGA, Sokoto State | M/s ShafabMultigate Ltd | NCB | MTB 06/11/14 | 24/11/14 | 48138240 | 4Weeks | 100% | Completed
3 | Supply of 238Nos Motorcycles, Dambatta/Makoda, Kano State | M/s Battawa Inv. Co. Ltd | NCB | MTB 06/11/14 | 24/11/14 | 36904855.96 | 4Weeks | 100% | Completed
4 | Provision of 34Nos Tricycles for Youth Empowerment, Uyo, NsitAtai, Uruan, BesikpoAsutai, AkwaIbom State | M/s Lento Nig. Ltd | NCB | MTB 06/11/14 | 24/11/14 | 22122500.36 | 4Weeks | 100% | Completed
5 | Provision of 66Nos Tricycles at Atiba LGA, Oyo State | M/s Millenium Global Tech & Eng. Services | NCB | MTB 06/11/14 | 24/11/14 | 29167434.45 | 4Weeks | 100% | Completed
6 | Provision of 90Nos Motorcycles at Atiba LGA, Oyo State | M/s Millenium Global Tech & Eng. Services | NCB | MTB 06/11/14 | 24/11/14 | 9744065.1 | 4Weeks | 100% | Completed
7 | Provision of 20Nos Grinding Machine at Atiba LGA, Oyo State | M/s Micson Integrated Service Ltd | NCB | MTB 06/11/14 | 24/11/14 | 934657.5 | 4Weeks | 100% | Completed
8 | Provision of 238Nos Motorcycles at DawakinTofa/RimiGado Federal Constituency, Kano State | M/s M.N. Ataj Construction Ltd | NCB | MTB 06/11/14 | 24/11/14 | 36735500 | 4Weeks | 100% | Completed
9 | Provision of 240Nos Sewing Machine, 56Nos Carpentry Kits, 100Nos Grinding machine and 120Nos Motorcycles at Gaya/Albasu/Ajingi Federal Constituency, Kano State | M/s H & I Construction Ltd | NCB | MTB 06/11/14 | 24/11/14 | 36446000 | 4Weeks | 100% | Completed
10 | Supply of 300Nos Furniture/Training Tools to Skills Training Centre at Ahoada Town, Rivers West Senatorial District, Rivers State | M/s Rowitz Engineering Service Nig. Ltd | NCB | MTB 06/11/14 | 24/11/14 | 35295000 | 4Weeks | 100% | Completed
11 | Construction of Youth Development Centre, Obi, Benue State | M/s Rafjaf Nig. Ltd | NCB | MTB 06/11/14 | 24/11/14 | 39865904.65 | 12 Weeks |  | On-going
12 | Construction of External Electrical Works at Youth Development Centre, Agatu, Benue State | M/s Barewa Investment Ltd | NCB | MTB 06/11/14 | 24/11/14 | 99768874.68 | 16 Weeks |  | On-going
13 | Construction of Youth Development Centre at Agbokim, Cross River State | M/s Gentab Int’l Ltd | NCB | MTB 06/11/14 | 24/11/14 | 148742180.44 | 16Weeks |  | On-going
14 | Construction of 1No 2 Bedroom Semi Detached Bungalow at Youth Development Centre at Ikom, Cross River State | M/s YegraY’owo Company Ltd | NCB | MTB 06/11/14 | 24/11/14 | 27722887.5 | 20 Weeks |  | On-going
15 | Construction of Football field, 2No Detached Bungalow and 1No classroom block at Youth Development Centre, Otada, Otukpo, Benue State | M/s Double Y & O Ventures Ltd | NCB | MTB 06/11/14 | 24/11/14 | 49197474.9 | 12 Weeks |  | On-going
16 | Construction and Furnishing of 1No Town Hall at Idikpa, IkotNtuen, NsitAkwaIbom State | M/s Randex Int’l Ltd | NCB | MTB 06/11/14 | 24/11/14 | 22924719.3 | 9 Weeks |  | On-going
17 | Renovation of Skill Training Centre at Ahoada East LGA, Rivers State | M/s Rojbel Service Ltd | NCB | MTB 06/11/14 | 24/11/14 | 24979999.28 | 12 Weeks |  | On-going
18 | Construction and Furnishing of Paramount Rulers Palace (Palace Hall) at Atodot, NsitAtai, AkwaIbom State | M/s SomiConstruzioni Nig. Ltd | NCB | MTB 06/11/14 | 24/11/14 | 23790490.5 | 12 Weeks |  | On-going
19 | Construction and Furnishing of 1No Town Hall at IwokObioAdung, NsitAtai, AkwaIbom State | M/s MEF Nig. Ltd | NCB | MTB 06/11/14 | 24/11/14 | 23531099.62 | 9 Weeks |  | On-going
20 | Electrical works at National Youth Development Centre, TohuSabon-gari, Kaduna State | M/s Bricks Int’l Concept Ltd | NCB | MTB 06/11/14 | 24/11/14 | 43021925.99 | 6 Weeks |  | On-going
21 | Skill Acquisition, Small and Medium Scale Enterprises Development in Zamfara North Senatorial District, Zamfara State | M/S AmsagDevt. Public Health Consulting Ltd. | NCB | MTB 02/02/15 | 2015-10-02 | 82442579.03 | 4Weeks | 100% | Completed
22 | Youth Empowerment Programme in Vocational Skill in Zamfara North Senatorial District, Zamfara State | M/ Gant Nig Ltd | NCB | MTB 02/02/15 | 2015-10-02 | 47107628 | 4Weeks | 100% | Completed
23 | Skills Training Programme for 250 Youths in Rivers West Senatorial District, Rivers State | M/S Rojbec Services Nig. Ltd | NCB | MTB 02/02/15 | 2015-10-02 | 23021915.7 | 4Weeks | 100% | Completed
24 | Empowerment Programme for 250 Youths in Rivers West Senatorial District, Rivers State | M/S Rowitz Engineering Services Ltd | NCB | MTB 02/02/15 | 2015-10-02 | 42393061.42 | 4Weeks | 100% | Completed
25 | Youth Empowerment Programme in Vocational Skills for Lagos West Senatorial District (Alimosho, IfakoIjaye&Agege LGA), Lagos State | Kezac Investment Ltd | NCB | MTB 02/02/15 | 2015-10-02 | 55988116.01 | 4Weeks | 100% | Completed
26 | Youth Empowerment Programme in Vocational Skills for Lagos West Senatorial District (Ikeja, Oshodi-Isolo& Mushin LGA), Lagos State | M/S sonola Investment Ltd | NCB | MTB 02/02/15 | 2015-10-02 | 53203106.94 | 4Weeks | 100% | Completed
27 | Youth Empowerment Programme in Vocational Skills for Lagos West Senatorial District (AmuwoOdofin, AjeromiIfelodun, Ojo&Badagry LGA), Lagos State |  | NCB | MTB 02/02/15 | 2015-10-02 |  | 4Weeks | 100% | Completed
28 | Value Re-orientation/ Empowerment Programme | M/S sonola Investment Ltd | NCB | MTB 02/02/15 | 2015-10-02 | 20623911.24 | 4Weeks | 100% | Completed
1131952368.57

## FMLH&UD
FEDERAL MINISTRY OF LANDS, HOUSING & URBAN DEVELOPMENT
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) :
MINISTRY :
FINANCIAL YEAR :
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2013 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2013 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | PREPARATION OF PHYSICAL DEVELOPMENT PLAN AT ORILLE OWU, | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 5/10/2014/ MTB | YES | M/S Moa Planners Ltd | OCT.,2014 | 14,675,000. 00 | 2 WEEKS | NOV.,2014 |  | 10 WEEKS | N/A |  | N/A | N/A
2 | PREPARATION OF PHYSICAL DEVELOPMENT PLAN AT OTUOKE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S EMMARY KONSULT | OCT.,2014 | 15,582,000. 00 | 2 WEEKS | NOV.,2014 |  | 10 WEEKS | N/A |  | N/A | N/A
3 | PREPARATION OF PHYSICAL DEVELOPMENT PLAN AT YELWA | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S DEVELOPMENT PLANING | OCT.,2014 | 15,702,488. 00 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
4 | SUPPLY OF MEDICAL EQUIPMENT TO THE STAFF CLINIC | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S EMMARY KONSULT | OCT.,2014 | 14,700,000. 00 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
5 | CONSTRUCTION OF ADMIN/ CLASSROOM BLOCK AT SCHOOL ARCHTECTURAL TECHNICIANS, KUJE, ABUJA | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S YEMZAL REPROC NIG. LTD | OCT.,2014 | 47,002,519. 17 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
6 | REHABILITATION AND PERTITIONING OF HOSTEL BLOCK A, AT SCHOOL OF ARCHITECTURAL TECHNICIANS, KUJE ABUJA | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S CIRO CONSTRUCTION COMPANY LTD | OCT.,2014 | 48,202,224. 45 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
7 | PROCUREMENT AND INSTALLATION OF FLEET TRACKING DEVICES FOR 112NOS DRF/MDGs AND THE OTHER FMLHUD HEADQUERTERS AND FIELD OFFICES | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S MTN TELECOMMUNICATION NIG. LTD | OCT.,2014 | 14,914,032. 00 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
8 | PROVISION OF INFRASTRUCTURE (ROADS, GRAINS AND CULVERTS) IN OSOGBO SITE II | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  |  | 15/10/2014/ MTB | YES | M/S ARCHY PROJECTS LTD | OCT.,2014 | 222,692,032. 63 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
9 | PROVISION OF ACCESS ROAD TO LINK FGN I AND II TO KUJE GWAGWALADA ABUJA | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S DELTA FORCE LTD | OCT.,2014 | 254,633,337. 00 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
10 | CONSTRUCTION OF ROADS PAVEMENT IN FED. HOUSING ESTATE ABUJA | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S DECENCY ASSOCIATES LTD | OCT.,2014 | 102,208,632. 75 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
11 | REHABILITATION OFACCES ROADS, PARKS AND DRIVES WITHIN FEDERAL SECRETARIATE BENIN | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S ALMIGHTY PROJECTS | OCT.,2014 | 60,555,820. 62 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
12 | REHABILITATION OF FIRE FIGHTING SYSTEM AT FEDERAL SECRETARITE COMPLEX KANO | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S CAVUDOX NIG. LTD/ CONTRADE NIG. LTD. | OCT.,2014 | 25,661,045. 39 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
13 | REHABILITATION OF FIRE FIGHTING SYSTEM AT FEDERAL SECRETARITE COMPLEX OWERRI | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S POWERBIRD RESOURCES NIG. LTD | OCT.,2014 | 29,936,681. 25 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
14 | REHABILITATION OF FIRE FIGHTING SYSTEM AT FEDERAL SECRETARITE COMPLEX IKOLABA, IBADAN | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S JODAH NIG, LTD | OCT.,2014 | 33,909,865. 50 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
15 | SUPPLY OF SYSTEM AT FEDERAL SECRETARIATE COMXPLEX, OWERRI | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S OTUGBA TAZIBA NIMORI LTD. | OCT.,2014 | 254,836,848. 00 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
16 | PROCUREMENT AND INSTALLATION OF EQUIPMENT AND WORKING TOOLS FOR LANDUSE AND ALLOCATION COMMITTEE (LUAC) HEADQUARTERS ABUJA | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S FAZAL NIG. LTD | OCT.,2014 | 19,883,850. 50 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
17 | PROCUREMENT, INSTALLATION AND MAINTANANCE OF LAND AND ESTATE MANAGEMENT ABUJA | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S OMAX NIG LTD | OCT.,2014 | 19371975 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
18 | DRAINAGE TO DEVELOP FINANCE INITIATIVE SITE AT ILLORIN | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S INTERNATIONAL & DEVELOPMENT CO. | OCT.,2014 | 120,719,535. 18 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
19 | PROVISION OF ELECTRICITY (OFFSITE-SITES) TO DEVELOP FINANCE ITIATIVE SITE ILLORIN KWARA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S TAHIR INVESTMENT | OCT.,2014 | 11,348,295. 00 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
20 | PROVISION OF INFRASTRUCTURE (ROAD) FOR SOCIAL HOUSING AT CALABAR | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S GOLDALMING WORLDWIDE NIG. LTD | OCT.,2014 | 62,113,122. 75 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
21 | PROVISION OF INFRASTRUCTURE (WATER) FOR SOCIAL HOUSING AT CALABAR | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S EOK GLOBAL LINK | OCT.,2014 | 32,309,162. 65 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
22 | PROVISION OF INFRASTRUCTURE (ELECTRICITY) FOR SOCIAL HOUSING AT CALABAR | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S WOOD KRAFTER LTD | OCT.,2014 | 21452970 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
23 | PROVISION OF INFRASTRUCTURE (DRAINAGE/EROSION CONTROL) TO DEVELOP FINANCE INITIATIVE SITE AT NKWUBOR, ENUGU | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S JERRYNEL CONSTRUCTION CO. LTD | OCT.,2014 | 126,380,362. 50 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
24 | LAYOUT/PERCELATION SURVEY FOR THE SITES & SERVICES AT OKENE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S BUDES ASSOCIATES NIG LTD | OCT.,2014 | 28,750,000. 00 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
25 | CONSTRUCTION OF BUILDING MATERIAL TESTING WORKSHOP GATE HOUSE & PERIMETER FENCE ABUJA. | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S ALLSWELL NIG. LTD | OCT.,2014 | 97478024.61 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
26 | CONSTRUCTION OF 60-ROOMS HOSTEL BLOCK AT ONIKON TRAINING CENTRE LAGOS. | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S SACHEMS INT'L SERVICES NIG. LTD | OCT.,2014 | 124727898 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
27 | CONSTRUCTION OF 3-STOREY BLOCK OF 2-BEDROOMS FLAT (12 FLATS PER BLOCK) AT IKORODU | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S YAMZAL REPROC. NIG LTD | OCT.,2014 | 103,705,888. 23 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
28 | CONSTRUCTION OF 3-STOREY BLOCK OF 2-BEDROOMS FLAT (12 FLATS PER BLOCK) AT IKORODU | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S FROSH NIG LTD | OCT.,2014 | 103,705,888. 23 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
29 | CONSTRUCTION OF 3-STOREY BLOCK OF 2-BEDROOMS FLAT (12 FLATS PER BLOCK) | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S 1ST STEP CONSTRUCTION LTD. | OCT.,2014 | 103,705,888. 24 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
30 | CONSTRUCTION OF 3-STOREY BLOCK OF 2-BEDROOMS FLAT (12 FLATS PER BLOCK) AT IKORODU | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S VIC-PHRANIC NIG. LTD | OCT.,2014 | 103,705,888. 25 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
31 | CONSTRUCTION OF 3-STOREY BLOCK OF 2-BEDROOMS FLAT (12 FLATS PER BLOCK) AT IKORODU | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S AE&E NIG LTD | OCT.,2014 | 103,705,888. 26 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
32 | CONSTRUCTION OF 3-STOREY BLOCK OF 2-BEDROOMS FLAT (12 FLATS PER BLOCK) AT IKORODU | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S SACOTEL NIG. LTD. | OCT.,2014 | 103,705,888. 27 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
33 | CONSTRUCTION OF 3-STOREY BLOCK OF 2-BEDROOMS FLAT (12 FLATS PER BLOCK) AT IKORODU | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S FRANCO FINISHING NIG. LTD | OCT.,2014 | 103,705,888. 28 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
34 | CONSTRUCTION OF 3-STOREY BLOCK OF 2-BEDROOMS FLAT (12 FLATS PER BLOCK) AT IKORODU | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S ABIGRANT NIG LTD | OCT.,2014 | 103,705,888. 29 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
35 | CONSTRUCTION OF 3-STOREY BLOCK OF 2-BEDROOMS FLAT (12 FLATS PER BLOCK) AT IKORODU | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/SVERIFY CONCEPTS NIG. LTD | OCT.,2014 | 103,705,888. 30 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
36 | CONSTRUCTION OF 3-STOREY BLOCK OF 2-BEDROOMS FLAT (12 FLATS PER BLOCK) AT IKORODU | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S CONTINENTAL TRADING SERVICES LTD. | OCT.,2014 | 103,705,888. 31 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
37 | CONSTRUCTION OF 3-STOREY BLOCK OF 2-BEDROOMS FLAT (12 FLATS PER BLOCK) AT IKORODU | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S DINAMIC GLOBAL CONSTR. & ENGR. LTD | OCT.,2014 | 103,705,888. 32 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
38 | CONSTRUCTION OF 3-STOREY BLOCK OF 2-BEDROOMS FLAT (12 FLATS PER BLOCK) AT IKORODU | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S OLUBUCK NIG. LTD | OCT.,2014 | 103,705,888. 33 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
39 | PROVISION OF EXTERNAL ELECTRICITY IGBOGBO , IKORODU | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S STABLE TECH. LTD. | OCT.,2014 | 128686796.3 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
40 | PROVISION WATER SUPPLY AT IGBOGBO , IKORODU | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S SABTECH TOWERS NIG LTD | OCT.,2014 | 53119492.5 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
41 | COMPLETION OF MODIFY OFFICE EXTENSION AT FMLHUD HEADQUARTERS ABUJA | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S ROYAL VALUE INT'L NIG LTD. | OCT.,2014 | 136539251.11 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
42 | PROVISION OF ACCESS (OFF-SITE) ROAD AND DRAINAGES TO DEVELOP FINANCE INITIATIVE SITE AT ILESHA | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S MAINSTREAM CONTRACTORS NIG. LTD | OCT.,2014 | 147958783.23 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
43 | PROVISION OF INFRASTRUCTURE (ROAD AND DRAINAGE) FOR SOCIAL HOUSING ORON | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S A.G. VISION | OCT.,2014 | 243179212.5 | 2 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
1 | COMPLICTION OF WORKS AT NYANYA LABOUR CAMP ABUJA FCT | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 5/10/2014/ MTB | YES | M/S. COSMOS ENGINEERING NIG. LTD | OCT.,2014 | 34000000 | 10 WEEKS | NOV.,2014 |  | 10 WEEKS | N/A |  | N/A | N/A
2 | COMPLETION OF EZWNRI PlCE NARI ANAOCHA LGA ANAMBRA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S. PARLARJONNA GLOBAL RESC. LTD | OCT.,2014 | 24500000 | 10 WEEKS | NOV.,2014 |  | 10 WEEKS | N/A |  | N/A | N/A
3 | COMPLETION OF CONVENTIONAL STREET LIGHT AT BONNY TOWN PHASE 11 RIVERS STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S. TLMB CONSTRUCTION LTD | OCT.,2014 | 32500000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
4 | CONSTRUCTION OF BOREHOLE AT KADEMI AND ALBASU KANO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S. AL BUSHARA NIG LTD | OCT.,2014 | 30250000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
5 | COMPLETION OF 2 BLOCK OF CLASSROOM AT LAMORDE ADAMAWA STATE. | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | DWELL SERVICES NIG. LTD | OCT.,2014 | 10200000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
6 | COMPLEETION OF GONIRI ROAD YOBE STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S. YOBE ENGINEERING LTD | OCT.,2014 | 30250000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
7 | CONSTRUCTION OF MARKET STALL AND WATER SUPPLY AT BIDA CENTRAL MARKET NIGER STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S. REDWOOD INTEGRATED SERVICES LTD | OCT.,2014 | 18300000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
8 | PROVISION OF BLOCK OF 2 CLASSROOM BLOCK AT EKAN MEJE OKE ERO LGA, KWARA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S. AUSCHRIS GEOSPATIAL NIG LTD | OCT.,2014 | 12800000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
9 | PROVISION OF COMMUNITY BASED WATER SUPPLY AT EKAN MEJE OKE ERO LGA | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S. ADELEKE AWOYEMI ARELOWO & ASSOCIATES LTD | OCT.,2014 | 7200000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
10 | 2 NOS OF VOCATIONAL TRANING CENTRE IN VARIOUS LOCATION OF AKA IBOM STATE IGINTA ORON | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S JKR SYNERGY LTD | OCT.,2014 | 33000000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
11 | CONSTRUCTION OF ONE BLOCK OF THREE (3) CLASSROOM STAFF OFFICE AND TOILET IN IVOGBA, MBAYEM, USHOGO LGA BENUE STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S.ISRAB CONCEPT NIG. LTD | OCT.,2014 | 15800000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
12 | CONSTRUCTION AND COMPLETION OF TOWN HALL IN AWE, AWE/DOMA/KEMA FEDERAL CONSTITURNCY, NASARAWA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S. HARDY CRUST NIG. LTD | OCT.,2014 | 18000000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
13 | CONSTRUCTION OF SKILL ACQUISITION CENTRE WITH EQUIPMENT AT UMUAWULU ANAMBRA STATE. | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S.OMAX NIG. LTD | OCT.,2014 | 12,800,00.00 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
14 | COMPLETION OF COMMUNITY CENTRE AT AWLAW ENUGU | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S CHRISTABBS INVESTMENTS LTD | OCT.,2014 | 20080000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
15 | CONSTRUCTION OF 2 CLASSROOM BLOCK ATOLOGOGBE BAYELSA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S OGISO SW CONSTRUCTION WA LTD | OCT.,2014 | 12100000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
16 | CONSTRUCTION OF 3NOS VOCATIONAL CENTRES IN ESSIEN UDIM, IKONO, ETINAN LGAS, AKWA-IBOM | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S LAMPLIGHT NIG. LTD. | OCT.,2014 | 60100000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
17 | CONSTRUCTION OF 3NOS VOCATIONAL CENTRES IN AKARA, ORON AND IKA LGAS, AKWA-IBOM | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S BANKSFORTE GLOBAL LTD | OCT.,2014 | 60100000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
18 | CONSTRUCTION OF COMMUNITY CENTRE WITH SPORTS FACILITY AT OKODI OGBIA LGA, BAYELSA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S HARJOKES LIMITED | OCT.,2014 | 14000000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
19 | CONSTRUCTION OF CLASSROOMS AT GAYA, GAYA LGA, KANO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S ACCURATE INTER-CONTINENTAL LTD | OCT.,2014 | 8900000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
20 | CONSTRUCTION OF CIVIC CENTRE WITH FURNISHING AT ODO OSIN ASA LGA | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 15/10/2014/ MTB | YES | M/S COSBY NIGERIA LTD | OCT.,2014 | 18900000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
21 | CONSTRUCTION OF COMMUNITY HALL AGBAMU KWARA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S AFFIXING INTEGRATED SERVICES LTD | OCT.,2014 | 13250000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
22 | RENOVATION OF BLOCK OF 2 CLASSROOMS WITH FURNITURE AT YAWURMA PRIMARY SCH. ALBASU LGA. KANO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S FAS PANDA NIG. LTD. | OCT.,2014 | 7500000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
23 | CONSTRUCTION OF 1NO BLOCK OF 3 CLASSROOM EACH AT SUPARE AKOKO ONDO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S ICADOVA NIGERIA LTD. | OCT.,2014 | 11040000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
24 | CONSTRUCTION OF 1NO BLOCK OF 3 CLASSROOM BLOCK AND PERIMETER FENCE AT PRIMARY SCHOOL IDUA ASANG ORON AKWA-IBOM | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S MACAIRE CONSULT LTD | OCT.,2014 | 35500000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
25 | CONSTRUCTION OF MULTI-PURPOSE HALL WITH FURNISHING IN IQUITA, ORON LGA, AKWA-IBOM | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S DIAMOND SQUARE LTD. | OCT.,2014 | 45000000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
| CONSTRUCTION OF 1NO BLOCK OF 3 CLASSROOM EACH FOR POLICE CHILDREN SCHOOL, OGBOMOSHO OYO CENTRAL SANATORIAL DISTRICT, OYO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S MIDLAND R. V. LTD. | OCT.,2014 | 11040000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
26 | CONSTRUCTION OF 1NO BLOCK OF 3 CLASSROOM EACH FOR POLICE CHILDREN SCHOOL, OGBOMOSHO OYO CENTRAL SANATORIAL DISTRICT, OYO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S RASTON NIG. LTD. | OCT.,2014 | 11040000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
27 | CONSTRUCTION OF 1NO BLOCK OF 3 CLASSROOM AT ARABIC TRAINING CENTER (MARKAZ) AGEGE LAGOS STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S PVEEM NIG. LTD. | OCT.,2014 | 11040000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
28 | SKILL ACQUISITION CENTRE, IRESADU, OYO CENTRAL SANATORIAL DISTRICT, OYO STATE. | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S HEIRS NIG LTD | OCT.,2014 | 18000000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
29 | UPGRADING OF TOWNSHIP INFRASTRUCTURE (ROADS AND DRAINAGE IN KORAMA, OKU OFODUO ADUN BEACH IN OBUBRA AND BENDEGHE EKIEM IN ETUNG LGA | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S LONG HORN CONSTRUCTION LTD | OCT.,2014 | 220350000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
30 | UPGRADING OF TOWNSHIP INFRASTRUCTURE (ROADS AND DRAINAGES IN GADAGE AND KARO KADUNA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S ROYAL GATE GLOBAL CONTRACTER LTD. | OCT.,2014 | 225500000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
31 | UPGRADING OF TOWNSHIP INFRASTURE ROADS AND DRAINAGES IN MAHUTA AND GALADIMAWA SOKOTO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S ALL PHASE CONSTRUCTION LTD | OCT.,2014 | 220000000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
32 | KAYARDA-DAM ALHAJI FEEDER ROAD IN SAMINAKA LOCAL GOVERNMENT OF KADUNA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S ASSWORTH VENTURES LTD | OCT.,2014 | 90100000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
33 | URBAN RENEWAL AND SLUMP UPGRADING: CONSTRUCTION OF TORAUKE-DAGAJI, GAMJI ROAD, SOKOTO STATE. | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S VEECATEL GLOBAL LTD | OCT.,2014 | 130100000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
34 | UPGRADE OF ACCESS ROADS INTO THE REGENT SECONDARY SCHOOL, MABUSHI | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S LEGEND OTOLORIN CONSTRUCTION LTD | OCT.,2014 | 45100000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
35 | URBAN RENEWAL AND SLUM UPGRADING: COMPLETION OF BASHAR GUDUS ROAD, WASE LGA, PLATEAU STATE. | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S SEM-LUK VENTURES LTD | OCT.,2014 | 70200000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
36 | UPGRADING OF INFRASTRACTURE CONSTRUCTION OF PATHS AND DRIVEWAYS SECTION 2 AT FULANI WARD ILORIN KWARA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S ELEKU CONSTRUCTION LTD. | OCT.,2014 | 40100000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
37 | CONSTRUCTION OF UMUOKORO AMAUKWU UMUOKAZI ROAD (SPUR TO ONWULIRIS) AMUZI AHIAZU LGA IMO STATE. | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S TIMDOZ ENGINEERING NIG. LTD. | OCT.,2014 | 75080000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
38 | CONSTRUCTION OF BAYELSA/EKEREMO ROAD | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S EBIKEWENEMOR NIG LTD | OCT.,2014 | 27208690 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
39 | REHABILITATION OF ROAD AT ADAZINNUKWU ANAOCHA LGA, ANAMBRA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | MIC TINAPEX INTERNATIONAL LTD | OCT.,2014 | 40100000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
40 | CONSTRUCTION OF ROAD AT SALIU GIWA STREET OZIOKUTU, NEW ZANGO LAYOUT OKENE/KABBA ROAD, KOGI STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | IBREM STANDARD ESTERPRISES | OCT.,2014 | 25600000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
41 | CONSTRUCTION OF ROAD AT JAMA"ARE BAUCHI STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | BAWASA NIGERIA LTD | OCT.,2014 | 40080000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
42 | CONSTRUCTION OF ROAD AT RUMUODOMAYA AGRIC STAFF QUARTERS, RIVERS STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | GOAL UMMAD NIG LTD | OCT.,2014 | 18700000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
43 | CONSTRUCTION OF ROAD AT ALOR IDEMILI NOTH LGA, NAAMBRA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8TH MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S FRACTL NIG. LTD | OCT.,2014 | 63050000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
44 | CONSTRUCTION ROADS AND DRAINAGE IN FEDERAL HOUSING ESTATE UYO AKWA IBOM STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | ZULMA RESOURCES NIGERIA LTD | OCT.,2014 | 91193177.5 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
45 | CONSTRUCTION OF AYEGBAJU ROAD FROM HON. MATHEW TO CHIEF AKOGUN HOUSE AND ARIKINKIN JUNCTION TO ISALE GBEKE LINKING GBOGAN IN ORILE OWU, OSUN STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | OMEGA ALPHA CONSTRUCTION COMPANY LTD | OCT.,2014 | 171005830 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
46 | CONSTRUCTIONOF ROADS AND DRAINAGE PARTY ROAD OFF EBUGHU ORUN AKWA IBOM STAE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | IIC CONSTRUCTION COMPANY LTD | OCT.,2014 | 56600000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
47 | CONSTRUCTION OF SUPO PHOTO HOUSE OF APOMU/ORILE OWU ROAD TO ST. PAUL'S JUNCTION IN ORILE OWU, OSUN STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | TLMB VONDTRUCTION LTD | OCT.,2014 | 101400000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
48 | CONSTRUCTION OF ORIDUNBSRE ROAD LINKING CHIEF OTUN LAMIDE HOUSE WITH SOLAR STREET LIGHT IN ORILE OWU, OSUN STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M/S MEMTAZ GLOBAL RESOURCES LTD | OCT.,2014 | 135000000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
49 | PROVISION OF SOLAR SSTREET ;IGHT AT KORAMA, OKU, AJASSOR IN ETUNG LGA AND OCHON ISABANG IN OBUBRA LGA CROSS RIVERS | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | WELZY NIGEIA LTD | OCT.,2014 | 115000000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
50 | CONSTRUCTION OF COMMUNITY BASED WATER SUPPLY AT KORAMA CROSS RIVERS STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | CAVINA CONSTRUCTION AND DESIGN | OCT.,2014 | 7200000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
51 | PROVISION OF POWER SUPPLY AND SOLAR STREET LIGHT,IN, GADAGE AND KARO | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | SHERAZ INTERNATIONAL RESOURCES NIG. LTD | OCT.,2014 | 78000000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
52 | PROVISION OF POWERED SUPPLY SCHEME IN MAHUTA AND GALADIMAWA SOKOTO, SOKOTO | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | CHARlotte project concept ltd | OCT.,2014 | 80000000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
53 | SOLAR STREET LIGHT IN WURNO AND RABAH SOKOTO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | QURID INTERBIZ LTD | OCT.,2014 | 55100000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
54 | CONSTRUCTION AND INSTALLATION OF SOLAR STREET LIGHTS AT BODA FOBUR DISTRICT,
55 | PROVISION OF SOLAR STREET LIGHTS AT IKOT IDEM ETIM-ABIAKPOR, EKOI VILLAGE OFF UMUAHIA ROAD B, IKOT EKPENE, UKANA IKOT OFOK-ESSIEN UDIM, AND NTO IDE IKOT EMEH-OBOT AKARA AKWA IBOM STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | A.C. LINK NIGERIA LTD | OCT.,2014 | 65001000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
56 | CONSTRUCTION OF SOLAR STREEET LIGHT IN WASE TOWN, WASE LGA PLATEAU STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | FOLADIF NIG. LTD | OCT.,2014 | 70050000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
57 | POWER SUPPLY AND DISTRIBUTION INCLUDING INSTALLATION OF 500KVA TRANSFORMER ETITI-MBGIDI UMUOKPARA ETITI-MGBIDI AND UMUORJI MGBIDI-AUTONOMOUS ORU WEST LGA, IMO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | AMIJAPP NIG. LTD | OCT.,2014 | 25100000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
58 | provision of 500kva transformer at amanmamwu-umuabiahu, imo | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | M.S AKOWIND NIGERIA LTD | OCT.,2014 | 70800000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
59 | PROVISION OF SOLAR STREET LIGHT IN GRA, OFFA COMMUNITY, OFFA LGA KWA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | MAPLE-RUN GLOBAL RESOURCES | OCT.,2014 | 7500000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
60 | PROVISION OF TRANSFORMET AT IKOT OSUKPONG AKWA IBOM STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | AJARAYAMTU CORPORATE BUSINESS | OCT.,2014 | 14200000 | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
61 | PROVISION OF 500KVA TRANSFORMET AT BWONPE AMPANG WEST DISTICT MANGU LGA, PLATEAU STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | HABIUKU NIG. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
62 | COMPLETION OF ELECTRIFICATION AT AWO AKPALI, KOGI STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | JUMART JOE NIG. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
63 | RETICULATION AND ELECTRIFICTION AT ANCHIMOGBO IYECHE, OJU BENUE STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | BEDAS HUMAN RESOURCES MANAGEMENT | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
64 | PROVISION OF SOALR POWER STREET LIGHT AT IPOTI EKITI | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | FEM INTEGRATED CONCEPTS SERVICES | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
65 | PROVISION OF STREET LIGHT AT OBBO ILE KWARA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | MUTIBIZ ADEBUMI NIGERIA LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
66 | PROVISION OF SOLAR STREET LIGHT AT AYEGBAJU ROAD, SUPO PHOTO HOUSE, ORISUNBARE ROAD AND OBALUFON ROAD ORILE OWU, OSUN STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | FARIQ INTERBIZ LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
67 | PROVISION OF SOLAR STREET LIGHT AT IYAMOYE, IJUMU LGA, KOGI STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | REDBRICKS CONSTRUCTION LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
68 | PROVISION OF TWO SOLAR POWERED MOTORIZED BOREHOLES IN KIYAWA/DUTSE LGA IN JIGAWA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | FLOH GENERAL LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
69 | INSTALLATION OF SOLAR POWERED BOREHOLES AT 27 OHI QUARTERS IFFE IJUMU IJUMU LGA, KOGI STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | SKAVITO NIG. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
70 | INSTALLATION OF SOLAR POWERED BOREHOLES IN TWO LOCATION IN JERE FEDERAL CONSTITUENCY, BAUCHI STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | GUMIK NIG. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
71 | CONSTRUCTION OF MOTORISED BOREHOLES AT ILORIN WEST LGA 1 KWARA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | WHYKAY GLOBAL SERVICES LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
72 | CONSTRUCTION OF HAND PUMP BOREHOLE AT IREE, OSUN STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | TELYAKOK NIGERIA LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
73 | CONSTRUCTION OF MOTORISED BOREHOLES AT ILORIN WEST LGA 2 KWARA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | BABAGONA NIGEIA LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
74 | CONSTRUCTION OF 6NO COMMUNITY BASED WATER SUPPLY SCHEMES IN ILORIN/ASA ENVIRONS, KWARA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | DINAMIKI INVESTMENT NIG. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
75 | CONSTRUCTION OF COMMUNITY BASED WATER SUPPLY SCHEMES IN OJUEKUN, ZARUMI WARD, KWARA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | skynet synergy nig. Ltd | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
76 | construction of community based water supply schemes baboko ward 3, kwara state | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | KSNMI-OLS NIGERIA LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
77 | CONSTRUCTION OF COMMUNITY WATER SUPPLY SCHEMES IN OKO ERIN WARD, KWARA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | ALFRED CHARLES CONSULT | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
78 | CONSTRUCTION OF COMMUNITY BASED WATER SUPPLY SCHEMES IN ALANAMU WRDS, KWARA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | ELDERMAN LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
79 | CONSTRUCTION OF COMMUNITY BASED WATER SUPPLY SCHEMES IN MAGAJIN GERI WARD, KWARA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | SAWALIZ NIG. LLTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
80 | CONSTRUCTION OF COMMUNITY BASED WATER SUPPLY SCHEMES IN ODE GIWA, KWARA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | DESK TIDY RESOURCES ENTERPRISES | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
81 | CONSTRUCTION OF COMMUNITY BASED WATER SUPPLY SCHEMES IN BUDO EGBA, KWARA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | KAOLDESH NIGERIA LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
82 | CONSTRUCTION OF COMMUNITY BASEDD WATER SUPPLY SCHEMES IN APATA, KWARA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | FURAME ENARGY RESOURCES LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
83 | CONSTRUCTION OF COMMUNITY BASED WATER SUPPLY SCHEMES IN AFON, KWARA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | LOAT NIGERIA LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
84 | CONSTRUCTION OF COMMUNITY BASED WATER SUPPLY SCHEMES IN OMOLE, KWARA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | RAJID CONSTRUCTION NIG. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
85 | CONSTRUCTION OF COMMUNITY BASED WATER SUPPLY SCHEMES IN UMUHU OKABIA ORLU LGA, IMO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | AFRI TECH. PROJECT AND CONSULTANCY SERVICES | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
86 | COMMUNITY BASED MOTORISED BOREHOLE WATER SUPPLY WITH PUBLIC STAND POSTS IN UMU-IWURKE UMUOKPARA, NWANGELE LGA, IMO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | WEB NIG. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
87 | CONSTRUCTION OF MOTORISED BOREHOLE IN ST. PAUL's CATHOLIC CHURCH, IVOGBA MBAYEM USHONGO LGA, BENUE STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | CONIELO NIG. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
88 | water supply at badagry west agorin beach lagos sate | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | OKE MEJE GLOBAL RESOURCES LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
89 | COMMUNITY WATER SUPPLY AT ADZI NNUKWU ANAOCHA LGA, ANAMBRA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | JEMISI AND COMPANY LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
90 | COSTRUCTION OF 3 NOS SOLAR BOREHOLE AT AKOKO EDO | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | HYDRO-SYSTEM DESIGN AND CONSTRUCTION NIG. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
91 | CONSTRUCTION OF 2NOS COMMUNITY BASE WATER SCHEME AT IGBO AKA EDUCATIONAL CENTER, OYO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | MORASHAT NIGERIA LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
92 | CONSTRUCTION OF COMMUNITY BASED WATER SCHEME, ODI OLOWO, FIELD AREA, OKE ESO AREA, ODI OLOWA WATER RESERVIOUR, APENA COMPOUND, SASA AREA AND APENA COMPOUND 2 ORILE OWU, OSUN STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | LEKTUN ROYAL GEO SERVICES LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
93 | CONSTRUCTION OF COMMUNITY BASED WATER SCHEME IN OLUGBON HOUSE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | ZARAB VENTURES LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
94 | CONSTRUCTION OF PUBLIC TOILETS IN OLUGBON HOUSE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | MUNAB INTEGRATED | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
95 | CONSTRUCTION OF COMMUNITY BASED WATER SCHEME AND PUBLIC TOILETS IN EJEMU COMPOUND ORILE OWU | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | CHOICE CHEMICAL AND ALLIED PRODUCTS LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
96 | CONSTRUCTION OF COMMUNITY BASED WATER SCHEME AND PUBLIC TOILETS IN CATERPILLA AREA/APOSTOLIC ORILE OWU, OSUN STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | FAJ-ULTIMATE CONCEPT LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
97 | CONSTRUCTION OF COMMUNITY BASED WATER SCHEME AND PUBLIC TOILETS IN BAALE EXTENSION ORILE OWU, OSUN STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | SKY EDGE GLOBAL SOLUTION NIG. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
98 | CONSTRUCTION OF ONE BLOCK OF TWO (2) CLASSROOM IN UZEBBA (Oronya) INLEHA OWAN WEST LGA EDO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | PRIME TAAD NIG. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
99 | MOTORIZED POWER BOREHOLE AT ORKUMA KATYO COMPOUND, MBATOV USHONGO, BENUE STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | ESIVIC NIGEIA LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
100 | CONSTRUCTION OF 1 NO BLOCK OF TWO CLASSROOMS AT BALGADI IN SOBA FEDERAL CONSTITUENCY, KADUNA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | SATGUARD INTERGRARED SERVICES NIG. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
101 | CONSTRUCTION OF CLASSROOM IN DUDI PRIMARY SCHOOL MALUNFASHI LGA, KATSINA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | ZEPPLLIN INTERNATIONAL CONCEPT LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
102 | SOLAR POWERED BOREHOLES AT OKE IFE STREET ,OKOOKO, IPETUMUDU, OSUN STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | PERAI GLOBAL SERVICES | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
103 | SOLAR POWERED BOREHOLES AT MORIGI STREET ,OKOOKO, IPETUMUDU, OSUN STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | NDCA CONSTRUCTION & ENGINEERING COMPANY NIGERIA | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
104 | PROVISION OF 1NO SOLAR POWERED MOTORIZED BOREHOLES IN KIYAWA/DUTSE LG IN JIGAWA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | DECHALAL GLOBAL SERVICES LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
105 | CONSTRUCTION OF 2 BLOCKS CLASSROOMS IN DUDI PRIMARY SCHOOLMALUMFASHI LGA, KATSINA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | JAFAAR LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
106 | CONSTRUCTION OF 2 BLOCKS CLASSROOMS AT JIGAWA DAY SECONDARY SCHOOL BABURA LGA, JIGAWA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | TENUP NIG LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
107 | SOLAR STREET LIGHT AT KYARANA KIRU LGA, KANO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | LUKANE ORIN NIG LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
108 | CONSTRUCTION OF SKILL ACQUISITION CENTRE WITH EQUIPMENT AT AKU, IGBO EKITI LGA, ENUGU STATE. | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | DAMIR LINKS LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
109 | EQUIPPING OF SKILL ACQUISITION CENTRE AT AKU, IGBO EKITI LGA, ENUGU STATE. | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | BOND ORGANISATION CO. LTD. | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
110 | CONSTRUCTION OF COMMUNITY BASSED WATER SUPPLY SCHEMES AT SOSBA FEDERAL CONSTITUENCY, KADUNA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | LARAM NIG.LTD. | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
111 | CONSTRUCTION OF HAND PUMP AT IREE OSUN STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | NURDELAK RESOURCES LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
112 | CONSTRUCTION OF SOLAR STREET LIGHT AT OBANIKORO STREET LAGOS ISLAND. | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | EXCELSIOR NIG. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
113 | CONSTRUCTION OF BLOCK OF CLASSROOM AT UNGEAN TASHE TUDUN WADA LGA, KANO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | APPLE EYE NIG. ENTERPRISES | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
114 | CONSTRUCTION OF SKILLS ACQUISITION CENTRE IN GORONVO TOWN GORONYO LGS SOKOTO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | MUDIS KINGSLEG LTD. | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
115 | PROVISION OF HAND PUMP IN WUDIL LGA, KANO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | ABAME INVESTMENT LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
116 | CONSTRUCTION OF SKILLS ACQUISITION CENTRE IN KASSE IN GADA LG SOKOTO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | EASTWIND INVESTMENT LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
117 | CONSTRUCTION OF NOS OF SKILLS ACQUISITION CENTRES IN GADA IN GADA LGA, SOKOTO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | MUTBAR CONTINENTAL INT'L | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
118 | COMMUNITY WATER SUPPLY SCHEME AT WUDIL LGA, KANO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | ROCK 1 GLOBAL CONCEPTS NIG. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
119 | CONSTRUCTION OF COMMUNITY WATER BASED SUPPLY SCHEMES AT SOBA FEDERAL CONSTITUENCY, KADUNA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | EL-NASIR VENTURES LTD. | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
120 | PROVISION OF TRANSFORMER AT CENTRAL MOSQUE IREE OSUN | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | JUMSEN INTEGRATED SERVICES LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
121 | CONSTRUCTION OF COMMUNITY BASED WATER SUPPLY SCHEMES AT PRINCE OBIORO MGBAKOR'S COMPOUND AMAJANOLI NEW LAYOUT AMADIE VILLAGE IFITE - OGWARI AYAMELUM LGA, ANAMBRA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | NONNOLLY WEST LTD. | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
122 | COMPLETION OF ALAKE'S PALACE IN ABEOKUTA OGUN STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | HIGHDELL INVESTMENTS LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
123 | CONSTRUCTION OF COTTAGE HOSPITAL AND WATER SUPPLY AT DUMBULWA FIKA LGA YOBE STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | HAQ CONSTRUCTION LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
124 | CONSTRUCTION OF BLOCK OF CLASSROOM AND TOILET AT AGALISA (ETUKWU) TOWN IN ALAMABORO LGA, KOGI STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | SSAN ZAMAT ENTERPRISES | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
125 | CONSTRUCTION OF COMMUNITY BASED WATER SUPPLY SCHEMES AT SOBA FEDERAL CONSTITUENCY, KADUNA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | BAMO PROPERTY NIG. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
126 | CONSTRUCTION OF 2 NOS HAND PUMP AT BAPTIST LSMB PRIMARY SCHOOL MOPA KOGI STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | BABSTECH GLOBAL SERVICES LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
127 | CONSTRUCTION OF COMMUNITY BASED WATER SUPPLY SCHEMES AT SOBA FEDERAL CONSTITUENCY, KADUNA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | CAMEL NIGERIA LTD. | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
128 | PROVISION OF SOLAR POWERED STREET LIGHT AT OSUMA/OGBE STREET, EDO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | FOJOLAHD INVESTMENTS LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
129 | CONSTRUCTION OF BLOCK OF CLASSROOM AT ANSARUL ISLAM PRIMARY SCHOOL IREE OSUN | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | RAPID TECHNOLISM & INVESTMENT | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
130 | COMMUNITY BASED WATER SUPPLY AT ILA ORANGUN OSUN STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | ADASICA STATE | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
131 | PROVISION OF SOLAR STREET LIGHT AT LADUBA ASA LGA KWARA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | OMATAHAB NIG. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
132 | PROVISION OF TRANSFORMER AT AIYETORO QUARTERS ILESA WEST OSUN STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | PUMECO INDUSTRIES NIG. LTD. | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
133 | REHABILITATION OF ROAD & ASPHALTING AT OGUANOGBE STREET, OGBE COMMUNITY, EDO STATE. | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | MUNIR INDUSTRIES & TADE NIG. LTD. | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
134 | PROVISION OF SOLAR STREET LIGHT AT ARABIC TRAINING CENTER (MAKRAZ) AGEGE LAGOS STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | EDDY BEN VENTURES NIGERIA SERVICES LTD. | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
135 | PROVISION OF SOLAR POWERED STREET LIGHT AT IGUN STREET, FROM 1ST EAST CIRCULAR TO AGBADO STREET, EDO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | KURFI INTEGRATED SERVICES LTD. | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
136 | CONSTRUCTION OF BATTAYA ALBASU ROAD KANO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | D + H NIGERIA LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
137 | CONSTRUCTION OF GAYA BALARE ROAD KANO. | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | MITECK TECH SERV. NIG. LTD. | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
138 | CONSTRUCTION OF COMMUNITY BASED WATER SUPPLY SCHEMES AT SA ASALA AREA OTAN AIYEGBAJU OSUN STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | HENDON NIG. LTD. | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
139 | COMMUNITY TOWN HALL, ST. PETER'S CATHEDRAL COMPOUND, OKRIKA LGA, RIVERS STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | ANDRO MEDIA INTEGRATED LTD. | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
140 | CONSTRUCTION OF BLOCK OF CLASSROOM AT BAPTIST HIGH SCHOOL IREE KOGI STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | ELECO WORKS | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
141 | CONSTRUCTION OF BLOCK OF CLASSROOM AT BAPTIST LSMB PRIMARY SCHOOL MOPA KOGI STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | PFAZE CONTRACTORS LTD. | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
142 | CONSTRUCTION OF MARKET STALL AT OMUHU OKABIA ORLU LGA IMO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | MOGALINK LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
143 | CONSTRUCTION OF COMMUNITY BASED WATER SUPPLY SCHEMES AT EMURE EKITI, EKITI STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | DESTINE CHILD NIG. LTD. | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
144 | CONSTRUCTION OF COMMUNITY BASED WATER SUPPLY SCHEMS AT OKOLOMESIKE SQUARE IFITE OGBUNIKE OYI LGA ANAMBRA | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | IFESON INT'L CONCEPT | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
145 | CONSTRUCTION OF COMMUNITY BASED WATER SUPPLY SCHEMES AT LIMAN ZANGINA STREET BY MAGAJI UMARU KALGO HOUSE NASARAWA BIRNIN KEBBI, KEBBI STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | OJ KINGS NIG. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
146 | CONSTRUCTION OF MARKET STALLS AT OMUHU OKABIA ORLU LGA IMO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | PER NIGERIA LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
147 | PROVISION OF HAND PUMP BOREHOLE AT OKE ARE IREE OSUN STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | DAYDOT NIG. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
148 | PROVISION OF HAND PUMP BOREHOLE AT SUPARE AKOKO ONDO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | STRUCT-CON NIGERIA LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
149 | CONSTRUCTION OF BLOCK OF CLASSROOM AT GOV'T COLLEGE KEFFI NASARAWA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | STHORMS NIG. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
150 | PROVISION OF HAND PUMP AT IFFE IJUMU PRIMARY SCHOOL KEFFI, NASARAWA STATE. | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | FLAY VENTURES | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
151 | PROVISION OF HAND PUMP BOREHOLE AT GOV'T COLLEGE KEFFI, NASARAWA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | U.U.ILO NIG. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
152 | INSTALLATION OF SOALR STREET LIGHT AT KUTIGI AND EDATI TOWN IN NIGER STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | DENSE GLOBAL INVESTMENT LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
153 | INSTALLATION OF SOLAR STREEET LIGHT AT KUTIGI, MOKWA AND EDATI TOWN IN NIGER STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | SABITI NIG. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
154 | CONSTRUCTION OF EARTH ROAD ADUM EAST (OBI LGA) ANYIBO FARM BENUE STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | TORA BORA NIG. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
155 | CONSTRUCTION OF COMMUNITY BASED WATER SUPPLY SCHEMES AT KORNYA/KONSHISHA LGA BENUE STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | TALL DREAMS CO, NIG. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
156 | CONSTRUCTION OF BLOCK OF 2 CLASSROOM AT COMMUNITY SECONDARY SCHOOL IJAGODO AKPANYA, IGALAMELA-ODOLU LGA KOGI STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | HONNIE BAZ NIGERIA LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
157 | CONSTRUCTION OF COMMUNITY BASED WATER SUPPLY SCHEMES AT OLUNLADE KAMBU SURULERE ILORIN KWARA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | ASMAJUWON NIG. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
158 | CONSTRUCTION OF EROSION CONTROL AT KONTAGORA PHASE III LGA, NIGER STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | CONVENTRICS TECHONOLOGY LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
159 | CONSTRUCTION OF COMMUNITY BASED WATER SUPPLY SCHEMES AT ILE OYE EJIGBO OSUN | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | DUAL DESIGN COMPANY LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
160 | CONSTRUCTION OF COMMUNITY BASED WATER SUPPLY SCHEMES AT OKE AMUTUTU STREET ARAMOKO EKITI EKITI WEST LGA EKITI STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | NASMOJI NIGERIA LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
161 | CONSTRUCTION OF COMMUNITY BASED WATER SUPPLY SCHEME AT OLUBEKE COMPOUND MASIFA OGBOMOSHO, OYO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | SAHADAT CONSTRUCTION CO. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
162 | PROVISION OF TRANSFORMER AT EMURE EKITI EKITI STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | EXPO CREATIONS LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
163 | PROVISION OF HAND PUMP BOREHOLE AT SOUN HIGH SCHOOL OGBOMOSHO OYO SSTATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | DIAS RESOURCES AND LOGISTICS LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
164 | CONSTRUCTION OF COMMUNITY BASED WATER SUPPLY SCHEMES AT LIGEGERE STREEET AKE ABEOKUTA | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | SILVERGREY ENTERPRISES LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
165 | CONSTRUCTION OF HEALTH CENTER AT aramoko ekiti ekiti west lga ekiti state | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | yobetech nig. Ltd | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
166 | PROVISION OF TRANSFORMER AND RETICULATION AT SANTA MARIA ESTATE, AKA, EFFA RESIDENTIAL LAYOUT OFF MCC ROAD CALABAR, CROSS RIVER STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | BIMAZ PROJECTS LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
167 | CONSTRUCTION OF MOTORISED BOREHOLE AT NNABUIKE NZEH COMPOUND OBODO EGBU ISIKWE VILLAGE ACHI OJI RIVER LGA ENUGU STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | STAN-JAY ENDEAVOURS LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
168 | CONSTRUCTION OF MOTORISED BOREEHOLE AT IGBUISHEGBA IN EDEOHA EAST LGA OF ROVERS STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | MNIC NIGERIA LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
169 | CONSTRUCTION OF COMMUNITY BASED WATER SUPPLY SCHEMES AT OGIRIGA NEW SITE OKUGBE OKPELLA ETSAKO EAST LGA, EDO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | MEFANO VENTURES LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
170 | CONSTRUCTION OF COMMUNITY BASED WATER SUPPLY SCHEMES AT UMUAFIA COMPOUND MKPOLOWU VILLAGE UKEHE, ENUGU STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | TYONEX NIG. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
171 | CONSTRUCTION OF UMUOKASI OPARAEHI ROAD AMUZI AHIAZU LGA, IMO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | TIMDOZ ENGINEERING NIG. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
172 | PROVISION OF SOLAR POWERD BOREHOLE AT TSE PUUSU KWANDE LGA BENUE STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | KARIF BASE RESOURCES NIG. LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
173 | CONSTRUCTION OF MOTORISED BOREHOLE AT GARKO ACEDEMY GAMAWA IN GAMAWA LGA, BAUCHI STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | ADOLAKS KONTINENTAL LTD LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
174 | PROVISION OSOLAR STRET LIGHT AT SAKI WEST FEDERAL CONSTITUENCY OYO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | MOHAWI INTERNATIONAL LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
175 | SUPPLY AND INSTALLATION OF 300KVA TRANFORMERS AT UMUAGHARA OGBE AHIAZU MBAISE, IMO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | MAKBLO INTEGRATED GLOBAL SERVICES | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
176 | PROVISION OF SOALR STREET LIGHT AT EMADIKE COMMUNITY IN OGGBIA LGA BAYELSA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | ORRION TRUST INTERNATION LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
177 | PROVISION OF SOLAR STREET LIGHT AT ISAMPOU, EKEREMOR LGA BAYELSA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | NIGERBULL LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
178 | CONSTRUCTION OF EMANYI EGBECHE ROAD OFF ANYIGBA ANKPA BYE PASS, KOGI STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | EL MARKEM VENTURES LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
179 | PROVISION OF SOLAR STREET LIGHT AT ORI OKO MAKANA FULANI WARD ILORIN, KWARA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | RASWAS NIGERIA LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
180 | COMPLETION OF CONVENTIONAL STREET LIGHT AT BONNY TOWN PHASE III, RIVERS STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | OPEN DOOR SYSTEMS LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
181 | CONSTRUCTION OF ROAD AT FEDERAL LOW COST HOUSING ESTATE (AB AND AG) ROAD FROM GATE) IKORODU LAGOS STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | ROLLALONG INVESTMENT LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
182 | PROVISION OF HAND PUMP IN CHIEF OBIOHA'S COMPOUND IKPAOZARA NDIANCHIE-UNO ARONDIZUOGU IDEATO NORTH IMO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | LEOTOP NIGERIA LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
183 | CONSTRUCTION OF COMMUNITY BASED WATER SUPPLY SCHEMES AT DR ABU HOUSE TO ABETIANBE'S OPP AG CHURCH NEW SITE BEBUABIE VILLAGE OBUDU LGA, CROSS RIVER STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | RANRODS DRILLING CONSTRUCTION LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
184 | CONSTRUCTION OF SKILLS ACQUISITION CENTRE WITH EQUIPMENT IN BAR TOWN BOGORO LGA, BAUCHI STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | BELLA DIO VENTURES LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
185 | CONSTRUCTION OF PRIMARY HEALLTH CLINIC AT TSE YINA AGINDE, AKOKO MBAYEM USHONGO LGA BENUE STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | E.F. IKEYINA NIGERIA LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
186 | PROVISION OF HAND PUMP IN WUDIL LGA, KANO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | CEEDAR CREED LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
187 | PROVISION O SOLAR-POWERED STREET LIGHTS IN BUNU AND IJUMU IN KOGI STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | ETELUX INVESTMENT LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
188 | CONSTRUCTION OF COMMUNITY BASED WATER SUPPLY SCHEME AT AJOBI HILL TOP, AKPANYA, IGALAMELA-ODOLU LGA, KOGI STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | HEAVENS CONCEPTS AND SERVICES | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
189 | CONSTRUCTION OF HAND PUMPS BOREHOLE IN DIFFERENT LOCATIONS OF KANO FEDERAL CONTITUENCY IN KANO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | BALTIMORE NIGERIA LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
190 | PROVISION OF SOLAR STREET LIGHT EUGENE NDUBUSI CLOSE/OSI-EFA CRESCENT AT LILLY ESTATE, AMUWO ODOFIN, OFF FESTAC LINK ROAD, LAGOS STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | GREENWORLD SOLAR ENERGY LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
191 | construction of community based water supply schemes at shao, kwara state | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | AMI LOGISTICS LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
192 | CONSTRUCTION OF BLOCK OF THREE CLASSROOMS WITH VIP TOILET, FURNITURE AND BOOKS IN KAMBARI KARIM LAMIDI LGA, TARABA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | EPPIN FOREST ENGINEERING SERVICES | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
193 | SUPPLY AND INSTALLATION OF KVA TRANSFORMER IN ILORIN SOUTH FEDERAL CONSITITUENCY, AND ILORIN EAST/SOUTH FEDERAL CONSTITUENCY, KWARA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | SAROS TECHNOLOGIES LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
194 | SOLAR STREET LIGHT AT RUMUODOMAYA AGRIC STAFF QUARTERS AKWA IBOM | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | FRANKEEZA INTEGRATED SERVICES | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
195 | CONSTRUCTION OF 6 NOS BOREHOLES AT UROMI & UBIAJA IN EDO CENTRAL SENETORIAL DISTRICT, EDO STATE. | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | ZANCH INTERNATIONAL LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
196 | PROVISION OF SOLAR STREET LIGHT AT NTO IDE USUNG-OBOT AKARA, AKWA-IBOM STATE & AGBONMOBA STREET, EDO STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | PROOFLOAD SERVICES | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
197 | CONSTRUCTION OF BLOCK OF THREE CLASSROOMS, WITH VIP TOILET, FURNITURE AND BOOKS IN AMAR, K/LAMIDO LGA, TARABA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | KRUGER MULTI SERVICES LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
198 | URBAN RENEWAL & SLUMP UPGRADING, SOLAR MOTORIZED BOREHOLES AT WASE CONSTITUENCY, PLATEAU STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | MARYLAND INT'L | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
| URBAN RENEWAL & SLUMP UPGRADING, SOLAR MOTORIZED BOREHOLES AT KURE VILLAGE VIA IPONRI ILORIN EAST KWARA STATE | DAILY TRUST, MARCH, 27TH,2014. |  | NCB | 8th MAY,2014 |  |  | NA | 28/10/2014/ MTB | YES | NOSTRO VENTURES NIGERIA LTD | OCT.,2014 |  | 10 WEEKS | NOV.,2014 |  | " | N/A |  | N/A | N/A
4071323100.75

## LNRBDA
LOWER NIGER RIVER BASIN DEVELOPMENT AUTHORITY
2014 PROCUREMENT RECORDS
S/NO | PROJECT DESCRIPTION | APPROPRIATION | BENEFICIARY | DATE OF AWARD | RATE OF AWARD | AMOUNT
1 | Consultancy Service for the Drainages, Flood and Erosion Control in Yagba Market to Kara Market Road, Pategi, Kwara State | DRAINAGES,FLOOD AND EROSION CONTROL IN YAGBA MARKET TO KARA MARKET ROAD,PATEGI,KWARA STATE. :(11,420,950.15) | Tech Consultant International Limited. 27 Reserrahn Road, GRA, Ilorin, Kwara State | 2014-02-09 | 5428500 | 5428500
2 | Consultancy Service for the Study and Design of Construction of Ekuku Dam RESERVOIR Tanks (Okeneba and Idichei Reticulation) Pipe Network and Excavation | CONSTRUCTION OF EKUKU DAM RESERVOIR TANKS (OKENEBA AND IDICHE), RETICULATION (PIPE NETWORKS) AND EXCAVATION. (125,000,000.00) | Golf Crystal Nigeria limited. Plot 376, Gbzango Layout, Kubwa Abuja. | 2014-02-09 | 7200000 | 7200000
3 | Consultancy Service for the Study and Design of Granite Surfacing of Okesa/Ero Road in Ekiti Local Government, Kwara South Senatorial District in Kwara State | REHAB. OF INFRA ( GRANITE SURFACING ON OKESA/ERO ROAD, EKITI LGA (100,000,000.00) | Jaal Engineering Services. House 1 old Administrative Block Staff Quarters, Gwarinpa, Abuja Ftc., | 2014-02-09 | 9000000 | 9000000
4 | Consultancy Service for the Study and Design of Okene Water Supply Project in Kogi State. | OKENE WATER WORKS PROJECT, OKENE LGA, KOGI STATE (250,000,000.00) | Golf Crystal Nigeria limited. Plot 376, Gbzango Layout, Kubwa Abuja. | 2014-02-09 | 10275524.02 | 10275524.02
5 | Consultancy Service for the Study and Design of Pategi Airstrip Rehabilitation in Kwara State | REHABILITATION OF PATIGI AIRSTRIP (11,420,950.15) | Sanisi Partnership Limited . No 59, Offa Road G.R.A Ilorin, Kwara State. | 2014-02-09 | 11146516.49 | 11146516.49
6 | Consultancy Service for the Igboaka Earth Dam in Oyo State | IGBOAKA EARTH DAM :25,000,000.00 | Networth Engineering Limited. No 2 Ogunfayo Owolabi Crescent, Rainbow Area Ashi Ibadan, Oyo State. | 2014-02-09 | 8500000 | 8500000
7 | Consultancy Service for the Oziokutu/Nagazi Erosion Control in Kogi Central Senatorial District (Kogi State). | OZIOKUTU/NAGAZI EROSION CONTROL:(80,000,000.00) | Networth Engineering Limited. No 2 Ogunfayo Owolabi Crescent, Rainbow Area Ashi Ibadan, Oyo State. | 2014-02-09 | 7500000 | 7500000
8 | Consultancy Service for the Supervision of Iyara Earth Dam Project, Kogi State | COMPLETION OF IYARA-IJUMU WATER DAM AND IYARA TOWNSHIP WATER RETICULATION PROJECT IN IYARA, IJUMU LGA OF KOGI WEST SENATORIAL DISTRICT OF KOGI STATE (180,000,000.00) | Golf Crystal Nigeria Limited Plot 378, Gbzango Layout, Kubwa Abuja | 2014-02-09 | 20059873.34 | 20059873.34
9 | Consultancy Service for the Supervision of Malete Water Works Project, Kwara State | CONSTRUCTION OF MOLETE WATER WORKS, MORO LGA, KWARA STATE (625,000,000.00) | JBA Consults Nigeria Limited 54, Offa Road, GRA Ilorin, Kwara State | 2014-02-09 | 15022084.22 | 15022084.22
10 | Consultancy Services For the Eviromental Impact Assessment (EIA) of Iyara Earth Dam Project, Kogi State | COMPLETION OF IYARA-IJUMU WATER DAM AND IYARA TOWNSHIP WATER RETICULATION PROJECT IN IYARA, IJUMU LGA OF KOGI WEST SENATORIAL DISTRICT OF KOGI STATE (180,000,000.00) | Ktistes Engineering Nigeria Limited,Plot 606 Cadastral Zone Wuye District FCT P,o box 18290 Garki Abuja | 2014-02-09 | 14000000 | 14000000
11 | FENCING OF OKENE WATER WORKS | OKENE WATER WORKS PROJECT, OKENE LGA KOGI STATE :(250,000,000.00) | Sanakad Nigeria Limited. ,Okene/Kabba Rd Old Living Faith Junction Lokongoma,Lokoja Kogi State. | 2014-02-10 | 51114007 | 51114007
12 | CONSTRUCTION OF ACCESS ROAD AND CULVERTS AT OKENE WATER WORKS |  | Deechez Global Limited., No. 21 Aswan Str, Zone III Wuse Abuja | 2014-02-10 | 50033665.25 | 50033665.25
13 | REHAB. OF WATER WORKS AT OKENE WATER WORKS |  | Indigenous Construction Engineering Limited, House 19, Oke-Agba Str, Garki Abuja | 2014-02-10 | 106819119.23 | 106819119.23
14 | CONSTRUCTION OF EKUKU DAM RESERVOIR TANKS (OKENEBA AND IDICHE), RETICULATION (PIPE NETWORKS) AND EXCAVATION. | CONSTRUCTION OF EKUKU DAM RESERVOIR TANKS (OKENEBA AND IDICHE), RETICULATION (PIPE NETWORKS) AND EXCAVATION. (125,000,000.00) | Water-Top International No. 17 Mofoti Str., Wuse II, Abuja | 2014-02-10 | 58039364.3 | 58039364.3
15 | CONSTR. AND REHAB. OF EKUKU WATER WORKS IN KOGI STATE |  | Water-Top International No. 17 Mofoti Str., Wuse II, Abuja | 2014-02-10 | 95315290 | 95315290
16 | REHAB OF OGORI WATER TREATMENT PLANT IN KOGI CENTRAL SEN DISTR.KOGI STATE | REHAB. OF OGORI WATER PLANT TREATMENT IN KOGI CENTRAL SEN.DISTRICT :(75,000,000.00) | Nomforms Associates Limited. Suite 520, Febson Mall, Wuse Zone 4 Abuja | 2014-02-10 | 216778071.51 | 216778071.51
17 | CONSTRUCTION OF AHACHI EROSION AND DRAINAGE CONTROL AT OKENE LGA,KOGI STATE | AHACHI EROSION AND DRAINAGE CONTROL IN KOGI CENTRAL SENATORIAL DISTRICT:(12,500,000.00) | Pentrade Kings Limited, Ijebu-Ode, Ogun State. | 2014-02-10 | 12152835.4 | 12152835.4
18 | CONSTRUCTION OF OZIOKUTU/NAGAZI EROSION CONTROL IN ADAVI LGA KOGI STATE | OZIOKUTU/NAGAZI EROSION CONTROL:(80,000,000.00) | Tos Global Concept Ventures., 3 ECWA Str., GRA P.O. Box 30 Omu-Aram, Kwara State. | 2014-02-10 | 69197741.25 | 69197741.25
19 | CONSTRUCTION OF IGBOAKA EARTH DAM PROJECT IN OYO STATE. | IGBOAKA EARTH DAM :25,000,000.00 | Turning Point Engineering Limited , 17 Bacita Rd, Adewole Estate Ilorin, Kwara State | 2014-02-10 | 169569106.88 | 169569106.88
20 | CONSTR. OF ACCESS RD. , CULVERT AND DRAINAGE AT EIKA ADAGU LAYOUT THROUGH M. MUSA ADABARA STR.,OKEHI LGA, KOGI STATE | CONSTR. OF ACCESS RD. , CULVERT AND DRAINAGE AT EIKA ADAGU LAYOUT THROUGH M. MUSA ADABARA STR.,OKEHI LGA (30,000,000.00) | Zurich Nigeria Limited , 27 B Lane, Ewet Housing Est., Uyo, Akwa-Ibom State | 2014-02-10 | 27496157.5 | 27496157.5
21 | CONSTRUCTION OF DRAINAGE FLOOD AND EROSION CONTROL AT EMMANUEL STREET OGBOMOSHO, OYO STATE | FLOOD AND EROSION CONTROL, ISALE AFON, OGBOMOSHO NORTH, OYO STATE; N70,000,000.00 | Lush Tech Engineering Co. Limited 187/208, Ibrahim Taiwo Rd Ilorin, Kwara State. | 2014-02-10 | 65732614.5 | 65732614.5
22 | CONSTRUCTION FLOOD CONTROL ON RIVER EGWA, LAFIAGI IN EDU LGA, KWARA STATE | FLOOD AND EROSION CONTROL ON RIVER EGWA-LAFIAGI IN EDU LGA,N50,000,000.00 | Coasterners Engineering & Building Services Limited, Suite 1, Blk, EE Shopping Centre Zone E,Apo Legistilators Quarters, Abuja | 2014-02-10 | 49900000 | 49900000
23 | SUPPLY AND CONSTRUCTION OF SOLAR STREET LIGHT (32nos) IN LADE OF KWARA STATE | 50NOS SOLAR STREET LIGHT FOR LADE/KPADA/PATIGI/LAFIAGI/BODE SADU AND JEBBA LGAS (19,034,917) | Electric Multi Field Nigeria Limited . No 1-3 Fate Road Ilorin, Kwara State | 2014-02-10 | 592241.36 | 18951723.52
24 | CONSTRUCTION OF FLOOD CONTROL IN LAFIAGI IN EDU LGA, KWARA STATE. | EROSION CONTROL IN LAFIAGI LGAS OF KWARA NORTH SENATORIAL DISTRICT, N60, 000,000.00 | Pace Setter Global Technology Limited, 48, Idowu Martins Street Wuse Abuja | 2014-02-10 | 59471854.13 | 59471854.13
25 | CONSTRUCTION OF 2 CELL BOX CULVERTS AT VARIOUS LOCATIONS AT KWARA NORTH SENATORIAL DISTRICT, KWARA STATE. | CONSTRUCTION OF CULVERT AND BRIDGES IN KWARA NORTH SENATORIAL DISTRICT GBUGBU EFAN ROAD LAFIAGI III 2MX2MX7M,N40,000,000.00 | Needs Technologies Limited, Leribe Close, Off Kolda Link Street, Wuse II, Abuja. | 2014-02-10 | 38387685 | 38387685
26 | COMPLETION AND OVERLAYING OF KISHI ROAD OF IREPO LGA, OYO STATE | COMPLETION OF EROSION CONTROL PROJECT AT OJA TITUN AREA KISI,IREPO LGA,OYO STATE, N31,500,000.00 | Malmag Nigeria Limited. 28, Sulu Gambari Road, GRA, Ilorin, Kwara State. | 2014-02-10 | 26000000 | 26000000
27 | COMPLETION AND OVERLAYING OF GALADIMA ROAD 1 & 11 (PHASE 1) IN KWARA STATE | COMPLETION AND OVERLAYING OF GALADIMA ROAD 1 & 11 IN KWARA STATE, N47,500,000.00 | Malmag Nigeria Limited. 28, Sulu Gambari Road, GRA, Ilorin, Kwara State. | 2014-02-10 | 75180200 | 75180200
28 | REHAB. OF INFRA ( GRANITE SURFACING ON OKESA/ERO ROAD, EKITI LGA, KWARA STATE | REHAB. OF INFRA ( GRANITE SURFACING ON OKESA/ERO ROAD, EKITI LGA (100,000,000.00) | Antwise Nigeria Limited 5a, Abiodun Adebiyi Close, Ilorin, Kwara State | 2014-02-10 | 99740392.4 | 99740392.4
29 | EXTENSION OF LOW TENSION DISTR. NETWORK FOR ILESHA BARUBA, GWANARA IN KWARA STATE | RURAL ELECTRIFICATION PROJECT IN THE FOLLOWING LGAS OF KWARA NORTH SENATORIAL DISTRICT A. BARUTEN LG ,N40,000,000 | Maaqallah Integrated Service Limited LCS 011-002,Minna Road, Suleja, Niger State. | 2014-02-10 | 39996650.39 | 39996650.39
30 | REHABILITATION OF JEBBA/BACITA 33KVA FEEDER IN JEBBA AND LAFIAGI AXIS, KWARA STATE. | REHABILITATION OF JEBBA/BACITA 33KVA FEEDER IN JEBBA AND LAFIAGI AXIS, KWARA STATE. N20,000,000.00 | Needs Technologies Limited, Leribe Close, Off Kolda Link Street, Wuse II, Abuja. | 2014-02-10 | 19851281.33 | 19851281.33
31 | SUPPLY AND CONSTRUCTION OF SOLAR STREET LIGHT (48nos) IN YAGBA WEST AND EAST OF KOGI STATE | SOLAR POWERED STREET LIGHTNING IN COMMUNITIES IN YAGBA WEST, & YAGBA EAST, KOGI STATE,N50,000,000.00 | Mayocome Nigeria Limited, Yakwo Street, Banawa, Kaduna, Kaduna State. | 2014-02-10 | 776850.73 | 37288834.8
32 | SUPPLY AND CONSTRUCTION OF SOLAR STREET LIGHT (15nos) IN YAGBA WEST AND EAST OF KOGI STATE |  | Suchuchase Engineering Limited No 4 Tunde Ogheha Street Gudu District ,Abuja | 2014-02-10 | 776850.73 | 11652760.95
33 | EMPOWERMENT ITEMS FOR YOUNG FARMERS IN IFELODUN/OFFA/OYUN FEDERAL CONSTITUENCY, KWARA STATE | EMPOWERMENT ITEMS FOR YOUNG FARMERS IN IFELODUN/OFFA/OYUN FEDERAL CONSTITUENCY, KWARA STATE, N100,000,000.00 | Ibrafunds Limited, 95, Awolowo Road, Ikoyi, Lagos, Lagos State, . | 2014-02-10 | 99377250 | 99377250
34 | CONSTR. OF TUBEWELLS/MOTORCYCLES FOR FARMERS AT EDU/MORO/PATIGI LGAS IN KWARA STATE | 50NOS. TUBEWELLS/MOTORCYCLES FOR FARMERS IN EDU/MORO/PATIGI LGAS, N11,944,410.37 | Micheal Jacobs Limited, Suite 001, Sharon Ultimate Hotels, Plot 1710 Tafawa Balewa Way, Area 3, Garki, Abuja. | 2014-02-10 | 6293371.88 | 6293371.88
35 | Construction of 2Nos Electrically Driven Motorised Borehole with 22.5m3 Steel Tank Storage in Oke-Omore,Iludun-Eju (Ajase Ward 2) & Oke Onigbin Road, Water Works Arandun Ward at Irepodun LGA in Kwara State | CONSTRUCTION OF MOTORISED BOREHOLES IN VARIOUS LOCATION IN KWARA SOUTH SENATORIAL DISTRICT, KWARA STATE (N80,000,000.00) AND CONSTRUCTION OF MOTORISED BOREHOLES IN EKITI, IREPODUN, OKE-ERO & ISIN LGAS KWARA STATE (N61,200,000.00) | Mail-Rem Ventures Limited 15 Wamon Taofeek Avenue Abule Egba, Lagos State. | 2014-02-10 | 6690030 | 13380060
36 | CConstruction of 2Nos Electrically Driven Motorised Borehole with 22.5m3 Steel Tank Storage in Araromi Irebode (Oro Ward 2) in Irepodun LGA &Are-Opin (Opin Ward) in Ekiti LGA of Kwara State |  | Bashmol Ventures Limited, Suite 28,Manjal Plaza, Wuze ZoneI, Abuja. | 2014-02-10 | 6690030 | 13380060
37 | Construction of 2Nos Electrically Driven Motorised Borehole with 22.5m3 Steel Tank Storage in Owu-Isin, Isin LGA & Omu Aran GRA In Ireodun LGA in Kwara State |  | Fat Dee Enterprises Limited, Plot 1, Ajagbolu Layout, Akobo Ibadan, Oyo State. | 2014-02-10 | 6690030 | 13380060
38 | Construction of 2Nos Electrically Driven Motorised Borehole with 22.5m3 Steel Tank Storage in Ekan Oke Ero LGA and Arifowomo in Ifelodun LGA of Kwara State |  | Alasinrin (W) Nigeria Limited, No 12, Haman Pategi Road GRA , Ilorin, Kwara State. | 2014-02-10 | 6690030 | 13380060
39 | Construction of Electrically Driven Motorised Borehole with 22.5m3 Steel Tank Storage in Iwoto Fulani, Aran-Orin in Irepodun LGA of Kwara State |  | Lab-Shir Ventures Suite 28 Mega-Plaza, Wuse Zone 1, Abuja. | 2014-02-10 | 6690030 | 6690030
40 | Construction of Electrically Driven Motorised Borehole with 22.5m3 Steel Tank Storage in Saganmu Alakara in Irepodun LGA in Kwara State |  | Febab Nigeria Limited, No 5 Biodun Adebiyi Close Off New Yidi Road,Ilorin, Kwara State | 2014-02-10 | 6690030 | 6690030
41 | Construction of Electrically Driven Motorised Borehole with 22.5m3 Steel Tank Storage in Obbo Aiyegunle in Ekiti LGA in Kwara State |  | Akatech Construction Limited, S 62 Police Road, Ilorin, Kwara State. | 2014-02-10 | 6690030 | 6690030
42 | Construction of Electrically Driven Motorised Borehole with 22.5m3 Steel Tank Storage in Ekanmeje, Oke Ero LGA in Kwara State |  | Rotech Limited, No 79, Ibrahim Taiwo Road Ilorin, Kwara State. | 2014-02-10 | 6690030 | 6690030
43 | Construction of Electrically Driven Motorised Borehole with 22.5m3 Steel Tank Storage in Oke-Onigbin in Isin LGA in Kwara State |  | Bintayah Global Resources Services Limited, No 350, Umaru Saro Road, Ilorin, Kwara State. | 2014-02-10 | 6690030 | 6690030
44 | Construction of Electrically Driven Motorised Borehole with 22.5m3 Steel Tank Storage in Ikoja Compound Omu Aran in Irepodun LGA in Kwara State |  | Geocrystal Nigeria Limited, Western Reserviour Road, Olorunshogo Area, Ilorin, Kwara State. | 2014-02-10 | 6690030 | 6690030
45 | Construction Of Electrically Driven Motorised Borehole with Steel Tank Storage in Igbonla in Irepodun LGA in Kwara State |  | Horler Global Concept Limited, No 155, Ibrahim Taiwo Road, Ilorin, Kwara State. | 2014-02-10 | 6690030 | 6690030
46 | Construction of Electrically Driven Motorised Borehole with 22.5m3 Steel Tank Storage in Comprehensive High School Aran-Orin in Irepodun LGA & Obbo Aiyegunle In Ekiti LGA in Kwara State | CONSTRUCTION OF MOTORISED BOREHOLES IN VARIOUS LOCATION IN KWARA SOUTH SENATORIAL DISTRICT, KWARA STATE (N80,000,000.00) AND CONSTRUCTION OF MOTORISED BOREHOLES IN EKITI, IREPODUN, OKE-ERO & ISIN LGAS KWARA STATE (N61,200,000.00) | Tripad Engineering& Construction Limited, House 1A Close 22 Road Festac, Lagos State. | 2014-02-10 | 6690030 | 6690030
47 | Drilling and Reticulation of Conventional Solar Powered Borehole With Plastic Tank (2Nos 5000 Litres UPVC PLASTIC Tank On Storage at Oloro Compound, Opposite Filling Station, Irra in Oyun LGA of Kwara State | CONSTRUCTION OF MOTORISED BOREHOLE AT OLORI CAMP OPP FILLING STATION IRA, OYUN LGA, KWARA STATE (5,000,000.00) | Ibyets International Limited, No 23, Achimugu GRA Ilorin ,Kwara State. | 2014-02-10 | 5000000 | 5000000
48 | Drilling and Reticulation of Conventional Solar Powered Borehole With Plastic Tank (2Nos 5000 Litres UPVC PLASTIC Tank On Storage at Aiyede Amuro at Mopa/Muro LGA IN Kogi State | SOLAR POWERED BOREHOLES IN THE FEDERAL CONSTITUENCY WITH 1000 LITRE UPVC TANK ON 6M STEEL TOWER AT YAGBA IN KOGI STATE (15,000,000.00) | Jefayo Nigeria Limited, Block 2 Flat 2, Lokoja, Kogi State. | 2014-02-10 | 5000000 | 5000000
49 | Drilling and Reticulation of Conventional Solar Powered Borehole With Plastic Tank (2Nos 5000 Litres UPVC PLASTIC Tank On Storage at Igbo Ero in Yagba East LGA of Kogi State |  | Fadel Geo Services Limited, No 28, Busari Street Off Old Ota Road, Alagbado, Lagos State. | 2014-02-10 | 5000000 | 5000000
50 | Drilling and Reticulation of Conventional Solar Powered Borehole With Plastic Tank (2Nos 5000 Litres UPVC PLASTIC Tank On Storage at Agric Area, Mopo Isanlu in Yagba East LGA of Kogi State | MOTORIZED BOREHOLE AT AGRIC AREA MOPO ISANLU LGA(5,000,000) | Ibyets International Limited, No 23, Achimugu GRA Ilorin ,Kwara State. | 2014-02-10 | 5000000 | 5000000
51 | drilling of One (1) No conventional Solar-Powered Bore-Holes with 2nos 5000 litres UPVC Plastic tank storage capacity on 6m tower at Leadership Academy, Oro-Road, Obehira in Okene LGA of Kogi State a | CONSTRUCTION OF SOLAR POWERED BOREHOLE IN LEADERSHIP ACADEMY, ORO RAOD, OBEHIRA OKENE LGA, KOGI STATE (10,000,000.00) | Geocrystal Nigeria Limited, Western Reserviour Road, Olorunshogo Area, Ilorin, Kwara State. | 2014-02-10 | 5000000 | 5000000
52 | Drilling one (1no) Solar-Powered Boreholes at Adinoyi’s Quarters Ayite New Layout Ayiododo-Obangede of Kogi State |  | Geocrystal Nigeria Limited, Western Reserviour Road, Olorunshogo Area, Ilorin, Kwara State. | 2014-02-10 | 5000000 | 5000000
53 | Drilling one (1no) Solar-Powered Boreholes at Akodi Quarters Akutupa-kiribunu IN Kabba Bunu LGA of Kogi State | SOLAR POWERED BOREHOLES AT AKODI QTRS, AKUTUPA-KIRIBUNU IN KABBA BUNU LGA OF KOGI STATE (5,000,000.00) | Geocrystal Nigeria Limited, Western Reserviour Road, Olorunshogo Area, Ilorin, Kwara State. | 2014-02-10 | 5000000 | 5000000
54 | Drilling one (1no) Solar-Powered Boreholes at Sango Area in Ilorin East LGA of Kwara State | SOLAR POWERED BOREHOLE IN SANGO AREA, ILORIN EAST LGA (10,000,000.00) | Geocrystal Nigeria Limited, Western Reserviour Road, Olorunshogo Area, Ilorin, Kwara State. | 2014-02-10 | 5000000 | 5000000
55 | Construction of 1Nos Electrically Driven Motorised Borehole with 22.5m3 Steel Tank Storage at Osochi Okodo Hajia Hausa Isah Street in Okene LGA IN Kogi State | CONSTRUCTION OF SOLAR POWERED BOREHOLE IN OSOCHI OKODO,HAJIA HAUWA ISAH STREET OKENE LGA (10,000,000.00) | Hamsal Tad Limited, Block 77, Flat 3, Phase 2, Site 1,Kubwa, Abuja. | 2014-02-10 | 6690030 | 6690030
56 | Construction of 1No Electrically Driven Motorised Borehole with 22.5m3 Steel Tank Storage at Oziokutu, Alh Tanko’s Street, Ogaminana Kabba Road Adavi LGA IN Kogi State | CONSTRUCTION OF SOLAR POWERED BOREHOLE IN OZIOKUTU ALH TANKO'S STREET, OGAMINANA, KABBA ROAD, ADAVI LGA, KOGI STATE(10,000,000.00) | Hamsal Tad Limited, Block 77, Flat 3, Phase 2, Site 1,Kubwa, Abuja. | 2014-02-10 | 6690030 | 6690030
57 | Construction of Electrically Driven Motorised Borehole with 22.5m3 Steel Tank Storage in Mia Abdulazeez Yusuf Resident No D6 Opposite Jummat Mosque Kuchi Kau2,in Nasarawa State | CONSTRUCTION OF SOLAR POWERDED BOREHOLE AT MAI ABDULAZEEZ YUSUF RESIDENCE NO D6, OPPOSITE JUMMAT MOSQUE KUCHIKAUZ, KARU LGA, NASARAWA STATE (10,000,000.00) | Numed Nigeria Limited 10A, M/Muhamed Way Ilorin, Kwara State. | 2014-02-10 | 7177000 | 7177000
58 | Drilling of conventional Solar-Powered Bore-Holes with 2nos 5000 litres UPVC Plastic tank storage capacity on 6m tower in Okunchi at Asema of Adavi Compound in Kogi State | PROVISION OF SOLAR POWERED BOREHOLES IN VARIOUS LOCATIONS AT OKENE (100,000,000.00) | Sedibullahi Nigeria Limited, Km 15, Okene Lokoja Road Opp Camp2 Itakpe Okene, Kogi State. | 2014-02-10 | 5000000 | 5000000
59 | Drilling of conventional Solar-Powered Bore-Holes with 2nos 5000 litres UPVC Plastic tank storage capacity on 6m tower in Okunchi at Plot 121 Along Obehira/Lagos Road Beside Charismatic Church Okene |  | Dyish Ventures, No 20 Kaduna, Kaduna State. | 2014-02-10 | 5000000 | 5000000
60 | Drilling of conventional Solar-Powered Bore-Holes with 2nos 5000 litres UPVC Plastic tank storage capacity on 6m tower in Okunchi at St John Catholic Hospital kabba, Kabba Bunu LGA in Kogi State |  | Aqual Gem Mining & Engineering Limited, NNPC Petrol Station, Dadinkowa Jos, Plateau State. | 2014-02-10 | 5000000 | 5000000
61 | Drilling of 5Nos conventional mini electrically driven motorised Bore-Holes with 1No 5000 UPVC Plastic Tank Storage Capacity on 1.5M Block Work Stand in Lafiagi,Rifu, Patigi , Kusogi and Mafa in Kwara State | RURAL WATER SUPPLY IN AREA OF KWARA NORTH SENATORIAL DISTRICT (60,000,000.00) | Needs Technologies Limited, Leribe Close, Off Kolda Link Street, Wuse II, Abuja. | 2014-02-10 | 2500000 | 12500000
62 | Drilling of 1No conventional mini electrically driven motorised Bore-Holes with 1No 5000 UPVC Plastic Tank Storage Capacity on 1.5M Block Work Stand in Lalagi Patigi LGA in Kwara State |  | Itopa Asuku Nigeria Limited, 1st Avenue Gwarinpa, Abuja. | 2014-02-10 | 2500000 | 2500000
63 | Drilling of 1No conventional mini electrically driven motorised Bore-Holes with 1No 5000 UPVC Plastic Tank Storage Capacity on 1.5M Block Work Stand in Lanwa, Moro LGA in Kwara State |  | Al-Zayyad Concept Limited, 1st Avenue Gwarinpa, Abuja. | 2014-02-10 | 2500000 | 2500000
64 | Drilling of 1No conventional mini electrically driven motorised Bore-Holes with 1No 5000 UPVC Plastic Tank Storage Capacity on 1.5M Block Work Stand in Motor Park Tsaragi in Edu LGA in Kwara State |  | Geocrystal Nigeria Limited, Western Reserviour Road, Olorunshogo Area, Ilorin, Kwara State. | 2014-02-10 | 2500000 | 2500000
65 | Drilling of 1No conventional mini electrically driven motorised Bore-Holes with 1No 5000 UPVC Plastic Tank Storage Capacity on 1.5M Block Work Stand in Bi-Elesin in Moro LGA of Kwara State |  | Geocrystal Nigeria Limited, Western Reserviour Road, Olorunshogo Area, Ilorin, Kwara State. | 2014-02-10 | 2500000 | 2500000
66 | Drilling of 1No conventional mini electrically driven motorised Bore-Holes with 1No 5000 UPVC Plastic Tank Storage Capacity on 1.5M Block Work Stand in Safari Malete in Moro LGA of Kwara State | RURAL WATER SUPPLY IN AREA OF KWARA NORTH SENATORIAL DISTRICT (60,000,000.00) | Geocrystal Nigeria Limited, Western Reserviour Road, Olorunshogo Area, Ilorin, Kwara State. | 2014-02-10 | 2500000 | 2500000
67 | Drilling of 1No conventional mini electrically driven motorised Bore-Holes with 1No 5000 UPVC Plastic Tank Storage Capacity on 1.5M Block Work Stand in Mangida in Moro LGA of Kwara State |  | Geocrystal Nigeria Limited, Western Reserviour Road, Olorunshogo Area, Ilorin, Kwara State. | 2014-02-10 | 2500000 | 2500000
68 | Drilling of 1No conventional mini electrically driven motorised Bore-Holes with 1No 5000 UPVC Plastic Tank Storage Capacity on 1.5M Block Work Stand in Lafiagi in Kwara State | RURAL WATER SUPPLY IN AREA OF KWARA NORTH SENATORIAL DISTRICT (60,000,000.00) | Geocrystal Nigeria Limited, Western Reserviour Road, Olorunshogo Area, Ilorin, Kwara State. | 2014-02-10 | 2500000 | 2500000
69 | Drilling of 5Nos conventional mini electrically driven motorised Bore-Holes with 1No 5000 UPVC Plastic Tank Storage Capacity on 1.5M Block Work Stand in Egban Shaab,Egban Ndamaraki Lafiagi, Egban Nnafa,Bindofu Phase II Lafiagi and Tukurafu Lafiaji in Kwara State |  | Maaqallah Integrated Service Limited LCS 011-002,Minna Road, Suleja, Niger State. | 2014-02-10 | 2500000 | 12500000
70 | Drilling of 1No conventional mini electrically driven motorised Bore-Holes with 1No 5000 UPVC Plastic Tank Storage Capacity on 1.5M Block Work Stand in Efu Hakeem Tsaragi in Edu LGA of Kwara State |  | Geocrystal Nigeria Limited, Western Reserviour Road, Olorunshogo Area, Ilorin, Kwara State. | 2014-02-10 | 2500000 | 2500000
71 | Drilling of 1No conventional mini electrically driven motorised Bore-Holes with 1No 5000 UPVC Plastic Tank Storage Capacity on 1.5M Block Work Stand in Efu Maiyaki Tsaragi in Edu LGA of Kwara State |  | Geocrystal Nigeria Limited, Western Reserviour Road, Olorunshogo Area, Ilorin, Kwara State. | 2014-02-10 | 2500000 | 2500000
72 | Construction Of 10Nos Handpump Borehole in Lade Area in Patigi LGA of Kwara State | 133Nos Handpumps Boreholes At Various Locations in Patigi LGA in Kwara State (60,759,553) | Malmag Nigeria Limited No 28 Sulu Gambari Rd Ilorin, Kwara State. | 2014-02-10 | 1300000 | 13000000
73 | Construction Of 15Nos Handpump Borehole in Patigi Area in Patigi LGA of Kwara State |  | Platform Nigeria Limited. Plot 936, Azores St, Wuse II, Abuja . | 2014-02-10 | 1300000 | 19500000
74 | Construction Of 1No Handpump Borehole in Patigi Area in Patigi LGA of Kwara State |  | 1st Kamblag Nigeria Limited No 55 Taiwo Road Ilorin, Kwara State. | 2014-02-10 | 1300000 | 1300000
75 | Construction Of 2Nos Handpump Borehole in Lafiagi Area in Edu LGA of Kwara State |  | Goslam Logistic Ventures Wahab Shopping Complex Zango Mkt Ilorin, Kwara State. | 2014-02-10 | 1300000 | 1300000
76 | Construction Of 2Nos Handpump Borehole in Lafiagi Area in Moro LGA of Kwara State |  | Tani Nig Enterprises No 10 Olorunshogo Road Ilorin, Kwara State. | 2014-02-10 | 1300000 | 2600000
77 | Construction Of 3Nos Handpump Borehole in Lafiagi Area in Edu LGA of Kwara State | 20Nos Handpumps Boreholes At Edu LGA in Kwara State (10,659,533.00) | Nilank Nigeria Limited No 15 Basin Road Ilorin, Kwara State. | 2014-02-10 | 1300000 | 3900000
78 | Construction Of 4Nos Handpump Borehole in Lafiagi Area in Edu LGA of Kwara State |  | Emlat Royal Ventures 60 Tipper Garage Area Ilorin, Kwara State. | 2014-02-10 | 1300000 | 3900000
79 | Construction Of 1No Handpump Borehole in Lafiagi Area in Edu LGA of Kwara State |  | Mubol Ventures Limited Road 9, Plot 4 , Omolayo Avenue Akobo Area, Ibadan, Oyo State. | 2014-02-10 | 1300000 | 1300000
80 | Construction Of 1No Handpump Borehole in Moro Area in Moro LGA of Kwara State | 20Nos Handpumps Boreholes At Moro LGA in Kwara State(10,659,533.00) | Plusman Associates B5, Okene- Eba road Okene, Kogi State. | 2014-02-10 | 1300000 | 1300000
81 | Construction Of 1No Handpump Borehole in Moro Area in Moro LGA of Kwara State |  | Royal System Water Project Limited No12 Edagbeja Street, Off Coker Road Ejigba, Lagos State. | 2014-02-10 | 1300000 | 1300000
82 | Construction Of 1No Handpump Borehole in Moro Area in Moro LGA of Kwara State |  | Pinnacle Solution Network Limited Suite 37D, EFAB Mail Extension, Off Gimbiya Street, Area II, Garki , Abuja. | 2014-02-10 | 1300000 | 1300000
83 | Construction Of 1No Handpump Borehole in Moro Area in Moro LGA of Kwara State | 20Nos Handpumps Boreholes At Moro LGA in Kwara State(10,659,533.00) | Seal Multi-Services Limited BlockSame Global Estate Dakwo District, Abuja. | 2014-02-10 | 1300000 | 1300000
84 | Construction Of 1No Handpump Borehole in Moro Area in Moro LGA of Kwara State |  | Flors Dav Ventures No 40 Lagos Avenue Kulende Estate Ilorin, Kwara State. | 2014-02-10 | 1300000 | 1300000
85 | Construction Of 1No Handpump Borehole in Moro Area in Moro LGA of Kwara State |  | Camel Construction Nigeria Limited No 17B Ijumu Road GRA Ilorin ,Kwara State. | 2014-02-10 | 1300000 | 1300000
86 | Construction Of 2Nos Handpump Borehole in Moro Area in Moro LGA of Kwara State |  | Atuswell Services Enterprises 22 Ita Alamu Bola Technical Workshop, Ilorin South LGA, Kwara State. | 2014-02-10 | 1300000 | 2600000
87 | Construction Drilling and Reticulation of Conventional Powered Borehole With Plastic Tank (2Nos 5000 Litres UPVC PLASTIC Tank On 6m tower at Madaki,Onchici, Igo Aloma District, Ofu LGA,Kogi State | Construction Of Solar Power Borehole at Madaki,Onchici, Igo Aloma District, Ofu LGA,Kogi State(10,000,000.00) | Maroon Ventures Ltd. Block 4 Shop 13 Stadium Shopping Arcarde, Lokoja, Kogi State. | 2014-02-10 | 6666000 | 6666000
88 | Provision of borehole Flushing/Reticulation works at Ozuwaya II in Kogi Central Senatorial District, Kogi State | PROVISION OF SOLAR POWERED BOREHOLES IN VARIOUS LOCATIONS AT OKENE (100,000,000.00) | Vicmasonic Nig Ltd. 3 Anne Ifeoluwa Str Tanke Ilorin,, Kwara State. | 2014-02-10 | 1376326.24 | 1376326.24
89 | Provision of borehole Flushing/ Provision and Installation of Hand Pump works in Ohuodo and Ogaminana in Kogi Central Senatorial District, Kogi State |  | Vicmasonic Nig Ltd. 3 Anne Ifeoluwa Str Tanke Ilorin,, Kwara State. | 2014-02-10 | 625602.84 | 1251205.68
90 | Drilling of Three (3) Nos New borehole with Reticulation works and Rehabilitation of overhead tank at Adavi Eba, Anyoke and Okesi (Ogori) in Kogi Central Senatorial District, Kogi State |  | Vicmasonic Nig Ltd. 3 Anne Ifeoluwa Str Tanke Ilorin,, Kwara State. | 2014-02-10 | 3753617.02 | 11260851.06
91 | Two (2) Nos borehole Flushing, Provision and Installation of Submersible pump and rehabilitation of overhead tank at Agasa and Egge in Kogi Central Senatorial District, Kogi State |  | Aqual Gem Mining & Engineering Limited, NNPC Petrol Station, Dadinkowa Jos, Plateau State. | 2014-02-10 | 2055466.67 | 2055466.67
92 | Drilling of Three (3) Nos New borehole with Reticulation works at Enynare,Etahi and Idanuha in Kogi Central Senatorial District, Kogi State |  | Aqual Gem Mining & Engineering Limited, NNPC Petrol Station, Dadinkowa Jos, Plateau State. | 2014-02-10 | 3083200 | 9249600
93 | Two (2) Nos borehole Flushing/Reticulation works in Idoji and Karaworo in Kogi Central Senatorial District, Kogi State | PROVISION OF SOLAR POWERED BOREHOLES IN VARIOUS LOCATIONS AT OKENE (100,000,000.00) | Don Global Concepts Anifowose Shopping Complex, Opp Kwara Express, Ajase-Ipo Road Ilorin, Kwara State. | 2014-02-10 | 1281875.78 | 2563751.56
94 | Drilling of New borehole with Provision and Installation of Pump at Idogido in Kogi Central Senatorial District, Kogi State |  | Don Global Concepts Anifowose Shopping Complex, Opp Kwara Express, Ajase-Ipo Road Ilorin, Kwara State. | 2014-02-10 | 2214149.07 | 2214149.07
95 | Drilling of Two (2) Nos New borehole with Reticulation works/Rehabilitation of overhead tank at Obeiba I and Oborokeuvete in Kogi Central Senatorial District, Kogi State |  | Integrated Nna Enterprises No 196 Ajase-Ipo Road Ilorin Kwara State. | 2014-02-10 | 3496024.84 | 6992049.68
96 | Drilling of Two (2) Nos New borehole with Reticulation works/Rehabilitation of overhead tank at Obeiba I and Oborokeuvete in Kogi Central Senatorial District, Kogi State |  | Rohwell Services Nigeria Enterprises No 4 Erin Road, Gaa Akanbi Ilorin,Kwara State. | 2014-02-10 | 3496024.84 | 6992049.68
97 | Completion of Construction of Isapa Dam in Ekiti Local Area of Kwara State | COMPLETION OF CONSTRUCTION OF ISAPA DAM IN EKITI LGA, KWARA STATE (40,000,000.00) | Geocrystal Niogeria Limited Western Reserviour Road, Olorunshogo Area, Ilorin, Kwara State | 2014-02-10 | 39500000 | 39500000
98 | Oyun Water work(Extension of Water Supply to Offa GRA Igosun Road and Area Filteration and Backwash System, Kwara State | PROVISION FOR WATER RETICULATION IN GRA/ADESOYE COLLEGE AREA, OFFA LGA,KWARA STATE (30,000,000.00) | Allianz Development Company Limited. No 4, Kikuyi Close, Wuse II, Box 2432, Garki Abuja | 2014-02-10 | 41400000 | 41400000
1858510806.14

## MTI Onitsha
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) : |  | METALLURGICAL TRAINING INSTITUTE, ONITSHA
MINISTRY : |  | MINISTRY OF MINES & STEEL DEVELOPMENT
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2014 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | CONSTRUCTION OF AUDITORIUM | 2007-11-06 | MINISTERIAL TENDER BOARD (MTB) | NCB | 17/10/2007 | 2007-12-11 | 332445866.68 | 29/10/2007 | 29/10/2007 | YES | JIMBAZ (W.A) LTD | 26/11/2007 | 332445866.68 | 78 WEEKS | 26/11/2007 | 312725994.68 | DEC. 2014 | WORKS | 100% | - | - | Outstanding auditorium work is provision of 1300 seats for which contract has been awarded at cost of 29,719,872 and supplied in May, 2015 with outstanding balance of 19,719,872 yet to be effected.
2 | PURCHASE OF ADDITIONAL CNC LATHE, MILLING & SHAPING MACHINES | 2014-11-08 | MANAGEMENT TENDERS BOARD (MTB) | NCB | 2014-08-09 | 15/09/2014 | 29344765 | N/A | 16/09/2014 | YES | UGOLANSON NIG LIMITED | 29/09/2014 | 29229375 | 9 WEEKS | N/A | NIL | 2014-01-12 | GOODS | 100% | N/A | NIL | Machines supplied & installed but payment yet to be effected
3 | PROCUREMENT OF PNEUMATIC COILING & ELECTRICAL INSTALLATION EQUIPMENT | 2014-11-08 | MANAGEMENT TENDERS BOARD (MTB) | NCB | 2014-08-09 | 15/09/2014 | 24366057 | N/A | 16/09/2014 | YES | UGOLANSON NIG LIMITED | 2014-09-10 | 24219300 | 9 WEEKS | N/A | NIL | 2014-11-12 | GOODS | 100% | N/A | NIL | Machines supplied & installed but payment yet to be effected
4 | PURCHASE OF POOL VEHICLE [2 NOS TOYOTA HILUX DOUBLE CABIN VANS] | 2014-11-08 | MANAGEMENT TENDERS BOARD (MTB) | NCB | 2014-08-09 | 15/09/2014 | 14000000 | N/A | 16/09/2014 | YES | ELIZADE NIGERIA LIMITED | 17/9/2014 | 12805000 | 2 WEEKS | N/A | 12805000 | 2014-01-10 | GOODS | 100% | N/A | NIL | Vehicles supplied and paid for.

## NOFC Abakaliki
PROCURING ENTITY (MDA) : |  | NATIONAL OBSTETRIC FISTULA CENTRE ABAKALIKI
MINISTRY :HEALTH
FINANCIAL YEAR :2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014(NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2013 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | LANDSCAPPING AND ASHALTING OF PREMISES | 14/07/14: NEW NIGERIAN & DAILY CHAMPION | PTB | NCB | 17/9/12 | SEPT. 2012 | 23000000 | NOT APPLICABLE | 19/9/12 | YES | CUTE ARC PROJECTS LIMITED | 18/11/13 | 51498541.85 | 4 WEEKS | NA | 23000000 | 18/12/13 | ON GOING | 85% | NON | NON | ON GOING
2 | SUPPLY/INSTALLATION OF ANAESTHETIC MACHINE AND TRAINING | 14/07/2014: HALLMARK & DAILY CHAMPION | PTB | NCB | 25/08/14 | SEPT. 2014 | 14200000 | NOT APPLICABLE | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NA | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | INCOMPLETE FUNDING
3 | SUPPLY/INSTALLATION OF HYSTEROSCOPE AND TRAINIG | 14/07/2014: HALLMARK & DAILY CHAMPION | PTB | NCB | 25/08/14 | SEPT. 2014 | 10000000 | NOT APPLICABLE | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NA | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | INCOMPLETE FUNDING
4 | SUPPLY/INSTALLATION OF OPERATIVE LAPROSCOPE MACHINE /TRAINING | 14/07/2014: HALLMARK & DAILY CHAMPION | PTB | NCB | 25/08/14 | SEPT. 2014 | 19000000 | NOT APPLICABLE | 17/10/14 | YES | G-SYSTEMS NIGERIA LIMTED | 22/10/14 | 17931420 | 6 WEEKS | NA | 17931420 | 6/12/14 | COMPLETED | 100% | NON | NON | CONTRACT EXECUTED
5 | SUPPLY/INSTALLATION OF THEATER EQUIPMENT AND TRAINING | 14/07/2014: HALLMARK & DAILY CHAMPION | PTB | NCB | 25/08/14 | SEPT. 2014 | 19258600 | NOT APPLICABLE | 12/9/14 | YES | SWISS BIOSTADT NIGERIA LIMITED | 15/09/14 | 12184500 | 8 WEEKS | NOT APPLICABLE | 12184500 | 15/11/14 | COMPLETED | 100% | NON | NON | CONTRACT EXECUTED
6 | SUPPLY/INSTALLATION OF COLPOSCOPE AND TRAINING | 14/07/2014: HALLMARK & DAILY CHAMPION | PTB | NCB | 25/08/14 | SEPT. 2014 | 4000000 | NOT APPLICABLE | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED
7 | SUPPLY/INSTALLATION OF X-RAY MACHINE AND TRAINING | 14/07/2014: HALLMARK & DAILY CHAMPION | PTB | NCB | 25/08/14 | SEPT. 2014 | 25402200 | NOT APPLICABLE | 12/9/14 | YES | SWISS BIOSTADT NIGERIA LIMITED | 15/09/14 | 21000000 | 8 WEEKS | NOT APPLICABLE | 21000000 | 15/11/14 | COMPLETED | 100% | NON | NON | CONTRACT EXECUTED
8 | SUPPL/INSTALLATION OF ULTRA SOUND MACHINE | 14/07/2014: HALLMARK & DAILY CHAMPION | PTB | NCB | 25/08/14 | SEPT. 2014 | 7200000 | NOT APPLICABLE | 12/9/14 | YES | SWISS BIOSTADT NIGERIA LIMITED | 15/09/14 | 7150000 | 8 WEEKS | NOT APPLICABLE | 7150000 | 15/11/14 | COMPLETED | 100% | NON | NON | CONTRACT EXECUTED
9 | SUPPLY/INSTALLATION OF LABORATORY EQUIPMENT AND TRAINING | 14/07/2014: HALLMARK & DAILY CHAMPION | PTB | NCB | 25/08/14 | SEPT. 2014 | 6700000 | NOT APPLICABLE | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT APPLICABLE | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | INCOMPLETE FUNDING
10 | SUPPLY/INSTALLATION OF CLINIC AND WARD EQUIPMENT | 14/07/2014: HALLMARK & DAILY CHAMPION | PTB | NCB | 25/08/14 | SEPT. 2014 | 13127200 | NOT APPLICABLE | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NON | INCOMPLETE FUNDING
11 | SUPPLY/INSTALLATION OF E-LIBRARY FACILITIES AND TRAINING | 14/07/2014: HALLMARK & DAILY CHAMPION | PTB | NCB | 25/08/14 | SEPT. 2014 | 11232900 | NOT APPLICABLE | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NON | INCOMPLETE FUNDING
12 | SUPPLY/INSTALLATION OF OFFICE EQUIPMENT | 14/07/2014: HALLMARK & DAILY CHAMPION | PTB | NCB | 25/08/14 | SEPT. 2014 | NOT APPLICABLE | NOT APPLICABLE | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NON | NOT AWARDED | INCOMPLETE FUNDING
13 | SUPPLY/INSTALLATION OF OFFICE FITTINGS | 14/07/2014: HALLMARK & DAILY CHAMPION | PTB | NCB | 25/08/14 | SEPT. 2014 | 13462080 | NOT APPLICABLE | 23/9/14 | YES | WOOD AFFAIRS NIGERIA LTD | 30/09/14 | 13059750 | 8 WEEKS | NOT APPLICABLE | 13059750 | 30/11/14 | COMPLETED | 100% | NON | NON | CONTRACT EXECUTED
14 | SUPPLY OF OFFICE FURNITURE | 14/07/2014: HALLMARK & DAILY CHAMPION | PTB | NCB | 25/08/14 | SEPT. 2014 | NOT AWARDED | NOT APPLICABLE | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT APPLICABLE | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | INCOMPLETE FUNDING
15 | EQUIPPING OF STORES | 14/07/2014: HALLMARK & DAILY CHAMPION | PTB | NCB | 25/08/14 | SEPT. 2014 | NOT AWARDED | NOT APPLICABLE | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT APPLICABLE | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED
16 | SUPPLY/INSTALLATION OF VARIOUS MEDICAL (WARD) EQUIPMENT AND TRAINING | 30/10/14:SOLICITATION OF QUOTATION | AO | QSL | 17/11/14 | NOV. 2014 | 1220000 | NOT APPLICABLE | 1/12/14 | YES | GRAFIL MEDICALS NIGERIA LIMITED | 2/12/14 | 700125 | 2 WEEKS | NOT APPLICABLE | 700125 | 16/12/14 | COMPLETED | 100% | NON | NON | CONTRACT EXECUTED
17 | SUPPLY/INSTALLATION OF VARIOUS MEDICAL EQUIPMENT(LABORATORY) EQUIPMENT AND TRAINING | 10/9/14:SOLICITATION OF QUOTATION | AO | QSL |  | NOV. 2014 | 6700000 | NOT APPLICABLE | 17/12/14 | YES | GRAFIL MEDICALS NIGERIA LIMITED | 20/10/14 | 3150780 | 6 WEEKS | NOT APPLICABLE | 3,150,780.00 | 5/11/14 | NOT AWARDED | NOT AWARDED | NOT AWARDED | NOT AWARDED | INCOMPLETE FUNDING
18 | SUPPLY OF TELEVISION SETS FOR ADMIN COMPLEX | 4/12/14:SOLICITATION OF QUOTATION | AO | QSL | 18/12/14 | DEC. 2014 | 1176000 | NOT APPLICABLE | 18/12/14 | YES | BIGMA GLOBAL CONCEPT, LTD | 18/12/14 | 100002 | 2 WEEKS | NOT APPLICABLE | 100000 | 30/10/14 | COMPLETED | 100% | NON | NON | CONTRACT EXECUTED

## NIMET
PROCUREMENT RECORDS
PROCURING ENTITY (MDA): NIGERIAN METEOROLOGICAL AGENCY
MINISTRY: AVIATION
FINANCIAL YEAR: 2014
S/N | CONTRACT DESCRIPTION | DATE OF ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION | AMOUNT PAID AS AT 31/12/2014 | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION DATE | DATE OF VARIATION APPROVAL | VARIATION AMOUNT (NGN) | REMARKS
1 | Procurement of 3No. Digital Anemometers / Wind Sensors | NA | PTB | DIRECT PROCUREMENT | NA | NA | 31762500 | 24/12/2014 | 24/12/2014 | NA | ALIFIG IN'L LTD | 24/12/2014 | 31762500 | 6months |  | 27528375 | June, 2014 | Completed | 100% | NA | NA | Completed
2 | Contract for Alteration & Extension Works of NiMet Instrument Calibration Laboratory (NICL) at Abuja | NA | PTB | Repeat Procurement | NA | NA | 177383207 | 19/12/2014 | 24/12/2014 | NA | Enatech Nig. Ltd | 24/12/2014 | 47321435.6 | 3months |  | 7098215.36 | Mar, 2014 | On-going | 15% | NA | NA | On-going
3 | Contract for the Procurement of Low Level Wind Shear Alert System (LLWAS) Spare parts | NA | PTB | Direct Procurement | NA | NA | 123662817 | 2014-11-07 | 31/7/2014 | NA | Communications and Environmental Solutions Limited | 31/7/2014 | 87225240 | 6months |  | 62303137.35 | Jan. 2015 | Completed | 100% | NA | NA | Completed
4 | Contract for Upgrade of Instrument Test and Calibration Equipment at NWF &CRC, Abuja | NA | PTB | Direct Procurement | NA | NA | 40000000 | 27/11/2014 | 2014-02-12 | NA | ALIFIG IN'L LTD | 2014-02-12 | 90994188.6 | 12months |  | 13649128.29 | Dec, 2015 | On-going | 15% | NA | NA | On-going
5 | Contract for the Procurement of Office Furniture for the Office of Head, International Unit; General Manager, Strategic Processes and Planning; Chief Security Officer; Chief Protocol Officer; Senior Admin Officer; Con Secretary and Coffee Room at the National Weather Forecasting and Climate Research centre Nnamdi Azikiwe International Airport Abuja | 14/2/2014 | PTB | OCB | 28/2/2014 | 2014-07-03 | 177383207 | NA | 13/3/2014 | Yes | Iggo Jorje Int'l Ltd | 13/3/2014 | 9900000 | 2weeks |  | 9900000 | March, 2014 | Completed | 100% | NA | NA | Completed
6 | Contract for the Procurement, Installation and Servicing of Fire Extinguishers at NWF & CRC, Abuja | 15/8/2014 | PTB | OCB | 2014-04-09 | 2014-11-09 | 15000000 | NA | 15/9/2014 | Yes | Lobic Engineering Services Ltd | 15/9/2014 | 9873675 | 3months |  | 9873675 | December, 2014 | Completed | 100% | NA | NA | Completed
7 | 60 No. Double Bunk Beds, 100 Mattresses, 100 Pillows, 100 Writing Chairs, 6 No. Magnetic Boards, 1 No. 5.0 KVA Generator and 1 No. Portable Coloured Photocopier for RTC Oshodi | 24/4/2014 | PTB | OCB | 2014-08-05 | 2014-12-05 | 150000000 | NA | 13/5/2014 | Yes | Bessels Technologies Ltd | 13/5/2014 | 9730000 | 3months |  | 9730000 | August, 2014 | Completed | 100% | NA | NA | Completed
8 | Contract for the Procurement of Furniture for the Offices of Director, Legal Services; Director, Weather Forecasting Services; Director, Applied Meteorological services; director, Finance and Accounts and Ag. Director, Engineering and Technical Services at the National Weather Forecasting and Climate Research Centre Nnamdi Azikiwe International Airport Abuja | 28/4/2014 | PTB | OCB | 2014-10-05 | 2014-12-05 | 177383207 | NA | 13/5/2014 | Yes | Tara - Frikk Int'l Ltd | 13/5/2014 | 9940000 | 10days |  | 9940000 | 23/5/2014 | Completed | 100% | NA | NA | Completed
9 | Contract for Corrective Maintenance of Low Level Wind Shear Alert System (LLWAS) Facility at Nnamdi Azikiwe International Airport, Abuja | 27/02/2014 | PTB | Direct Procurement | NA | NA | 25000000 | NA | 14/5/2014 | NA | Avsatel Communications Ltd. | 14/5/2014 | 6950921.25 | 3months |  | Nil | August, 2014 | Completed | NA | NA | NA | Completed
10 | Contract for Upgrade of Messir-Sat from 2nd to 3rd Generation System at Lagos Airport | 28/4/2014 | PTB | Direct Procurement | NA | NA | 50000000 | NA | 14/5/2014 | NA | Teledom Int'l Ltd | 14/5/2014 | 8607972.53 | 3months |  | Nil | August, 2014 | Completed | 100% | NA | NA | Completed
11 | Contract for the Rehabilitation and Remodeling of Instrument Calibration Workshop Oshodi, Lagos | 2014-09-06 | PTB | OCB | 16/6/2014 | 18/6/2014 |  | NA | 20/6/2014 | Yes | E.O.D Global Delight Ltd | 14/5/2014 | 9990200 | 3months |  | 9990200 | Sept. 2014 | Completed | 100% | NA | NA | Completed
12 | Contract for the Procurement of Furniture for the Offices of General Manager, Engineering; General Manager, Business Development; General Manager, Climate Services; General Manager, Admin and Supplies and General Manager, Human Resources at the National Weather Forecasting and Climate Research Centre Nnamdi Azikiwe International Airport Abuja | 2014-09-06 | PTB | OCB | 16/6/2014 | 18/6/2014 | 177383207 | NA | 20/6/2014 | Yes | Cool Park Nig. Ltd | 20/6/2014 | 9949950 | 10days |  | 9949950 | 30/6/2014 | Completed | 100% | NA | NA | Completed
13 | Contract for Renovation of Computer and Data Processing Building, Oshodi, Lagos | 2014-12-06 | PTB | OCB | 18/6/2014 | 20/6/2014 |  | NA | 20/6/2014 | Yes | Keniah Nigeria Ltd. | 20/6/2014 | 9950800 | 3months |  | 9950800 | Sept. 2014 | Completed | 100% | NA | NA | Completed
14 | Extension of Completion Period for Contract on Rehabilitation, Remodeling and Construction of Regional Meteorological Training Centre (RMTC) Infrastructure (Students Hostel), Oshodi, Lagos | 2012 | NA | NA | NA | NA | NA | NA | NA | NA | NA | 19/11/2014 | 231301927.08 | 78weeks |  | NA | 2014-01-11 | NA | NA | NA | NA | NA
15 | Contract for the Procurement and Installation of Messir-Sat System Upgrade for Aminu Kano | 2014-06-11 | PTB | OCB | 20/11/2014 | 27/11/2014 | 50000000 | NA | 2014-02-12 | Yes | Teledom Int'l Ltd | 2014-02-12 | 9042254.38 | 3months |  | Nil | March, 2015 | Ongoing | 60% | NA | NA | On-going
16 | Contract for Procurement of Furniture for the Offices of Director, Administration and Supply; Head of Audit; Assistant Director, Procurement; Chief Store Officer (Procurement); Senior Admin Officer & PA/DAS; Administrative Officer II (Procurement); Clerical Officer II (Procurement) at the National Weather Forecasting and Climate Research Centre Nnamdi Azikiwe International Airport Abuja. | 2014-08-07 | PTB | OCB | 22/7/2014 | 29/7/2014 | 177383207 | NA | 31/7/2014 | Yes | Galleria Nicole Ltd | 31/7/2014 | 9945000 | 10days |  | Nil | 2014-10-08 | Completed | 100% | NA | NA | Completed
17 | Contract for the Supply and Installation of Wooden Window Blinds in all Offices in Phase II and Office of Director, Administration and Supply in Phase I of the National Weather Forecasting and Climate Research Centre Nnamdi Azikiwe International Airport Abuja | 2014-08-07 | PTB | OCB | 22/7/2014 | 29/7/2014 | 177383207 | NA | 31/7/2014 | Yes | The Address Synergy Ltd | 31/7/2014 | 9850140 | 4weeks |  | Nil | August, 2014 | Completed | 100% | NA | NA | Completed
18 | Contract for Remodeling of NiMet Synoptic Office Lokoja | 15/8/2014 | PTB | OCB | 2014-04-09 | 2014-11-09 | 100000000 | NA | 15/9/2014 | Yes | Kawonci Nig. Ltd | 15/9/2014 | 9950400 | 3months |  | 9950400 | December, 2014 | Completed | 100% | NA | NA | Completed
19 | Contract for Procurement of Furniture and Curtains for Rented Official Residence of Director, WMO’s Regional Office for Africa | 2014-08-07 | PTB | OCB | 22/7/2014 | 29/7/2014 | 177383207 | NA | 31/7/2014 | Yes | Home Vestors Concept | 31/7/2014 | 9934000 | 4weeks |  | 9934000 | August, 2014 | Completed | 100% | NA | NA | Completed
20 | Contract for the Procurement of Low Level Windshear Alert System (LLWAS) Spare Parts for Lagos International Airport | 15/8/2014 | PTB | OCB | 2014-04-09 | 2014-11-09 | 100000000 | NA | 15/9/2014 | Yes | Dataway Limited | 15/9/2014 | 9821700 | 3months |  | 9821700 | December, 2014 | Completed | 100% | NA | NA | Completed
21 | Contract for the Supplies of 15 No. Steel Cardboard, 2 No. Photocopier, 2 No. High Performance Scanner, 8 No. Laptop Computer, 3 No. Desktop Computer, 1 No. Ground Type Split Air Conditioner, 2 No. Ipad Tablet, 3 No. A3/A4 Colored Printer, 1 No. A4 Black and White Printer, 3 No. Water Dispenser, 3 No. Spiral Binder, 4 No. Electronic Shredding Machine, 2 No. Photocopier Stand, 1 No. Paper Cutter and other Office Equipment/Tools for Procurement Office | 2014-08-07 | PTB | OCB | 22/7/2014 | 29/7/2014 | 177383207 | NA | 31/7/2014 | Yes | Crucial Concept Limited | 31/7/2014 | 9897000 | 4weeks |  | 9897000 | August, 2014 | Completed | 100% | NA | NA | Completed
22 | Contract for the Renovation of Printing Office, Oshodi, Lagos | 15/8/2014 | PTB | OCB | 2014-04-09 | 2014-11-09 | 100000000 | NA | 15/9/2014 | Yes | Giftson Ehi Enterprises Ltd | 15/9/2014 | 9985001 | 3months |  | 9985001 | December, 2014 | Completed | 100% | NA | NA | Completed
23 | Contract for the Renovation and Rehabilitation, Development of Interlocks and Drainage at the Synoptic Office, Yelwa | 15/8/2014 | PTB | OCB | 2014-04-09 | 2014-11-09 | 100000000 | NA | 15/9/2014 | Yes | Knight Consulting Limited | 15/9/2014 | 9980000 | 3months |  | 9980000 | December, 2014 | Completed | 100% | NA | NA | Completed
24 | Contract for the Procurement of Furniture for Waiting Room, Reception Centres of the 1st, 2nd And 3rd Floors and the Office of the Assistant Chief Admin Officer, Senior Admin Officer, Higher Executive Officer and Assistant Data Processing Officer at the National Weather Forecasting and Climate Research Centre Nnamdi Azikiwe International Airport Abuja | 18/3/2014 | PTB | OCB | 2014-01-04 | 2014-07-04 | 177383207 | NA | 2014-08-04 | Yes | Cool Park Nig. Ltd | 2014-08-04 | 9960000 | 10days |  | 9960000 | April, 2014 | completed | 100% | NA | NA | Completed
25 | Procurement by Trade in on Official Peugeot 508 with a High Performance Jeep | 2014-03-09 | PTB | OCB | 23/9/2014 | 2014-07-10 |  | NA | 15/9/2014 | Yes | Messrs Kefiano Autos | 15/9/2014 | 18000000 | 7weeks |  | 18000000 | Nov. 2014 | Completed | NA | NA | NA | Completed
26 | Contract for the Procurement and Installation of Solar Powered Lighting System for NiMet Weather Observatories at Owerri, Enugu and Uyo Airports | 14/8/2014 | PTB | OCB | 2014-05-09 | 2014-12-09 | 30000000 | NA | 15/9/2014 | Yes | Bessels Technologies Ltd | 15/9/2014 | 9744000 | 3months |  | 9744000 | Dec. 2014 | Completed | 100% | NA | NA | Completed
27 | Contract for the Provision of Consultancy and Strategic Support on Production and Distribution of Rebranded NiMet Digest Newsletters | 15/8/2014 | PTB | OCB | 2014-04-09 | 2014-11-09 | 21085000 | NA | 15/9/2014 | Yes | Shan - Joe Media Plus | 15/9/2014 | 3850000 | Quarterly |  | Nil | NA | Completed | 100% | NA | NA | Completed
28 | Contract for Partitioning of Office Spaces to Create Additional Offices for Officers at the NWF & CRC Abuja | 15/8/2014 | PTB | OCB | 2014-04-09 | 2014-11-09 | 177383207 | NA | 25/9/2014 | Yes | Enatec Nig. Ltd | 25/9/2014 | 9950400 | 4weeks |  | Nil | Oct. 2015 | Completed | 100% | NA | NA | Completed
29 | Contract for Provision of Portakabin and Construction of Platform and Soak Away at NiMet Synoptic Office Benin City, Edo State | 15/8/2014 | PTB | OCB | 2014-04-09 | 2014-11-09 |  | NA | 25/9/2014 | Yes | Y'al & Ned Services | 25/9/2014 | 9950400 | 3months |  | 9950400 | Dec. 2014 | Completed | 100% | NA | NA | Completed
30 | Contract for Procurement and Installation of Solar Powered Lighting system for NiMet Weather Observatories at Calabar, Ogoja and Obudu Airports | 26/8/2014 | PTB | OCB | 2014-09-09 | 16/9/2014 | 30000000 | NA | 25/9/2014 | Yes | Scientific Sales Nig. Ltd | 25/9/2014 | 9951900 | 3months |  | 9951900 | Dec. 2014 | Completed | 100% | NA | NA | Completed
31 | Contract for the Renovation of Forecast Office Ikeja, Lagos state | 26/8/2014 | PTB | OCB | 2014-09-09 | 16/9/2014 | 100000000 | NA | 25/9/2014 | Yes | Diamond well enterprises | 25/9/2014 | 9990000 | 6months |  | Nil | March, 2015 | Completed | NA | NA | NA | Completed
32 | Contract for the Procurement and Installation of 1 No. Digital Remote Indicating Wind Anemometer for NiMet Station at Kaduna Airport | 26/8/2014 | PTB | OCB | 2014-09-09 | 16/9/2014 |  | NA | 25/9/2014 | Yes | IEPC Int'l Ltd | 25/9/2014 | 9980000 | 3months |  | 9980000 | Dec. 2014 | Completed | 100% | NA | NA | Completed
33 | Contract for the Procurement of Low Level Windshear Alert System (LLWAS) Spare Parts (IP68 Instrument enclosure and 60Ah batteries) for continuous sustainability of LLWAS at Lagos, Port Harcourt and Kano International Airports | 26/8/2014 | PTB | OCB | 2014-09-09 | 16/9/2014 | 60000000 | NA | 25/9/2014 | Yes | Associated Air Safety Equipment's Ltd | 25/9/2014 | 9906750 | 3months |  | 9906750 | Dec. 2014 | Completed | 100% | NA | NA | Completed
34 | Contract for the Total Landscaping and Pavement of NiMet Lokoja Complex Environment Lokoja, Kogi State | 26/8/2014 | PTB | OCB | 2014-09-09 | 16/9/2014 | 100000000 | NA | 25/9/2014 | Yes | Holdall Limited | 25/9/2014 | 9950200 | 4months |  | 9950200 | Jan. 2015 | Completed | 100% | NA | NA | Completed
35 | Contract for the Procurement and Installation of Stabilizing System (200 KVA Industrial Stabilizer) for the Doppler Weather Radar at NWF & CRC Abuja | 26/8/2014 | PTB | OCB | 2014-09-09 | 16/9/2014 | 40000000 | NA | 25/9/2014 | Yes | NDMOS Technology Network | 25/9/2014 | 9943500 | 2months |  | 9943500 | Nov. 2014 | Completed | 100% | NA | NA | Completed
36 | Contract for the Supply of 10 No. Steel Cardboard, 1 No. Photocopier, 1 No. High Performance Scanner, 4 No. Laptop Computer, 1 No. Desktop Computer, 3 No. A3/A4 Colored Printer, 1 No. A4 Black and White Printer, 3 No. Water Dispenser, 1 No. Spiral Binder, 4 No. Electronic Shredding Machine, 1 No. Photocopier Stand, 3 No. External Hard Drives, 4 No. Power Stabilizer and 1 No. Paper Cutter in Offices at the Multi-Purpose Block at Oshodi, Lagos | 2014-02-10 | PTB | OCB | 30/10/2014 | 14/11/2014 | 100000000 | NA | 2014-05-11 | Yes | Abalito Oil & Gas Ltd | 2014-05-11 | 9897000 | 4weeks |  | 9897000 | December, 2014 | Completed | NA | NA | NA | Completed
37 | Contract for Rehabilitation of NiMet Weather Observatory and Installation of Solar Powered Lighting System for the Enclosure and Environment at Murtalla Mohammed International Ikeja Airport, Lagos | 2015-03-09 | PTB | OCB | 17/9/2014 | 24/9/2015 | 100000000 | NA | 2015-09-10 | Yes | Global Nameks Ltd | 2015-09-10 | 8400000 | 3months |  | 8400000 | Dec. 2014 | Completed | 100% | NA | NA | Completed
38 | Contract for the Renovation of Synoptic Office Dutse, Jigawa State | 2015-03-09 | PTB | OCB | 17/9/2014 | 24/9/2015 | 100000000 | NA | 2015-09-10 | Yes | Norrice Lea Ltd | 2015-09-10 | 9985001 | 3months |  | 9985001 | Dec. 2014 | Completed | 100% | NA | NA | Completed
39 | Contract for the Procurement and Installation of 1 No Digital Remote Indicating Wind Anemometer for NiMet Station at Owerri Airport | 2015-03-09 | PTB | OCB | 17/9/2014 | 24/9/2015 | 30000000 | NA | 2015-09-10 | Yes | Abalito Oil & Gas Ltd | 2015-09-10 | 9880000 | 3months |  | 9880000 | Dec. 2014 | Completed | 100% | NA | NA | Completed
40 | Contract for the Procurement and Installation of 3Nos 5KVA Inverter Power Backup System for the NiMet Data/Computer Center Oshodi, Lagos | 2015-03-09 | PTB | OCB | 17/9/2014 | 24/9/2015 |  | NA | 2015-09-10 | Yes | Dianchamdz Resources Ltd | 2015-09-10 | 8475600 | 3months |  | Nil | Dec. 2014 | Ongoing | 90% | NA | NA | On-going
41 | Contract for the Procurement of Furniture for the Central Library of National Weather Forecasting and Climate Research Centre, Abuja | 20/10/2014 | PTB | OCB | 2014-04-11 | 2014-11-11 | 28689360 | NA | 2014-11-11 | Yes | Iggo Jorje Int'l Ltd | 2014-11-11 | 9930000 | 10days | Nil | 9930000 | Dec. 2014 | Completed | 100% | NA | NA | Completed
42 | Contract for the Procurement and Installation of Stabilizing System (200 KVA Industrial Stabilizer) for the Doppler Weather Radar at Port Harcourt International Airport | 18/9/2014 | PTB | OCB | 15/10/2014 | 22/10/2014 | 40000000 | NA | 23/10/2014 | Yes | Janedyke ServicesLtd | 23/10/2014 | 9850000 | 2months |  | Nil | December, 2014 | Completed | NA | NA | NA | Completed
43 | Contract for the Procurement and Installation of Solar Powered Lighting System for the Enclosure at Ilorin, Sokoto and Yola Airports | 17/9/2014 | PTB | OCB | 15/10/2014 | 22/10/2014 | 30000000 | NA | 23/10/2014 | Yes | Ofeama CEO Enterprises Ltd | 23/10/2014 | 9956900 | 3months |  | Nil | Jan. 2015 | Completed | NA | NA | NA | Completed
44 | Contract for the Procurement of AWODS Spare Parts for Lagos, Port Harcourt and Kano International Airports | 17/9/2014 | PTB | OCB | 15/10/2014 | 22/10/2014 | 30000000 | NA | 23/10/2014 | Yes | Meteo- Technologies Limited | 23/10/2014 | 10475600 | 3months |  | Nil | Jan. 2015 | Completed | NA | NA | NA | Completed
45 | Contract for the Procurement and Installation of Solar Powered Lighting System for the Enclosures at Abeokuta, Ijebode and Shaki NiMet Stations | 18/9/2014 | PTB | OCB | 2014-02-10 | 2015-09-10 | 30000000 | NA | 30/10/2014 | Yes | Spirit Touch Energy SolutionNig. Ltd | 30/10/2014 | 9933000 | 3months |  | Nil | Jan. 2015 | Completed | NA | NA | NA | Completed
46 | Contract for the Procurement of Furniture for the Office of Director, Research and Training; Principal, RMTC; Head Agro Met, Head Engineering; Administrative Officer II; Clerical Officer II; Head, Administration at the Multi-Purpose Building at Oshodi Complex, Lagos | 18/9/2014 | PTB | OCB | 2014-02-10 | 2015-09-10 |  | NA | 30/10/2014 | Yes | Jemefs Flowers and Gardens Ltd | 30/10/2014 | 9945000 | 10days |  | Nil | Nov. 2014 | Completed | NA | NA | NA | Completed
47 | Contract for the Renovation of Central Electronics, Refrigeration and Air Conditioning Workshop at NiMet Operational Headquarters Oshodi, Lagos | 17/9/2014 | PTB | OCB | 2014-01-10 | 2014-08-10 | 100000000 | NA | 30/10/2014 | Yes | R.E Unicorn Services Ltd | 30/10/2014 | 9950250 | 3months |  | 9950250 | Jan. 2015 | Completed | 100% | NA | NA | Completed
48 | Contract for the Reconstruction of the Collapsed Block Work Perimeter Fence, Rehabilitation of the Fence Structure and Installation of Constantine Wire Round the Entire Fence of NiMet Upper Air station Akanu Ibiam International Airport Enugu | 16/9/2014 | PTB | OCB | 2014-01-10 | 2014-08-10 | 100000000 | NA | 30/10/2014 | Yes | Valban Enterprises | 30/10/2014 | 9990200 | 3months |  | 9990200 | Jan. 2015 | Completed | 100% | NA | NA | Completed
50 | Contract for Supply and Installation of Wooden Window Blinds in Students Classrooms of the Multi-Purpose Building of the Oshodi Complex, Lagos | 16/9/2014 | PTB | OCB | 2014-01-10 | 2014-08-10 | 100000000 | NA | 30/10/2014 | Yes | Knight Consultancy Ltd | 30/10/2014 | 9970000 | 3months |  | 9970000 | Jan. 2015 | Completed | 100% | NA | NA | Completed
51 | Contract for the Procurement of Low Level Windshear Alert System (LLWAS) Spare Parts for LLWAS at Port Harcourt International Airport | 2015-03-09 | PTB | OCB | 17/9/2014 | 24/9/2015 | 123662817 | NA | 2015-09-10 | Yes | Purity Instruments & Technologies Ltd | 2015-09-10 | 9854250 | 3months |  | 9854250 | Dec. 2014 | Completed | 100% | NA | NA | Completed
52 | Contract for the Supply of 10 No. Steel Cardboard, 1 No. Photocopier, 1 No. High Performance Scanner, 4 No. Laptop Computer, 1 No. Desktop Computer, 3 No. A3/A4 Colored Printer, 1 No. A4 Black and White Printer, 3 No. Water Dispenser, 1 No. Spiral Binder, 4 No. Electronic Shredding Machine, 1 No. Photocopier Stand, 3 No. External Hard Drives, 4 No. Power Stabilizer and 1 No. Paper Cutter in Offices at the Multi-Purpose Block at Oshodi, Lagos | 17/9/2014 | PTB | OCB | 2014-01-10 | 2014-08-10 | 100000000 | NA | 30/10/2014 | Yes | Seltrix Limited | 30/10/2014 | 9897000 | 4weeks |  | Nil | Nov. 2014 | Completed | NA | NA | NA | Completed
53 | Contract for the Procurement and Installation of Solar Powered Lighting System for NiMet Weather Enclosures at Dutse, Yelwa and Kano Airports | 26/9/2015 | PTB | OCB | 24/10/2014 | 31/10/2014 | 15000000 | NA | 2014-05-11 | Yes | Steao Integrated Services Ltd | 2014-05-11 | 9956900 | 3months |  | 9956900 | Jan, 2015 | Completed | 100% | NA | NA | Completed
54 | Contract for the Remodeling of Upper Air Hydrogen Building and Renovation of Upper Air Office with Convenient Facilities for Upper Air Section Akanu Ibiam International Airport Enugu | 30/9/2015 | PTB | OCB | 28/10/2014 | 2014-05-11 | 58883200 | NA | 2014-05-11 | Yes | Multiquip W/A Ltd | 2014-05-11 | 9990200 | 3months |  | Nil | Jan, 2015 | Completed | NA | NA | NA | Completed
55 | Contract for the Supply and Installation of Wooden Window Blinds in the Office of the Director, Research and Training; All Staff Offices in the Multi-Purpose Building of the Oshodi Complex, Lagos | 2014-02-10 | PTB | OCB | 30/10/2014 | 2014-04-11 | 100000000 | NA | 2014-05-11 | Yes | Home Vestors Concept | 2014-05-11 | 9950000 | 1month |  | 9950000 | Dec, 2014 | Completed | 100% | NA | NA | Completed
56 | Contract for the Procurement of Furniture for Students Classrooms of the Multi-Purpose Building at Oshodi Complex, Lagos | 30/9/2014 | PTB | OCB | 28/10/2014 | 2014-04-11 | 100000000 | NA | 2014-05-11 | Yes | El-Investment Ltd | 2014-05-11 | 9945000 | 10 days |  | 9945000 | Dec, 2014 | Completed | 100% | NA | NA | Completed
57 | Contract for the Remodeling of NiMet Office at Gombe Airport, Gombe | 30/9/2014 | PTB | OCB | 28/10/2014 | 2014-04-11 | 100000000 | NA | 2014-05-11 | Yes | Sihat I.N.E Ltd | 2014-05-11 | 9950400 | 3months |  | 9950000 | Dec, 2014 | Completed | 100% | NA | NA | Completed
58 | Contract for Procurement of Upper Air Consumables for NiMet Upper Air Sounding Stations at Lagos, Kano and Maiduguri Airports | NA | PTB | Direct Procurement | NA | NA | 50474174.97 | 23/9/2014 | 2014-12-11 | NA | Alifig Int'l Limited | 2014-12-11 | 36895000 | 3months |  | 36895000 | Feb. 2015 | Completed | 100%700 | NA | NA | Completed
59 | Contract for Supply and Installation of Wooden Window Blinds for Central Library, Offices of GM Commercial, DGM Commercial, Chief Commercial Officer, Commercial Support Staff, Registry Operation Office, GM Accounts, ICT Operation Office, DAS Operation Office, DAS Support Staff and Public Relation Unit at NiMet Office, Abuja | 20/10/2014 | PTB | OCB | 2014-04-11 | 2014-11-11 | 177383207 | NA | 2014-12-11 | Yes | The Adress Synergy Limited | 2014-12-11 | 7559470 | 4weeks | Nil | 7559470 | Dec, 2014 | Completed | 100% | NA | NA | Completed
60 | Contract for the Procurement of Low Level Windshear Alert System (LLWAS) Spare Parts for LLWAS at Kano International Airport | 18/9/2014 | PTB | OCB | 15/10/2014 | 22/10/2014 | 25000000 | NA | 23/10/2014 | Yes | Mesophere Scientific Instruments Ltd | 23/10/2014 | 9500300 | 3months |  | 8247200 | Jan. 2015 | Ongoing | 86% | NA | NA | On-going
61 | Contract for Procurement of Spare Parts for Automatic Weather Observation and Display System at Maiduguri and Owerri Airports | NA | PTB | Direct Procurement | NA | NA | 123662817 | 29/8/2014 | 2014-11-11 | NA | SMC Limited | 2014-11-11 | 27593672 | 12months | Nil | 4139050.8 | Nov. 2014 | Ongoing | 15% | NA | NA | On-going
62 | Contract for the Upgrade of NiMet Accounting Services Environment | 2014-07-10 | PTB | OCB | 21/10/2014 | 2014-04-11 | 25000000 | NA | 2014-12-11 | Yes | kinshalom Nig.ltd | 2014-12-11 | 9707250 | 6weeks | Nil | Nil | Jan, 2015 | Completed | NA | NA | NA | Completed
63 | Contract for the Procurement and Installation of LLWAS at Ilorin Airport | NA | PTB | Repeat Procurement | NA | NA | 400000000 | 28/11/2014 | 2014-02-12 | NA | Communication and Environmental Solutions Ltd | 2014-02-12 | 132722100 | 12months | Nil | 17917483.5 | Dec, 2015 | On-going | 13% | NA | NA | On-going
64 | Contract for the Procurement and Installation of LLWAS at Kaduna Airport | NA | PTB | Repeat Procurement | NA | NA | 400000000 | 28/11/2014 | 2014-02-12 | NA | Communication and Environmental Solutions Ltd | 2014-02-12 | 132722100 | 12months | Nil | 17917483.5 | Dec, 2015 | On-going | 13% | NA | NA | On-going
65 | Contract for the Procurement of Laptops and Desktop Computers for Engineers and Engineering Offices at NWF & CRC, Abuja | 2014-03-11 | PTB | OCB | 17/11/2014 | 24/11/2014 | 177383207 | NA | 2014-02-12 | Yes | Gloname Nig. Ltd | 2014-02-12 | 9990000 | 3months | Nil | 9990000 | March, 2015 | Completed | 100% | NA | NA | Completed
66 | Contract Variation for the Procurement of Upper Air Consumables | NA | PTB | Repeat Procurement | NA | NA |  | 24/12/2014 | 24/12/2014 | NA | Alifig Int'l Ltd | 24/12/2014 |  | 3months | Nil | Nil | March, 2015 | Ongoing | NA | 24/12/2014 | 2093000 | On-going
67 | Contract for Provision of Strategic and Technical Co-ordination Assistance to NiMet on the Launch of the 2015 Seasonal Rainfall Prediction | 2014-09-09 | PTB | OCB | 16/10/2014 | 20/10/2014 |  | NA | 24/12/2014 | Yes | Strategy & Executors Co. Ltd | 24/12/2014 | 9980000 | 3months | Nil | 9980000 | March, 2015 | Completed | 100% | NA | NA | On-going
68 | Contract for the supply of 15No. Laptops, 4 No. Desktops, 2 No. Copier and other Accessories for Administrative and IPPIS Staff at NWF & CRC, Abuja | 2014-10-11 | PTB | OCB | 24/11/2014 | 18/12/2014 | 177383207 | NA | 24/12/2014 | Yes | FMiT Int'l LTD | 24/12/2014 | 9996000 | 3months | Nil | 3000000 | March, 2015 | Ongoing | 30% | NA | NA | On-going
69 | Procurement of Furniture for the Weather Public Telecast Studio of Central Forecast Office at National Weather Forecasting ad Climate Research Centre, Abuja | 2014-10-11 | PTB | OCB | 24/11/2014 | 18/12/2014 | 177383207 | NA | 24/12/2014 | Yes | The Adress Synergy Limited | 24/12/2014 | 9945500 | 10days | Nil | Nil | Jan, 2015 | Completed | NA | NA | NA | Completed
70 | Procurement and Installation of MESSIR-SAT System Upgrade for Port-Harcourt Int'l Ltd | 2014-08-10 | PTB | OCB | 2014-06-11 | 20/11/2014 | 50000000 | NA | 24/12/2014 | Yes | Teledom Int'l Ltd | 24/12/2014 | 9042254 | 3months | Nil | Nil | March, 2015 | Completed | NA | NA | NA | Completed

## UUTH
PROCUREMENT RECORDS
MINISTRY |  | MINISTRY OF HEALTH
PROCURING ENTITY |  | UNIVERSITY OF UYO TEACHING HOSPITAL, UYO, AKWA IBOM STATE
1st January - 31st December 2014
| BASIC DATA | [6 empty] | CONTRACT AWARD | [8 empty] | CONTRACT IMPLEMENTATION
sn | Contract description (include quantity of goods) | contract type | advertisment dates and Media | approving authority | procurement Method | Bid opening date | date of competion of financial/ technical bids evaluation report | recommended contractor | date of certificate of no objection (if applicable) | approval date by AP/PTB/MTB/FEC | date of contract award | awarded to the lowest tenderer | contract period | contract extension period | contract value (N) | budgetary provision (N) | date of contract commencement | date of contract commencement (physical mobilization) | date of variation approval | amount of variation | amount paid as at date | expected completion date | % of completion as at date | remarks
1 | completion of construction of General outpatient department block | works | June 27 2010, the nation, Leadership Federal Tenders Journal | PTB | NCB | 2014-02-10 |  | MESSERS DONARSON SERVICES LIMITED | NA |  | 2014-04-17 | no | 4 months |  | 119419417.5 | 50000000 | 2014-05-01 | 2014-05-01 |  |  | 35786100.72 | Dec, 2015 | 20%
2 | expansion and eqipping of mortuary | supply | June 2013, Federal teanders journal, punch, daily trust | PTB | NCB | 2013-07-29 |  | Messrs swiss biostadt Limited | NA |  | 2013-09-19 | no | 12 weeks |  | 49997015 | 35000000 | 2013-10-01 | Oct, 2013 |  |  | 23776567.25 | 2014-12-01 | 100%
3 | Building of CT Scan and Accessories | works | July 25,2011 punch, Daily trust | PTB | NCB | Sept 5,2013 |  | Messrs Enorasol International Limited | NA |  | 2011-11-04 | yes | 6months |  | 197534172.75 | 50200000 | 2013-11-01 | nov, 2011 |  |  | 125978454.74 | Dec, 2015 | 62%
4 | construction of 2 storey school block | works | June 17,2013, punch, daily trust Federal Tenders Journal | PTB | NCB | July 29,2013 |  | Messrs Best Southern Global Service Limited | NA |  | 2013-09-20 | Yes | 12 months |  | 173112423.75 | 80000000 | 2013-10-01 | 2013-10-01 |  |  | 34318044.7 | Dec, 2016 | 20%
5 | Completion of theater in Othopedic Block | Works | May 28, 2012 Punch, Leadership, Federal Tenders Journal | PTB | NCB | July 9,2012 |  | Messrs Vikage Delite Services Company | NA |  | 2014-11-10 | yes | 6 months |  | 56899150.48 | 54758230 |  | Nov, 2012 |  |  | 8534873 | Dec, 2015 | 30%
6 | Construction of 2 Storey Laboratory Building | works | May 28, 2012 Punch, Leadership, Federal Tenders Journal | PTB | NCB | July 9,2012 |  | Messrs Kubito Techcnical Services | NA |  | 2012-08-17 | Yes | 6months |  | 174113650 | 84549000 |  | Aug, 2012 | 2013-12-16 | 18810345 | 121175079.02 | Dec, 2015 | 60%

## CBDA
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) : |  |  | CHAD BASIN DEVELOPMENT AUTHRITY
MINISTRY : |  |  | FEDERAL MINSTRY OF WATER RESOURCES
FINANCIAL YEAR : |  |  | 2014
|  | BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2014 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 |  | GORA IRRIGATION SCHEME` | [5 empty] | 12000000
I | 1 | Provision of 29nos. Washbores with Pumps for Irrigation at Gora Irrigation Scheme | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Alh. Adam Umar Nigeria Enterprises | 8th September, 2014 | 4788103 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed awaitimg payment
II | 2 | Supply of Agric. Herbicides | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Shitikam Farms Ltd | 8th September, 2014 | 1470500 | 2MONTHS | 22nd Sept. 2014 | 1470500 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed awaiting payment
III | 3 | Supply of consumable items to commission CASIDA Water plant to commence production. | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | A.A.M Standard Vision Ltd | 8th September, 2014 | 3360000 | 2MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed awaiting payment
2 |  | GASHUA IRRIGATION SCHEME | [5 empty] | 16000000
I | 4 | Completion of Gashua Area Office (on-going) | 28th May, 2012 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | ongoing | ongoing |  | 4th September, 2012 | 4th September, 2012 | LEAST TENDERER | Tekno Concept Construction Ltd | 4th September, 2012 | 16000000 | 3MONTHS | 20th September, 2012 | 16000000 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed
3 |  | MICHIKA IRRIGATION SCHEME | [5 empty] | 24000000
I | 5 | Provision of 29nos. Washbores with pumps for irrigation at Michika Irrigation Scheme | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Bizinda Enterprises | 8th September, 2014 | 4843000 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed awaiting payment
II | 6 | Supply of Furniture for Michika Irrigation Scheme | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Musami Supplies Co. Nigeria Ltd | 8th September, 2014 | 3452866 | 2MONTHS | 22nd Sept. 2014 | 3452866 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | completed
III | 7 | Procurement of 66,000litres AGO | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Masida Nigeria Ltd | 8th September, 2014 | 12790800 | 2MONTHS | 22nd Sept. 2014 | 6395400 | 31st Dec. 2014 | 50% | 50% | N/A | N/A | contract determined at 50%
IV | 8 | Feasibility Studies for Small Earth Dam at Mussa Askira – Uba LGA, Yobe State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | UBCS Ltd | 8th September, 2014 | 1200000 | 2MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed awaiting payment
4 |  | GARIN GADA / NGALDA IRRIGATION SCHEME | [5 empty] | 13600000
I | 9 | Provision of 29nos.Washbores with Pumps for Irrigation at Garin Gada / Ngalda Irrigation Scheme | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Shuma Ventures | 8th September, 2014 | 4785058 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed Awaiting payment
II | 10 | Procurement of 40,000litres AGO | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Bamus Investment Ltd | 8th September, 2014 | 7752000 | 2MONTHS | 22nd Sept. 2014 | 7752000 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed
5 |  | JERE BOWL RICE SCHEME | [5 empty] | 8000000
I | 11 | Development of Fish hatchery | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Teakwood Nigeria Ltd | 8th September, 2014 | 5684779.6 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 70% | 70% | N/A | N/A | Contractor could not make progress beyond 70% due to non funding (payment of work done)
II | 12 | Supply of Hatchery Equipment, Fish Feeds & Medicals | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | El-Qasim & Associates | 8th September, 2014 | 1835640 | 2MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed awaiting payment
6 |  | HYDROMET | [5 empty] | 16400000
I | 13 | Establishment of 2nos. Automated Hydromet Stations | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | A.B.A Metrotech. Nigeria Ltd | 8th September, 2014 | 14284700 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed awaitimg payment
7 |  | PROVISION OF 3NOS. SOLAR POWERED BOREHOLES AT MAJITA – NGANZAI LGA, ALKEDEWO – JERE LGA & SOGOMA – DIKWA LGA BORNO STATE | [5 empty] | 18000000
I | 14 | Drilling of 1no. Solar Powered Borehole at Manjita – Nganzai LGA, Borno State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Muzafa Drilling Co. Nigeria Ltd | 8th September, 2014 | 18000000 | 3MONTHS | 22nd Sept. 2014 | 18000000 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed
8 |  | CONSTRUCTION OF SOLAR POWERED BOREHOLE AND RETICULATION AT JUMMAA POTISKUM LGA, YOBE STATE | [5 empty] | 20000000
I | 15 | Drilling & Reticulation of 1no. Solar Powered Borehole at Jummaa, Potiskum LGA, Yobe State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | All Sets Ventures | 8th September, 2014 | 13666575 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed awaitimg payment
II | 16 | Drilling of 5nos. Handpump Boreholes at Potiskum LGA, Yobe State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Tarik Multi Concept Ltd | 8th September, 2014 | 6333425 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed awaitimg payment
9 |  | WATER SUPPLY IN THE FEDERAL UNIVERSITY GASHUA YOBE STATE | [5 empty] | 20000000
I | 17 | Drilling of Solar Powered Borehole at Federal University Gashua, Yobe State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Safcon Intl. Wells | 8th September, 2014 | 11096700 | 3MONTHS | 22nd Sept. 2014 | 0 |  | 100% | 100% | N/A | N/A | Completed awaitimg payment
II | 18 | Drilling of 8nos. Handpump Boreholes at Bade LGA, Yobe State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Nugget Wells Intl. Nig. Ltd | 8th September, 2014 | 8903300 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed awaitimg payment
10 |  | SOLAR POWERED BOREHOLES AT BADE LGA | [5 empty] | 100000000
I | 19 | Drilling of 7nos. Solar Powered Boreholes at Bade LGA, Yobe State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Kimrams Nigeria Ltd | 8th September, 2014 | 99750000 | 3MONTHS | 22nd Sept. 2014 | 12468750 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed awaiting payment of balance
11 |  | SOLAR POWERED BOREHOLES AT JAKUSKO LGA | [5 empty] | 100000000
I | 20 | Drilling of 7nos. Solar Powered Boreholes at Jakusko LGA, Yobe State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Marmai Nigeria Ltd | 8th September, 2014 | 98265755 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed awaitimg payment
12 |  | PROCUREMENT OF WATER PUMPS FOR DRY SEASON FARMING FOR MAFA/DIKWA/KONDUGA FEDERAL CONSTITUENCY | [5 empty] | 15989330
I | 21 | Procurement of 500nos. 2” Portable Irrigation Pumps for Mafa/Dikwa/Konduga Federal Constituency | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Gascomedia Nigeria Ltd | 8th September, 2014 | 13850000 | 2MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 50% | 50% | N/A | N/A | 50% supplied awaiting payment for items supplied
13 |  | PROVISION OF WASHBORES & TUBEWELLS WITH 2” & 3” WATERPUMPS FOR IRRIGATION IN GUJBA & GULANI LGA | [5 empty] | 70000000
I | 22 | Provision of 120nos. Washbores with 2” pumps for Irrigation at Gujba & Gulani LGA, Yobe State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Nugela Standard Resources | 8th September, 2014 | 11166120 | 3MONTHS | 22nd Sept. 2014 | 5583060 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed
II | 23 | Provision of 120nos. Washbores with 2” pumps for Irrigation at Gujba & Gulani LGA, Yobe State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Alhaji Ali Kaka and Sons Nigeria Ltd | 8th September, 2014 | 11166120 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed awaiting payment
III | 24 | Provision of 120nos. Washbores with 2” pumps for Irrigation at Gujba & Gulani LGA, Yobe State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Al-Tajir Global Services Ltd | 8th September, 2014 | 11140800 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed awaiting payment
IV | 25 | Provision of 120nos. Washbores with 3” pumps for Irrigation at Gujba & Gulani LGA, Yobe State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Amoturi Drilling & Construction Ltd | 8th September, 2014 | 12432120 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed awaiting payment
V | 26 | Provision of 120nos. Washbores with 3” pumps for Irrigation at Gujba & Gulani LGA, Yobe State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Al-Adamali Global Company Ltd | 8th September, 2014 | 12432120 | 3MONTHS | 22nd Sept. 2014 | 12432120 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed
VI | 27 | Provision of 120nos. Washbores with 3” pumps for Irrigation at Gujba & Gulani LGA, Yobe State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Majab Global Services Ltd | 8th September, 2014 | 11520600 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed awaiting payment
14 |  | CONSTRUCTION OF 5BLOCKS OF THREE CLASS ROOM AND FURNITURE AT FIKA & FUNE LGAS, YOBE STATE | [5 empty] | 38069834
I | 28 | Construction of 3blocks of Three Classroom with Furniture at Jangam Community High Islamic School – Gadaka, Moi Mama Primary School, Damazai Primary School Fika LGA, Yobe State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Al-Tajir Global Services Ltd | 8th September, 2014 | 22253650.65 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed awaitimg payment
II | 29 | Construction of 2blocks of Three Classroom with Furniture at Abakire Primary School, Jajere Central Primary School in Fune LGA, Yobe State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Zaifam Global Services | 8th September, 2014 | 15349165.6 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed awaitimg payment
15 |  | PROVISION OF WASHBORES AND TUBEWELLS WITH 2” & 3” WATER PUMPS FOR IRRIGATION IN KWAYA KUSAR, SHANI, BAYO & BIU LGAs, BORNO STATE | [5 empty] | 50000000
I | 30 | Provision of 39nos. Tubewells with 2” Pumps for Irrigation in Kwaya Kusar, Shani, Bayo & Biu LGAs, Borno State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | L&T Hydrogeo Engineering Co. Nigeria Ltd | 8th September, 2014 | 19563375 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 40% | 40% | N/A | N/A | Project work 40% completion, but stalled due to insurgency
II | 31 | Provision of 58nos. Tubewells with 3” Pumps for Irrigation in Kwaya Kusar, Shani, Bayo & Biu LGAs, Borno State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | L&T Hydrogeo Engineering Co. Nigeria Ltd | 8th September, 2014 | 30105480 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 40% | 40% | N/A | N/A | Project work 40% completion, but stalled due to insurgency
16 |  | PROVISION OF 1NO. SOLAR POWERED BOREHOLES IN EACH OF THE 17NOS. LGAS OF YOBE STATE | [5 empty] | 102000000
I | 32 | Drilling of 3nos. Solar Powered Borehole at Dadingel Village, Gujba LGA, Gagure, Gulani LGA and Sungul, Tarmuwa LGA, Yobe State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Aqua Mega Tech. Synergy Ltd | 8th September, 2014 | 38550002.75 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 40% | 40% | N/A | N/A | Stalled due to insurgency
II | 33 | Drilling of 3nos. Solar Powered Borehole at Sauda Village, Alagarno Ward Fune LGA, Hausari Gadaka Fika LGA, and Yanki Shida, Potiskum LGA, Yobe State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Tarik Multi Concept Ltd | 8th September, 2014 | 36032550 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 40% | 40% | N/A | N/A | Stalled due to insurgency
III | 34 | Drilling of 1no. Solar Powered Borehole at Dami, Machina LGA, & Rehabilitation of 2nos. Boreholes at Katuzu & 1no. Borehole at Gashua Prison Jabulle Bade LGA, Yobe State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Well Truth Nigeria Ltd | 8th September, 2014 | 18536740 | 3MONTHS | 22nd Sept. 2014 | 10000000 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed,53.9% paid awaiting payment of balance
IV | 35 | Drilling of 5nos. Handpump Boreholes at Karasuwa Galu, Bayamari, Karage, Garin Rafi and Jaji Maji in Yobe State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Tsofo & Company Nigeria Ltd | 8th September, 2014 | 6039875 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed awaitimg payment
17 |  | IMPROVEMENT OF WATER SUPPLY IN BUNI GARI / BUNI YADI | [5 empty] | 12000000
I | 36 | Improvement of Water Supply in Buni Gari / Buni Yadi (Drilling of 1no. solar powered tubewell & conversion of 3nos. motorized boreholes to solar powered boreholes) | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | F&B Water Skills Nigeria Ltd | 8th September, 2014 | 11936130 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 25% | 25% | N/A | N/A | project stalled at 25% due to insurgency
18 |  | BAGA POLDER PROJECT (REHABILITATION WORKS) | [5 empty] | 26000000
I | 37 | Completion of Pump House (On-going) | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Hywatts Engineering & Construction Co. Ltd | 8th September, 2014 | 7850000 | 3MONTHS | 22nd Sept. 2014 | 7850000 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed
II | 38 | Procurement of Welding Machine, Repairs of Plants & Transport Vehicles | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Real Tech. Ventures | 8th September, 2014 | 4716180 | 2MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed awaiting payment
III | 39 | Procurement of Combine Harvester Spare Parts | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Scoa Nigeria Plc | 8th September, 2014 | 6000000 | 2MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 0% | 0% | N/A | N/A | Yet to supplied
IV | 40 | Procurement of 33,000litres AGO & Lubricants | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Mai Azir Nigeria Ltd | 8th September, 2014 | 7348112.15 | 2MONTHS | 22nd Sept. 2014 | 7348112.15 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | completed
19 |  | REHABILITATION OF PLANT & MACHINERY | [5 empty] | 37053960
I | 41 | Procurement of 1no. Land Cruiser Jeep | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Sauki Supplies Ltd | 8th September, 2014 | 20570000 | 2MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | supplied awaiting payment
II | 42 | Procurement of 5nos. offset Semi Mounted Heavy Duty Harrow | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Scoa Nigeria Plc | 8th September, 2014 | 14750000 | 2MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | supplied awaiting payment
20 |  | ALAU DAM | [5 empty] | 10000000
I | 43 | Rehabilitation of Dam Auxiliaries (Dam Gate Electrical Component) | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Chris Electrical Works | 8th September, 2014 | 2000000 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 0% | 0% | N/A | N/A | contractor could not mobilized due to insecurity
II | 44 | Procurement of Complete Engine for CAT 120H Motor Grader | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Abdulaziz Amao Technical Co. Ltd | 8th September, 2014 | 8000000 | 2MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 0% | 0% | N/A | N/A | Contract determined
21 |  | SOUTH CHAD IRRIGATION PROJECT | [5 empty] | 82000000
I | 45 | Rehabilitation of 30MW Power Station and Pump Stations Mechanical & Electrical Components at SCIP I New Marte | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Orunrun Energy Services Ltd | 8th September, 2014 | 48623058.5 | 3MONTHS | 22nd Sept. 2014 | 16779000 | 31st Dec. 2014 | 35% | 35% | N/A | N/A | Training completed supply of spares awaited
II | 46 | Supply of 4nos. Toyota Corolla 1.6litre Engine Model 2014 | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Malam Ka’amari Ventures | 8th September, 2014 | 27720000 | 2MONTHS | 22nd Sept. 2014 | 27720000 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | completed
III | 47 | Completion of Reconstruction of CBDA Guest House MAN CAMP SCIP I New Marte | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 3rd June, 2013 | 30 June, 2013 |  | 2013-09-06 | 2013-09-05 | LAEST TENDERER | Maimusari Investment Ltd | 6th September, 2013 | 19058530 | 3MONTHS | 20th Sept. 2012 | 11435118.3 | 31st Dec. 2012 | 80% | 80% | N/A | N/A | Work stalled due to insurgency
22 |  | HEADQUARTERS & AREA OFFICES DEVELOPMENT | [5 empty] | 24000000
I | 48 | Improvement of Water Supply in CBDA Colony AHQ – Maiduguri Borno State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Eauxwell Nigeria Ltd | 8th September, 2014 | 10497900 | 3MONTHS | 22nd Sept. 2014 | 10497900 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed
II | 49 | Construction of Access Road Network Phase IV to Water Bottling Plant | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Hywatts Engineering & Construction Co. Ltd | 8th September, 2014 | 13502100 | 3MONTHS | 22nd Sept. 2014 | 13502100 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed
23 |  | PROVISION OF 3 UNITS OF MOTORIZED BOREHOLES KARLAJE GUNDENYI – GUYUK ADAMAWA STATE | [5 empty] | 20000000
I | 50 | Drilling of 2nos. Motorized Boreholes at Karlaje Gundenyi – Guyuk Adamawa State. | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Aquavic Investment Co. Nigeria Ltd | 8th September, 2014 | 14406550 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed awaitimg payment
II | 51 | Drilling of 5nos. Handpump Boreholes at Karlaje Gundenyi – Guyuk Adamawa State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Aquavic Investment Co. Nigeria Ltd | 8th September, 2014 | 5593450 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed awaitimg payment
24 |  | EARTH DAM ON GOING PROJECTBOGGA GELLA MUBI ADAMAWA STATE | [5 empty] | 70000000
I | 52 | Completion of Earth Dam at Bogga Gella Mubi South LGA, Adamawa State | 5th May, 2013 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | ongoing | ongoing |  | 6th September, 2013 | 6th September, 2013 | LEAST TENDERER | Bam Darley Nigeria Ltd | 20th September, 2013 | 68763810.47 | 3MONTHS | 31st December, 2014 | 10314571.57 | 31st Dec. 2014 | 50% | 50% | N/A | N/A | Work in progress project rolled over
25 |  | COMPLETION OF 3NOS. WATER CONTROL GATES PROJECTS BADE LGA, YOBE STATE | [5 empty] | 20000000
I | 53 | Completion of 3nos. Water Control Gates Projects at Bade LGA, Yobe State | 5th May, 2013 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | ongoing | ongoing |  | 6th September, 2013 | 6th September, 2013 | LEAST TENDERER | Kaks Construction and Consult Ltd | 20th September, 2013 | 20000000 | 3MONTHS | 31st December, 2014 | 20000000 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed
26 |  | REHABILITATION OF 1NO. BOREHOLE IN ZANGO GASHUA, YOBE STATE | [5 empty] | 4880000
I | 54 | Rehabilitation of 1no. Borehole in Zango Gashua Bade LGA, Yobe State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Aqua Magic Resources Nigeria Ltd | 8th September, 2014 | 4171470 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed awaitimg payment
27 |  | PROVISION OF 3NOS. SOLAR BOREHOLES IN BADE/JAKUSKO LGA, YOBE STATE | [5 empty] | 45000000
I | 55 | Drilling of 3nos. Solar Powered Boreholes at Katuzu in Gashua, Bade LGA and Jakusko & Dachia in Jakusko LGA, Yobe State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Alfa Development Services Ltd | 8th September, 2014 | 36818625 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed awaitimg payment
II | 56 | Drilling of 7nos. Handpump Boreholes at Bade & Jakusko LGAs, Yobe State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Danna Umar Global Nigeria Ltd | 8th September, 2014 | 8181375 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed awaitimg payment
28 |  | PROVISION OF 3NOS. HANlDPUMPS AT N2M EACH YOBE STATE | [5 empty] | 6000000
I | 57 | Drilling of 3nos. Handpump Boreholes at Musulli & Zango in Bade LGA and Kajuwa Bula-Bade in Jakusko LGA, Yobe State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Ains Borehole Drilling Services | 8th September, 2014 | 2670783 | 3MONTHS | 22nd Sept. 2014 | 2670783 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed
29 |  | PROVISION OF 60NOS. TBS TRICYCLES AT N500,000 EACH FOR 20 WARDS IN BADE/JAKUSKO LGAs OF YOBE STATE | [5 empty] | 30000000
I | 58 | Procurement of 49nos. Tricycles for 20wards in Bade & Jakusko LGAs, Yobe State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Ecarg Global Resources Nigeria Ltd | 8th September, 2014 | 29767500 | 2MONTHS | 22nd Sept. 2014 | 6378500 | 31st Dec. 2014 | 50% | 50% | N/A | N/A | contract determined at 50%
30 |  | PROVISION OF 200NOS. KASEA/MOTOR BI MOTOR CYCLES AT N150,000EACH FOR 20WARDS IN BADE/JAKUSKO LGAs IN YOBE STATE | [5 empty] | 30000000
I | 59 | Procurement of 200nos. Motorcycles for 20wards in Bade & Jakusko LGAs, Yobe State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Yerima Kida Memorial Co. Ltd | 8th September, 2014 | 29329000 | 2MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 0% | 0% | N/A | N/A | Contract Determined
31 |  | ON-GOING PURCHASE OF 1NO. 27KVA WATER PUMP & RETICULATION FROM KONKONMA TO MACHINA, YOBE STATE | [5 empty] | 16600000
I | 60 | Completion of Works on 1no. 27.5 KVA Gen. Set, Buster Pump and Reticulation Works from Kaisawa to Goki, Barmadi and Goki Jajere in Machina LGA Yobe State | 28th May, 2012 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | ongoing | ongoing |  | 4th September, 2012 | 4th September, 2012 | LEAST TENDERER | Bolo Water Ventures Ltd | 4th September, 2012 | 16600000 | 3MONTHS | 20th September, 2012 | 16000000 | 31st Dec. 2013 | 100% | 100% | N/A | N/A | Completed
32 |  | ON-GOING PROVISION OF 2NOS. BOREHOLES AT KONKONMA , YOBE STATE | [5 empty] | 17100000
I | 61 | Completion of 2nos. Motorized Boreholes at Konkonma – Machina LGA – Yobe State | 28th May, 2012 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | ongoing | ongoing |  | 4th September, 2012 | 4th September, 2012 | LEAST TENDERER | Damaram Design and Construction Nigeria Ltd | 4th September, 2012 | 17100000 | 3MONTHS | 20th September, 2012 | 17100000 | 31st Dec. 2013 | 100% | 100% | N/A | N/A | completed
33 |  | ON – GOING CONSTRUCTION OF OVERHEAD TANK & RETICULATION AT GOKI TOWN, GOKI VILLAGE MACHINA LGA, YOBE STATE | [5 empty] | 9600000
I | 62 | Completion of works on Erection of 10,000 Gallons Overhead Tank at Goki in Machina LGA, Yobe State | 28th May, 2012 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | ongoing | ongoing |  | 4th September, 2012 | 4th September, 2012 | LEAST TENDERER | Tropical Investment Ltd | 4th September, 2012 | 9600000 | 3MONTHS | 20th September, 2012 | 9600000 | 31st Dec. 2013 | 100% | 100% | N/A | N/A | Completed
34 |  | PROVISION OF HAND PUMPS AT MACHINA, YOBE STATE | [5 empty] | 5000000
I | 63 | Drilling of 4nos. Handpump Boreholes Ghana A., Kangarwa Gabar, Kangarwa Yamma & Rigar Hardo Bamai in Machina LGA, Yobe State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Hypernet Homes Ltd | 8th September, 2014 | 3350680 | 3MONTHS | 22nd Sept. 2014 | 3350680 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed
35 |  | 2 UNITS SOLAR POWERED BOREHOLE COMPLETE @ N7,000,000 EACH IN (1) ASKIRA TOWN (2) UBA TOWN, ASKIRA UBA LGA, BORNO STATE | [5 empty] | 14000000
I | 64 | Drilling of 2nos. Solar Powered Boreholes at Askira Town & Uba Town in Askira Uba LGA, Borno State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Lama Drilling Co. Nigeria Ltd | 8th September, 2014 | 13801550 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 50% | 50% | N/A | N/A | Work stalled due to insurgency
36 |  | 2 UNITS SOLAR POWERED BOREHOLE COMPLETE @ N7,000,000 EACH (1) CHATA TOWN (2) KWAYA BURA TOWN, HAWUL LGA, BORNO STATE | [5 empty] | 14000000
I | 65 | Drilling of 2nos. Solar Powered Boreholes at Chata Town & Kwaya Bura Town in Hawul LGA, Borno State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Lama Drilling Co. Nigeria Ltd | 8th September, 2014 | 13841550 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 50% | 50% | N/A | N/A | Work stalled due to insurgency
37 |  | HAND PUMP WATER BOREHOLES AT BAYO AND BIU LGA, BAYO/BIU/SHANI/KWAYA KUSAR FED. CONST. BORNO STATE | [5 empty] | 40000000
I | 66 | Drilling of 16nos. Handpump Boreholes at Bayo LGAs in Bayo/Biu/Shani/Kwaya Kusar Federal Constituency – Borno State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | L&T Hydrogeo Engineering Co. Nigeria Ltd | 8th September, 2014 | 19817120 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 50% | 50% | N/A | N/A | Work stalled due to insurgency
II | 67 | Drilling of 16nos. Handpump Boreholes at Biu LGAs in Bayo/Biu/Shani/Kwaya Kusar Federal Constituency – Borno State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | L&T Hydrogeo Engineering Co. Nigeria Ltd | 8th September, 2014 | 18306352 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 50% | 50% | N/A | N/A | Work stalled due to insurgency
38 |  | COMPLETION OF 23KM (33KV LINE) PROJECT FROM DACHIA – DAWAYO JUNCTION BADE LGA, YOBE STATE | [5 empty] | 41120000
I | 68 | Completion of 33KV Line from Dachia to Dawayo Junction Bade LGA, Yobe State | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Kaks Construction and Consult Ltd | 8th September, 2014 | 40576305 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed Awaiting payment
39 | 69 | Construction of 2nos. Poultry house for 500 birds capacity, | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Shet Scientific Nigeria Ltd. | 8th September, 2014 | 5512796 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 70% | 70% | N/A | N/A | Project stalled at 70% due to non payment for work done
40 | 70 | Supply of 1no. Tubewell drilling Rig. | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Truchads Nigeria Ltd. | 8th September, 2014 | 4900000 | 2MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed Awaiting payment
41 | 71 | Supply of office furniture and equipment for finance/accounts and planning divission | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Musami Supplies Co. Nigeria Ltd | 8th September, 2014 | 4937400 | 2MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed Awaiting payment
42 | 72 | Rehabilitation of SSQ at AHQ Maiduguri | 30th June, 2014 (1.) Federal Tenders Journal. (2.) Daily Trust News Papers (3.) Leadership News Paper | PTB | Open Compitative Bidding | 12th August, 2014 | 3rd September, 2014 |  | 8th September, 2014 | 8th September, 2014 | LEAST TENDERER | Global Tickson | 8th September, 2014 | 4733274 | 3MONTHS | 22nd Sept. 2014 | 0 | 31st Dec. 2014 | 100% | 100% | N/A | N/A | Completed Awaiting payment
|  | GRAND TOTAL | [5 empty] | 1198413124 | [5 empty] | 1203753521.72 |  |  | 274101461.02

## EMSL
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) : |  | ELECTRICITY MANAGEMENT SERVICES LIMITED (EMSL)
MINISTRY : |  | FEDERAL MINISTRY OF POWER
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE (TECHNICAL & FINANCIAL) | BIDS EVALUATION REPORT DATE (TECHNICAL & FINANCIAL) | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2014 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | Preparation of IT Standards and Policies for EMSL | 30th June, 2014 (Federal Tenders Journal, The Guardian and Daily Trust Newspapers) | ETB | Open | 20th August, 2014 24th September, 2014 | 17th September, 2014 3rd October, 2014 | 19800000 | N/A | 3rd October, 2014 | Yes | Messrs ChallyDoff Ltd | 15th October, 2014 | 14805000 | Three (3) months | October, 2014 | 0 | December, 2014 | Completed | 100% | N/A | N/A
2 | Purchase and Installation of Office Furniture | 30th June, 2014 (Federal Tenders Journal, The Guardian and Daily Trust Newspapers) | ETB | Open | 21st August, 2014 24th September, 2014 | 17th September, 2014 3rd October, 2014 | 72192628.775 | N/A | 3rd October, 2014 | Yes | Messrs Itex Furniture Ltd | 15th October, 2014 | 60402772.5 | Four (4) weeks | October, 2014 | 36241663.49 | December, 2014 | On-going | 60% | N/A | N/A
3 | Procurement and Installation of Computer Systems and Accessories | 30th June, 2014 (Federal Tenders Journal, The Guardian and Daily Trust Newspapers) | ETB | Open | 21st August, 2014 24th September, 2014 | 17th September, 2014 3rd October, 2014 | 49,500,000.00 | N/A | 3rd October, 2014 | Yes | Messrs Pyrich Group Ltd | 15th October, 2014 | 40760520.08 | Four (4) weeks | October, 2014 | 0 | December, 2014 | Completed | 100% | N/A | N/A
4 | Procurement and installation of Working Tools for the Three Meter Test Stations | 30th June, 2014 (Federal Tenders Journal, The Guardian and Daily Trust Newspapers) | ETB | Open | 26th August, 2014 24th September, 2014 | 17th September, 2014 3rd October, 2014 | 27,277,659.57 | N/A | 3rd October, 2014 | Yes | Messrs Gastec E & P Services Ltd | 15th October, 2014 | 21174615 | Two (2) weeks | October, 2014 | 0 | November, 2014 | On-going | 5% | N/A | N/A
5 | Procurement and Installation of Industrial Mechanical Equipment and Machines for Transformer Repairs Workshop | 30th June, 2014 (Federal Tenders Journal, The Guardian and Daily Trust Newspapers) | ETB | Open | 28th August, 2014 24th September, 2014 | 17th September, 2014 3rd October, 2014 | 293903023.98 | N/A | 3rd October, 2014 | Yes | Messrs Sectronics International Ltd | 15th October, 2014 | 105000000 | Fourteen (14) weeks | October, 2014 | 15750000 | January, 2015 | On-going | 10% | N/A | N/A
6 | Procurement and Installation of Test Equipment and Instruments for Transformer Repairs Workshop | 30th June, 2014 (Federal Tenders Journal, The Guardian and Daily Trust Newspapers) | ETB | Open | 28th August, 2014 24th September, 2014 | 17th September, 2014 3rd October, 2014 |  | N/A | 3rd October, 2014 | Yes | Messrs Newbay Engineering Ltd | 15th October, 2014 | 48417001.92 | Twelve (12) weeks | October, 2014 | 0 | January, 2015 | On-going | 5% | N/A | N/A
7 | Purchase and Installation of Industrial Electrical Equipment and Machines for Transformer Repairs Workshop | 30th June, 2014 (Federal Tenders Journal, The Guardian and Daily Trust Newspapers) | ETB | Open | 28th August, 2014 24th September, 2014 | 17th September, 2014 3rd October, 2014 |  | N/A | 14th October, 2014 | Yes | Messrs Matini Eng. & Construction Nig. Ltd | 22nd October, 2014 | 97756181.25 | Eight (8) weeks | October, 2014 | 14663427.18 | December, 2014 | On-going | 30% | N/A | N/A
8 | Establishment of Local Area Networks (LANs) in EMS Headquarters | 30th June, 2014 (Federal Tenders Journal, The Guardian and Daily Trust Newspapers) | ETB | Open | 20th August, 2014 24th September, 2014 | 17th September, 2014 3rd October, 2014 | 39600000 | N/A | 14th October, 2014 | Yes | Messrs ASM Technologies Ltd | 15th October, 2014 | 36379665 | Six (6) weeks | October, 2014 | 21827799 | December, 2014 | On-going | 55% | N/A | N/A
9 | Acquisition and Installation of EMIS Equipment and Development of a Management System | 30th June, 2014 (Federal Tenders Journal, The Guardian and Daily Trust Newspapers) | ETB | Open | 20th August, 2014 24th September, 2014 | 17th September, 2014 3rd October, 2014 | 69300000 | N/A | 14th October, 2014 | Yes | Messrs O. T. Otis Engineering Ltd | 15th October, 2014 | 65000000 | Three (3) months | October, 2014 | 48750000 | January, 2015 | On-going | 60% | N/A | N/A
10 | Purchase of One (1) No. Heavy Duty Truck (25 Tons) with Self Loading Crane (20 Tons) with Spare Parts and Two (2) Nos. Forklift (3 Tons) with Spare Parts | 30th June, 2014 (Federal Tenders Journal, The Guardian and Daily Trust Newspapers) | ETB | Open | 25th August, 2014 24th September, 2014 | 17th September, 2014 3rd October, 2014 | 79200000 | N/A | 14th October, 2014 | Yes | Messrs Sam & Sam International Ltd | 15th October, 2014 | 73451881.68 | Four (4) weeks | October, 2014 | 0 | November, 2014 | Completed | 100% | N/A | N/A
11 | Remodeling of Meter Test Station Oshodi, Lagos | 30th June, 2014 (Federal Tenders Journal, The Guardian and Daily Trust Newspapers) | ETB | Open | 28th August, 2014 24th September, 2014 | 17th September, 2014 3rd October, 2014 | 118800000 | N/A | 14th October, 2014 | Yes | Messrs Dizzat Engineering Co. Ltd | 15th October, 2014 | 115200000 | Three (3) months | October, 2014 | 87552000 | January, 2015 | On-going | 85% | N/A | N/A
12 | Renovation of the Central Workshop, Ijora | 30th June, 2014 (Federal Tenders Journal, The Guardian and Daily Trust Newspapers) | ETB | Open | 28th August, 2014 24th September, 2014 | 17th September, 2014 3rd October, 2014 | 110000000 | N/A | 14th October, 2014 | Yes | Messrs Ephdeino Nig. Ltd | 15th October, 2014 | 104329782.64 | Three (3) months | October, 2014 | 64622576 | January, 2015 | On-going | 75% | N/A | N/A
13 | Consultancy for Selection, Design and Customisation for the Implementation of an ERP for EMSL (Accounting, HR System, Payroll, Audit and Inventory System) | 30th June, 2014 (Federal Tenders Journal, The Guardian and Daily Trust Newspapers) | ETB | Open | 20th August, 2014 24th September, 2014 | 17th September, 2014 3rd October, 2014 | 79200000 | N/A | 21st October, 2014 | Yes | Messrs Ernst & Young Ltd | 22nd October, 2014 | 47900000 | Ten (10) months | October, 2014 | 19160000 | July, 2015 | Completed | 40% | N/A | N/A
14 | Consultancy for Data Gathering, Processing, Archiving, Indexing and Management for Electricity Management Information System (EMIS) | 30th June, 2014 (Federal Tenders Journal, The Guardian and Daily Trust Newspapers) | ETB | Open | 20th August, 2014 24th September, 2014 | 17th September, 2014 3rd October, 2014 | 49500000 | N/A | 21st October, 2014 | Yes | Messrs H. Pierson Associates Ltd | 22nd October, 2014 | 46500000 | Six (6) months | October, 2014 | 19530000 | April, 2015 | On-going | 40% | N/A | N/A
15 | VSAT/ Telecoms Equipment and Bandwidth Costs for EMSL | 30th June, 2014 (Federal Tenders Journal, The Guardian and Daily Trust Newspapers) | ETB | Open | 20th August, 2014 24th September, 2014 | 17th September, 2014 3rd October, 2014 | 29700000 | N/A | 21st October, 2014 | Yes | Messrs Radial Circle Telecoms Ltd | 22nd October, 2014 | 25000000 | Eight (8) weeks | October, 2014 | 0 | December, 2014 | On-going | 70% | N/A | N/A
16 | Acquisition and installation of Software Licenses (Operating Systems, Firewalls, Desktop Applications and Antivirus) for EMSL | 30th June, 2014 (Federal Tenders Journal, The Guardian and Daily Trust Newspapers) | ETB | Open | 20th August, 2014 24th September, 2014 | 17th September, 2014 3rd October, 2014 | 24750000 | N/A | 21st October, 2014 | Yes | Messrs Task Systems Ltd | 22nd October, 2014 | 21650000 | Eight (8) weeks | October, 2014 | 0 | December, 2014 | On-going | 80% | N/A | N/A
17 | Purchase and Installation of Three (3) Nos. Mobile Test Equipment Class 0.05, One (1) No. Shock Test Equipment and One (1) No. Vibration Test Equipment | 30th June, 2014 (Federal Tenders Journal, The Guardian and Daily Trust Newspapers) | ETB | Open | 26th August, 2014 24th September, 2014 | 17th September, 2014 3rd October, 2014 | 30436363.64 | N/A | 21st October, 2014 | Yes | Messrs Mojec International Ltd | 22nd October, 2014 | 42430342.5 | Three (3) months | October, 2014 | 0 | January, 2015 | On-going | 0% | N/A | N/A
18 | Purchase and Installation of Working Tools for Ijora Central Workshop | 30th June, 2014 (Federal Tenders Journal, The Guardian and Daily Trust Newspapers) | ETB | Open | 28th August, 2014 24th September, 2014 | 17th September, 2014 3rd October, 2014 | 19103696.56 | N/A | 21st October, 2014 | Yes | Messrs Enzha Services Ltd | 22nd October, 2014 | 19479390 | Four (4) weeks | October, 2014 | 0 | November, 2014 | On-going | 5% | N/A | N/A
19 | Procurement and Installation of 33KV Outdoor Circuit Breaker at Kontagora Transmission Station for Matandi Dam, Niger State | 28th July, 2014 (Federal Tenders Journal, The Guardian and Daily Trust Newspapers) | ETB | Open | 8th September, 2014 15th October, 2014 | 3rd October, 2014 3rd November, 2014 | 24750000 | N/A | 5th November, 2014 | Yes | Messrs Heartians Investment Corporation Ltd | 6th November, 2014 | 12676675 | Four (4) weeks | November, 2014 | 0 | December, 2014 | On-going | 30% | N/A | N/A
20 | Procurement and Installation of 3 Units of 500KVA, 11/0.415KV Transformers in Ondo Central Senatorial District, Ondo State | 28th July, 2014 (Federal Tenders Journal, The Guardian and Daily Trust Newspapers) | ETB | Open | 8th September, 2014 15th October, 2014 | 3rd October, 2014 3rd November, 2014 | 29700000 | N/A | 5th November, 2014 | Yes | Messrs Bedrock Construction Ltd | 6th November, 2014 | 21016275 | Six (6) weeks | November, 2014 | 0 | January, 2015 | On-going | 70% | N/A | N/A
21 | Procurement and Installation of 2 Nos. 500KVA Transformers in Kontagora/ Wushishi/ Mairiga/ Mashegu L.G.A. Niger State | 28th July, 2014 (Federal Tenders Journal, The Guardian and Daily Trust Newspapers) | ETB | Open | 8th September, 2014 15th October, 2014 | 3rd October, 2014 3rd November, 2014 | 19800000 | N/A | 5th November, 2014 | Yes | Messrs Sam & Sam International Ltd | 6th November, 2014 | 23441939.2 | Four (4) weeks | November, 2014 | 0 | December, 2014 | On-going | 90% | N/A | N/A
22 | Construction of Street Light at opoji, Edenu, Ugbegun, Esan Central L.G.A of Edo State | 28th July, 2014 (Federal Tenders Journal, The Guardian and Daily Trust Newspapers) | ETB | Open | 8th September, 2014 15th October, 2014 | 3rd October, 2014 3rd November, 2014 | 29600000 | N/A | 5th November, 2014 | Yes | Messrs Asa-lambda Tech. Ltd | 6th November, 2014 | 24648625 | Six (6) weeks | November, 2014 | 17254637.5 | January, 2015 | On-going | 70% | N/A | N/A
23 | Construction of Solar Street Light at Olayide Street, Off Isu Wada Road, Owo, Owo L.G.A. of Ondo State | 28th July, 2014 (Federal Tenders Journal, The Guardian and Daily Trust Newspapers) | ETB | Open | 8th September, 2014 15th October, 2014 | 3rd October, 2014 4th November, 2014 | 29700000 | N/A | 5th November, 2014 | Yes | Messrs Toluyan Integrated Services Ltd | 6th November, 2014 | 28080000 | Six (6) weeks | November, 2014 | 26760000 | January, 2015 | Completed | 100% | N/A | N/A
24 | Civil Work for Installation of Relief 1x 15MVA, 33/11KV and 11KV Panel in Idi Ogun Injection Substation at Offa | 28th July, 2014 (Federal Tenders Journal, The Guardian and Daily Trust Newspapers) | ETB | Open | 8th September, 2014 15th October, 2014 | 3rd October, 2014 18th November, 2014 |  | N/A | 24th November, 2014 | Yes | Messrs New Moon Nig. Ltd | 27th November, 2014 | 35666500 | Four (4) weeks | November, 2014 | 0 | December, 2014 | On-going | 70% | N/A | N/A
25 | Repairs of Old Machines and Equipment at Transformer Workshop | 30th June, 2014 (Federal Tenders Journal, The Guardian and Daily Trust Newspapers) | ETB | Open | 28th August, 2014 24th September, 2014 | 17th September, 2014 3rd October, 2014 | 23390302.4 | N/A | 24th November, 2014 | Yes | Messrs Andever Resources Ltd | 27th November, 2014 | 23990610 | Four (4) weeks | November, 2014 | 0 | December, 2014 | On-going | 5% | N/A | N/A
26 | Procurement and Installation of Five (5) Nos. 100KVA Diesel Generators | 30th June, 2014 (Federal Tenders Journal, The Guardian and Daily Trust Newspapers) | ETB | Open | 21st August, 2014 24th September, 2014 | 17th September, 2014 3rd October, 2014 |  | N/A | 24th November, 2014 | Yes | Messrs Angel-Kelv Nig. Ltd | 27th November, 2014 | 24358083.75 | Four (4) weeks | November, 2014 | 0 | December, 2014 | Completed | 100% | N/A | N/A
27 | Procurement of Two (2) Nos. Sentra Tekna 1.8L AT 2014 Model, One (1) No. Altima SV 2.5L 2014 Model, Three (3) Nos. NP 300 Hard Body Double Cabin 4WD 2.4L Petrol MT 2014 Model, One (1) No. Urvan 15-Seater Bus (Wide Body, High Roof 2.5 Petrol MT 2014 Model) | N/A | ETB | Open | 30th October, 2014 | 30th October, 2014 | 68300000 | N/A | 4th December, 2014 | Yes | Messrs Adekunle Abogun Motors Nig. Ltd | 5th December, 2014 | 49507500 | Two (2) weeks | December, 2014 | 0 | December, 2014 | Completed | 100% | N/A | N/A
28 | Procurement and Installation of New Machines & Test Equipment for Ijora Engineering Laboratory | 30th June, 2014 (Federal Tenders Journal, The Guardian and Daily Trust Newspapers) | ETB | Open | 26th August, 2014 24th September, 2014 | 17th September, 2014 3rd October, 2014 | 9500000 | N/A | 8th December, 2014 | Yes | Messrs TonyCane Nig. Ltd | 9th December, 2014 | 10736033.44 | Three (3) months | December, 2014 | 0 | February, 2015 | On-going | 0% | N/A | N/A
29 | Consultancy Services for the Evaluation of IT Services in EMSL | 29th September, 2014 (The Guardian and Daily Trust Newspapers) 6th October, 2014 (Federal Tenders Journal) | ETB | Open | 10th November, 2014 4th December, 2014 | 26th November, 2014 5th December, 2014 | 39600000 | N/A | 8th December, 2014 | Yes | Messrs Global Knowledge Consulting Ltd | 9th December, 2014 | 30460500 | Six (6) months | December, 2014 | 9138000 | June, 2015 | On-going | 35% | N/A | N/A
30 | Consultancy Services for Electricity Management Information System (EMIS) | 29th September, 2014 (The Guardian and Daily Trust Newspapers) 6th October, 2014 (Federal Tenders Journal) | ETB | Open | 10th November, 2014 4th December, 2014 | 26th November, 2014 5th December, 2014 | 29700000 | N/A | 8th December, 2014 | Yes | Messrs Trilet Technologies Ltd | 9th December, 2014 | 26130300 | Twelve (12) weeks | December, 2014 | 9145605 | February, 2015 | On-going | 40% | N/A | N/A
31 | Consultancy for Restructuring and Repositioning of EMSL Medical Clinics in Abuja, Lagos, Enugu and the Establishment of Trauma Centers | 29th September, 2014 (The Guardian and Daily Trust Newspapers) 6th October, 2014 (Federal Tenders Journal) | ETB | Open | 25th November, 2014 4th December, 2014 | 26th November, 2014 5th December, 2014 |  | N/A | 8th December, 2014 | Yes | Messrs Units Environmental Sciences | 9th December, 2014 | 25000000 | Six (6) months | December, 2014 | 8750000 | February, 2015 | On-going | 100% | N/A | N/A
32 | Partitioning and Perimeter Fencing | 29th September, 2014 (The Guardian and Daily Trust Newspapers) 6th October, 2014 (Federal Tenders Journal) | ETB | Open | 10th November, 2014 4th December, 2014 | 26th November, 2014 5th December, 2014 | 49500000 | N/A | 8th December, 2014 | Yes | Messrs Cardan Engineering Works Limited | 9th December, 2014 | 16933140 | Three (3) weeks | December, 2014 | 0 | January, 2015 | On-going | 40% | N/A | N/A
33 | Refurbishment/ Repairs of One (1) No. Crane (35 Tons) | 29th September, 2014 (The Guardian and Daily Trust Newspapers) 6th October, 2014 (Federal Tenders Journal) | ETB | Open | 10th November, 2014 4th December, 2014 | 26th November, 2014 5th December, 2014 | 16500000 | N/A | 8th December, 2014 | Yes | Messrs Charse International Ltd | 9th December, 2014 | 15045030 | Eight (8) weeks | December, 2014 | 0 | January, 2015 | Completed | 100% | N/A | N/A
34 | Purchase of Office Equipment | 29th September, 2014 (The Guardian and Daily Trust Newspapers) 6th October, 2014 (Federal Tenders Journal) | ETB | Open | 25th November, 2014 4th December, 2014 | 26th November, 2014 5th December, 2014 | 72192628.775 | N/A | 8th December, 2014 | Yes | Messrs Scanwater (Nig.) Ltd | 9th December, 2014 | 37500000 | Eight (8) weeks | December, 2014 | 37499040 | February, 2015 | Completed | 100% | N/A | N/A
35 | Rental of Accommodation for EMSL Abuja Zonal Area Office and Electricity Management Information Systems Centre |  | ETB |  |  |  |  | N/A | 29th December, 2014 | Yes | Messrs Cardiff Properties Ltd |  | 55000000 | Two (2) years |  | 0 |  | Completed | 100% | N/A | N/A
36 | Supply of 1 No. Toyota Land Cruiser V6 (2014 Model) |  | MTB | Open |  |  | 18900000 | N/A | 5th September, 2014 | Yes | Messrs Eric Many Limited | 5th September, 2014 | 18900000 | Two (2) weeks | September, 2014 | 18900000 | October, 2014 | Completed | 100% | N/A | N/A
37 | Supply of 3 Nos. Toyota Prado TXL (2014 Model) |  | MTB | Open |  |  | 40005000 | N/A | 5th September, 2014 | Yes | Messrs Dilly Motors Limited | 5th September, 2014 | 40005000 | Two (2) weeks | September, 2014 | 40005000 | October, 2014 | Completed | 100% | N/A | N/A
38 | Supply of 6 Nos. Toyota Camry 2.5L and 1 No. Toyota Avensis 2.0L |  | MTB | Open |  |  | 59684625 | N/A | 5th September, 2014 | Yes | Messrs Eric Many Limited | 5th September, 2014 | 59684625 | Two (2) weeks | September, 2014 | 59684625 | October, 2014 | Completed | 100% | N/A | N/A
1564417988.96

## FHA
BUREAU OF PUBLIC PROCUREMENT
MINISTRY: |  |  | FMHL&UD
PROCURING ENTITY(MDA): |  |  | FEDERAL HOUSING AUTHORITY, ABUJA
FINANCIAL YEAR: |  |  | 2014
| BASIC DATA | [6 empty] | CONTRACT AWARD | [8 empty] | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | CONTRACT TYPE | ADVERTISEMENT DATES AND MEDIA | APPROVAL AUTHORITY | PROCUREMENT METHOD | BID OPENING DATE | DATE OF COMPLETION OF FINANCIAL/TECHICAL BIDS EVAL REPORT | RECOMMENDED CONTRACTOR | DATE OF CERT OF NO OBJECTION | APPROVAL DATE BY AO/PTB/MTB/FEC | DATE OF CONTRACT AWARD | AWARDED TO LOWEST TENDERER | CONTRACT PERIOD | CONTRACT EXTENSION PERIOD | CONTRACT VALUE (N) | BUDGETARY PROVISION | DATE OF CONTRACT COMMENCEMENT | DATE OF CONTRACT COMMENCEMENT (PHYSICAL MOB.) | DATE OF VARIATION APPROVAL | AMOUNT OF VARIATION | AMOUNT PAID AS AT DATE | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT DATE | REMARK
1 | DIRECT PROCUREMENT OF GOODS | SUPPLY OF GOODS | N/A | N/A | DIRECT PROCUREMENT | N/A | N/A | SEE ATTACHED ANNEXURE I | N/A | N/A | JAN-DEC,20114 | SEE ATTACHED ANNEXURE I | N/A | N/A | 23075450 | FHA 2014 BUDGET | JAN-DEC,2014 | JAN-DEC,2014 | N/A | N/A | 23075450 | 2014-12-31 | 100%

## FMC-NGURU
FEDERAL MEDICAL CENTRE, NGURU
PROCUREMENT PLAN FOR THE YEAR 2014
[9 empty] | FINANCIALS |  |  |  | PHYSICALS
S/No | Project/ Programme Title | Project/ Programme Description | Name of Contractor | Project/ Programme Location and Commencement Date | Project/ Programme Total Cost | Completion Date | Project/ Programme Financial Commitment Since Inception | Appropriation for 2014 | Key Performance Indicators/ Deliverable for 2014 | Amount Released for the Quarter | Amount Released in the year so far | Amount Utilized so far in this year | Planned Deliverable for the Quarter | Actual Performance in the year | Cummulative Performance since inception | Remarks (Constraint/ Challenges)
| 2 | 3 | 4 | 5 | 6 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Construction and Provision of Medical Health Centre | Completion and Furnishing of Physiotherapy Building Complex | Echa & Iga Engineering and Cons. Ltd | FMC Nguru 23/08/ 2012 | 149425969.25 | 149,425,969.25 31/12/2016 | 140693166.15 | 50000000 | 94% | 3331502.89 | 3331502.89 | 3331502.89 | Construction of Standard Physiotherapy Complex equiped with modern equipment was built | 2% | 94% | Project on-going
2 | Construction and Provision of Medical Health Centre | Completion & Furnishing of Ante Natal Extension | Salow Global Links Nig. Ltd | FMC Nguru 18/11/2014 | 39235739.55 | 39,235,739.55 31/12/2015 | 25000000 | 40000000 | 63% | 779000 | 25779000 | 25779000 | Construction of Standard Ante-Natal Complex has reached Completion Stage | 2% | 63% | Project on-going
3 | Construction and Provision of Medical Health Centre (Retention Payments for Completed Structures) | Completion of Works & Maintenance Dept. | Ndazz Resource Nig. Ltd | FMC Nguru 08/03/2012 | 29304714.75 | 29,304,714.75 31/12/2012 | 29304714.75 | 9883486 | 100% | 1465235.74 | 1465235.74 | 1465235.74 | Standard Works & Maintenance Dept. was built | 5% | 100% | Project Completed
4 |  | Completion of Admin Block (Additional Work) | Form Survival Nig. Ltd | FMC Nguru 19/12/20… | 12666482.54 | 12,666,482.54 31/12/2012 | 12666482.54 |  | 100% | 633324.13 | 633324.13 | 633324.13 | Standard Admin Block was Built | 5% | 100% | Project Completed
5 |  | Completion of Female Medical Ward | X-MATRIX 369 Nig. Ltd | FMC Nguru 31/09/2012 | 61654299.34 | 61, 654,299.34 31/12/2013 | 61654299.34 |  | 100% | 3082714.97 | 3082714.97 | 3082714.97 | Standard Male Medical Ward was Builth | 5% | 100% | Project Completed
6 |  | Completion of Gate and Generator at Board Guest House | Core Ventures Nig. Ltd | FMC Nguru 23/02/2012 | 10252069.21 | 10,252,069.21 31/12/2012 | 10252069.21 |  | 100% | 512603.46 | 512603.46 | 512603.46 | Standard Gate and Generator House was Constructed | 5% | 100% | Project Completed
7 |  | Completion of House Keepers' House | Echa & Iga Engineering and Cons. Ltd | FMC Nguru 23/02/2012 | 8906602.64 | 8,906,602.64 31/12/2012 | 8906602.64 |  | 100% | 445330.13 | 445330.13 | 445330.13 | Standard House Keppers House at Board Guest House was Constructed | 5% | 100% | Project Completed
8 |  | Payment of Consultancy Fees on Capital Projects | Jadu & Partners Nig. Ltd | FMC Nguru 23/02/2012 | 1991084.67 | 1,991,084.67 31/12/2012 | 1991084.67 |  | 100% | 1991084.67 | 1991084.67 | 1991084.67 | Consultancy Services was provided | 100% | 100% | Project Completed
9 |  | Construction of Walkway Extension | Salow Global Links Nig. Ltd | FMC Nguru 02/11/2012 | 21954030 | 21,954,030.00 31/12/2012 | 21954030 |  | 100% | 1209486 | 1209486 | 1209486 | Standard Walkway was Constructed to Link Completed Structures | 5% | 100% | Project Completed
10 | Construction and Provision of Medical Health Centre (Intervention Fund to Support Movement to Permanent Site including Basic Working Equipment ETC ) | Upgrading of Former Works Department | Usmasco Nig. Ltd | FMC Nguru 25/072013 | 4963855 | 4,963,855.00 31/12/ 2014 | 4963855 | 50000000 | 100% | 248192.25 | 4963855 | 4963855 | Standard Interns Quarters was upgraded | 5% | 100% | Project Completed
11 |  | Construction of Sockaway, Double Face Drawer, Drilling of Boreholes and Construction of Lube Bay | Salow Global Links Nig. Ltd | FMC Nguru 12/06/2013 | 2448089.75 | 2, 448, 089.75 31/122014 | 2448089.75 |  | 100% | - | 2448089.75 | 2448089.75 | Standard Sockaway, Double Face Drawer, Drilling of Boreholes and Lube Bay were constructed | - | 100% | Project Completed
12 |  | Construction/Partitioning of Revenue Unit with Alluminium Sheets | ABL Resource and Properties | FMC Nguru 17/07/2013 | 1581164.75 | 1,581,164.75 31/122014 | 1581164.75 |  | 100% | - | 1581164.75 | 1581164.75 | Standard Partioning Works was made in the Revenue Unit | - | 100% | Project Completed
13 |  | Upgrading of Skills Acquisation Centre | ABK & Sons Nig. Ltd | FMC Nguru 08/11/2012 | 3879484.5 | 3,879,484.50 31/12/2014 | 3879484.5 |  | 100% | - | 3879484.5 | 3879484.5 | Standard Skills Acquisation Centre was Upgraded | - | 100% | Project Completed
14 |  | Maintenance Works in the Hospital | Kugibar Eng. Ltd | FMC Nguru 05/06/2014 | 7666029 | 7,666,029.00 31/12/2014 | 7666029 |  | 100% | - | 7666029 | 7666029 | Standard Maintenance Works were carried out | - | 100% | Project Completed
15 |  | Construction of Car Park | Damaran Design & Construction Ltd | FMC Nguru 05/06/2014 | 2594900 | 2,594,900.00 31/12/2014 | 2594900 |  | 100% | 2594900 | 2594900 | 2594900 | Standard Car Park was Constructed | 100% | 100% | Project Completed
16 |  | Renovation Works at A&E Complex | ASU Global Ventures Nig. Ltd | FMC Nguru 05/06/2014 | 5513718 | 5,513,718.00 31/12/2012 | 5513718 |  | 100% | 5513718 | 5513718 | 5513718 | Standard Renovation Works were Made | 100% | 100% | Project Completed
17 |  | Provision of Solar Light and Supplies of Inverter | Gidan Dawa Investment | FMC Nguru 05/06/2014 | 4312413 | 4,312,413 31/12/2014 | 3207750 |  | 100% | - | 3207750 | 3207750 | Qualitative Solar Light and Inverters were provided | - | 74% | Project Completed but have unpaid balance
18 |  | Supply and Installation of Solar System and Accessories | Kugibar Eng. Ltd | FMC Nguru 05/06/2014 | 6003766.26 | 6,003,766.26 31/12/2014 | 6003766.26 |  | 100% | 6003766.26 | 6003766.26 | 6003766.26 | Installation of Qualitative Solar Lights was made | 100% | 100% | Project Completed
19 |  | Supply of Furniture to Interns Quarters | Rahama Computers | FMC Nguru 21/12/2012 | 7679200 | 7,679,200 31/12/2012 | 7679200 |  | 100% | - | 7679200 | 7679200 | Quantative Furniture were supplied | - | 100% | Project Completed
20 |  | Construction of Main Gate | Kison Kanta Nig. Ltd | FMC Nguru 21/12/2012 | 6027608.42 | 6,027,608.42 31/12/2015 | 2000000 |  | 90% | 2000000 | 2000000 | 2000000 | A Standard Gate was Constructed | 33% | 33% | Project on-going
21 |  | Replacement of Doors and Keys in the Hospital | Kugibar Eng. Ltd | FMC Nguru 09/012014 | 3465990 | 3,465,990 31/12/2014 | 1339379.74 |  | 39% | 1339379.74 | 1339379.74 | 1339379.74 | Standard doors and keys were replaced | 39% | 39% | Project Completed but have unpaid balance
22 | Purchase of Vans | Purchase of Emergency Ambulance Ford F-350 Mobile Clinic and Medical Equipment | Sahar Continental Nig. Ltd | FMC Nguru 02/11/2012 | 49675899.45 | 49,675,899.45 31/12/2016 | 7451384.92 | 22224515 | 15% | - | - | - | A Mobile Ambulance (F-350) Ford equiped with Medical Equipment would be purchase |  | 15% | Project on-going
23 | Purchase of Office Furniture & Fittings (equiping and furnishing of Completed Structures) | Supply and Furnishing of Board Guest House | AL Amir Resource | FMC Nguru 10/03/ 2014 | 4123004 | 4,123,004.00 31/12/2014 | 4123004 | 10000000 | 100% | - | 4123004 | 4123004 | Standard Furniture was supplied | 100% | 100% | Project Completed
24 |  | Supply and Installation of Window Blinds | Lapaz Investment Company | FMC Nguru 18/02/2013 | 2771350 | 2,771,350.00 31/12/2012 | 2771350 |  | 100% | 2771350 | 2771350 | 2771350 | Window Blid was purchased and Installed | 100% | 100% | Project Completed
25 |  | Drilling and Installation of Borehole | Kunnari Intergrated Services | FMC Nguru 10/03/ 2014 | 994731.41 | 994,731.41 31/12/2014 | 994731.41 |  | 100% | 994731.41 | 994731.41 | 994731.41 | A Standard Borehole was Drilled | 100% | 100% | Project Completed
26 |  | Supply of Trees and Maintenance of Generator | New Gimbiya Global Services | FMC Nguru 21/01/2014 | 3686244 | 3,686,244.00 31/12/2014 | 500000 |  | 100% | - | 500000 | 500000 | Good number of Trees were Purchased | - | 14% | Project Completed
27 |  | Supply of Food Flasks & Warmers to Board Guest House | Hadson Resources Enterprises | FMC Nguru 07/06/2014 | 774000 | 774,000.00 31/12/2014 | 774000 |  | 100% | 774000 | 774000 | 774000 | Quantative Warmers & Food Flasks were purchased | 100% | 100% | Project Completed
28 |  | Maintenance Works in the Hospital | ABL Resource and Properties | FMC Nguru 17/03/2014 | 3735270 | 3,735,270.00 31/12/2014 | 836915.9 |  | 100% | 836915.9 | 836915.9 | 836915.9 | Quality Maintenance Works Provided | 22% | 22% | Project Completed but have unpaid balance
29 | Purchase of Medical Health Equipment | Procurement, Installation and Commissioning of Cardiac Centre Equipment | Sahar Continental Nig. Ltd | FMC Nguru 28/08/2012 | 49853857.47 | 49,853,857.47 31/12/2016 | 10640154.4 | 10500000 | 100% | - | - | - | A Standard Cardiology Equipment was Purchased | - | - | Project Completed but have unpaid balance
30 | Purchase of Medical Health Equipment | Supply of Histopathology Equipment | Desert Medical Company | FMC Nguru 18/11/2014 | 9413775 | 9,413,775.00 31/12/2016 | - | 20000000 | - | - | - | - | Standard Histopathology Equipment would be supplied | - | - | Lack of Fund but Due Process Completed
31 | Purchase of Medical Health Equipment | Supply of Ophthalmology | ASU Global Ventures Nig. Ltd | FMC Nguru 18/11/2014 | 9789225 | 9,789,225.00 31/12/2016 | - |  | - | - | - | - | Standard Histopathology Equipment would be procured | - | - | Lack of Fund but Due Process Completed
32 | Purchase of Medical Health Equipment | Supply and Commissioning of Laundry Equipment | Allison Yalwata Nig. Enterprises | FMC Nguru 22/01/2011 | 59953950 | 59,953,950.00 31/12/2012 | 40000000 | 28000000 | 100% | 8000000 | 8000000 | 8000000 | Standard Laundry Equipment were supplied and Installed | 13% | 67% | Project Completed but have unpaid balance
33 | Purchase of fire fighting Equipment | Procurement of Fire Fighting Vehicles & Equipment | Abba Babale and Sons Nig.Ltd. | FMC Nguru 02/11/2011 | 49696322.91 | 49,696,322.91 31/12/2012 | 49696322.91 | 18868786 | 100% | 16540022.92 | 16540022.92 | 16540022.92 | Standard Fire service Vehicles & Equipment were Supplied | 33.2% | 100% | Completed and Fully paid
34 | Construction and Provision of Roads. | Construction of Walkway, to link existing Structures | ABK and Sons Ltd | FMC Nguru 18/11/2014 | 14960408.93 | 14,960,408.93 31/12/2014 | 7000000 | 15000000 | 100% | - | 7000000 | 7000000 | A Standard Walkway was Constructed to link structures | 47% | 47% | Project Completed but have unpaid balance
35 | Training Research and Development | Training and Development | Training and Development to staff | FMC Nguru 2014 | 10000000 | 10000000 | 6503211.81 | 10000000 | 100% | 828880 | 6503211.81 | 6503211.81 | Qualitative Training to staff was provided | 13% | 64% | 64% of the fund was utilized
36 | Tree Planting and Landscaping | Purchases of Trees and Landscaping | New Gimbiya Global Services | FMC Nguru 14/04/2014 | 4980000 | 4,980,000.00 31/12/2014 | 4980000 | 5000000 | 100% | 4980000 | 4980000 | 4980000 | Trees were supplied and Quality maintenance Services was provided | 100% | 100% | Projected completed and fully paid
37 | Construction/Procurement of Health Centre Equipment | Procurement of ENT Surgical Equipment | Ado Jones Ltd | FMC Nguru 2014 | 29097281.55 | 29097281.55 | - | 30000000 | - | - | - | - | Standard Surgical Equipment would be procured | - | - | Lack of Fund but Due Process Completed
38 | Computer and Software Acquisation | Computerisation of Medical Record | Media Villi Nig Ltd. | FMC Nguru 18/11/2014 | 14462263 | 14,462,263.00 31/12/2014 | 7000000 | 15000000 | 100% | - | 7000000 | 7000000 | Standard Computers & Softwares were Purchased and Installed in the Medical Record Unit | - | 48% | Project Completed but have unpaid balance
|  |  |  | ongoing is 18 | 474732084.65
|  |  |  | new in 2014 | #REF!

## FERMA
PROCUREMENT RECORDS
F ERMA |  | FEDERAL ROAD MAINTENANCE AGENCY
WORKS
2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2014 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | MAINTENANCE OF ROADS IN ENUGU NORTH/SOUTH FEDERAL CONSISITENCY | N/A | MTB | DIRECT PROCUREMENT | N/A | N/A | RECURRENT | 5TH DEC.2013 | MTB | N/A | AKUMAST NIG.LTD | 12TH DEC.2013 | 200000000 | 12 MONTHS |  | 94000000 | 11TH DEC.2014 | COMPLETED | 100 | N/A | N/A | WORK COMPLETED
2 | OLUKU-SOBE-IFON ROAD, ROUTE NO.35 (A122) IN EDO STATE | N/A | MTB | DIRECT PROCUREMENT | N/A | N/A | RECURRENT | 5TH DEC.2013 | MTB | N/A | AKUMAST NIG.LTD | 12TH DEC.2013 | 250000000 | 12 MONTHS |  | 226000000 | 11TH DEC.2014 | COMPLETED | 100 | N/A | N/A | WORK COMPLETED
3 | ASABA-IIA-ILUSHI ROAD IN DELTA STATE. ROUTE 35 | N/A | MTB | DIRECT PROCUREMENT | N/A | N/A | RECURRENT | 5TH DEC.2013 | MTB | N/A | WILLANGY NIG. LTD. | 12TH DEC.2013 | 150000000 | 12 MONTHS |  | 22000000 | 11TH DEC.2014 | ON-GOING | 50 | N/A | N/A | WORK IN PROGRESS
4 | IBADAN-GBONGAN-IFE DUAL CARRIAGE ROUTE NO35 IN OYO/OSUN STATE | N/A | MTB | DIRECT PROCUREMENT | N/A | N/A | RECURRENT | 5TH DEC.2013 | MTB | N/A | FRACTAL CONSTRUCTION NIG.LTD | 12TH DEC.2013 | 200000000 | 12 MONTHS |  | 0 | 11TH DEC.2014 | ON-GOING | 35 | N/A | N/A | WORK IN PROGRESS

## Invet Sec Tribunal
PROCUREMENT RECORDS
2014
INVESTMENTS AND SECURITIES TRIBUNAL
S/N | CONTRACT DESCRIPTION | ADVERTISEMENT DATE & MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | CONTRACTOR | DATE OF CONTRACT AWARD | DATE OF CONTRACT COMMENCEMENT | CONTRACT PERIOD | CONTRACT VALUE (N) | BUDGETARY PROVISION (N) | AMOUNT PAID AS AT 31.12.14 | EXPECTED COMPLETION DATE | % OF COMPLETION AS AT 31.12.14 | REMARKS
1 | SUPPLY OF CHAIRS AND WORKSTATIONS | 24TH NOVEMBER – DECEMBER 12TH 2014 | HCM | NS | 12.12.14 | R & J INTERIORS LTD | 19.12.14 | 19.12.14 | 1 WEEK | 3775000 | 6000000 | 3775000 | 26.12.14 | 100
2 | SUPPLY OF LAPTOPS AND OTHER OFFICE FITTING | 24 NOV. – 12 DECEMBER 2014 | HCM | NS | 12. 12 14 | ANSEL COMPUTERS LTD | 19.12.14 | 19.12.14 | 1 WEEK | 2325.75 | 6000000 | 2325.75 | 26.12.14 | 100
3 | SUPPLY OF ONE (1) LIBERTY TRANSCRIBING MACHINE | Sept.8th | TB | NCB | 22.10.14 | COLLIN IJEOMA & ASSOCIATES | 15.10.2014 | 15.10.2014 | 1 WEEK | 5123250 | 8000000 | 5123250 | 23. 11.2014 | 100
- October 22, 2014
THE BLUEPRINT & NEW TELEGRAPH
4 | SUPPLY OF FIVE (5) NEW MODEL FORD EDGE | Sept.8th | TB | NCB | 22.10.14 | COSCHARIS MOTORS LTD | 10.11.14 | 17.11.14 | 1 WEEK | 38500000 | 100000000 | 38500000 | 17.11.2014 | 100
- October 22, 2014
THE BLUEPRINT & NEW TELEGRAPH
5 | SUPPLY OF FOUR (4) PROJECT VEHICLES | Sept.8th | TB | NCB | 22.10.14 | COSCHARIS MOTORS LTD | 10.11.14 | 17.11.14 | 1 WEEK | 32230000 | 100000000 | 32, 230,000 | 17.11.2014 | 100
- October 22, 2014
THE BLUEPRINT & NEW TELEGRAPH
6 | SUPPLY OF 200 USERS BIT DEFENDER ANTI – VIRUS SOFTWARE WITH 3 YEARS LICENSE | 15TH – 29TH | HCM | NS | 29..9. | SQT WEB SOLUTION LTD | 23.10. 2014 | 23.10. 2014 | 1week | 1399650 | 8000000 | 1399650 | OCT. 2017 | 100
|  | SEPT. |  |  | 2014
2014
7 | SUPPLY OF PRINTERS AND HEAVY DUTY SCANNERS | 4TH – 21ST NOV. 2014 | HCM | NS | 21.11.2014 | TRIDITE ENTERPRISES LTD | 08.12.14 | 08.12.2014 | 1 WEEK | 1670000 | 1800000 | 1670000 | 15.12. | 100
2014
8 | SUPPLY OF 45 KVA MARAKPO PERKING ENGINE GENERATOR | Sept.8th | TB | NCB | 22.10.14 | NEWLAND TECHNOLOGIES LTD | 12.12.14 | 12.12.2014 | 1 WEEK | 4306500 | 6000000 | 4306500 | 19.12. | 100
|  | - October 22, 2014 | [10 empty] | 2014
9 | SUPPLY OF OFFICE FITTING | 24 Nov- | HCM | NS | 12.12 | ANSEL COMPUTERS LTD | 19.12.14 | 19.12.2014 | 1 WEEK | 2325750 | 8500000 | 2325750 | 29.12. | 100
|  | 2015-12-12 |  |  | 2014 | [7 empty] | 2014
2014
10 | SUPPLY OF SHREDDERS | 4TH -12ST NOV.2014 | HCM | NS | 12 | HOUSNEY NIG. LTD | 8.12.2014 | 8.12 | 1 WEEK | 300000 | 300000 | 300000 | 15.12. | 100
[5 empty] | .11. |  |  | 2014 |  |  |  |  | 2014
2014
11 | SUPPLY OF NWLR 2014 SETS | 4TH – 21ST NOV. 2014 | HCM | NS | 21STNOV 2014 | AKPETERS NIG. LTD | 8.12.2014 | 8.12. | 1 WEEK | 2221155 | 3146573 | 2221155 | 15.12. | 100
[8 empty] | 2014 |  |  |  |  | 2014
12 | SUPPLY OF AIR – CONDITIONERS & OTHERS | 4TH – 21ST NOV. 2014 | HCM | NS | 21STNOV 2014 | HOUSNEY NIG. LTD | 8.12.2014 | 8.12. | 1 WEEK | 2410000 | 8500000 | 2410000 | 15.12. | 100
[8 empty] | 2014 |  |  |  |  | 2014
13 | SUPPLY OF LEGALPEDIA | 4.11.14 - 19.12.14 | HCM | NS | 19.12.14 | HONEY | 19.12.14 | 19.12.2014 | 1 WEEK | 1323000 | 8000000 | 1323000 | 29.12. | 100
[6 empty] | CONSULT FOUNTAIN LTD | [6 empty] | 2014
14 | SUPPLY OF THE LAWS OF THE FEDERATION OF NIGERIA | 4TH – 21ST NOV. 2014 | HCM | NS | 21STNOV | AKPETERS NIG. LTD | 8.12.2014 | 8.12. | 1 WEEK | 836000 | 3146573 | 836000 | 15.12. | 100
[5 empty] | 2014 |  |  | 2014 |  |  |  |  | 2014
96422630.75

## LBRBDA
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) : |  | LOWER BENUE RIVER BASIN DEVELOPMENT AUTHORITY
MINISTRY : |  | FEDERAL MINISTRY OF WATER RESOURCES
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014(NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2014 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | Lot2 /ws/14- Renovation of the Managing Director's official Residence at Headquarters, Makurdi | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 31500000 | N/A | 29/10/14 | Beltu Investment Nig. Ltd. | Beltu Investment Nig. Ltd. | 31/10/14 | 32354715.45 | 12months | 2014-12-05 |  | OCTOBER, 2015 | 100% | 40% | NIL | NIL | COMPLETED
2 | Lot3 /sw/14- Construction of motorize borehole at Mbayuan Chia Community Hall, Ugbeme Mbaakura, Mbagen, Buruku, Benue state | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 10000000 | N/A | 29/10/14 | Godonna Petroleum & Energy Service Ltd No. 1688, Jarka Road, Effurun Warri | Godonna Petroleum & Energy Service Ltd No. 1688, Jarka Road, Effurun Warri | 31/10/14 | 10714285.71 | 6 months | November, 2014 |  | May, 2015 | 30% |  | NIL | NIL | On-Going
3 | Lot4/ws/14- construction of solar power borehole at Late Isa Apa Ohianis Compound, near LEA Primary school, Agaasa, Okene LGA, Kogi State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 10000000 | N/A | 29/10/14 | Bevira Nig. Ltd No 28 Shendam Street Jos | Bevira Nig. Ltd No 28 Shendam Street Jos | 31/10/14 | 10815840 | 6 months | November, 2014 |  | May, 2015 | 80% |  | NIL | NIL | On-Going
4 | Lot5/ws/14- Construction of motorized borehole in Kyeng, Bashi, District, Riyom LGA, Plateau State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 10000000 | N/A | 29/10/14 | Cojoma resources Ltd No. 40, Zion street, North Bank Makurdi | Cojoma resources Ltd No. 40, Zion street, North Bank Makurdi | 31/10/14 | 10735586.2 | 6 months | November, 2014 |  | May, 2015 | 30% |  | NIL | NIL | On-Going
5 | Lot7/ws/14 - Construction of Motorized Borehole at kenti Duwa Mbagen, Buruku LGA, Benue State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 20000000 | N/A | 29/10/14 | Danihopewell Services Ltd No. 4 Edwrd Ujege Street high Level, Makurdi | Danihopewell Services Ltd No. 4 Edwrd Ujege Street high Level, Makurdi | 31/10/14 | 20286634.28 | 6 months | November, 2014 |  | May, 2015 |  |  | NIL | NIL
6 | Lot8/ws/14- Construction of Motorized Borehole at Turan Kwande LGA and Atirkyase LGA, Benue State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 10000000 | N/A | 29/10/14 | Midobet Venture Ltd No. 18, Iorkyaaa Ako Street High Level Makurdi | Midobet Venture Ltd No. 18, Iorkyaaa Ako Street High Level Makurdi | 31/10/14 | 10590400 | 6 months | November, 2014 |  | May,2015 | 50% |  | NIL | NIL | On-Going
7 | Lot10/ws/14- provision of 35 Nos Hand Pump Borehole at Mangu/Bokkos Federal Connstituency, Plateau State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 20000000 | N/A | 29/10/14 | Tsensuu Nig. Ltd Rayfiel Zarmangadda, Jos | Tsensuu Nig. Ltd Rayfiel Zarmangadda, Jos | 31/10/14 | 22000000 | 6 months | November, 2014 |  | May, 2015 | 100% |  | NIL | NIL
8 | Lot 11/ws/14- construction of solar powered borehole at Azhosh-Ezere Fobur District, Jos East LGA, Plateau State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 16800000 | N/A | 29/10/14 | I&B Properties & Investment Ltd. No. 10 Kastina Crescent Maitama Abuja | I&B Properties & Investment Ltd. No. 10 Kastina Crescent Maitama Abuja | 31/10/14 | 16332550.5 | 6 months | November, 2014 |  | May, 2015 | 5% |  | NIL | NIL | On-Going
9 | Lot12/ws/14- Construction of motorized Borehole at Duwa Mbagen Buruku LGA, Benue State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 10000000 | N/A | 29/10/14 | Sottam Synergy resources Ltd, Suite B3 Halima Plaza behind Sahad Stores, Abuja | Sottam Synergy resources Ltd, Suite B3 Halima Plaza behind Sahad Stores, Abuja | 31/10/14 | 11000000 | 6 months | November, 2014 |  | May, 2015 | 80% |  | NIL | NIL | On-Going
10 | Lot13/ws/14-Construction of motorized borehole at Gindiri 1 town, Mangu LGA, Plateau state | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 10000000 | N/A | 29/10/14 | Ujatgold Ltd, 14 Otukpa Close High level Makurdi | Ujatgold Ltd, 14 Otukpa Close High level Makurdi | 31/10/14 | 10600400 | 6 months | November, 2014 | 5000000 | May,2015 | 100% |  | NIL | NIL | COMPLETED
11 | Lot14/ws/14-Construction of motoried Borehole at Gindiri Town II, Mangu LGA, Plateau State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 10000000 | N/A | 29/10/14 | Latin Global Services Ltd, Chinaka House Igoli Ogoja | Latin Global Services Ltd, Chinaka House Igoli Ogoja | 31/10/14 | 10782870 | 6 months | November, 2014 |  | May,2015 | 80% |  | NIL | NIL | On-Going
12 | Lot15/ws/14- construction of 7 Nos hand Pump boreholes at Mangu, Mangu LGA, Plateau State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 20000000 | N/A | 29/10/14 | Atsuku Nig. Ltd, No. 7 Iorkyaa Ako Street, High Level Makurdi | Atsuku Nig. Ltd, No. 7 Iorkyaa Ako Street, High Level Makurdi | 31/10/14 | 10700350 | 6 months | November, 2014 |  | May, 2015 | 100% |  | NIL | NIL | COMPLETED
13 | Lot16/w/14- construction of small earth Dam at Foron, Barkin Ladi Lga, Plateau State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 70000000 | N/A | 29/10/14 | ANBEZ Services Ltd, 86, Emeka Anyaoku Street Area II, Graki Abuja | ANBEZ Services Ltd, 86, Emeka Anyaoku Street Area II, Graki Abuja | 31/10/14 | 220100350 | 6 months | 31/10/14 |  | May, 2015 | 75% | 40% | NIL | NIL | On-Going
14 | Lot18/ws/14- Construction of small and irrigation Scheme for Logo | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 31500000 | N/A | 29/10/14 | Odinacho nig. Ltd, suite D10, jabi Plaza, Obafemi Awolowo Way, Jabi Abuja | Odinacho nig. Ltd, suite D10, jabi Plaza, Obafemi Awolowo Way, Jabi Abuja | 31/10/14 | 207200556.55 | 6 months |  |  | May, 2015 |  |  | NIL | NIL
16 | Lot20/ws/14- Construction of 4 Nos. Motorized Boreholes with exensive reticulation in the following Lgas of Plateau Central Senatorial Disrict: Bokkos, Mangu, Pankshin and kanke | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 226000000 | N/A | 29/10/14 | GEO-B Integrated business Ltd | GEO-B Integrated business Ltd | 31/10/14 | 206795720 | 6 months | November, 2014 | 205673877.93 | May, 2015 | 100% |  | NIL | NIL | COMPLETED
17 | Lot 21/ws/14 - Construction of 1No Motorized Borehole with extensive reticulation in the following Lga of Plateau Centralsenatorial District; Kanam | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 |  | N/A | 29/10/14 | Kanke Enterprises Nig. Ltd, No. 29, Rwang Pam Street, Jos | Kanke Enterprises Nig. Ltd, No. 29, Rwang Pam Street, Jos | 31/10/14 | 53848455 | 6 months |  |  | May, 2015 |  |  | NIL | NIL
18 | Lot 22/ws/14 - Construction of 6Nos Hand Pump Boreholes in Wamba LGA, Nasarawa North Senatorial District | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 10000000 | N/A | 29/10/14 | Pajamam Nig. Ltd, No. 89 LMCC Road, Calabar | Pajamam Nig. Ltd, No. 89 LMCC Road, Calabar | 31/10/14 | 9357970 | 6 months | November, 2014 |  | May, 2015 | 100% |  | NIL | NIL
19 | Lot 23/ws/14 - Construction of 6Nos Hand Pump Boreholes in Nasarawa Eggon LGA, Nasarawa North Senatorial District | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 10000000 | N/A | 29/10/14 | Andex press & Allied Services Ltd, No. 4A, Tafawa Balewa Street, Jos | Andex press & Allied Services Ltd, No. 4A, Tafawa Balewa Street, Jos | 31/10/14 | 9400513 | 6 months | November, 2014 | 5500000 | May, 2015 | 100% |  | NIL | NIL | COMPLETED
20 | Lot 24/ws/14 - Construction of 6Nos Hand Pump Boreholes in Akwanga LGA, Nasarawa North Senatorial District | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 10000000 | N/A | 29/10/14 | Andex press & Allied Services Ltd, No. 4A, Tafawa Balewa Street, Jos | Andex press & Allied Services Ltd, No. 4A, Tafawa Balewa Street, Jos | 31/10/14 | 9357970 | 6 months | November, 2014 | 5500000 | May, 2015 | 100% |  | NIL | NIL | COMPLETED
21 | Lot26/ws/14 - Driling of 1No motorized Borehole in Yuli-Wase, Wase LGA, Plateau State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 10000000 | N/A | 29/10/14 | Argandu Nig. Ltd. Suite D8, othni plaza, Opp NDE HQ Wuse Zone I Abuja | Argandu Nig. Ltd. Suite D8, othni plaza, Opp NDE HQ Wuse Zone I Abuja | 31/10/14 | 10903075 | 6 months | November, 2014 |  | May, 2015 | 100% |  | NIL | NIL | COMPLETED
22 | Lot 27/ws/14 - Drilling of 1No Motorized Borehole in Sabon Gari Wase, Wase LGA, Plateau State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 10000000 | N/A | 29/10/14 | Walbansa Nig. Ltd. D8, Othni Plaza, Wuse Zone I, Abuja | Walbansa Nig. Ltd. D8, Othni Plaza, Wuse Zone I, Abuja | 31/10/14 | 10903075 | 6 months | November, 2014 | 10380952.39 | May, 2015 | 100% |  | NIL | NIL | COMPLETED
23 | Lot 28/ws/14 - Drilling of 1No. Motorized Borejole in Bangalala, Wase LGA, Plateau State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 10000000 | N/A | 29/10/14 | Bashar Building & Construction Company Ltd, Suite D8, 3rd floor, othni Plaza, wuse Zone I, Abuja | Bashar Building & Construction Company Ltd, Suite D8, 3rd floor, othni Plaza, wuse Zone I, Abuja | 31/10/14 | 10903075 | 6 months | November, 2014 |  | May, 2015 | 100% |  | NIL | NIL
24 | Lot 29/ws/14 - Drilling of 1No. Motorized borehole in Lamba Gyambar LGA, Plateau State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 10000000 | N/A | 29/10/14 | Noider Investment Ltd, No. 20A Bank Road Kaduna | Noider Investment Ltd, No. 20A Bank Road Kaduna | 31/10/14 | 11016400.5 | 6 months | November, 2014 |  | May, 2015 | 5% |  | NIL | NIL | On-Going
25 | Lot 30/ws/14 - Drilling of 1No Motorized Borehole in Dangyam, Wase LGA , plateau State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 10000000 | N/A | 29/10/14 | The Leela Constr & Borehole Drilling Co. Ltd. No. 16, Independent Street. Ikeja, Lagos | The Leela Constr & Borehole Drilling Co. Ltd. No. 16, Independent Street. Ikeja, Lagos | 31/10/14 | 10622330 | 6 months | November, 2014 |  | May, 2015 | 100% |  | NIL | NIL | COMPLETED
26 | Lot31/ws/14 - Drilling of 1 No. Motorized Borehole in gimbi, Wase LGA, Plateau State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 10000000 | N/A | 29/10/14 | Onwudinjor brothers Ltd, No. 7, Road 1k, Sector F, FHA. Kugbe Abuja | Onwudinjor brothers Ltd, No. 7, Road 1k, Sector F, FHA. Kugbe Abuja | 31/10/14 | 10800150 | 6 months | November, 2014 |  | May, 2015 | 5% |  | NIL | NIL | On-Going
27 | Lot 32/ws/14 - Drilling of 1No. Motorized borehole in Pinali, Wase Lga, Plateau State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 10000000 | N/A | 29/10/14 | Id-Amid Group of Companies, No. 20A, Bank Road Kaduna | Id-Amid Group of Companies, No. 20A, Bank Road Kaduna | 31/10/14 | 10520052.6 | 6 months | November, 2014 |  | May, 2015 | 5% |  | NIL | NIL | On-Going
28 | Lot33/ws/14 - Drilling of 1No Solar powered water Scheme at Mikang LGA, Plateau state | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 11000000 | N/A | 29/10/14 | Abhumu Ltd, Suite B41, Area 11Mall, Ahmadu Bello Way Garki Abuja | Abhumu Ltd, Suite B41, Area 11Mall, Ahmadu Bello Way Garki Abuja | 31/10/14 | 10711690.5 | 6 months |  |  | May, 2015 |  |  | NIL | NIL
29 | Lot34/ws/14 - construction of 7 nos Hand Pump Boreholes with aring platform at Pankshin/Kanke LGAs Plateau State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 14700000 | N/A | 29/10/14 | A&J Investment & Management Company Ltd. | A&J Investment & Management Company Ltd. | 31/10/14 | 10915277.5 | 6 months | November, 2014 |  | May, 2015 | 10% |  | NIL | NIL | On-Going
30 | Lot35/ws/14 - Laying of Asphalt on 1Km Road in Nasarawa Town, Nasarawa State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 15000000 | N/A | 29/10/14 | Privent Construction Ltd, GP 651, Ankpa Qtrs, Makurdi, Benue State | Privent Construction Ltd, GP 651, Ankpa Qtrs, Makurdi, Benue State | 31/10/14 | 37507050 | 2 months |  |  | May, 2015 |  |  | NIL | NIL
31 | Lot 37/ws/14 - Water project at Mbahumun (Solar Powered Borehole) in Kwande LGA, Benue State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 25000000 | N/A | 29/10/14 | Amid merchants Company Ltd, No. 20A, Bank Road, Kaduna | Amid merchants Company Ltd, No. 20A, Bank Road, Kaduna | 31/10/14 | 26816934.74 | 6 months | November, 2014 |  | May, 2015 | 5% |  | NIL | NIL | On-Going
32 | Lot38/ws/14 - Underground Water Development (Driling of 2Nos motorized Boreholes) in Ogbadigbo | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 60000000 | N/A | 29/10/14 | Nasibelco resources Nig. Ltd. No 11, Behind No.5 Gyado hospital Road GRA, Gboko | Nasibelco resources Nig. Ltd. No 11, Behind No.5 Gyado hospital Road GRA, Gboko | 31/10/14 | 22900000 | 6 months | November, 2014 |  | May, 2015 | 80% |  | NIL | NIL | On-Going
33 | lot 39/ws/14 - underground water development (Drilling of 1No Motorized borehole) in Fwavwei, jos South LGA, Plateau State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 |  | N/A | 29/10/14 | Lobot dong Nig. Ltd, Dagee House, Bahwol Kanang, Jos, Plateau State | Lobot dong Nig. Ltd, Dagee House, Bahwol Kanang, Jos, Plateau State | 31/10/14 | 10535096.25 | 6 months | November, 2014 | 7000000 | May, 2015 | 100% |  | NIL | NIL | COMPLETED
34 | Lot40/ws/14 - Underground water development ( drilling of 1No. Motorized borehole) in Uikpam, Guma LGA, Benue State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 |  | N/A | 29/10/14 | Chenkibou Nig Ltd, 19 Balewa Crescent High/level. Makurdi, Benue State | Chenkibou Nig Ltd, 19 Balewa Crescent High/level. Makurdi, Benue State | 31/10/14 | 10925250 | 6 months | November, 2014 |  | May, 2015 | 100% |  | NIL | NIL | COMPLETED
35 | ot 41/ws/14 - underground water development (drilling of 1 no. motorized borehole) in Lafia, Lafia LGA, Nasarwa State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 |  | N/A | 29/10/14 | Jankasa Resources Nig. Ltd. | Jankasa Resources Nig. Ltd. | 31/10/14 | 10529125 | 6 months | November, 2014 | 7000000 | May, 2015 | 100% |  | NIL | NIL | COMPLETED
36 | 4 - underground water development (driling of 1no. Motorized borehole) in Ochadamu, Ofu LGA, Kogi State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 |  | N/A | 29/10/14 | E O Ogidi & Sons NIG. LTD block B, Flat 19, Powa Shopping Complex, Abuja | E O Ogidi & Sons NIG. LTD block B, Flat 19, Powa Shopping Complex, Abuja | 31/10/14 | 13728100 | 3 months | November, 2014 | 13041695 |  | 100% |  | NIL | NIL | COMPLETED
37 | Lot 43/ws/14 - construction of flood channelization & gully reclaimation works in Dyegh, Buruku LGA, Benue state | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 40000000 | N/A | 29/10/14 | Nbeichon Engineering Services Ltd, 3 ihiala Street Area2, Garki Abuja | Nbeichon Engineering Services Ltd, 3 ihiala Street Area2, Garki Abuja | 31/10/14 | 180200562.69 | 6 months |  | 10000000 |  |  |  | NIL | NIL
38 | Lot44/ws/14 - Provision of 5 nos Solar powered boreholes in Makurdi LGA, Benue North-West Senatorial District | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 300000000 | N/A | 29/10/14 | Sdeel & Associates Ltd, Plot 1396, Lagos Crescent, Garki II Abuja | Sdeel & Associates Ltd, Plot 1396, Lagos Crescent, Garki II Abuja | 31/10/14 | 54745525 | 6 months | November, 2014 |  | May, 2015 | 40% |  | NIL | NIL | On-Going
39 | lot45/ws/14 - provision of 5nos Solar powered boreholes in Gboko LGA, Benue North-West Senatorial District | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 |  | N/A | 29/10/14 | Studio Appartments Ltd, Suite D6, Othni Plaza, Nouchott Street, Zone 1 Wuae, Abuja | Studio Appartments Ltd, Suite D6, Othni Plaza, Nouchott Street, Zone 1 Wuae, Abuja | 31/10/14 | 54093275 | 6 months | November, 2014 |  | May, 2015 | 40% |  | NIL | NIL | On-Going
40 | Lot46/ws/14-Provision of 5nos Solar powered boreholes in Guma LGA Benue North -West Senatorial District | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 |  | N/A | 29/10/14 | Aim Frontline Nig Ltd, No. 5, 5th Avenue Bida Street, Wadata, Makurdi | Aim Frontline Nig Ltd, No. 5, 5th Avenue Bida Street, Wadata, Makurdi | 31/10/14 | 54075751.63 | 6 months | November, 2014 |  | May, 2015 | 40% |  | NIL | NIL | On-Going
41 | Lot47/ws/14 - provision of 5nos solar powered boreholes in Buruku LGA, Benue North West Senatorial District | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 |  | N/A | 29/10/14 | Wanfa Trading Ltd | Wanfa Trading Ltd | 31/10/14 | 54093275 | 6 months | November, 2014 | 8113991 | May, 2015 | 40% |  | NIL | NIL | On-Going
42 | Lot 48/ws/14 - Provision of 5 Nos Solar Powered Boreholes in Gwer-West LGA, Benue North-West Senatorial District | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 |  | N/A | 29/10/14 | Ochijele Nig. Ltd, No 54, Benue Crescent, Makurdi | Ochijele Nig. Ltd, No 54, Benue Crescent, Makurdi | 31/10/14 | 54,166,741. 88 | 6 months | November, 2014 | 5416674.88 | May, 2015 | 40% |  | NIL | NIL | On-Going
43 | Lot 49/ws/14 - provision of 5 nos solar powered boreholes in Tarka LGA, Benue North-West Senatorial District | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 |  | N/A | 29/10/14 | Krais Civil Engineering Ltd, No. E 007, Kari road Housing Estate, Maiduguri Road, Bauchi | Krais Civil Engineering Ltd, No. E 007, Kari road Housing Estate, Maiduguri Road, Bauchi | 31/10/14 | 544271175 | 6 months | November, 2014 | 5000000 | May, 2015 | 20% |  | NIL | NIL | On-Going
44 | Lot56/ws/14- provision of water reticulation in GRA/Adesoye College Area, Offa, Offa Lga, kwara State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 30000000 | N/A | 29/10/14 | Energy Konnect Nig Ltd. No. 22, Kofoworola crescent, Ikeja, Lagos | Energy Konnect Nig Ltd. No. 22, Kofoworola crescent, Ikeja, Lagos | 31/10/14 | 29635173 | 6 months | November, 2014 | 4445275.95 | May, 2015 | 80% |  | NIL | NIL | On-Going
45 | Lot57/ws/14 - Construction of Flood Control Dyke, Phase III at DEP Irrigation project | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 30000000 | N/A | 29/10/14 | Beniga Synergy Resources Ltd, 24 konshisha Street, High Level Makurdi | Beniga Synergy Resources Ltd, 24 konshisha Street, High Level Makurdi | 31/10/14 | 33167377.43 | 6 months | [5 empty] | NIL | NIL
46 | Lot56/ws/14- provision of water reticulation in GRA/Adesoye College Area, Offa, Offa Lga, kwara State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 45250000 | N/A | 29/10/14 | Elah Services Ltd, Plot 1247, Aminu Kano Crescent, wuse II, Abuja | Elah Services Ltd, Plot 1247, Aminu Kano Crescent, wuse II, Abuja | 31/10/14 | 54424671 | 6 months | 2015-04-01 | 8163424 | June,2015 |  |  | NIL | NIL | On-Going
47 | Lot59/ws/14 - construction of small earth dam in Agbashi (Drilling og Motorized Borehole) Nasarawa State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 15140200 | N/A | 29/10/14 | Almaj Concept International Ltd, No. 53 Oba Overanwen street Gwarimpa Abuja | Almaj Concept International Ltd, No. 53 Oba Overanwen street Gwarimpa Abuja | 31/10/14 | 15074115 | 6 months | November, 2014 |  | May, 2015 | 20% |  | NIL | NIL | On-Going
48 | Lot 60/ws/14 - Construction of small Earth Dam in Azara (Drilling of Motorized Borehole) Nasarawa State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 14150000 | N/A | 29/10/14 | Chamberlin Dickama Nig. Ltd No. 9 Railway bye-pass, High-Level makurdi | Chamberlin Dickama Nig. Ltd No. 9 Railway bye-pass, High-Level Makurdi | 31/10/14 | 14129115 | 6 months | November, 2014 |  | May, 2015 | 5% |  | NIL | NIL | On-Going
49 | lot61/ws/14 - Construction of small Earth Dam in Assakio (Drilling of Motorized Borehole) Nasarawa State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 15179115 | N/A | 29/10/14 | Jankasa Resources Nig. Ltd. | Jankasa Resources Nig. Ltd. | 31/10/14 | 15179115 | 6 months | November, 2014 |  | May, 2015 | 60% |  | NIL | NIL | On-Going
50 | lot62/ws/14 - Construction of small Earth Dam in Keana (Drilling of Motorized Borehole) Nasarawa State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 13150000 | N/A | 29/10/14 | Chenkibou Nig Ltd, 19 Balewa Crescent High/level. Makurdi, Benue State | Chenkibou Nig Ltd, 19 Balewa Crescent High/level. Makurdi, Benue State | 31/10/14 | 13079115 | 6 months | November, 2014 |  | May, 2015 | 20% |  | NIL | NIL | On-Going
51 | Lot63/ws/14 Construction of Ganawuri Earth Dam Riyom LGA, Plateau State (Supply of outlet steel pipes). | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 25000000 | N/A | 29/10/14 | Aim Frontline Ltd. no. 5, 5th Avenue, Bida Street, Wadata, Makurdi | Aim Frontline Ltd. no. 5, 5th Avenue, Bida Street, Wadata, Makurdi | 31/10/14 | 23097375 | 3 months | [5 empty] | NIL | NIL
52 | Lot64/ws/14 - Expansion of irrigation delivery capacity for Naka project | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 20000000 | N/A | 29/10/14 | Am' Synergy Nig. Ltd. Plot 770, Behind Wuye Market, wuye District Abuja | Am' Synergy Nig. Ltd. Plot 770, Behind Wuye Market, wuye District Abuja | 31/10/14 | 20212500 | 6 months | 17/12/14 |  |  |  |  | NIL | NIL
53 | Lot68/ws/14 -Supply of Parts for D7G Buldozer No4 B & No5, Repare of Mercedes Benz,Haib Crane & Supply of Slasher/Repair of MF260 Tractor | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 18072331.2 | N/A | 29/10/14 | Zateco Ltd. | Zateco Ltd. | 31/10/14 | 18072331.2 | 3 months | March, 2015 | 2710849.68 |  |  |  | NIL | NIL
54 | Lot 69/ws/ 14 - Rescreeding/ Refelting of gutters and renovation of toilets at Headquarters Office Complex, Makurdi | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 24017268 | N/A | 29/10/14 | DAC Technology, Plot 8723 Baaver Dzeremo Street, Judges Quarters, Gbko Road, Makurdi | DAC Technology, Plot 8723 Baaver Dzeremo Street, Judges Quarters, Gbko Road, Makurdi | 31/10/14 | 24017268 | 3 months | [5 empty] | NIL | NIL
55 | Lot70/ws/14 - Construction of a Block of 3 Classrooms at Ogbere and Tondo Primary School in Toto LGA (Phase I), Toto LGA, Nasarawa State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 14036770 | N/A | 29/10/14 | Suyang Nig. Ltd No. 73, IBB Way Calabar | Suyang Nig. Ltd No. 73, IBB Way Calabar | 31/10/14 | 14036770 | 3 months | November, 2014 |  |  |  |  | NIL | NIL
56 | Lot1/Gs/14 - Purchase pf operational vehicles for Iyoba-Otukpa Multipurpose Dam | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 18677500.001 | N/A | 29/10/14 | Chenkibou Nig Ltd, 19 Balewa Crescent High/level. Makurdi, Benue State | Chenkibou Nig Ltd, 19 Balewa Crescent High/level. Makurdi, Benue State | 31-10-2014 | 18677500 | 30 Days from the Date of signing Contract Agreement | November, 2014 | 18677500 | 31-12- 2014 | 100% |  | NIL | NIL | Completed
57 | Lot1/Cs/ 14 - Design of Earth Dam with potential for irrigation at Ariri, Miango, Bassa LGA, Plateau state | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 30000000 | N/A | 29/10/14 | Consek Associates Ltd, No. 5 Imalefalafia street, oke ado, ibadan, Oyo State | Consek Associates Ltd, No. 5 Imalefalafia street, oke ado, ibadan, Oyo State | 31/10/14 | 14209846 | 3 months | November, 2014 |  | May, 2015 | 75% |  | NIL | NIL | On-Going
58 | Lot 2/cs/14- Design of Earth Dam at Foron, Barkin Ladi LGA, Plateau state | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 14470312.5 | N/A | 29/10/14 | Water center Nig. Ltd, Plot 31 Close Fed. Low Cost Estate, Jos, Plateau State | Water center Nig. Ltd, Plot 31 Close Fed. Low Cost Estate, Jos, Plateau State | 31/10/14 | 14470312.5 | 3 months | November, 2014 |  | February, 2015 | 75% |  | NIL | NIL | On-Going
59 | Lot3/cs/14 - Design of Magarhorop Rural Road with 3 culverts and 2 bridges in Bokkos LGA, Plateau Central Senatorial District, plateau state | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 100000000 | N/A | 29/10/14 | Real Naija Concpets Ltd, 27 reservation road GRA, Ilorin, Kwara State | Real Naija Concpets Ltd, 27 reservation road GRA, Ilorin, Kwara State | March, 2015 | 18058950 | 3 months | November, 2014 | 4914000 | February, 2015 | 75% |  | NIL | NIL | On-Going
60 | Construction of Magar - Horop Rural Road in Bokkos Lga Of Plateau State. | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 |  | N/A | 29/10/14 | Damak Properties Ltd | Damak Properties Ltd | March, 2015 | 221574167 | 6 months | [5 empty] | NIL | NIL
61 | Lot4/cs/14 - Design of Nasarawa Dam (Tede) | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 40000000 | N/A | 29/10/14 | Chido-Amajuyi & Partners, Chimboma house, jos, Plateau State | Chido-Amajuyi & Partners, Chimboma house, jos, Plateau State | 31/10/14 | 19900801 | 3 months | November, 2014 |  |  |  |  | NIL | NIL
62 | Lot5/cs/14 - Design of Flood Channelization and gully reclaimation work in Dyegh-mbatikyaa, Dyegh, Buruku LGA, Benue State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 11269479.38 | N/A | 29/10/14 | Team work Global, No. 13B Gwari Ave. Barnawa P.O. Box 4092, Kaduna State | Team work Global, No. 13B Gwari Ave. Barnawa P.O. Box 4092, Kaduna State | 31/10/14 | 11269479.38 | 3 months | November, 2014 |  | February, 2015 | 75% |  | NIL | NIL | On-Going
63 | Lot6/cs/14 - Survey Towards Obtaining Land title Deed for Okete and Kefi Colonies (Area; About 1, 059.45 Hectares) | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 16/9/2014 | 30/09/2014 | 14231250 | N/A | 29/10/14 | Shedaston Services No. 36 NNDC Quarters, Off Old Lamingo road, Jos | Shedaston Services No. 36 NNDC Quarters, Off Old Lamingo road, Jos | 31/10/14 | 14231250 | 3 months | [5 empty] | NIL | NIL
64 | Drilling of 1no Motorised Borehole at Efekpe-Imane, Olamaboro Lga, Kogi State | Notice Board Advertisement. Novevmeber 2014 | PTB | Open competative bidding | 13/11/14 | 21/11/14 | 9981768.74 | N/A | 26/11/14 | Emmic Global Services Ltd | Emmic Global Services Ltd. | 27/11/14 | 9981768.74 | 3 months | November, 2014 |  |  | 5% |  | NIL | NIL | On-Going
65 | Solar Powered Borehole at Ikomija(Drilling of 3 Nos Handpump Boreholes) | Notice Board Advertisement. Novevmeber 2014 | PTB | Open competative bidding | 13/11/14 | 21/11/14 | 5000000 | N/A | 26/11/14 | Sottams Synergy Resources Ltd | Sottams Synergy Resources Ltd | 27/11/14 | 4500000 | 3 months | November, 2014 |  | May, 2015 | 5% |  | NIL | NIL | On-Going
66 | Provision of Motorised Borehole at Tsambe Mbakor Tsenyamshagh Village, Vandeikya Lga( Drilling of 3nos Hand Pump Boreholes) | Notice Board Advertisement. Novevmeber 2014 | PTB | Open competative bidding | 13/11/14 | 21/11/14 | 5000000 | N/A | 26/11/14 | Mutesk Geotechnical And Drilling Co. Ltd | Mutesk Geotechnical And Drilling Co. Ltd | 27/11/14 | 4500000 | 3 months | November, 2014 |  | March,2015 | 5% |  | NIL | NIL | On-Going
67 | Provision of Solar Powered Borehole at Akwanga/Wamba/Nassarawa Eggon Federal Const.( Drilling of 5nos Hand Pump Boreholes) | Notice Board Advertisement. Novevmeber 2014 | PTB | Open competative bidding | 13/11/14 | 21/11/14 | 7994665 | N/A | 26/11/14 | Bronac Nig Ltd | Bronac Nig Ltd | 27/11/14 | 7500000 | 3 months | November, 2014 |  |  |  |  | NIL | NIL
68 | Provision of 5nos Hand Pump Boreholes at Gboko/Tarka Fed. Const. | Notice Board Advertisement. Novevmeber 2014 | PTB | Open competative bidding | 13/11/14 | 21/11/14 | 7613967 | N/A | 26/11/14 | Midag Ltd. No. 3 Alpha St. Off Inikpi St.High Level, Makurdi. | Midag Limited No 3 Alpha St. Off Inikpi St. High Level, Makurdi. | 27/11/14 | 7500000 | 3 months | November, 2014 | 1200000 |  |  |  | NIL | NIL
69 | Drilling of 2nos Hand Pump Boreholes at Rcm Pry School, Akehe Mbaishor | Notice Board Advertisement. Novevmeber 2014 | PTB | Open competative bidding | 13/11/14 | 21/11/14 |  | N/A | 26/11/14 | Davedanwonder Nig Ltd | Davedanwonder Nig Ltd | 27/11/14 | 2500000 | 3 months | November, 2014 |  | March,2015 | 20% |  | NIL | NIL | On-Going
70 | Drilling of 2nos Hand Pump Boreholes at Lafia/Obi Fed Const | Notice Board Advertisement. Novevmeber 2014 | MD | Open competative bidding | 13/11/14 | 21/11/14 | 2664888 | N/A | 26/11/14 | La-Rio Construstion Ltd | La-Rio Construstion Ltd | 27/11/14 | 2664888 | 3 months | November, 2014 |  | March,2015 | 10% |  | NIL | NIL | On-Going
71 | Drilling of 5nos Hand Pump Boreholesat Awe/Doma/Keana Fed. Const. | Notice Board Advertisement. Novevmeber 2014 | PTB | Open competative bidding | 13/11/14 | 21/11/14 | 7309408 | N/A | 26/11/14 | Ozzigi Multi Services Ltd | Ozzigi Multi Services Ltd | 27/11/14 | 7309408 | 3 months | November, 2014 |  | March,2015 | 60% |  | NIL | NIL | On-Going
72 | Drilling of 4nos Hand Pump Boreholes in Korinya and Tse Agbaragba Town 1 Konshisha Lga | Notice Board Advertisement. Novevmeber 2014 | PTB | Open competative bidding | 13/11/14 | 21/11/14 | 6091173 | N/A | 26/11/14 | Gold Initiative Nig Ltd | Gold Initiative Nig Ltd | 27/11/14 | 6000000 | 3 months | November, 2014 |  | March,2015 | 40% |  | NIL | NIL | On-Going
73 | Drilling of 5nos Hand Pump Boreholes at Mikang & Quan Pan Lgas, Plateau State | Notice Board Advertisement. Novevmeber 2014 | PTB | Open competative bidding | 13/11/14 | 21/11/14 |  | N/A | 26/11/14 | Geo-B Integrated Business Ltd | Geo-B Integrated Business Ltd | 27/11/14 | 7500000 | 3 months | November, 2014 |  | March,2015 | 5% |  | NIL | NIL | On-Going
74 | Rural Electrification of Wamba-Wude-Wayo in Nasarawa North Senatorial District | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 27/11/14 | 2014-11-12 | 40000000 | N/A |  | ANDEX PRESS & ALLIED SERVICES LTD | ANDEX PRESS & ALLIED SERVICES LTD | 27/11/14 | 100118749.5 |  | November, 2014 |  |  |  |  | NIL | NIL
75 | Mini Irrigation Scheme at Tse Dikki, Atirkyase Ushongo Lga, Benue State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 30/12/14 | 13/01/15 | 10000000 | N/A |  | Poga Skyline International | Poga Skyline International |  | 9662034.37 |  |  |  |  | 0% |  | NIL | NIL
76 | Con/120/14: Ochekwu River Gully Reclamation, Ugbokpo Village, Apa Lga, Benue State | Notice Board Advertisement. Novevmeber 2014 | PTB | Open competative bidding | 13/11/14 | 21/11/14 | 10000000 | N/A | 26/11/14 | Jessaza Global Resources,58 Bank Road | Jessaza Global Resources,58 Bank Road | 27/11/14 | 9489480 | 6 months | [5 empty] | NIL | NIL
77 | Construction of Dam & Irrigation Scheme at Vandeikya, Vandeikya LGA, Benue State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 30/12/14 | 13/01/15 | 70000000 | N/A | 26/11/14 | Mia Three (3) Nig Ltd, No. 15 Sokoto St., Central Mission Ward, P.O Box 239, Makurdi | Mia Three (3) Nig Ltd, No. 15 Sokoto St., Central Mission Ward, P.O Box 239, Makurdi |  | 220940294.4 | 6 months |  |  |  | 0% |  | NIL | NIL
78 | Purchase of Desktop and Laptop Computers for GIFMIS and IPPS Operators in the Authority. | Notice Board Advertisement. Novevmeber 2014 | PTB | Open competative bidding | 2014-02-11 | 21/11/14 | 10327750 | N/A | 26/11/14 | Maikam Enterprises, No. 5, Atom Kpera Road, High Level, Makurdi. | Maikam Enterprises, No. 5, Atom Kpera Road, High Level, Makurdi. | 27/11/14 | 9903175 | 3 months |  | 1485476.25 |  |  |  | NIL | NIL
79 | Supply of Spare Parts and Repair of Toyota Hilux 2.7 Vehicles No. FG 28-M25 and other Vehicle Tyres | Notice Board Advertisement. Novevmeber 2014 | PTB | Open competative bidding | 2014-02-11 | 21/11/14 | 6300000 | N/A | 26/11/14 | Austin Namson W/A Ltd. No 33, Bank Road, New Garage Makurdi. | Austin Namson W/A Ltd. No 33, Bank Road, New Garage Makurdi. | 27/11/14 | 6325767 | 3 months | [5 empty] | NIL | NIL
80 | Refurbishment of Workshop Machines | Notice Board Advertisement. Novevmeber 2014 | PTB | Open competative bidding | 2014-02-11 | 21/11/14 | 31500000 | N/A | 26/11/14 | Binowel Intergrated Services Ltd, Plot 41, Patrick Bokor Street, Jabi, Abuja. | Binowel Intergrated Services Ltd, Plot 41, Patrick Bokor Street, Jabi, Abuja. | 27/11/14 | 9981768.74 | 3 months | [5 empty] | NIL | NIL
81 | 25 Nos. Tubewells Irrigation Pumps and Motorcycles for Farmers in Bashar/Lamba, Wase LGA, Plateau State. | Notice Board Advertisement. Novevmeber 2014 | PTB | Open competative bidding | 2014-02-11 | 21/11/14 | 5972205 | N/A | 26/11/14 | Jerbeerou Nig. Ltd. No. 1 Beside Aisha Sondaji Plaza, Bukan Sidi, Lafia, Nasarawa State | Jerbeerou Nig. Ltd. No. 1 Beside Aisha Sondaji Plaza, Bukan Sidi, Lafia, Nasarawa State | 27/11/14 | 5972205 | 3 months | [5 empty] | NIL | NIL
82 | Comprehensive Renovation of 1 No. Three Bedroom C- Series Bungalow at Oforachi Project, Kogi State to include total Re-roofing. | Notice Board Advertisement. Novevmeber 2014 | PTB | Open competative bidding | 2014-02-11 | 21/11/14 | 45250000 | N/A | 26/11/14 | Satu Motors, No. 21 Idah Road, Anyigba, Kogi State | Satu Motors, No. 21 Idah Road, Anyigba, Kogi State | 27/11/14 | 8796579.75 | 3 months | [5 empty] | NIL | NIL
83 | Comprehensive Renovation of 1 No. Three bedroom C- Series Bungalow (PM`s House) at Oguma Project, Kogi State. | Notice Board Advertisement. Novevmeber 2014 | PTB | Open competative bidding | 2014-02-11 | 21/11/14 |  | N/A | 26/11/14 | Becky & Sam J. Nig. Ltd. 19, Ede-Okewu Cresent, Ojira, Ojira Quarters, Otukpo, Benue State. | Becky & Sam J. Nig. Ltd. 19, Ede-Okewu Cresent, Ojira, Ojira Quarters, Otukpo, Benue State. | 27/11/14 | 8524892.25 | 3 months | [5 empty] | NIL | NIL
84 | Renovation of GIS Laboratory at Headquarters. | Notice Board Advertisement. Novevmeber 2014 | PTB | Open competative bidding | 2014-02-11 | 21/11/14 | 12600000 | N/A | 26/11/14 | Leom Nig. Ltd, 13, Crescent House, Kado Estate, Abuja | Leom Nig. Ltd, 13, Crescent House, Kado Estate, Abuja | 27/11/14 | 5954300 | 3 months | [5 empty] | NIL | NIL
85 | Rehabilitation of the Headquarters Central Water Supply Sytstem. | Notice Board Advertisement. Novevmeber 2014 | PTB | Open competative bidding | 2014-02-11 | 21/11/14 |  | N/A | 26/11/14 | Envy-Chrisso International Ltd. C179, Federal Housing Estate, North Bank, Makurdi | Envy-Chrisso International Ltd. C179, Federal Housing Estate, North Bank, Makurdi | 27/11/14 | 6111000 | 3 months | [5 empty] | NIL | NIL
86 | Rebuilding of Collapsed Section of Fence/Construction of Support Columns and Provision of Gate at A4 Residential Quarters, Makurdi. | Notice Board Advertisement. Novevmeber 2014 | PTB | Open competative bidding | 2014-02-11 | 21/11/14 | 31500000 | N/A | 26/11/14 | I. U Thonisco Ent. Nig. Ltd. No. 22, Benue Crescent, Ankpa Qtrs. Makurdi | I. U Thonisco Ent. Nig. Ltd. No. 22, Benue Crescent, Ankpa Qtrs. Makurdi | 27/11/14 | 5270565 | 3 months | Demember, 2014 |  |  | 80% |  | NIL | NIL | On-going
87 | Enlargement of Poultry Farm at the Headquarters Makurdi | Notice Board Advertisement. Novevmeber 2014 | PTB | Open competative bidding | 2014-02-11 | 21/11/14 |  | N/A | 26/11/14 | DSA Global | DSA Global | 27/11/14 | 13040402.5 | 3 months | [5 empty] | NIL | NIL
88 | Revitalization of Fish Pond at the Headquarter Makurdi | Notice Board Advertisement. Novevmeber 2014 | PTB | Open competative bidding | 2014-02-11 | 21/11/14 |  | N/A | 26/11/14 | Giftson Ehi Enterprises Ltd. | Giftson Ehi Enterprises Ltd. | 27/11/14 | 5858848.44 | 3 months | [5 empty] | NIL | NIL
89 | Drilling of 3 No. Hand Pump Borehole in Makurdi, Benue State. | Notice Board Advertisement. Novevmeber 2014 | PTB | Open competative bidding | 2014-02-11 | 21/11/14 |  | N/A | 26/11/14 | Ureta Engineering constult Ltd. | Ureta Engineering constult Ltd. | 27/11/14 | 4500000 | 3 months | [5 empty] | NIL | NIL
90 | Drilling of 2nos Hand Pump Boreholes at Lbrbda Colony & Uec N/B Makurdi | Notice Board Advertisement. Novevmeber 2014 | PTB | Open competative bidding | 2014-02-11 | 21/11/14 |  | N/A | 26/11/14 | Base One Global Business Nig Ltd | Base One Global Business Nig Ltd | 27/11/14 | 2996700 | 3 months |  | 2857365 |  | 100% |  | NIL | NIL | COMPLETED
91 | Drilling of 1no Hand Pump Borehole at Ehatope Okpiko, Ohimini LGA, Benue State | Notice Board Advertisement. Novevmeber 2014 | PTB | Open competative bidding | 2014-02-11 | 21/11/14 |  | N/A | 26/11/14 | Bis Alu Properties Ltd | Bis Alu Properties Ltd | 27/11/14 | 1500000 | 3 months |  |  |  | 100% |  | NIL | NIL | COMPLETED
92 | Drilling Of 3nos Hand Pump Boreholes to Lower Benue Communities | Notice Board Advertisement. Novevmeber 2014 | PTB | Open competative bidding | 2014-02-11 | 21/11/14 |  | N/A | 26/11/14 | Quion Nig Ltd | Quion Nig Ltd | 27/11/14 | 4500000 | 3 months |  |  |  | 100% |  | NIL | NIL | COMPLETED
93 | Re-Establishment/Installation and upgrading Hydromet Instruments | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 2014-02-11 | 21/11/14 | 6300000 | N/A | 26/11/14 | Nia-Kins Nig. Ltd. | Aim Frontline Nig. Ltd. | Sept.2014 |  | 3 months | December, 2014 |  |  |  |  | NIL | NIL
84 | Training of Management and Senior Staff Of The Authority | Notice Board Advertisement. 2014 | MD | Open competative bidding | 14/9/14 | 21/9/14 |  | N/A | 26/9/14 | Kensas Company Nig. Ltd | Kensas Company Nig Ltd | Sept.2014 | 2409750 | 3 months | [5 empty] | NIL | NIL
95 | Purchase and Supply of fire resistant safe/Bullet Proof Cabinet | Notice Board Advertisement. 2014 | MD | Open competative bidding | 14/9/14 | 21/9/14 |  | N/A | 26/9/14 | Okaha Limited. | Okaha Limited | Sept.2014 | 2419775 | 3 months |  | 2419775 |  |  |  | NIL | NIL
96 | Training of the Accountants and Store Officers of the Authority | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 14/9/14 | 21/9/14 |  | N/A | 26/9/14 | Hero Joo Associates | Hero Joo Associates | Sept.2014 | 4819500 | 3 months |  | 4819500 |  |  |  | NIL | NIL
97 | Training of the staff of the Authority due for retirement on pre-retirement and managing a new beginning | Notice Board Advertisement. 2014 | MD | Open competative bidding | 14/9/14 | 21/9/14 |  | N/A | 26/9/14 | Motac Management Consultant Services | Motac Management Consultant Services | 31-10-2014 | 3331125 | 3 months | [5 empty] | NIL | NIL | Completed
98 | Furnishing of Assistant Director (Admin.) Office | Notice Board Advertisement. 2014 | MD | Open competative bidding | 14/9/14 | 21/9/14 |  | N/A | 26/9/14 | Ochejele Farmers Multipurpose Nig. Ltd. | Ochejele Farmers Multipurpose Nig. Ltd. | Sept.2014 | 2494800 | 3 months | [5 empty] | NIL | NIL | On Going
99 | Contract for the training of Project Managers and Assistant Project Managers of the Authority on Security awareness & Challenges | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 14/9/14 | 21/9/14 |  | N/A | 26/9/14 | Core Associates Consultant Limited | Core Associates Consultant Limited | Sept.2014 | 12818183 | 3 months |  |  |  | 100% |  | NIL | NIL | Completed
100 | Contract for the training of security, supervisor and Guards Working for the Authority | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 14/9/14 | 21/9/14 |  | N/A | 26/9/14 | Shirmark Resources Limited | Shirmark Resources Limited | Sept.2014 | 11923942 | 3 months |  | 11923942 |  |  |  | NIL | NIL | Completed
101 | Sensitization/Awareness Workshop on enhancing Effectiveness and Efficiency in Project Management through Health Security : On Prevention Control and Management of Ebola Virus Disease (EVD) for Staff in Headquarters and Nasarawa, Kogi and Benue State | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 14/11/14 | 21/11/14 |  | N/A | 26/11/14 | Core Associate Consultant Limited | Core Associate Consultant Limited | Dec. 2014 | 23452000 | 3 months | [5 empty] | NIL | NIL | On Going
102 | Supply of Executive Tables and Chairs at the Headquarters | Notice Board Advertisement. 2014 | MD | Open competative bidding | 14/11/14 | 21/11/14 |  | N/A | 26/11/14 | Beltu Nigeria Ltd. | Beltu Nigeria Ltd. | Nov. 2014 | 2499000 | 3 months |  | 2100000 |  |  |  | NIL | NIL | Completed
103 | Supply of 2 Nos. Operational Vehicles for Iyobo – Otukpa Multipurpose Dam | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 14/11/14 | 21/11/14 |  | N/A | 26/11/14 | Chenkibou Nig. Ltd. | Chenkibou Nig. Ltd. | Nov. 2014 | 18677500 | 3 months |  | 18677500 |  |  |  | NIL | NIL | Completed
104 | Training Workshop for Management and Senior Staff of the Authority on Security Awareness and Challenges | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 14/11/14 | 21/11/14 |  | N/A | 26/11/14 | Core Associates Consultant Limited | Core Associates Consultant Limited | Nov. 2014 | 19894875 | 3 months | [5 empty] | NIL | NIL | Completed
105 | Supply of Executive Tables and Chairs at the Headquarters | Notice Board Advertisement. 2014 | MD | Open competative bidding | 14/11/14 | 21/11/14 |  | N/A | 26/11/14 | Beltu Nigeria Ltd. | Beltu Nigeria Ltd. | Nov. 2014 | 2499000 | 3 months | [5 empty] | NIL | NIL | Completed
106 | Supply of Studio Equipment at Headquarters | Notice Board Advertisement. 2014 | MD | Open competative bidding | 15/5/14 | 22/5/24 |  | N/A | 27/5/14 | ALMAJ CONCEPT INTERNATIONAL LTD No. 53, Oba Overanwen Street Gwarinpa, Abuja | ALMAJ CONCEPT INTERNATIONAL LTD No. 53, Oba Overanwen Street Gwarinpa, Abuja | 28/5/24 | 2486295 | 3 months |  | 2486295 |  | 100% |  | NIL | NIL | Completed
107 | Provision of 3 Nos. Handpump Boreholes in Benue State | Notice Board Advertisement. 2014 | MD | Open competative bidding | 15/5/14 | 22/5/24 |  | N/A | 27/5/14 | JADIDA NIGERIA LTD No. 5, Court Quarters Road Karu Site, Abuja | JADIDA NIGERIA LTD No. 5, Court Quarters Road Karu Site, Abuja | 28/5/24 | 4500000 | 3 months |  | 4290749.97 |  |  |  | NIL | NIL
108 | Provision of 3 Nos. Handpump Boreholes in Anyiin, Gaambe-Tiev, Logo LGA, Benue State | Notice Board Advertisement. 2014 | MD | Open competative bidding | 15/5/14 | 22/5/24 |  | N/A | 27/5/14 | ZOZO MARKETING COMPANY LTD No. 64, Wukari-Ainsa Road Opposite Ugba Road Junction Anyii, Gaambe-Tiev PO Box 1102, Makurdi | ZOZO MARKETING COMPANY LTD No. 64, Wukari-Ainsa Road Opposite Ugba Road Junction Anyii, Gaambe-Tiev PO Box 1102, Makurdi | 28/5/24 | 4500000 | 3 months | [5 empty] | NIL | NIL
109 | Provision of 3 Nos. Handpump Boreholes in Benue State | Notice Board Advertisement. 2014 | MD | Open competative bidding | 15/5/14 | 22/5/24 |  | N/A | 27/5/14 | GOTAM INTEGRATED SERVICES LTD No. 4, Khartoum Street Wuse Zone 5, Abuja | GOTAM INTEGRATED SERVICES LTD No. 4, Khartoum Street Wuse Zone 5, Abuja | 28/5/24 | 4500000 | 3 months |  | 4290749.97 |  |  |  | NIL | NIL
110 | Provision of 3 Nos. Handpump Boreholes in Makurdi, Ukum and Logo LGAs, Benue State | Notice Board Advertisement. 2014 | MD | Open competative bidding | 15/5/14 | 22/5/24 |  | N/A | 27/5/14 | GABTER RESOURCES LTD No. 1, Yima Plaza, Jonah Jang Crescent Opposite Voice Newspaper, Makurdi | GABTER RESOURCES LTD No. 1, Yima Plaza, Jonah Jang Crescent Opposite Voice Newspaper, Makurdi | 28/5/24 | 4500000 | 3 months | [5 empty] | NIL | NIL
111 | Provision of 3 Nos. Handpump Boreholes in the three Senatorial Districts of Benue State | Notice Board Advertisement. 2014 | MD | Open competative bidding | 28/5/24 | 2014-06-06 |  | N/A | 2014-08-06 | GEOTOIS HYDROSERVICES LTD Plot 35, Block II, FGSSP Shagari Estate, Akure | GEOTOIS HYDROSERVICES LTD Plot 35, Block II, FGSSP Shagari Estate, Akure | 13/6/14 | 4500000 | 3 months | [5 empty] | NIL | NIL
112 | Provision of 3 Nos. Handpump Boreholes in the three Senatorial Districts of Benue State | Notice Board Advertisement. 2014 | MD | Open competative bidding | 28/5/24 | 2014-06-06 |  | N/A | 2014-08-06 | EMMIC GLOBAL SERVICES LTD No. 278, Aba Express Road Shell R/A, PortHarcourt | EMMIC GLOBAL SERVICES LTD No. 278, Aba Express Road Shell R/A, PortHarcourt | 13/6/14 | 4500000 | 3 months |  | 4500000 |  |  |  | NIL | NIL
113 | Provision of 3 Nos. Handpump Boreholes at locations in the three Senatorial Districts of Benue State | Notice Board Advertisement. 2014 | MD | Open competative bidding | 28/5/24 | 2014-06-06 |  | N/A | 2014-08-06 | MUTESK GEOTECHNICAL AND DRILLING COMPANY LTD Km 8, Makurdi-Otukpo Road Near Apir Mech Village Makurdi | MUTESK GEOTECHNICAL AND DRILLING COMPANY LTD Km 8, Makurdi-Otukpo Road Near Apir Mech Village Makurdi | 13/6/14 | 4500000 | 3 months | [5 empty] | NIL | NIL
114 | Provision of 3 Nos. Handpump Boreholes at locations in the three Senatorial Districts of Benue State | Notice Board Advertisement. 2014 | MD | Open competative bidding | 28/5/24 | 2014-06-06 |  | N/A | 2014-08-06 | TECOM INVESTMENT LTD No. 216, Obiwali Road Rimmugbo, Port Harcourt | TECOM INVESTMENT LTD No. 216, Obiwali Road Rimmugbo, Port Harcourt | 13/6/14 | 4500000 | 3 months |  | 4500000 |  |  |  | NIL | NIL
115 | Provision of 3 Nos. Handpump Boreholes in Benue State | Notice Board Advertisement. 2014 | MD | Open competative bidding | 28/5/24 | 2014-06-06 |  | N/A | 2014-08-06 | OCHIEJELE FARMERS MULTIPURPOSE NIGERIA LTD No. 54, Benue Crescent Makurdi | OCHIEJELE FARMERS MULTIPURPOSE NIGERIA LTD No. 54, Benue Crescent Makurdi | 13/6/14 | 4500000 | 3 months | [5 empty] | NIL | NIL
116 | Supply of Diesel and Engine Oil at Headquarters | Notice Board Advertisement. 2014 | MD | Open competative bidding | 28/5/24 | 2014-06-06 |  | N/A | 2014-08-06 | PIVOT PETROLEUM SERVICES LTD No. 3, New Layout, Behind Government College Makurdi | PIVOT PETROLEUM SERVICES LTD No. 3, New Layout, Behind Government College Makurdi | 13/6/14 | 2493750 | 3 months |  | 2493750 |  |  |  | NIL | NIL
117 | Provision of 3 Nos. Handpump Boreholes at locations in the three Senatorial Districts of Benue State | Notice Board Advertisement. 2014 | MD | Open competative bidding | 28/5/24 | 2014-06-06 |  | N/A | 2014-08-06 | TAQULAH ENGINEERING LTD Km 8, Makurdi-Otukpo Road Near Apir Mech Village Makurdi | TAQULAH ENGINEERING LTD Km 8, Makurdi-Otukpo Road Near Apir Mech Village Makurdi | 13/6/14 | 4604796 | 3 months |  | 4604796 |  |  |  | NIL | NIL
118 | Provision of 3 Nos. Handpump Boreholes at locations in Benue State | Notice Board Advertisement. 2014 | MD | Open competative bidding | 28/5/24 | 2014-06-06 |  | N/A | 2014-08-06 | DAJOH-UGBADA NIG LTD No. 333, 3rd Avenue 3rd Avenue, Lobi Quarters Makurdi | DAJOH-UGBADA NIG LTD No. 333, 3rd Avenue 3rd Avenue, Lobi Quarters Makurdi | 13/6/14 | 4500000 | 3 months | [5 empty] | NIL | NIL
119 | Provision of 3 Nos. Handpump Boreholes at locations in the three Senatorial Districts of Benue State | Notice Board Advertisement. 2014 | MD | Open competative bidding | 28/5/24 | 2014-06-06 |  | N/A | 2014-08-06 | DENTICA NIGERIA LTD Post Office Building PO Box 545, Katsina-Ala Benue State | DENTICA NIGERIA LTD Post Office Building PO Box 545, Katsina-Ala Benue State | 13/6/14 | 4500000 | 3 months | [5 empty] | NIL | NIL
120 | Provision of 3 Nos. Handpump Boreholes in Benue State | Notice Board Advertisement. 2014 | MD | Open competative bidding | 28/5/24 | 2014-06-06 |  | N/A | 2014-08-06 | HY-KREST PLODINE SOLUTIONS NIGERIA LTD Suite D15, 11 Bumbuna Street Zone 1, Wuse Abuja | HY-KREST PLODINE SOLUTIONS NIGERIA LTD Suite D15, 11 Bumbuna Street Zone 1, Wuse Abuja | 13/6/14 | 4500000 | 3 months | [5 empty] | NIL | NIL
121 | Supply of Stationery at Headquarters, Makurdi | Notice Board Advertisement. 2014 | MD | Open competative bidding | 28/5/24 | 2014-06-06 |  | N/A | 2014-08-06 | AIM FRONTLINE NIGERIA LTD No. 5, fifth Avenue, Bida Street Wadata, Makurdi | AIM FRONTLINE NIGERIA LTD No. 5, fifth Avenue, Bida Street Wadata, Makurdi | 13/6/14 | 2496217.5 | 3 months | [5 empty] | NIL | NIL
122 | Maintenance of Doma Dam Slopes, Doma, Nasarawa State | Notice Board Advertisement. 2014 | MD | Open competative bidding | 28/5/24 | 2014-06-06 |  | N/A | 2014-08-06 | MIA THREE (3) NIGERIA LTD No. 15 Sokoto Street Central Mission Ward P.O Box 239 Makurdi | MIA THREE (3) NIGERIA LTD No. 15 Sokoto Street Central Mission Ward P.O Box 239 Makurdi | 13/6/14 | 8584561.12 | 3 months | [5 empty] | NIL | NIL
123 | Renovation of 2Nos. Classroom Blocks in NKST Primary School, Tum Mbadura, Kwande LGA, Benue State | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 28/5/24 | 2014-06-06 |  | N/A | 2014-08-06 | AIM FRONTLINE NIGERIA LTD No. 5, fifth Avenue, Bida Street Wadata, Makurdi | AIM FRONTLINE NIGERIA LTD No. 5, fifth Avenue, Bida Street Wadata, Makurdi | 13/6/14 | 12860862 | 3 months | [5 empty] | NIL | NIL
124 | Supply of 11, 000 litres of Diesel and 400 litres of Engine Oil at the Authority’s Headquarters | Notice Board Advertisement. 2014 | MD | Open competative bidding | 28/5/24 | 2014-06-06 |  | N/A | 2014-08-06 | PIVOT PETROLEUM SERVICES LTD No. 3, New Layout, Behind Government College Makurdi | PIVOT PETROLEUM SERVICES LTD No. 3, New Layout, Behind Government College Makurdi | 13/6/14 | 2493750 | 3 months |  | 2493750 |  |  |  | NIL | NIL
125 | Provision of 3 Nos. Handpump Boreholes at various locations in Benue State | Notice Board Advertisement. 2014 | MD | Open competative bidding | 28/5/24 | 2014-06-06 |  | N/A | 2014-08-06 | ENVY-CHRISSO INTERNATIONAL LTD Block C179, Federal Low Cost Housing Estate North Bank, Makurdi | ENVY-CHRISSO INTERNATIONAL LTD Block C179, Federal Low Cost Housing Estate North Bank, Makurdi | 13/6/14 | 4503149.97 | 3 months | [5 empty] | NIL | NIL
126 | Supply of Executive Office Tables and Chairs at Headquarters | Notice Board Advertisement. 2014 | MD | Open competative bidding | 28/5/24 | 2014-06-06 |  | N/A | 2014-08-06 | BELTU NIGERIA LTD No. 7, Mission Ward Northbank, Makurdi | BELTU NIGERIA LTD No. 7, Mission Ward Northbank, Makurdi | 13/6/14 | 2499000 | 3 months | [5 empty] | NIL | NIL
127 | Provision of 3 Nos. Handpump Boreholes at various locations in Benue State | Notice Board Advertisement. 2014 | MD | Open competative bidding | 28/5/24 | 2014-06-06 |  | N/A | 2014-08-06 | INDVA INTERNATIONAL RESOURCES LTD No. 46B Clerk Quarters Behind Edomart Kitchen Makurdi | INDVA INTERNATIONAL RESOURCES LTD No. 46B Clerk Quarters Behind Edomart Kitchen Makurdi | 13/6/14 | 4512375 | 3 months | [5 empty] | NIL | NIL
128 | Fumigation of Oforachi Project, Kogi State | Notice Board Advertisement. 2014 | MD | Open competative bidding | 28/5/24 | 2014-06-06 |  | N/A | 2014-08-06 | AHWENS LTD 24, Osisiogu Street Utako, Abuja | AHWENS LTD 24, Osisiogu Street Utako, Abuja | 13/6/14 | 2505497.5 | 3 months |  | 2, 505, 497.50 |  |  |  | NIL | NIL
129 | Clearing of Unwanted Grasses at the Staff Residential Quarters (A, B & C Series) Headquarters, Makurdi | Notice Board Advertisement. 2014 | MD | Open competative bidding | 28/5/24 | 2014-06-06 |  | N/A | 2014-08-06 | FAVOUR GALORE LTD No. 3, Beach Road By Spring Bank PO Box 2156, Jos | FAVOUR GALORE LTD No. 3, Beach Road By Spring Bank PO Box 2156, Jos | 13/6/14 | 2516450 | 3 months |  | 2, 516, 450.00 |  |  |  | NIL | NIL
130 | Purchase/Supply of Compound Fertilers (NPK 15:15:15) Headquarters, Makurdi | Notice Board Advertisement. 2014 | MD | Open competative bidding | 28/5/24 | 2014-06-06 |  | N/A | 2014-08-06 | JANKASA RESOURCES NIGERIA LTD No. 3, Rumbek Close, Wuse Zone 6 Abuja | JANKASA RESOURCES NIGERIA LTD No. 3, Rumbek Close, Wuse Zone 6 Abuja | 13/6/14 | 4822800 | 3 months |  | 4, 822, 800.00 |  |  |  | NIL | NIL
131 | Clearing of 14Ha Farmland at Okete Project, Benue State | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 28/5/24 | 2014-06-06 |  | N/A | 2014-08-06 | KARL T. GEOTECHNICAL & ENGINEERING SERVICES LTD No. E007, Kari Road Housing Estate Maiduguri Road, Bauchi | KARL T. GEOTECHNICAL & ENGINEERING SERVICES LTD No. E007, Kari Road Housing Estate Maiduguri Road, Bauchi | 13/6/14 | 19000000 | 3 months |  | 19, 000, 000.00 |  |  |  | NIL | NIL
132 | Clearing of Unwanted Grasses at the Staff Residential Quarters (D & JS Series), Makurdi | Notice Board Advertisement. 2014 | MD | Open competative bidding | 28/5/24 | 2014-06-06 |  | N/A | 2014-08-06 | NASIBELCO RESOURCES NIGERIA LTD No. 11, Behind No. 50, Gyado Hospital Road GRA, Gboko | NASIBELCO RESOURCES NIGERIA LTD No. 11, Behind No. 50, Gyado Hospital Road GRA, Gboko | 13/6/14 | 2495187.5 | 3 months |  | 2, 495, 187.50 |  |  |  | NIL | NIL
133 | Clearing of Unwanted Grasses at the Headquarters, Makurdi | Notice Board Advertisement. 2014 | MD | Open competative bidding | 28/5/24 | 2014-06-06 |  | N/A | 2014-08-06 | TONAB NIGERIA LTD 44, Old Otukpo Road Makurdi | TONAB NIGERIA LTD 44, Old Otukpo Road Makurdi | 13/6/14 | 4490075 | 3 months |  | 4, 490, 075.00 |  |  |  | NIL | NIL
134 | Supply of Urea Fertilizers at Headquarters, Makurdi | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 28/5/24 | 2014-06-06 |  | N/A | 2014-08-06 | VIMAC ENGINEERING SERVICES LTD No. 5, Murtala Mohammed Way Jos | VIMAC ENGINEERING SERVICES LTD No. 5, Murtala Mohammed Way Jos | 13/6/14 | 7542650 | 3 months | [5 empty] | NIL | NIL
135 | Construction Supervision of Owukpa Dam, Benue State | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 2014-03-07 | 2014-10-07 |  | N/A | 17/7/14 | MULTI-ENGINEERING SOLUTION & DESIGN LTD D208, Garki Mall, Plot 1580 Kabo Crescent, Opposite Garki International Market Abuja | MULTI-ENGINEERING SOLUTION & DESIGN LTD D208, Garki Mall, Plot 1580 Kabo Crescent, Opposite Garki International Market Abuja | 18/7/14 | 21116035.18 | 6 months | [5 empty] | NIL | NIL
136 | Construction Supervision of Pagna Dam, Plateau State | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 2014-03-07 | 2014-10-07 |  | N/A | 17/7/14 | REAL NAJIA CONCEPTS LTD No. 27 Reservation Road, GRA Ilorin, Kwara State | REAL NAJIA CONCEPTS LTD No. 27 Reservation Road, GRA Ilorin, Kwara State | 18/7/14 | 16078007.32 | 6 months | [5 empty] | NIL | NIL
137 | Construction Supervision of Mbachoughul Dam, Benue State | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 2014-03-07 | 2014-10-07 |  | N/A | 17/7/14 | MBS ENGINEERING LTD No. 124 Main Street, NNDC Quarters Off Maiduguri Road , Hotoro GRA, PO Box 10819 Kano | MBS ENGINEERING LTD No. 124 Main Street, NNDC Quarters Off Maiduguri Road , Hotoro GRA, PO Box 10819 Kano | 18/7/14 | 20929020.54 | 6 months | [5 empty] | NIL | NIL
138 | Construction Supervision of the Construction of Township Roads in Otukpo, Benue State | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 2014-03-07 | 2014-10-07 |  | N/A | 17/7/14 | MBS ENGINEERING LTD No. 124 Main Street, NNDC Quarters Off Maiduguri Road, Hotoro GRA, PO Box 10819 Kano | MBS ENGINEERING LTD No. 124 Main Street, NNDC Quarters Off Maiduguri Road, Hotoro GRA, PO Box 10819 Kano | 18/7/14 | 9789672.33 | 6 months | [5 empty] | NIL | NIL
139 | Supervision of the Construction of Roads, Bridges and Culverts at Owukpa, Benue State | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 2014-03-07 | 2014-10-07 |  | N/A | 17/7/14 | VIABLE ENGINEERING CONSULTANTS LTD, Suite RFL 3, 4th Floor City Plaza, Ahmadu Bello Way Garki II, Abuja | VIABLE ENGINEERING CONSULTANTS LTD, Suite RFL 3, 4th Floor City Plaza, Ahmadu Bello Way Garki II, Abuja | 18/7/14 | 20221604.39 | 6 months |  | 3033240.66 |  |  |  | NIL | NIL
140 | Construction Supervision of Adoka-Okpaflo earth Dam, Benue State | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 2014-03-07 | 2014-10-07 |  | N/A | 17/7/14 | WATER CENTER NIGERIA LTD D208, Garki Mall, Plot 1580 Kabo Crescent, Opposite Garki International Market , Abuja | WATER CENTER NIGERIA LTD D208, Garki Mall, Plot 1580 Kabo Crescent, Opposite Garki International Market , Abuja | 18/7/14 | 33398498.51 | 6 months | [5 empty] | NIL | NIL
141 | Supervision of the Construction of Water Treatment Plant at Benue Polytechnic, Ugbokolo, Benue State | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 2014-03-07 | 2014-10-07 |  | N/A | 17/7/14 | SURDS ENGINEERING SERVICES LTD, No. 60, 3rd Avenue, Gwarimpa, Abuja | SURDS ENGINEERING SERVICES LTD, No. 60, 3rd Avenue, Gwarimpa, Abuja | 18/7/14 | 13645058.62 | 6 months | [5 empty] | NIL | NIL
142 | Supervision of the Construction of 6km Access Road to Pankshin Dam, Plateau State | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 2014-03-07 | 2014-10-07 |  | N/A | 17/7/14 | CHIDO-AMAJUOYI & PARTNERS LTDChimboma House, P.O.Box 6138, Jos | CHIDO-AMAJUOYI & PARTNERS LTDChimboma House, P.O.Box 6138, Jos | 18/7/14 | 14726817.06 | 6 months | [5 empty] | NIL | NIL
143 | Supervision of the Rehabilitation of Doma Dam Project, Nasarawa State | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 2014-03-07 | 2014-10-07 |  | N/A | 17/7/14 | TECTONIC ENGINEERING & CONSULTS LTD No 8, 32 Crescent Off 3 Road Avenue Gwarinpa, FCT Abuja | TECTONIC ENGINEERING & CONSULTS LTD No 8, 32 Crescent Off 3 Road Avenue Gwarinpa, FCT Abuja | 18/7/14 | 16702049.23 | 6 months | [5 empty] | NIL | NIL
144 | Construction Supervision of Gazum Dam, Langtang South LGA, Plateau State | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 2014-03-07 | 2014-10-07 |  | N/A | 17/7/14 | ENVIPLAN INTERNATIONAL LTD 22, Gobarau Road , P.O. Box 11041, Kaduna | ENVIPLAN INTERNATIONAL LTD 22, Gobarau Road , P.O. Box 11041, Kaduna | 18/7/14 | 16577287.65 | 6 months | [5 empty] | NIL | NIL
145 | Construction Supervision of Ber Agbum Dam, Ushongu LGA, Benue State | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 2014-03-07 | 2014-10-07 |  | N/A | 17/7/14 | VIABLE ENGINEERING CONSULTANTS LTD Suite RFL 3, 4th Floor City Plaza, Ahmadu Bello Way, Garki II, Abuja | VIABLE ENGINEERING CONSULTANTS LTD Suite RFL 3, 4th Floor City Plaza, Ahmadu Bello Way, Garki II, Abuja | 18/7/14 | 16585463.06 | 6 months | [5 empty] | NIL | NIL
146 | Construction Supervision of Katanga Earth Dam, Wamba LGA, Nasarawa State | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 2014-03-07 | 2014-10-07 |  | N/A | 17/7/14 | CRESTPLAN ASSOCIATES LTD Lungi Barracks Plaza, Suite 14 &18c, Maitama, P.O.Box 11988, Garki, Abuja | CRESTPLAN ASSOCIATES LTD Lungi Barracks Plaza, Suite 14 &18c, Maitama, P.O.Box 11988, Garki, Abuja | 18/7/14 | 17725383.49 | 6 months | [5 empty] | NIL | NIL
147 | Supervision of the Construction of Bridge at Adim, Egbala/Adankari, Otukpo LGA, Benue State | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 2014-03-07 | 2014-10-07 |  | N/A | 17/7/14 | MULTI-ENGINEERING SOLUTION & DESIGN LTD D208, Garki Mall, Plot 1580 Kabo Crescent, Opposite Garki International Market Abuja | MULTI-ENGINEERING SOLUTION & DESIGN LTD D208, Garki Mall, Plot 1580 Kabo Crescent, Opposite Garki International Market Abuja | 18/7/14 | 21069594.86 | 6 months | [5 empty] | NIL | NIL
148 | Construction Supervision of Ugar Earth Dam, Benue State | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 2014-03-07 | 2014-10-07 |  | N/A | 17/7/14 | TECTONICS ENGINEERING & CONSULTS LTD No 8, 32 Crescent Off 3 Road Avenue Gwarinpa, FCT Abuja | TECTONICS ENGINEERING & CONSULTS LTD No 8, 32 Crescent Off 3 Road Avenue Gwarinpa, FCT Abuja | 18/7/14 | 20395445.07 | 6 months | [5 empty] | NIL | NIL
149 | Construction Supervision of Iyoba-Otukpa Earth dam, Ogbadibo LGA, Benue State | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 2014-03-07 | 2014-10-07 |  | N/A | 17/7/14 | TEAMWORK GLOBAL ASSOCIATES D208, Garki Mall, Plot 1580 Kabo Crescent, Opposite Garki International Market, Abuja | TEAMWORK GLOBAL ASSOCIATES D208, Garki Mall, Plot 1580 Kabo Crescent, Opposite Garki International Market, Abuja | 18/7/14 | 33398498.51 | 6 months | [5 empty] | NIL | NIL
150 | Construction Supervision of Otobi-Akpegede Earth Dam (Ajide), Benue State | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 2014-03-07 | 2014-10-07 |  | N/A | 17/7/14 | BILMAP (W/A) LTD No. 30 Iyorchia Ayu Road Wurukum, P.o.Box 1949, Makurdi | BILMAP (W/A) LTD No. 30 Iyorchia Ayu Road Wurukum, P.o.Box 1949, Makurdi | 18/7/14 | 10725383.49 | 6 months | [5 empty] | NIL | NIL
151 | Maintenance of Doma Dam Slopes, Doma, Nasarawa State | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 2014-01-08 | 2014-08-08 |  | N/A | 15/8/14 | MIA THREE (3) NIGERIA LTD No. 15 Sokoto Street Central Mission Ward P.O Box 239 Makurdi | MIA THREE (3) NIGERIA LTD No. 15 Sokoto Street Central Mission Ward P.O Box 239 Makurdi | 18/8/14 | 8584561.12 | 3 months | [5 empty] | NIL | NIL
152 | Construction of Iyoba-Otukpa Dam, Ogbadibo LGA, Benue State | The Guardian 6-8-14 and Fed. Tenders Journal: Mon.11-Sun 24-8-14. | PTB | Open competative bidding | 2014-01-08 | 2014-08-08 |  | N/A | 15/8/14 | PALGREG NIGERIA LTD No. 82, 11 Cresecent Kado Estate, Abuja | PALGREG NIGERIA LTD No. 82, 11 Cresecent Kado Estate, Abuja | 20/8/14 | 241825106.25 | 6 months |  | 36273765.94 |  |  |  | NIL | NIL
153 | Construction of the 5th Avenue Road, Phase One (1) (450m length), Off Abu King Shuluwa Road, Makurdi | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 2014-01-08 | 2014-08-08 |  | N/A | 15/8/14 | PRIVENT CONSTRUCTION NIGERIA LTD GP 651, Ankpa Quarters Makurdi | PRIVENT CONSTRUCTION NIGERIA LTD GP 651, Ankpa Quarters Makurdi | 27/8/14 | 9859629.94 | 6 months | [5 empty] | NIL | NIL
154 | Construction of the 5th Avenue Road, Phase Two (2) (450m length) after Phase 1, Off Abu King Shuluwa Road, Makurdi | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 2014-01-08 | 2014-08-08 |  | N/A | 15/8/14 | PRIVENT CONSTRUCTION NIGERIA LTD GP 651, Ankpa Quarters Makurdi | PRIVENT CONSTRUCTION NIGERIA LTD GP 651, Ankpa Quarters Makurdi | 27/8/14 | 9887552.92 | 6 months | [5 empty] | NIL | NIL
155 | Construction of the 5th Avenue Road, Phase Three (3) (450m length), after the 2nd Phase, Off Abu King Shuluwa Road, Makurdi | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 2014-01-08 | 2014-08-08 |  | N/A | 15/8/14 | PRIVENT CONSTRUCTION NIGERIA LTD GP 651, Ankpa Quarters Makurdi | PRIVENT CONSTRUCTION NIGERIA LTD GP 651, Ankpa Quarters Makurdi | 27/8/14 | 9849288.09 | 6 months | [5 empty] | NIL | NIL
156 | Construction of the 5th Avenue Road, Phase Four (4) (350m length), after the Third Phase, Off Abu King Shuluwa Road, Makurdi | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 2014-01-08 | 2014-08-08 |  | N/A | 15/8/14 | NABAYI & SONS CONSTRUCTION COMPANY NIGERIA LTD No. 5, Gudum Hausawa Industrial Estate Bauchi State | NABAYI & SONS CONSTRUCTION COMPANY NIGERIA LTD No. 5, Gudum Hausawa Industrial Estate Bauchi State | 27/8/14 | 9913096.59 | 6 months | [5 empty] | NIL | NIL
157 | Obtaining Land Title Deeds for the Authority’s Doma and Dep Projects, Nasarawa State | Notice Board Advertisement. 2014 | PTB | Open competative bidding | 14/11/14 | 21/11/14 |  | N/A | 28/11/14 | REBDAS SURVEYS No. 56, Mercyland Road Sabon Gonin Gora Kaduna | REBDAS SURVEYS No. 56, Mercyland Road Sabon Gonin Gora Kaduna | Nov. 2014 | 10356120 | 3 months |  |  |  | 100% |  | NIL | NIL | Completed
4026117512.11

## TCN
PROCUREMENT RECORDS
PROCURING ENTITY (MDA) : |  | TRANSMISSION COMPANY OF NIGERIA
MINISTRY : POWER
FINANCIAL YEAR : 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD | [5 empty] | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) |  | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2013 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2013 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | Drilling of Boreholes in 132/33Kv substations at Zaria, Funtua, Danagundi, Dakata and Kankia. |  | Parastatal Tender Board | Selective Tendering | 2014-08-20 | 2014-08-25 | System operation Imprest |  | 2014-10-24 | Yes | Alamsabaz Engineering & Construction Ltd |  | 6094499
2 | Design and Development of TCN Website WWW.TCNORG.COM and Intranet Portal Facilities-TCN.ORG.COM |  | Parastatal Tender Board | Selective Tendering | 2014-09-23 | 2014-10-09 | FGN 2014 Appropriation |  | 2014-10-24 | Yes | Netportal Nig. Ltd |  | 28560000 | [5 empty] | Completed
3 | Supply of 2000mtrs 4 x 4 mm2Armoured control cable and 1000mtrs 2.5mm2 x 4Core control cable |  | Parastatal Tender Board | Selective Tendering |  | 2014-09-16 | System operation Imprest |  | 2014-10-24 | Yes | Yfeey Global Concept Ltd |  | 3150000
4 | Purchase of work tool equipment and computersystem for Public Affairs Operations |  | Parastatal Tender Board | Selective Tendering |  | 2014-09-22 | FGN 2014 Appropriation |  | 2014-10-24 | Yes | Segtekinfo Ltd |  | 4817400
5 | Supply and Installation of 39Nos 48VDC battery bank and charger for TCN substation |  | Parastatal Tender Board | Selective Tendering | 2014-10-13 | 2014-10-14 | System operation Imprest |  | 2014-12-01 | Yes | North-South Continental Nig. Ltd. |  | 160072500 |  | 12 months | 27/01/2015 | nil | 26/01/2016 | 0n-going
6 | Supply and Installation of Radio Communication Facility at Ayobo and Damaturu Substations |  | Parastatal Tender Board | Selective Tendering | 2014-09-23 | 2014-10-13 | System operation Imprest |  | 2014-12-01 | Yes | Biflek Engineering Ltd |  | 9438000 |  | 3 months | 13/01/2015 | 9438000 | 13/04/2015 | completed | 100% completed | nil | nil
7 | Extension of Alheri Engineering Fibre to TCN Communication Facilities (Benin-Onitsha) |  | Parastatal Tender Board | Selective Tendering | 2014-09-23 | 2014-10-13 | System operation Imprest |  | 2014-12-01 | Yes | Ahneka Nig. Ltd |  | 10582000 |  | 2 months | 2015-12-01 | 10582000 | 2015-12-03 | completed | 100% completed
8 | Renovation works of Benin Regional Control Room (Felt Works and Floor Tiles on 330KV Building) |  | Parastatal Tender Board | Selective Tendering | 2014-04-07 |  |  |  | 2014-12-01 | Yes | Glyno Engineering Ltd |  | 4810589.78 |  | 2 months | 2015-08-01 | nil | 2015-08-03 | completed | 100% completed
9 | Renovation works of Benin Regional Control Room (felt Works, Fittings and Fixtures on 132KV Building/Annex Building) |  | Parastatal Tender Board | Selective Tendering |  |  |  |  | 2014-12-01 | Yes | Glyco Engineering Ltd |  | 4784001.87 |  | 2 months | 2015-08-01 | nil | 2015-08-03 | completed | 100% completed
10 | Renovation works of Benin Regional Control Room (Painting of 330KV Building Annex and 132KV Building) |  | Parastatal Tender Board | Selective Tendering |  |  |  |  | 2014-12-01 | Yes | Gabrok Quarry Services |  | 4371410.4 |  | 2 months | 2015-08-01 | nil | 2015-08-03 | completed | 100% completed
11 | Urgent erection of perimeter Block wall fencing of Headquaters Central Stores Ojo, Lagos. (Total Perimeter : 312Mtrs) |  | Parastatal Tender Board | Selective Tendering | 2013-11-26 |  |  |  | 2014-03-14 | Yes | Ab-Lad Investment Nig Ltd |  | 14777226.45
12 | Supply of Safety Wears for field Workers. |  | Parastatal Tender Board | Selective Tendering | 2013-11-26 |  |  |  | 2014-01-31 |  | Jubic Joe Investment Ltd |  | 12337500
13 | Supply, Installation and commissioning of 50VDC battery banks and Chargers in 25 TCN Substations. |  | Parastatal Tender Board | Selective Tendering | 2014-01-23 | 2014-01-27 | System Operation Imprest |  | 2014-01-31 | Yes | Pimtek Nig Ltd/EverExceed Industrial Company Ltd |  | 61715937.5 |  | 12 months | 17/7/2015 | nil | 16/07/2015 | on-going
14 | Supply of 2HP Split unit Air conditional for TCN Control Rooms in the stations |  | Parastatal Tender Board | Selective Tendering | 2014-01-23 | 2014-01-27 | System Operation Imprest |  | 2014-02-12 | Yes | Amu & Mul Nig Ltd |  | 19306875
15 | Erosion Control Works on Tower 146 Gombe-Yola 330KV transmission Line |  | Parastatal Tender Board | Selective Tendering | 2013-08-23 | 2013-12-04 |  |  | 2014-03-14 | Yes | Happy World Global Options |  | 15583190.7
16 | Erosion Control Works on Tower 173 New Haven-Otukpo 132KV transmission Line |  | Parastatal Tender Board | Selective Tendering | 08/23/13 | 2013-12-04 |  |  | 2014-03-14 | Yes | Jukol Nigeria Ltd |  | 8526210
17 | Erosion Control Works on Tower 525 Jebba-Shiroro 330KV transmission Line 2 |  | Parastatal Tender Board | Selective Tendering |  | 2013-12-04 |  |  | 2014-03-14 | Yes | Royal Husband Intl Ltd |  | 23764791.8
18 | Renovation of Aba Sub-Regional Administrative Block complex |  | Parastatal Tender Board | Selective Tendering | 2014-01-09 |  |  |  | 2014-01-31 | Yes | Pinnacle Solution Networks Ltd |  | 24176088.75
19 | Emergency Erosion control works on Tower 412 Gombe-Yola 330KV Transmission Line |  | Parastatal Tender Board | Selective Tendering |  |  |  |  | 2014-01-31 | Yes | Diamond Global Eng. Invest Ltd |  | 49781943.75
20 | Additional Contract for the design, Manufacture, Supply, and installation of double channel power line carrier (PLC) communication system and associated equipment. Ikej west to Olorun Shogo Tranmisiion Station |  | Parastatal Tender Board | Single Sourcing |  | 2014-01-06 |  |  |  | Yes | Siemens Ltd |  | 7705273.97
21 | Emergency preparation of fixed asset for Lagos & Benin Region |  | Parastatal Tender Board | Single Sourcing |  | 2013-08-09 |  |  | 2014-02-28 | Yes | Pomanep Micro Services Ltd |  | 25524555
22 | Emergency supply of (3Sets) 132KV oil filled current transformer ratio :300/150/1/1A for system maintenance |  | Parastatal Tender Board | Emergency Advert |  | 2014-01-06 | F&A |  | 2014-03-28 | Yes | Dalian Instrument Transformer Co. Nig. Ltd |  | 11591875.38
23 | Site testing and online regeneration of Ino. 45MVA 132/33KV Hyudai , 2Nos 15MVA 132/33KV (OEL) and 1No 30MVA 132/33KV (Pauwels) Power Transformer at Ilupeju Transmission station. Lagos. |  | Parastatal Tender Board | Single Sourcing |  | 2013-07-19 | F&A |  | 2014-03-28 | Yes | GTA Engineering Ltd |  | 27899130 |  |  |  | Invoice with MGT ACCT. for Payment | Job Completed | Job Completed | Job Completed | Nil | Nil
24 | Emergency Supply of Two (2 No) 132KV and Ten (10 Nos) 33KV Cromton Greaves SF6 Gas Circuit Breakers for System Maintenance use |  | Parastatal Tender Board | Single Sourcing |  | 2014-01-31 | AFDB |  | 2014-03-28 | Yes | North - South continental Nig. Ltd | Six (6) Months | 44866500 |  | Six (6) Months | 3rd March, 2014 | Nil | Nil | Completed | Completed | Nil | Nil | Equipmentshas been Delivered to TCN CHQ Stores Ojo, Lagos.
25 | Emergency regeneration and disluging of transformer oil for 1X90MVA, 330/132/13.8KV ASGEN HYUDAI,TRANSFORMER AT ONITSHA T/S. |  | Parastatal Tender Board | Single Sourcing |  | 2014-01-29 | F&A |  | 2014-03-28 | Yes | Environmental Technologies Ltd |  | 39357675
26 | Emergency relocation and positioning of 2X30MVA 132/33KV (Trafo Union made) Power Transformer |  | Parastatal Tender Board | Single Sourcing |  | 2014-01-06 | F&A |  | 2014-03-28 | Yes | Nelson - C Strabec Engineering serVices Ltd |  | 10440150 |  |  |  | Payed Complete | Job Completed | Job Completed | Job Completed | Nil | Nil
27 | 2nd Benin - Onitsha 330KV SC Transmission Line additional works. And extension of official works order. |  | Parastatal Tender Board | Through Tendering |  | 2014-01-06 |  |  | 2014-03-28 | Yes | Colenco Consulting Nig. Ltd |  | 49132441.8
28 | Supply of 6Nos. Toyota Hilux Van for Civil Maintenance and Procurement Department. |  | Parastatal Tender Board | Selective tendering | 2014-03-14 | 2014-03-18 | F&A |  | 2014-03-28 | Yes | Elizade Nig. Ltd |  | 36000000
29 | Electrification of staff Quarters at Talata Mafara |  | Parastatal Tender Board | Single Sourcing |  | 2013-06-11 | F&A |  | 2014-03-28 | Yes | Continental Engineering Nig. Ltd |  | 7497357.7
30 | Movement of 100MVA Transformer from AJA to Ikorodu and removal of failed 60MVA Transformer from Plinth. |  | Parastatal Tender Board | Single Sourcing |  | 2014-02-07 | F&A |  | 2014-03-28 | Yes | Ohms Sources and Systems Ltd |  | 18900000 |  |  |  | Payed Complete | Job Completed | Job Completed | Job Completed | Nil | Nil
31 | Supply of office stationeries for the QUARTER |  | Parastatal Tender Board | Selective Tendering | 2014-02-10 |  | F&A |  | 2014-03-28 | Yes | Stonefast Construction Nig. Ltd |  | 10107299
32 | Purchase of Ten (10 Nos.) 400AH 110VDC Battery Banks for System Maintenance Use. |  | Parastatal Tender Board | Single Sourcing |  | 2014-01-30 | F&A |  | 2014-03-28 | Yes | Tauber Nig. Ltd | 3/28/2014 | 39884523 |  | Six (6) Months | 2014-12-12 | Retention in Process | Six (6) Months | Completed | 100% Completed | Nil | Nil | Equipmentshas been Delivered to TCN CHQ Stores Ojo, Lagos.
33 | Supply of (19Nos.)IPAD AIR, with WI-FI, cellular and internet connections |  | Parastatal Tender Board | Single Sourcing |  | 2014-02-03 | IGR |  | 2014-03-28 | Yes | Profile Technologies Ltd |  | 4588500 | [5 empty] | Completed
34 | Emergency supply of (50 Nos) set of 33KV 1250A, out door HV Disconnector switches. |  | Parastatal Tender Board | Single Sourcing |  |  | F&A |  | 2014-04-14 | Yes | Manek Enterprises | 4/14/2014 | 48195000 |  | Six (6) Months | 4/14/2014 | Nil | Completed | 95% Payment made to Contractor | Nil | Completed | Nil | Equipmentshas been Delivered to TCN CHQ Stores Ojo, Lagos.
35 | Supply of (10 Nos) 400AH VDC Battery Banks , complete with accessories for system use. |  | Parastatal Tender Board | Selective Tendering | 2014-02-10 | 2014-03-24 | MYTO |  | 2014-04-14 | Yes | Eusavour Global Ent. Ltd | 4/14/2014 | 35994000 |  | Six (6) Months | 4/14/2014 | Nil | Completed | 95% Payment made to Contractor | Nil | Completed | Nil | Equipmentshas been Delivered to TCN CHQ Stores Ojo, Lagos.
36 | Printing of application protection guarantee forms | N/A | Parastatal Tender Board | Selective Tendering | 2014-02-10 | 2014-03-18 | System Operation Account | N/A | 2014-04-14 | Yes | Baysic Productions | 2014-04-28 | 7770000 |  | 8 weeks | 2014-04-28 | Nil | 2014-06-27 |  | Completed | Nil | N/A | N/A
37 | Emergency supply of (14 Nos) 33KV 1250A, 31.5KA, SF6 Gas Circuit Breaker for system use. |  | Parastatal Tender Board | Single Sourcing |  | 2013-12-05 | F&A |  | 2014-04-14 | Yes | Arriot Engineering Ltd | 4/14/2014 | 47040000 |  | Six (6) Months | 4/14/2014 | Nil | Completed | 95% Payment made to Contractor | Nil | Nil | Nil | Equipments has been Delivered to TCN CHQ Stores Ojo, Lagos.
38 | TALLY. ERP9. Pay roll development, customization, Installation, implementation and training. |  | Parastatal Tender Board | Single Sourcing |  | 2014-01-22 | F&A |  | 2014-04-14 | Yes | CEA Professional Services Ltd |  | 6825000 |  |  |  | Nil | Completed | 100% completed | Nil | Nil | Nil | Materials has been Delivered to TCN CHQ Stores Ojo, Lagos.
39 | Supply of Weed Control Chemical for system use. |  | Parastatal Tender Board | Selective Tendering | 2014-02-10 | 2014-03-18 | F&A |  | 2014-04-14 | Yes | Miles Chemicals Nig. Ent. Ltd | 4/14/2014 | 15960000 |  | Six (6) Months | 4/14/2014
40 | Supply and Installation of radio communication facilities at Odukpani and Adiaboh 330KV Substation |  | Parastatal Tender Board | Selective Tendering | 2014-03-14 | 2014-03-18 | System Operation Account |  | 2014-04-14 | yes | Biflek Engineering Serv. Ltd |  | 8998500 |  | 1 month | 30/05/2014 | 8570000 | completed | 100% completed | 100% completed | nil | nil
41 | Supply of (10 Nos) 132KV SF6 Gas Circuit Breaker for system use. |  | Parastatal Tender Board | Selective Tendering | 2014-02-10 | 2014-03-24 | AFDB |  | 2014-04-14 | Yes | Pimtek Nig. Ltd | 4/14/2014 | 49999998 |  | Six (6) Months | 4/14/2014 | Nil | Completed | 95% Payment made to Contractor | nil | nil | nil | Equipments has been Delivered to TCN CHQ Stores Ojo, Lagos.
42 | Emergency Erosion control works on tower 54 Kumbotso - Dakata 330KV Trx. Line |  | Parastatal Tender Board | Single Sourcing |  | 2014-02-17 | F&A |  | 2014-04-14 | Yes | Raps Group Nig. Ltd |  | 62783469
43 | Procurement of critical IT Productivity Toolsto Protect TCN Domain and Data CentreAgainst Interna / External Abuse |  | Parastatal Tender Board | Single Sourcing |  | 2014-02-24 | operational Enhancement fund (OEF) |  | 2014-04-14 | Yes | T-One Technologies Ltd |  | 28027781.25 | [5 empty] | Completed
44 | Provision of Maintenance and Service Support for TCN Network Domain at TCN CHQs Maitama Abuja |  | Parastatal Tender Board | Single Sourcing |  | 2014-03-20 | ICT 2014 Budget |  | 2014-04-14 | Yes | Orshor Technoloy Ltd |  | 10036467 | [5 empty] | Completed
45 | Emergency supply of (15 Nos) 33KV Crompton Greaves circuit breakers for system use |  | Parastatal Tender Board | Single Sourcing |  |  | F&A |  | 2014-04-14 | Yes | Rarities Limited | 4/14/2014 | 50400000 |  | Six (6) Months | 4/14/2014 | 95% Payment made to Contractor | Nil | Completed | Nil | Nil | Nil | Equipments has been Delivered to TCN CHQ Stores Ojo, Lagos.
46 | Repair of Telecomunication Equipment and RTUs in Power Stations and 330KV Substations |  | Parastatal Tender Board | Single Sourcing |  | 2014-04-07 | S/O Imprest Fund |  | 2014-04-14 | Yes | Telemit International Ltd |  | 247061796
47 | Repair of Telecomunication Equipment and RTUs in Power Stations and 330KV Substations |  | Parastatal Tender Board | Single Sourcing |  | 2014-04-07 | S/O Imprest Fund |  | 2014-04-14 | Yes | Telemit International Ltd |  | 248859350
48 | Repair of Telecomunication Equipment and RTUs in Power Stations and 330KV Substations |  | Parastatal Tender Board | Single Sourcing |  | 2014-04-07 | S/O Imprest Fund |  | 2014-04-14 | Yes | Telemit International Ltd |  | 152622696
49 | Fibre Optic Link between RCC Benin, Delta I+IV, Sapele and Aladja |  | Parastatal Tender Board | Single Sourcing |  | 2014-04-07 | S/O Imprest Fund |  | 2014-04-14 | Yes | Telemit International Ltd |  | 7056774.9
50 | Fibre Optic Link between, Sapele and Delta IV. |  | Parastatal Tender Board | Single Sourcing |  | 2014-04-07 | S/O Imprest Fund |  | 2014-04-14 | Yes | Telemit International Ltd |  | 27338283
51 | Fibre Optic Repair between, Ikeja west and Egbin. |  | Parastatal Tender Board | Single Sourcing |  | 2014-04-07 | S/O Imprest Fund |  | 2014-04-14 | Yes | Telemit International Ltd |  | 8575182
52 | Over voltage Protection 70 Locations for chargers |  | Parastatal Tender Board | Single Sourcing |  | 2014-04-07 | S/O Imprest Fund |  | 2014-04-14 | Yes | Telemit International Ltd |  | 33930750
53 | linux and Oracle Training in Oshogbo |  | Parastatal Tender Board | Single Sourcing |  | 2014-04-07 | S/O Imprest Fund |  | 2014-04-14 | Yes | Telemit International Ltd |  | 7928100
54 | RTU Spare Parts |  | Parastatal Tender Board | Single Sourcing |  | 2014-04-07 | S/O Imprest Fund |  | 2014-04-14 | Yes | Telemit International Ltd |  | 46575000
55 | SDH,PLC Spare Parts |  | Parastatal Tender Board | Single Sourcing |  | 2014-04-07 | S/O Imprest Fund |  | 2014-04-14 | Yes | Telemit International Ltd |  | 92971543
56 | Radio Repair (US) |  | Parastatal Tender Board | Single Sourcing |  | 2014-04-07 | S/O Imprest Fund |  | 2014-04-14 | Yes | Telemit International Ltd |  | 9108000
57 | Emergency Reinforcement of National Electricity Grid - Alagbon Substation |  | Parastatal Tender Board | Single Sourcing |  | 2014-02-20 | AFDB |  | 2014-06-12 | Yes | Sahellian Energy & Integrated Serv. Ltd | 2014-12-06 | 135678950 |  | Six (6) Months | 2014-12-06 | On going | Nil | 15% APG Being Processed | Nil | Nil | Nil | On going
58 | Emergency Erosion of Control works on tower 281 Jebba - Shiroro 330KV Transmission Line. |  | Parastatal Tender Board | Single Sourcing |  |  | IGR |  | 2014-06-12 | Yes | Ubangiji Resources Ltd |  | 76021522
59 | Emergency Erosion of Control works on tower 48 Kano - Kankia 330KV Transmission Line. |  | Parastatal Tender Board | Single Sourcing |  | 2014-01-23 | IGR |  | 2014-06-12 | Yes | Abdul Rasaq S. Musa Nig. Ltd |  | 24952042.5
60 | Provision of Consultancy Services for the New 132KV Line Bays for Naimey at Birnin Kebbi 330/132KV Substation. |  | Parastatal Tender Board | Advert |  |  | NIGELEC |  | 2014-06-12 | Yes | Arcon Engineers / Arcon Offshore Resources |  | 19440000
61 | Reinforcement of Bauchi Substation 60MVA, 132/33kv Transformer and Three (3 No) 33KV feeders. |  | Parastatal Tender Board | Single Sourcing |  | 2014-02-04 | AFDB |  | 2014-06-12 | Yes | Edginton Nigeria Ltd | 2014-12-06 | 85000000 |  | Six (6) Months | 2014-12-06 | On going | Nil | 15% APG Being Processed | Nil | Nil | Nil | On going
62 | Emergency dismantling, removal and transportation of 60MVA 132/33KV (LEEEC MAKE) power transformer main tank and its accessories from Ayede to GTA workshop Ikorodu. |  | Parastatal Tender Board | Single Sourcing |  | 2014-05-06 | FGN 2014 |  | 2014-06-12 | Yes | SAT Power-On Limited |  | 15407700 |  |  |  | Payed Complete | Job Completed | Job Completed | Job Completed | Nil | Nil
63 | Emergency movement of 75MVAR 330KV (Hyosung Made) shunt reactor main tank and its accessories from Osogbo T.S. to Gwagwalada T.S. FCT and cfonstruction of plinth, skidway and extension of access road at Gwagwalada T.S. |  | Parastatal Tender Board | Single Sourcing |  | 2014-05-12 | FGN 2014 |  | 2014-06-12 | Yes | Netland Engineering Ltd. |  | 53734140.08 |  |  |  | Payed Complete | Job Completed | Job Completed | Job Completed | Nil | Nil
64 | Emergency movement of 150MVA 330/132/33KV (Hyosung Made) power transformer main tank ant its accessories from Shiroro T.S. Maiduguri T.S. Borno State. |  | Parastatal Tender Board | Single Sourcing |  | 2014-04-02 | Euro bond |  | 2014-06-12 | Yes | Zeman Engineering and Technical Services Ltd |  | 49875000 |  |  |  | 14962500 | Job Completed | Job Completed | Job Completed | Nil | Nil
65 | Emergency Supply of ten (10 Nos) of 33KV 1250A Sf6 Gas Circuit Breakers for System Maintenance. |  | Parastatal Tender Board | Single Sourcing |  | 2013-12-17 | IGR |  | 2014-06-12 | Yes | Michi Ventures and Services Ltd | 2014-12-06 | 33600000 |  | Six (6) Months | 10/22/2014 | 100% Made to Contractor | Six (6) Months | Completed | 100% Completed | Nil | Nil | Equipments has been Delivered to TCN CHQ Stores Ojo, Lagos.
66 | Upgrade of Internet links and Provision of wide area connectivity in SNCC, RCC Benin and RCC Ikeja West |  | Parastatal Tender Board | Single Sourcing |  | 2014-04-15 | S/O Imprest |  | 2014-06-12 | Yes | NetIT Solutions Ltd. |  | 22115000
67 | Preparation of Fixed Asset Regiter for Kaduna and Shiroro Regions |  | Parastatal Tender Board | Single Sourcing |  | 2014-04-25 | IGR |  | 2014-06-12 | Yes | Mega Heights Nigeria Ltd. |  | 44824920
68 | 2nd Benin Onitsha 330kv Single Circuit Transmission Line |  | Parastatal Tender Board | Single Sourcing |  | 2013-08-10 | Contingency fund |  | 2014-06-12 | Yes | Dextron Engineering Ltd. |  | 61293043 | 73969.65
69 | Emergency Reinforcement of National Electricity Grid; Construction of outdoor switch gear at Oworonshoki Substation |  | Parastatal Tender Board | Single Sourcing |  | 2014-02-04 | AFDB |  | 2014-06-12 | Yes | Edginton Nigeria Ltd |  | 160000000
70 | Renovation of Port harcourt (Main) T/S Control Room Building at Port Harcourt, River State. | 2013-06-26 | Parastatal Tender Board | Notice Board Advert |  | 2013-11-14 | S/O Imprest |  | 2014-06-12 | Yes | ANSI Ventures |  | 14071459
71 | Emergency Block Wall fencing of New Haven 330/132/33KV Sub-station Enugu |  | Parastatal Tender Board | Single Sourcing |  | 2014-02-20 | IGR |  | 2014-06-12 | Yes | Striving Links Ltd |  | 32223583.35
72 | Reinforcement of Afam TS with 1X150MVA, 330/132/33KV, Power Transformer and Cdontruction of Afam IV to Afam 1, 132KV D/C Line |  | Parastatal Tender Board | 2009 Advert |  | 2014-01-06 | Euro bond |  | 2014-06-12 | Yes | Taleveras Group |  | 101978710
73 | Emergency Erosion Control Works on Tower 12 Ganmo - Jebba 330KV Line (Turn in Turn out) Line at Ganmo Works Centre |  | Parastatal Tender Board | Single Sourcing |  | 2014-06-05 | IGR |  | 2014-06-12 | Yes | Safer Project Ltd |  | 31298022
74 | Repair/Refurbishment of defective 60 MVA 132/33 (LEEC Made) power Transformer at Ayede Transmissin Substation. |  | Parastatal Tender Board | Single Sourcing |  |  | FGN 2014 |  | 2014-06-12 | Yes | GTA Engineering Nig Ltd |  | 21734999 |  |  |  | Invoice wiyh MGT ACCT for Payment | Job Completed | Job Completed | Job Completed | Nil | Nil
75 | Emergency Removal and relocation of burnt 150MVA 330/132/33KV (TBEA Made) Power Transformer Main tank to a distance of about 180 metre within Osogbo TS and relocation of New 150MVA 330/132/33KV (Crompton Greaves Made) Power Transformer Main tank to a distance of about 160 metres from its new plinth to 4T1 Plinth within Osogbo TS |  | Parastatal Tender Board | Single Sourcing |  |  | FGN 2014 |  | 2014-06-12 | Yes | Netland Engineering Ltd. |  | 44348700 |  |  |  | Payed Complete | Job Completed | Job Completed | Job Completed | Nil | Nil
76 | supply and installation of "POWER PATCH" oil and gas solution for onitsha and Oji River Transformer |  | Parastatal Tender Board | Single Sourcing |  |  | FGN 2014 |  | 2014-06-12 | Yes | MMT INTEGRATED SERVICES LTD |  | 30131640
77 | Construction of Bauchi Transmission Regional Office Variation Claims |  | Parastatal Tender Board | Variation Claim |  | 2014-03-31 | F&A |  | 2014-08-08 | Yes | Dans Associates. |  | 9125067
78 | Purchase of Toyota Corolla cars for System Operation AGM |  | Parastatal Tender Board | Selective Tendering | 2014-06-23 | 2014-06-26 | System Operation Imprest |  | 2014-08-08 | Yes | Autocorp Automobiles Ltd |  | 44232300
79 | Construction of Enugu Transmission Regional Headquarters Building. Variation Claim. |  | Parastatal Tender Board | Variation Claim |  | 2014-03-18 | F&A |  | 2014-08-08 | Yes | Ayolex Investment Ltd |  | 7632707.41
80 | Approval for the Purcahse of (Fifty) 50 Nos 33KV Isolators |  | Parastatal Tender Board | Repeat Procurement | 2012-02-09 | 2014-05-19 | AFDB |  | 2014-08-22 | Yes | incomtel (Nig.) Ltd | 10/31/2014 | 6993000 | 248940 | Six (6) Months | 10/31/2014 | 15% APG |  | Nil | Nil | Nil | Nil | LC open for APG
81 | Supply of 8 Nos 132KV SF6Gas Circuit Breakers |  | Parastatal Tender Board | Selective Tendering | 2014-05-23 | 2014-06-25 | AFDB |  | 2014-08-22 | Yes | Mobank Services Ltd | 8/22/2014 | 45066000 |  | Six (6) Months | 10/15/2014 | 100% Made to Contractor | Six (6) Months | Completed | 100% Completed | Nil | Nil | Equipments has been Delivered to TCN CHQ Stores Ojo, Lagos.
82 | Supply of 16MM2x4 amoured Cable for system Maintenance. |  | Parastatal Tender Board | Selective Tendering | 2014-05-23 | 2014-06-26 | IGR |  | 2014-08-22 | Yes | Vanchok Ltd | 8/22/2014 | 21525000 |  | Six (6) Months | 01/28/2015 | Nil | Six (6) Months | On Going | On Going | Nil | Nil | Equipments has been Delivered to TCN CHQ Stores Ojo, Lagos.
83 | Maintenance Support for TCN Virtual / VMWare Infrastructure proposal from T-One Technologies Ltd. |  | Parastatal Tender Board | Single Sourcing |  | 2014-05-27 | TSP & SO |  | 2014-08-22 | Yes | T -One Technologies Ltd |  | 49342115 | [5 empty] | On Going
84 | Movement of materials from Ojo store, Lagos to Apo Transmission Station Abuja |  | Parastatal Tender Board | Single Sourcing |  | 2014-05-21 | FGN 2014 Appropriation |  | 2014-08-22 | Yes | Ohms Sources and Systems Ltd | 8/22/2014 | 6800000 |  | Six (6) Months | 10/28/2015 | Nil | Six (6) Months | Materials have been moved from TCN Stores Ojo Lagos to Apo Transmission Sub-Station inj Abuja | 100% Completed | Nil | Nil | Materials have been moved from TCN Stores Ojo Lagos to Apo Transmission Sub-Station inj Abuja. Contactor's Invoice in Progress
85 | Supply of 2000mtrs each of 240mm2 and 95mm2 X 4 core Armoured Power Cable For System Maintenance |  | Parastatal Tender Board | Selective Tendering | 2014-06-23 | 2014-06-26 | FGN 2014 Appropriation |  | 2014-08-22 | Yes | Striving Link Ltd |  | 49876050 |  | Six (6) Months | 10/15/2014 | 95% Payment made to Contractor | Six (6) Months | Completed | 100% Completed | Nil | Nil | Materials have been moved from TCN Stores Ojo Lagos to Apo Transmission Sub-Station inj Abuja. 5% Retention being Processed.
86 | construction of Enugu 330/132KV Transmission Sub Region Administraive Block Office |  | Parastatal Tender Board | Selective Tendering | 2014-01-09 | 2014-01-14 |  |  | 2014-08-22 | Yes | Janco Resources Ltd |  | 106028567.35
87 | Mechanized Trace of Some Critical 132KV Transmission Line in order to fast track the Trace of Port Harcourt Region:- Alaoji - Owerri 132KV Line. (1 - 174) |  | Parastatal Tender Board | Selective Tendering | 2014-06-05 | 2014-06-20 | Optn Electrify Nig. Intervention Fund |  | 2014-08-22 | Yes | Tariowei Construction Nig. Ltd | 29th october 2014 | 8347500 |  | 3 months | 29th october 2014 |  | nil | 2015-07-15 | 100 | completed | nil | nil
88 | Mechanized Trace of Some Critical 132KV Transmission Line in order to fast track the Trace of Port Harcourt Region:- Owerri - Ahoada 132KV Line. (1 - 219) |  | Parastatal Tender Board | Selective Tendering | 2014-06-05 | 2014-06-20 | Optn Electrify Nig. Intervention Fund |  | 2014-08-22 | Yes | Swanak Nig. Ltd | 29th october 2014 | 12757500 |  | 3 months | 29th october 2014 |  | nil | 2015-07-15 | 80 |  | nil | nil
89 | Mechanized Trace of Some Critical 132KV Transmission Line in order to fast track the Trace of Port Harcourt Region:- Ahoada - Yenagoa 132KV Line. (1 - 140) |  | Parastatal Tender Board | Selective Tendering | 2014-06-05 | 2014-06-20 | Optn Electrify Nig. Intervention Fund |  | 2014-08-22 | Yes | Coastline Project Ltd | 13th February 2015 | 10216500 |  | 3 months | 13th February 2015 |  | nil | 2015-07-15 | 80 | 80 | nil | nil
90 | Mechanized Trace of Some Critical 132KV Transmission Line in order to fast track the Trace of Port Harcourt Region:- Onitsha - Oji River 132KV Line. (1 - 83) |  | Parastatal Tender Board | Selective Tendering | 2014-06-05 | 2014-06-20 | Optn Electrify Nig. Intervention Fund |  | 2014-08-22 | Yes | Jubic Joe Investment Ltd | 21st October 2014 | 4221000 |  | 3 months | 21st October 2014 |  | nil | 2015-07-15 | 80 | 80 | nil | nil
91 | Mechanized Trace of Some Critical 132KV Transmission Line in order to fast track the Trace of Port Harcourt Region:- Onitsha - Oji River 132KV Line. (83 - 174) |  | Parastatal Tender Board | Selective Tendering | 2014-06-05 | 2014-06-20 | Optn Electrify Nig. Intervention Fund |  | 2014-08-22 | Yes | Miki-Mez Engineering Ltd | 6th November 2014 | 4567500 |  | 3 months | 6th November 2014 |  | nil | 2015-07-15 | 80 | 80 | nil | nil
92 | Purchase of 6,000Kg Blue Silica Gel for Transformer Maintenance. |  | Parastatal Tender Board | Selective Tendering | 2014-05-23 | 2014-08-19 | FGN Appropriation |  | 2014-10-16 | Yes | Power System Advantage Int,l Ltd | 10/16/2014 | 14476170 |  | Six (6) Months | May, 2015 |  | on-going |  |  | nil | nil
93 | Approval Request for additionalworks at hadejia and kontagora substation in the Reinforcement of Hadejia, Katsina and Kontagora 132/33KV Substations with 1x6oMVA, 132/33KV Transformers each and associated switch gears. Contract Variation |  | Parastatal Tender Board | Variation Claim |  | 2014-07-10 | FGN Appropriation |  | 2014-10-16 | Yes | Junot construction Ltd |  | 50877330
94 | Transportation of Composite Insulators To Kainji and Gusau |  | Parastatal Tender Board | Selective Tendering | 23rd May 2014 | 2014-08-13 | 2009 Power intervention Fund |  | 2014-10-16 | Yes | Oak Instrument Nig. Ltd | 2014-12-24 | 13640000 |  | 3 months | nil | nil | nil | nil | nil | nil | nil | nil
95 | Purchase of 8Nos Set of 400AH Battery Bank for System Maintenance Use.. |  | Parastatal Tender Board | Selective Tendering | 2014-08-22 | 2014-08-27 | FGN Appropriation |  | 2014-10-16 | Yes | Abdulrazaq S. Musa Ltd | 10/16/2014 | 28375200 |  | Six (6) Months | 15th December 2014 | nil | 100% Payment made to Contractor | nil | completed | nil | nil | Material have been Delivered to TCN CHQ Stores Ojo, Lagos.
96 | Supply of 9Nos 132KV SF6 Gas Circuit Breaker for System Use |  | Parastatal Tender Board | Selective Tendering | 2014-06-23 | 2014-06-26 | AFDB |  | 2014-10-16 | Yes | Dace Projects Ltd | 10/16/2014 | 47430989.6 |  | Six (6) Months | 12th December 2014 | nil | 100% Payment made to Contractor | nil | completed | nil | nil | Material have been Delivered to TCN CHQ Stores Ojo, Lagos.
97 | Purchase of 30 sets, 2000(AMPS) 33KV Centre Break Isolator for system Maintenance |  | Parastatal Tender Board | Selective Tendering | 2014-08-22 | 2014-08-26 | AFDB |  | 2014-10-16 | Yes | Oke-Odu Nig. Co. Ltd | 10/16/2014 | 37800000 |  | Six (6) Months | 15th December 2014 | nil | 100% Payment made to Contractor | nil | completed | nil | nil | Material have been Delivered to TCN CHQ Stores Ojo, Lagos.
98 | Supply of 1000M of 500MM2X1 CORE 33KV XLPE Armoured Power Cables for System Maintenance at Owerri |  | Parastatal Tender Board | Selective Tendering | 2014-08-22 | 2014-08-26 | F&A |  | 2014-10-16 | Yes | SoarHigh Integrated Service Ltd | 10/16/2014 | 21472500 |  | Six (6) Months | 15th December 2014 | nil | nil | nil | nil | nil | nil | Contractor is yet to Supply
99 | Sealing of Oil Leakage on 5Nos Power Transformers in Enugu Sub-Region |  | Parastatal Tender Board | Selective Tendering | 2014-08-22 | 2014-08-25 | F&A |  | 2014-10-16 | Yes | Power accessories & Works Ltd | 10/16/2014 | 40572250 |  | Six (6) Months | 12th December 2014 | Completed | nil | nil | Completed | nil | nil | Contractor's Invoice in Progres
100 | Supply of 9Nos 132KV SF6 Gas Circuit Breaker for Maitenance |  | Parastatal Tender Board | Selective Tendering | 2014-08-22 | 2014-08-25 | AFDB |  | 2014-10-16 | Yes | Arriot Enginrring ltd | 10/16/2014 | 49424255 |  | Six (6) Months | 12th December 2014 | nil | nil | nil | nil | nil | nil | nil
101 | Suply of 29Nos Coils, Manila Ropes for system Maintenance use |  | Parastatal Tender Board | Selective Tendering | 8/22/14 | 8/27/14 | FGN Appropriation 2014 |  | 2014-10-16 | Yes | Vinosa Ind. (Nig) Ltd | 2015-12-15 | 9896250 |  | 6 months | nil | nil |  | completed | completed |  | nil | nil
102 | Supply of 450 Drums of Transformer Oil for system Maintenance use |  | Parastatal Tender Board | Selective Tendering | 22nd August 2014 | 2014-08-27 | FGN Appropriation 2014 |  | 2014-10-16 | Yes | H & X Limited | 10/16/2014 | 49612500 |  | 6 months | 27th February 2015 | Completed | nil | nil | Completed | nil | nil | Contractor's Invoice in Progres
103 | Provision of CCTV for Abuja Sub - Region Katampe 330/132/33KV Sub-Station |  | Parastatal Tender Board | Selective Tendering | 2014-08-22 | 2014-09-09 | IGR |  | 2014-10-16 | Yes | Nelson -C-Strabek Eng. Serv. Ltd | 10/16/2014 | 18129300 |  | 6 months | 12th December 2014 | Completed | nil | nil | Completed | nil | nil | Contractor's Invoice in Progres
104 | construction of Ajaokuts 330/132KV Transmission Administraive Block Office |  | Parastatal Tender Board | Notice Board Advert | 2014-01-09 |  | FGN Appropriation 2014 |  | 2014-10-16 | Yes | Base san Ventures Ltd |  | 101064631.75
105 | Preparation of Fixed Assets Register for Enugu and Oshogbo Region |  | Parastatal Tender Board | Selective Tendering |  | 2014-08-15 | IGR |  | 2014-10-16 | Yes | Pomanep Micro Services Ltd |  | 40830950
106 | Supply of 14Nos 132KV SF6 Gas Circuit Breaker for System Use |  | Parastatal Tender Board | Selective Tendering | 2014-09-23 | 2014-10-10 | FGN Appropriation 2014 |  | 2014-10-16 | Yes | Frankdel Nig. Ltd | 10/16/2014 | 46746000 |  | 6 months | 12th December 2014 | Completed | nil | nil | Completed | nil | nil | Contractor's Invoice in Progres
107 | Rehabilitation of 4 Nos Collapsed Towers Tegina - Kontagora 132KV SC Transmission Line |  | Parastatal Tender Board | Selective Tendering |  | 2014-10-14 | IGR |  | 2014-11-28 | emergency | Energo Nig. Ltd | 2015-01-15 | 88394826.98 |  | 60days | completed |  | completed |  | completed | completed | nil | nil
108 | Construction / Diversion of colapsed Tower No. 48, 49, &51 on Tegina - Kontagora 132KV SC Transmission Line |  | Parastatal Tender Board | Single Sourcing |  | 2014-09-25 | IGR |  | 2014-11-28 | Yes | Raps Nigeria Ltd | 2015-01-01 | 47494860 |  | 2weeks | completed |  | completed |  | completed | completed | nil | nil
109 | Procurement of 10Nos 110VDC 200AH Battery Bank for system Use |  | Parastatal Tender Board | Selective Tendering | 2014-09-23 | 2014-10-10 | FGN Appropriation 2014 |  | 2014-11-28 | Yes | Pimtek Nig. Ltd | 11/28/2014 | 23892750 |  | 6 months | 15th January 2015 | Nil | Nil | Nil | On going | On going | nil | On going
110 | Emergency Movement of 100MVA 132/33KV (Speco Made) Power Transformer from Ikeja West TS Lagos to Alimosho TS Lagos and Relocation of defective 1No. 60MVA 132/33KV (LEEEC Made) Power Transformer main tank to a safe place within the switch yard at Alimosho TS |  | Parastatal Tender Board | Single Sourcing |  | 2014-09-03 | FGN Appropriation 2014 |  | 2014-11-28 | Yes | Baltic air, Cargo & Maritime Serv. Ltd |  | 19235475 |  |  |  | Payed Complete | Job Completed | Job Completed | Job Completed | Nil | Nil
111 | Purchase of 100Nos SF6 Gas in 40Kg cylinders for system Maintenance. |  | Parastatal Tender Board | Selective Tendering | 2014-09-23 | 2014-10-09 | FGN Appropriation 2014 |  | 2014-11-28 | Yes | Ginan Nigeria Ltd | 11/28/2014 | 27667500 |  | 6 months | 20th January 2015 | Nil | Nil | On going | Nil | Nil | Nil | On going
112 | Purchase of 5000 Litres Round - up- Mosanto Herbicide Chemical for system Maintenance. |  | Parastatal Tender Board | Selective Tendering | 2014-09-23 | 2014-10-09 | FGN Appropriation 2014 |  | 2014-11-28 | Yes | Vinjosco Int'l Ltd | 11/28/2014 | 13702500 |  | 6 months | 13th January 2015 | Nil | Nil | On going | Nil | Nil | Nil | On going
113 | Procurement of 7Nos 132KV Gas Circuit Breaker for system Use |  | Parastatal Tender Board | Selective Tendering | 9/23/14 | 10/14/14 | FGN Appropriation 2014 |  | 2014-11-28 | Yes | Mobank Serv. Ltd | 12/28/2014 | 39432750 |  | 6 months | 31st December 2014 | Nil | Nil | Nil | Nil | Nil | Nil | Nil
114 | Urgent Rehabilitation of GM Trx. Shiroro Region Office, Store/Warehouse and the Guest House damaged by Windstorm. |  | Parastatal Tender Board | Selective Tendering |  |  |  |  | 2014-11-28 | Yes | G. N. Ikechukwu Nig. Ent. |  | 8608430.25
115 | Supply, installation and Commissioning of Multi Functional Printer(MFP)in TCN |  | Parastatal Tender Board | Selective Tendering | 2014-09-23 | 2014-10-09 | FGN 2014 Appropriation |  | 2014-11-28 | Yes | ZMJ Technologies Ltd |  | 74812500 | [5 empty] | On Going
116 | Purchase of Desktop Computer Set & Accessories for use in TSP Sector |  | Parastatal Tender Board | Selective Tendering |  | 2014-09-02 | FGN 2014 Appropriation |  | 2014-11-28 | Yes | Lesttat Nig Ltd |  | 5684700 | [5 empty] | Completed
117 | Purchase of Laptop, Desktop Computer Set, Printers, and other Accessories for use in TSP Sector |  | Parastatal Tender Board | Selective Tendering |  | 2014-11-11 | FGN 2014 Appropriation |  | 2014-11-28 | Yes | striving Link Ltd |  | 3516450 | [5 empty] | Completed
118 | Purchase of Laptop, Desktop Computer Set, Printers, and other Accessories for use in TSP Sector |  | Parastatal Tender Board | Selective Tendering |  | 2014-11-17 | FGN 2014 Appropriation |  | 2014-11-28 | Yes | Ginan Nigeria Ltd |  | 7103250 | [5 empty] | Completed
119 | Design and development of invoice and payment Authorization process software solution for the use of Audit Directorate in TSP |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-25 | FGN 2014 Appropriation |  | 2014-11-28 | Yes | T-One Technologies LTD |  | 58752750 | [5 empty] | On Going
120 | Emergency Erosion Control Works on Tower T306 Jos - Bauchi 132KV Line |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Manisco Holding & Properties Ltd. |  | 3900000
121 | Emergency Erosion Control Works on Tower 252 Jos-Gombe 330KV Line |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Raps Nig. Ltd |  | 20000000
122 | Emergency Erosion Control Works on Tower 317 Gombe-Ashaka-Potiskum 132KV Line |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Valley Lilly Ltd. |  | 25000000
123 | Emergency Erosion Control Works on Tower 117 Gombe-Damaturu 330KV Line |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Jewel Construction & Engineering Services Ltd |  | 15700000
124 | Emergency Erosion Control Works on Tower 116 Gombe-Damaturu 330KV Line |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Jewel Construction & Engineering Services Ltd |  | 40500000
125 | Emergency Erosion Control Works on Tower 115 Gombe-Damaturu 330KV Line |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Happy World Global Options Ltd. |  | 35000000
126 | Emergency Erosion Control Works on Tower 84 Gombe-Damaturu 330KV Line |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Newatuh International Concepts Ltd. |  | 25000000
127 | Emergency Erosion Control Works on Tower 407 Gombe-Yola 330KV Line |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Klent Nig. Ltd |  | 45000000
128 | Emergency Erosion Control Works on Tower 406 Gombe-Yola 330KV Line |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Eusavour Global Enterprises Ltd. |  | 7000000
129 | Emergency Erosion Control Works on Tower 150 Gombe-Yola 330KV Line |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Blue Marina Ltd |  | 55000000
130 | Emergency Erosion Control Works on Tower 238 Gombe-Yola 132KV Line |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | JAFC Best Nig. Ltd |  | 23000000
131 | Emergency Erosion Control Works on Tower 677 Kano-Zaria 132KV Line |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Vanchok Ltd |  | 20710978
132 | Emergency Erosion Control Works on Tower 468 Gusau-Funtua 132KV Line |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Tony Cane Nig. Ltd |  | 37767122.58
133 | Emergency Erosion Control Works on Tower 140 Tegina-Birnin Gwari 132KV TRX Line |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Venture DE Zodac Ltd |  | 50000000
134 | Emergency Erosion control works on tower 34 shiroro-Tegina 134kv TRX Line |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Ramtai Nig ltd |  | 12632734
135 | Emergency Perimeter Wall Fence at 132/33 KV S/S. Omu-Aran Kwara State |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Mobank Services Ltd |  | 45000000
136 | Emergency Erosion Control Works at Katampe Central Area Underground Cable Route |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Comvil Nig. Ltd |  | 2900000
137 | Emergency Re-Gravelling of 132/33 KV T/S at Otukpo, Benue State |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Elkaris Nig. Ltd |  | 13500000
138 | Emergency Re-Gravelling of 132/33 KV T/S at Yandev, Benue State |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Rasdak Company Ltd |  | 11500000
139 | Emergency Landscapping of Ganmo 330/132KV S/Station |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Pimtek Nig. Ltd |  | 66500000
140 | Emergency Expansion Works on Old Yandev 132/33 KV S/S C/Room Benue State |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Base-San Ventures Ltd |  | 28000000
141 | Emergency Erosion Control on Tower 42 and 44 Kainji-Jebba 330kv Line |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Amenco Ltd |  | 15000000
142 | Re-Gravelling of Nkalagu 132/33kv s/s |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Renilla Enterprises |  | 22500000
143 | Proposed wall fence for Ogba 132/33kv S/S |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | African Dev. Co. Ltd |  | 16000000
144 | Additional works at the Enugu TCN Regional headquarters building |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Lordship Services Ltd |  | 8000000
145 | Re-Gravelling of Abakaliki 132/33kv S/S |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Malydia & Co. Ltd |  | 10700000
146 | Proposed wall fence for 132/33kv S/S Nkalagu |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Catsobic Nig. Ltd |  | 38240800
147 | Emergency Erosion Control works on Tower T20 Owerri-Ahoad 132KV Line |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Munoshka Ventures Ltd |  | 45000000
148 | Emergency Erosion Control works on Tower T136 Onitsha-Oji 132KV Line Legs |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Royal –Ritz Nig Ltd |  | 6000000
149 | Provision of Concrete Base for Enugu Sub-Regional dump stock yard |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Kalic Konsultant |  | 22000000
150 | Emergency Erosion control works on tower 156 T4A 330KV Onitsha- Alaoji trx line |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Blue Bird Resources Co.Ltd |  | 55000000
151 | Emergency Erosion control works on tower 157 T4A 330KV Onitsha- Alaoji trx line |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | S & Bros Nig. Ltd |  | 25000000
152 | Emergency block wall fence at Amuwo 132/33kv S/S |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Fairby Int’l Ltd |  | 22000000
153 | Emergency Erosion control works on Tower T24 T4A Benin-Ajaokuta (B11J) 330kv line |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-11-28 | Yes | Maston George |  | 55000000
154 | Erosion Control Works on Tower T458 Zaria-Kano 330KV Line |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-12-04 | Yes | Raps Group Nig. Ltd |  | 55000000
155 | Erosion Control Works on Tower T44 Birnin Kebbi/Niamey 132KV Line |  | Parastatal Tender Board | Single Sourcing |  | 2014-11-14 |  |  | 2014-12-04 | Yes | Maskeem Plus Nig. Ltd |  | 43000000
156 | Purchase of Equipment, Furniture & other office Requirment. |  | Parastatal Tender Board | Selective |  |  | ERP Budget 2014 (CounterpartFund) |  |  | Yes | Tredin Technologies Ltd |  | 7410375
157 | Procurement of 1000 metres of 500mm2 X 1 Core 33KV XLPE Armoured Cable for System Maintanance Use |  | Parastatal Tender Board | Selective |  |  | FGN 2014 Appropriation |  | 2015-01-08 | Yes | AGG DE-AYES Construction Company Ltd | 2015-02-10 | 1050000
158 | Resolution of Oil Leakages on 75MX Reactor at Jebba 330KV Switchyard |  | Parastatal Tender Board | Selective |  |  | FGN 2014 Appropriation |  | 2015-01-08 | Yes | Power Accessories and Works Ltd | 2015-03-30 | 14960000
159 | Procurment of 5 Nos. 110V DC 400AH Battery Bank for System Use |  | Parastatal Tender Board | Selective |  |  | FGN 2014 Appropriation |  |  | Yes | C. Oasis Associates Nig. Ltd. |  | 19090521.5
160 | Installation of Pile Foundation and Erection of collapsed tower T29 on Gombe-Ashaka-Potiskum 132KV Single-Circuit Transmissiuon |  | Parastatal Tender Board | Selective |  |  | IGR |  |  | Yes | Gammon India Ltd |  | 41033404.65
161 | Onitsha-Ifitedunu 132kV DC transmission line. | Done in 2013 |  | Competitve bidding | Done in 2013 | Done in 2013 | 261686649 | Dec. 2013 | Aug. 2014 | yes | Sinotec/CCC Internation Hoint Venture | Yet to be awarded | 1141865028.73 | 5992974.24 | 24 Months | Yet to commence | Nil | Yet to be determine | Yet to commence | 0% | Nil | N/A | Negotiations on going
162 | 2x60MVA, 132/33kV substation at Ifitedunu and 2x132kV line bays extension at Onitsha. | Done in 2013 |  | Competitve bidding | Done in 2013 | Done in 2013 | 289409290 | Dec. 2013 | Aug. 2014 | yes | MBH Power Limited | Aug. 2014 | 1269915395 | 7996436.31 | 24 Months | Yet to commence | Nil | Yet to be determine | Yet to commence | 0% | Nil | N/A | No funds to pay advance for the project to commence
163 | 2x60MVA, 132/33kV substation at Amasiri and 2x132kV line bays extension at Abakaliki substation. | Done in 2013 |  | Selective Tendering | Done in 2013 | Jan. 2014 | 198163324 | May, 2014 | Aug. 2014 | yes | North China Power Engineering and NCEP Nigeria Limited | Aug. 2014 | 551070542.8 | 5557493.78 | 24 Months | Yet to commence | Nil | Yet to be determine | Yet to commence | 0% | Nil | N/A | Advance payment and LC funding being processed
164 | Additional construction of 1x60MVA, 132/33kV transformer to Maiduguri 1x150MVA, 330/132kV substation. | N/A |  | Selective Tendering | N/A | Jan. 2014 |  | Feb. 21, 2014 | Aug. 2014 | N/A | Best abd Crompton Nig. Limited | Aug. 2014 | 208592058.01 | 2250446.72 | 12 Months |  | Nil | Yet to be determine | Yet to commence | 0% | Nil | N/A

## Source1-2
ANALYSIS OF 2014 PROCUREMENT RECORDS SUBMITTED BY PROCURING ENTITIES
SN | PARENT MINISTRY | SN | AGENCIES | No. of Contracts Awarded | Total Contracts Value (NGN) | No. of Contracts with Cert. of "No Objection | Values of Contracts with Cert. of "No Objection" (NGN) | No. of Contracts within MDA's Approval | Values of Contracts within MDA's Approval (NGN) | % No. of Contracts with Cert. of "No Objection" | % No. of Contracts Within MDA's Approval | % Value of Contracts with Cert. of "No Objection" | % value of Contracts Within MDA's Approval | Foreign ($) | Exch Rate ($) | Foreign (€) | Exch Rate (€) | Foreign (£) | Exch Rate (£) | Conversion (NGN)
1 | Presidency | 1 | Bureau of Public Procurement | 27 | 145056353.35 | 0 | 0 | 27 | 145056353.35 | 0 | 100 | 0 | 100
|  | 2 | Office of the Scretary to the Government of the Federation | 25 | 1836172589.55 | 1 | 570167570.7 | 24 | 1266005018.85 | 4 | 96 | 31.052 | 68.948
|  | 3 | Code of Conduct Bureau | 6 | 196951696 | 0 | 0 | 6 | 196951696 | 0 | 100 | 0 | 100
|  | 4 | Infrastructure Concession Regulatory Commission | 12 | 24652491.59 | 0 | 0 | 12 | 24652491.59 | 0 | 100 | 0 | 100
|  | 5 | Federal Road Safety Commission | 15 | 1135192884.59 | 3 | 179812500 | 12 | 955380384.59 | 20 | 80 | 15.8398 | 84.1602
|  | 6 | National Human Right Commission | 33 | 85395162.96 | 0 | 0 | 33 | 85395162.96 | 0 | 100 | 0 | 100
|  | 7 | Pension Transitional Arrangement Directorate | 32 | 803094451 | 0 | 0 | 32 | 803094451 | 0 | 100 | 0 | 100
|  | 8 | NEPAD Nigeria | 22 | 223756814.6 | 0 | 0 | 22 | 223756814.6 | 0 | 100 | 0 | 100
|  |  |  | 172 | 4450272443.64 | 4 | 749980070.7 | 168 | 3700292372.94 | 2.3256 | 97.6744 | 16.8525 | 83.1475
2 | Federal Capital Territory Administration | 9 | Education Secretariat | 68 | 1811006137.87 | 0 | 0 | 68 | 1811006137.87 | 0 | 100 | 0 | 100
|  | 10 | Area Council Services Secretariat | 10 | 53821300 | 0 | 0 | 10 | 53821300 | 0 | 100 | 0 | 100
|  | 11 | Abuja Metropolitan Management Council | 34 | 1321833334.63 | 0 | 0 | 34 | 1321833334.63 | 0 | 100 | 0 | 100
|  | 12 | FCT Archives & History Bureau | 1 | 7045078 | 0 | 0 | 1 | 7045078 | 0 | 100 | 0 | 100
|  | 13 | Agricultural and Rural Development Secretariat | 5 | 433764600 | 0 | 0 | 5 | 433764600 | 0 | 100 | 0 | 100
|  | 14 | FCT Water Board | 6 | 609941877.8 | 0 | 0 | 6 | 609941877.8 | 0 | 100 | 0 | 100
|  | 15 | Security Services Department | 1 | 464996555.32 | 0 | 0 | 1 | 464996555.32 | 0 | 100 | 0 | 100
|  | 16 | Abuja Environmental Protection Board | 1 | 14443548.08 | 0 | 0 | 1 | 14443548.08 | 0 | 100 | 0 | 100
|  | 17 | Social Development Secretariat | 3 | 5267400 | 0 | 0 | 3 | 5267400 | 0 | 100 | 0 | 100
|  | 18 | STDD | 25 | 3136729406.37 | 0 | 0 | 25 | 3136729406.37 | 0 | 100 | 0 | 100
|  | 19 | Federal Capital Development Authority | 17 | 113992854745.48 | 4 | 113320443097.62 | 13 | 672411647.86 | 23.5294 | 76.4706 | 99.4101 | 0.58987
|  | 20 | Department Of FCT Treasury | 2 | 86304750 | 0 | 0 | 2 | 86304750 | 0 | 100 | 0 | 100
|  |  |  | 173 | 121938008733.55 | 4 | 113320443097.62 | 169 | 8617565635.93 | 2.3121 | 97.6879 | 92.9328 | 7.0672
3 | Federal Ministry of Water Resources | 21 | Federal Ministry of Water Resources | 93 | 11716357695.23 | 0 | 0 | 93 | 11716357695.23 | 0 | 100 | 0 | 100
|  | 22 | Cross River Basin Development Authority | 78 | 4136158126.98 | 0 | 0 | 78 | 4136158126.98 | 0 | 100 | 0 | 100
|  | 23 | Hadejia-Jama'are River Basin Development Authority | 110 | 4167280257.12 | 0 | 0 | 110 | 4167280257.12 | 0 | 100 | 0 | 100
|  | 24 | Ogun-Oshun River Basin Development Authority | 58 | 3169907390.93 | 0 | 0 | 58 | 3169907390.93 | 0 | 100 | 0 | 100
|  | 25 | Upper Benue River Basin Development Authoriy | 76 | 4824914958.02 | 0 | 0 | 76 | 4824914958.02 | 0 | 100 | 0 | 100
|  | 26 | Niger Delta River Basin Development Authority | 45 | 1045908675.72 | 0 | 0 | 45 | 1045908675.72 | 0 | 100 | 0 | 100
|  | 27 | Gurara Water Management Authority | 7 | 19992312 | 0 | 0 | 7 | 19992312 | 0 | 100 | 0 | 100
|  | 11 | Benin Owena River Basin Development Authority | 132 | 3672350630.7 | 0 | 0 | 132 | 3672350630.7 | 0% | 100% | 0% | 100%
|  | 12 | Lower Niger River Basin Development Authority | 98 | 1858510806.14 | 0 | 0 | 98 | 1858510806.14 | 0% | 100% | 0% | 100%
|  | 13 | Sokoto Rima River Basin Development Authority | 114 | 4353507698.11 | 0 | 0 | 114 | 4353507698.11 | 0% | 100% | 0% | 100%
|  | 14 | Chad Basin Development Authority | 72 | 1203753521.72 | 0 | 0 | 72 | 1203753521.72 | 0% | 100% | 0% | 100%
|  | 15 | Lower Benue River Basin Development Authority | 157 | 4026117512.11 | 0 | 0 | 157 | 4026117512.11 | 0% | 100% | 0% | 100%
|  | 28 | National Water Resources Institute | 10 | 27335863.55 | 0 | 0 | 10 | 27335863.55 | 0 | 100 | 0 | 100
|  | 29 | Nigeria Hydrological Services Agency | 4 | 127343775 | 0 | 0 | 4 | 127343775 | 0 | 100 | 0 | 100
|  |  |  | 1054 | 44349439223.33 | 0 | 0 | 1054 | 44349439223.33 | 0 | 100 | 0 | 100
4 | Federal Ministry of Aviation | 30 | Federal Airports Authority of Nigeria | 207 | 7344740130.84 | 0 | 0 | 207 | 7344740130.84 | 0 | 100 | 0 | 100
|  | 31 | Nigerian Civil Aviation Authority | 56 | 551875440.3 | 0 | 0 | 56 | 551875440.3 | 0 | 100 | 0 | 100
|  | 1 | Nigerian Metrological Agency | 69 | 1394917402.44 | 0 | 0 | 69 | 1394917402.44 | 0% | 100% | 0% | 100%
|  | 32 | Nigerian College of Aviation Technology | 6 | 6112873273.02 | 3 | 4537873273.02 | 3 | 1575000000 | 50 | 50 | 74.2347 | 25.7653
|  |  |  | 338 | 15404406246.6 | 3 | 4537873273.02 | 335 | 10866532973.58 | 0.88757 | 99.1124 | 29.4583 | 70.5417
5 | Federal Ministry of Interior | 33 | Nigerian Prisons Service | 85 | 2176920783.74 | 0 | 0 | 85 | 2176920783.74 | 0 | 100 | 0 | 100
|  | 34 | Nigeria Immigration Service | 346 | 2885626125.57 | 0 | 0 | 346 | 2885626125.57 | 0 | 100 | 0 | 100
|  | 35 | Nigeria Securty and Civil Defence Corps | 24 | 1246799879.96 | 0 | 0 | 24 | 1246799879.96 | 0 | 100 | 0 | 100
|  |  |  | 455 | 6309346789.27 | 0 | 0 | 455 | 6309346789.27 | 0 | 100 | 0 | 100
6 | Federal Ministry of Science and Technology | 36 | Federal Ministry of Science and Technology | 10 | 53011754.5 | 0 | 0 | 10 | 53011754.5 | 0 | 100 | 0 | 100
|  | 37 | National Board for Technology Incubation | 23 | 283163197.37 | 0 | 0 | 23 | 283163197.37 | 0 | 100 | 0 | 100
|  | 38 | National Office for Technology Acquisition & Promotion | 10 | 44943000 | 0 | 0 | 10 | 44943000 | 0 | 100 | 0 | 100
|  |  |  | 43 | 381117951.87 | 0 | 0 | 43 | 381117951.87 | 0 | 100 | 0 | 100
7 | Federal Ministry of Education | 39 | National Board for Technical Education | 3 | 366680901.75 | 0 | 0 | 3 | 366680901.75 | 0 | 100 | 0 | 100
|  | 40 | National Mathematical Centre | 11 | 129083665.2 | 0 | 0 | 11 | 129083665.2 | 0 | 100 | 0 | 100
|  |  |  | 14 | 495764566.95 | 0 | 0 | 14 | 495764566.95 | 0 | 100 | 0 | 100
8 | Federal Ministry of Works | 41 | Federal Ministry of Works | 35 | 483340194305.1899 | 20 | 469900077214.84 | 15 | 13440117090.3499 | 57.1429 | 42.8571 | 97.2193 | 2.7807
|  | 16 | Federal Road Maintenance Agency | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0%
|  | 17 | Office of the Surveyor-General of the Federation | 144 | 762455459.12 | 0 | 0 | 144 | 762455459.12 | 0% | 100% | 0% | 100%
6 | Federal Ministry of Power | 42 | Nigerian Electricity Regulatory Commission | 104 | 11663816217.94 | 1 | 11236147312.36 | 103 | 427668905.58 | 0.96154 | 99.0385 | 96.3334 | 3.6666
|  | 9 | Electricity Management Services Limited | 38 | 1564417988.96 | 0 | 0 | 38 | 1564417988.96 | 0% | 100% | 0% | 100%
|  | 10 | Transmission Company of Nigeria | 164 | 10323804855.86 | 3 | 4676811111.485 | 161 | 5646993744.375 | 1.829% | 98.17% | 45.3% | 54.7%
10 | Federal Ministry of Environment | 43 | Federal Ministry of Environment | 122 | 4258885861.65 | 0 | 0 | 122 | 4258885861.65 | 0 | 100 | 0 | 100
11 | Federal ministry of Information | 44 | Federal Ministry of Information | 5 | 247511147.45 | 0 | 0 | 5 | 247511147.45 | 0 | 100 | 0 | 100
12 | Ministry of Police Affairs | 45 | Ministry of Police Affairs | 27 | 2269517802 | 0 | 0 | 27 | 2269517802 | 0 | 100 | 0 | 100
3 | Federal Ministry of Health | 3 | National Obstetric Fistula Centre Abakaliki | 8 | 75276577 | 0 | 0 | 8 | 75276577 | 0% | 100% | 0% | 100%
|  | 4 | University of Uyo Teaching Hospital | 2 | 176318567.98 | 0 | 0 | 2 | 176318567.98 | 0% | 100% | 0% | 100%
|  | 5 | Federal Medical Centre Nguru | 20 | 234762708.7 | 0 | 0 | 20 | 234762708.7 | 0% | 100% | 0% | 100%
|  | 46 | Neuropsychiatric Hospital, Aro, Abeokuta | 3 | 126066456.96 | 0 | 0 | 3 | 126066456.96 | 0 | 100 | 0 | 100
15 | Ministry of Defence | 47 | Ministry of Defence | 10 | 2289175615.89 | 0 | 0 | 10 | 2289175615.89 | 0 | 100 | 0 | 100
16 | Federal Ministry of Tourism Culture and National Orientation | 48 | Federal Ministry of Tourism Culture and National Orientation | 14 | 205306689.52 | 0 | 0 | 14 | 205306689.52 | 0 | 100 | 0 | 100
17 | Ministry of Justice | 49 | Ministry of Justice | 9 | 184527656.19 | 0 | 0 | 9 | 184527656.19 | 0 | 100 | 0 | 100
2 | Federal Ministry of Finance | 2 | Investments and Securities Tribunal | 14 | 96422630.75 | 0 | 0 | 14 | 96422630.75 | 0% | 100% | 0% | 100%
| Federal Ministry of Land, Housing & Urban Development | 6 | Federal Ministry of Lands, Housing & Urban Devpt. | 98 | 4071323100.75 | 0 | 0 | 98 | 4071323100.75 | 0% | 100% | 0% | 100%
|  | 50 | Federal Housing Authority | 1 | 23075450 | 0 | 0 | 1 | 23075450 | 0 | 100 | 0 | 100
9 | Federal Ministry of Youth Development | 18 | Federal Ministry of Youth Development | 27 | 1131952368.57 | 0 | 0 | 27 | 1131952368.57 | 0% | 100% | 0% | 100%
10 | ICPC | 19 | ICPC | 3 | 149688361.5 | 0 | 0 | 3 | 149688361.5 | 0% | 100% | 0% | 100%
5 | Federal Ministry of Mines & Steel Devpt. | 8 | Metallurgical Training Institute Onitsha | 3 | 66253675 | 0 | 0 | 3 | 66253675 | 0% | 100% | 0% | 100%
19 | Federal Ministry Of Women Affairs and Social Development | 51 | Federal Ministry Of Women Affairs and Social Development | 15 | 268201692.84 | 0 | 0 | 15 | 268201692.84 | 0 | 100 | 0 | 100
TOTAL |  |  |  | 2594 | 698204634850.84 | 32 | 599744520968.5399 | 2562 | 98460113882.2999 | 1.2336 | 98.7664 | 85.8981 | 14.1019

## FCDA
PROCURING ENTITY: FEDERAL CAPITAL DEVELOPMENT AUTHORITY
MINISTRY: FEDERAL CAPITAL TERRITORY ADMINISTRATION
FINACIAL YEAR: 2014
| BASIC DATA | [8 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVING THRESHOLD | BID OPENING DATE | BID EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AD/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2014 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % COMPLETION AS AT 31/12/2014 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
CAPITAL PROJECTS
1 | Extension of the Inner Southern Expressway (ISEX) from the Southern Parkway (S8/S9) to Ring Road II in the FCC | 21/10/2013 | FEC | 2013-04-11 | Nov., 2013 | 3500000000 | 2014-09-10 | 2014-06-11 | YES | M/s CGC Nigeria Limited | 2014-04-12 | 43458849973.94 | 30 Months |  | NIL | 2017-04-06 |  | N/A | N/A | N/A
2 | Construction of One Service Carriageway (14Km) of Inner Northern Expressway (INEX) from Ring Road III to Ring Road IV (Abuja) Industrial Park | 17/6/2013 | FEC | 17/9/2013 | Oct., 2013 | 1200000000 | 2014-03-10 | 2014-06-11 | YES | M/s Salini Nigeria Limited | 2014-04-12 | 7179322294.15 | 24 Months |  | NIL | 2016-04-12 |  | N/A | N/A | N/A
3 | Provision of Sccess Road and Engineering Infrastructure to Plot 1458 and Adjoining Plots Around Hot 98 FM in Gudu District | 2013-09-09 | FEC | 20/12/2013 | Feb., 2014 | 400000000 | 13/8/2014 | 2014-06-11 | YES | M/s Sageto Limited | 2014-04-12 | 1794778172.88 | 17 Months |  | NIL | 2016-04-05 |  | N/A | N/A | N/A
4 | Provision of Engineering Infrastructure to Kyami District, Zone C | 21/10/2013 | FEC | 2013-04-11 | Nov., 2013 | 6000000000 | 15/10/2014 | 17/11/2014 | YES | M/s Mangrovetech Construction & Engineering Nigeria Limited (Kakatar CE Limited) | 2014-04-12 | 60887492656.65 | 60 Months |  | NIL | 2019-04-12 |  | N/A | N/A | N/A
5 | Provision of Engineering Infrastructure to Plots 3448 - 4356, Asokoro. | 2013-09-09 | MTB | 16/9/2013 | 2014-12-02 | 150000000 | N/A |  | YES | M/s Rockbridge Construction Limited | 29/12/2014 | 612845459.5 | 4 Months |  | NIL | 28/4/2015 |  | N/A | N/A | N/A
RECURRENT PROJECTS
6 | Printing of Security Documents | 14/2/2013 | E.S | NA |  | 4079398 | NA | 15/03/2014 | YES | M/s Fatai Ofania Co. Ltd. | 14/05/2014 | 658240 | 2 Wks | NA | NA | 28/05/2014 | Completed | 100 | NA | NA
7 | Computer Consumables | 26/8/2013 | FCDA/TB | 2013-07-10 | Nov. 2013 | 23581610 | NA | 23/4/20/14 | YES | M/s JFP Williams Nig. Ltd. | 20/05/2014 | 5963650.1 | 6 Wks | NA | NA | 2014-01-17 | Completed | 100 | NA | NA
8 | Computer Consumables | 26/8/2013 | FCDA/TB | 2013-07-10 | Nov, 2013 | 23581610 | NA | 23/4/20/14 | YES | M/s Philip Auto & Company Ltd. | 20/05/2014 | 8170521.64 | 6 Wks | NA | NA | 2014-01-17 | Completed | 100 | NA | NA
9 | Stationaries | 26/8/2013 | FCDA/TB | 2013-07-10 | Nov, 2013 | 197752174 | NA | 19/5/20/14 | YES | M/s Saleeman Nig. Ltd. | 20/05/2014 | 8468000 | 6 Wks | NA | NA | 2014-01-17 | Completed | 100 | NA | NA
10 | Stationaries | 26/8/2013 | FCDA/TB | 2013-07-10 | Nov, 2013 | 19775174 | NA | 19/5/20/14 | YES | M/s Iduoko Ent. Nig. Ltd. | 20/05/2014 | 4800000 | 6 Wks | NA | NA | 2014-01-17 | Completed | 100 | NA | NA
11 | Stationaries | 26/8/2013 | FCDA/TB | 2013-07-10 | Nov, 2013 | 19775174 | NA | 19/5/20/14 | YES | M/s Kaosisochukwu Int. Concept. | 20/05/2014 | 3589955 | 6 Wks | NA | NA | 2014-01-17 | Completed | 100 | NA | NA
12 | Stationaries | 26/8/2013 | FCDA/TB | 2013-07-10 | Nov, 2013 | 19775174 | NA | 19/5/20/14 | YES | M/s Elvis Digital World Ltd. | 20/05/2014 | 4862550 | 6 Wks | NA | NA | 2014-01-17 | Completed | 100 | NA | NA
13 | Printing of Non-Security Documents | 26/8/2013 | E.S | NA | Nov, 2013 | 4073398 | NA | 23/4/20/14 | YES | M/s ABC Iyas Nig. Ltd. | 20/05/2014 | 1950375 | 6 Wks | NA | NA | 2014-01-17 | Completed | 100 | NA | NA
14 | Printing of Non-Security Documents | 26/8/2013 | FCDA/TB | 2013-07-10 | Nov, 2013 | 4073398 | NA | 23/4/20/14 | YES | M/s Rabimoh Agaie Nig. Ltd. | 20/05/2014 | 2986278.75 | 6 Wks | NA | NA | 2014-01-17 | Completed | 100 | NA | NA
15 | Office Equipment | 26/8/2013 | E.S | NA |  | 5000000 | NA | 2014-03-09 | YES | M/s George Henry Nig. Ltd. | 2014-03-09 | 507500 | 2Wks | NA | NA | 17/09/2014 | Completed | 100 | NA | NA
16 | Isurance cover for FCDA Corp. H/Quarter | 26/8/2013 | FCDA/TB | 2013-09-09 | Oct, 2013 | 28050000 | NA | 19/5/2014 | YES | M/s Fin Insurance Co. Ltd. | 20/5/2014 | 15171752.95 | 12 Wks | NA | NA | 2014-12-18 | Completed | 100 | NA | NA
17 | Maintenance of Office Equipments | 26/8/2013 | E.S | NA |  | 5954600 | NA | 27/8/2014 | YES | M/s Xerox A.S. Nig. Ltd. | 28/8/2014 | 2437364.92 | 2 Wks | NA | NA | 2014-11-09 | Completed | 100 | NA | NA
| TOTAL | [10 empty] | 113992854745.48
1794778172.88
7179322294.15
43458849973.94
60887492656.65
113320443097.62
672411647.86