## AIB
Ministry/Department/Agency: Accident Investigation Bureau
Budget Year: 2015
|  | Basic Data | [7 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [8 empty] | Contract Implementation - Consultancy
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2.2 - 2 weeks | 3 weeks | 2 - 4 weeks | 2 weeks | 4 - 6 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
Preventive Monitoring of facilities and compliance to safety recommendations (On-going accident investigations) | Plan |  |  |  | NCB |  |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Actual

## AIRBD
Ministry/Department/Agency: Anambra-Imo River Basin Development Authority
Budget Year: 2015
|  | Basic Data | [7 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  |  |  |  | Contract Implementation - Works
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Plan vs Actual
AROCHUKWU WATER SUPPLY SCHEME | Plan | AIRBDA/13/LOTC2/03 |  | BEME | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | NA | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 |  |  | 14/03/14 | 25/04/14 | 28/04/14 - 12/05/14 | 13/05/14 - 20/05/14 | NA | 21/05/14 - 4/06/14 | 5/06/14 - 12/06/14
Actual

## BPP
Ministry/Department/Agency: Bureau of Public Procurement
Budget Year: 2015
|  | Basic Data | [7 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  |  |  |  | Contract Implementation - Works
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Plan vs Actual
Maintenance of Motor Vehicles/Transport Equipments | Plan |  |  |  | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 13/01/14 - 17/01/14 | 20/01/14 - 24/01/14 | 3/02/14 - 3/03/14 | 4/03/14 - 14/03/14 | 17/03/14 - 31/03/14 | 31/03/14 - 18/04/14 | 21/04/14 - 2/06/14 | 2/06/14 | 2/06/14 | 2/06/14 - 20/06/14 | 23/06/14 - 18/07/14 | NA | 21/07/14 - 25/07/14 | 28/07/14 - 28/07/14 | NA | 31/07/15 | 3/08/15
| Actual | [8 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Maintenance of Office Furniture | Plan |  |  |  | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID
Actual
Maintenance of Office Building/Residential Qtrs | Plan |  |  | Lump Sum |  | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 19/03/14 - 28/03/14 | 28/03/14 - 3/04/14 | NA | NA | NA |  |  | 3/04/14 | 15/05/14 | 15/05/14 - 29/05/14 | 29/05/14 - 13/06/14 | NA | 13/06/14 - 20/06/14 | 20/06/14 - 30/06/14
Actual
Maintenance of Office/IT Equipments | Plan |  |  | Lump Sum |  | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 7/01/14 - 17/01/14 | 20/01/14 - 22/01/14 | 27/01/14 - 7/02/14 | 10/02/14 - 14/02/14 | 17/02/14 - 19/02/14 |  |  | 10/03/14 | 4/04/14 | 7/04/14 - 18/04/14 | 21/04/14 - 25/04/14 | 28/04/14 - 2/05/14 | 5/05/14 - 9/05/14 | 12/05/14 - 15/05/14
Actual
Maintenance of Plants/Generators | Plan |  |  | Lump Sum |  | Accounting Officer: Permanent Secretary | LERB - LOWEST EVALUATED RESPONSIVE BID
Actual
Other Maintenance Services | Plan |  |  | Lump Sum |  | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID
Actual

## CBDA
| Ministry/Department/Agency: | CHAD BASIN DEVELOPMENT AUTHORITY |  |  |  |  | THE TIME LINE IS TO BE COMPARED WITH THE COUNCILS APPROVAL
| Budgetary Year: 2015 | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
| Desk Officer/Contact #: |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation | [6 empty] | Contract Implementation
S/N | Project Description* | Package Number | Lot Number | Procurement Method | Pre-qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Plan vs. Actual | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
| Norm Duration of Proc Steps |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 4 wks | 2 wks | 2 wks | 1 - 2 wks | Plan | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
I | GORA IRRIGATION SCHEME |  | B1 | [11 empty] | Plan
Actual
1 | Supply of Consumable items to commission CASIDA water plant to commence production | B1 (I) |  | National Competitive Bidding | Pre-qualification | PTB | Plan | 29th January - 12th February, 2015 | 13th - 26th February, 2015 | 27th February - 13th March, 2015 | 14th March - 24th April, 2015 | 24th April, 2015 | 24th April - 7th May, 2015 | 7th - 21st May, 2015 | Plan | NA | 22nd May - 5th June, 2015 | 12th June, 2015 | 12th - 26th June, 2015 | 90days | 26th June - 26th September, 2015
[7 empty] | Actual | [7 empty] | Actual
2 | Supply of 33,000litres of AGO & Lubricants | B1 (II) |  | National Competitive Bidding | Pre-qualification | PTB | Plan | 29th January - 12th February, 2015 | 13th - 26th February, 2015 | 27th February - 13th March, 2015 | 14th March - 24th April, 2015 | 24th April, 2015 | 24th April - 7th May, 2015 | 7th - 21st May, 2015 | Plan | NA | 22nd May - 5th June, 2015 | 12th June, 2015 | 12th - 26th June, 2015 | 90days | 26th June - 26th September, 2015
[7 empty] | Actual | [7 empty] | Actual
II | GARIN GADA / NGALDA IRRIGATION SCHEME |  | B2 |  |  |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
1 | Supply of furnitures for Gashua Irrigation Scheme | B2 (I) |  | National Competitive Bidding | Pre-qualification | PTB | Plan | 29th January - 12th February, 2015 | 13th - 26th February, 2015 | 27th February - 13th March, 2015 | 14th March - 24th April, 2015 | 24th April, 2015 | 24th April - 7th May, 2015 | 7th - 21st May, 2015 | Plan | NA | 22nd May - 5th June, 2015 | 12th June, 2015 | 12th - 26th June, 2015 | 90days | 26th June - 26th September, 2015
[7 empty] | Actual | [7 empty] | Actual
III | MICHIKA IRRIGATION SCHEME |  | B3 |  |  |  | Plan
Actual
1 | Supply of 33,000litres of AGO | B3 (I) |  | National Competitive Bidding | Pre-qualification | PTB | Plan | 29th January - 12th February, 2015 | 13th - 26th February, 2015 | 27th February - 13th March, 2015 | 14th March - 24th April, 2015 | 24th April, 2015 | 24th April - 7th May, 2015 | 7th - 21st May, 2015 | Plan | NA | 22nd May - 5th June, 2015 | 12th June, 2015 | 12th - 26th June, 2015 | 90days | 26th June - 26th September, 2015
[7 empty] | Actual | [7 empty] | Actual
2 | Supply of Lubricants | B3 (II) |  | National Competitive Bidding | Pre-qualification | PTB | Plan | 29th January - 12th February, 2015 | 13th - 26th February, 2015 | 27th February - 13th March, 2015 | 14th March - 24th April, 2015 | 24th April, 2015 | 24th April - 7th May, 2015 | 7th - 21st May, 2015 | Plan | NA | 22nd May - 5th June, 2015 | 12th June, 2015 | 12th - 26th June, 2015 | 90days | 26th June - 26th September, 2015
[7 empty] | Actual | [7 empty] | Actual
IV | GARIN GADA / NGALDA IRRIGATION SCHEME |  | B4
1 | Supply of 18,000litres of AGO and Lubricants | B4 (I) |  | National Competitive Bidding | Pre-qualification | PTB | Plan | 29th January - 12th February, 2015 | 13th - 26th February, 2015 | 27th February - 13th March, 2015 | 14th March - 24th April, 2015 | 24th April, 2015 | 24th April - 7th May, 2015 | 7th - 21st May, 2015 | Plan | NA | 22nd May - 5th June, 2015 | 12th June, 2015 | 12th - 26th June, 2015 | 90days | 26th June - 26th September, 2015
[7 empty] | Actual | [7 empty] | Actual
V | JERE RICE BOWL |  | B5 |  |  |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
1 | Supply of Hatchery Equipment fish feeds & Materials | B5 (I) |  | National Competitive Bidding | Pre-qualification | PTB | Plan | 29th January - 12th February, 2015 | 13th - 26th February, 2015 | 27th February - 13th March, 2015 | 14th March - 24th April, 2015 | 24th April, 2015 | 24th April - 7th May, 2015 | 7th - 21st May, 2015 | Plan | NA | 22nd May - 5th June, 2015 | 12th June, 2015 | 12th - 26th June, 2015 | 90days | 26th June - 26th September, 2015
[7 empty] | Actual | [7 empty] | Actual
VI | HYDROMET |  | B6
1 | Supply of 3nos. Laptop Computers & Softwares | B6 (II) |  | National Competitive Bidding | Pre-qualification | PTB | Plan | 29th January - 12th February, 2015 | 13th - 26th February, 2015 | 27th February - 13th March, 2015 | 14th March - 24th April, 2015 | 24th April, 2015 | 24th April - 7th May, 2015 | 7th - 21st May, 2015 | Plan | NA | 22nd May - 5th June, 2015 | 12th June, 2015 | 12th - 26th June, 2015 | 90days | 26th June - 26th September, 2015
Actual
VII | BAGA POLDER PROJECT |  | B7 |  |  |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
1 | Procurement of Welding Machine, Repairs of Plants & Transport Vehicles | B7 (I) |  | National Competitive Bidding | Pre-qualification | PTB | Plan | 29th January - 12th February, 2015 | 13th - 26th February, 2015 | 27th February - 13th March, 2015 | 14th March - 24th April, 2015 | 24th April, 2015 | 24th April - 7th May, 2015 | 7th - 21st May, 2015 | Plan | NA | 22nd May - 5th June, 2015 | 12th June, 2015 | 12th - 26th June, 2015 | 90days | 26th June - 26th September, 2015
[7 empty] | Actual | [7 empty] | Actual
2 | Supply of AGO & Lubricants | B7 (II) |  | National Competitive Bidding | Pre-qualification | PTB | Plan | 29th January - 12th February, 2015 | 13th - 26th February, 2015 | 27th February - 13th March, 2015 | 14th March - 24th April, 2015 | 24th April, 2015 | 24th April - 7th May, 2015 | 7th - 21st May, 2015 | Plan | NA | 22nd May - 5th June, 2015 | 12th June, 2015 | 12th - 26th June, 2015 | 90days | 26th June - 26th September, 2015
[7 empty] | Actual | [7 empty] | Actual
VIII | REHABILITATION OF PLANT & MACHINERY |  | B8
1 | Procurement of 1no. Toyota Land Cruiser Jeep | B8 (I) |  | National Competitive Bidding | Pre-qualification | PTB | Plan | 29th January - 12th February, 2015 | 13th - 26th February, 2015 | 27th February - 13th March, 2015 | 14th March - 24th April, 2015 | 24th April, 2015 | 24th April - 7th May, 2015 | 7th - 21st May, 2015 | Plan | NA | 22nd May - 5th June, 2015 | 12th June, 2015 | 12th - 26th June, 2015 | 90days | 26th June - 26th September, 2015
[7 empty] | Actual | [7 empty] | Actual
2 | Supply of 1no. Tubewell Drilling Rig | B8 (II) |  | National Competitive Bidding | Pre-qualification | PTB | Plan | 29th January - 12th February, 2015 | 13th - 26th February, 2015 | 27th February - 13th March, 2015 | 14th March - 24th April, 2015 | 24th April, 2015 | 24th April - 7th May, 2015 | 7th - 21st May, 2015 | Plan | NA | 22nd May - 5th June, 2015 | 12th June, 2015 | 12th - 26th June, 2015 | 90days | 26th June - 26th September, 2015
[7 empty] | Actual | [7 empty] | Actual
X | HEAD QUATER AND AREA OFFICE DEVELOPMENT |  | B9
1 | Procurement Abuja Liaison Office | B9 (I) |  | National Competitive Bidding | Pre-qualification | PTB | Plan | 29th January - 12th February, 2015 | 13th - 26th February, 2015 | 27th February - 13th March, 2015 | 14th March - 24th April, 2015 | 24th April, 2015 | 24th April - 7th May, 2015 | 7th - 21st May, 2015 | Plan | NA | 22nd May - 5th June, 2015 | 12th June, 2015 | 12th - 26th June, 2015 | 90days | 26th June - 26th September, 2015
[7 empty] | Actual | [7 empty] | Actual
2 | Payment of Balance for Supply of 1no. Tubewell Drilling Rig | B9 (II) |  | National Competitive Bidding | Pre-qualification | PTB | Plan | 29th January - 12th February, 2015 | 13th - 26th February, 2015 | 27th February - 13th March, 2015 | 14th March - 24th April, 2015 | 24th April, 2015 | 24th April - 7th May, 2015 | 7th - 21st May, 2015 | Plan | NA | 22nd May - 5th June, 2015 | 12th June, 2015 | 12th - 26th June, 2015 | 90days | 26th June - 26th September, 2015
[7 empty] | Actual | [7 empty] | Actual

## CRBDA
| Ministry/Department/Agency: | CROSS RIVER BASIN DEVELOPMENT AUTHORITY
| Budgetary Year: 2015 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
| Desk Officer/Contact #: |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation | [5 empty] | Contract Implementation
| Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Pre-or Post Qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance
| Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
| List of Contracts | [7 empty] | (18 days) | (5 days) | (18 days) | (30 days) | (1) | (17 days) | (10 days) |  |  | (14 days) | (5 days)
1 | Itu Irrigation / Drainage / Flood Control Project, Itu, AKS. | 5 | 1 | BEME | NCB | On going | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | Dec 2008 | Dec 2008 | Jan 2009
[8 empty] | Actual | [7 empty] | Actual
2 | Owakande/Obubra Irrigatoin/Drainage/Flood Control Project, Obubra LGA, CRS | 6 | 1 | BEME | N/A | On going | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 2010 | Sept. 2010 | Sept. 2010 | Oct. 2010
[8 empty] | Actual | [7 empty] | Actual
3 | Oniong Nung Ndem Irrigation/Drainage, Onna LGA, AKS | 7 | 1 | BEME | NCB | Postqualification | PTB | Plan | 2/2/2015-22/2/2015 | 23/2/2015 - 27/2/2015 | 2/3/2015-20/3/2015 | 21/3/2015 - 20/4/2015 | 20/4/2015 | 21/4/2015 - 8/5/2015 | 11/5/2015 - 21/5/2015 | Plan | N/A | 25/5/2015 - 8/6/2015 | 9/6/2015 -15/6/2015 | 22/6/2015 | 31/8/2015 | 1/2/2015
[8 empty] | Actual | [7 empty] | Actual
4 | Itigidi Irrigation /Drainage /Flood Control Project, Itigidi, CRS.. | 8 | 1 | BEME | NCB | On going | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[8 empty] | Actual | [7 empty] | Actual
5 | Bunyia / Akatom Irruan Dam Project, Boki LGA, CRS | 2 | 1 | BEME | N/A | On going | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 2008 | Dec 2008 | Dec 2008 | Jan 2009
[8 empty] | Actual | [7 empty] | Actual
6 | Hydrological & Hydrometerological services | 3 | 1 | BEME | NCB | Postqualification | PTB | Plan | 2/2/2015-22/2/2015 | 23/2/2015 - 27/2/2015 | 2/3/2015-20/3/2015 | 21/3/2015 - 20/4/2015 | 20/4/2015 | 21/4/2015 - 8/5/2015 | 11/5/2015 - 21/5/2015 | Plan | 2010 | 25/5/2015 - 8/6/2015 | 9/6/2015 -15/6/2015 | 22/6/2015 | 31/8/2015 | 1/2/2015
[8 empty] | Actual | [7 empty] | Actual
7 | Ogoja Irrigation Project, Ogoja LGA, CRS | 9 | 1 | BEME | NCB | Postqualification | PTB | Plan | 2/2/2015-22/2/2015 | 23/2/2015 - 27/2/2015 | 2/3/2015-20/3/2015 | 21/3/2015 - 20/4/2015 | 20/4/2015 | 21/4/2015 - 8/5/2015 | 11/5/2015 - 21/5/2015 | Plan | N/A | 25/5/2015 - 8/6/2015 | 9/6/2015 -15/6/2015 | 22/6/2015 | 31/8/2015 | 1/2/2015
[8 empty] | Actual | [7 empty] | Actual
8 | Abak Irrigation Project Abak, AKS | 10 | 1 | BEME | NCB | Postqualification | PTB | Plan | 2/2/2015-22/2/2015 | 23/2/2015 - 27/2/2015 | 2/3/2015-20/3/2015 | 21/3/2015 - 20/4/2015 | 20/4/2015 | 21/4/2015 - 8/5/2015 | 11/5/2015 - 21/5/2015 | Plan | N/A | 25/5/2015 - 8/6/2015 | 9/6/2015 -15/6/2015 | 22/6/2015 | 31/8/2015 | 1/2/2015
[8 empty] | Actual | [7 empty] | Actual
9 | Study and Design of Dams/ Barrages at AKS/ CRS | 17 | 2 | BEME | NCB | Postqualification | PTB | Plan | 2/2/2015-22/2/2015 | 23/2/2015 - 27/2/2015 | 2/3/2015-20/3/2015 | 21/3/2015 - 20/4/2015 | 20/4/2015 | 21/4/2015 - 8/5/2015 | 11/5/2015 - 21/5/2015 | Plan | N/A | 25/5/2015 - 8/6/2015 | 9/6/2015 -15/6/2015 | 22/6/2015 | 31/8/2015 | 1/2/2015
[8 empty] | Actual | [7 empty] | Actual
10 | Obudu Multi-purpose Dam /Irrigation Project, Obudu, CRS | 11 | 2 | BEME | NCB | Postqualification | Ongoing | Plan | 2/2/2015-22/2/2015 | 23/2/2015 - 27/2/2015 | 2/3/2015-20/3/2015 | 21/3/2015 - 20/4/2015 | 20/4/2015 | 21/4/2015 - 8/5/2015 | 11/5/2015 - 21/5/2015 | Plan | N/A | 25/5/2015 - 8/6/2015 | 9/6/2015 -15/6/2015 | 22/6/2015 | 31/8/2015 | 1/2/2015
[8 empty] | Actual | [7 empty] | Actual
11 | Water projects in various locations in Akwa Ibom and Cross River States | 4 | 4 | BEME | NCB | Postqualification | PTB | Plan | 2/2/2015-22/2/2015 | 23/2/2015 - 27/2/2015 | 2/3/2015-20/3/2015 | 21/3/2015 - 20/4/2015 | 20/4/2015 | 21/4/2015 - 8/5/2015 | 11/5/2015 - 21/5/2015 | Plan | N/A | 25/5/2015 - 8/6/2015 | 9/6/2015 -15/6/2015 | 22/6/2015 | 31/8/2015 | 1/2/2015
[8 empty] | Actual | [7 empty] | Actual
12 | Erosion Control Works at various locations in Akwa Ibom and Cross River States | 19 | Various | BEME | NCB | Postqualification | PTB | Plan | 2/2/2015-22/2/2015 | 23/2/2015 - 27/2/2015 | 2/3/2015-20/3/2015 | 21/3/2015 - 20/4/2015 | 20/4/2015 | 21/4/2015 - 8/5/2015 | 11/5/2015 - 21/5/2015 | Plan | N/A | 25/5/2015 - 8/6/2015 | 9/6/2015 -15/6/2015 | 22/6/2015 | 31/8/2015 | 1/2/2015
[8 empty] | Actual | [7 empty] | Actual
13 | Nkari Irrigation Project, Ini LGA, AKS. | 12 | 2 | BEME | NCB | Postqualification | PTB | Plan | 2/2/2015-22/2/2015 | 23/2/2015 - 27/2/2015 | 2/3/2015-20/3/2015 | 21/3/2015 - 20/4/2015 | 20/4/2015 | 21/4/2015 - 8/5/2015 | 11/5/2015 - 21/5/2015 | Plan | N/A | 25/5/2015 - 8/6/2015 | 9/6/2015 -15/6/2015 | 22/6/2015 | 31/8/2015 | 1/2/2015
[8 empty] | Actual | [7 empty] | Actual
14 | Ijegu Yala Dam / Irrigation Project Yala, CRS. | 13 | 1 | BEME | NCB | Prequalification | PTB | Plan | 2/2/2015-22/2/2015 | 23/2/2015 - 27/2/2015 | 2/3/2015-20/3/2015 | 21/3/2015 - 20/4/2015 | 20/4/2015 | 21/4/2015 - 8/5/2015 | 11/5/2015 - 21/5/2015 | Plan | N/A | 25/5/2015 - 8/6/2015 | 9/6/2015 -15/6/2015 | 22/6/2015 | 31/8/2015 | 1/2/2015
[8 empty] | Actual | [7 empty] | Actual
15 | Calabar River Irrigation, Drainage / Flood Control Project, Odukpani, CRS. (Construction of access road culverts/bridge) | 14 | 2 | BEME | NCB | On going | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[8 empty] | Actual | [7 empty] | Actual
16 | Eniong Creek Irrigation/ Drainage / Flood Control Project, Odukpani LGA, CRS. | 15 | 1 | BEME | NCB | On going | N.A. | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[8 empty] | Actual | [7 empty] | Actual
17 | Health Services and other Disease Sensitazation workshop. | 1 | 1 | BEME | NCB | PostQualificattion | PTB | Plan | 2/2/2015-22/2/2015 | 23/2/2015 - 27/2/2015 | 2/3/2015-20/3/2015 | 21/3/2015 - 20/4/2015 | 20/4/2015 | 21/4/2015 - 8/5/2015 | 11/5/2015 - 21/5/2015 | Plan | N/A | 25/5/2015 - 8/6/2015 | 9/6/2015 -15/6/2015 | 22/6/2015 | 31/8/2015 | 1/2/2015
[8 empty] | Actual | [7 empty] | Actual
18 | Revitalization of the RBDA projects and Gender | 16 | 3 | BEME | NCB | Postqualification | PTB | Plan | 2/2/2015-22/2/2015 | 23/2/2015 - 27/2/2015 | 2/3/2015-20/3/2015 | 21/3/2015 - 20/4/2015 | 20/4/2015 | 21/4/2015 - 8/5/2015 | 11/5/2015 - 21/5/2015 | Plan | N/A | 25/5/2015 - 8/6/2015 | 9/6/2015 -15/6/2015 | 22/6/2015 | 31/8/2015 | 1/2/2015
[8 empty] | Actual | [7 empty] | Actual
19 | Servicom and anti corruption | 21 | 1 | BEME | NCB | Postqualification | PTB | Plan | 2/2/2015-22/2/2015 | 23/2/2015 - 27/2/2015 | 2/3/2015-20/3/2015 | 21/3/2015 - 20/4/2015 | 20/4/2015 | 21/4/2015 - 8/5/2015 | 11/5/2015 - 21/5/2015 | Plan | N/A | 25/5/2015 - 8/6/2015 | 9/6/2015 -15/6/2015 | 22/6/2015 | 31/8/2015 | 1/2/2015
[8 empty] | Actual | [7 empty] | Actual
20 | Rehabilitation and Procurement of plants, Machinery and Equipment | 17 | 2 | BEME | NCB | Postqualification | PTB | Plan | 2/2/2015-22/2/2015 | 23/2/2015 - 27/2/2015 | 2/3/2015-20/3/2015 | 21/3/2015 - 20/4/2015 | 20/4/2015 | 21/4/2015 - 8/5/2015 | 11/5/2015 - 21/5/2015 | Plan | N/A | 25/5/2015 - 8/6/2015 | 9/6/2015 -15/6/2015 | 22/6/2015 | 31/8/2015 | 1/2/2015
[8 empty] | Actual | [7 empty] | Actual
21 | Headquarters, Area office and Liaison office Development, Calabar, CR/Akwa Ibom Area Office/Abuja Liaison Office | 18 | 3 | BEME | NCB | Postqualification | PTB | Plan | 2/2/2015-22/2/2015 | 23/2/2015 - 27/2/2015 | 2/3/2015-20/3/2015 | 21/3/2015 - 20/4/2015 | 20/4/2015 | 21/4/2015 - 8/5/2015 | 11/5/2015 - 21/5/2015 | Plan | N/A | 25/5/2015 - 8/6/2015 | 9/6/2015 -15/6/2015 | 22/6/2015 | 31/8/2015 | 1/2/2015
[8 empty] | Actual | [7 empty] | Actual
22 | Ongoing zonal intervention projects | 20 | 1 | BEME | NCB | On going | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[8 empty] | Actual | [7 empty] | Actual

## DMO
Ministry/Department/Agency: Debt Management Office
Budget Year: 2015
|  | Basic Data | [7 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  |  |  |  | Contract Implementation - Goods
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Arrival of Goods | Inspection/Final Acceptance
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
Plan vs Actual
ACQUISITION OF COMPUTER SOFTWARE | Plan |  | 2 |  | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 24/07/15 - 7/08/15 | NA | NA | NA | NA | 11/08/15 | 22/09/15 | 24/09/15 - 30/09/15 | NA | NA | 23/10/15 - 27/10/15 | 27/10/15 - 30/10/15 | 3/11/15 - 6/11/15 | 10/11/15 - 13/11/15 | 13/11/15 - 13/11/15
Actual
PURCHASE OF COMPUTER PRINTERS AND NETWORK SECURITY APPLIANCE | Plan |  | 4 |  | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 24/07/15 - 7/08/15 | NA | NA | NA | NA | 11/08/15 | 22/09/15 | 24/09/15 - 30/09/15 | NA | NA | 23/10/15 - 27/10/15 | 27/10/15 - 30/10/15 | 3/11/15 - 6/11/15 | 10/11/15 - 13/11/15 | 13/11/15 - 13/11/15
Actual
PURCHASE OF OFFICE FURNITURE AND FITTINGS | Plan |  | 3 |  | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 24/07/15 - 7/08/15 | NA | NA | NA | NA | 11/08/15 | 22/09/15 | 24/09/15 - 30/09/15 | NA | NA | 23/10/15 - 27/10/15 | 27/10/15 - 30/10/15 | 3/11/15 - 6/11/15 | 10/11/15 - 13/11/15 | 13/11/15 - 13/11/15
Actual
PURCHASE OF SHREDDING MACHINES AND FILE CABINETS | Plan |  | 5 |  | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 24/07/15 - 7/08/15 | NA | NA | NA | NA | 11/08/15 | 22/09/15 | 24/09/15 - 30/09/15 | NA | NA | 23/10/15 - 27/10/15 | 27/10/15 - 30/10/15 | 3/11/15 - 6/11/15 | 10/11/15 - 13/11/15 | 13/11/15 - 13/11/15
Actual
PURCHASE OF PHOTOCOPYING MACHINE | Plan |  | 1 |  | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 24/07/15 - 7/08/15 | NA | NA | NA | NA | 11/08/15 | 22/09/15 | 24/09/15 - 30/09/15 | NA | NA | 23/10/15 - 27/10/15 | 27/10/15 - 30/10/15 | 3/11/15 - 6/11/15 | 10/11/15 - 13/11/15 | 13/11/15 - 13/11/15
| Actual | [10 empty] | NA

## DICON
Ministry/Department/Agency: Defence Industrial Corporation Of Nigeria (DICON), Kaduna
Budget Year: 2015
|  | Basic Data | [7 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  |  |  |  | Contract Implementation - Works
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Plan vs Actual
Otical Emmission Spectrometer | Plan | DICON/2012/004 | 1 | BEME | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | 1/05/12 - 17/05/12 | NA | NA | 17/05/12 | 28/06/12 | 28/06/12 - 19/07/12 | 19/07/12 - 10/08/12 | NA | 10/08/12 - 17/08/12 | 17/08/12 - 24/08/12 | 24/08/12 - 7/09/12 | 31/01/13 | 15/02/13 | NA
Actual

## FAAN WORKS
| FEDERAL AIRPORTS AUTHORITY OF NIGERIA Budgetary Year: 2015 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
| Desk Officer/Contact #: |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
| Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | MDA APPROVAL | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Inspection /Acceptance
| Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 4wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
2015 NEW IGR CAPITAL PROJECTS (WORKS)
1 | Fire Alarm System: All Airports | WKS 1 | 1 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2015 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
2 | Bush Clearing & Landscaping | WKS2 | 2 | BOQ | NCB | YES | MTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-30/3/2015 | 30/3/2015 | 1-15/4/2015 | N/A | Plan | N/A | N/A | 16-30/4/2015 | 1-21/5/2015 | 22/5 -5/6/15 | 30/7/2015 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
3 | Production of obstacle/obstruction evaluation maps @N20M | WKS 3 | 3 | BOQ | NCB | YES | MTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-30/3/2015 | 30/3/2015 | 1-15/4/2015 | N/A | Plan | N/A | N/A | 16-30/4/2015 | 1-21/5/2015 | 13-27/5/15 | 30/7/2015 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
4 | Extension of implementation of integrated Enterprises Resources Planning System to 6 Int'l Airports (Licensing 35m, Ls, Abuja, PH 9m each, Cal Kano Enugu 6m each) | WKS 4 | 4 | BOQ | NCB | N/A | PTB | Plan | 16-30/9/2013 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
5 | c) Mechanical workshop and Engineering Building d) Aviation Medical Clinic e) Fire and Safety Building f) Airline Office Block | WKS 5 | 5 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
6 | Construction of: a) Dilapidated FAAN building at HQ and all Airports (including power house building and power house) | WKS 6 | 6 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
7 | Construction of: a) New Admin Block at New Landslide Abuja, b) Construction of Airline/Admin office c) Fire Watch Tower d) Aviation Medical Clinic | WKS 7 | 7 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
8 | Expansion/Extension of: a) Washroom at ARFFS office Building b) Conference Room and Store for Procurement Department c) Civil and Building Department (FAAN HQ) d) Commercial Dept (FAAN HQ) | WKS 8 | 8 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
9 | Completion of: a) Fire & Rescue building at Ilorin Airport, b) abandoned building behind the Aviation Clinic/beside the Police station, c) Control Tower | WKS 9 | 9 | BOQ | NCB | YES | MTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-30/3/2015 | 30/3/2015 | 1-15/4/2015 | N/A | Plan | N/A | N/A | 16-30/4/2015 | 1-21/5/2015 | 22/5 -5/6/15 | 30/7/2015 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
10 | Continuous remarking and maintenance pavements in all Airports | WKS 10 | 10 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
11 | Remarking of Runway/Apron | WKS 11 | 11 | BOQ | NCB | YES | FEC | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-30/3/2015 | 30/3/2015 | 1-15/4/2015 | N/A | Plan | N/A | N/A | 16-30/4/2015 | 1-21/5/2015 | 22/5 -5/6/15 | 30/7/2015 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
12 | Reactivation/Rehabilitation of 1st and 2nd phase, Akure Airport 3km access road illumination | WKS 12 | 12 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
13 | Reconstruction of fuel dump at Headquarters | WKS 13 | 13 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
14 | Erosion control at Engineering ?oil & Gas Office block | WKS 14 | 14 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
15 | Completion of Bi-metal Operational Perimeter Fence | WKS 15 | 15 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
16 | Construction of Fuel Dump at Makurdi | WKS 16 | 16 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
17 | Supply and installation of transformers to upgrade power supply infrastructure | WKS 17 | 17 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
18 | Provision of 11KV power supply direct feed to B.O.T | WKS 18 | 18 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
19 | Complete replacement of entire lighting system with LG low energy lighting system, totaling 3000 points at MMIA Lagos, Procurement | WKS 19 | 19 | BOQ | NCB | YES | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 22/5 -5/6/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
20 | Rehabilitation of Airfield Lighting system to ICAO standard at the various Airports i.e. Benin, Maiduguri,Sokoto,Kad,Yola & Minna Airports | WKS 20 | 20 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
21 | Rehabilitation of Airport street light | WKS 21 | 21 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
22 | Construction and installation of Apron poles and light in Airport | WKS 22 | 22 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
23 | Rehabilitation staff quarter & Renovation Works for HQ and all Airports | WKS 23 | 23 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
24 | Rehabilitation of staff club and swimming pool | WKS 24 | 24 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
25 | Improvement of water supply | WKS 25 | 25 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
26 | Supply and installation of Gen Sets and Transformers and Accessories | WKS 26 | 26 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
27 | Replacement of OTIS Esclators and Travelators at MMIA Lagos by OEM (Phase 1) | WKS 27 | 27 | BOQ | NCB | YES | MTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-30/3/2015 | 30/3/2015 | 1-15/4/2015 | N/A | Plan | N/A | N/A | 16-30/4/2015 | 1-21/5/2015 | 22/5 -5/6/15 | 30/7/2015 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
28 | Reconfiguration of MMIA Baggage Hall Departure Conveyors N20,000,000 each x 4 nos MMA | WKS 28 | 28 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
29 | Supply and installation of 1No Escalator and 1No lift for Domesstic departure module B (NAIA) | WKS 29 | 29 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
30 | Replacement of escalators and 2 Nos passengeer lift at Abuja | WKS 30 | 30 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
31 | Digital checking counters and weighing scales (6 Nos) | WKS 31 | 31 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
32 | Improving of Airport coolling system | WKS 32 | 32 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
33 | Construction of speed Breakers at GAT Lagos | WKS 33 | 33 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
34 | Mech and Civil Engineering Consumables | WKS 34 | 34 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
35 | Supply and installation of bomb containment vessel for two international airports (MAKIA & PHIA) | WKS 35 | 35 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
36 | Screening Machine for Cabin/Walk Through Metal Dectector CEIA | WKS 36 | 36 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
37 | Auto Barrier Access control | WKS 37 | 37 | BOQ | NCB | N/A | MTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-30/3/2015 | 30/3/2015 | 1-15/4/2015 | N/A | Plan | N/A | N/A | 16-30/4/2015 | 1-21/5/2015 | 13-27/5/15 | 30/7/2015 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
38 | Routine maintenance of Narcotics and /explosie Trace Detectors | WKS 38 | 38 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
39 | Extension of Public Address System at 4 Int'l and re-modeled Airports at N25m each | WKS 39 | 39 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
40 | Installation of CCTV Surveillance system at the 4 Int'l Airports | WKS 40 | 40 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
41 | Installation of VSAT Communication system at Kano, OH, Enugu & Link with HQ | WKS 41 | 41 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
42 | ICT: Fibre Optic connecting backbone | WKS 42 | 42 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
43 | Provision of UPS for 3 Int'l Airports (PHC, Abuja) | WKS 43 | 43 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
44 | Acquisition of New Software & Licence fees | WKS 44 | 44 | BOQ | NCB | YES | MTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-30/3/2015 | 30/3/2015 | 1-15/4/2015 | N/A | Plan | N/A | N/A | 16-30/4/2015 | 1-21/5/2015 | 22/5 -5/6/15 | 30/7/2015 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
45 | Implement of Messaging, Collaborating and Document Managment System for Legal, Procurement, Board and HR | WKS 45 | 45 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
46 | Completion of 6Nos Control towers | WKS 46 | 46 | BOQ | NCB | N/A | PTB | Plan | 16-30/9/2013 | 1- 15/10/2013 | N/A | 3/2-3/3/2014 | 3/3/2014 | 4-18/3/2014 | N/A | Plan | N/A | N/A | 19/3-2/4/2014 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 23/1/2014 | N/A | Jan, 20115
[8 empty] | Actual | [7 empty] | Actual
2015 FGN CAPITAL PROJECTS
47 | Height extension of existing blockwal fence Around the new Protocool Loung/Personel Building - Lagos | WKS 47 | 47 | BOQ | NCB | N/A | MTB | Plan | 0n-going | 0n-going | N/A | 0n-going | 0n-going | 0n-going | 0n-going | Plan | 0n-going | 0n-going | 0n-going | 0n-going | 13-27/5/15 | 0n-going | 0n-going | 0n-going | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
48 | Improvement of the Airstrip Runway end Safety Area - NAIA Abuja | WK S48 | 48 | BOQ | NCB | N/A | PTB | Plan | 0n-going | 0n-going | N/A | 0n-going | 0n-going | 0n-going | 0n-going | Plan | 0n-going | 0n-going | 0n-going | 0n-going | 13-27/5/15 | 0n-going | 0n-going | 0n-going | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
49 | Restoration of Sewage treatment plant - PH | WKS 49 | 49 | BOQ | NCB | N/A | PTB | Plan | 0n-going | 0n-going | N/A | 0n-going | 0n-going | 0n-going | 0n-going | Plan | 0n-going | 0n-going | 0n-going | 0n-going | 13-27/5/15 | 0n-going | 0n-going | 0n-going | Jan, 20115
[8 empty] | Actual | [7 empty] | Actual

## FAAN GOODS
| FEDERAL AIRPORTS AUTHORITY OF NIGERIA Budgetary Year: 2015 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
| Desk Officer/Contact #: |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
| Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | MDA APPROVAL | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Inspection /Acceptance
| Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 4wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
2015 NEW IGR CAPITAL PROJECTS (WORKS)
1 | Fire Alarm System: All Airports | WKS 1 | 1 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2015 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
2 | Bush Clearing & Landscaping | WKS2 | 2 | BOQ | NCB | YES | MTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-30/3/2015 | 30/3/2015 | 1-15/4/2015 | N/A | Plan | N/A | N/A | 16-30/4/2015 | 1-21/5/2015 | 22/5 -5/6/15 | 30/7/2015 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
3 | Production of obstacle/obstruction evaluation maps @N20M | WKS 3 | 3 | BOQ | NCB | YES | MTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-30/3/2015 | 30/3/2015 | 1-15/4/2015 | N/A | Plan | N/A | N/A | 16-30/4/2015 | 1-21/5/2015 | 13-27/5/15 | 30/7/2015 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
4 | Extension of implementation of integrated Enterprises Resources Planning System to 6 Int'l Airports (Licensing 35m, Ls, Abuja, PH 9m each, Cal Kano Enugu 6m each) | WKS 4 | 4 | BOQ | NCB | N/A | PTB | Plan | 16-30/9/2013 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
5 | c) Mechanical workshop and Engineering Building d) Aviation Medical Clinic e) Fire and Safety Building f) Airline Office Block | WKS 5 | 5 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
6 | Construction of: a) Dilapidated FAAN building at HQ and all Airports (including power house building and power house) | WKS 6 | 6 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
7 | Construction of: a) New Admin Block at New Landslide Abuja, b) Construction of Airline/Admin office c) Fire Watch Tower d) Aviation Medical Clinic | WKS 7 | 7 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
8 | Expansion/Extension of: a) Washroom at ARFFS office Building b) Conference Room and Store for Procurement Department c) Civil and Building Department (FAAN HQ) d) Commercial Dept (FAAN HQ) | WKS 8 | 8 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
9 | Completion of: a) Fire & Rescue building at Ilorin Airport, b) abandoned building behind the Aviation Clinic/beside the Police station, c) Control Tower | WKS 9 | 9 | BOQ | NCB | YES | MTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-30/3/2015 | 30/3/2015 | 1-15/4/2015 | N/A | Plan | N/A | N/A | 16-30/4/2015 | 1-21/5/2015 | 22/5 -5/6/15 | 30/7/2015 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
10 | Continuous remarking and maintenance pavements in all Airports | WKS 10 | 10 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
11 | Remarking of Runway/Apron | WKS 11 | 11 | BOQ | NCB | YES | FEC | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-30/3/2015 | 30/3/2015 | 1-15/4/2015 | N/A | Plan | N/A | N/A | 16-30/4/2015 | 1-21/5/2015 | 22/5 -5/6/15 | 30/7/2015 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
12 | Reactivation/Rehabilitation of 1st and 2nd phase, Akure Airport 3km access road illumination | WKS 12 | 12 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
13 | Reconstruction of fuel dump at Headquarters | WKS 13 | 13 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
14 | Erosion control at Engineering ?oil & Gas Office block | WKS 14 | 14 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
15 | Completion of Bi-metal Operational Perimeter Fence | WKS 15 | 15 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
16 | Construction of Fuel Dump at Makurdi | WKS 16 | 16 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
17 | Supply and installation of transformers to upgrade power supply infrastructure | WKS 17 | 17 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
18 | Provision of 11KV power supply direct feed to B.O.T | WKS 18 | 18 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
19 | Complete replacement of entire lighting system with LG low energy lighting system, totaling 3000 points at MMIA Lagos, Procurement | WKS 19 | 19 | BOQ | NCB | YES | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 22/5 -5/6/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
20 | Rehabilitation of Airfield Lighting system to ICAO standard at the various Airports i.e. Benin, Maiduguri,Sokoto,Kad,Yola & Minna Airports | WKS 20 | 20 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
21 | Rehabilitation of Airport street light | WKS 21 | 21 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
22 | Construction and installation of Apron poles and light in Airport | WKS 22 | 22 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
23 | Rehabilitation staff quarter & Renovation Works for HQ and all Airports | WKS 23 | 23 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
24 | Rehabilitation of staff club and swimming pool | WKS 24 | 24 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
25 | Improvement of water supply | WKS 25 | 25 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
26 | Supply and installation of Gen Sets and Transformers and Accessories | WKS 26 | 26 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
27 | Replacement of OTIS Esclators and Travelators at MMIA Lagos by OEM (Phase 1) | WKS 27 | 27 | BOQ | NCB | YES | MTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-30/3/2015 | 30/3/2015 | 1-15/4/2015 | N/A | Plan | N/A | N/A | 16-30/4/2015 | 1-21/5/2015 | 22/5 -5/6/15 | 30/7/2015 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
28 | Reconfiguration of MMIA Baggage Hall Departure Conveyors N20,000,000 each x 4 nos MMA | WKS 28 | 28 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
29 | Supply and installation of 1No Escalator and 1No lift for Domesstic departure module B (NAIA) | WKS 29 | 29 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
30 | Replacement of escalators and 2 Nos passengeer lift at Abuja | WKS 30 | 30 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
31 | Digital checking counters and weighing scales (6 Nos) | WKS 31 | 31 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
32 | Improving of Airport coolling system | WKS 32 | 32 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
33 | Construction of speed Breakers at GAT Lagos | WKS 33 | 33 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
34 | Mech and Civil Engineering Consumables | WKS 34 | 34 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
35 | Supply and installation of bomb containment vessel for two international airports (MAKIA & PHIA) | WKS 35 | 35 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
36 | Screening Machine for Cabin/Walk Through Metal Dectector CEIA | WKS 36 | 36 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
37 | Auto Barrier Access control | WKS 37 | 37 | BOQ | NCB | N/A | MTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-30/3/2015 | 30/3/2015 | 1-15/4/2015 | N/A | Plan | N/A | N/A | 16-30/4/2015 | 1-21/5/2015 | 13-27/5/15 | 30/7/2015 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
38 | Routine maintenance of Narcotics and /explosie Trace Detectors | WKS 38 | 38 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
39 | Extension of Public Address System at 4 Int'l and re-modeled Airports at N25m each | WKS 39 | 39 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
40 | Installation of CCTV Surveillance system at the 4 Int'l Airports | WKS 40 | 40 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
41 | Installation of VSAT Communication system at Kano, OH, Enugu & Link with HQ | WKS 41 | 41 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
42 | ICT: Fibre Optic connecting backbone | WKS 42 | 42 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
43 | Provision of UPS for 3 Int'l Airports (PHC, Abuja) | WKS 43 | 43 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
44 | Acquisition of New Software & Licence fees | WKS 44 | 44 | BOQ | NCB | YES | MTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-30/3/2015 | 30/3/2015 | 1-15/4/2015 | N/A | Plan | N/A | N/A | 16-30/4/2015 | 1-21/5/2015 | 22/5 -5/6/15 | 30/7/2015 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
45 | Implement of Messaging, Collaborating and Document Managment System for Legal, Procurement, Board and HR | WKS 45 | 45 | BOQ | NCB | N/A | PTB | Plan | 15/9-3/10/2014 | 6- 17/10/2014 | N/A | 16/2-16/3/2015 | 16/3/2015 | 17/3- 7/4/2015 | N/A | Plan | N/A | N/A | 8-22/4/2015 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 30/1/2016 | N/A | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
46 | Completion of 6Nos Control towers | WKS 46 | 46 | BOQ | NCB | N/A | PTB | Plan | 16-30/9/2013 | 1- 15/10/2013 | N/A | 3/2-3/3/2014 | 3/3/2014 | 4-18/3/2014 | N/A | Plan | N/A | N/A | 19/3-2/4/2014 | 23/4- 12/5/2015 | 13-27/5/15 | 23/7/2014 | 23/1/2014 | N/A | Jan, 20115
[8 empty] | Actual | [7 empty] | Actual
2015 FGN CAPITAL PROJECTS
47 | Height extension of existing blockwal fence Around the new Protocool Loung/Personel Building - Lagos | WKS 47 | 47 | BOQ | NCB | N/A | MTB | Plan | 0n-going | 0n-going | N/A | 0n-going | 0n-going | 0n-going | 0n-going | Plan | 0n-going | 0n-going | 0n-going | 0n-going | 13-27/5/15 | 0n-going | 0n-going | 0n-going | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
48 | Improvement of the Airstrip Runway end Safety Area - NAIA Abuja | WK S48 | 48 | BOQ | NCB | N/A | PTB | Plan | 0n-going | 0n-going | N/A | 0n-going | 0n-going | 0n-going | 0n-going | Plan | 0n-going | 0n-going | 0n-going | 0n-going | 13-27/5/15 | 0n-going | 0n-going | 0n-going | Jan, 2016
[8 empty] | Actual | [7 empty] | Actual
49 | Restoration of Sewage treatment plant - PH | WKS 49 | 49 | BOQ | NCB | N/A | PTB | Plan | 0n-going | 0n-going | N/A | 0n-going | 0n-going | 0n-going | 0n-going | Plan | 0n-going | 0n-going | 0n-going | 0n-going | 13-27/5/15 | 0n-going | 0n-going | 0n-going | Jan, 20115
[8 empty] | Actual | [7 empty] | Actual

## Ministry of Agriculture Goods
Ministry/Department/Agency: FEDERAL MINISTRY OF AGRICULTURE AND RURAL DEVELOPMENT
Budgetary Year: 2015 | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Procurement Method | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to 4 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan | 2 wks | 1 - 2 wks | 3 wks
|  |  |  | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
SUPPLY OF 15 NOS LAPTOPS, 15 NOS 1 TB EXTERNAL DISK DRIVER | DAES004005015E | DAES 01 | NS | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
SUPPLY OF START-UP PACKS FOR 3000 TRAINED YOUTH IN TEN VALUE CHAINS | Y&G004005361 | Y&G 01 | MOU | N/A | MTB | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
SUPPLY OF FERTILIZER | Y&G004005364 | Y&G 02 | MOU | N/A | MTB | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
SUPPLY OF SEEDS/FEEDS | Y&G004005365 | Y&G 03 | MOU | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
SUPPLY OF START-UP PACKS FOR 2500 TRAINED WOMEN IN TEN VALUE CHAINS | Y&G004005382 | Y&G 04 | MOU | N/A | MTB | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
SUPPLY OF FERTILIZER TO THE TRAINED WOMEN | Y&G004005387 | Y&G 05 | MOU | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
SUPPLY OF SEEDS/FEEDS TO THE TRAINED WOMEN | Y&G004005389 | Y&G 06 | MOU | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
SUPPLY OF STARTER PACKS FOR 1000 VULNERABLE PERSONS IN DIFFERENT VALUE CHAINS AND OFF-FARM INCOME GENERATING ACTIVITIES | Y&G004005395 | Y&G 07 | MOU | N/A | MTB | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROVISION OF 3000 BAGS (50KG) OF INDUSTRIAL SALTS TO 1500 SKIN BUYERS IN 12 STATES | FDL002004254 | GES | MOU | N/A | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
SUPPLY OF VACCINE FOR ONE MILLION SHEEP AND GOATS AGAINST PESTE-DE-PETITE RUMINANTS (PPR VACCINE) | FDL002004254A | N/A | DP | N/A | MTB | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
SUPPLY OF VACCINE FOR ONE MILLION CATTLE AGAINST CONTAGIOUS BOVINE PLEURO PNEUMONIA (CBPP) | FDL002004254A | N/A | DP | N/A | MTB | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
SUPPLY OF BIOSECURITY COMMODITIES FOR THE CONTROL OF AFRICAN SWINE FEVER (ASF) | FDL002004254A | VET 01 | NCB | N/A | MTB | Plan | 6TH-20TH FEB | N/A | N/A | 23RD-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
SUPPLY OF 12500 RABIES VACCINES FOR VACCINATION OF DOGS AND CATS NATIONWIDE | FDL002004254C | N/A | DP | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
SUPPLY OF MEAT INSPECTION KITS AND TRAINING OF MEAT INSPECTORS | FDL002004254C | N/A | NS | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
FURNISHING OF OFFICE SPACE AS SECRETARIAT FOR REFORM COORDINATION DEPARTMENT | FMA&RD004005098 | N/A | NS | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
SUPPLY OF EQUIPMENT FOR THE ICT TRAINING ROOM | ICT004005081 | ICT 02 | NCB | N/A | MTB | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF 2 NOS PROJECT PROJECT VEHICLES |  | N/A | DP | N/A | MTB | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROVISION OF 77,616 UNITS OF COTTON HARVEST SACKS | FDA002004081 | FDA 01 | NCB | N/A | MTB | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROVISION OF 3,950KG OF BREEDER SEED, 4,334KG OF FOUNDATION SEED, AND 553.1MT CERTIFIED SEEDS | FDA002004067 | FDA 02 | MOU | N/A | MTB | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROVISION OF 8,002 BAGS OF NPK | FDA002004070 | FDA03 | GES | N/A | MTB | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROVISION OF 1,344 BAGS OF UREA | FDA002004073 | FDA 04 | GES | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROVISION OF 1280 LITRES OF MAXI CROP | FDA002004075 | FDA 05 | MOU | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROVISION OF 25268 LITRES OF INSECTICIDES | FDA002004078 | FDA | MOU | N/A | MTB | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
DEVELOPMENT OF CONTAINMENT FACILITEIS IN COLLABORATION WITH NABDA | FDA002004078 | FDA | MOU | N/A | MTB | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF 2,400KG OF IRISH POTATO FOUNDATION SEED (FS) (IMPROVED HIGH YIELDING PESTS/ DISEASE-FREE IRISH POTATO SEED | FDA002004559 | FDA 03 | NCB | N/A | MTB | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
COST PROCESSING, PACKAGING TRANSPORTATION AND DISTRIBUTION TO OUT-GROWERS IN PLATEAU, KADUNA AND CROSS RIVER STATE | FDA002004559 | FDA 04 | DP | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
SUPPLY OF 1,152 LITRES OF ORGANIC FERTILIZER | FDA002004567 | FDA 05 | DP | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
SUPPLY OF 1,153 LITRES OF ORGANIC FERTILIZER | FDA002004556 | N/A | GES | N/A | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
ESTABLISHMENT OF TISSUE CULTURE LABORATORIES | FDA002004556 | N/A | DP | N/A | MTB | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
REHABILITATION OF EXISTING TISSUE CULTURE EXPERIMENTAL FACILITIES IN NRCRI | FDA002004556 | NA | DP | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
SUPPLY OF SOIL FIELD ENGINEERING EQUIPMENT | AL&CCMS004005011 | AL&CCMS 02 | NCB | N/A | PS | plan | 6TH-27TH FEB | N/A | 2ND MARCH-13TH APRIL | 2ND MARCH-13TH APRIL | 13TH APRIL | 20TH APRIL-8TH MAY | N/A | Plan | N/A | 25TH-29TH MAY | 1ST-12JUNE | 19TH-30TH JUNE | 4 WEEKS | 31ST JULY-7TH AUGUST
[6 empty] | Actual | [7 empty] | Actual
Primting and Production Soil Extension Manuals for Distribution to Farmers Through Extension Department | AL&CCMS004005015 | AL&CCMS 01 | NCB | N/A | MTB | plan | 6TH-27TH FEB | N/A | 2ND MARCH-13TH APRIL | 2ND MARCH-13TH APRIL | 13TH APRIL | 20TH APRIL-8TH MAY | N/A | Plan | N/A | 25TH-29TH MAY | 1ST-12JUNE | 19TH-30TH JUNE | 4 WEEKS | 31ST JULY-7TH AUGUST
[6 empty] | Actual | [7 empty] | Actual
Procurement of 350nos 10gram sachets indeterminate hybrid tomato seeds (Havana) for fresh friut production | FDA002004084 | FDA 05 | NCB | N/A | MTB | Plan | 6TH-27TH FEB | N/A | 2ND MARCH-13TH APRIL | 2ND MARCH-13TH APRIL | 13TH APRIL | 20TH APRIL-8TH MAY | N/A | Plan | N/A | 25TH-29TH MAY | 1ST-12JUNE | 19TH-30TH JUNE | 4 WEEKS | 31ST JULY-7TH AUGUST
[6 empty] | Actual | [7 empty] | Actual
Procurement of 500kg onion (Red creole | FDA002004090 | FDA 06 | N.S | N/A | P.S | Plan | 6TH-27TH FEB | N/A | 2ND MARCH-13TH APRIL | 2ND MARCH-13TH APRIL | 13TH APRIL | 20TH APRIL-8TH MAY | N/A | Plan | N/A | 25TH-29TH MAY | 1ST-12JUNE | 19TH-30TH JUNE | 4 WEEKS | 31ST JULY-7TH AUGUST
[6 empty] | Actual | [7 empty] | Actual
Procurement of 500kg hybrid ( Okro Seeds) | FDA002004085 | FDA 06 | NCB | N/A | MTB | Plan | 6TH-27TH FEB | N/A | 2ND MARCH-13TH APRIL | 2ND MARCH-13TH APRIL | 13TH APRIL | 20TH APRIL-8TH MAY | N/A | Plan | N/A | 25TH-29TH MAY | 1ST-12JUNE | 19TH-30TH JUNE | 4 WEEKS | 31ST JULY-7TH AUGUST
[6 empty] | Actual | [7 empty] | Actual
Procurement of 5.0kg Ugu Seeds | FDA002004087 | FDA 06 | NCB | N/A | MTB | Plan | 6TH-27TH FEB | N/A | 2ND MARCH-13TH APRIL | 2ND MARCH-13TH APRIL | 13TH APRIL | 20TH APRIL-8TH MAY | N/A | Plan | N/A | 25TH-29TH MAY | 1ST-12JUNE | 19TH-30TH JUNE | 4 WEEKS | 31ST JULY-7TH AUGUST
[6 empty] | Actual | [7 empty] | Actual
Production of 30,000nos Improved citrus seedlings stands by College of Agric, Yandev and NIHORT, Ibadan | FDA002004090 | FDA 06 | NCB | N/A | MTB | Plan | 6TH-27TH FEB | N/A | 2ND MARCH-13TH APRIL | 2ND MARCH-13TH APRIL | 13TH APRIL | 20TH APRIL-8TH MAY | N/A | Plan | N/A | 25TH-29TH MAY | 1ST-12JUNE | 19TH-30TH JUNE | 4 WEEKS | 31ST JULY-7TH AUGUST
[6 empty] | Actual | [7 empty] | Actual
Mop up of 9,000nos improved Mangoes seedling Stands from Yam International Investment Ltd Adamawa and lilkub Ventures Zaria | FDA002004090 | FDA 06 | MOU | N/A | MTB | Plan | 6TH-27TH FEB | N/A | 2ND MARCH-13TH APRIL | 2ND MARCH-13TH APRIL | 13TH APRIL | 20TH APRIL-8TH MAY | N/A | Plan | N/A | 25TH-29TH MAY | 1ST-12JUNE | 19TH-30TH JUNE | 4 WEEKS | 31ST JULY-7TH AUGUST
[6 empty] | Actual | [7 empty] | Actual
Procrement of Z-Force/Ethrel | FDA002004097 | FDA 07 | N,S | N/A | P.S | Plan | 6TH-27TH FEB | N/A | 2ND MARCH-13TH APRIL | 2ND MARCH-13TH APRIL | 13TH APRIL | 20TH APRIL-8TH MAY | N/A | Plan | N/A | 25TH-29TH MAY | 1ST-12JUNE
[6 empty] | Actual | [7 empty] | Actual
Procurement of Karate (Insectiside) | FDA002004101 | N/A | N.S | N/A | P.S | Plan | 6TH-27TH FEB | N/A | 2ND MARCH-13TH APRIL | 2ND MARCH-13TH APRIL | 13TH APRIL | 20TH APRIL-8TH MAY | N/A | Plan | N/A | 25TH-29TH MAY | 1ST-12JUNE | 19TH-30TH JUNE | 4 WEEKS | 31ST JULY-7TH AUGUST
[6 empty] | Actual | [7 empty] | Actual
Procurement fo Touchdown (Herbicide) | FDA002004099 | N/A | N.S | N/A | P.S | Plan | 6TH-27TH FEB | N/A | 2ND MARCH-13TH APRIL | 2ND MARCH-13TH APRIL | 13TH APRIL | 20TH APRIL-8TH MAY | N/A | Plan | N/A | 25TH-29TH MAY | 1ST-12JUNE | 19TH-30TH JUNE | 4 WEEKS | 31ST JULY-7TH AUGUST
[6 empty] | Actual | [7 empty] | Actual
Procurement of Dizengoff AMIRAN KITS to support fresh procedure structures | FDA002004103 | FDA 08 | NCB | N/A | MTB | Plan | 6TH-27TH FEB | N/A | 2ND MARCH-13TH APRIL | 2ND MARCH-13TH APRIL | 13TH APRIL | 20TH APRIL-8TH MAY | N/A | Plan | N/A | 25TH-29TH MAY | 1ST-12JUNE | 19TH-30TH JUNE | 4 WEEKS | 31ST JULY-7TH AUGUST
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF 50NOS. MECHANICAL DESTONER (300kg/hr) | ABM002003774/01 | ABM 01 | NCB | N/A | MTB | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
date
PROCUREMENT OF 50NOS MECHANICAL RAPID STEAM PARBOILER (250-300kg BATCH/DAY) | ABM002003774/02 | ABM 02 | NCB | N/A | MTB | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF 50NOS MOTORIZED CHIPPING MACHINE FOR FARMERS COOPERATIVE COUPLET WITH 7HP DIESEL ENGINE | ABM002003879/01 | ABM 03 | NCB | N/A | MTB | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROVISION OF 80 COMPUTERS FOR STATE DIRECTORATE FOR CANOE REGISTRATION & DATA COLLECTION | FDF002004447 | FDF 07 | NCB | N/A | MTB | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF 2 PROJECT VEHICLE | FDF002004447 | FDF 08 | NS | N/A | MTB | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF VEHICLE FOR THE MSC OFFICE IN LAGOS | FDF002004447/02 | N/A | NS | N/A | MTB | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF SORGHUM SEEDS | FDA002003790 | N/A | GES | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF MILLET SEEDS | FDA002003790 | N/A | GES | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
SUPPLY OF ORGANIC FERTILIZER | FDA002003802 | N/A | GES | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
INORGANIC FERTILIZER SORGHUM | FDA002003797 | N/A | GES | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
INORGANIC FERTILIZER MILLET | FDA002003797 | N/A | GES | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF 36,864 SARCHETS OF APRON PLUS SEED DRESSER | FDA002003793 | FDA 01 | NCB | N/A | MTB | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF 42 NUMBER SORGHUM/MILLET GRAIN THRESHER | FDA002003810 | FDA 02 | NCB | N/A | MTB | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
CERTIFIED MAIZE SEED (512.86MT) | FDA002003881 | N/A | MOU | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
NPK 27:13:13 & UREA FERTILIZERS | FDA002003884 | N/A | GES | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
ORGANIC FERTILIZER FOR MAIZE | FDA002003891 | N/A | GES | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
SUPPLY OF MICRO-NUTRIENT FORMULATIONS AS SOIL AMENDERS | FDA002003894 | N/A | GES | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF HERBICIDES | FDA002004020 | N/A | GES | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF INSECTICIDES | FDA002004022 | N/A | GES | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PRODUCTION OF 17TONS MAIZE BREEDER SEEDS | FDA002003881 | N/A | MOU | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PRODUCTION OF 3.6MILLION IMPROVED HYBRID COCOA POD | FDA002003536 | N/A | MOU | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF ACTARA | FDA002003606 | N/A | GES | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
INORGANIC FERTILIZER | FDA002003544 | N/A | GES | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
ORGANIC FERTILIZER | FDA002003550 | N/A | GES | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
SOIL AMENDER/MICRO NUTRIENTS | FDA002003357 | N/A | GES | N/A | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
FUNGICIDES-RIDOMIL, FUNGRURAN | FDA002003563 | N/A | GES | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF SOLO PUMP AND KNAPSACK SPRAYERS | FDA002003572 | N/A | GES | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF ASSORTED GRAINS/ FOOD COMMODITIES | FSRD004005049/01 | FSRD 01 | NCB | N/A | MTB | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
date
PROCUREMENT OF STORAGE AND ENVIROMENTAL CHEMICALS | FSRD004005049/02 | FSRD 02 | NCB | N/A | MTB | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 14TH AUGUST | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF HANDLING (PROTECTIVE GEARS) AND LABORATORY EQUIPMENT | FSRD004005049/03 | FSRD 03 | NCB | N/A | MTB | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
FEEDING OF PRIMARY SCHOOL PUPILS UNDER THE HGSFP IN 7 STATE | FSRD004005049/04 | FSRD 04 | NCB | N/A | MTB | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF KITCHEN EQUIPMENT, CUTLERIES, SPOONS, CUPS ETC FOR SCHOOL PUPILS | FSRD004005049/05 | FSRD 05 | NCB | N/A | MTB | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF 1NO M&E PROJECT VEHICLES TOYOTA HILUX DOUBLE CABIN | M&E | P&PC 01 | NCB | N/A | MTB | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF AGRIC BOOKS, JOURNALS ETC TO THE OUTSTATION | N/A | P&PC 04 | NCB | N/A | MTB | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF AGRIC BOOKS, JOURNAL ETC TO THE HEADQUATER LIBRARY | LIB001003516 |  | NA | N/A | PS | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT AND DISTRIBUTION OF IMPROVED RICE SEED | FDA002003615 | FDA 02 | NCB | N/A | GES | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT AND DISTRIBUTION OF NPK & UREA FERTILIZERS | FDA002003618 | FDA 04 | NCB | N/A | GES | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT AND DISTRIBUTION OF SOIL AMENDER/MICRO NUTRIENT | FDA002003676 | FDA 05 | NCB | N/A | GES | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
PROCUREMENT AND DITRIBUTION OF AGRO CHEMICALS | FDA002003771 | FDA 06 | NCB | N/A | GES | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
SUPPORT FOR SMALL SCALE PROCESSING FACILITIES AND EQUIPMENT | FDA002003774 | FDA 07 | NCB | N/A | GES | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
HYBRID RICE DEVELOPMENT | FDA002003776 | FDA 08 | NCB | N/A | GES | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
PROCUREMENT AND DISTRIBUTION OF ORNANIC FERTILIZERS | FDA002003620 | FDA 09 | NCB | N/A | GES | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
DISTRIBUTION OF 45MT CERTIFIED SEEDS @ 25kg Per FARMER | FDA002004024 | FDA 10 | NCB | N/A | GES | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
DISTRIBUTION OF 1,800 BAGS OF SINGLE SUPER PHOSPHATE (SSP) @ 1 Bag Per FARMER | FDA002004025 | FDA 11 | NCB | N/A | GES | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
DISTRIBUTION OF 3,600 SACHET OF HIGH QUALITY INOCULANT (NODUMAX ) @ 2 SACHET Per FARMER | FDA002004025 | FDA 12 | NCB | N/A | GES | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
DISTRIBUTION OF 1,800 LITRES OF HERBICIDES (FUSILADE) @ 1LITRE Per FARMER | FDA002004035 | FDA 13 | NCB | N/A | GES | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PRODUCTION OF 35 mt OF FOUNDATION SEEDS (NCRI) | FDA002004038 | FDA 14 | NCB | N/A | MTB | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF 8,010KG BRAZILIAN JUMBO VARIETY SEED | FDA002004217 | N/A | MoU | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | 3RD-24TH AUG | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF 314 BAGS OF INORGANIC FERTILIZER | FDA002004218 | N/A | GES | N/A | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | 3RD-24TH AUG | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF 2,880 LITERS OF GLYPHOSATE | FDA002004229 | N/A | GES | N/A | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | 3RD-24TH AUG | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF 18 BALES CARBON FREE JUTE BAGS | FDA002004231 | N/A | DP | N/A | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | 3RD-24TH AUG | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF 30 SOLO PUMPS ENGLAND | FDA002004231 | N/A | DP | N/A | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | 3RD-24TH AUG | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PROCUTREMENT AND DELIVERY OF 70NOS BALES OF 50KG HYDROCARBON FREE JUTE BAGS FOR SHEA NUTS | FDA002004719 | N/A | NS | N/A | PS | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT AND DELIVERY OF 5NOS. SHEANUT CRUSHER INCLUDING TRAINING OF OPERATORS FOR USE AND MAINTENANCE OF THE MACHINE FOR PRODUCTION OF PREMIUM SHEA BUTTER | FDA002004719 | N/A | NS | N/A | PS | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
BUY BACK OF 316,800 IMPROVED TENERA OIL PALM SEEDLINGS (2013-2014) | FDA002004117 | N/A | GES | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | 3RD-24TH AUG | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENTOF 3,230 BAGS OF N:P:K + Mg (12:12:17+2) FERTILIZER | FDA002004119 | N/A | GES | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | 3RD-24TH AUG | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF 3,150 LITRES OF TOUCHDOWN HERBICIDE | FDA002004121 | N/A | GES | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | 3RD-24TH AUG | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF 9NO. MOTORIZED HARVESTERS | FDA002004124 | N/A | GES | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | 3RD-24TH AUG | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF 3NOS. MEDIUM-SCALE PROCESSING EQUIPMENT (MSPE) | FDA002004126 | N/A | GES | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | 3RD-24TH AUG | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
GRANT TO SERVING AGRO-ALLIED LIMITED OWERRI, IMO STATE FOR EROSION CONTROL | FDA002004134A | N/A | DIRECT | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | 3RD-24TH AUG | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF 160,800 BUDDED RUBBER STUMP | FDA002004569 | N/A | MoU | N/A | MTB | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF 2,620 BAGS OF FERTILIZERS FOR FARMERS THROUGH GES | FDA002004574 | N/A | GES | N/A | MTB | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF 2,957KG OF ORGANIC FERTILIZERS FOR FARMERS THROUGH GES | FDA002004578 | N/A | DIRECT | N/A | MTB | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF 6,864 LITERS OF GLYPHOSATE FOR FARMERS THROUGH GES | FDA002004585 | N/A | DIRECT | N/A | MTB | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
COMPUTERIZATION OF THE STAFF CLINIC AND THE SUPPLY OF HOSPITAL EQUIPMENT | HRM004005094 | HRM 01 | NCB | N/A | MTB | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF 2 NOS HILUX VEHICLE | HRM004005094 | N/A | DP | N/A | MTB | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
COMPUTERIZATION OF REGISTERY AND RECORDS | HRM004005094 | N/A | NS | N/A | PS | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF COMPUTER AND ACCESSARIES FOR THE HRM DEPARTMENT | HRM004005094 | HRM 02 | NCB | N/A | MTB | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF 100 PKTS EACH OF APER, GEN. 60 FORMS AND FILE JACKETS | HRM004005094 | HRM 03 | NCB | N/A | MTB | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF MONITORING TOOLS | MONITORING AND EVALUATION | PP&C 08 | NCB | N/A | MTB | Plan | 6TH-20TH FEBUARY | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23TH MARCH -10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31STJULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROVISION OF 15 TONS OF FOUNDATION SEEDS OF GROUNDNUT | FDA002004042 | N/A | MOU | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | 3RD-24TH AUG | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT AND DISTRIBUTION OF 5TONS EACH CERTIFIED SEEDS TO 6,876 FARMERS 34.38 TONS | FDA002004042 | N/A | GES | N/A | GES | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | 3RD-24TH AUG | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT AND DISTRIBUTION OF SINGLE SUPER PHOSPHATE (SSP) FERTILIZER | FDA002004045 | N/A | GES | N/A | GES | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | 3RD-24TH AUG | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT AND DISTRIBUTION OF ORGANIC FERTILIZER | FDA002004049 | N/A | GES | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | 3RD-24TH AUG | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT AND DISTRIBUTION OF SOIL AMENDER/MICRO NUTRIENT | FDA002004053 | N/A | GES | N/A | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | 3RD-24TH AUG | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT AND DISTRIBUTION OF SACHETS OF FUNGICIDES | FDA002004056 | N/A | GES | N/A | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | 3RD-24TH AUG | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT AND DISTRIBUTION OF HERBICIDES | FDA002004059 | N/A | GES | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | 3RD-24TH AUG | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT AND DISTRIBUTION OF INSECTICIDES | FDA002004062 | N/A | GES | N/A | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | 3RD-24TH AUG | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PRODUCTION OF 2MT BREEDER SEED SESAME | FDA002004186 | FDA 01 | NS | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PRODUCTION OF 3MT BREEDER FOUNDATION SEED SESAME | FDA002004187 | FDA 02 | NS | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
INORGANIC FERTILIZER NPK 15:15:15 | FDA002004188 | FDA 03 | GES | N/A | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | 3RD-24TH AUG | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
SOIL AMENDER/ MICRO NUTRIENT | FDA002004190 | FDA 04 | GES | N/A | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | 3RD-24TH AUG | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
HERBICIDE FOR SESAME/ACHA | FDA002004197 | FDA 05 | GES | N/A | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | 3RD-24TH AUG | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
INSECTICIDES FOR SESAME/ACHA | FDA002004198 | FDA 06 | GES | N/A | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | 3RD-24TH AUG | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
ORGANIC FERTILIZER FOR SESAME | FDA002004189 | FDA 04 | NS | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PRODUCTION OF 2MT ACHA BREEDER SEED, PRODUCTION OF 3MT ACHA ACCERSSION SEED | FDA002004196 | FDA 05 | NS | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PRODUCTION TECHNOLOGY TRANSFER STATION UBIAJA TO PRODUCE & DISTRIBUTE 43.2MT OF CERTIFIED GINGER SEED | FDA002004139 | FDA 06 | MOU | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
INORGANIC FERTILIZER: NPK 15:15:15 | FDA002004141 | FDA 07 | GES | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
ORGANIC FERTILIZER | FDA002004182 | FDA 08 | GES | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
SOIL AMENDER | FDA002004183 | FDA 09 | GES | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
AGRO CHEMICAL | FDA002004183 | FDA 10 | GES | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF 560MT OF CERTIFIED SEEDS FOR DISTRIBUTION TO 5,600 WHEAT FARMERS IN THE 12 WHEAT PRODUCING STATES | FDA002004107 | FDA 11 | ON-GOING | N/A |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | 3RD-24TH AUG | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PROVISION AND DISTRIBUTION OF 384MT OF NPK FERTILIZER | FDA002004109 | FDA 12 | ON-GOING | N/A |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | 3RD-24TH AUG | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PROVISION AND DISTRIBUTION OF 31NOS OF TREASHING MACHINES | FDA002004109 | FDA 13 | ON-GOING | N/A |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | 3RD-24TH AUG | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
PROVISION OF MILK COOLING FACILITIES AND MILK TESTING KITS TO 1000 FULANI AND SMALL HOLDER MILK PRODUCERS IN 5 STATES | APHS002004233/01 | APHS 01 | NS | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROVISION OF 1,000 BAGS OF SUPPLEMENTARY FEED AND 500 BLOCKS OF SALT LICK TO 500 ARTIFICIAL INSEMINATED FARMERS AND PASTORALISTS CONFLICTS ON STOCK ROUTES | APHS002004233/02 | APHS 02 | NS | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
SUPPLY OF CATTLE FEED TO 5 STATES | APHS002004236 | APHS 03 | NS | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF 4 CHILLERS | APHS004005034 | APHS 04 | NS | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF 6 BOER/KALAHARI BUCKS FOR UPGRADING LOCAL BREEDS OF GOATS IN 6 STATES | APHS002004238/01 | APHS 05 | NS | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF 13 CROP RESIDUE CRUSHING MACHINES FOR 13 FARMERS' COOPERATIVE SOCITIES IN 13 STATES | APHS002004238/02 | APHS 06 | NS | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF 1400 BAGS OF PIG FEED FOR FARMERS IN 4 STATES | APHS002004242 | APHS 07 | NS | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROVISION OF DAY OLD CHICKS TO FARMERS IN 20 STATES | APHS002004248/01 | APHS 08 | DIRECT | N/A | MTB | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
SUPPLY OF POULTRY FEED TO FARMERS IN 20 STATES | APHS002004248/02 | APHS 09 | DIRECT | N/A | MTB | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
SUPPLY OF POULTRY DRUGS AND VACCINES TO FARMERS IN 20 STATES | APHS002004248/03 | APHS 10 | DIRECT | N/A | MTB | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF MICROLIVESTOCK STARTER PACKS | APHS002004250 | APHS 11 | DIRECT | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF AGRIC BOOKS, JOURNALS TO THE HEADQUARTER LIBRARY | P&PC001003516 | P&PC 05 | NCB | N/A | PS | Plan | 6TH-20TH FEB | N/A | N/A | 23RD FEB-20TH MARCH | 20TH MARCH | 23RD MARCH-10TH APRIL | N/A | Plan | N/A | 13TH-24TH JULY | 27TH-31ST JULY | 3RD-24TH AUG | 28TH AUGUST | 7TH-18TH SEPT
[6 empty] | Actual | [7 empty] | Actual
ESTABLISHMENT OF PLANTAIN/ BANANA MULTIPLICATION GARDEN (SEEDS GARDEN) | FDA002004103B | FDA 01 | MOU | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | 3RD-24TH AUG | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
Note on A134: OGAH: PACKAGE NUMBER CLASH WITH RICE UNDER FDA
Note on A137: OGAH: PACKAGE NUMBER CLASH WITH RICE UNDER FDA
Note on A140: OGAH: PACKAGE NUMBER CLASH WITH CASSAVA UNDER FDA

## Works Agric
0
Budgetary Year: 2015 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan | 2 - 4 wk | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
CONSTRUCTION OF 3.2KM SURFACE DRESSED ROAD AT SCPZ SITES | DRD005005401 | DRD 01 | BOQ | NCB | N/A | MTB | Plan | 6TH-20 FEB | N/A | N/A | 23rd Feb-6th April | 6TH APRIL | 10TH-30TH APRIL | N/A | Plan | N/A | 18TH-29TH MAY | 1ST-12TH JUNE | 3RD-24TH AUG | 16 WEEKS | 12TH-16TH OCTOBER
[7 empty] | Actual | [7 empty] | Actual
REHABILITATION/CONSTRUCTION OF 2.4KM RURAL FEEDERS ROAD TO CROP PRODUCTION CLUSTERS | DRD005005403 | DRD 02 | BOQ | NCB | N/A | MTB | Plan | 6TH-20 FEB | N/A | N/A | 23rd Feb-6th April | 6TH APRIL | 10TH-30TH APRIL | N/A | Plan | N/A | 18TH-29TH MAY | 1ST-12TH JUNE | 3RD-24TH AUG | 16 WEEKS | 12TH-16TH OCTOBER
[7 empty] | Actual | [7 empty] | Actual
PROVISION OF 5 UNITS MOTORIZED BOREHOLES FOR RURAL COMMUNITIES | DRD003004949 |  | LUM | NS | N/A | MTB | Plan | 6TH-20 FEB | N/A | N/A | 23rd Feb-6th April | 6TH APRIL | 10TH-30TH APRIL | N/A | Plan | N/A | 18TH-29TH MAY | 1ST-12TH JUNE | 3RD-24TH AUG | 16 WEEKS | 12TH-16TH OCTOBER
|  | DRD 03 |  |  |  |  | Actual | [7 empty] | Actual
PROVISION OF 10 UNITS EQUIPPED HAND PUMP BOREHOLES FOR RURAL COMMUNITIES | DRD003004958 | DRD 04 | LUM | NS | N/A | MTB | Plan | 6TH-20 FEB | N/A | N/A | 23rd Feb-6th April | 6TH APRIL | 10TH-30TH APRIL | N/A | Plan | N/A | 18TH-29TH MAY | 1ST-12TH JUNE | 3RD-24TH AUG | 16 WEEKS | 12TH-16TH OCTOBER
[7 empty] | Actual | [7 empty] | Actual
PROVISION OF 7 UNITS OF HOMESTEAD/ BACKYARD IRRIGATION FACILITIES | DRD003004964 | DRD 05 | LUM | NS | N/A | MTB | Plan | 6TH-20 FEB | N/A | N/A | 23rd Feb-6th April | 6TH APRIL | 10TH-30TH APRIL | N/A | Plan | N/A | 18TH-29TH MAY | 1ST-12TH JUNE | 3RD-24TH AUG | 16 WEEKS | 12TH-16TH OCTOBER
[7 empty] | Actual | [7 empty] | Actual
PROVISON OF CUMULATIVE 4KM EARTH ROAD AND 2 UNITS OF DRYING SLAB AT TWO ENCLAVE PROJECT | DRD003004964 | DRD 06 | LUM | NS | N/A | MTB | Plan | 6TH-20 FEB | N/A | N/A | 23rd Feb-6th April | 6TH APRIL | 10TH-30TH APRIL | N/A | Plan | N/A | 18TH-29TH MAY | 1ST-12TH JUNE | 3RD-24TH AUG | 16 WEEKS | 12TH-16TH OCTOBER
[7 empty] | Actual | [7 empty] | Actual
PAYMENT OF OUTSTANDING LIABILITIES ON RURAL ROADS AND RELATED PROJECTS, CONSTITUENCY ETC | DRD005005408 | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA
PAYMENT OF OUTSTANDING LIABILITIES ON RURAL ROADS AND RELATED PROJECTS, CONSTITUENCY ETC | [6 empty] | Plan
PAYMENT OF OUTSTANDING DEBT RELIEF FUND PROJECTS / MDG DEBTS | MDG DEBTS | NA | NA |  | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA
INSTALLATION OF INTRANET TO ENABLE THE WAREHOUSING OF BUSINESS PROCESS SOFTWARE | ICT004005081 | ICT 03 | BOQ | NCB | N/A | MTB | Actual | 6TH-20 FEB | N/A | N/A | 23rd Feb-6th April | 6TH APRIL | 10TH-30TH APRIL | N/A | Plan | N/A | 18TH-29TH MAY | 1ST-12TH JUNE | 3RD-24TH AUG | 16 WEEKS | 12TH-16TH OCTOBER
[7 empty] | Actual | [7 empty] | Actual
MAINTENANCE OF ICT EQUIPMENT | ICT007005415 | ICT 04 | BOQ | NCB | N/A | MTB | Plan | 6TH-20 FEB | N/A | N/A | 23rd Feb-6th April | 6TH APRIL | 10TH-30TH APRIL | N/A | Plan | N/A | 18TH-29TH MAY | 1ST-12TH JUNE | 3RD-24TH AUG | 16 WEEKS | 12TH-16TH OCTOBER
[7 empty] | Actual | [7 empty] | Actual
PROCUREMENT AND INSTALLATION OF MID IFRA RED (MIR) SOIL TEST EQUIPMENTS | AL&CCM004005015 | AL&CCM 04 | BOQ | NCB | N/A | PS | Plan | 6TH-27TH FEB | N/A | 2ND MARCH-13TH APRIL | 2ND MARCH-13TH APRIL | 13TH APRIL | 20TH APRIL-8TH MAY | N/A | Plan | N/A | 25TH-29TH MAY | 1ST-12JUNE | 3RD-24TH AUG | 4 WEEKS | 31ST JULY-7TH AUGUST
[7 empty] | Actual | [7 empty] | Actual
SERVICING AND MAINTENANCE OF GIS INFRASTRUCTURE TOGETHER WITH COMMUNICATION SOFTWARE | AL&CCM004005015 | AL&CCM 05 | BOQ | NCB | N/A | PS | Plan | 6TH-27TH FEB | N/A | 2ND MARCH-13TH APRIL | 2ND MARCH-13TH APRIL | 13TH APRIL | 20TH APRIL-8TH MAY | N/A | Plan | N/A | 25TH-29TH MAY | 1ST-12JUNE | 3RD-24TH AUG | 2 WEEKS | 31ST JULY-7TH AUGUST
[7 empty] | Actual | [7 empty] | Actual
REHABILITATION OF BUILDING WORKS AT NAT. SOIL & WATER LAB/ OFICE COMPLEX KADUNA | AL&CCM004005015 | AL&CCM 06 | BOQ | NCB | N/A | PS | Plan | 6TH-27TH FEB | N/A | 2ND MARCH-13TH APRIL | 2ND MARCH-13TH APRIL | 13TH APRIL | 20TH APRIL-8TH MAY | N/A | Plan | N/A | 25TH-29TH MAY | 1ST-12JUNE | 3RD-24TH AUG | 2 WEEKS | 31ST JULY-7TH AUGUST
[7 empty] | Actual | [7 empty] | Actual
CONSTRUCTION OF INTEGRATED COOPERATIVE SERVICE CENTRE | FDC004005039/01 | FDC 01 | BOQ | NCB | N/A | MTB | Plan | 6TH-20 FEB | N/A | N/A | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | Plan | N/A | 18TH-29TH MAY | 1ST-12TH JUNE | 3RD-24TH AUG | 12 WEEKS | 12TH-29TH OCTOBER
[7 empty] | Actual | [7 empty] | Actual
REACTIVATION OF KARU FRUIT AND VEGITABLE MODEL MARKET | FDC004005039/03 | FDC 03 | BOQ | NCB | N/A | MTB | Plan | 6TH-20 FEB | N/A | N/A | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | Plan | N/A | 18TH-29TH MAY | 1ST-12TH JUNE | 3RD-24TH AUG | 12 WEEKS | 12TH-29TH OCTOBER
[7 empty] | Actual | [7 empty] | Actual
COMPLETION OF PERIMETER FENCE AND GENERAL MAINTENANCE WORK | FDC004005039/02 | FDC 02 | BOQ | NS | N/A | PS | Plan | 6TH-20 FEB | N/A | N/A | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | Plan | N/A | 18TH-29TH MAY | 1ST-12TH JUNE | 3RD-24TH AUG | 4 WEEKS | 12TH-29TH OCTOBER
[7 empty] | Actual | [7 empty] | Actual
DESIGN AND CONSTRUCTION OF ADMINISTRATIVE OFFICES FOR SCPZ SITES | ABM004005056/01 | ABM 04 | BOQ | NCB | N/A | MTB | Plan | 6TH-20 FEB | N/A | N/A | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | Plan | N/A | 18TH-29TH MAY | 1ST-12TH JUNE | 3RD-24TH AUG | 16 WEEKS | 12TH-29TH OCTOBER
[7 empty] | Actual | [7 empty] | Actual
CONSTRUCTION OF SURFACE DRESSED ROADS TO SCPZs | ABM005005403/01 | ABM 05 | LUM | NCB | N/A | MTB | Plan | 6TH-20 FEB | N/A | N/A | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | Plan | N/A | 18TH-29TH MAY | 1ST-12TH JUNE | 3RD-24TH AUG | 16 WEEKS | 12TH-29TH OCTOBER
[7 empty] | Actual | [7 empty] | Actual
REHABILITATION/CONSTRUCTION OF RURAL FEEDER ROADS TO CROP PRODUCTION CLUSTERS | ABM005005405/01 | ABM 06 | LUM | NCB | N/A | MTB | Plan | 6TH-20 FEB | N/A | N/A | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | Plan | N/A | 18TH-29TH MAY | 1ST-12TH JUNE | 3RD-24TH AUG | 16 WEEKS | 12TH-29TH OCTOBER
[7 empty] | Actual | [7 empty] | Actual
ESTABLISHMENT OF FISH FINGERLING PRODUCTION CENTRES | FDF002004295/01 | FDF 01 | LUM | NCB | N/A | MTB | Plan | 6TH-20 FEB | N/A | N/A | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | Plan | N/A | 18TH-29TH MAY | 1ST-12TH JUNE | 3RD-24TH AUG | 16 WEEKS | 12TH-29TH OCTOBER
[7 empty] | Actual | [7 empty] | Actual
UPGRADING OF FISH FEED MILL THROUGH INCORPORATION OF EXTRUDING DEVICE TO PRODUCE FLOATING FEEDS | FDF002004418/01 | FDF 02 | LUM | NCB | N/A | MTB | Plan | 6TH-20 FEB | N/A | N/A | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | Plan | N/A | 18TH-29TH MAY | 1ST-12TH JUNE | 3RD-24TH AUG | 16 WEEKS | 12TH-29TH OCTOBER
[7 empty] | Actual | [7 empty] | Actual
FABRICATION/ESTABLISHMENT OF COTTAGE FISH PROCESSING PLANTS TO MEET STANDARD FOR FISH CERTIFICATION | FDF002004438/01 | FDF 03 | LUM | NCB | N/A | MTB | Plan | 6TH-20 FEB | N/A | N/A | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | Plan | N/A | 18TH-29TH MAY | 1ST-12TH JUNE | 3RD-24TH AUG | 16 WEEKS | 12TH-29TH OCTOBER
[7 empty] | Actual | [7 empty] | Actual
ESTABLISHMENT OF MODEL FISH MARKET | FDF002004256/01 | FDF 04 | LUM | NCB | N/A | MTB | Plan | 6TH-20 FEB | N/A | N/A | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | Plan | N/A | 18TH-29TH MAY | 1ST-12TH JUNE | 3RD-24TH AUG | 16 WEEKS | 12TH-29TH OCTOBER
[7 empty] | Actual | [7 empty] | Actual
RENOVATION/COMPLETION AND INSTALLATION OF EQUIPMENTS FOR THE UPGRADE OF NATIONAL FISHERIES LABORATORIES LAGOS | FDF002004441/01 | FDF 05 | LUM | NCB | N/A | MTB | Plan | 6TH-20 FEB | N/A | N/A | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | Plan | N/A | 18TH-29TH MAY | 1ST-12TH JUNE | 3RD-24TH AUG | 16 WEEKS | 12TH-29TH OCTOBER
[7 empty] | Actual | [7 empty] | Actual
SUPPLY AND INSTALLATION OF EQUIPMENTS FOR THE UPGRADE OF NATIONAL FISHERIES LABORATORIES, LAGOS | FDF002004447/01 | FDF 06 | LUM | NCB | N/A | MTB | Plan | 6TH-20 FEB | N/A | N/A | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | Plan | N/A | 18TH-29TH MAY | 1ST-12TH JUNE | 3RD-24TH AUG | 16 WEEKS | 12TH-29TH OCTOBER
[7 empty] | Actual | [7 empty] | Actual
REHABILITATION OF OLD EXISTING SILO COMPLEXES AND REPLACEMENT OF OBSOLETE SILO EQUIPMENT | FSRD/004005049 | FSRD 11 | BOQ | NCB | N/A | MTB | Plan | 6TH -20TH FEB | N/A | N/A | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | Plan | N/A | 18TH-19TH MAY | 1ST-12THJUNE | 3RD-24TH AUG | 16WEEKS | 12TH-16TH OCTORBER
[7 empty] | Actual | [7 empty] | Actual
PRODUCTION OF MONITORING REPORT |  | P&PC 09 | BOQ | N,S | N/A | PS | Plan | 6TH -20TH FEB | N/A | N/A | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | Plan | N/A | 18TH-19TH MAY | 1ST-12THJUNE | 3RD-24TH AUG | 16WEEKS | 12TH-16TH OCTORBER
[7 empty] | Actual | [7 empty] | Actual
REHABILITATION AND UPGRADING OF FOOD CROP PRODUCTION TECHNOLOGY TRANSFER STATION (FCPTTS) IN ENUGU, YOBE, EDO AND KANO | FDA002005400A/(FDA SPECIAL PROJECT) | FDA 01 | BOQ | NCB | N/A | MTB | Plan | 6TH -20TH FEB | N/A | N/A | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | Plan | N/A | 18TH-19TH MAY | 1ST-12THJUNE | 3RD-24TH AUG | 16WEEKS | 12TH-16TH OCTORBER
[7 empty] | Actual | [7 empty] | Actual
REHABILITATION OF FACILITIES AT BATSU IN ILORIN, CSU IN IBADAN, MECHANICS TRAINING CENTRE IN AKURE AND MISAU IN BAUCHI (FDA SPECIAL PROJECT) | FDA002005400B/(FDA SPECIAL PROJECT) | FDA 02 | BOQ | NCB | N/A | MTB | Plan | 6TH -20TH FEB | N/A | N/A | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | Plan | N/A | 18TH-19TH MAY | 1ST-12THJUNE | 3RD-24TH AUG | 16WEEKS | 12TH-16TH OCTORBER
[7 empty] | Actual | [7 empty] | Actual

## Consultancy Agric
Ministry/Department/Agency: |  | FEDERAL MINISTRY OF AGRICULTURE AND RURAL DEVELOPMENT
Budgetary Year: 2015 |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | Contract Type |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Approval Threshold | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report
Norm Duration of Proc Steps |  |  |  | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks | 4 wk |  | 3 wks | Plan
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
List of Contracts
EXTENDING GOOD AGRICULTURAL PRACTICES THROUGH COMMUNAL LEARNING BY FARMERS | QCBS | LUMPSUM | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
PROVIDE FARMERS WITH PROPER AGRONOMIC PRACTICES ON ALL CROPS THROUGHOUT THE YEAR | QCBS | LUMPSUM | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
PROVIDE FARMERS WITH ALERTS ON GOOD AGRICULTURAL PRACTICES THROUGH THEIR PHONES AND ANSWERING FIELD QUESTIONS USING TOLL FREE LINES | QCBS | LUMPSUM | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
REVIEW DEMONSTRATED TECHNOLOGY AT STATE LEVELS THROUGH MEETINGS WITH EXTENSION AGENTS AND FARMERS | QCBS | LUMPSUM | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
PROMOTE DEMAND DRIVEN EXTENSION SERVICES | QCBS | LUMPSUM | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
TECHNICAL FORUMS FOR NATIONAL EXTENSION DELIVERY | QCBS | LUMPSUM | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CAPACITY BUILDING FOR EXTENSION AGENT | QCBS | LUMP SUM | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CAPACITY BUILDING FOR EXTENSION STAFF | QCBS | LUMP SUM | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
TRAINING OF 3,000 YOUTH IN TEN VALUE CHAINS INCLUDING PLANTING, STORAGE, PROCESSING AND MARKETING | MOU | TIME BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
MENTORING OF 3000 COMMERCIAL FARMERS | MOU | TIME BASED | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
POST TRAINING MEDIA DOCUMENTARY | MOU | TIME BASED | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
TRAINING OF 2,500 WOMEN IN TEN VALUE CHAINS INCLUDING PLANTING, STORAGE, PROCESSING AND MARKETING | MOU | TIME BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
VULNERABLE ANALYSIS AND MAPPING OF VULNERABLE GROUPS: SURVEY ANALYSIS AND GROUP FORMATION | MOU | TIME BASED | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
TRAINING OF 1,000 VULNERABLE PERSONS ON AGRIC VALUE CHAINS AND OFF-FARM INCOME GENERATION ACTIVITIES | MOU | TIME BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
GENDER MAINSTRAMING | MOU | TIME BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
DESIGN OF TWO SKIN COLLECTION CENTRES | CQ | TIME BASED | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
DEVELOPMENT AND DISSEMINATION OF INTEGRATED PEST MANAGEMENT PLAN FOR MIGRATORY PESTS (BIOLOGICAL CONTROL) | CQ | TIME BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CONDUCT OF RISK ASSESSMENT AND ANALYSIS | LC | TIME BASED | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CONDUCT OF TRACE BACK AND FORWARD INVESTIGATION OF TADs OUTBREAKS | LC | TIME BASED | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
UPGRADING AND MAINTENACE OF VETERINARY CERTIFICATION DATABASE & SINGLE WINDOW INTEGRATED SYSTEM | QCBS | LUMP SUM | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
RENEWAL OF PREMIUM ON INSURED VEHICLES AND ASSETS OF THE MINISTRY | LC | LUMP SUM | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
PROVISION OF SECURITY SERVICES | LC | TIME BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
RENEWAL OF OFFICE ACCOMODATION | N/A | N/A | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CAPACITY BUILDING FOR SERVICOM STAFF IN THE HEADQUARTERS | LC | TIME BASED | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
SENSITIZATION OF SERVICOM STAFF NATIONWIDE | LC | TIME BASED | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
DEVELOPMENT OF PLATFORM/IMPACT ASSESSMENT OF GES | LC | TIME BASED | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
TRAINING / SEMINAR FOR 1000 HEADQUARTERS' STAFF ON ICT FOR EFFECTIVE DISSEMINATION OF INFORMATION | QCB | TIME BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
PROVISION TO UNDERSTUDY THE CELLULANT ON THE E-WALLET TECHNOLOGY | N/A | N/A | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
DESIGN OF CUSTOMISED APPLICATION FOR ALL THE VALUE CHAINS | QCB | TIME BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CREATION OF PLATFORM FOR THE COORDINATION OF RESEARCH INSTITUTES AND PARASTATALS' ICT ACTIVITIES ESPECIALLY THE WEBSITE | LC | TIME BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
PROVISION OF MOBILE APPLICATION TO SUPPORT ATA PROGRAMMES | LC | TIME BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
PROVISION OF INTERNET BANDWIDTH FOR THE MINISTRY'S NETWORK | LC | TIME BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
ESTABLISHMENT OF e-AGRIC PORTAL IN COLLABORATION WITH NITDA | LC | TIME BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
SPECIALISED TRAINING FOR WEBSITE EDITORS FROM REGINAL AND STATE OFFICES | LC | TIME BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
TRAINING OF ICT STAFF ON CLOUD COMPUTING, ORACLE AND JAVA | LC | TIME BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
TRAINING OF 300 AGRIC STATE OFFICERS ON ICT | LC | TIME BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CAPACITY BUILDING FOR FARMERS ON HANDLING OF TISSUE CULTURE | QCBS | TIME BASED | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
TRAINING OF ALCCMS STAFF AT ALL STAGES ON DATA GATHERING INPUT & ANALYSIS | NCB | TIME BASED | MTB | Plan | 6th feb-6th march | 6th feb-6th march | 1st may- 22nd may | 22nd may-5th june | 5th june- 19th june | 19th june-3rd july | 3rd july-17th july | Plan | 17th july-31st july | N/A | 3rd july - 31st july | August | 1st August-22nd August | Plan | 3RD-24TH AUG | 1st -11th Sept | 25th - 30 Sept
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CONDUCT DIGITAL SOIL MAP, DEVELOP APPROPRIATE SOIL/FARM MANAGEMENT, DEVELOP CAPACITY OF STAFF, ACQUIRE AND DIGITISE LEGACY DATA AND DEVELOP NISIS INFRASTRUCTURE TO AFSIS | NCB | TIME BASED | MTB | Plan | 6th feb-6th march | 6th feb - 1st may | 1st may- 22nd may | 22nd may-5th june | 5th june- 19th june | 19th june-3rd july | 3rd july-17th july | Plan | 17th july-31st july | N/A | 3rd july - 31st july | August | 1st August-22nd August | Plan | 3RD-24TH AUG | 1st -11th Sept | 25th - 30 Sept
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
TRAINING OF EXTENSION AGENTS ON THE USE OF SOIL DOC FOR ON THE SPOT ASSESSMENT | NCB | TIME BASED | MTB | Plan | 6th feb-6th march | 6th feb - 1st may | 1st may- 22nd may | 22nd may-5th june | 5th june- 19th june | 19th june-3rd july | 3rd july-17th july | Plan | 17th july-31st july | N/A | 3rd july - 31st july | August | 1st August-22nd August | Plan | 3RD-24TH AUG | 1st -11th Sept | 25th - 30 Sept
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
DESIGN AND SUPERVISION FOR THE CONSTRUCTION OF WATER HARVESTING STRUCTURE | NCB | TIME BASED | MTB | Plan | 6th feb-6th march | 6th feb - 1st may | 1st may- 22nd may | 22nd may-5th june | 5th june- 19th june | 19th june-3rd july | 3rd july-17th july | Plan | 17th july-31st july | N/A | 3rd july - 31st july | August | 1st August-22nd August | Plan | 3RD-24TH AUG | 1st -11th Sept | 25th - 30 Sept
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
TRAINING OF STAFF ON THE USE AND CALIBRATION OF THE EQUIPMENT | NCB | TIME BASED | MTB | Plan | 6th feb-6th march | 6th feb - 1st may | 1st may- 22nd may | 22nd may-5th june | 5th june- 19th june | 19th june-3rd july | 3rd july-17th july | Plan | 17th july-31st july | N/A | 3rd july - 31st july | August | 1st August-22nd August | Plan | 3RD-24TH AUG | 1st -11th Sept | 25th - 30 Sept
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
SAMPLING ANALYSIS & MONITORING OF SOIL, ESTABLISHMENT OF AGROFORESTRY TECHNOLOGY AND TRAINING OF FARMERS | NBC | TIME BASED | MTB | Plan | 6th feb-6th march | 6th feb - 1st may | 1st may- 22nd may | 22nd may-5th june | 5th june- 19th june | 19th june-3rd july | 3rd july-17th july | Plan | 17th july-31st july | N/A | 3rd july - 31st july | August | 1st August-22nd August | Plan | 3RD-24TH AUG | 1st -11th Sept | 25th - 30 Sept
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
AGRICULTURAL RESILENCE FOR CLIMATE CHANGE | NCB | TIME BASED | MTB | Plan | 6th feb-6th march | 6th feb - 1st may | 1st may- 22nd may | 22nd may-5th june | 5th june- 19th june | 19th june-3rd july | 3rd july-17th july | Plan | 17th july-31st july | N/A | 3rd july - 31st july | August | 1st August-22nd August | Plan | 3RD-24TH AUG | 1st -11th Sept | 25th - 30 Sept
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
WORKSHOP FOR 50 OFFICERS (PROG. SUPPORT OFFICERS AND SUBJECT MATTER SPECIALISTS) | L.C | TIME BASED | P.S | Plan | 6th feb-6th march | 6th feb - 1st may | 1st may- 22nd may | 22nd may-5th june | 5th june- 19th june | 19th june-3rd july | 3rd july-17th july | Plan | 17th july-31st july | N/A | 3rd july - 31st july | August | 1st August-22nd August | Plan | 3RD-24TH AUG | 1st -11th Sept | 25th - 30 Sept
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
ON FARM WORKSHOP FOR 50 ONION FARMERS | L.C | TIME BASED | P.S | Plan | 6th feb-6th march | 6th feb - 1st may | 1st may- 22nd may | 22nd may-5th june | 5th june- 19th june | 19th june-3rd july | 3rd july-17th july | Plan | 17th july-31st july | N/A | 3rd july - 31st july | August | 1st August-22nd August | Plan | 3RD-24TH AUG | 1st -11th Sept | 25th - 30 Sept
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
WORKSHOP FOR 50NOS PROGRAMME SUPPORT OFFICERS (FIELD OFFICERS) AND MARKETERS OF FRUITS | L.C | TIME BASED | P.S | Plan | 6th feb-6th march | 6th feb - 1st may | 1st may- 22nd may | 22nd may-5th june | 5th june- 19th june | 19th june-3rd july | 3rd july-17th july | Plan | 17th july-31st july | N/A | 3rd july - 31st july | August | 1st August-22nd August | Plan | 3RD-24TH AUG | 1st -11th Sept | 25th - 30 Sept
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
HORTICULTURE VALUE CHAIN STAKEHOLDERS MEETING (HORTICULTURE ASS.) | L.C | TIME BASED | P.S | Plan | 6th feb-6th march | 6th feb - 1st may | 1st may- 22nd may | 22nd may-5th june | 5th june- 19th june | 19th june-3rd july | 3rd july-17th july | Plan | 17th july-31st july | N/A | 3rd july - 31st july | August | 1st August-22nd August | Plan | 3RD-24TH AUG | 1st -11th Sept | 25th - 30 Sept
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
MEETING WITH HORTICULTURE AGRO-INPUT DEALERS ON CONSTRAINTS IN INOUT DISTRIBUTION | L.C | TIME BASED | P.S | Plan | 6th feb-6th march | 6th feb - 1st may | 1st may- 22nd may | 22nd may-5th june | 5th june- 19th june | 19th june-3rd july | 3rd july-17th july | Plan | 17th july-31st july | N/A | 3rd july - 31st july | August | 1st August-22nd August | Plan | 3RD-24TH AUG | 1st -11th Sept | 25th - 30 Sept
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
STRATEGIC PLAN FOR HORTICUTURE FRESH PRODUCE DISTRIBUTION & MARKETING | L.C | TIME BASED | P.S | Plan | 6th feb-6th march | 6th feb - 1st may | 1st may- 22nd may | 22nd may-5th june | 5th june- 19th june | 19th june-3rd july | 3rd july-17th july | Plan | 17th july-31st july | N/A | 3rd july - 31st july | August | 1st August-22nd August | Plan | 3RD-24TH AUG | 1st -11th Sept | 25th - 30 Sept
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
ADVERT PLACEMENT FOR HORTICULTURE VALUE CHAIN ACTIVITIES | MOU | TIME BASED | P.S | Plan | 6th feb-6th march | 6th feb - 1st may | 1st may- 22nd may | 22nd may-5th june | 5th june- 19th june | 19th june-3rd july | 3rd july-17th july | Plan | 17th july-31st july | N/A | 3rd july - 31st july | August | 1st August-22nd August | Plan | 3RD-24TH AUG | 1st -11th Sept | 25th - 30 Sept
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
ESTABLISHMENT OF 14 HA OF INDUSTRIARL SEEDCANE | MOU | TIME BASED | MOU | Plan | 6th feb-6th march | 6th feb - 1st may | 1st may- 22nd may | 22nd may-5th june | 5th june- 19th june | 19th june-3rd july | 3rd july-17th july | Plan | 17th july-31st july | N/A | 3rd july - 31st july | August | 1st August-22nd August | Plan | 3RD-24TH AUG | 1st -11th Sept | 25th - 30 Sept
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
MULTIPLICATION AND DISTRIBUTION OF SEEDCANE THROUGH TISSUE CULTURE | MOU | TIME BASED | MOU | Plan | 6th feb-6th march | 6th feb - 1st may | 1st may- 22nd may | 22nd may-5th june | 5th june- 19th june | 19th june-3rd july | 3rd july-17th july | Plan | 17th july-31st july | N/A | 3rd july - 31st july | August | 1st August-22nd August | Plan | 3RD-24TH AUG | 1st -11th Sept | 25th - 30 Sept
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
AUDITING/ RESCUCITATION OF 2 MORIBUND SME SUGARCANE PROCESSING MILLS THROUGH MOU WITH NCRI | MOU | TIME BASED | MOU | Plan | 6th feb-6th march | 6th feb - 1st may | 1st may- 22nd may | 22nd may-5th june | 5th june- 19th june | 19th june-3rd july | 3rd july-17th july | Plan | 17th july-31st july | N/A | 3rd july - 31st july | August | 1st August-22nd August | Plan | 3RD-24TH AUG | 1st -11th Sept | 25th - 30 Sept
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
WORKSHOP ON AWARENESS AND CAPACITY BUILDING FOR SUGARCANE PROCESSORS & FARMERS ON STRATEGYFOR ACCESSING LOANS FROM BOS, BOI AND OTHER FINANCIAL INSTITUTIONS | MOU | TIME BASED | MOU | Plan | 6th feb-6th march | 6th feb - 1st may | 1st may- 22nd may | 22nd may-5th june | 5th june- 19th june | 19th june-3rd july | 3rd july-17th july | Plan | 17th july-31st july | N/A | 3rd july - 31st july | August | 1st August-22nd August | Plan | 3RD-24TH AUG | 1st -11th Sept | 25th - 30 Sept
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CAPACITY BUILDING OF 44 GINGER FARMERS ON PRODUCTION AND COMMERTIALIZATION OF GINGER CROP | MOU | TIME BASED | PS | Plan | 6th feb-6th march | 6th feb - 1st may | 1st may- 22nd may | 22nd may-5th june | 5th june- 19th june | 19th june-3rd july | 3rd july-17th july | Plan | 17th july-31st july | N/A | 3rd july - 31st july | August | 1st August-22nd August | Plan | 3RD-24TH AUG | 1st -11th Sept | 25th - 30 Sept
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CAPACITY BUILDING OF 156 GINGER FARMERS AND PROCESSORS ON PROCESSING, PACKAGING, STORAGE& MARKETING OF GINGER PRODUCTS AT FED. COLL. OF AGRIC. PRODUCE TECH KANO | MOU | TIME BASED | MOU | Plan | 6th feb-6th march | 6th feb - 1st may | 1st may- 22nd may | 22nd may-5th june | 5th june- 19th june | 19th june-3rd july | 3rd july-17th july | Plan | 17th july-31st july | N/A | 3rd july - 31st july | August | 1st August-22nd August | Plan | 3RD-24TH AUG | 1st -11th Sept | 25th - 30 Sept
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CAPACITY BUILDING OF 74 GINGER FARMERS ON GOOD AGRONOMIC PRACTICES (GAP) FOR INCREASED PRODUCTION | MOU | TIME BASED | MOU | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
WORKSHOP ON POPULARISATION OF USERS AND HEALTH BENEFIT OF GINGER | L.C | TIME BASED | P.S | Plan | 6th feb-6th march | 6th feb - 1st may | 1st may- 22nd may | 22nd may-5th june | 5th june- 19th june | 19th june-3rd july | 3rd july-17th july | Plan | 17th july-31st july | N/A | 3rd july - 31st july | August | 1st August-22nd August | Plan | 3RD-24TH AUG | 1st -11th Sept | 25th - 30 Sept
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
SUPPORT TO MEDIA AND COMMUNICATION | L.C | TIME BASED | P.S | Plan | 6th feb-6th march | 6th feb - 1st may | 1st may- 22nd may | 22nd may-5th june | 5th june- 19th june | 19th june-3rd july | 3rd july-17th july | Plan | 17th july-31st july | N/A | 3rd july - 31st july | August | 1st August-22nd August | Plan | 3RD-24TH AUG | 1st -11th Sept | 25th - 30 Sept
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
ENCODING OF 50,000 FORMS (FINANCIAL & NON-FINANCIAL) OF COOPERATIVES INTO THE NATIONAL DATA PLATFORM | QCBS | TIME-BASED | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
IDENTIFICATION, PROMOTION AND FACILITATION OF THE FORMATION OF 10 NOS. COOPERATIVES/ FARMER GROUPS | QCBS | TIME-BASED | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
ORGANIZATION OF 1 NO. NATIONAL WORKSHOP FOR 50 NOS. FARMERS' GROUPS/ COOPERATIVES ON IMPROVING ACCESS TO CREDIT FROM FINANCIAL SERVICE PROVIDERS | QCBS | TIME-BASED | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
STATUTORY VISITS AND INSPECTION OF 30 NOS. APEX COOPERATIVE TO ENFORCE BEST PRACTICES | QCBS | TIME-BASED | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
ORGANIZATION POF ANNUAL RETREAT FOR 60NOS. COOPERATIVE OFFICERS FROM THE STATE | QCBS | TIME-BASED | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
SUPERVISION/COORDINATION OF ACTIVITIES OF COOPERATIVE TRANSFORMATION ACTION PLAN (CTAP) | QCBS | TIME-BASED | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
SUPPORT FOR COLLECTION AND COLLATION OF FIELD QUARTELY REPORTS FROM THE STATES | QCBS | TIME-BASED | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
MEDIA/ADVERTORIALS OF COOPERATIVE TRANSFORMATION ACTION PLAN ACTIVITIES | QCBS | TIME-BASED | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
ANNUAL SUBSCRIPTION TO INTERNATIONAL COOPERATIVE ALLIANCE | QCBS | LUMPSUM | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CONDUCT OF SEMINARS AND CONFERENCES | QCBS | TIME-BASED | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
PRIVATE SECTOR INVESTMENT FACILITATION | LC | TIME-BASED | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
INTERNATIONAL CONFERENCES- EUROPEAN MARKET RESEARCH COMMISSION (EMRC), WORLD ECONOMIC FORUM (WEF), NIGERIA ECONOMIC SUBMIT GROUP (NESG) GROW AFRICA, TRADE FAIRS ETC | LC | TIME-BASED | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
PROMOTION AND ADVOCACY ACTIVITIES FOR PRIORITY VALUE CHAINS | LC | TIME-BASED | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
DATA SOURCING AND PRODUCTION OF AGRIBUSINESS INVESTMENT BRIEF/GUIDES FOR PRIORITY VALUE CHAINS | LC | TIME-BASED | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
MARKET RESEARCH TEST MARKET AND CONSUMER INSIGHT FOR COMMERCIALIZATION | LC | TIME-BASED | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
PROMOTION OF FINANCIAL INCLUSION IN THE RURAL COMMUNITIES WITHIN THE STAPLE CROPS PROCESSING ZONES | LC | TIME-BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CRITICAL SAFEGUARDS STUDIES FOR ENVIRONMENTAL AND SOCIAL MANAGEMENT FRAMEWORK (ESMF), RESSETTLEMENT POLICY FRAMEWORK (RPF), INTEGRATED PEST MANAGEMENT PLAN (IPMP) AGRICULTURAL LAND USE, FINANCIAL AND ECONOMIC ANALYSIS | LC | TIME-BASED | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
VERIFICATION/ASSESSMENT EXERCISE ON THE EXISTING FISH FARM ESTATE | LC | TIME-BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
SENSITIZATION WORKSHOPS ON CANOE/CRAFTS REGISTRATION & DATA COLLECTION | QCBS | TIME-BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
GEOPOLITICAL ZONE WORKSHOPS ON THE SECOND PHASE OF ECOWAS PROJECTS | LC | TIME-BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
FISHERIES DATA COLLECTION IN THE 36 STATES AND FCT | LC | TIME-BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
SUPPORT FOR INVESTMENT AGRO-PROCESSING AND PRODUCT DEVELOPMENT | LC | TIME-BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
SUPPORT FOR SORGHUM, PRODUCTION, UTILIZATION AND COMMERCIALIZATION IN NIGERIA | LC | TIME-BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
SUPPORT FOR INVESTMENT IN AGRO-PROCESSING, PRODUCT DEVELOPMENT- SORGHUM | LC | TIME-BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
SEED DRESSING(PRACTICES AND SEED PROTECTION DEVELOPMENT) | LC | TIME BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
TRAINING OF 25,000 FARMERS ON FARMER BUSINESS SCHOOL | QCBS | TIME-BASED | MOU | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
TISSUE CULTURE DEVELOPMENT | QCBS | TIME-BASED | MOU | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
COCOA VARIETY & CAPACITY DEVELOPMENT | QCBS | TIME BASED | MOU | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
COMMUNITY SEED GARDEN BUDWOOD ESTABLISHMENT | QCBS | TIME BASED | MOU | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
REHABILITATION OF OLD PLANTATION | SS | LS | MOU | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
TRAINING OF ALCCMS STAFFS AT ALL STAGES ON DATA GATHERING INPUT AND ANALYSIS | QCBS | LS | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH -31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
DIGITAL SOIL MAP, FARM MANAGEMENT DECISSION SYSTEM, DEVELOPMENT OF STAFF, ACQUIRE AND DIGITALIZE LEGACY DATA AND DEVELOP NISIS INFRASTRUCTURE | Q&CBS | TIME BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
TRAINING OF EXTENSION AGENTS ON THE USE OF SOILDOC FOR ON THE SPOT ASSESSMENT | LCS | LS | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
MAPPING, ADVOCACY/ SENSITIZATION AND ON-FARM ESTABLISHMENT AND MAINTENANCE OF AGROFORESTRY | Q&CBS | TIME BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
DESIGN AND SUPERVISION FOR CONSTRUCTION OF FARM WATER STRUCTURE | LCS | LUMP SUM | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
TRAINING OF STAFF ON THE USE AND CALIBRATION OF THE EQUIPMENT | LCS | LUMP SUM | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND JUNE-3RD JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
TRAINING/ CAPACITY BUILDING OF STAFFON GRAIN MANAGEMENT AND SILO COMPLEXES | LCS | LUMP SUM | MTB | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
MEETINGS, SUPERVISORY VISITS AND MONITORING OF PROJECTS/ AACTIVITIES | LCS | LUMP SUM | MTB | Plan | 2ND FEB- 6TH APRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
RESEARCH IN TO SOCIO-ECONOMIC IMPACT OF THE PRESENT AGRICULTURAL POLICY e.i TH AGRICULTURAL TRANSFORMATION AGENDA | LCS | LUMP SUM | MTB | Plan | 2ND FEB- 6TH APRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
THE AGRICULTURALTRANSFORMATION AGENDA (ATA) POLICY SITUATION ANALYSIS | LCS | LUMP SUM | MTB | Plan | 2ND FEB- 6TH APRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
OPERATION, ORGANIZATION AND MANAGEMENT RESEARCH OF THE MINISTRY(RESEARCH IN TO THE INTERNAL ORGANIZATION AND OPERATIONAL MODALITIES OF THE MINISTRY) | LCS | LUMP SUM | MTB | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CONSTRAINT ANALYSIS OF PERFORMANCE AND DELIVERY OF TARGETS OF THE MINISTRY's OPERATION | LCS | TIME- BASED | MTB | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
AGRICULTURAL TRANSFORMATION AGENDA POLICY SITUATION ANALYSIS | LCS | TIME- BASED | MTB | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
TECHNOLOGY ADAPTATION AND TRANSFEER | LCS | LUMP SUM | MTB | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CAPACITY BUILDING ON INTEGRATED PEST MANAGEMENT | MoU | LUMP SUM | MTB | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
FABRICATION AND MANUFACTURING OF DRYERS (NCAM) | MoU | LUMP SUM | MTB | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
FABRICATION AND MANUFACTURE ATAT THRESHERS (HANIGHA NIG. LTD) | MoU | LUMP SUM | MTB | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
COLLABORATION WITH NCAM FOR DEMONSTRATION AND DEPOLOYMENT OF MINI COMBINED HARVESTERS | LCS | LUMP SUM | MTB | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CAPACITY BUILDING OF SMALLRICE MILLER ON PARBOILING AND PROCESSING TECHNIQUES | LCS | LUMP SUM | MTB | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
HYBRIDE RICE DEVELOPMENT | LCS | LUMP SUM | MTB | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
WORK SHOP ON RICE MARKET DEVELOPMENT | LCS | LUMP SUM | PS | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
EXHIBITION OF NIGERIA RICE VALUE CHAIN ADDED PRODUCTS | LCS | LUMP SUM | PS | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
RICE FAIR | LCS | LUMP SUM | MTB | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
STAKE HOLDERS MEETING | LCS | LUMP SUM | PS | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
REGISTRATION OF RICE CLUSTERS | LCS | LUMP SUM | PS | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
WORK SHOP ON INVSTMENT OPPORTUNITIES IN THE RICE SUB SECTOR | LCS | LUMP SUM | PS | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
NATIONAL FLAG OFF OF 2015 WET SEASON RICE PLANTING SEASON | LCS | LUMP SUM | PS | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
RICE TRANSFORMATION AGENDA (RTA) IMPLEMENTATION REVIEW | LCS | LUMP SUM | PS | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CAPACITY BUILDING ON LEADERSHIP AND RECORD KEEPING FOR CLUSTERS LEADERSHIP | LCS | LUMP SUM | PS | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CAPACITY BUILDING WORKSHOP ON RICE QUALITY CONTROL AND GRADING STANDARD | LCS | LUMP SUM | PS | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
PROJECT COORDINATION AND SUPERVISION | LCS | LUMP SUM | MTB | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
MEDIA | LCS | LUMP SUM | MTB | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CAPACITY BUILDING OF 185 SOYABEAN FARMERS ON GOOD AGRICULTURAL PRACTICES TO ENHANCE YIELD | LCS | LUMP SUM | MTB | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
DEMONSTRATION OF YIELD TRANSFER BY FOOD CROP PRODUCTION TECHNOLOGY TRANSFER STATION(FCPTTS), UBIAJA, EDO STATE | LCS | LUMP SUM | MTB | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
WORKSHOP ON SUSTAINABLE MANAGEMENT & BUSINESS PLAN, GOOD MANAGEMENT PRACTICES, PACKAGING HIGH NUTRITIONAL VALUE ADDED PRODUCTS FROM CASHEW | SS | LUMP SUM | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
WORKSHOP ON CASHEW SOIL FERTILITY MANAGEMENT PACKAGE FOR ORGANIZED SMALL HOLDER FARMERS | SS | LUMP SUM | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
PREPARATORY MEETING FOR GES MOBILIZATION AND REDEMPTION | SS | LUMP SUM | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
LAUNCHING OF MOTORIZED HARVESTER/2 DAY TRAIN THE TRAINER WORKSHOP ON USE AND MAINTAINANCE OF MOTORIZED HAVESTERS | SS | LUMP SUM | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
SUPERVISION/COORDINATION OF OIL PALM VALUE CHAIN ACTIVITIES IN THE 24 NOS. OIL PALM PRODUCING STATE | SS | LUMP SUM | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
GRANT SERVING AGRO-ALLIED LIMITED OWERRI IMO STATE FOR EROSION CONTROL | SS | LUMP SUM | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CAPACITY BUILDING FOR 50NOS NUT COLLECTORS, PROCESSORS/MARKETERS IN THE 10 NO SHEA PRODUCING STATES AND FCT | LC | LUMP SUM | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CAPACITY BUILDING OF FARMERS ON THE USE OF STORAGE FACILITIES TO ENHANCE QUALITY OF SHEA BUTTER | LC | LUMP SUM | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
OIL PALM RESEARCH (NIFOR) FOR RESEARCH/GENETIC STUDY TO REDUCE GESTATION PERIOD OF SHEA TREE | LC | LUMP SUM | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
DUE DELIGENCE AUDIT OF FCTORIES IN 15 RUBBER PRODUCING STATES | LC | LUMP SUM | PS | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
WORKSHOP ON TAPPING, FIELD HANDLING OF LATEX AND QUALITY | MoU | LUMP SUM | MTB | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
RUBBER INVESTMENT FORUM ON NATURAL RUBBER INVESTMENT AND REVIVING THE TYRE AND NON-TYRE PRODUCTS | SS | LUMP SUM | MTB | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CONTRIBUTION TO COUNTERPART FUNDING COMMITMENT TO CFC PHASE 2 PROJECT | SS | LUMP SUM | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
TRAINING OF THE MINISTRY STAFF | LC | LUMP SUM | MTB | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CONSULTANCY SERVICE FOR THE SUPPERVISION OF THE TRAINING ACTIVITIES | SS | LUMP SUM | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
MONITORING OF ALL ACTIVITIES OF ALL THE VALUE CHAINS IN COLLABORATION WITH RELEVANT DEPARTMENTS OF THE MINISTRY's | LCS | LUMP SUM | MTB | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
MONITORING OF 2014 CAPITAL PROJECTS AND PROGRAMMES UNDER THE 2014 APPROVED BUDGETOF THE MINISTRY's | LCS | LUMP SUM | MTB | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CAPACITY DEVELOPMENT FOR M&E STAFF ON REPORT WRITING AND DATACOLLECTION USING RELEVANT TOOLS | LCS | LUMP SUM | MTB | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
HIGH LEVEL OF MONITRING BY HMA, HMS & PS OF PROJECTS AND PROGRAMMED IMPLEMENTED THE MINISTRY's AND DEPARTMENTS ,AGENCIES AND PARASTATALS UNDER THE 2015 BUDGET | LCS | LUMP SUM | MTB | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
DEVELOPMENT OF VALUE CHAIN BUDGET AND ANNUAL PERFORMANCE TRACKER | LCS | LUMP SUM | PS | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
WORKSHOPS AND SEMINAS ON KPIS AND OUT COME INDICATORS AND IMPACT ASSESSMENT | LCS | LUMP SUM | PS | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
COLLA BORATIVE MONITORING WITH OTHER MDA's LIKE NPC,BoF, 0SG AND FNBS ETC. | LCS | LUMP SUM | MTB | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
MONITORING OF 2015 DRY SEASON FARMING | LCS | LUMP SUM | MTB | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
MONITORING OF 2015 GES PROGRAMME IN ALL THE STATES OF THE FEDERATION | LCS | LUMP SUM | MTB | Plan | 2ND FEB-6THAPRIL | 6TH APRIL | 10TH -30TH APRIL | N/A | 1ST - 18TH MAY | 25TH MAY -8TH JUNE | 2ND JUNE-3RD JULY | Plan | 3RD JULY | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT. | 25TH- 30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
(i) CAPACITY BUILDING OF 50 WOMEN ON THE USE OF MODERN TECHNOLOGY FOR GROUNDNUT OIL PROCESSING (ii) WORKSHOP ON AFLATOXIN MANAGEMENT FOR 50 PARTICIPANTS | LC | TIME BASED | GES | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
PUBLICATION AND INFORMATION DISSEMINATION | LC | TIME BASED | GES | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CULTIVATION OF 25HA BREEDER STOCK BY IITA. CULTIVATION OF 5,000 BUNDLES OF FOUNDATION STOCK | SS | TIME BASED | GES | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CULTIVATION OF 18HA BREEDER STOCK BY NRCRI. CULTIVATION OF 3,600 BUNDLES OF FOUNDATION STOCK | SS | TIME BASED | GES | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
COMMUNITY-BASED PLANTING IN SOUTH-WEST ON 58HA BY IITA TO PRODUCE 8,720 BUNDLES FOR 581 FARMERS | SS | TIME BASED | GES | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
| SS |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
COMMUNITY-BASED PLANTING IN SOUTH-WEST ON 43.5HA BY RTEP. TO PRODUCE 11,600 BUNDLES FOR 773 FARMERS | SS | TIME BASED | GES | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
COMMUNITY-BASED PLANTING IN SOUTH-SOUTH ON 10HA BY NRCRI. TO PRODUCE 2,000 BUNDLES FOR 13 FARMERS | SS | TIME BASED | GES | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
COMMUNITY-BASED PLANTING IN SOUTH-SOUTH ON 25HA BY IITA. TO PRODUCE 5,000 BUNDLES FOR 133 FARMERS | SS | TIME BASED | GES | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
COMMUNITY-BASED PLANTING IN SOUTH-SOUTH ON 25HA BY RTEP. 5,000 BUNDLES FOR 333 FARMERS | SS | TIME BASED | GES | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
COMMUNITY-BASED PLANTING IN NORTH-CENTRAL ON 35HA BY IITA TO PRODUCE 7,000 BUNDLES FOR 467 FARMERS | SS | TIME BASED | GES | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
COMMUNITY-BASED PLANTING IN NORTH-CENTRAL ON 35HA BY RTEP TO PRODUCE 10,000 BUNDLES FOR 667 FARMERS | SS | TIME BASED | GES | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
COMMUNITY-BASED PLANTING IN NORTH-WEST ON 10HA BY IITA TO PRODUCE 2,000 BUNDLES FOR 133 FARMERS | SS | TIME BASED | GES | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
COMMUNITY-BASED PLANTING IN NORT-WEST ON 20HA RTEP TO PRODUCE 4,000 BUNDLES FOR 267 FARMERS | SS | TIME BASED | GES | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
COMMUNITY-BASED PLANTING IN NORTH-EAST ON 20HA BY IITA TO PRODUCE 4,000 BUNDLES FOR 267 FARMERS | SS | TIME BASED | GES | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
COMMUNITY-BASED PLANTING IN SOUTH-EAST ON 30HA BY NRCRI TO PRODUCE 6,000 BUNDLES FOR 400 FARMERS | SS | TIME BASED | GES | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
COMMUNITY-BASED PLANTING IN SOUTH-EAST ON 20HA BY RTEP TO PRODUCE 4,000 BUNDLES FOR 267 FARMERS | SS | TIME BASED | GES | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
TRAINING OF PROCESSING ON QUALITY CONTROL OF HQCF INCLUSION IN BREAD AND OTHER CONFECTIONARIES | SS | TIME BASED | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
STAKEHOLDER CAPACITY BUILDING ON EXPORT PROMOTION OF SESAME | LC | TIME BASED | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
TRAINING SESAME FARMERS ON HOW TO USE LOCAL FABRICATION OF SESAME CLEANING AND TREASHING MACHINE | LC | TIME BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CAPACITY BUILDING ON FARMERS ON PRODUCT DEVELOPMENT FOR MAIZE | LC | TIME BASED | MOU | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
INTENSIVE TESTING OF NEW HIGH-YEILDING STRESS-TOLERANT & NUTRIENT EFFICIENT HYBRIDS | LC | TIME BASED | MOU | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CONDUCT SENSITIZATION OF THE RECENTLY RELEASED TWO VARIETIES (NORMAN AND REYAN-28) WITH YIELD POTENTIAL OF 6-8T/H IN CORE WHEAT PRODUCUING STATES | SS | TIME BASED | ON-GOING | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
MODEL TRIAL AND TEST RUN OF THE HOME GROWN SCHOOL FEEDING PROGRAMME PRIOR TO COMPREHENSIVE ROLL OUT IN ALL PUBLIC PRIMARY SCHOOLS | MOU | TIME BASED | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
PROMOTE THE UTILIZATION OF THE HEALTHY RECIPES FOR LOCALLY AVAILABLE NUTRITIOUS FOODS | MOU | TIME BASED | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
PROMOTION OF THE AFLASAFE TECHNOLOGY, SUPPORT CERTIFICATION FOR ENHANCED MARKETING, STRATEGY SESSION FOR NATIONAL COORDINATION, RESEARCH FOR NUTRITIONA IMPACT | MOU | TIME BASED | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
BUILDING ON EXISTING AGRICULTURE INNOVATIONS AND DELIVERY PLATFORMS THROUGH THE DISTRIBUTION OF MICRONUTRIENT POWERS INTO THE GROWTH ENHANCEMENT SCHEME BY USING THE E-WALLET SYSTEM | MOU | TIME BASED | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
INTEGRATED NUTRITION EDUCATION AND BEHAVIOURCHANGE PROGRAMMES, DEVELOPMENT AND PROMOTION OF HOME BASED UTILIZATION OF NUTRITIOUS FOODS FORMATIVE RESEARCH AND PLANNING WORKSHOP | MOU | TIME BASED | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
DEVELOPMENT OF POLICY DOCUMENT, INVESTMENT GUIDE AND IMPLEMENTATION OF STRATEGY ON TRANSFORMATION PARTNERSHIP ON HIGH ENERGY FOODS | MOU | TIME BASED | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
PROMOTION OF NUTRITION SENSITIVE AGRICULTURE THROUGH DOCUMENTARIES, MEDIA ACTIVITIES, RADIO PROGRAMMES | MOU | TIME BASED | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
ESTABLISHMENT OF TISSUE CULTURE LABORATORY BY NRCRI UMUDIKE | LC | TIME BASED | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
PREPARATION OF EXISTING TISSUE CULTURE FACILITIES (NURSERY) FOR IRISH POTATO PLANTLETS @ NRCRI KURU JOS | LC | TIME BASED | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CAPACITY BUILDING OF FARMERS ON THE MGT./ HANDLING OF TISSUE CULTURE IRISH POTATO PLANTLETS | LC | TIME BASED | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
PROGRAMME MANAGEMENT AND DIVERSIFIED PRODUCTS | LC | TIME BASED | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
VARIETAL SELECTION AND MULTIPLICATION | LC | TIME BASED | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
NUTRITIONAL VALUE AND DEMAND CREATION | LC | TIME BASED | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
INTERNATIONAL POTATO CENTRE | LC | TIME BASED | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
ADVOCACY ON MITIGATION BETWEEN CROP FARMERS AND PASTORLISTS CONFLICTS ON STOCK ROUTES | LC | TIME BASED | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
SENSITIZATION OF 1,200 FARMERS ON IMPROVED METHODS OF VILLAGE PRODUCTION IN 6 STATES | LC | TIME BASED | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
SENSITIZATION OF FARMERS ON DRY SEASON FEEDING IN 12 STATES | LC | TIME BASED | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
SENSITIZATION PROGRAMME FOR PIG FARMERS IN 4 STATES | LC | TIME BASED | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
DEVELOPMENT SUPPORT FOR MARKET AND MARKETING INFRASTRUCTURE (CONSTRUCTION OF HIDES AND SKIN DRYING SHED) | LC | TIME BASED | MTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
ASSESSMENT AND COSTING OF FACILITIES AT OJI RIVER TANNERY | LC | TIME BASED | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
SENSITIZATION AND COMMUNITY DIALOGUE IN 4 STATES | LC | TIME BASED | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
RESOURCE INVENTORY SURVEY IN 4 STATES | LC | TIME BASED | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
PROMOTION OF SETTLEMENT OF PASTORALISTS IN GRAZING RESERVES IN 4 STATES | LC | TIME BASED | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
10 HECTARES EACH PASTURE DEVELOPMENT IN 4 STATES | LC | TIME BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
PASTURE AND SEED MULTIPLICATION IN 2 STATES | LC | TIME BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CHEMICAL ANALYSIS OF FEED SAMPLES TO COMPLY WITH NAFDAC SPECIFICATIONS | LC | TIME BASED | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CODEX ALLIMENTARIUSSENSITIZATION AND SUPERVISION OF FEEDMILLERS, INPUT USERS, INPUT SUPPLIERS ON STANDARDS COMPLIANCE | LC | TIME BASED | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
PRODUCTION OF DRAUGHT RESISTANT PASTURE SEEDS IN 4 CONSERVATION CENTRES | LC | TIME BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
ASSESMENT AND COSTING OF PRODUCTION FACILITIES IN BREEDING FARMS | LC | TIME BASED | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
LIVESTOCK DATA MANAGEMENT | LC | TIME BASED | PS | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | Plan | 3RD-24TH AUG | N/A | N/A
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CAPACITY BUILDING OF FULANI MILK PRODUCERS | LC | TIME BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CAPACITY BUILDING ON PORK PRODUCTION FOR FARMERS | LC | TIME BASED | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
CAPACITY BUILDING FOR BUTCHERS AND OTHER STAKEHOLDERS ALONG THE LEATHER VALUE CHAIN IN 12 STATES | LC | TIME BASED | PS | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
UPGRADING AND MAINTENACE OF WEBSITE | LC | LUMP SUM | MTB | Plan | 23RD FEB-6TH APRIL | 6TH APRIL | 10TH-30TH APRIL | N/A | 1ST-15TH MAY | 25TH MAY-8TH JUNE | 22ND MAY-8TH JULY | Plan | N/A | N/A | 13TH-24TH JULY | 23RD FEB-6TH APRIL | 27TH-31ST JULY | Plan | 3RD-24TH AUG | 1ST-11TH SEPT | 25TH-30TH SEPT
|  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual

## Ministry of Environment
Ministry/Department/Agency: Federal Ministry Of Enviornment
Budget Year: 2015
|  | Basic Data | [7 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation - Works
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Plan vs Actual
ESTABLISHMENT OF 10 HECTARES WOODLOT PLANTATIONS IN THE 11 FRONTLINES STATES | Plan | DDA-1 | 1 | BEME | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/03/15 - 23/03/15 | 23/03/15 - 6/04/15 | 6/04/15 - 4/05/15 | 4/05/15 - 18/05/15 | 18/05/15 - 15/06/15 | NA | NA | 15/06/15 | 27/07/15 | 27/07/15 - 17/08/15 | 17/08/15 - 14/09/15 | NA | 14/09/15 - 28/09/15 | 28/09/15 - 12/10/15 | 12/10/15 - 19/10/15 | 14/12/15 | 21/12/15
Actual
ESTABLISHMENT OF 10 HECTARES ACACIA SENEGAL PLANTATIONS TO COMBAT DROUGTH AND DESERTIFICATION IN THE 11 FRONTLINES STATES. | Plan | DDA-2 | 2 | BEME | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/03/15 - 23/03/15 | 23/03/15 - 6/04/15 | 6/04/15 - 4/05/15 | 4/05/15 - 18/05/15 | 18/05/15 - 15/06/15 | NA | NA | 15/06/15 | 27/07/15 | 27/07/15 - 17/08/15 | 17/08/15 - 14/09/15 | NA | 14/09/15 - 28/09/15 | 28/09/15 - 12/10/15 | 12/10/15 - 2/11/15 | 21/12/15 | 28/12/15
Actual
EROSION CONTROL AND FLOOD CHANNELIZATION WORKS NEAR UBA DOGO HOUSE, DAWAKI, GOMBE LGA, GOMBE STATE | Plan | EFC-1 | 1 | BEME | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/03/15 -23/03/15 | 23/03/15-6/04/15 | 6/04/15-4/05/15 | 4/05/15 - 18/05/15 | 18/05/15 - 15/06/15 | NA | NA | 15/06/15 | 27/07/15 | 27/07/15 - 17/08/15 | 17/08/15 - 14/09/15 | NA | 14/09/15 - 28/09/15 | 28/09/15 - 12/10/15 | 12/10/15 - 2/11/15 | 21/12/15 | 28/12/15
Actual
EROSION AND FLOOD CONTROL PROJECT AT SOBA IN SOBA LGA, KADUNA STATE | Plan | EFC-2 | 2 | BEME | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/03/15 -23/03/15 | 23/03/15-6/04/15 | 6/04/15-4/05/15 | 4/05/15 - 18/05/16 | 18/05/15 - 15/06/15 | NA | NA | 15/06/15 | 27/07/15 | 27/07/15 - 17/08/15 | 17/08/15 - 14/09/15 | NA | 14/09/15 - 28/09/15 | 28/09/15 - 12/10/15 | 12/10/15 - 2/11/15 | 21/12/15 | 28/12/15
Actual
EROSION CONTROL WORKS AT ADAZI-ANI, ANAOCHA ANAMBRA STATE | Plan | EFC-3 | 3 | BEME | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/03/15 -23/03/15 | 23/03/15-6/04/15 | 6/04/15-4/05/15 | 4/05/15 - 18/05/17 | 18/05/15 - 15/06/15 | NA | NA | 15/06/15 | 27/07/15 | 27/07/15 - 17/08/15 | 17/08/15 - 14/09/15 | NA | 14/09/15 - 28/09/15 | 28/09/15 - 12/10/15 | 12/10/15 - 2/11/15 | 21/12/15 | 28/12/15
Actual
DREDGING AND CHANNELISATION OF EBUTTE METTA CANAL, LAGOS STATE | Plan | EFC-4 | 4 | BEME | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/03/15 -23/03/15 | 23/03/15-6/04/15 | 6/04/15-4/05/15 | 4/05/15 - 18/05/18 | 18/05/15 - 15/06/15 | NA | NA | 15/06/15 | 27/07/15 | 27/07/15 - 17/08/15 | 17/08/15 - 14/09/15 | NA | 14/09/15 - 28/09/15 | 28/09/15 - 12/10/15 | 12/10/15 - 2/11/15 | 21/12/15 | 28/12/15
Actual
EROSION AND FLOOD CONTROL PROJECT AT UMUOPARA-OZARA AVONKWU, UMUAHIA SOUTH LGA, ABIA STATE | Plan | EFC-5 | 5 | BEME | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/03/15 -23/03/15 | 23/03/15-6/04/15 | 6/04/15-4/05/15 | 4/05/15 - 18/05/19 | 18/05/15 - 15/06/15 | NA | NA | 15/06/15 | 27/07/15 | 27/07/15 - 17/08/15 | 17/08/15 - 14/09/15 | NA | 14/09/15 - 28/09/15 | 28/09/15 - 12/10/15 | 12/10/15 - 2/11/15 | 21/12/15 | 28/12/15
Actual
EROSION CONTROL AND DRAINAGE WORKS AT KOFAR MARUSA AREA OF KATSINA STATE | Plan | EFC-6 | 6 | BEME | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/03/15 -23/03/15 | 23/03/15-6/04/15 | 6/04/15-4/05/15 | 4/05/15 - 18/05/20 | 18/05/15 - 15/06/15 | NA | NA | 15/06/15 | 27/07/15 | 27/07/15 - 17/08/15 | 17/08/15 - 14/09/15 | NA | 14/09/15 - 28/09/15 | 28/09/15 - 12/10/15 | 12/10/15 - 2/11/15 | 21/12/15 | 28/12/15
Actual
EROSION CONTROL AND FLOOD CHANNELIZATION WORKS AT GADAM-DAWO ROAD, KWAMI LGA, GOMBE STATE | Plan | EFC-7 | 7 | BEME | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/03/15 -23/03/15 | 23/03/15-6/04/15 | 6/04/15-4/05/15 | 4/05/15 - 18/05/21 | 18/05/15 - 15/06/15 | NA | NA | 15/06/15 | 27/07/15 | 27/07/15 - 17/08/15 | 17/08/15 - 14/09/15 | NA | 14/09/15 - 28/09/15 | 28/09/15 - 12/10/15 | 12/10/15 - 2/11/15 | 21/12/15 | 28/12/15
Actual
EROSION AND FLOOD CONTROL WORKS AT PAPIRI, NIGER STATE | Plan | EFC-8 | 8 | BEME | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/03/15 -23/03/15 | 23/03/15-6/04/15 | 6/04/15-4/05/15 | 4/05/15 - 18/05/22 | 18/05/15 - 15/06/15 | NA | NA | 15/06/15 | 27/07/15 | 27/07/15 - 17/08/15 | 17/08/15 - 14/09/15 | NA | 14/09/15 - 28/09/15 | 28/09/15 - 12/10/15 | 12/10/15 - 2/11/15 | 21/12/15 | 28/12/15
Actual
EROSION AND FLOOD CONTROL WORKS AT OGUNDARO/OKOTA WAY, NEAR FESTAC, LAGOS | Plan | EFC-9 | 9 | BEME | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/03/15 -23/03/15 | 23/03/15-6/04/15 | 6/04/15-4/05/15 | 4/05/15 - 18/05/23 | 18/05/15 - 15/06/15 | NA | NA | 15/06/15 | 27/07/15 | 27/07/15 - 17/08/15 | 17/08/15 - 14/09/15 | NA | 14/09/15 - 28/09/15 | 28/09/15 - 12/10/15 | 12/10/15 - 2/11/15 | 21/12/15 | 28/12/15
Actual
EROSION AND FLOOD CONTROL WORKS AT IBONO USUK, NKARI CLAN, INI LGA, AKWA IBOM STATE | Plan | EFC-10 | 10 | BEME | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/03/15 -23/03/15 | 23/03/15-6/04/15 | 6/04/15-4/05/15 | 4/05/15 - 18/05/24 | 18/05/15 - 15/06/15 | NA | NA | 15/06/15 | 27/07/15 | 27/07/15 - 17/08/15 | 17/08/15 - 14/09/15 | NA | 14/09/15 - 28/09/15 | 28/09/15 - 12/10/15 | 12/10/15 - 2/11/15 | 21/12/15 | 28/12/15
Actual
FLOOD CONTROL AND CHANNELIZATION WORKS IN YAURI TOWN, YAURI LGA, KEBBI STATE | Plan | EFC-11 | 11 | BEME | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/03/15 -23/03/15 | 23/03/15-6/04/15 | 6/04/15-4/05/15 | 4/05/15 - 18/05/25 | 18/05/15 - 15/06/15 | NA | NA | 15/06/15 | 27/07/15 | 27/07/15 - 17/08/15 | 17/08/15 - 14/09/15 | NA | 14/09/15 - 28/09/15 | 28/09/15 - 12/10/15 | 12/10/15 - 2/11/15 | 21/12/15 | 28/12/15
Actual
EROSION CONTROL WORKS AT IDIM UKPONG ROAD, IDUNG OBONG AKPANTONG, AKWA IBOM STATE | Plan | EFC- 12 | 12 | BEME | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/03/15 -23/03/15 | 23/03/15-6/04/15 | 6/04/15-4/05/15 | 4/05/15 - 18/05/26 | 18/05/15 - 15/06/15 | NA | NA | 15/06/15 | 27/07/15 | 27/07/15 - 17/08/15 | 17/08/15 - 14/09/15 | NA | 14/09/15 - 28/09/15 | 28/09/15 - 12/10/15 | 12/10/15 - 2/11/15 | 21/12/15 | 28/12/15
Actual
FLOOD AND EROSION CONTROL THROUGH WATER HARVESTING IN NAMTARI, YOLA SOUTH LGA, ADAMAWA STATE | Plan | EFC-13 | 13 | BEME | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/03/15 -23/03/15 | 23/03/15-6/04/15 | 6/04/15-4/05/15 | 4/05/15 - 18/05/27 | 18/05/15 - 15/06/15 | NA | NA | 15/06/15 | 27/07/15 | 27/07/15 - 17/08/15 | 17/08/15 - 14/09/15 | NA | 14/09/15 - 28/09/15 | 28/09/15 - 12/10/15 | 12/10/15 - 2/11/15 | 21/12/15 | 28/12/15
Actual
EROSION CONTROL AT IFITE ANI VILLAGE, AGULU, ANAMBRA STATE PHASE I | Plan | EFC-14 | 14 | BEME | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/03/15 -23/03/15 | 23/03/15-6/04/15 | 6/04/15-4/05/15 | 4/05/15 - 18/05/28 | 18/05/15 - 15/06/15 | NA | NA | 15/06/15 | 27/07/15 | 27/07/15 - 17/08/15 | 17/08/15 - 14/09/15 | NA | 14/09/15 - 28/09/15 | 28/09/15 - 12/10/15 | 12/10/15 - 2/11/15 | 21/12/15 | 28/12/15
Actual
EROSION CONTROL AT MADUFA, BAUCHI STATE | Plan | EFC-15 | 15 | BEME | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/03/15 -23/03/15 | 23/03/15-6/04/15 | 6/04/15-4/05/15 | 4/05/15 - 18/05/29 | 18/05/15 - 15/06/15 | NA | NA | 15/06/15 | 27/07/15 | 27/07/15 - 17/08/15 | 17/08/15 - 14/09/15 | NA | 14/09/15 - 28/09/15 | 28/09/15 - 12/10/15 | 12/10/15 - 2/11/15 | 21/12/15 | 28/12/15
Actual
FLOOD CHANNELIZATION & CONSTRUCTION OF ASPHALTED ROAD ON NNEOGIDI-EJIKE IMOKE NWOBUALOR UBOH ROADS, AGULU TO CHECK EROSION MENACE, ANAMBRA STATE | Plan | EFC-16 | 16 | BEME | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/03/15 -23/03/15 | 23/03/15-6/04/15 | 6/04/15-4/05/15 | 4/05/15 - 18/05/30 | 18/05/15 - 15/06/15 | NA | NA | 15/06/15 | 27/07/15 | 27/07/15 - 17/08/15 | 17/08/15 - 14/09/15 | NA | 14/09/15 - 28/09/15 | 28/09/15 - 12/10/15 | 12/10/15 - 2/11/15 | 21/12/15 | 28/12/15
Actual
EROSION CONTROL AT USSA, TARABA STATE | Plan | EFC-17 | 17 | BEME | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/03/15 -23/03/15 | 23/03/15-6/04/15 | 6/04/15-4/05/15 | 4/05/15 - 18/05/31 | 18/05/15 - 15/06/15 | NA | NA | 15/06/15 | 27/07/15 | 27/07/15 - 17/08/15 | 17/08/15 - 14/09/15 | NA | 14/09/15 - 28/09/15 | 28/09/15 - 12/10/15 | 12/10/15 - 2/11/15 | 21/12/15 | 28/12/15
Actual
FLOOD CONTROL AND RIVER TRAINING WORKS ON UREJE RIVER ALONG FEDERAL POLYTECHNIC ROADS, ADO EKITI, EKITI STATE | Plan | EFC-18 | 18 | BEME | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/03/15 -23/03/15 | 23/03/15-6/04/15 | 6/04/15-4/05/15 | 4/05/15 - 18/05/32 | 18/05/15 - 15/06/15 | NA | NA | 15/06/15 | 27/07/15 | 27/07/15 - 17/08/15 | 17/08/15 - 14/09/15 | NA | 14/09/15 - 28/09/15 | 28/09/15 - 12/10/15 | 12/10/15 - 2/11/15 | 21/12/15 | 28/12/15
Actual
EROSION CONTROL AT ANIFOWOSHE (UBAN DAWAKI) AJIKOBI AND OLOJE IN ILORIN, KWARA STATE | Plan | EFC-19 | 19 | BEME | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/03/15 -23/03/15 | 23/03/15-6/04/15 | 6/04/15-4/05/15 | 4/05/15 - 18/05/33 | 18/05/15 - 15/06/15 | NA | NA | 15/06/15 | 27/07/15 | 27/07/15 - 17/08/15 | 17/08/15 - 14/09/15 | NA | 14/09/15 - 28/09/15 | 28/09/15 - 12/10/15 | 12/10/15 - 2/11/15 | 21/12/15 | 28/12/15
Actual
EROSION CONTROL WORKS AT EKE-AWKA /ACHALLA ROAD AWKA, AWKA SOUTH LGA, ANAMBRA STATE | Plan | EFC-20 | 20 | BEME | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/03/15 -23/03/15 | 23/03/15-6/04/15 | 6/04/15-4/05/15 | 4/05/15 - 18/05/33 | 18/05/15 - 15/06/15 | NA | NA | 15/06/15 | 27/07/15 | 27/07/15 - 17/08/15 | 17/08/15 - 14/09/15 | NA | 14/09/15 - 28/09/15 | 28/09/15 - 12/10/15 | 12/10/15 - 2/11/15 | 21/12/15 | 28/12/15
Actual
EROSION CONTROL ADISCO GAA IMAM, OKE-ERIN, ILORIN, KWARA STATE | Plan | EFC-21 | 21 | BEME | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/03/15 -23/03/15 | 23/03/15-6/04/15 | 6/04/15-4/05/15 | 4/05/15 - 18/05/33 | 18/05/15 - 15/06/15 | NA | NA | 15/06/15 | 27/07/15 | 27/07/15 - 17/08/15 | 17/08/15 - 14/09/15 | NA | 14/09/15 - 28/09/15 | 28/09/15 - 12/10/15 | 12/10/15 - 2/11/15 | 21/12/15 | 28/12/15
Actual
FLOOD AND EROSION CONTROL WORKS AT AMOGWU-AKU ALONG ST. PATRICK CATHOLIC CHURCH/NTURU/EKE-UWELU MARKET OBIE AKU, IGBO EKITI LGA, ENUGU STATE. | Plan | EFC-22 | 22 | BEME | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/03/15 -23/03/15 | 23/03/15-6/04/15 | 6/04/15-4/05/15 | 4/05/15 - 18/05/33 | 18/05/15 - 15/06/15 | NA | NA | 15/06/15 | 27/07/15 | 27/07/15 - 17/08/15 | 17/08/15 - 14/09/15 | NA | 14/09/15 - 28/09/15 | 28/09/15 - 12/10/15 | 12/10/15 - 2/11/15 | 21/12/15 | 28/12/15
Actual
EROSION CONTROL WORKS AND ASPHALTING AT UMUABU- ADAZI ENU, ANAMBRA STATE. | Plan | EFC-23 | 23 | BEME | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/03/15 -23/03/15 | 23/03/15-6/04/15 | 6/04/15-4/05/15 | 4/05/15 - 18/05/33 | 18/05/15 - 15/06/15 | NA | NA | 15/06/15 | 27/07/15 | 27/07/15 - 17/08/15 | 17/08/15 - 14/09/15 | NA | 14/09/15 - 28/09/15 | 28/09/15 - 12/10/15 | 12/10/15 - 2/11/15 | 21/12/15 | 28/12/15
Actual
EROSION CONTROL WORKS AT IBOKUN, OBOKUN LGA, OSUN STATE | Plan | EFC-24 | 24 | BEME | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/03/15 -23/03/15 | 23/03/15-6/04/15 | 6/04/15-4/05/15 | 4/05/15 - 18/05/33 | 18/05/15 - 15/06/15 | NA | NA | 15/06/15 | 27/07/15 | 27/07/15 - 17/08/15 | 17/08/15 - 14/09/15 | NA | 14/09/15 - 28/09/15 | 28/09/15 - 12/10/15 | 12/10/15 - 2/11/15 | 21/12/15 | 28/12/15
Actual
EROSION CONTROL AND FLOOD CHANNELIZATION AT DOLFIN ESTATE, LAGOS. | Plan | EFC-25 | 25 | BEME | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/03/15 -23/03/15 | 23/03/15-6/04/15 | 6/04/15-4/05/15 | 4/05/15 - 18/05/33 | 18/05/15 - 15/06/15 | NA | NA | 15/06/15 | 27/07/15 | 27/07/15 - 17/08/15 | 17/08/15 - 14/09/15 | NA | 14/09/15 - 28/09/15 | 28/09/15 - 12/10/15 | 12/10/15 - 2/11/15 | 21/12/15 | 28/12/15

## Ministry of information
Ministry/Department/Agency: Main Ministry of Information
Budget Year: 2015
|  | Basic Data | [7 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [8 empty] | Contract Implementation - Consultancy
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2.2 - 2 weeks | 3 weeks | 2 - 4 weeks | 2 weeks | 4 - 6 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
Production of various Publications on Government Policies | Plan | 01 | 1 | Lump Sum | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | NA |  | 8/01/15 - 22/01/15 | 9/02/15 - 23/02/15 | 2/03/15 - 16/03/15 | 17/03/15 - 31/03/15 | 20/04/15 | 4/05/15 - 8/05/15 | 8/05/15 - 19/06/15 | 19/06/15 | 22/06/15 - 3/07/15 | 6/07/15 - 10/07/15 | 13/07/15 - 17/07/15 | 20/07/15 - 24/07/15 | 27/07/15 -7/08/15 | 10/08/15 - 4/09/15 | NA | 7/09/15 - 18/09/15 | 21/09/15 - 2/10/15 | NA | NA | NA
Actual
Production of Documentaries and Jingles on Progress Made on Transformation Agenda, Sure, MDGs and other Government | Plan | FMI 02 | 2 | Lump Sum | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | NA |  | 8/01/15 - 22/01/15 | 9/02/15 - 23/02/15 | 2/03/15 - 16/03/15 | 17/03/15 - 31/03/15 | 20/04/15 | 4/05/15 - 8/05/15 | 8/05/15 - 19/06/15 | 19/06/15 | 30/06/14 - 7/07/14 | 6/07/15 - 10/07/15 | 13/07/15 - 17/07/15 | 20/07/15 - 24/07/15 | 27/07/15 -7/08/15 | 10/08/15 - 4/09/15 | NA | 7/09/15 - 18/09/15 | 21/09/15 - 2/10/15 | NA | NA | NA
| Actual | [8 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Human Capital Development for Staff of the Ministry (HRM) | Plan | FMI03 | 3 | Lump Sum | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | NA |  | 8/01/15 - 22/01/15 | 9/02/15 - 23/02/15 | 2/03/15 - 16/03/15 | 17/03/15 - 31/03/15 | 20/04/15 | 4/05/15 - 8/05/15 | 8/05/15 - 19/06/15 | 19/06/15 | 22/06/15 - 3/07/15 | 6/07/15 - 10/07/15 | 13/07/15 - 17/07/15 | 20/07/15 - 24/07/15 | 27/07/15 -7/08/15 | 10/08/15 - 4/09/15 | NA | 7/09/15 - 18/09/15 | 21/09/15 - 2/10/15 | NA | NA | NA
| Actual | [22 empty] | NA | NA | NA
External Publicity/Media Insertions in Foreign Media: Print Media, Electronic Media, Media Forum in Selected cities abroad, engagement with foreign News Agencies, Production of specilized publicity | Plan | FMI04 | 4 | Lump Sum | NS | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | NA |  | 8/01/15 - 22/01/15 | 9/02/15 - 23/02/15 | 2/03/15 - 16/03/15 | 17/03/15 - 31/03/15 | 20/04/15 | 4/05/15 - 8/05/15 | 8/05/15 - 19/06/15 | 19/06/15 | 22/06/15 - 3/07/15 | 6/07/15 - 10/07/15 | 13/07/15 - 17/07/15 | 20/07/15 - 24/07/15 | 27/07/15 -7/08/15 | 10/08/15 - 4/09/15 | NA | 7/09/15 - 18/09/15 | 21/09/15 - 2/10/15 | NA | NA | NA
Actual
Developing Social Media Platforms & Networking with other | Plan | FMI05 | 5 | Lump Sum | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | NA |  | 8/01/15 - 22/01/15 | 9/02/15 - 23/02/15 | 2/03/15 - 16/03/15 | 17/03/15 - 31/03/15 | 20/04/15 | 4/05/15 - 8/05/15 | 8/05/15 - 19/06/15 | 19/06/15 | 22/06/15 - 3/07/15 | 6/07/15 - 10/07/15 | 13/07/15 - 17/07/15 | 20/07/15 - 24/07/15 | 27/07/15 -7/08/15 | 10/08/15 - 4/09/15 | NA | 7/09/15 - 18/09/15 | 21/09/15 - 2/10/15 | NA | NA | NA
Actual
Organizing Ministerial Platform and Press Briefing of National | Plan | FMI06 | 6 | Lump Sum | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | NA |  | 8/01/15 - 22/01/15 | 9/02/15 - 23/02/15 | 2/03/15 - 16/03/15 | 17/03/15 - 31/03/15 | 20/04/15 | 4/05/15 - 8/05/15 | 8/05/15 - 19/06/15 | 19/06/15 | 22/06/15 - 3/07/15 | 6/07/15 - 10/07/15 | 13/07/15 - 17/07/15 | 20/07/15 - 24/07/15 | 27/07/15 -7/08/15 | 10/08/15 - 4/09/15 |  | 7/09/15 - 18/09/15 | 21/09/15 - 2/10/15 | NA | NA | NA
Actual
Development of Natioanl Policy, Conduct of National Council on Information | Plan | FMI07 | 7 | Lump Sum | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | NA |  | 8/01/15 - 22/01/15 | 9/02/15 - 23/02/15 | 2/03/15 - 16/03/15 | 17/03/15 - 31/03/15 | 20/04/15 | 4/05/15 - 8/05/15 | 8/05/15 - 19/06/15 | 19/06/15 | 22/06/15 - 3/07/15 | 6/07/15 - 10/07/15 | 13/07/15 - 17/07/15 | 20/07/15 - 24/07/15 | 27/07/15 -7/08/15 | 10/08/15 - 4/09/15 |  | 7/09/15 - 18/09/15 | 21/09/15 - 2/10/15 | NA | NA | NA
Actual
Production of Govt. Publications for Sale to Public | Plan | FMI08 | 8 | Lump Sum | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | NA |  | 8/01/15 - 22/01/15 | 9/02/15 - 23/02/15 | 2/03/15 - 16/03/15 | 17/03/15 - 31/03/15 | 20/04/15 | 4/05/15 - 8/05/15 | 8/05/15 - 19/06/15 | 19/06/15 | 22/06/15 - 3/07/15 | 6/07/15 - 10/07/15 | 13/07/15 - 17/07/15 | 20/07/15 - 24/07/15 | 27/07/15 -7/08/15 | 10/08/15 - 4/09/15 | NA | 7/09/15 - 18/09/15 | 21/09/15 - 2/10/15 | NA | NA | NA
Actual
Capacity Building on Budget Monitoring of Projects and Evalaution and Financial Monitoring in Line with Transformation Agenda | Plan | FMI09 | 9 | Lump Sum | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | NA |  | 8/01/15 - 22/01/15 | 9/02/15 - 23/02/15 | 2/03/15 - 16/03/15 | 17/03/15 - 31/03/15 | 20/04/15 | 4/05/15 - 8/05/15 | 8/05/15 - 19/06/15 | 19/06/15 | 22/06/15 - 3/07/15 | 6/07/15 - 10/07/15 | 13/07/15 - 17/07/15 | 20/07/15 - 24/07/15 | 27/07/15 -7/08/15 | 10/08/15 - 4/09/15 | NA | 7/09/15 - 18/09/15 | 21/09/15 - 2/10/15 | NA | NA | NA
Actual
Nation-Wide Media Tour of Federal Government Projects and Hosting | Plan | FMI10 | 10 | Lump Sum | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | NA |  | 8/01/15 - 22/01/15 | 9/02/15 - 23/02/15 | 2/03/15 - 16/03/15 | 17/03/15 - 31/03/15 | 20/04/15 | 4/05/15 - 8/05/15 | 8/05/15 - 19/06/15 | 19/06/15 | 22/06/15 - 3/07/15 | 6/07/15 - 10/07/15 | 13/07/15 - 17/07/15 | 20/07/15 - 24/07/15 | 27/07/15 -7/08/15 | 10/08/15 - 4/09/15 |  | 7/09/15 - 18/09/15 | 21/09/15 - 2/10/15 | NA | NA | NA
Actual
Production of Calendars and Diaries for 2014 | Plan | FMI11 | 11 | Lump Sum | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | NA |  | 8/01/15 - 22/01/15 | 9/02/15 - 23/02/15 | 2/03/15 - 16/03/15 | 17/03/15 - 31/03/15 | 20/04/15 | 4/05/15 - 8/05/15 | 8/05/15 - 19/06/15 | 19/06/15 | 22/06/15 - 3/07/15 | 6/07/15 - 10/07/15 | 13/07/15 - 17/07/15 | 20/07/15 - 24/07/15 | 27/07/15 -7/08/15 | 10/08/15 - 4/09/15 | NA | 7/09/15 - 18/09/15 | 21/09/15 - 2/10/15 | NA | NA | NA
Actual

## Ministry of information Goods
Ministry/Department/Agency: Main Ministry-information & Communication
Budget Year: 2015
|  | Basic Data | [7 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  |  |  |  | Contract Implementation - Goods
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Arrival of Goods | Inspection/Final Acceptance
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
Plan vs Actual
PURCHASE OF IDENTITY CARD MACHINE | Plan | MMSD/G/01 | 1 |  | NCB | Accounting Officer: Permanent Secretary | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 21/05/14 - 4/06/14 | 4/06/14 - 18/06/14 | NA | NA | NA | 25/08/14 | 6/10/14 | 6/10/14 - 20/10/14 | 20/10/14 - 3/11/14 | NA | 3/11/14 - 10/11/14 | 10/11/14 - 24/11/14 | 24/11/14 - 15/12/14
Actual

## Ministry of Justice
Ministry/Department/Agency: | FED MIN OF JUSTICE |  |  |  |  | THE TIME LINE IS TO BE COMPARED WITH THE COUNCILS APPROVAL
Budgetary Year: | 2015 | [5 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Procurement Method | Pre-qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Plan vs. Actual | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
|  |  |  | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Purchase of ICT equipment | [5 empty] | Plan | 7th Feb - 28th Feb | 28th Feb - 8th March |  | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | To be determined | N/A | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th August 2015 | August 2015
|  | 1 | OCB |  | MTB | Actual | [7 empty] | Actual
Construction of Customized Library (Virtual) | [5 empty] | Plan | 7th Feb - 28th Feb | 28th Feb - 8th March |  | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | To be determined | N/A | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th August 2015 | August 2015
|  | 2 | OCB |  | MTB | Actual | [7 empty] | Actual
Customized Archive | [5 empty] | Plan | 7th Feb - 28th Feb | 28th Feb - 8th March |  | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | To be determined | N/A | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th August 2015 | August 2015
|  | 3 | OCB |  | MTB | Actual | [7 empty] | Actual
Baseline Survey of Justice Institutions | [5 empty] | Plan | 7th Feb - 28th Feb | 28th Feb - 8th March |  | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | To be determined | N/A | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th August 2015 | August 2015
|  | 4 | OCB |  | MTB | Actual | [7 empty] | Actual
Justice Data Bank | [5 empty] | Plan | 7th Feb - 28th Feb | 28th Feb - 8th March |  | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | To be determined | N/A | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th August 2015 | August 2015
|  | 5 | OCB |  | MTB | Actual | [7 empty] | Actual
Purchase of Law Books, Library Journals and Periodicals | [5 empty] | Plan | 7th Feb - 28th Feb | 28th Feb - 8th March |  | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | To be determined | N/A | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th August 2015 | August 2015
|  | 6 | OCB |  | MTB | Actual | [7 empty] | Actual
Renovation of Zonal Offices including High Tension Power Equipment for Headquarters Office | [5 empty] | Plan | 7th Feb - 28th Feb | 28th Feb - 8th March |  | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | To be determined | N/A | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th August 2015 | August 2015
|  | 7 | OCB |  | MTB | Actual | [7 empty] | Actual
Improvement of Security Infrastructure | [5 empty] | Plan | 7th Feb - 28th Feb | 28th Feb - 8th March |  | 12th April | 24th May | 31st May - 14th June | 21st June - 28th June | Plan | To be determined | N/A | 19th July - 2nd August | 2nd Aug -9th Aug. | 15th August 2015 | August 2015
|  | 8 | OCB |  | MTB | Actual | [7 empty] | Actual
[6 empty] | Plan | [7 empty] | Plan
[6 empty] | Actual | [7 empty] | Actual
Total Cost | [5 empty] | Plan | [7 empty] | Plan
[6 empty] | Actual | [7 empty] | Actual | 0
Fill gray cells only!

## Ministry of Power goods
FEDERAL MINISTRY OF POWER
Ministry/Department/Agency: GOODS
| Budgetary Year: 2015 | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
| Desk Officer/Contact #: |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
S/N | Project Description* | Package Number | Lot Number | Procurement Method | Pre-qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Plan vs. Actual | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
| Norm Duration of Proc Steps |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks | Plan | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
1 | Procurement of Computer & accessories system networking, internet, subscription, procurement of printers, photocopiers and shredder |  |  | National Shopping |  | PS | Plan | 2nd - 19th March | 19th March - 4th April | 19 April | 19th April - 19th May | 26th June | 10th July |  | Plan |  | 13th - 24th July | 27th-7th August
[7 empty] | Actual | [7 empty] | Actual

## Works
M
Ministry/Department/Agency: WORKS
| Budgetary Year: 2015 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
| Desk Officer/Contact #: |  | Basic Data | [7 empty] | Spec Proc Notice Advert |  | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
S/N | Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Pre-or Post Qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | S/N | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance
| Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks |  | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
[6 empty] | add 2 wks |  | Actual | [8 empty] | Actual
List of Contracts
| Video Conferencing system |  |  | lump sum | NCB |  | PS | Plan | 19th - 20th March | 3rd April | 17th April | 1 | 17th April - 29th May | 29th May | 11th June | 19th June | Plan |  | N/A | 6th July | 14th July | 3rd August | 22nd October | 22nd December
1 | [7 empty] | Actual | [8 empty] | Actual
| 10MW Katsina Wind farm |  |  | lump sum | NCB |  | MTB | Plan | 19th - 20th March | 3rd April | 17th April | 2 | 17th April - 29th May | 29th May | 11th June | 19th June | Plan |  | N/A | 6th July | 14th July | 3rd August | 22nd October | 22nd December
2 | [7 empty] | Actual | [8 empty] | Actual
lump sum
| 215MW LPFO/Gas Power Plant |  |  | lump sum | NCB |  | MTB | Plan | 12th March | 3rd April | 20th April | 3 | 6th May | 22nd June | 7th July | 14thJuly | Plan |  | N/A | 21th July | 28th July | 14th August | 30th September | 18th December
3 | [7 empty] | Actual | [8 empty] | Actual
lump sum
| Connection of Gurara to National Grid, Kaduna |  |  | lump sum | NCB |  | MTB | Plan | 18th March | 7th April | 24th April | 4 | 11th May | 29th June | 13th July | 21st July | Plan |  | N/A | 28th July | 5th August | 20th August | 22nd October | 18th December
4 | [7 empty] | Actual | [8 empty] | Actual
lump sum
| Provision of Amenities & Utility Services to Zungeru Hydro Power Station |  |  | lump sum | NCB |  | MTB | Plan | 17th March | 9th April | 16th April | 5 | 4th May | 23rd June | 9th July | 15thJuly | Plan |  | N/A | 29th July | 4th August | 13th August | 25th September | 9th December
5 | [7 empty] | Actual | [8 empty] | Actual
| Data Integration system for power sector |  |  | Lumpsum | NCB |  | MTB | Plan | 18th March | 7th April | 24th April | 6 | 11th May | 29th June | 13th July | 21st July | Plan |  | N/A | 21th July | 28th July | 14th August | 30th September | 18th December
6 | [7 empty] | Actual | [8 empty] | Actual
| Procurement of Electronic Filling & Storage System (Hardware), Software, Installation & Maintenance |  |  | Lumpsum | NCB |  | PS | Plan | 12th March | 3rd April | 20th April | 7 | 6th May | 22nd June | 7th July | 14thJuly | Plan |  | N/A | 29th July | 4th August | 13th August | 25th September | 9th December
7 | [7 empty] | Actual | [8 empty] | Actual
| Establishments of Computerized Records & Registry (E-Registry) |  |  | Lumpsum | NCB |  | PS | Plan | 17th March | 9th April | 16th April | 8 | 4th May | 23rd June | 9th July | 15thJuly | Plan |  | N/A | 28th July | 5th August | 20th August | 22nd October | 18th December
8 | [7 empty] | Actual | [8 empty] | Actual
| Electrify Nigeria (Light up Nigeria) |  |  | Lumpsum | NCB |  | MTB | Plan | 13th March | 20th March | 3rd April | 9 | 1st May | 12th June | 26th June | 10th July | Plan |  | N/A | 24th July | 31st July | 12th August | 18th September | 20th December
9 | [7 empty] | Actual | [8 empty] | Actual
Lumpsum
| Connection of Bayelsa to National Grid |  |  | Lumpsum | NCB |  | MTB | Plan | 13th March | 20th March | 3rd April | 10 | 1st May | 12th June | 26th June | 10th July | Plan |  | N/A | 24th July | 31st July | 12th August | 18th September | 20th December
10 | [7 empty] | Actual | [8 empty] | Actual
11 | Renewable Energy for Electricity Generation |  |  | Lumpsum | NCB |  | MTB | Plan | 17th March | 9th April | 16th April | 11 | 4th May | 23rd June | 9th July | 15thJuly | Plan |  | N/A | 28th July | 5th August | 20th August | 22nd October | 18th December
[8 empty] | Actual | [8 empty] | Actual
12 | Provision of Mordern ICT Trainind Center |  |  | Lumpsum | NCB |  | PS | Plan | 13th March | 20th March | 3rd April | 12 | 1st May | 12th June | 26th June | 10th July | Plan |  | N/A | 24th July | 31st July | 12th August | 18th September | 20th December
[8 empty] | Actual | [8 empty] | Actual
13 | Development of an Information Resource Center (IRC) Virtual Library (VL) |  |  | Lumpsum | NCB |  | PS | Plan | 13th March | 20th March | 3rd April | 13 | 1st May | 12th June | 26th June | 10th July | Plan |  | N/A | 24th July | 31st July | 12th August | 18th September | 20th December
[8 empty] | Actual | [8 empty] | Actual

## Consultancy
Ministry/Department/Agency: CONSULTANCY
| Budgetary Year: 2013 |  | If Post-Review, No-objection Dates are not needed |  |  |  |  | Request for Expression of Interest (when required)
| Desk Officer/Contact #: |  | Contract Type |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  | Contract Implementation
S/N | Project Description* | Selection Method | Lumpsum or Time-Based | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | S/N | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | Plan vs. Actual | No-objection Date | FEC Approval | Contract Offer | S/N | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report
| Norm Duration of Proc Steps |  |  |  | Plan | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks | 1 wks | 1 - 2 wks |  | Plan | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks | 1- 2 wk |  | 2 wks | Plan | 2 wks | 3 wks | 2 Months
[5 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
List of Contracts
| Monitoring & Evaluation of Power Projects | Least Cost | Lumpsum | PS | Plan | 10th March | 23rd March | 6th April | 14th April | 20th April | 27th April | 1 | Plan | 14t May | 24th June | 6th July | 21st July | 4th August | 18th August | 31st August | Plan | N/A | N/A | 8th September | 1 | 22nd September | Plan | 6th October | 30th October | 21st December
1 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Participation at Bi-lateral & Multilateral Meeting | Least Cost | Lumpsum | MTB | Plan | 4th March | 16th March | 31st March | 7th April | 14th April | 28th April | 2 | Plan | 12th May | 16th June | 30th June | 14th July | 28th July | 11th August | 28th August | Plan | N/A | N/A | 11th September | 2 | 25th September | Plan | 9th October | 30th October | 19th December
2 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Policy & Planning Development | Least cost | Lumpsum | PS | Plan | 2nd March | 13th March | 27th March | 3rd April | 10th April | 24th April | 3 | Plan | 8th May | 29th May | 12th June | 26th June | 10th July | 30th July | 14th August | Plan | N/A | N/A | 28th August | 3 | 11th September | Plan | 25th September | 16th October | 18th December
3 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Security Services & Critical Asset Protection | Least Cost | Lumpsum | MTB | Plan | 4th March | 16th March | 31st March | 7th April | 14th April | 28th April | 4 | Plan | 12th May | 16th June | 30th June | 14th July | 28th July | 11th August | 28th August | Plan | N/A | N/A | 11th September | 4 | 25th September | Plan | 9th October | 30th October | 19th December
4 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Advocacy and Mobilizing Public Support for Power sector reforms | Least Cost | Lumpsum | MTB | Plan | 10th March | 23rd March | 6th April | 14th April | 20th April | 27th April | 5 | Plan | 14t May | 24th June | 6th July | 21st July | 4th August | 18th August | 31st August | Plan | N/A | N/A | 8th September | 5 | 22nd September | Plan | 6th October | 30th October | 21st December
5 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Investment Impact Assessment | Least Cost | Lumpsum | MTB | Plan | 2nd March | 13th March | 27th March | 3rd April | 10th April | 24th April | 6 | Plan | 8th May | 29th May | 12th June | 26th June | 10th July | 30th July | 14th August | Plan | N/A | N/A | 28th August | 6 | 11th September | Plan | 25th September | 16th October | 18th December
6 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Technical Capacity Building IPPs | Least Cost | Lumpsum | MTB | Plan | 5th March | 19th March | 2nd April | 9th April | 16th April | 28th April | 7 | Plan | 11th May | 8th June | 22nd June | 6th July | 20 July | 3rd August | 17th August | Plan | N/A | N/A | 31st August | 7 | 14th September | Plan | 28th September | 19th October | 21st December
7 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Organisation & Sponsorship of Power Exhibition Conference & Trade Fairs | Least Cost | Lumpsum | MTB | Plan | 3rd March | 17th March | 31st March | 7th April | 14th April | 28th April | 8 | Plan | 12th May | 16th June | 30th June | 14th July | 28th July | 11th August | 28th August | Plan | N/A | N/A | 11th September | 8 | 25th September | Plan | 9th October | 30th October | 19th December
8 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Sustenance of Power Sector Administrative Support Structure | Least Cost | Lumpsum | MTB | Plan | 10th March | 23rd March | 6th April | 14th April | 20th April | 27th April | 9 | Plan | 14t May | 24th June | 6th July | 21st July | 4th August | 18th August | 31st August | Plan | N/A | N/A | 8th September | 9 | 22nd September | Plan | 6th October | 30th October | 21st December
9 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Advocacy & Awareness for Successor Companies | Least Cost | Lumpsum | MTB | Plan | 4th March | 16th March | 31st March | 7th April | 14th April | 28th April | 10 | Plan | 12th May | 16th June | 30th June | 14th July | 28th July | 11th August | 28th Auguat | Plan | N/A | N/A | 11th September | 10 | 25th September | Plan | 9th October | 30th October | 19th December
10 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Coal fied Power plant (Feasibility Studies) at Enugu (LOT 1), Gombe, Benue & Kogi State (Lot 2) | Least Cost | lumpsum | MTB | Plan | 2nd March | 13th March | 27th March | 3rd April | 10th April | 24th April | 11 | Plan | 8th May | 29th May | 12th June | 26th June | 10th July | 30th July | 14th August | Plan | N/A | N/A | 28th August | 11 | 11th September | Plan | 25th September | 16th October | 18th December
11 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Mambilla HEPP Geotechnical/Geodetic survey | Least Cost | Lumsump | MTB | Plan | 4th March | 16th March | 31st March | 7th April | 14th April | 28th April | 12 | Plan | 12th May | 16th June | 30th June | 14th July | 28th July | 11th August | 28th August | Plan | N/A | N/A | 11th September | 12 | 25th September | Plan | 9th October | 30th October | 19th December
12 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Consultancy Services for Detailed Engineering Design & Projects | Least Cost | Lumpsum | MTB | Plan | 10th March | 23rd March | 6th April | 14th April | 20th April | 27th April | 13 | Plan | 14t May | 24th June | 6th July | 21st July | 4th August | 18th August | 31st August | Plan | N/A | N/A | 8th September | 13 | 22nd September | Plan | 6th October | 30th October | 21st December
13 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Sensitization Workshop on Capital Budget implementation (M) | Least Cost | Lumpsum | MTB | Plan | 2nd March | 13th March | 27th March | 3rd April | 10th April | 24th April | 14 | Plan | 8th May | 29th May | 12th June | 26th June | 10th July | 30th July | 14th August | Plan | N/A | N/A | 28th August | 14 | 11th September | Plan | 25th September | 16th October | 18th December
14 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Sectoral Contract Management | Least Cost | Lumpsum | MTB | Plan | 5th March | 19th March | 2nd April | 9th April | 16th April | 28th April | 15 | Plan | 11th May | 8th June | 22nd June | 6th July | 20 July | 3rd August | 17th August | Plan | N/A | N/A | 31st August | 15 | 14th September | Plan | 28th September | 19th October | 21st December
15 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Implementation of Bilateral and Multilateral Agreement/MOUS | Least cost | Lumpsum | PS | Plan | 3rd March | 17th March | 31st March | 7th April | 14th April | 28th April | 16 | Plan | 12th May | 16th June | 30th June | 14th July | 28th July | 11th August | 28th August | Plan | N/A | N/A | 11th September | 16 | 25th September | Plan | 9th October | 30th October | 19th December
16 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Tender Advertisement, Tender Evaluation (Technical & Finance) Renting of Evaluation Venue | Least Cost | Lumpsum | PS | Plan | 5th March | 19th March | 2nd April | 9th April | 16th April | 28th April | 17 | Plan | 11th May | 8th June | 22nd June | 6th July | 20 July | 3rd August | 17th August | Plan | N/A | N/A | 31st August | 17 | 14th September | Plan | 28th September | 19th October | 21st December
17 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Engagement of Transaction Advisers for PPP Projects | Least Cost | Lumpsum | PS | Plan | 3rd March | 17th March | 31st March | 7th April | 14th April | 28th April | 18 | Plan | 12th May | 16th June | 30th June | 14th July | 28th July | 11th August | 28th August | Plan | N/A | N/A | 11th September | 18 | 25th September | Plan | 9th October | 30th October | 19th December
18 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Consultancy Services, Data Gathering & Price Data Stoarage & Projects Monitoring | Least Cost | Lumpsum | PS | Plan | 10th March | 23rd March | 6th April | 14th April | 20th April | 27th April | 19 | Plan | 14t May | 24th June | 6th July | 21st July | 4th August | 18th August | 31st August | Plan | N/A | N/A | 8th September | 19 | 22nd September | Plan | 6th October | 30th October | 21st December
19 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Counter Part Funding of Procurement Indenture & Capacity up-grading (UNDP,ILI, IP3) | Least Cost | Lumpsum | PS | Plan | 4th March | 16th March | 31st March | 7th April | 14th April | 28th April | 20 | Plan | 12th May | 16th June | 30th June | 14th July | 28th July | 11th August | 28th August | Plan | N/A | N/A | 11th September | 20 | 25th September | Plan | 9th October | 30th October | 19th December
20 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Up-grading of Accounting system Facilities (A) | Least Cost | Lumpsum | PS | Plan | 2nd March | 13th March | 27th March | 3rd April | 10th April | 24th April | 21 | Plan | 8th May | 29th May | 12th June | 26th June | 10th July | 30th July | 14th August | Plan | N/A | N/A | 28th August | 21 | 11th September | Plan | 25th September | 16th October | 18th December
21 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Privatization & Sector Reform Communication Framework/project (HMO) | Least cost | Lumpsum | MTB | Plan | 4th March | 16th March | 31st March | 7th April | 14th April | 28th April | 22 | Plan | 12th May | 16th June | 30th June | 14th July | 28th July | 11th August | 28th August | Plan | N/A | N/A | 11th September | 22 | 25th September | Plan | 9th October | 30th October | 19th December
22 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Directive Operational System | Least Cost | Lumpsum | MTB | Plan | 10th March | 23rd March | 6th April | 14th April | 20th April | 27th April | 23 | Plan | 14t May | 24th June | 6th July | 21st July | 4th August | 18th August | 31st August | Plan | N/A | N/A | 8th September | 23 | 22nd September | Plan | 6th October | 30th October | 21st December
23 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Sector management information system (PSMIS) | Least Cost | Lumosum | PS | Plan | 2nd March | 13th March | 27th March | 3rd April | 10th April | 24th April | 24 | Plan | 8th May | 29th May | 12th June | 26th June | 10th July | 30th July | 14th August | Plan | N/A | N/A | 28th August | 24 | 11th September | Plan | 25th September | 16th October | 18th December
24 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Power Infrastructure Census | Least Cost | Lumpsum | PS | Plan | 5th March | 19th March | 2nd April | 9th April | 16th April | 28th April | 25 | Plan | 11th May | 8th June | 22nd June | 6th July | 20 July | 3rd August | 17th August | Plan | N/A | N/A | 31st August | 25 | 14th September | Plan | 28th September | 19th October | 21st December
25 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Electrical Demand Load | Least Cost | Lumpsum | MTB | Plan | 3rd March | 17th March | 31st March | 7th April | 14th April | 28th April | 26 | Plan | 12th May | 16th June | 30th June | 14th July | 28th July | 11th August | 28th August | Plan | N/A | N/A | 11th September | 26 | 25th September | Plan | 9th October | 30th October | 19th December
26 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Audit to Evaluate the Status of Budget Implementation,Post Award Audit of Contracts to ensure Conformity with Design & Specifications | Least Cost | Lumpsum | PS | Plan | 10th March | 23rd March | 6th April | 14th April | 20th April | 27th April | 27 | Plan | 14t May | 24th June | 6th July | 21st July | 4th August | 18th August | 31st August | Plan | N/A | N/A | 8th September | 27 | 22nd September | Plan | 6th October | 30th October | 21st December
27 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Electrical Learning | Least Cost | Lumpsum | PS | Plan | 4th March | 16th March | 31st March | 7th April | 14th April | 28th April | 28 | Plan | 12th May | 16th June | 30th June | 14th July | 28th July | 11th August | 28th August | Plan | N/A | N/A | 11th September | 28 | 25th September | Plan | 9th October | 30th October | 19th December
28 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Dashboard Project Monitoring System | Least Cost | lumpsum | MTB | Plan | 2nd March | 13th March | 27th March | 3rd April | 10th April | 24th April | 29 | Plan | 8th May | 29th May | 12th June | 26th June | 10th July | 30th July | 14th August | Plan | N/A | N/A | 28th August | 29 | 11th September | Plan | 25th September | 16th October | 18th December
29 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
| Development of Small & Medium Hydropower Plants | Least Cost | Lumpsum | MTB | Plan | 4th March | 16th March | 31st March | 7th April | 14th April | 28th April | 30 | Plan | 12th May | 16th June | 30th June | 14th July | 28th July | 11th August | 28th August | Plan | N/A | N/A | 11th September | 30 | 25th September | Plan | 9th October | 30th October | 19th December
30 |  |  |  |  | Actual | [7 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual

## Ministry of Tourism Goods
Ministry/Department/Agency: Federal Ministry of Tourism, Culture & National Orientation
Budget year : 2015 | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Procurement Method | Pre-qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Plan vs. Actual | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks | Plan | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
|  |  |  | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Office Stationery/Computer consumables | 001 | 1 | NCB | N/A | MTB | Plan | 5th - 19th Mar | 20th - 27th March | N/A | 1st - 13th April | 25th May | 8th June | 15th June | Plan | N/A | 29th June | 13th July | N/A | 20th June | 6th July
[6 empty] | Actual |  |  |  | N/A |  |  |  | Actual
Purchase of Books |  |  | NS | N/A | A O | Plan | 5th - 19th Mar | 20th - 27 thMarch | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | 20th June | 6th July
[6 empty] | Actual | [7 empty] | Actual
Drugs and Medical Supplies |  |  | NS | N/A | A O | Plan | 5th - 19th Mar | 20th - 27 thMarch | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A |  | N/A | 20th June | 6th July
[6 empty] | Actual | [7 empty] | Actual
Uniforms& other Clothing |  |  | NS | N/A | AO | Plan | 5th - 19th Mar | 20th - 27 thMarch | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A |  | N/A | 20th June | 6th July
[6 empty] | Actual | [7 empty] | Actual
Plant/Generator Fuel |  |  | NS | N/A | AO | Plan | 5th - 19th Mar | 20th - 27 thMarch | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A |  | N/A | 20th June | 6th July
[6 empty] | Actual | [7 empty] | Actual
Purchase of Vehicle fuel | 001 | 2 | NCB | N/A | MTB | Plan | 5th - 19th Mar | 20th - 27 thMarch | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A |  | N/A | 20th June | 6th July
[6 empty] | Actual | [7 empty] | Actual
Sports Equipment | 002 | 1 | NCB |  | MTB | Plan | 5th - 19th Mar | 20th - 27 thMarch | N/A | 1st - 13 April | 25th May | 8th June | 15th June | Plan | N/A | 29th June | 13th July | N/A | 20th June | 6th July
[6 empty] | Actual | [7 empty] | Actual
Acquisition of Cultural Artworks | 002 | 2 | NCB |  | MTB |  | 5th - 19th Mar | 20th - 27 thMarch | N/A | 1st - 13 April | 25th May | 8th June | 15th June |  | N/A | 29th June | 13th July | N/A | 20th June | 6th July
Purchase of Library Books | 002 | 3 | NCB |  | MTB |  | 5th - 19th Mar | 20th - 27 thMarch | N/A | 1st - 13 April | 25th May | 8th June | 15th June |  | N/A | 29th June | 13th July | N/A | 20th June | 6th July
Purchase & Installation of Thermometer Scanners , Hand Washing Machines and Overhead tanks | 002 | 4 |  |  | MTB |  | 5th - 19th Mar | 20th - 27 thMarch | N/A | 1st - 13 April | 25th May | 8th June | 15th June |  | N/A | 29th June | 13th July | N/A | 20th June | 6th July
Purchase of working tools for Cultural Industry centre at Lagos | 002 | 5 |  |  | MTB |  | 5th - 19th Mar | 20th - 27 thMarch | N/A | 1st - 13 April | 25th May | 8th June | 15th June |  | N/A | 29th June | 13th July | N/A | 20th June | 6th July
Procurement of Materials for the slave route Resource centre | 002 | 6 |  |  | MTB |  | 5th - 19th Mar | 20th - 27 thMarch | N/A | 1st - 13 April | 25th May | 8th June | 15th June |  | N/A | 29th June | 13th July | N/A | 20th June | 6th July
Acquisition of underwater Cultural Equipment | 002 | 7 | NCB |  | MTB |  | 5th - 19th Mar | 20th - 27 thMarch | N/A | 1st - 13 April | 25th May | 8th June | 15th June |  | N/A | 29th June | 13th July | N/A | 20th June | 6th July
Acquisition of softwaresfor automation of the Ministry's operations | 002 | 8 | NCB |  | MTB |  | 5th - 19th Mar | 20th - 27 thMarch | N/A | 1st - 13 April | 25th May | 8th June | 15th June |  |  | 29th June | 13th July | N/A | 20th June | 6th July
Procurement of project vehicles | 002 | 9 | NCB |  | MTB |  |  | 20th - 27 thMarch | N/A | 1st - 13 April | 25th May | 8th June | 15th June |  |  | 29th June | 13th July | N/A | 20th June | 6th July

## Works
W
Budgetary Year: 2015 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation | [5 empty] | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Pre-or Post Qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[7 empty] | Actual | [7 empty] | Actual
Printing of non-security documents |  |  | LS | NS | Post Qualification | AO | Plan | 5th - 19th Mar | 20th - 27 thMarch | [5 empty] | Plan | N/A |  |  | N/A
[7 empty] | Actual | [7 empty] | Actual
Printing of Security documents |  |  | LS | NS | Post Qualification | AO | Plan | 5th - 19th Mar | 20th - 27 thMarch | [5 empty] | Plan | N/A |  |  | N/A
Maintenance of Motor vehicle/transport Equipment |  |  | LS | NS | Post Qualification | AO | Plan | 5th - 19th Mar | 20th - 27 thMarch | [5 empty] | Plan | N/A |  |  | N/A
Maintenance of Office Furniture |  |  | LS | NS | Post Qualification | AO | Plan | 5th - 19th Mar | 20th - 27 thMarch | [5 empty] | Plan | N/A |  |  | N/A
Maintenance of Office Building | 001 | 01 | LS | NCB | Post Qualification | MTB | Plan | 5th - 19th Mar | 20th - 27 thMarch | N/A | 1st - 13 April | 25th May | 8th June | 15th June | Plan | N/A | 29th June | 13th July | N/A | Oct 2015 | Dec 2015
[7 empty] | Actual | [7 empty] | Actual
Maintenance of Office/IT Equipment |  |  | LS | NS | Post Qualification | AO | Plan | 5th - 19th Mar | 20th - 27 thMarch | [5 empty] | Plan | N/A |  |  | N/A
[7 empty] | Actual | [7 empty] | Actual
Maintenance of Plant/Generator |  |  | LS | NS | Post Qualification | AO | Plan | 5th - 19th Mar | 20th - 27 thMarch | [5 empty] | Plan | N/A |  |  | N/A
[7 empty] | Actual | [7 empty] | Actual
Other Maintenance Services |  |  |  | NS | Post Qualification | AO | Plan | 5th - 19th Mar | 20th - 27 thMarch | [5 empty] | Plan | N/A |  |  | N/A
[7 empty] | Actual | [7 empty] | Actual
Cleaning & Fumigation Services |  |  | LS | NS | Post Qualification | AO | Plan | 5th - 19th Mar | 20th - 27 thMarch | [5 empty] | Plan | N/A |  |  | N/A
[7 empty] | Actual | [7 empty] | Actual
Office Rent |  |  | LS | DC | Post Qualification | MTB | Plan | 5th - 19th Mar | 20th - 27 thMarch | N/A | 1st - 13 April | 25th May | 8th June | 15th June | Plan | N/A |  |  | N/A | Oct 2015 | Dec 2015
[7 empty] | Actual | [7 empty] | Actual
Construction of 2nd National Arts Theatre in Calabar | 002 | 1 | BoQ | NCB | Post Qualification | MTB |  | 5th - 19th Mar | 20th - 27 thMarch | N/A | 1st - 13 April | 25th May | 8th June | 15th June |  | N/A | 29th June | 13th July | N/A | Oct 2015 | DEC 2015
Construction of cultural Industry Centre at Lagos | 002 | 2 | BoQ | NCB | Post Qualification | MTB |  | 5th - 19th Mar | 20th - 27 thMarch | N/A | 1st - 13 April | 25th May | 8th June | 15th June |  | N/A | 29th June | 13th July | N/A | Oct 2015 | DEC 2015
Construction & provision of infrastructure at Gidan Makama |  |  | LS | NS | Post Qualification | AO |  | 5th - 19th Mar | 20th - 27 thMarch | N/A | [5 empty] | N/A |  |  | N/A
Development of Igbo Ukwu cave | 002 | 3 | BoQ | NCB | Post Qualification | MTB |  | 5th - 19th Mar | 20th - 27 thMarch | N/A | 1st - 13 April | 25th May | 8th June | 15th June |  | N/A |  |  | N/A | Oct 2015 | DEC 2015
Implementation of Tourism Master Plan | 002 | 4 | LS | NCB | Post Qualification | MTB |  | 5th - 19th Mar | 20th - 27 thMarch | N/A | 1st - 13 April | 25th May | 8th June | 15th June |  | N/A | 29th June | 13th July | N/A | Oct 2015 | DEC 2015
Establishment/Maintenance of Cultural Centres | 002 | 5 | LS | NCB | Post Qualification | MTB |  | 5th - 19th Mar | 20th - 27 thMarch | N/A | 1st - 13 April | 25th May | 8th June | 15th June |  | N/A | 29th June | 13th July | N/A | Oct 2015 | DEC 2015
| 002 | 6 | LS | NCB | Post Qualification | MTB |  | 5th - 19th Mar | 20th - 27 thMarch | N/A | 1st - 13 April | 25th May | 8th June | 15th June |  | N/A | 29th June | 13th July | N/A | Oct 2015 | DEC 2015
Production of Tourism promotional Materials
Establishment of community theatres in geo political zones | 002 | 7 | LS | NCB | Post Qualification | MTB |  | 5th - 19th Mar | 20th - 27 thMarch | N/A | 1st - 13 April | 25th May | 8th June | 15th June |  | N/A | 29th June | 13th July | N/A | Oct 2015 | DEC 2015
Development/restructuring of festivals, carnivals exhibition & fashion shows |  |  | LS | NS | Post Qualification | MTB |  | 5th - 19th Mar | 20th - 27 thMarch | N/A | 1st - 13 April | 25th May | 8th June | 15th June |  | N/A |  |  | N/A
Development of creative Industry in Nigeria | 002 | 8 | LS | NCB | Post Qualification | MTB |  | 5th - 19th Mar | 20th - 27 thMarch | N/A | 1st - 13 April | 25th May | 8th June | 15th June |  | N/A | 29th June | 13th July | N/A | Oct 2015 | DEC 2015
Implementation of Cultural Policy | 002 | 9 | LS | NCB | Post Qualification | MTB |  | 5th - 19th Mar | 20th - 27 thMarch | N/A | 1st - 13 April | 25th May | 8th June | 15th June |  | N/A | 29th June | 13th July | N/A | Oct 2015 | DEC 2015
Setting up of Electronic studio | 002 | 10 | LS | NCN | Post Qualification | MTB |  | 5th - 19th Mar | 20th - 27 thMarch | N/A | 1st - 13 April | 25th May | 8th June | 15th June |  |  | 29th June | 13th July | N/A | Oct 2015 | DEC 2015
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual

## Consultancy
Fed. Min. of Tourism,Culture & Nat. Orientation
3EDSX |  | If Post-Review, No-objection Dates are not needed |  |  |  |  | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | Plan vs. Actual | No-objection Date | FEC Approval | Contract Offer | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report
Norm Duration of Proc Steps |  |  |  | Plan | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | Plan | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks | 1- 2 wk | 2 wks | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
List of Contracts
Financial Consulting | QCS | LS | MTB | Plan | 16th Feb 2015 | 9th March 2015 | 24th March | 31stMarch | 3rd April | 13th April,'15 | Plan |  | 1st June 2015 | 15th June 2015 | 29th June 2015 | 13th July, 2015 | 27th July 2015 |  | Plan |  |  | 4th August 2015 | 17th August, 2015 | Plan |  | 21st Sept. | 9th Nov
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Information Technology Consulting | CQS | LS | AO | Plan | 16th Feb 2015 | 9th March 2015 | 24th March | 31stMarch | 3rd April | 13th April,'15 | Plan |  | 1st June 2015 | 15th June 2015 | 29th June 2015 | 13th July, 2015 | 27th July 2015 |  | Plan |  |  | 4th August 2015 | 17th August, 2015 | Plan |  | 21st Sept. | 9th Nov
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Local Training | QCBS | LS | MTB | Plan | 16th Feb 2015 | 9th March 2015 | 24th March | 31stMarch | 3rd April | 13th April,'15 | Plan |  | 1st June 2015 | 15th June 2015 | 29th June 2015 | 13th July, 2015 | 27th July 2015 | 10th August 2015 | Plan |  |  | 17th August 2015 | 24th Augusat, 2015 | Plan | On request | 28th Sept | 7th Dec
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Culture, Costume, Hairdo, Compendium on Traditional Rulers & their Regalia, Cultural Sites & Monuments | LCS | LS | MTB | Plan | 16th Feb 2015 | 9th March 2015 | 24th March | 31stMarch | 3rd April | 13th April,'15 | Plan |  | 1st June 2015 | 15th June 2015 | 29th June 2015 | 13th July, 2015 | 27th July 2015 |  | Plan |  |  | 4th August 2015 | 17th August, 2015 | Plan |  | 21st Sept. | 9th Nov
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Mapping & Documentation of Nigerian Languages (ENDANGERED) | LCS | LS | MTB | Plan | 16th Feb 2015 | 9th March 2015 | 24th March | 31stMarch | 3rd April | 13th April,'15 | Plan |  | 1st June 2015 | 15th June 2015 | 29th June 2015 | 13th July, 2015 | 27th July 2015 |  | Plan |  |  | 4th August 2015 | 17th August, 2015 | Plan |  | 21st Sept. | 9th Nov
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Special Publication on Harmful and Negative Cultural Practices | LCS | LS | MTB | Plan | 16th Feb 2015 | 9th March 2015 | 24th March | 31stMarch | 3rd April | 13th April,'15 | Plan |  | 1st June 2015 | 15th June 2015 | 29th June 2015 | 13th July, 2015 | 27th July 2015 |  | Plan |  |  | 4th August 2015 | 17th August, 2015 | Plan |  | 21st Sept. | 9th Nov
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Preparation/Production of Cultural policy implementation document | QCBS | LS | MTB | Plan | 16th Feb 2015 | 9th March 2015 | 24th March | 31stMarch | 3rd April | 13th April,'15 | Plan |  | 1st June 2015 | 15th June 2015 | 29th June 2015 | 13th July, 2015 | 27th July 2015 | 10th August, 2015 | Plan |  |  | 17th August 2015 | 24th Augusat, 2015 | Plan | On Request | 28th Sept | 7th Dec
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Research/Documentation of traditional foods | CQS | LS | MTB | Plan | 16th Feb 2015 | 9th March 2015 | 24th March | 31stMarch | 3rd April | 13th April,'15 | Plan |  | 1st June 2015 | 15th June 2015 | 29th June 2015 | 13th July, 2015 | 27th July 2015 |  | Plan |  |  | 4th August 2015 | 17th August, 2015 | Plan |  | 21st Sept. | 9th Nov
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Capacity buildsing workshop for practitioners in dance, drama etc. | CQS | LS | MTB | Plan | 16th Feb 2015 | 9th March 2015 | 24th March | 31stMarch | 3rd April | 13th April,'15 | Plan |  | 1st June 2015 | 15th June 2015 | 29th June 2015 | 13th July, 2015 | 27th July 2015 |  | Plan |  |  | 4th August 2015 | 17th August, 2015 | Plan |  | 21st Sept. | 9th Nov
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Documentary on Nigerian Cultural Icons | LCS | LS | MTB | Plan | 16th Feb 2015 | 9th March 2015 | 24th March | 31stMarch | 3rd April | 13th April,'15 | Plan |  | 1st June 2015 | 15th June 2015 | 29th June 2015 | 13th July, 2015 | 27th July 2015 |  | Plan |  |  | 4th August 2015 | 17th August, 2015 | Plan |  | 21st Sept. | 9th Nov
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Domestication of International Cultural codes (Publication) | CQS | LS | AO | Plan | 16th Feb 2015 | 9th March 2015 | 24th March | 31stMarch | 3rd April | 13th April,'15 | Plan |  | 1st June 2015 | 15th June 2015 | 29th June 2015 | 13th July, 2015 | 27th July 2015 |  | Plan |  |  | 4th August 2015 | 17th August, 2015 | Plan |  | 21st Sept. | 9th Nov
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
International Tourism Congress & Investment EXPO | QCBS | LS | MTB | Plan | 16th Feb 2015 | 9th March 2015 | 24th March | 31stMarch | 3rd April | 13th April,'15 | Plan |  | 1st June 2015 | 15th June 2015 | 29th June 2015 | 13th July, 2015 | 27th July 2015 | 10th August, 2015 | Plan |  |  | 17th August 2015 | 24th Augusat, 2015 | Plan | On Request | 28th Sept | 7th Dec
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Formulation of National Policy on Orientation | LCS | LS | MTB | Plan | 16th Feb 2015 | 9th March 2015 | 24th March | 31stMarch | 3rd April | 13th April,'15 | Plan |  | 1st June 2015 | 15th June 2015 | 29th June 2015 | 13th July, 2015 | 27th July 2015 |  | Plan |  |  | 4th August 2015 | 17th August, 2015 | Plan |  | 28th Sept | 7th Dec
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Civic Education | LCS | LS | MTB | Plan | 16th Feb 2015 | 9th March 2015 | 24th March | 31stMarch | 3rd April | 13th April,'15 | Plan |  | 1st June 2015 | 15th June 2015 | 29th June 2015 | 13th July, 2015 | 27th July 2015 |  | Plan |  |  | 4th August 2015 | 17th August, 2015 | Plan |  | 28th Sept | 7th Dec
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Production of sensitization film on core values | LCS | LS | MTB | Plan | 16th Feb 2015 | 9th March 2015 | 24th March | 31stMarch | 3rd April | 13th April,'15 | Plan |  | 1st June 2015 | 15th June 2015 | 29th June 2015 | 13th July, 2015 | 27th July 2015 |  | Plan |  |  | 4th August 2015 | 17th August, 2015 | Plan |  | 21st Sept. | 9th Nov
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Seminars & workshops on Integrity at work place | LCS | LS | MTB | Plan | 16th Feb 2015 | 9th March 2015 | 24th March | 31stMarch | 3rd April | 13th April,'15 | Plan |  | 1st June 2015 | 15th June 2015 | 29th June 2015 | 13th July, 2015 | 27th July 2015 |  | Plan |  |  | 4th August 2015 | 17th August, 2015 | Plan |  | 21st Sept. | 9th Nov
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Production/airing of jingles on ethic and religious tolerance | CQS | LS | MTB | Plan | 16th Feb 2015 | 9th March 2015 | 24th March | 31stMarch | 3rd April | 13th April,'15 | Plan |  | 1st June 2015 | 15th June 2015 | 29th June 2015 | 13th July, 2015 | 27th July 2015 |  | Plan |  |  | 4th August 2015 | 17th August, 2015 | Plan |  | 21st Sept. | 9th Nov
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Formulation of National Policy on Civic Education | LCS | LS | MTB | Plan | 16th Feb 2015 | 9th March 2015 | 24th March | 31stMarch | 3rd April | 13th April,'15 | Plan |  | 1st June 2015 | 15th June 2015 | 29th June 2015 | 13th July, 2015 | 27th July 2015 |  | Plan |  |  | 4th August 2015 | 17th August, 2015 | Plan |  | 21st Sept. | 9th Nov
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Formulation of policy on Citizenship & Patriotism | CQS | LS | MTB | Plan | 16th Feb 2015 | 9th March 2015 | 24th March | 31stMarch | 3rd April | 13th April,'15 | Plan |  | 1st June 2015 | 15th June 2015 | 29th June 2015 | 13th July, 2015 | 27th July 2015 |  | Plan |  |  | 4th August 2015 | 17th August, 2015 | Plan |  | 21st Sept. | 9th Nov
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Consultancy/Equipping of E- Library | CQS | LS | MTB | Plan | 16th Feb 2015 | 9th March 2015 | 24th March | 31stMarch | 3rd April | 13th April,'15 | Plan | 4th May '15 | 1st June 2015 | 15th June 2015 | 29th June 2015 | 13th July, 2015 | 27th July 2015 |  | Plan |  |  | 4th August 2015 | 17th August, 2015 | Plan |  | 21st Sept. | 9th Nov
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Quarterly Progress Report &^Publication | LCS | LS | MTB | Plan | 16th Feb 2015 | 9th March 2015 | 24th March | 31stMarch | 3rd April | 13th April,'15 | Plan |  | 1st June 2015 | 15th June 2015 | 29th June 2015 | 13th July, 2015 | 27th July 2015 |  | Plan |  |  | 4th August 2015 | 17th August, 2015 | Plan |  | 21st Sept. | 9th Nov
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
R&D Research on vital statistics | CQBS | LS | MTB | Plan | 16th Feb 2015 | 9th March 2015 | 24th March | 31stMarch | 3rd April | 13th April,'15 | Plan |  | 1st June 2015 | 15th June 2015 | 29th June 2015 | 13th July, 2015 | 27th July 2015 | 10th August, 2015 | Plan |  |  | 17th August 2015 | 24th Augusat, 2015 | Plan | On Request | 28th Sept | 7th Dec
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual

## Transport Works
FEDERAL MINISTRY OF TRANSPORT Works
Budget Year: 2015
|  |  | Basic Data | [7 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation - Works
| Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pro-Qualification | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance
| Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 24 weeks
Plan vs Actual
1 | Signalling and Communication Equipment (Ajaokuta - Warri) Rail Line (ON-GOING) | Plan | W1 | Lot 1 | Lump Sum | International/National Competitive Bidding | FEC | Lowest Evaluated Responsive Bid | Pre Qualification | Prior Review | 1/3/12 - 16/3/12 | 19/3/12 - 30/3/12 | 2/4/12 - 13/4/12 | 30/4/12 - | 9/6/12 | 11/6/12 - 22/6/12 | 25/6/12 - 6/7/22 | N/A | 9/7/12 - 20/7/12 | 23/7/12 - 3/8/12 | 6/8/12 - 24/8/12 | 27/8/12 - 14/12/12
|  | Actual | [15 empty] | N/A
2 | Construction / Completion Abuja-Idu- Kaduna Rail Line (ON - GOING) | Plan | W2 | Lot 2 | Lump Sum | Direct Procurement | FEC | Most Responsive Bid | Post Qualification | Post Review | 1/3/12 - 16/3/12 | 19/3/12 - 30/3/12 | 2/4/12 - 13/4/12 | 30/4/12 - | 9/6/12 | 11/6/12 - 22/6/12 | 25/6/12 - 6/7/22 | N/A | 9/7/12 - 20/7/12 | 23/7/12 - 3/8/12 | 6/8/12 - 24/8/12 | 27/8/12 - 14/12/12
|  | Actual | [15 empty] | N/A
3 | Construction of National Freight Office, Ilela Border-Sokoto (ON-GOING) | Plan | W4 | Lot 4 | Lump Sum | International/National Competitive Bidding | FEC | Lowest Evaluated Responsive Bid | Pre Qualification | Post Review | 25/3/14 - 15/4/14 | 18/14 - 29/4/14 | 01/5/14 - 12/5/14 | 15/5/14 - 24/6/14 - | 24/6 /14 | 27/6/14 - 15/7/14 | 17/7/14 - 05/8/14 | N/A | 08/8/14 - 19/8/14 | 22/8/14 - 02/9/14 | 5/9/14 - 23/9/14 | 18/11/14 - 22/12/14 | 18/12/14 - 28/12/14
Actual
4 | Construction/Completion of Lagos-Ibadan Rail Line (ON - GOING) | Actual |  |  | Lump Sum | National Competitive Bidding | FEC | Lowest Evaluated Responsive Bid | Pre Qualification | Post Review | 1/3/12 - 16/3/12 | 19/3/12 - 30/3/12 | 2/4/12 - 13/4/12 | 30/4/12 - | 9/6/12 | 11/6/12 - 22/6/12 | 25/6/12 - 6/7/22 | N/A | 9/7/12 - 20/7/12 | 23/7/12 - 3/8/12 | 6/8/12 - 24/8/12 | 27/8/12 - 14/12/12
|  | Plan | w8 | Lot 10
5 | Completion and Rehabilitation of Ajaokuta-Warri Rail Line (ON-GIONG) | Actual |  |  | Lump Sum | National Competitive Bidding | FEC | Lowest Evaluated Responsive Bid | Pre Qualification | Post Review | 1/3/12 - 16/3/12 | 19/3/12 - 30/3/12 | 2/4/12 - 13/4/12 | 30/4/12 - | 9/6/12 | 11/6/12 - 22/6/12 | 25/6/12 - 6/7/22 | N/A | 9/7/12 - 20/7/12 | 23/7/12 - 3/8/12 | 6/8/12 - 24/8/12 | 27/8/12 - 14/12/12
6 | Construction of National Freight Office, Seme Border-Lagos | Plan | W3 | Lot 3 | Lump Sum | International/National Competitive Bidding | FEC | Lowest Evaluated Responsive Bid | Pre Qualification | Post Review | 9/2/15-20/02/2015 | 23/2/15-6/3/2015 | NA | 2015-03-09 | 17/4/15 | 20/4/15-01/5/2015 | 4/5/15-15/5/2015 | N/A | 18/5/15-29/5/2015 | 1/6/15-12/6/2015 | N/A | 15/6/15-29/6/15 | 15/6/15-29/6/2015
Actual
7 | Computerization of Accounting and Budgeting Systems. | Plan | W5 |  | Lump Sum | National Competitive Bidding | MTB | Lowest Evaluated Responsive Bid | Post Qualification | Post Review | 9/2/15-20/02/2015 | 23/2/15-6/3/2015 | NA | 2015-03-09 | 17/4/15 | 20/4/15-01/5/2015 | 4/5/15-15/5/2015 | N/A | 18/5/15-29/5/2015 | 1/6/15-12/6/2015 | N/A | 15/6/15-29/6/15 | 15/6/15-29/6/2015
Actual
8 | Upgrading of Conference Room to Enable Communication/Video Conferencesa and Telepresence System | Actual | NC 4 | Lot 4 | Lump Sum | National Competitive Bidding | PS | Lowest Evaluated Responsive Bid | Post Qualification | Post Review | 9/2/15-20/02/2015 | 23/2/15-6/3/2015 | NA | 2015-03-09 | 17/4/15 | 20/4/15-01/5/2015 | 4/5/15-15/5/2015 | N/A | 18/5/15-29/5/2015 | 1/6/15-12/6/2015 | N/A | 15/6/15-29/6/15 | 15/6/15-29/6/2015
8 | Computerization of Registries and Training of Officers | Plan | W6 | Lot 9 | Lump Sum | National Competitive Bidding | PS | Lowest Evaluated Responsive Bid | Post Qualification | Post Review | 9/2/15-20/02/2015 | 23/2/15-6/3/2015 | NA | 2015-03-09 | 17/4/15 | 20/4/15-01/5/2015 | 4/5/15-15/5/2015 | N/A | 18/5/15-29/5/2015 | 1/6/15-12/6/2015 | N/A | 15/6/15-29/6/15 | 15/6/15-29/6/2015
Actual
Plan
9 | Purchase of Computers/Computerization of Library Including purchase of Scanners and Office Processors for Budget Division | Plan | W7 | Lot 11 | Lump Sum | National Competitive Bidding | PS | Lowest Evaluated Responsive Bid | Post Qualification | Post Review | 9/2/15-20/02/2015 | 23/2/15-6/3/2015 | NA | 2015-03-09 | 17/4/15 | 20/4/15-01/5/2015 | 4/5/15-15/5/2015 | N/A | 18/5/15-29/5/2015 | 1/6/15-12/6/2015 | N/A | 15/6/15-29/6/15 | 15/6/15-29/6/2015
Actual
10 | ECOWAS Freight Offices | Plan | NC 2 | Lot 2 | Lump Sum | National Competitive Bidding | PS | Lowest Evaluated Responsive Bid | Post Qualification | Post Review | 9/2/15-20/02/2015 | 23/2/15-6/3/2015 | NA | 2015-03-09 | 17/4/15 | 20/4/15-01/5/2015 | 4/5/15-15/5/2015 | N/A | 18/5/15-29/5/2015 | 1/6/15-12/6/2015 | N/A | 15/6/15-29/6/15 | 15/6/15-29/6/2015
Actual
Note on H22: FMOT (R&MT):
Note on H25: FMOT (R&MT):

## Non consultancy
FEDERAL MINISTRY TRANSPORT Non-Consultancy Services
Budget Year: 2015
|  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  | Contract Implementation - Consultancy
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 1 weeks | 2 - 4 weeks | 2 weeks | 2 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
Use of National Roads/National Accident Prevention, Road Transport and Transport Scheme, Road Transport Operation Manual and National Transport Master Plan | Plan | NC 1 | Lot 1 | Lumpsum |  | National Competitive Bidding | MTB | Lowest Evaluated Responsive Bid | Post Qualification | Post Review | [14 empty] | NA
Actual
Establishment of the Public Private Partnership | Actual | NC 3 | Lot 3 | Lumpsum |  | National Competitive Bidding | MTB | Lowest Evaluated Responsive Bid | Post Qualification | Post Review | [14 empty] | NA
Forensic Audit Exercise for the Ministry and its Agencies | Plan | NC 5 | Lot 5 | Lumpsum |  | National Competitive Bidding | MTB | Lowest Evaluated Responsive Bid | Post Qualification | Post Review | [14 empty] | NA
Guarantee Seed Fund for Inter State Road Transport | Plan | NC 6 | Lot 6 | Lumpsum |  | National Competitive Bidding | MTB | Lowest Evaluated Responsive Bid | Post Qualification | Post Review | [14 empty] | NA
Participation at Road Sector Development Team (RSDT) & National/International Meetings, Conference and Seminars | Plan | NC 7 | Lot 7 | Lumpsum |  | National Competitive Bidding | MTB | Lowest Evaluated Responsive Bid | Post Qualification | Post Review | [14 empty] | NA
Need Assessment for Institutional capacity strengthning of staff of the dept of Mass Transit | Plan | NC 8 | Lot 8 | Lumpsum |  | National Competitive Bidding | MTB | Lowest Evaluated Responsive Bid | Post Qualification | Post Review
Engineering Research and Development on Rail and Marine Infrastructures | Plan | NC 9 | Lot 9 | Lumpsum |  | National Competitive Bidding | MTB | Lowest Evaluated Responsive Bid | Post Qualification | Post Review | [14 empty] | NA
Implementation of Maritime Safety & Security issues, Coaster Trade(ISPS Code, search and Rescue, Marine Board of Inquiry, Cabotage, NIMPORT,NIMAREX) | Plan | NC 10 | Lot 10 | Lumpsum |  | National Competitive Bidding | MTB | Lowest Evaluated Responsive Bid | Post Qualification | Post Review
Development of Policies/Implementation of water-hycinth removal and utilisation | Plan | NC 11 | Lot 11 | Lumpsum |  | National Competitive Bidding | MTB | Lowest Evaluated Responsive Bid | Post Qualification | Post Review
Co-ordinating Greenfield Port Infrastuture | Plan | NC 12 | Lot 12 | Lumpsum |  | National Competitive Bidding | MTB | Lowest Evaluated Responsive Bid | Post Qualification | Post Review
Stevedoring and related activities | Plan | NC 13 | Lot 13 | Lumpsum |  | National Competitive Bidding | MTB | Lowest Evaluated Responsive Bid | Post Qualification | Post Review
Development of masterplan on Port Development in Nigeria & Inland water Transportation | Plan | NC 14 | Lot 14 | Lumpsum |  | National Competitive Bidding | MTB | Lowest Evaluated Responsive Bid | Post Qualification | Post Review
Supervision /Monitoring of Inland Container Depots | Plan | NC 15 | Lot 15 | Lumpsum |  | National Competitive Bidding | MTB | Lowest Evaluated Responsive Bid | Post Qualification | Post Review

## Goods Transport
FEDERAL MINISTRY OF TRANSPORT
Budget Year: 2015
|  |  | Basic Data | [7 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation - Goods
| Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pro-Qualification | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Arrival of Goods | Inspection/Final Acceptance
| Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
Plan vs Actual
1 | Purchase of Sport Equipments | Plan | G1 | Lot1 | Schedule on Specification | National Competitive Bidding | PS | Lowest Evaluated Responsive Bid | Post Qualification | Post Review | 9/2/15-20/02/2015 | 23/2/15-6/3/2015 | N/A | 2015-03-09 | 17/4/2015 | 20/4/15-01/5/2015 | 4/5/15-15/5/2015 | N/A | 18/5/15-29/5/2015 | 1/6/15-12/6/2015 |  | 15/6/15-29/6/15 | 15/6/15-29/6/2015
Actual
2 | Procurement of Computer Accessories | Plan | G2 | Lot 2 | Schedule on Specification | National Competitive Bidding | MTB | Lowest Evaluated Responsive Bid | Post Qualification | Post Review | 9/2/15-20/02/2015 | 23/2/15-6/3/2015 | N/A | 2015-03-09 | 17/4/2015 | 20/4/15-01/5/2015 | 4/5/15-15/5/2015 | N/A | 18/5/15-29/5/2015 | 1/6/15-12/6/2015 |  | 15/6/15-29/6/15 | 15/6/15-29/6/2015
Actual
3 | Acquisition of materials, Equipments, Softwares and Quality Control Tools for Engineering Dept
|  | Plan | G3 | Lot 3 | Schedule on Specification | National Competitive Bidding | PS | Lowest Evaluated Responsive Bid | Post Qualification | Post Review | 9/2/15-20/02/2015 | 23/2/15-6/3/2015 | N/A | 2015-03-09 | 17/4/2015 | 20/4/15-01/5/2015 | 4/5/15-15/5/2015 | N/A | 18/5/15-29/5/2015 | 1/6/15-12/6/2015 |  | 15/6/15-29/6/15 | 15/6/15-29/6/2015

## Consultancy Transport
FEDERAL MINISTRY OF TRANSPORT Consultancy Services
Budget Year: 2015
|  |  | Basic Data | [7 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [8 empty] | Contract Implementation - Consultancy
| Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/ Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/ Financial | Negotiations | MDA Approval/No Objection Date | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report
| Normal duration of procurement Process | Plan vs Actual | [6 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 4 weeks | 1 weeks | 2 - 4 weeks | 2 weeks | 2 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
1 | National Road Transport and Mass transit Survey and Projection | Actual |  |  | Lump Sum | National Competitive Bidding | MTB | QCBS | Pre - Qualification | Post Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
2 | Compensation/Bill of Qunantities/Construction of frieght offices Nation wide, saki-Oyo State, Idiroko-Ogun State, Seme-Lagos State, Kamba-Kebbi State | Plan
|  | Actual |  |  |  | National Competitive Bidding | FEC | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
3 | Engagement of transaction Advisors(Lead Advisor inclusive) for standard gauge Rail Line- Benin-Agbor-Onitsha-Nnewi-Owerri-Aba with Additional line from Onitsha-Enugu-Abakaliki (500km) | Actual |  |  | Lump Sum | Selective Method | FEC | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
4 | Feasibility Studies for 3No Hinterland Roads Connecting Lekki Deep Sea Port (LDSP) with National Rail and Highways | Plan |  |  | Lump Sum | National Competitive Bidding | FEC | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
5 | Development of Road Transport Operational Manual, Publication, Documentation and Distribution | Plan |  |  | Lump Sum | National Competitive Bidding | PS | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
6 | Sport Development and Capacity Biulding | Plan |  |  | Lump Sum | National Competitive Bidding | PS | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
7 | National Council on Transport Strategy Planning and Implementation | Plan |  |  | Lump Sum | National Competitive Bidding | PS | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
8 | Servicom | Plan |  |  | Lump Sum | National Competitive Bidding | PS | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
9 | Establishment of Public Private Partnership unit | Plan |  |  | Lump Sum | National Competitive Bidding | PS | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
10 | Anticorruption and Transparency Unit | Plan |  |  | Lump Sum | National Competitive Bidding | PS | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
11 | Use of National Road Transport and Transport Scheme, Road Transport Operational Manual and National Transport | Plan |  |  | Lump Sum | National Competitive Bidding | PS | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
12 | National Facilitation Committee under ECOWAS | Plan |  |  | Lump Sum | National Competitive Bidding | PS | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
13 | Biometric and Access Control | Plan |  |  | Lump Sum | National Competitive Bidding | PS | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
14 | Capacity Building for Implementation of FOI Act | Plan |  |  | Lump Sum | National Competitive Bidding | PS | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
15 | Participation at Road Sector Development Team (RSDT) and National/International Meetings, Conferences and Seminars | Plan |  |  | Lump Sum | National Competitive Bidding | PS | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
16 | NEEDS Assessment for Institutional Capacity Strengthening of Staff of the Department of Mass Transit | Plan |  |  | Lump Sum | National Competitive Bidding | PS | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
17 | Establishment of Public Private Partnership unit | Plan |  |  | Lump Sum | National Competitive Bidding | PS | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
18 | Engineering Research and Development on Rail and Marine Infrastructure | Plan |  |  | Lump Sum | National Competitive Bidding | PS | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
19 | Development of Policies/Implementation of Water-Hyacinth Removal and Utilisation | Plan |  |  | Lump Sum | National Competitive Bidding | MTB | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
20 | Coordinating Greenfield Port Infrastructure | Plan |  |  | Lump Sum | National Competitive Bidding | MTB | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
21 | Stevedoring and Related Activities | Plan |  |  | Lump Sum | National Competitive Bidding | MTB | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
22 | Development of Master Plan on Port Development in Nigeria and Inland Water Transportation | Plan |  |  | Lump Sum | National Competitive Bidding | MTB | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
23 | Budget Monitoring and Evaluation | Plan |  |  | Lump Sum | National Competitive Bidding | MTB | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
24 | Capital Budget Implementation and Evaluation | Plan |  |  | Lump Sum | National Competitive Bidding | MTB | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
25 | Forensic Audit Exercise for the Ministry and its Agencies | Plan |  |  | Lump Sum | National Competitive Bidding | PS | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
26 | Guanrantee Seed Fund for InterState Road Transport | Plan |  |  | Lump Sum | National Competitive Bidding | MTB | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
27 | Regional and National Road Corridor Monitoring and Evaluation Exercises (i) Abidjan - Lagos Corridor (ALCO) (ii) Lagos - Kano - Jibiya (LAKAJI) Corridor Group (iii) Borderless Alliance; ECOWAS | Plan |  |  | Lump Sum | National Competitive Bidding | PS | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
28 | Staff Auditing of the Ministry and its Parastatals including Annual Manpower Budget | Plan |  |  | Lump Sum | National Competitive Bidding | PS | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
29 | Periodic Inspection of Infrastructure/Projects for Standard Specification and Quality Control | Plan |  |  | Lump Sum | National Competitive Bidding | PS | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
30 | Supervision/Monitoring of Inland Container Depots | Plan |  |  | Lump Sum | National Competitive Bidding | PS | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
31 | Domestification and Ratification of Imoconvetions | Plan |  |  | Lump Sum | National Competitive Bidding | PS | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
32 | Ministerial Press Briefing and Life Coverages | Plan |  |  | Lump Sum | National Competitive Bidding | MTB | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
33 | Stakeholders Workshop on Urban and Transport Policy | Plan |  |  | Lump Sum | National Competitive Bidding | PS | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
34 | Matters Relating to Port Management Association of West and Central Africa | Plan |  |  | Lump Sum | National Competitive Bidding | PS | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
35 | Attending Engineering International Conferences (IMO, ITU of which the Ministry is in the Technical Team and Rail Technical Conferences) | Plan |  |  | Lump Sum | National Competitive Bidding | PS | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
36 | Implementatiion of Maritime Safety and Security Issues, Coastal Trade (ISPS Code,, Search and Rescue, Marine Board of Enquiry, Cabotage, NIMPORT, NIMAREX) | Plan |  |  | Lump Sum | National Competitive Bidding | MTB | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15
37 | IMO Conventions, Protocols and Compliance Matters (IMO Meetings, World Maritime Day, Port Reception Facility Inspection, Sea Farers Day, IOPC) | Plan |  |  | Lump Sum | National Competitive Bidding | PS | QCBS | Pre-qualification | Prior Review | 2/2/15 - 20/2/15 | 23/2/15 - 6/3/15 | 9/3/15 - 20/3/15 | 23/3/15 - 27/3/15 | 30/3/15 - 10/4/15 | 13/4/15 - 24/4/15 | 2015-04-27 | 2015-05-22 | 25/5/15 - 5/6/15 | 8/6/15 - 19/6/15 | 22/6/15 - 3/7/15 | 6/7/15 - 17/7/15 | 20/7/15 - 31/7/15 | 3/8/15 - 28/8/15 | 31/8/15 - 28/8/15 | 14/9/15 - 25/9/15 | 28/9/15 - 9/10/15 | 12/10/15 - 23/10/15

## Water Resources Goods
MINISTRY OF WATER RESOURCES | [5 empty] | THE TIME LINE IS TO BE COMPARED WITH THE COUNCILS APPROVAL
Budgetary Year: 2015 | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Procurement Method | Pre-qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing/ Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Plan vs. Actual | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection/ Final Acceptance
Norm Duration of Proc Steps |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 4 -6 wks |  | 2 wks | 2 - 4 wks | Plan | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
|  |  |  | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Purchase of Office Furniture and Fittings | (WR.GS C01) | C1 | NCB | 1st Wk. Mar | AO | Plan | 2nd. Wk.March | 3rd wkMarch | 4th Wk. March | 1st Wk.April. | 1st Wk. June | 3rd Wk. June | 1st Wk. July | Plan | N/A | 2nd Wk. July | 3rd Wk. July | 2nd Wk. Aug. | 4th Wk Aug. | 4th Wk. Aug.
[6 empty] | Actual | [7 empty] | Actual
Purchase of Computers | WR.GS C02 | C2 | NCB | 1st Wk. Mar | AO | Plan | 2nd. Wk.March | 3rd wkMarch | 4th Wk. March | 1st Wk.April. | 1st Wk. June | 3rd Wk. June | 1st Wk. July | Plan | N/A | 2nd Wk. July | 3rd Wk. July | 2nd Wk. Aug. | 4th Wk Aug. | 4th Wk. Aug.
[6 empty] | Actual | [7 empty] | Actual
Purchase of Shredding Machines | WR.GS C03 | C3 | NCB | 1st Wk. Mar | AO | Plan | 2nd. Wk.March | 3rd wkMarch | 4th Wk. March | 1st Wk.April. | 1st Wk. June | 3rd Wk. June | 1st Wk. July | Plan | N/A | 2nd Wk. July | 3rd Wk. July | 2nd Wk. Aug. | 4th Wk Aug. | 4th Wk. Aug.
[6 empty] | Actual | [7 empty] | Actual
Purchase of Power Generating Set | WR.GS C04 | C4 | NCB | 1st Wk. Mar | AO | Plan | 2nd. Wk.March | 3rd wkMarch | 4th Wk. March | 1st Wk.April. | 1st Wk. June | 3rd Wk. June | 1st Wk. July | Plan | N/A | 2nd Wk. July | 3rd Wk. July | 2nd Wk. Aug. | 4th Wk Aug. | 4th Wk. Aug.
[6 empty] | Actual | [7 empty] | Actual
Purchase of Fire Fighting Equipment | WR.GS C05 | C5 | NCB | 1st Wk. Mar | AO | Plan | 2nd. Wk.March | 3rd wkMarch | 4th Wk. March | 1st Wk.April. | 1st Wk. June | 3rd Wk. June | 1st Wk. July | Plan | N/A | 2nd Wk. July | 3rd Wk. July | 2nd Wk. Aug. | 4th Wk Aug. | 4th Wk. Aug.
[6 empty] | Actual | [7 empty] | Actual
Purchase of Security Equipment | WR.GS C06 | C6 | NCB | 1st Wk. Mar | AO | Plan | 2nd. Wk.March | 3rd wkMarch | 4th Wk. March | 1st Wk.April. | 1st Wk. June | 3rd Wk. June | 1st Wk. July | Plan | N/A | 2nd Wk. July | 3rd Wk. July | 2nd Wk. Aug. | 4th Wk Aug. | 4th Wk. Aug.
[6 empty] | Actual | [7 empty] | Actual
Purchase of Motor Vehicles for Accounts, Budget and Internal Audit. | WR DFA C07 | C7 | NCB | 1st Wk. Mar | AO | Plan | 2nd. Wk.March | 3rd wkMarch | 4th Wk. March | 1st Wk.April. | 1st Wk. June | 3rd Wk. June | 1st Wk. July | Plan | NA | 2nd Wk. July | 3rd Wk. July | 2nd Wk. Aug. | 4th Wk Aug. | 4th Wk. Aug.
[6 empty] | Actual | [7 empty] | Actual
Note on K5: BPP:

## Works water resources
Ministry/Department/Agency:
Budgetary Year: 2015 | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: |  | Basic Data | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation | [5 empty] | Contract Implementation
Project Description* | Package Number | Lot Number | Procurement Method | Pre-or Post Qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Plan vs. Actual | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance
Norm Duration of Proc Steps |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks |  | 2 - 3 wks | 1 - 2 wks | Plan | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
|  |  |  | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts |  |  |  | YES/NO
Rehabilitation of existing irrigation infrastructure at the Lower Anambra Irrigation Project | WRIR.01 | A1 | NCB | 1st Wk. March | AO | Plan | 3rd Wk.Mar | 2nd Wk Mar. | 3rd Wk. Mar. | 4th Wk. Mar. | 2nd Wk.May | 4th Wk. May | 1st Wk. June | Plan | N/A | 1st Wk. June | 1st Wk. June | N/A | 4th Wk Sept. | 4th Wk. Dec.
[6 empty] | Actual | [7 empty] | Actual
Rehabilitation of water Pumping and Treatment Plant at Ibore-Irrua and Reservior Facilities at Livue-Uromi | WRWS. 02 | A2 | NCB | 1st Wk. March | MTB | Plan | 3rd Wk.Mar | 2nd Wk Mar. | 3rd Wk. Mar. | 4th Wk. Mar. | 2nd Wk.May | 4th Wk. May | 1st Wk. June | Plan | N/A | 1st Wk. June | 1st Wk. June | N/A | 4th Wk Sept. | 4th Wk. Dec.
[6 empty] | Actual | [7 empty] | Actual
Upgrading of small water supply Scheme | WRWS. 03 | A3 | NCB | 1st Wk. March | MTB | Plan | 3rd Wk.Mar | 2nd Wk Mar. | 3rd Wk. Mar. | 4th Wk. Mar. | 2nd Wk.May | 4th Wk. May | 1st Wk. June | Plan | N/A | 1st Wk. June | 1st Wk. June | N/A | 4th Wk Sept. | 4th Wk. Dec.
Rehabilitation of Azare Water Supply Scheme | WRWS. 04 | A4 | NCB | 1st Wk. March | MTB | Plan | 3rd Wk.Mar | 2nd Wk Mar. | 3rd Wk. Mar. | 4th Wk. Mar. | 2nd Wk.May | 4th Wk. May | 1st Wk. June | Plan | N/A | 1st Wk. June | 1st Wk. June | N/A | 4th Wk Sept. | 4th Wk. Dec.
Digital Achiving of the Ministry's Registry | WRHR. 05 | A5 | NCB | 1st Wk. March | AO | Plan | 3rd Wk.Mar | 2nd wk. Marc | 2nd Wk. Mar. | 3rd Wk. Mar. | 30th Apr. | 2nd Wk. May | 3rd Wk.May | Plan | N/A | 1st Wk.June | 2nd Wk. Jun | 4th Wk.June | 3rd Wk. Jul. | 1st Wk. Aug.
Equipping of the Ministry's In-house Clinic | WRHR. 06 | A6 | NS | 1st Wk. March | AO | Plan | 3rd Wk.Mar | 1st Wk. Mar. | 2nd Wk. Mar. | 3rd Wk. Mar. | 30th Apr. | 2nd Wk. May | 3rd Wk.May | Plan | N/A | 1st Wk.June | 2nd Wk. Jun | 4th Wk.June | 3rd Wk. Jul. | 1st Wk. Aug.
[6 empty] | Actual | [7 empty] | Actual
Procurement and equipping of the main Minisry's Training Hall. | WRHR. 07 | A7 | NS | 1st Wk. March | AO | Plan | 3rd Wk.Mar | 1st Wk. Mar. | 2nd Wk. Mar. | 3rd Wk. Mar. | 30th Apr. | 2nd Wk. May | 3rd Wk.May | Plan | N/A | 1st Wk.June | 2nd Wk. Jun | 4th Wk.June | 3rd Wk. Jul. | 1st Wk. Aug.
[6 empty] | Actual | [7 empty] | Actual
Installation of Editting Suite for timely editing for airing of news stories and YouTube posting. | WR.PRESS 08 | A8 | NS | 1st Wk. March | AO | Plan | 3rd Wk.Mar | 1st Wk. Mar. | 1st Wk. Mar. | 1st Wk. Mar. | 3rd Wk. Mar | 4th Wk. Mar | 4th Wk. Mar | Plan | N/A | 1st Wk. Apr. | 1st Wk. Apr. | 1st Wk. Apr. | 1st Wk. May | 1st Wk. May
[6 empty] | Actual | [7 empty] | Actual
Purchase and installation of 10 nos. Computer Desttop and 10 nos Laptop | WR.PRESS 09 | A9 | NS | 1st Wk. March | AO | Plan | 3rd Wk.Mar | 1st Wk. Mar. | 1st Wk. Mar. | 1st Wk. Mar. | 3rd Wk. Mar | 4th Wk. Mar | 4th Wk. Mar | Plan | N/A | 1st Wk. Apr. | 1st Wk. Apr. | 1st Wk. Apr. | 1st Wk. May | 1st Wk. May
[6 empty] | Actual | [7 empty] | Actual
Rehabilitation /Repairs of Office Buildings | WR.GS 10 | A10 | NCB | 1st Wk. March | MTB | Plan | 3rd Wk.Mar | 2nd Wk Mar. | 3rd Wk. Mar. | 4th Wk. Mar. | 2nd Wk.May | 4th Wk. May | 1st Wk. June | Plan | N/A | 1st Wk. June | 1st Wk. June | N/A | 4th Wk Sept. | 4th Wk. Dec.
[6 empty] | Actual | [7 empty] | Actual
Construction of Oghidekpe Earth Dam Ekpoma, Edo State. | WR DR.11 | A11 | NCB | 1st Wk. March | MTB | Plan | 3rd Wk.Mar | 2nd Wk Mar. | 3rd Wk. Mar. | 4th Wk. Mar. | 2nd Wk.May | 4th Wk. May | 1st Wk. June | Plan | N/A | 1st Wk. June | 1st Wk. June | N/A | 4th Wk Sept. | 4th Wk. Dec.
[6 empty] | Actual | [7 empty] | Actual
Construction of Ezeala Akpaka Earth Dam and Hydropower Project, Umueze 1 Ehime Mbano LGA, Imo State | WR DR 12 | A12 | NCB | 1st Wk. March | MTB | Plan | 3rd Wk.Mar | 2nd Wk Mar. | 3rd Wk. Mar. | 4th Wk. Mar. | 2nd Wk.May | 4th Wk. May | 1st Wk. June | Plan | NA | 1st Wk. June | 1st Wk. June | N/A | 4th Wk Sept. | 4th Wk. Dec.
[6 empty] | Actual | [7 empty] | Actual
Construction of Small Earth Dam FUT Minna | WR DR 13 | A13 | NCB | 1st Wk. March | MTB | Plan | 3rd Wk.Mar | 2nd Wk Mar. | 3rd Wk. Mar. | 4th Wk. Mar. | 2nd Wk.May | 4th Wk. May | 1st Wk. June | Plan | NA | 1st Wk. June | 1st Wk. June | NA | 4th Wk Sept. | 4th Wk. Dec.
[6 empty] | Actual | [7 empty] | Actual
Kano River Irrigation Project | WR IR 14 | A14 | NCB | 1st Wk. March | MTB | Plan | 3rd Wk.Mar | 2nd Wk Mar. | 3rd Wk. Mar. | 4th Wk. Mar. | 2nd Wk.May | 4th Wk. May | 1st Wk. June | Plan | NA | 1st Wk. June | 1st Wk. June | NA | 4th Wk Sept. | 4th Wk. Dec.
[6 empty] | Actual | [7 empty] | Actual

## Consultancy water resources
Ministry/Department/Agency:
Budgetary Year: 2015 |  | If Post-Review, No-objection Dates are not needed |  |  |  |  | Request for Expression of Interest (when required)
Desk Officer/Contact #: MUSA ODINIYA |  | Contract Type |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | Plan vs. Actual | No-objection Date | FEC Approval | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report
Norm Duration of Proc Steps |  |  |  | Plan | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | Plan | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks | 2 wks | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  | Actual
List of Contracts
Participation at Conferences & Seminars: Organise National Sensitization Workshop on Climate Change information dissemination. (WRCC. B01) | NS | Lumpsum | AO | Plan | 3rd Wk.Feb. | 1st Wk. Mar. | 2nd Wk. Mar. | 3rd Wk. Mar. | 4th Wk. Mar | 2nd Wk. May | Plan | 3rd Wk.May | 2nd Wk. June | 4th Wk. June | 2nd Wk. July | 4th Wk. July | 2nd Wk. Aug. | 2nd Wk. Aug. | Plan | N/A | N/A | 4th Wk. Aug. | Plan | 4th Wk. Aug. | OCT. | NOV.
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  | Actual
Publication of Climate Change Information Model for Hydrological Area One: Part payment to Messrs. Seda Afritech International Nig. Ltd. For the publication of "Climate Change Information Guide" (WRCC. B02) | NS | Lumpsum | AO | Plan | 3rd Wk.Feb. | 1st Wk. Mar. | 2nd Wk. Mar. | 3rd Wk. Mar. | 4th Wk. Mar | 2nd Wk. May | Plan | 3rd Wk.May | 2nd Wk. June | 4th Wk. June | 2nd Wk. July | 4th Wk. July | 2nd Wk. Aug. | 2nd Wk. Aug. | Plan | N/A | N/A |  | Plan | 4th Wk. Aug. | OCT. | NOV.
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  | Actual
Urumba North Regional Water Supply Scheme (Study and Design Only) (WRWS. B03) | NCB | Lumpsum | AO | Plan | 3rd Wk.Feb. | 1st Wk. Mar. | 2nd Wk. Mar. | 3rd Wk. Mar. | 4th Wk. Mar | 2nd Wk. May | Plan | 3rd Wk.May | 2nd Wk. June | 4th Wk. June | 2nd Wk. July | 4th Wk. July | 2nd Wk. Aug. | 2nd Wk. Aug. | Plan | N/A | N/A |  | Plan | 4th Wk. Aug. | OCT. | NOV.
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  | Actual
Social Media Engagement (Instant feedback from intended Beneficiaries) (WR.PRESS B04) | NS | Lumpsum | AO | Plan | 3rd Wk.Feb. | 1st Wk. Mar. | 2nd Wk. Mar. | 3rd Wk. Mar. | 4th Wk. Mar | 2nd Wk. May | Plan | 3rd Wk.May | 2nd Wk. June | 4th Wk. June | 2nd Wk. July | 4th Wk. July | 2nd Wk. Aug. | 2nd Wk. Aug. | Plan | N/A | N/A | 4th Wk. Aug. | Plan | 4th Wk. Aug. | OCT. | NOV.
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  | Actual
Establishment of Information Management System (WR.PRESS B05) | NS | Lumpsum | AO | Plan | 3rd Wk.Feb. | 1st Wk. Mar. | 2nd Wk. Mar. | 3rd Wk. Mar. | 4th Wk. Mar | 2nd Wk. May | Plan | 3rd Wk.May | 2nd Wk. June | 4th Wk. June | 2nd Wk. July | 4th Wk. July | 2nd Wk. Aug. | 2nd Wk. Aug. | Plan | N/A | N/A | 4th Wk. Aug. | Plan | 4th Wk. Aug. | OCT. | NOV.
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  | Actual
Development and Implementation of Communication Strategy (WR.PRESS B06) | NS | Lumpsum | AO | Plan | 3rd Wk.Feb. | 1st Wk. Mar. | 2nd Wk. Mar. | 3rd Wk. Mar. | 4th Wk. Mar | 2nd Wk. May | Plan | 3rd Wk.May | 2nd Wk. June | 4th Wk. June | 2nd Wk. July | 4th Wk. July | 2nd Wk. Aug. | 2nd Wk. Aug. | Plan | N/A | N/A | 4th Wk. Aug. | Plan | 4th Wk. Aug. | OCT. | NOV.
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  | Actual
Development of Social Media Networking (WR. PRESS B07) | NS | Lumpsum | AO | Plan | 3rd Wk.Feb. | 1st Wk. Mar. | 2nd Wk. Mar. | 3rd Wk. Mar. | 4th Wk. Mar | 2nd Wk. May | Plan | 3rd Wk.May | 2nd Wk. June | 4th Wk. June | 2nd Wk. July | 4th Wk. July | 2nd Wk. Aug. | 2nd Wk. Aug. | Plan | N/A | N/A | 4th Wk. Aug. | Plan | 4th Wk. Aug. | OCT. | NOV.
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  | Actual
Development of Advanced and Information Technology (WR. PRESS B08) | NS | Lumpsum | AO | Plan | 3rd Wk.Feb. | 1st Wk. Mar. | 2nd Wk. Mar. | 3rd Wk. Mar. | 4th Wk. Mar | 2nd Wk. May | Plan | 3rd Wk.May | 2nd Wk. June | 4th Wk. June | 2nd Wk. July | 4th Wk. July | 2nd Wk. Aug. | 2nd Wk. Aug. | Plan | N/A | N/A | 4th Wk. Aug. | Plan | 4th Wk. Aug. | OCT. | NOV.
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  | Actual
Coordinating & Appraisal of Ministry's Capacity Building Programme. (WR.HR B09) | DC | Lumpsum | AO | Plan | 3rd Wk.Feb. | 1st Wk. Mar. | 2nd Wk. Mar. | 3rd Wk. Mar. | 4th Wk. Mar | 2nd Wk. May | Plan | 3rd Wk.May | 2nd Wk. June | 4th Wk. June | 2nd Wk. July | 4th Wk. July | 2nd Wk. Aug. | 2nd Wk. Aug. | Plan | N/A | N/A | 4th Wk. Aug. | Plan | 4th Wk. Aug. | OCT. | NOV.
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  | Actual
In-house Capacity Building | DIRECT | Lumpsum | AO | Plan | 3rd Wk.Feb. | 1st Wk. Mar. | 2nd Wk. Mar. | 3rd Wk. Mar. | 4th Wk. Mar | 2nd Wk. May | Plan | 3rd Wk.May | 2nd Wk. June | 4th Wk. June | 2nd Wk. July | 4th Wk. July | 2nd Wk. Aug. | 2nd Wk. Aug. | Plan | N/A | N/A | 4th Wk. Aug. | Plan | 4th Wk. Aug. | OCT. | NOV.
| DIRECT | Lumpsum | AO | Actual | 3rd Wk.Feb. | 1st Wk. Mar. | 2nd Wk. Mar. | 3rd Wk. Mar. | 4th Wk. Mar | 2nd Wk. May | Actual | 3rd Wk.May | 2nd Wk. June | 4th Wk. June | 2nd Wk. July | 4th Wk. July | 2nd Wk. Aug. | 2nd Wk. Aug. | Actual | N/A | N/A | 4th Wk. Aug. | Actual | 4th Wk. Aug. | OCT. | NOV.
Plan
Study and Design of Amagu Dam, Ebonyi State | NCB | Com.T/Bas. | MTB |  | 3rd Wk.Feb. | 1st Wk. Mar. | 2nd Wk. Mar. | 3rd Wk. Mar. | 4th Wk. Mar | 2nd Wk. May |  | 3rd Wk.May | 2nd Wk. June | 4th Wk. June | 2nd Wk. July | 4th Wk. July | 2nd Wk. Aug. | 2nd Wk. Aug. | Actual | N/A | N/A | 4th Wk. Aug. |  | 4th Wk. Aug. | OCT. | NOV.
Plan
Study and Design of Shimankar Dam, Shandam LGA Plateau State | NCB | Com.T/Bas. | MTB |  | 3rd Wk.Feb. | 1st Wk. Mar. | 2nd Wk. Mar. | 3rd Wk. Mar. | 4th Wk. Mar | 2nd Wk. May |  | 3rd Wk.May | 2nd Wk. June | 4th Wk. June | 2nd Wk. July | 4th Wk. July | 2nd Wk. Aug. | 2nd Wk. Aug. | Actual | N/A | N/A | 4th Wk. Aug. |  | 4th Wk. Aug. | OCT. | NOV.
Plan
Study and Design of Madara/Bukachuwa Earth Dam, Bauchi State. | NCB | Com.T/Bas. | MTB |  | 3rd Wk.Feb. | 1st Wk. Mar. | 2nd Wk. Mar. | 3rd Wk. Mar. | 4th Wk. Mar | 2nd Wk. May |  | 3rd Wk.May | 2nd Wk. June | 4th Wk. June | 2nd Wk. July | 4th Wk. July | 2nd Wk. Aug. | 2nd Wk. Aug. | Actual | N/A | N/A | 4th Wk. Aug. |  | 4th Wk. Aug. | OCT. | NOV.
Plan
Study and Design of Koko Earth Dam, Kebbi, Kebbi State. | NCB | Com.T/Bas. | MTB |  | 3rd Wk.Feb. | 1st Wk. Mar. | 2nd Wk. Mar. | 3rd Wk. Mar. | 4th Wk. Mar | 2nd Wk. May |  | 3rd Wk.May | 2nd Wk. June | 4th Wk. June | 2nd Wk. July | 4th Wk. July | 2nd Wk. Aug. | 2nd Wk. Aug. | Actual | N/A | N/A | 4th Wk. Aug. |  | 4th Wk. Aug. | OCT. | NOV.
Fill gray cells only!

## Women Affairs
Ministry/Department/Agency: FEDERAL MINISTRY OF WOMEN AFFAIRS AND SOCIAL DEVELOPMENT. | [5 empty] | CATEGORY D
Budget Year: 2015
|  | Basic Data | [7 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  | Contract Implementation - Consultancy
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 1 weeks | 2 - 4 weeks | 2 weeks | 2 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
ESTABLISHMENT AND UPGRADING OF DATA BANK. | PLAN | FMWASD/2015/CONS/CAP/1 | D1 | CONSULTANCY | NCB | MTB | LEB | NA | NA | 23RD FEB.- 16TH MARCH. | 16TH - 30TH MARCH | 30TH MARCH - 13TH APRIL | 13TH -20TH APRIL | 20TH APRIL - 18TH MAY | 18TH MAY- 1ST JUNE | 1ST - 15TH JUNE | 15TH JUNE | 27TH APRIL - 11TH MAY | 11TH - 25TH MAY | 25TH MAY - 8TH JUNE | 8TH - 22ND JUNE | NA | 10TH AUG. - 7TH SEPT. | NA | 7TH - 21ST SEPT. | 21ST - 5TH OCT. | NA | 5TH OCT.-2ND NOV. | 2ND -16TH NOV.
REVIEW AND PRODUCTION OF NIGERIA GENDER STATISTICS BOOK | PLAN | FMWASD/2015/CONS/CAP/2 | D2 | CONSULTANCY | NCB | PS | LEB | NA | NA | 23RD FEB.- 16TH MARCH. | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
IMPACT EVALUATION ON THE INTERVENTIONS OF THE 2008 VC SURVEY IN NIGERIA. | PLAN | FMWASD/2015/CONS/CAP/3 | D3 | CONSULTANCY | NCB | PS | LEB | NA | NA | 23RD FEB.- 16TH MARCH. | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
SURVEY AND PRODUCTION OF THE STATISCAL DATA OF THE CONDITIONS OF VGs (VC, PWDs AND OLDER PERSONS) IN NIGERIA. (TO REPLACE, REVIEW AND PRODUCE THE 3RD EDITION OF NATIONAL GENDER STATISTICS BOOK). | PLAN | FMWASD/2015/CONS/CAP/4 | D4 | CONSULTANCY | NCB | MTB | LEB | NA | NA | 23RD FEB.- 16TH MARCH. | 16TH - 30TH MARCH | 9TH - 23RD FEBRUARY. | 23RD FEB. - 2ND MARCH | 2ND -30TH MARCH | 30TH MARCH - 13TH APRIL | 13TH - 27TH APRIL | 27TH APRIL | 27TH APRIL - 11TH MAY | 11TH - 25TH MAY | 25TH MAY - 8TH JUNE | 8TH - 22ND JUNE | NA | 22ND JUNE- 6TH JULY | NA | 6TH - 28TH JULY | 28TH JULY | NA | 28TH JULY - 8TH SEPT. | 8TH - 22ND SEPT.
CONSULTANCY SERVICES FOR THE CONSTRUCTION OF MALE AND FEMALE HOSTELS AT THE NATIONAL REHABILITATION INSTITUTE AND RESOURCE CENTRE, ABUJA. | ACTUAL | FMWASD/2015/CONS/ONGOING/1 | ONGOING | CONSULTANCY

## Goods women affairs
Ministry/Department/Agency: FEDERAL MINISTRY OF WOMEN AFFAIRS AND SOCIAL DEVELOPMENT
Budget Year: 2015
|  | Basic Data | [7 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation - Goods
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | MDA Approval/No Objection Date | Submission of Prequalification Evaluation Report | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Arrival of Goods | Inspection/Final Acceptance
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 - 4 weeks | 2 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
Plan vs Actual
PROCUREMENT AND DISTRIBUTION OF AIDS APPLIANCES AND MATERIAL RELIEF TO OLD PEOPLES HOMES AND DAYCARE CENTRES FOR ELDERLY. | PLAN | FMWASD/2015/GOODS/CAP/1 | A1 | GOODS | NCB | MTB | LEB | NA | NA | 23RD FEB.- 16TH MARCH. | 16TH - 30TH MARCH | NA | NA | NA | 30TH MARCH - 11TH MAY | 11TH MAY | 11TH MAY - 1ST JUNE | 1ST -29TH JUNE | NA | 29TH JUNE- 13TH JULY | 13TH - 27TH JULY | NA | 27TH JULY -17TH AUG. | 17TH - 31ST AUG.
PROCUREMENT OF AIDS APPLIANCES FOR PERSONS WITH DISABILITIES (PWDs) | PLAN | FMWASD/2015/GOODS/CAP/2 | A2 | GOODS | NCB | MTB | LEB | NA | NA | 23RD FEB.- 16TH MARCH. | 16TH - 30TH MARCH | NA | NA | NA | 30TH MARCH - 11TH MAY | 11TH MAY | 11TH MAY - 1ST JUNE | 1ST -29TH JUNE | NA | 29TH JUNE- 13TH JULY | 13TH - 27TH JULY | NA | 27TH JULY -17TH AUG. | 17TH - 31ST AUG.
SUPPLY OF OFFICE EQUIPMENTS | PLAN | FMWASD/2015/GOODS/CAP/3 | A3 | GOODS | NCB | MTB | LEB | NA | NA | 23RD FEB.- 16TH MARCH. | 16TH - 30TH MARCH | NA | NA | NA | 30TH MARCH - 11TH MAY | 11TH MAY | 11TH MAY - 1ST JUNE | 1ST -29TH JUNE | NA | 29TH JUNE- 13TH JULY | 13TH - 27TH JULY | NA | 27TH JULY -17TH AUG. | 17TH - 31ST AUG.
SUPPLY OF OFFICE STATIONERIES / COMPUTERS CONSUMABLES | PLAN | FMWASD/2015/GOODS/REC/1 | A4 | GOODS | NCB | MTB | LEB | NA | NA | 23RD FEB.- 16TH MARCH. | 16TH - 30TH MARCH | NA | NA | NA | 30TH MARCH - 11TH MAY | 11TH MAY | 11TH MAY - 1ST JUNE | 1ST -29TH JUNE | NA | 29TH JUNE- 13TH JULY | 13TH - 27TH JULY | NA | 27TH JULY -17TH AUG. | 17TH - 31ST AUG.
SUPPLY OF TEACHING AIDS/INSTRUCTION MATERIALS (PROVISION FOR ALL DEPARTMENTS) | PLAN | FMWASD/2015/GOODS/REC/2 | A5 | GOODS | NCB | MTB | LEB | NA | NA | 23RD FEB.- 16TH MARCH. | 16TH - 30TH MARCH | NA | NA | NA | 30TH MARCH - 11TH MAY | 11TH MAY | 11TH MAY - 1ST JUNE | 1ST -29TH JUNE | NA | 29TH JUNE- 13TH JULY | 13TH - 27TH JULY | NA | 27TH JULY -17TH AUG. | 17TH - 31ST AUG.
SUPPLY OF OFFICE/IT EQUIPMENT | PLAN | FMWASD/2015/GOODS/REC/3 | A6 | GOODS | NCB | MTB | LEB | NA | NA | 23RD FEB.- 16TH MARCH. | 16TH - 30TH MARCH | NA | NA | NA | 30TH MARCH - 11TH MAY | 11TH MAY | 11TH MAY - 1ST JUNE | 1ST -29TH JUNE | NA | 29TH JUNE- 13TH JULY | 13TH - 27TH JULY | NA | 27TH JULY -17TH AUG. | 17TH - 31ST AUG.
PROCUREMENT OF MATERIALS FOR NATIONAL RE-INTEGRATION OF EX-JUVENILE OFFENDERS. | PLAN | FMWASD/2015/GOODS/CAP/4 | A7 | GOODS | NCB | PS | LEB | NA | NA | 23RD FEB.- 16TH MARCH. | 16TH - 30TH MARCH | NA | NA | NA | 30TH MARCH - 11TH MAY | 11TH MAY | 11TH MAY - 1ST JUNE | 1ST -29TH JUNE | NA | 29TH JUNE- 13TH JULY | 13TH - 27TH JULY | NA | 27TH JULY -17TH AUG. | 17TH - 31ST AUG.
CAPACITY BUILDING FOR SOCIAL WORKERS AND SOCIAL WELFARE SUPPORT FOR FAMILIES AND ALL VULNERABLE GROUPS. (MDG) | PLAN | FMWASD/2015/GOODS/CAP/5 | A8 | GOODS | NCB | PS | LEB | NA | NA | 23RD FEB.- 16TH MARCH. | 16TH - 30TH MARCH | NA | NA | NA | 30TH MARCH - 11TH MAY | 11TH MAY | 11TH MAY - 1ST JUNE | 1ST -29TH JUNE | NA | 29TH JUNE- 13TH JULY | 13TH - 27TH JULY | NA | 27TH JULY -17TH AUG. | 17TH - 31ST AUG.
PROCUREMENT OF MAMA KITS AND OTHER ADVOCACY MATERIALS. | PLAN | FMWASD/2015/GOODS/CAP/6 | A9 | GOODS | NCB | MTB | LEB | NA | NA | 23RD FEB.- 16TH MARCH. | 16TH - 30TH MARCH | NA | NA | NA | 30TH MARCH - 11TH MAY | 11TH MAY | 11TH MAY - 1ST JUNE | 1ST -29TH JUNE | NA | 29TH JUNE- 13TH JULY | 13TH - 27TH JULY | NA | 27TH JULY -17TH AUG. | 17TH - 31ST AUG.
PROCUREMENT OF STATIONARIES | PLAN | FMWASD/2015/GOODS/CAP/7 | A10 | GOODS | NCB | PS | LEB | NA | NA | 23RD FEB.- 16TH MARCH. | 16TH - 30TH MARCH | NA | NA | NA | 30TH MARCH - 11TH MAY | 11TH MAY | 11TH MAY - 1ST JUNE | 1ST -29TH JUNE | NA | 29TH JUNE- 13TH JULY | 13TH - 27TH JULY | NA | 27TH JULY -17TH AUG. | 17TH - 31ST AUG.
PROCUREMENT OF WORKSHOP BAGS AND OTHER GIFTS MATERIALS. | PLAN | FMWASD/2015/GOODS/CAP/8 | A11 | GOODS | NCB | MTB | LEB | NA | NA | 23RD FEB.- 16TH MARCH. | 16TH - 30TH MARCH | NA | NA | NA | 30TH MARCH - 11TH MAY | 11TH MAY | 11TH MAY - 1ST JUNE | 1ST -29TH JUNE | NA | 29TH JUNE- 13TH JULY | 13TH - 27TH JULY | NA | 27TH JULY -17TH AUG. | 17TH - 31ST AUG.

## Non consultancy women affairs
Ministry/Department/Agency: FEDERAL MINISTRY OF WOMEN AFFAIRS AND SOCIAL DEVELOPMENT. |  |  |  |  | CATEGORY C
Budget Year: 2015
|  | Basic Data | [7 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  | Contract Implementation - Consultancy
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 1 weeks | 2 - 4 weeks | 2 weeks | 2 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
COLLABORATION WITH UN DEVELOPMENT AGENCIES: COUNTERPART FUNDS TO UN AGENCIES FOR CAPACITY BUILDING. | PLAN | FMWASD/2015/NC/CAP/1 | C1 | NON- CONSULTANCY | NA | MTB | NA | NA | NA | 23RD FEB.- 16TH MARCH. | 16TH - 30TH MARCH | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
CAPACITY BUILDING WORKSHOP FOR RELEVANT WOMEN (CSOs & NGOs) AND STAKEHOLDERS | PLAN | FMWASD/2015/NC/CAP/2 | C2 | NON- CONSULTANCY | NA | MTB | LEB | NA | NA | 23RD FEB.- 16TH MARCH. | 16TH - 30TH MARCH | 30TH MARCH - 13TH APRIL | 13TH -20TH APRIL | 20TH APRIL - 18TH MAY | 18TH MAY- 1ST JUNE | 1ST - 15TH JUNE | 15TH JUNE | 15TH - 29TH JUNE | 29TH JUNE - 13TH JULY | 13TH - 27TH JULY | 27TH JULY- 10TH AUG. | 10TH - 24TH AUG. | 24TH AUG. - 21ST SEPT. | NA | 21ST SEPT. - 5TH OCT. | 5TH - 19TH OCT. | NA | 16TH NOV. | 23RD NOV.
KNOWLEDGE UPDATE AND TRAINING SESSIONS FOR NGOs. | PLAN | FMWASD/2015/NC/CAP/3 | C3 | NON- CONSULTANCY | NA | MTB | LEB | NA | NA | 23RD FEB.- 16TH MARCH. | 16TH - 30TH MARCH | 30TH MARCH - 13TH APRIL | 13TH -20TH APRIL | 20TH APRIL - 18TH MAY | 18TH MAY- 1ST JUNE | 1ST - 15TH JUNE | 15TH JUNE | 15TH - 29TH JUNE | 29TH JUNE - 13TH JULY | 13TH - 27TH JULY | 27TH JULY- 10TH AUG. | 10TH - 24TH AUG. | 24TH AUG. - 21ST SEPT. | NA | 21ST SEPT. - 5TH OCT. | 5TH - 19TH OCT. | NA | 16TH NOV. | 23RD NOV.
SENSITIZATION AND AWARENESS CREATION FOR WOMEN ON CLIMATE AND ENVIRONMENTAL CHANGES IN SIX GEO POLITICAL ZONES. | PLAN | FMWASD/2015/NC/CAP/4 | C4 | NON- CONSULTANCY | NA | MTB | LEB | NA | NA | 23RD FEB.- 16TH MARCH. | 16TH - 30TH MARCH | 30TH MARCH - 13TH APRIL | 13TH -20TH APRIL | 20TH APRIL - 18TH MAY | 18TH MAY- 1ST JUNE | 1ST - 15TH JUNE | 15TH JUNE | 15TH - 29TH JUNE | 29TH JUNE - 13TH JULY | 13TH - 27TH JULY | 27TH JULY- 10TH AUG. | 10TH - 24TH AUG. | 24TH AUG. - 21ST SEPT. | NA | 21ST SEPT. - 5TH OCT. | 5TH - 19TH OCT. | NA | 16TH NOV. | 23RD NOV.
CAPACITY BUILDING FOR COORDINATORS OF WOMEN POLITICAL EMPOWERMENT OFFICES IN SIX GEO POLITICAL ZONES. | PLAN | FMWASD/2015/NC/CAP/5 | C5 | NON- CONSULTANCY | NA | MTB | LEB | NA | NA | 23RD FEB.- 16TH MARCH. | 16TH - 30TH MARCH | 30TH MARCH - 13TH APRIL | 13TH -20TH APRIL | 20TH APRIL - 18TH MAY | 18TH MAY- 1ST JUNE | 1ST - 15TH JUNE | 15TH JUNE | 15TH - 29TH JUNE | 29TH JUNE - 13TH JULY | 13TH - 27TH JULY | 27TH JULY- 10TH AUG. | 10TH - 24TH AUG. | 24TH AUG. - 21ST SEPT. | NA | 21ST SEPT. - 5TH OCT. | 5TH - 19TH OCT. | NA | 16TH NOV. | 23RD NOV.
STAKEHOLDERS FORUM AND UPDATE KNOWLEDGE ON RESOLUTION 1325 ON PEACE. | PLAN | FMWASD/2015/NC/CAP/6 | C6 | NON- CONSULTANCY | NA | MTB | LEB | NA | NA | 23RD FEB.- 16TH MARCH. | 16TH - 30TH MARCH | 30TH MARCH - 13TH APRIL | 13TH -20TH APRIL | 20TH APRIL - 18TH MAY | 18TH MAY- 1ST JUNE | 1ST - 15TH JUNE | 15TH JUNE | 15TH - 29TH JUNE | 29TH JUNE - 13TH JULY | 13TH - 27TH JULY | 27TH JULY- 10TH AUG. | 10TH - 24TH AUG. | 24TH AUG. - 21ST SEPT. | NA | 21ST SEPT. - 5TH OCT. | 5TH - 19TH OCT. | NA | 16TH NOV. | 23RD NOV.
ADVOCACY VISITS BY PRINCIPAL OFFICERS OF NATIONAL CHILDREN'S PARLIAMENT WITH THE HONOURABLE MINISTER, PERMANENT SECRETARY AND STAFF OF THE MINISTRY ON CHILD RIGHTS ACTS (CRA), GIRL-CHILD EDUCATION AND OTHER ISSUES THAT INVOLVE THE NIGERIAN CHILDREN (MDG). | ON-GOING | FMWASD/2015/NC/ONGOING/1 | ON-GOING | NON- CONSULTANCY
WOMEN'S SMALL TO MEDIUM SCALE ENTERPRENEURS SUPPORT PROGRAMME - BUSINESS AND DEVELOPMENT FUND FOR WOMEN (BUDFOW) AGRIC BUSINESS AND INVESTMENT FOR WOMEN | ON-GOING | FMWASD/2015/NC/ONGOING/2 | ON-GOING | NON- CONSULTANCY
CAPACITY BUILDING WORKSHOP FOR FEDERAL CHILD DEV. DEPT. OFFICERS SELECTED NON-GOVT ORG. (NGOs) AND STATE CHILD DEV. DEPT. OFFICERS. (MDG) | ON-GOING | FMWASD/2015/NC/ONGOING/3 | ON-GOING | NON- CONSULTANCY
TECHNICAL MEETING OF EXPERT FROM THE SIX GEOPOLITICAL ZONES OF THE COUNTRY ON THE GIRL CHILD EDUCATION INTERVENTION (MDG) | ON-GOING | FMWASD/2015/NC/ONGOING/4 | ON-GOING | NON- CONSULTANCY
UPDATING OF THE NATIONAL POLICY ON REHABILITATION OF PERSONS WITH DISABILITIES-MDGs | ON-GOING | FMWASD/2015/NC/ONGOING/5 | ON-GOING | NON- CONSULTANCY
IMPLEMENTATION OF THE NATIONAL PRIORITY AGENDA (NPA) ON ORPHANS AND VULNERABLE CHILDREN (OVC) (MDG) | ON-GOING | FMWASD/2015/NC/ONGOING/6 | ON-GOING | NON- CONSULTANCY
REVIEW OF OVC SITUATION IN NIGERIA (MDG) | ON-GOING | FMWASD/2015/NC/ONGOING/7 | ON-GOING | NON- CONSULTANCY
RESPONSE PLAN ON VIOLENCE AGAINST CHILDREN (RPVAC) IN NIGERIA (MDG) | ON-GOING | FMWASD/2015/NC/ONGOING/8 | ON-GOING | NON- CONSULTANCY
COMMEMORATION OF INTERNATIONAL AND NATIONAL EVENTS - NATIONAL CHILDREN'S DAY. | ON-GOING | FMWASD/2015/NC/ONGOING/9 | ON-GOING | NON- CONSULTANCY
COMMEMORATION OF INTERNATIONAL AND NATIONAL EVENTS - DAY OF AFRICAN CHILD | ON-GOING | FMWASD/2015/NC/ONGOING/10 | ON-GOING | NON- CONSULTANCY
COMMEMORATION OF INTERNATIONAL AND NATIONAL EVENTS - UNIVERSAL DAY OF CHILD | ON-GOING | FMWASD/2015/NC/ONGOING/11 | ON-GOING | NON- CONSULTANCY
COMMEMORATION OF INTERNATIONAL AND NATIONAL EVENTS - WORLD'S AID DAY | ON-GOING | FMWASD/2015/NC/ONGOING/12 | ON-GOING | NON- CONSULTANCY
COMMEMORATION OF INTERNATIONAL DAY OF PEACE | ON-GOING | FMWASD/2015/NC/ONGOING/13 | ON-GOING | NON- CONSULTANCY

## Works women affairs
Ministry/Department/Agency: FEDERAL MINISTRY OF WOMEN AFFAIRS AND SOCIAL DEVELOPMENT
Budgetary Year: 2015 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Pre-or Post Qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
RENOVATION WORK AT BRAILLE PRESS LIBRARY, LAGOS AND BRAILLE PRESS, KADUNA. | FMWASD/2015/WORKS/CAP/1 | B1 | BOQ | NCB | NA | PS | Plan | 23RD FEB.- 16TH MARCH. | 16TH - 30TH MARCH | NA | NA | NA | NA | NA | Plan | NA | 29TH JUNE- 13TH JULY | 13TH - 27TH JULY | NA | 4MONTHS | 6TH MONTH
[7 empty] | Actual | [7 empty] | Actual
PRINTING OF SECURITY AND NON SECURITY DOCUMENTS. | FMWASD/2015/WORKS/CAP/2 | B2 | BOQ | NCB | NA | PS | Plan | 23RD FEB.- 16TH MARCH. | 16TH - 30TH MARCH | NA | NA | NA | NA | NA | Plan | NA | 29TH JUNE- 13TH JULY | 13TH - 27TH JULY | NA | 4MONTHS | 6TH MONTH
[7 empty] | Actual | [7 empty] | Actual
UPGRADE AND STANDARDIZATION OF RECORD KEEPING. | FMWASD/2015/WORKS/CAP/3 | B3 | BOQ | NCB | NA | PS | Plan | 23RD FEB.- 16TH MARCH. | 16TH - 30TH MARCH | NA | NA | NA | NA | NA | Plan | NA | 29TH JUNE- 13TH JULY | 13TH - 27TH JULY | NA | 4MONTHS | 6TH MONTH
[7 empty] | Actual | [7 empty] | Actual
PRINTING OF PROGRAMMES AND BANNERS. | FMWASD/2015/WORKS/CAP/4 | B4 | BOQ | NCB | NA | PS | Plan | 23RD FEB.- 16TH MARCH. | 16TH - 30TH MARCH | NA | NA | NA | NA | NA | Plan | NA | 29TH JUNE- 13TH JULY | 13TH - 27TH JULY | NA | 2 WEEKS | 3RD WEEK
[7 empty] | Actual | [7 empty] | Actual
SKILLS ACQUISITION CENTRE AT ONITSHA-UKU NORTH, DELTA STATE. | FMWASD/2015/ONGOING/1 | ON-GOING | BOQ | NCB |  |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
CONSTRUCTION AND EQUIPING OF SKILLS ACQUISITION CENTRE AT ORA OWODE, OGBOMOSO NORTH, OYO STATE. | FMWASD/2015/ONGOING/2 | ON - GOING | BOQ | NCB |  |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
SKILLS ACQUISITION CENTRE AT LERE, KADUNA STATE. | FMWASD/2015/ONGOING/3 | ON - GOING | BOQ | NCB |  |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
SKILLS ACQUISITION CENTRE AT OHAOZARA, EBONYI STATE. | FMWASD/2015/ONGOING/4 | ON - GOING | BOQ | NCB |  |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
COMPLETION OF FEDERAL MINISTRY OF WOMEN AFFAIRS HEADQUARTERS BUILDING, ABUJA. | FMWASD/2015/ONGOING/5 | ON - GOING | BOQ | NCB |  |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
COMPLETION OF THE RENOVATION, FURNISHING AND EQUIPING AT THE FEDERAL SCHOOL OF SOCIAL WORK, EMENE, ENUGU STATE. | FMWASD/2015/ONGOING/6 | ON - GOING | BOQ | NCB |  |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual

## Ministry of Youth
Ministry/Department/Agency: |  | FEDERAL MINISTRY OF YOUTH DEVELOPMENT |  |  | ENTERPRISE DEVELOPMENT AND PROMOTION DEPARTMENT
Budget Year: 2015
Desk Officer/Contact #: |  | Basic Data | [7 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  | Contract Implementation - Consultancy
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/ Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/ Financial | Negotiations | MDA Approval/ No Objection Date | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks
| Plan vs Actual | [8 empty] | 23/2 - 9/3/15 | 9/3 - 23/3/15 | 23/3 - 6/4/15 | 6/4 - 13/4/15 | 13/4 - 11/5/15 | 11/5 - 25/5/15 | 25/5 - 8/6/15 | 2015-08-06 | 8/6 - 22/6/15 | 22/6 - 6/7/15 | 6/7 - 20/7/15 | 20/7 - 10/8/15 | 10/8 - 24/8/15 | 24/8 - 7/9/15 | N/A | 7/9 - 21/9/15 | 21/9 - 5/10/15 | 5/10 - 19/10/15 | 19/10 - 2/11/15 | 2/11 - 16/11/15
National Youth Empowerment Programme in Agricultural Production and Value Chains for 250 Youths in Northern Zone (North-East North West and North Central) | Plan |  | Lot 1 | Non-Consultancy | NCB | MTB | NCB | Pre-qualification | PPC/MTB | 23/2 - 9/3/15 | 10/3 - 24/3/15 | 25/3 - 8/4/15 | 9/4 - 16/4/15 | 17/4 - 15/5/15 | 18/5 - 1/6/15 | 2/6 - 16/6/15 | 16/6/2015 | 17/6 - 1/7/15 | 1/7 - 15/7/15 | 16/7 - 30/7/15 | 31/7 - 21/8/15 | 24/8 - 7/9/15 | 8/9 - 22/9/15 | N/A | 8/9 - 22/9/15 | 23/9 - 7/10/15 | 8/10 - 22/10/15 | 23/10 - 6/11/15 | 9/11 - 23/11/15
National Youth Empowerment Programme in Vocational & Livelihoods Skills for 250 Unemployed Youths in Southern Zones (South East, South West and South-South) | Plan |  | Lot 2 | Non-Consultancy | NCB | MTB | NCB | Pre-qualification | PPC/MTB | 23/2 - 9/3/15 | 10/3 - 24/3/15 | 25/3 - 8/4/15 | 9/4 - 16/4/15 | 17/4 - 15/5/15 | 18/5 - 1/6/15 | 2/6 - 16/6/15 | 16/6/2015 | 17/6 - 1/7/15 | 1/7 - 15/7/15 | 16/7 - 30/7/15 | 31/7 - 21/8/15 | 24/8 - 7/9/15 | 8/9 - 22/9/15 | N/A | 8/9 - 22/9/15 | 23/9 - 7/10/15 | 8/10 - 22/10/15 | 23/10 - 6/11/15 | 9/11 - 23/11/15
Empowerment of 700 Youths trained in Agro-Allied Businesses (MDG) | Plan |  | Lot 3 | Non-Consultancy | NCB | MTB | NCB | Pre-qualification | PPC/MTB | 23/2 - 9/3/15 | 10/3 - 24/3/15 | 25/3 - 8/4/15 | 9/4 - 16/4/15 | 17/4 - 15/5/15 | 18/5 - 1/6/15 | 2/6 - 16/6/15 | 16/6/2015 | 17/6 - 1/7/15 | 1/7 - 15/7/15 | 16/7 - 30/7/15 | 31/7 - 21/8/15 | 24/8 - 7/9/15 | 8/9 - 22/9/15 | N/A | 8/9 - 22/9/15 | 23/9 - 7/10/15 | 8/10 - 22/10/15 | 23/10 - 6/11/15 | 9/11 - 23/11/15

## FRSC
Ministry/Department/Agency: Federal Road Safety Corps
Budget Year: 2015
|  | Basic Data | [7 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation - Works
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Plan vs Actual
COMPLETION OF RS8.0 HQ ILORIN | Plan | WKS/2014/21 | 21 |  | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW
Actual
CONSTRUCTION (On-going Projects) Medical Centre | Plan | PROC/UDI/2015/1 | 1 | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW
Actual
CONSTRUCTION (On-going Projects) Junior Staff Quarters | Plan | PROC/UDI/2015/1 | 2 | Bills of Quantity | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW
Actual
CONSTRUCTION (On-going Projects) Septic Tank and Soak Away Pit | Plan | PROC/UDI/2015/1 | 3 | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW
Actual
REHABILITATION (On-going Projects) Repairs of Residential Buildings ( Renovation of Marshal Quarters Karu) | Plan | PROC/REH/2015/1 | 1 | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW
Actual
REHABILITATION (On-going Projects) Repairs of Office Buildings ( Renovation of FRSC Headquarters , Wuse Zone 3, Abuja) | Plan | PROC/REH/2015/2 | 1 | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW
Actual
REHABILITATION (On-going Projects) Repairs of Office Buildings ( Rehabilitation of Ilorin XZonal Command) | Plan | PROC/REH/2015/2 | 2 |  | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW
Actual
REHABILITATION (On-going Projects) Repairs of Office Buildings ( Pre-fabricated Cabin Structures for Rescue Post 2 @ 2,639,500.00)) | Plan | PROC/REH/2015/2 | 4 | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW
Actual

## FRSC Consultancy
Ministry/Department/Agency: Federal Road Safety Corps
Budget Year: 2015
|  | Basic Data | [7 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2.2 - 2 weeks | 3 weeks | 2 - 4 weeks | 2 weeks | 4 - 6 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
RESEARCH AND DEVELOPMENT (on-going) | Plan | PROC/RD/2015/1 | 1 | Lump Sum | NCB | Accounting Officer: Director General/CEO | QCBS - Quality and Cost Based Selection | NA | POST REVIEW
Actual

## FIRS Goods
Ministry/Department/Agency: Procurement Department
Budget Year: 2015
|  | Basic Data | [7 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation - Goods
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Arrival of Goods | Inspection/Final Acceptance
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
Plan vs Actual
purchase of air conditions | Plan | parkage/goods/firs/2015/01 | 123 | Bills of Quantity | NCB | BPP issues "No Objection" to award/FEC approves | LERB - LOWEST EVALUATED RESPONSIVE BID | PRE-QUALIFICATION | PRIOR REVIEW | 20/02/15 - 6/03/15 | 9/03/15 - 23/03/15 | [7 empty] | NA | 5/09/14 - 15/09/14 | 15/09/14 - 19/09/14
Actual

## FIRS Works
Ministry/Department/Agency: Procurement Department
Budget Year: 2015
|  | Basic Data | [7 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Works
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Plan vs Actual
CONSTRUCTION OF BRANCH OFFICE BENIN | Plan | FIRS/WORKS/2015/1 | 3 |  | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PRE-QUALIFICATION | POST REVIEW | 2/01/15 - 15/01/15 | 16/01/15 - 23/01/15
Actual

## Galaxy backbone
Ministry/Department/Agency: Galaxy Backbone PLC
Budget Year: 2015
|  | Basic Data | [7 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  | Contract Implementation - Consultancy
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2.2 - 2 weeks | 3 weeks | 2 - 4 weeks | 2 weeks | 4 - 6 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
TECHNICAL PROFESSIONAL SERVICES | Plan |  |  | Lump Sum | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | [14 empty] | NA | 6/06/14 - 13/06/14 | 13/06/14 - 20/06/14
Actual
QUALITY ASSURANCE AUDIT | Plan |  |  |  | NCB | Accounting Officer: Director General/CEO | LC - Least Cost | NA | POST REVIEW | [14 empty] | NA | 21/07/14 - 28/07/14 | 28/07/14 - 4/08/14
Actual
TECHNICAL TRAINING AND CAPACITIY BUILDING | Plan |  |  | Lump Sum | NCB | Parastatals Tenders Board | LC - Least Cost | POST-QUALIFICATION | POST REVIEW | [14 empty] | NA | 21/07/14 - 28/07/14 | 28/07/14 - 4/08/14
Actual
MANAGED SECURITY SERVICES | Plan |  |  | Lump Sum | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | [14 empty] | NA | 21/07/14 - 28/07/14 | 28/07/14 - 4/08/14
Actual
TRAINING ON VIRTUALISATION POWER AND ENVIRONMENT BACKUPS STORAGE | Plan |  |  |  | NCB | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | POST-QUALIFICATION | POST REVIEW | [14 empty] | NA | 21/05/14 - 4/06/14 | 5/06/14 - 12/06/14
Actual
PROGRAM MANAGEMENT SERVICES | Plan |  |  | Lump Sum | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | [14 empty] | NA | 21/05/14 - 4/06/14 | 5/06/14 - 12/06/14
Actual

## Galaxy backbone Goods
Ministry/Department/Agency: Galaxy Backbone PLC
Budget Year: 2015
|  | Basic Data | [7 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation - Goods
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Arrival of Goods | Inspection/Final Acceptance
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
Plan vs Actual
PROCUREMENT OF MOTOR VEHICLES | Plan |  |  | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW
Actual
PROCUREMENT OF STATIONERIES | Plan |  |  | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW
Actual
PROCUREMENT OF DEISEL | Plan |  |  | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | [9 empty] | NA | 23/12/14 - 6/01/15 | 6/01/15 - 20/01/15
Actual
PROCUREMENT OF VSAT SPARES FOR SUPPORT | Plan |  |  |  | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | [9 empty] | NA | 23/12/14 - 6/01/15 | 6/01/15 - 20/01/15
Actual
PROCUREMENT OF ACTIVE DEVICES | Plan |  |  |  | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | [9 empty] | NA | 23/12/14 - 30/12/14 | 30/12/14 - 13/01/15
Actual
PROCUREMENT OF FURNITURES AND FITTINGS | Plan |  |  |  | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | [9 empty] | NA | 23/12/14 - 30/12/14 | 30/12/14 - 13/01/15
Actual
PROCUREMENT OF OFFICE EQUIPMENT | Plan |  |  | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 16/05/14 - 30/05/14 | 30/05/14 - 13/06/14 | NA | NA | NA | 28/07/14 | 8/09/14 | 12/09/14 - 26/09/14 | 26/09/14 - 24/10/14 | NA | 24/10/14 - 31/10/14 | 31/10/14 - 14/11/14
Actual
PROCUREMENT OF VARIOUS IT EQUIPMENT | Plan |  |  | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 16/05/14 - 30/05/14 | 30/05/14 - 13/06/14 | NA | NA | NA | 28/07/14 | 8/09/14 | 12/09/14 - 26/09/14 | 26/09/14 - 24/10/14 | NA | 24/10/14 - 31/10/14 | 31/10/14 - 14/11/14
Actual
PRINTING OF DOCUMENTS | Plan |  |  | Bills of Quantity | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 16/05/14 - 30/05/14 | 30/05/14 - 13/06/14 | NA | NA | NA | 28/07/14 | 8/09/14 | 12/09/14 - 26/09/14 | 26/09/14 - 24/10/14 | NA | 24/10/14 - 31/10/14 | 31/10/14 - 14/11/14
Actual
PROCUREMENT OF NEWSPAPERS AND MAGAZINES | Plan |  |  |  | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 16/05/14 - 30/05/14 | 30/05/14 - 13/06/14 | NA | NA | NA | 28/07/14 | 8/09/14 | 12/09/14 - 26/09/14 | 26/09/14 - 24/10/14 | NA | 24/10/14 - 31/10/14 | 31/10/14 - 14/11/14
Actual
PROCUREMENT OF IP TELEPHONES | Plan |  |  | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 16/05/14 - 30/05/14 | 30/05/14 - 13/06/14 | NA | NA | NA | 28/07/14 | 8/09/14 | 12/09/14 - 26/09/14 | 26/09/14 - 24/10/14 | NA | 24/10/14 - 31/10/14 | 31/10/14 - 14/11/14
Actual
FLEET MANAGEMENT SYSTEM | Plan |  |  | Bills of Quantity | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 10/04/14 - 24/04/14 | 25/04/14 - 30/04/14 | 30/04/14 - 28/05/14 | 30/05/14 - 13/06/14 | 16/06/14 - 18/06/14 | 18/06/14 | 2/07/14 | 4/07/14 - 18/07/14 | 21/07/14 - 25/07/14 | 25/07/14 - 8/08/14 | 11/08/14 - 11/08/14 | 15/08/14 - 15/08/14
| Actual | [8 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
MOBILE GENERATORS | Plan |  |  | Bills of Quantity | NCB | Accounting Officer: Permanent Secretary | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 | 14/03/14 - 21/03/14 | 9/04/14 | 21/05/14 | 21/05/14 - 5/06/14 | 6/06/14 - 20/06/14 | NA | 23/06/14 - 30/06/14 | 1/07/14 - 8/07/14
Actual
PROJECT VEHICLES | Plan |  |  | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 | 14/03/14 - 21/03/14 | 9/04/14 | 21/05/14 | 21/05/14 - 5/06/14 | 6/06/14 - 20/06/14 | NA | 23/06/14 - 30/06/14 | 1/07/14 - 8/07/14
Actual
PROCUREMENT OF SYSLOG SERVER | Plan |  |  | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 8/04/14 - 15/04/14 | 15/04/14 - 21/04/14 | NA | NA | NA | 19/05/14 | 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | NA | 21/07/14 - 28/07/14 | 28/07/14 - 4/08/14
Actual

## Galaxy backbone Works
Ministry/Department/Agency: Galaxy Backbone PLC
Budget Year: 2015
|  | Basic Data | [7 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation - Works
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Plan vs Actual
DATA CENTER ENTERPRISE APPLICATION LICENSES & SUPPORT | Plan |  |  | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 7/04/14 - 21/04/14 | 22/04/14 - 29/04/14 | 30/04/14 - 28/05/14 | 30/05/14 - 13/06/14 | 16/06/14 - 23/06/14 | 23/06/14 - 7/07/14 | 14/07/14 - 28/07/14 | 30/07/14 | 10/09/14 | 10/09/14 - 17/09/14 | 22/09/14 - 6/10/14 | 8/10/14 - 22/10/14 | 24/10/14 - 31/10/14 | 5/10/15 - 19/10/15 | 19/10/15 - 26/10/15 | 25/12/15 | 31/12/15
| Actual | [8 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
TRANSMISSION INFRASTRUCTURE MTCE AND SUPPORT | Plan |  |  | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 18/03/14 - 31/03/14 | 31/03/14 - 7/04/14 | NA | NA | NA |  |  | 7/04/14 | 19/05/14 | 19/05/14 - 27/05/14 | 27/05/14 - 6/06/14 | NA | 6/06/14 - 13/06/14 | 13/06/14 - 20/06/14
Actual
EDMS INFRASTRUCTURE SUPPORT | Plan |  |  | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 3/03/14 - 14/03/14 | 14/03/14 - 24/03/14 | NA | NA | NA |  |  | 28/03/14 | 30/04/14 | 30/04/14 - 9/05/14 | 9/05/14 - 16/05/14 | NA | 16/05/14 - 23/05/14 | 23/05/14 - 30/05/14
Actual
NETWORK SECURITY SOLUTIONS AND UPGRADES | Plan |  |  | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 18/03/14 - 28/03/14 | 28/03/14 - 11/04/14 | NA | NA | NA |  |  | 11/04/14 | 23/05/14 | 23/05/14 - 6/06/14 | 6/06/14 - 13/06/14 | NA | 13/06/14 - 20/06/14 | 20/06/14 - 4/07/14
Actual
POWER SUPPLY AND INSTALLATION | Plan |  |  | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 | 14/03/14 - 21/03/14 | 24/03/14 - 31/03/14 | 1/04/14 - 8/04/14 | 9/04/14 | 21/05/14 | 21/05/14 - 5/06/14 | 6/06/14 - 20/06/14 | NA | 23/06/14 - 30/06/14 | 1/07/14 - 8/07/14 | 9/07/14 - 16/07/14 | 7/07/15 | 8/07/15
Actual
MIGRATION OF SITES FROM VSAT TO LTE/MICROWAVE/FIBER | Plan |  |  | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | NA | 27/02/14 - 13/03/14 | 14/03/14 - 21/03/14 | 24/03/14 - 31/03/14 | 1/04/14 - 8/04/14 | 9/04/14 | 21/05/14 | 21/05/14 - 5/06/14 | 6/06/14 - 20/06/14 | NA | 23/06/14 - 30/06/14 | 1/07/14 - 8/07/14 | NA | 7/07/15 | 8/07/15
Actual
FIBRE OPTIC BACKBONE & ABUJA METRO DEPLOYMENT | Plan |  |  | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 3/12/12 - 10/12/12 | 11/12/12 - 18/12/12 | NA | 2/12/14 | 3/12/14
Actual
METRO FIBRE SUPPORT AND MAINTENANCE | Plan |  |  | Bills of Quantity | NCB | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW
Actual
VSAT SUPPORT AND MAINTENANCE | Plan |  |  | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 8/04/14 - 15/04/14 | 15/04/14 - 21/04/14 | NA | NA | NA | NA | NA | 19/05/14 | 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | NA | 21/07/14 - 28/07/14 | 28/07/14 - 4/08/14 | NA | 29/09/14 | 27/10/14
Actual
NETWORK SECURITY UPGRADE | Plan |  |  | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 3/12/12 - 10/12/12 | 11/12/12 - 18/12/12 | NA | 2/12/14 | 3/12/14
Actual
WEB APPLICATION FIREWALL | Plan |  |  | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | NA | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 |  |  | 14/03/14 | 25/04/14 | 28/04/14 - 12/05/14 | 13/05/14 - 20/05/14 | NA | 21/05/14 - 4/06/14 | 5/06/14 - 12/06/14
Actual
PROCUREMENT OF A MULTI-TENANT GLOBAL SITE LOAD BALANCER - NETSCALER | Plan |  |  | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | NA | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 |  |  | 14/03/14 | 25/04/14 | 28/04/14 - 12/05/14 | 13/05/14 - 20/05/14 | NA | 21/05/14 - 4/06/14 | 5/06/14 - 12/06/14
Actual
SITE ACQUISITION OPERATIONS AND MAINTENANCE | Plan |  |  | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | NA | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 |  |  | 14/03/14 | 25/04/14 | 28/04/14 - 12/05/14 | 13/05/14 - 20/05/14 | NA | 21/05/14 - 4/06/14 | 5/06/14 - 12/06/14
Actual

## GWMA
Ministry/Department/Agency: | Gurara Water Management Authority | [7 empty] | Gurara Water Management Authority
Budgetary Year: 2015 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Pre-or Post Qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification / Financial Bids | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[7 empty] | Actual | [7 empty] | Actual
Maintenance and Operation of Gurara Dam and Associated Works |  |  | Lumpsum | NCB | N/A | MTB | Plan | 9th June, 2015 | 25th Jnue, 2015 | 30th June, 2015 | 30th June, 2015 | 15th July, 2015 | 30th July, 2015 | 5th August, 2015 | Plan | MTB | 12th August, 2015 | 19th August, 2015 | N/A
[7 empty] | Actual | [7 empty] | Actual
Maintenance of 75 km long water transfer pipeline to FCT |  |  | Bill of Quantities | NCB | N/A | MTB | Plan | N/A | N/A | 15th Dec. 2014 | 15th Dec. 2014 | 26th May, 2015 | 15th May, 2015 | 3rd June, 2015 | Plan | N/A | 7th July, 2015 | 14th July, 2015 | N/A

## GWMA Consultants
Ministry/Department/Agency: |  | Gurara Water Management Authority
Budgetary Year: 2015 |  | If Post-Review, No-objection Dates are not needed |  |  |  |  | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | Plan vs. Actual | No-objection Date | FEC Approval | Contract Offer | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report
Norm Duration of Proc Steps |  |  |  | Plan | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | Plan | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks | 1- 2 wk | 2 wks | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
List of Contracts
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Gurara Phase 2 Project Procurement | Consultant Qualification | Lumpsum | Agency | Plan | N/A | 15th April, 2015 | N/A |  | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | N/A | N/A | Plan | N/A
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Procurement and Maintenance of Infrastructural Facilities for Office | Consultant Qualification | Lumpsum | Agency | Plan | N/A | 15th April, 2015 | N/A |  | N/A | N/A | Plan | 15th April, 2015 | 29th April, 2015 | 15th June,2015 | 29th June, 2015 | N/A | N/A | N/A | Plan |  | N/A | 3rd July, 2015 | 3rd July, 2015 | Plan | N/A
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Dam Break Study (Community Sensitization) | Consultant Qualification | Lumpsum | Agency | Plan | N/A | 15th April, 2015 | N/A |  | N/A | N/A | Plan | N/A | N/A | N/A | N/A |  | N/A |  | Plan | N/A | N/A | 10th july, 2015 | 10th july, 2015 | Plan | N/A
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Updating of Hydromet Network for Gurara Basin | Consultant Qualification | Lumpsum | Agency | Plan | N/A | 15th April, 2015 | N/A |  | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | 10th July, 2015 | 10th July, 2015 | Plan | N/A
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Capacity Building for Operation and Maintenance of Gurara 1 Project | Consultant Qualification | Lumpsum | Agency | Plan | N/A | 15th April, 2015 | N/A |  | N/A | N/A | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | N/A | N/A | 10th july, 2015 | 10th july, 2015 | Plan | N/A
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  |  |  | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Updating of Hardware and Software for the Development of Data Base | Consultant Qualification | Lumpsum | Agency | Plan | N/A | 15th April, 2015 | N/A |  | N/A | N/A | Plan | [7 empty] | Plan | N/A | N/A | 10th july, 2015 | 10th july, 2015 | Plan | N/A
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual

## Hadejia Works
PROCUREMENT PLANNING (WORKS)
Ministry/Department/Agency: | HADEJIA - JAMA'ARE RIVER BASIN DEVELOPMENT AUTHORITY, KANO.
Budgetary Year: 2015 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Pre-or Post Qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Construction of Challawa/Karaye Irrigation Scheme | HJ/W/IRRI/CHG/2012/01-05 | Lot 1 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA
Galala Dam Irrigation Project | HJ/W/IRRI/GALALA/2013/01-05 | Lot 1 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA
Establishment of Small Scale Irrigation Scheme in Kano State. | HJ/W/IRRI/KNS/2013/01-05 | Lot 1 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA
Establishment of Small Scale Irrigation Scheme in Jigawa State. | HJ/W/IRRI/JGS/2013/01-05 | Lot 1 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA
Establishment of Small Scale Irrigation Scheme in Bauchi State. | HJ/W/IRRI/BAS/2013/01-05 | Lot 1 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA
Rehablitaion of Kano River Irrigation Project Infrastructures | HJ/W/RLSI-KRIP/2015/01-05 | Lot 1 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA
Rehablitaion of Hadejia Valley Irrigation Project Infrastructures | HJ/W/RLSI-HVIP/2015/01-05 | Lot 1 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA
Rehabilitation of Tiga Dam and Ruwan Kanya Reservior | HJ/W/RLD-RKTD/2015/01-05 | Lot 1 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA
Rehabilitation of Challawa Gorge Dam | HJ/W/RLD-CHG/2015/01-05 | Lot 1 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA
Rehabilitation of Hadejia Barrage | HJ/W/RLD-HVIP/2015/01-05 | Lot 1 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA
Rehabilitation of Wudil Pilot Irrigation Scheme | HJW//RLD-WPIS/2015/01-05 | Lot 1 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA
Rehabilitation and Expansion of Sawe Pilot Irrigation Scheme | HJW//RLD-SPIS/2013/01-05 | Lot 1 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA
Rehabilitation of Yamidi Pilot Farm | HJW//RLD-YPF/2015/01-05 | Lot 1 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA
Construction of Water Supply Scheme in Kano State | HJ/W/WS-KNS/2015/01-05 | Lot 1 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA
Construction of Water Supply Scheme in Jigawa State | HJ/W/WS-JGWS/2015/01-05 | Lot 1 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA
Construction of Water Supply Scheme in Bauchi State | HJ/WS-BAS/2015/01-05 | Lot 1 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA
Katagum Irrigation Project | HJ/W/KIP-IRRI/2015/01-05 | Lot 1 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA
Flood/Erosion Control Project in Kano State | HJ/W/EROSION - KNS /2013/01-05 | Lot 1 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA
Flood/Erosion Control Project in Jigawa State | HJ/W/EROSION - JGWS /2013/01-05 | Lot 1 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA
Flood/Erosion Control Project in Bauchi State | HJ/W/EROSION - BAS /2013/01-05 | Lot 1 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA
Establishment of data bank and ICT centre at H-JRBDA Headquarters | HJ/W/DATABASE /2015/01-05 | Lot 1 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA
Rehabilitation of Kano River Irrigation Project Office | HJ/W/REHAB-KRIP/2015/01-05 | Lot 1 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA
Rehabilitation of Hadejia Valley Irrigation Project Office | HJ/W/REHAB-HVIP/2015/01-05 | Lot 2 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA
Rehabilitation of Jama'are Irrigation Project Office | HJ/W/REHAB-JVP/2015/01-05 | Lot 1 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA
Rehabilitation of Kadawa Farm Centre, Garun Mallam LGA, Kano State | HJ/W/RLD-KFC/2015/01-05 | Lot 1 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA
Rehabilitation of Challawa Gorge Dam Intake & outlet Control structure | HJ/W/RLD-CHGD/2015/01-05 | Lot 1 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA
Rehabilitation of Ruwan Kanya Reservior | HJ/W/RLD-RKY/2015/01-05 | Lot 1 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA
Establishment of Hydrometeorological Stations | HJ/W/HYDROMET/2015/01-05 | Lot 1 | BOQ | NCB | Pre- Qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[7 empty] | Actual | [7 empty] | Actual | NA

## Hadejia Goods
PROCUREMENT PLANNING (GOODS)
Ministry/Department/Agency: | HADEJIA - JAMA'ARE RIVER BASIN DEVELOPMENT AUTHORITY, KANO |  |  |  |  | THE TIME LINE IS TO BE COMPARED WITH THE COUNCILS APPROVAL
Budgetary Year: 2015 | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Procurement Method | Pre-qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Plan vs. Actual | FEC Approval | Date Contract Offer | Date Contract Signature |  | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks | Plan | 2 wks | 1 - 2 wks | 2 wks |  | 2 - 3 wks | T | 2 wks
|  |  |  | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Plants & Machineries | HJ/G/P&M/2015/01-05 | Lot 1 | NCB | Pre-qualification | PTB | Plan | 2nd - 23th March, 2015 | 24th March - 7th April, 2015 | 8th - 22nd April , 2015 | 23rd April - 4th June, 2015 | 4th June, 2015 | 5th - 19th June, 2015 | 22nd June - 20th July, 2015 | Plan | NA | 21st July - 4th August, 2015 | 5th - 19th August, 2015 | 28th May - 12th June, 2013 | 20th August - 10th September, 2015 | 30th November, 2015 | 1st - 15th December, 2015
[6 empty] | Actual | [7 empty] | Actual

## LBRBDA
Ministry/Department/Agency: FMWR/LBRBDA, MKD
Budgetary Year: 2015 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Pre-or Post Qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Cropping of 10 ha at Katsina-Ala project | [6 empty] | Plan | [7 empty] | Plan
| FMWR/LB | Lot 1/WS | BOQ | PRE-QUAL | Pre-Qual | PTB | Actual | 9/3/15 | 23/3/15 | 13-4-2015 | 4-5-2015 | 15-6-2015 | 29-6-2015 | 13-7-2015 | Actual | N/A | 27/7/15 | 3/8/15 | N/A | N/A | N/A
Expansion of irrigation delivery capacity for Naka Project | [6 empty] | Plan | [7 empty] | Plan
| FMWR/LB | On-going | BOQ | PRE-QUAL | Pre-Qual | PTB | Actual | 9/3/15 | 23/3/15 | 13-4-2015 | 4-5-2015 | 15-6-2015 | 29-6-2015 | 13-7-2015 | Actual | N/A | 27/7/15 | 3/8/15 | N/A | N/A | N/A
Construction of small Earth Dam/water treatment plant at owukpa/road,Culverts and Bridges | [6 empty] | Plan | [7 empty] | Plan
| FMWR/LB | On-going | BOQ | PRE-QUAL | Pre-Qual | PTB | Actual | 9/3/15 | 23/3/15 | 13-4-2015 | 4-5-2015 | 15-6-2015 | 29-6-2015 | 13-7-2015 | Actual | N/A | 27/7/15 | 3/8/15 | N/A | N/A | N/A
Rehabilitation of Access Road to Yonov Dam | [6 empty] | Plan | [7 empty] | Plan
| FMWR/LB | Lot 2/WS | BOQ | PRE-QUAL | Pre-Qual | PTB | Actual | 9/3/15 | 23/3/15 | 13-4-2015 | 4-5-2015 | 15-6-2015 | 29-6-2015 | 13-7-2015 | Actual | N/A | 27/7/15 | 3/8/15 | N/A | N/A | N/A
Construction of Small Earth Dam at Mbusu | [6 empty] | Plan | [7 empty] | Plan
| FMWR/LB | On-going | BOQ | PRE-QUAL | Pre-Qual | PTB | Actual | 9/3/15 | 23/3/15 | 13-4-2015 | 4-5-2015 | 15-6-2015 | 29-6-2015 | 13-7-2015 | Actual | N/A | 27/7/15 | 3/8/15 | N/A | N/A | N/A
Construction of Konshisha Earth Dam (Rehabilitation of access roads) | [6 empty] | Plan | [7 empty] | Plan
| FMWR/LB | Lot3/WS | BOQ | PRE-QUAL | Pre-Qual | PTB | Actual | 9/3/15 | 23/3/15 | 13-4-2015 | 4-5-2015 | 15-6-2015 | 29-6-2015 | 13-7-2015 | Actual | N/A | 27/7/15 | 3/8/15 | N/A | N/A | N/A
Comprehensive Rehabilitation of Doma Dam irrigation Project | [6 empty] | Plan | [7 empty] | Plan
| FMWR/LB | On-going | BOQ | PRE-QUAL | Pre-Qual | PTB | Actual | 9/3/15 | 23/3/15 | 13-4-2015 | 4-5-2015 | 15-6-2015 | 29-6-2015 | 13-7-2015 | Actual | N/A | 27/7/15 | 3/8/15 | N/A | N/A | N/A
Dep Irrigation Scheme (Rehabilitation of staff quarters) | [6 empty] | Plan | [7 empty] | Plan
| FMWR/LB | Lot4/WS | BOQ | PRE-QUAL | Pre-Qual | PTB | Actual | 9/3/15 | 23/3/15 | 13-4-2015 | 4-5-2015 | 15-6-2015 | 29-6-2015 | 13-7-2015 | Actual | N/A | 27/7/15 | 3/8/15 | N/A | N/A | N/A
Construction of Small Earth Dam at Foron, Barkin Ladi / Rehabilitation of Culverts and Bridges at Topp Jos South | [6 empty] | Plan | [7 empty] | Plan
| FMWR/LB | On-going | BOQ | PRE-QUAL | Pre-Qual | PTB | Actual | 9/3/15 | 23/3/15 | 13-4-2015 | 4-5-2015 | 15-6-2015 | 29-6-2015 | 13-7-2015 | Actual | N/A | 27/7/15 | 3/8/15 | N/A | N/A | N/A
Construction of Gazum Dam, Langtang North Plateau state | [6 empty] | Plan | [7 empty] | Plan
| FMWR/LB | On-going | BOQ | PRE-QUAL | Pre-Qual | PTB | Actual | 9/3/15 | 23/3/15 | 13-4-2015 | 4-5-2015 | 15-6-2015 | 29-6-2015 | 13-7-2015 | Actual | N/A | 27/7/15 | 3/8/15 | N/A | N/A | N/A
Construction of Ojokpachi Earth Dam | [6 empty] | Plan | [7 empty] | Plan
| FMWR/LB | On-going | BOQ | PRE-QUAL | Pre-Qual | PTB | Actual | 9/3/15 | 23/3/15 | 13-4-2015 | 4-5-2015 | 15-6-2015 | 29-6-2015 | 13-7-2015 | Actual | N/A | 27/7/15 | 3/8/15 | N/A | N/A | N/A
UNDERGROUND WATER DEVELOPMENT: | [6 empty] | Plan | [7 empty] | Plan
Drilling of 1No Motorized Borehole at Topp, Jos South | [6 empty] | Plan | [7 empty] | Plan
| FMWR/LB | Lot5/WS | BOQ | PRE-QUAL | Pre-Qual | PTB | Actual | 9/3/15 | 23/3/15 | 13-4-2015 | 4-5-2015 | 15-6-2015 | 29-6-2015 | 13-7-2015 | Actual | N/A | 27/7/15 | 3/8/15 | N/A | N/A | N/A
Drilling of 1No Motorized Borehole at Tse-Antiv, Makurdi Benue State | FMWR/LB | [5 empty] | Plan | [7 empty] | Plan
|  | Lot6/WS | BOQ | PRE-QUAL | Pre-Qual | PTB | Actual | 9/3/15 | 23/3/15 | 13-4-2015 | 4-5-2015 | 15-6-2015 | 29-6-2015 | 13-7-2015 | Actual | N/A | 27/7/15 | 3/8/15 | N/A | N/A | N/A
Drilling of 1No Motorized Borehole at Angwan Yazawa, Lafia | [6 empty] | Plan | [7 empty] | Plan
| FMWR/LB | Lot7/WS | BOQ | PRE-QUAL | Pre-Qual | PTB | Actual | 9/3/15 | 23/3/15 | 13-4-2015 | 4-5-2015 | 15-6-2015 | 29-6-2015 | 13-7-2015 | Actual | N/A | 27/7/15 | 3/8/15 | N/A | N/A | N/A
Drilling of 1No Motorized Borehole at Ogbakpedo, Ofu, Kogi State | [6 empty] | Plan | [7 empty] | Plan
| FMWR/LB | Lot8/WS | BOQ | PRE-QUAL | Pre-Qual | PTB | Actual | 9/3/15 | 23/3/15 | 13-4-2015 | 4-5-2015 | 15-6-2015 | 29-6-2015 | 13-7-2015 | Actual | N/A | 27/7/15 | 3/8/15 | N/A | N/A | N/A
Repair of Light Vehicle | [6 empty] | Plan | [7 empty] | Plan
| FMWR/LB | Lot 9/WS | BOQ | PRE-QUAL | Pre-Qual | PTB | Actual | 9/3/15 | 23/3/15 | 13-4-2015 | 4-5-2015 | 15-6-2015 | 29-6-2015 | 13-7-2015 | Actual | N/A | 27/7/15 | 3/8/15 | N/A | N/A | N/A
Human Capital Development | [6 empty] | Plan | [7 empty] | Plan
| FMWR/LB | Continous | BOQ | PRE-QUAL | Pre-Qual | PTB | Actual | 9/3/15 | 23/3/15 | 13-4-2015 | 4-5-2015 | 15-6-2015 | 29-6-2015 | 13-7-2015 | Actual | N/A | 27/7/15 | 3/8/15 | N/A | N/A | N/A
Servicom Activities | [6 empty] | Plan | [7 empty] | Plan
| FMWR/LB | Continous | BOQ | PRE-QUAL | Pre-Qual | PTB | Actual | 9/3/15 | 23/3/15 | 13-4-2015 | 4-5-2015 | 15-6-2015 | 29-6-2015 | 13-7-2015 | Actual | N/A | 27/7/15 | 3/8/15 | N/A | N/A | N/A
HIV and AIDS Prevention | [6 empty] | Plan | [7 empty] | Plan
| FMWR/LB | Continous | BOQ | PRE-QUAL | Pre-Qual | PTB | Actual | 9/3/15 | 23/3/15 | 13-4-2015 | 4-5-2015 | 15-6-2015 | 29-6-2015 | 13-7-2015 | Actual | N/A | 27/7/15 | 3/8/15 | N/A | N/A | N/A
Anti-Corruption Activities | [6 empty] | Plan | [7 empty] | Plan
| FMWR/LB | Continous | BOQ | PRE-QUAL | Pre-Qual | PTB | Actual | 9/3/15 | 23/3/15 | 13-4-2015 | 4-5-2015 | 15-6-2015 | 29-6-2015 | 13-7-2015 | Actual | N/A | 27/7/15 | 3/8/15 | N/A | N/A | N/A
Monitoring and Evaluation of Capital Project implementation | [6 empty] | Plan | [7 empty] | Plan
| FMWR/LB | Continous | BOQ | PRE-QUAL | Pre-Qual | PTB | Actual | 9/3/15 | 23/3/15 | 13-4-2015 | 4-5-2015 | 15-6-2015 | 29-6-2015 | 13-7-2015 | Actual | N/A | 27/7/15 | 3/8/15 | N/A | N/A | N/A

## Maritime Academy Works
Ministry/Department/Agency: | MARITIME ACADEMY OF NIGERIA, ORON
Budget Year: | 2015
|  | Basic Data | [7 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Bidding Period |  | Bid Evaluation |  |  |  |  | Contract Implementation - Works
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing/ Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 24 weeks
| Plan vs Actual | Plan vs Actual | Plan vs Actual | Plan vs Actual | Plan vs Actual | Plan vs Actual | Plan vs Actual | Plan vs Actual | Plan vs Actual | Plan vs Actual | Plan vs Actual | Plan vs Actual | Plan vs Actual | Plan vs Actual | Plan vs Actual | Plan vs Actual | Plan vs Actual | Plan vs Actual | Plan vs Actual | Plan vs Actual | Plan vs Actual | Plan vs Actual
| Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan
| Actual | MAN/PU/CP/1/2015 | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual
CONSTRUCTION OF NEW ROADS FOR THE ACADEMY’S NEWLY ACQUIRED LAND | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CONSTRUCTION OF INTERNAL ROAD 19 | Plan | W1 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
CONSTRUCTION OF INTERNAL ROAD 20 | Plan | W2 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
CONSTRUCTION OF INTERNAL ROAD 21 | Plan | W3 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
CONSTRUCTION OF INTERNAL ROAD 22 | Plan | W4 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
CONSTRUCTION OF INTERNAL ROAD 23 | Plan | W5 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
CONSTRUCTION OF STAFF MODELS SCHOOLS | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CONSTRUCTION OF 1 NO. BUNGALOW CLASSROOM BLOCK (A) | Plan | W6 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
CONSTRUCTION OF 1 NO. BUNGALOW CLASSROOM BLOCK (B) | Plan | W7 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
CONSTRUCTION OF 1 NO. BUNGALOW CLASSROOM BLOCK (C ) | Plan | W8 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
CONSTRUCTION OF 1 NO. BUNGALOW CLASSROOM BLOCK (D) | Plan | W9 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
CONSTRUCTION OF 1 NO. ADMINISTRATIVE BLOCK BUNGALOW FOR STAFF SCHOOL | Plan | W10 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
ESTABLISHING OF ABUJA STUDY CENTRE AND LIAISON OFFICE | Plan | W11 |  | LUMP SUM | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
CONSTRUCTION OF 1 NO. 200 CAPACITY MALE CADETS’ HOSTEL BLOCK (B) | Plan | W12 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
CONCRETE CASTING OF SURROUNDINGS AND WALKWAY OF THE 1 NO. ONE-STOREY CLASSROOM BLOCK | Plan | W13 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
CONSTRUCTION OF A NEW SIMULATOR COMPLEX | Plan | W14 |  | LUMP SUM | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
EXPANSION OF SEAMSHIP WORKSHOP | Plan | W15 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
CONSTRUCTION OF MARINE ENGINEERING AND REPAIR WORKSHOP FOR THE UTILIZATION OF SCRAPS FROM THE SHIP RECYCLING COMPANY AT CALABAR | Plan | W16 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
CONSTRUCTION OF SHIP BRIDGE EQUIPMENT STORE | Plan | W17 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
CONSTRUCTION AND UTILIZATION OF OLD SHIP ENGINES FOR THE GENERATION OF ELECTRICITY | Plan | W18 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
UPGRADING OF KITCHEN IN REFECTORY PHASE I AND ELECTRICAL/GAS PARTITIONING | Plan | W19 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
PROVISION OF COLD ROOM 4FT BY 6FT AND FOOD STORE | Plan | W20 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
EXTENSION OF HOOD AND AIR EXTRACTOR IN THE KITCHEN | Plan | W21 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
MANAGEMENT OF LIQUID AND SOLID WASTE AND PROVISION OF ADDITIONAL URINARY FACILITIES | Plan | W22 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
HOST COMMUNITY DEVELOPMENT PROJECTS | Plan | W23 |  | LUMP SUM | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
PROVISION OF SOLAR LIGHT AT THE COLLEGE ROAD SIDE B COVERING THE REMAINING CHAINAGE 0+000 TO 0+250 AT 12.5 METERS SPACING | Plan | W24 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
EROSION CONTROL AT THE ACADEMY BOAT/SHIP BUILDING YARD | Plan | W25 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
SOIL RECLAMATION WITHIN THE ENTIRE ACADEMY AND ENVIRONS | Plan | W26 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
LANDSCAPING OF THE BACK LAYOUT OF THE MARITIME ACADEMY OF NIGERIA LIAISON OFFICE, LAGOS | Plan | W27 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
RENOVATION/FURNISHING OF QUARTER 3 | Plan | W28 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
RENOVATION/FURNISHING OF QUARTER 4 | Plan | W29 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
COMPLETION OF ON-GOING PROJECTS | Plan | W30 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
COMPLETION OF BOATYARD PROJECTS AND OTHER FGN FUNDED ON-GOING PROJECTS | Plan | W31 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
CONSTRUCTION OF THREE BEDROOM FLAT TWIN BUNGALOW STAFF QUARTERS - A | Plan | W32 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
CONSTRUCTION OF THREE BEDROOM FLAT TWIN BUNGALOW STAFF QUARTERS - B | Plan | W33 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
CONSTRUCTION OF THREE BEDROOM FLAT TWIN BUNGALOW STAFF QUARTERS - C | Plan | W34 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
CONSTRUCTION OF THREE BEDROOM FLAT TWIN BUNGALOW STAFF QUARTERS - D | Plan | W35 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
CONSTRUCTION OF THREE BEDROOM FLAT TWIN BUNGALOW STAFF QUARTERS - E | Plan | W36 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15 - 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
ESTABLISHMENT OF LAGOS STUDY CENTRE AND LAISON OFFICE FOR THE MARITIME ACADEMY OF NIGERIA, ORON | Plan | W37 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
SCRAPPING AND PAINTING OF THE ENTIRE ACADEMY'S PERIMETER FENCE (INTERNAL/EXTERNAL) | Plan | W38 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
RESTORATION OF POWER TO FIRE PUMP AND SERVICING OF FIRE HYDRANT AT THE FIRE GROUND OF MAN, ORON | Plan | W39 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
COMPUTERIZATION OF THE NEWLY CONSTRUCTED CADETS RESOURCE CENTRE - PHASE II | Plan | W40 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
PROVISION OF INTRANET AND E-CAMPUS EDUCATIONAL FACILITIES | Plan | W41 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
PROVISION OF STREETLIGHTS AT THE NEWLY CONSTRUCTED ROAD IN ACADEDMY. | Plan | W42 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
GENERAL OVERHAULING OF ACADEMY’S 18-SEATER BOAT FOR CADETS’ TRAINING (MV SOUTHERN CROSS) | Plan | W43 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
RE-ROOFING OF THE SIMULATOR COMPLEX | Plan | W44 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
PROVISION OF LAND BASE SEWAGE TREATMENT SYSTEM UNIT | Plan | W45 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
REMOVAL OF OLD SHIP AND CONSTRUCTION OF CONCRETE BASE AND ELECTRICAL INSTALLATION | Plan | W46 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST - REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
REHABILITATION OF OLD SURVIVAL CAPSULE FOR GENERAL TRAINING ON SEAMANSHIP | PLAN | W47 |  | SCHEDULE ON DELIVERY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
EXPANSION OF SEAMSHIP LABORATORY | PLAN | W48 |  | SCHEDULE ON DELIVERY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
RENOVATION OF 3 NOS. CLASSROOMS WITH CURRENT FACILITIES. | PLAN | W49 |  | SCHEDULE ON DELIVERY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
PROVISION OF SEPARATE CLASSROOM FOR CHEMICAL AND OIL TANKER FAMILIARIZATION TRAINING | PLAN | W50 |  | SCHEDULE ON DELIVERY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15

## Non-Consultancy
Ministry/Department/Agency: | MARITIME ACADEMY OF NIGERIA, ORON
Budget Year: | 2015
|  | Basic Data | [7 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals | Proposal Evaluation and Negotiation | [8 empty] | Contract Implementation - Consultancy
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 1 weeks | 2 - 4 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
AUGMENTATION OF STAFF TRAINING AND DEVELOPMENT | PLAN | 2 | N/A | SCHEDULE ON DELIVERY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
AUGMENTATION OF OVERHEAD COST | PLAN | NC2 | N/A | SCHEDULE ON DELIVERY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
PROVISION OF PECULIAR ALLOWANCE IN PERSONNEL COST | PLAN | NC3 | N/A | SCHEDULE ON DELIVERY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
PROVISION OF GENERAL CLEANING SERVICES AT THE MARITIME ACADEMY OF NIGERIA, ORON | PLAN | NC4 | N/A | SCHEDULE ON DELIVERY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
PROVISION OF SECURITY SERVICE AROUND BOUNDARIES WITHIN COMMUNITIES LINKING MAN, ORON ON MONTHLY BASIS | PLAN | NC5 | N/A | SCHEDULE ON DELIVERY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
RESEARCH | PLAN | NC6 | N/A | SCHEDULE ON DELIVERY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
MONITORING AND EVALUATION | PLAN | NC7 | N/A | SCHEDULE ON DELIVERY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
ORANISATION/CONDUCT OF ADMISSION EXERCISE | PLAN | NC8 | N/A | SCHEDULE ON DELIVERY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
TRAINING OF SIMULATOR INSTRUCTORS FOR EFFECTIVE USE OF THE SIMULATOR SYSTEM | PLAN | NC9 | N/A | SCHEDULE ON DELIVERY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
ADMINISTRATION/CONDUCT OF REGULAR PROGRAMMES | PLAN | NC10 | N/A | SCHEDULE ON DELIVERY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15

## Goods
Ministry/Department/Agency: | MARITIME ACADEMY OF NIGERIA, ORON
Budget Year: | 2015
|  | Basic Data | [7 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals | Proposal Evaluation and Negotiation | [8 empty] | Contract Implementation - Consultancy
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 1 weeks | 2 - 4 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
AUGMENTATION OF STAFF TRAINING AND DEVELOPMENT | PLAN | 2 | N/A | SCHEDULE ON DELIVERY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
AUGMENTATION OF OVERHEAD COST | PLAN | NC2 | N/A | SCHEDULE ON DELIVERY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
PROVISION OF PECULIAR ALLOWANCE IN PERSONNEL COST | PLAN | NC3 | N/A | SCHEDULE ON DELIVERY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
PROVISION OF GENERAL CLEANING SERVICES AT THE MARITIME ACADEMY OF NIGERIA, ORON | PLAN | NC4 | N/A | SCHEDULE ON DELIVERY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
PROVISION OF SECURITY SERVICE AROUND BOUNDARIES WITHIN COMMUNITIES LINKING MAN, ORON ON MONTHLY BASIS | PLAN | NC5 | N/A | SCHEDULE ON DELIVERY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
RESEARCH | PLAN | NC6 | N/A | SCHEDULE ON DELIVERY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
MONITORING AND EVALUATION | PLAN | NC7 | N/A | SCHEDULE ON DELIVERY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
ORANISATION/CONDUCT OF ADMISSION EXERCISE | PLAN | NC8 | N/A | SCHEDULE ON DELIVERY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
TRAINING OF SIMULATOR INSTRUCTORS FOR EFFECTIVE USE OF THE SIMULATOR SYSTEM | PLAN | NC9 | N/A | SCHEDULE ON DELIVERY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15
ADMINISTRATION/CONDUCT OF REGULAR PROGRAMMES | PLAN | NC10 | N/A | SCHEDULE ON DELIVERY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | N/A | N/A | 30TH MARCH, 2015 | 15/5/15 - 13/6/15 | 13/6/15 - 15/6/15 | 15/6/15- 29/6/15 | 30/6/15 - 15/7/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15 | N/A | 25/7/15 - 7/9/15 | 8/9/15 - 29/9/15 | 29/9/15 - 12/10/15 | 12/10/15 - 19/10/15 | 20/10/15 - 25/10/15

## Maritime Consultancy
Ministry/Department/Agency: | MARITIME ACADEMY OF NIGERIA, ORON
Budget Year: | 2015
|  | Basic Data | [7 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 1 weeks | 2 - 4 weeks | 2 weeks | 2 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
| Plan vs Actual | MAN/PU/CP/1/2015
CONSULTANCY FOR THE ACADEMY'S NEW DEVELOPMENTAL PROJECTS. | PLAN | C1 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | 31/10/14 - 4/10/14 | 7/11/14 - 11/11/14 | 15/11/14- 18/11/14 | 21/11/14- 25/11/14 | 28/11/14- 2/12/14 | 5/12/14 - 9/12/14 | 12/12/14 - 16/12/14 | 19/12/14 - 23/12/14 | 26/12/14 - 30/12/14 | 2/1/15 - 6/1/15 | 9/1/15 - 14/1/15 | 16/1/15- 20/1/15 | 23/1/15 - 27/1/15 | 30/1/15 - 3/1/15 | 6/2/15 - 10/2/15 | 14/2/15 - 17/2/15 | 20/2/15- 24/2/15 | 27/2/15 - 2/3/15 | 5/3/15 - 9/3/15 | 10/3/15 - 11/3/15 | 12/3/15 - 15/3/15
CONSULTANCY FOR REVENUE GENERATION | PLAN | C2 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | 31/10/14 - 4/10/14 | 7/11/14 - 11/11/14 | 15/11/14- 18/11/14 | 21/11/14- 25/11/14 | 28/11/14- 2/12/14 | 5/12/14 - 9/12/14 | 12/12/14 - 16/12/14 | 19/12/14 - 23/12/14 | 26/12/14 - 30/12/14 | 2/1/15 - 6/1/15 | 9/1/15 - 14/1/15 | 16/1/15- 20/1/15 | 23/1/15 - 27/1/15 | 30/1/15 - 3/1/15 | 6/2/15 - 10/2/15 | 14/2/15 - 17/2/15 | 20/2/15- 24/2/15 | 27/2/15 - 2/3/15 | 5/3/15 - 9/3/15 | 10/3/15 - 11/3/15 | 12/3/15 - 15/3/15
CONSULTANCY FOR ACADEMY’S NEW DEVELOPMENTAL PROJECTS FOR YEAR 2015 | PLAN | C3 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | 31/10/14 - 4/10/14 | 7/11/14 - 11/11/14 | 15/11/14- 18/11/14 | 21/11/14- 25/11/14 | 28/11/14- 2/12/14 | 5/12/14 - 9/12/14 | 12/12/14 - 16/12/14 | 19/12/14 - 23/12/14 | 26/12/14 - 30/12/14 | 2/1/15 - 6/1/15 | 9/1/15 - 14/1/15 | 16/1/15- 20/1/15 | 23/1/15 - 27/1/15 | 30/1/15 - 3/1/15 | 6/2/15 - 10/2/15 | 14/2/15 - 17/2/15 | 20/2/15- 24/2/15 | 27/2/15 - 2/3/15 | 5/3/15 - 9/3/15 | 10/3/15 - 11/3/15 | 12/3/15 - 15/3/15
CONSULTANCY FOR HOST COMMUNITY DEVELOPMENT PROJECTS | PLAN | C4 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | 31/10/14 - 4/10/14 | 7/11/14 - 11/11/14 | 15/11/14- 18/11/14 | 21/11/14- 25/11/14 | 28/11/14- 2/12/14 | 5/12/14 - 9/12/14 | 12/12/14 - 16/12/14 | 19/12/14 - 23/12/14 | 26/12/14 - 30/12/14 | 2/1/15 - 6/1/15 | 9/1/15 - 14/1/15 | 16/1/15- 20/1/15 | 23/1/15 - 27/1/15 | 30/1/15 - 3/1/15 | 6/2/15 - 10/2/15 | 14/2/15 - 17/2/15 | 20/2/15- 24/2/15 | 27/2/15 - 2/3/15 | 5/3/15 - 9/3/15 | 10/3/15 - 11/3/15 | 12/3/15 - 15/3/15
CONSULTANCY FOR CURRICULUM DEVELOPMENT | PLAN | C5 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | 31/10/14 - 4/10/14 | 7/11/14 - 11/11/14 | 15/11/14- 18/11/14 | 21/11/14- 25/11/14 | 28/11/14- 2/12/14 | 5/12/14 - 9/12/14 | 12/12/14 - 16/12/14 | 19/12/14 - 23/12/14 | 26/12/14 - 30/12/14 | 2/1/15 - 6/1/15 | 9/1/15 - 14/1/15 | 16/1/15- 20/1/15 | 23/1/15 - 27/1/15 | 30/1/15 - 3/1/15 | 6/2/15 - 10/2/15 | 14/2/15 - 17/2/15 | 20/2/15- 24/2/15 | 27/2/15 - 2/3/15 | 5/3/15 - 9/3/15 | 10/3/15 - 11/3/15 | 12/3/15 - 15/3/15
CONSULTANCY FOR NEGOTIATION WITH NUC FOR REGISTRATION WITH NUC FOR THE COMMENCEMENT OF UNIVERSITY PROGRAMMES | PLAN | C6 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | 31/10/14 - 4/10/14 | 7/11/14 - 11/11/14 | 15/11/14- 18/11/14 | 21/11/14- 25/11/14 | 28/11/14- 2/12/14 | 5/12/14 - 9/12/14 | 12/12/14 - 16/12/14 | 19/12/14 - 23/12/14 | 26/12/14 - 30/12/14 | 2/1/15 - 6/1/15 | 9/1/15 - 14/1/15 | 16/1/15- 20/1/15 | 23/1/15 - 27/1/15 | 30/1/15 - 3/1/15 | 6/2/15 - 10/2/15 | 14/2/15 - 17/2/15 | 20/2/15- 24/2/15 | 27/2/15 - 2/3/15 | 5/3/15 - 9/3/15 | 10/3/15 - 11/3/15 | 12/3/15 - 15/3/15
CONSULTANCY FOR THE VALIDATION OF THE MARITIME ACADEMY OF NIGERIA QUOTA OF THE TERTIARY EDUCATION TRUST FUND (TETFUND) | PLAN | C7 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | 31/10/14 - 4/10/14 | 7/11/14 - 11/11/14 | 15/11/14- 18/11/14 | 21/11/14- 25/11/14 | 28/11/14- 2/12/14 | 5/12/14 - 9/12/14 | 12/12/14 - 16/12/14 | 19/12/14 - 23/12/14 | 26/12/14 - 30/12/14 | 2/1/15 - 6/1/15 | 9/1/15 - 14/1/15 | 16/1/15- 20/1/15 | 23/1/15 - 27/1/15 | 30/1/15 - 3/1/15 | 6/2/15 - 10/2/15 | 14/2/15 - 17/2/15 | 20/2/15- 24/2/15 | 27/2/15 - 2/3/15 | 5/3/15 - 9/3/15 | 10/3/15 - 11/3/15 | 12/3/15 - 15/3/15
CONSULTANCY FOR AUDITING OF 2014/2015 ACCOUNT BOOKS OF THE MARITIME ACADEMY OF NIGERIA, ORON | PLAN | C8 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | 31/10/14 - 4/10/14 | 7/11/14 - 11/11/14 | 15/11/14- 18/11/14 | 21/11/14- 25/11/14 | 28/11/14- 2/12/14 | 5/12/14 - 9/12/14 | 12/12/14 - 16/12/14 | 19/12/14 - 23/12/14 | 26/12/14 - 30/12/14 | 2/1/15 - 6/1/15 | 9/1/15 - 14/1/15 | 16/1/15- 20/1/15 | 23/1/15 - 27/1/15 | 30/1/15 - 3/1/15 | 6/2/15 - 10/2/15 | 14/2/15 - 17/2/15 | 20/2/15- 24/2/15 | 27/2/15 - 2/3/15 | 5/3/15 - 9/3/15 | 10/3/15 - 11/3/15 | 12/3/15 - 15/3/15
CONSULTANCY FOR ACCESSMENT, MANAGEMENT AND ADMINISTRATION OF ACADEMY'S FUND DOMICILED AT THE CENTRAL BANK OF NIGERIA, ORON | PLAN | C9 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | 31/10/14 - 4/10/14 | 7/11/14 - 11/11/14 | 15/11/14- 18/11/14 | 21/11/14- 25/11/14 | 28/11/14- 2/12/14 | 5/12/14 - 9/12/14 | 12/12/14 - 16/12/14 | 19/12/14 - 23/12/14 | 26/12/14 - 30/12/14 | 2/1/15 - 6/1/15 | 9/1/15 - 14/1/15 | 16/1/15- 20/1/15 | 23/1/15 - 27/1/15 | 30/1/15 - 3/1/15 | 6/2/15 - 10/2/15 | 14/2/15 - 17/2/15 | 20/2/15- 24/2/15 | 27/2/15 - 2/3/15 | 5/3/15 - 9/3/15 | 10/3/15 - 11/3/15 | 12/3/15 - 15/3/15
CONSULTANCY FOR MEDIA SERVICES FOR THE MARITIME ACADEMY OF NIGERIA, ORON | PLAN | C10 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | 31/10/14 - 4/10/14 | 7/11/14 - 11/11/14 | 15/11/14- 18/11/14 | 21/11/14- 25/11/14 | 28/11/14- 2/12/14 | 5/12/14 - 9/12/14 | 12/12/14 - 16/12/14 | 19/12/14 - 23/12/14 | 26/12/14 - 30/12/14 | 2/1/15 - 6/1/15 | 9/1/15 - 14/1/15 | 16/1/15- 20/1/15 | 23/1/15 - 27/1/15 | 30/1/15 - 3/1/15 | 6/2/15 - 10/2/15 | 14/2/15 - 17/2/15 | 20/2/15- 24/2/15 | 27/2/15 - 2/3/15 | 5/3/15 - 9/3/15 | 10/3/15 - 11/3/15 | 12/3/15 - 15/3/15
CONSULTANCY FOR LOCAL MEDIA SERVICES FOR THE MARITIME ACADEMY OF NIGERIA, ORON | PLAN | C11 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | 31/10/14 - 4/10/14 | 7/11/14 - 11/11/14 | 15/11/14- 18/11/14 | 21/11/14- 25/11/14 | 28/11/14- 2/12/14 | 5/12/14 - 9/12/14 | 12/12/14 - 16/12/14 | 19/12/14 - 23/12/14 | 26/12/14 - 30/12/14 | 2/1/15 - 6/1/15 | 9/1/15 - 14/1/15 | 16/1/15- 20/1/15 | 23/1/15 - 27/1/15 | 30/1/15 - 3/1/15 | 6/2/15 - 10/2/15 | 14/2/15 - 17/2/15 | 20/2/15- 24/2/15 | 27/2/15 - 2/3/15 | 5/3/15 - 9/3/15 | 10/3/15 - 11/3/15 | 12/3/15 - 15/3/15
CONSULTANCY FOR THE ACADEMY'S ENDOWMENT FUND | PLAN | C12 |  | BILL OF QUANTITY | PUBLIC COMPETITIVE BIDDING | PTB | OPEN COMPETITIVE BIDDING | POST-QUALIFICATION | POST-REVIEW | 31/10/14 - 4/10/14 | 7/11/14 - 11/11/14 | 15/11/14- 18/11/14 | 21/11/14- 25/11/14 | 28/11/14- 2/12/14 | 5/12/14 - 9/12/14 | 12/12/14 - 16/12/14 | 19/12/14 - 23/12/14 | 26/12/14 - 30/12/14 | 2/1/15 - 6/1/15 | 9/1/15 - 14/1/15 | 16/1/15- 20/1/15 | 23/1/15 - 27/1/15 | 30/1/15 - 3/1/15 | 6/2/15 - 10/2/15 | 14/2/15 - 17/2/15 | 20/2/15- 24/2/15 | 27/2/15 - 2/3/15 | 5/3/15 - 9/3/15 | 10/3/15 - 11/3/15 | 12/3/15 - 15/3/15

## Aviation Works
S/N | Ministry of Aviation Budgetary Year: 2015 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
| Desk Officer/ |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
| Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | MDA APPROVAL | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Inspection /Acceptance
| Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 6wks | 4-6 wks | 2 - 3 wks | 1 - 2 wks |  | 2 - 4 wk | 1 - 2 wks | 3 wks | 2WKS | 4WKS | 2WKS | 1WK
[6 empty] | add 2 wks |  | Actual
2015 (SMALL WORKS) PROJECTS
1 | Renovation of FGN Airstrip Facilities at Gboko, Benue State | FMA/SW/2015 | 1 | BOQ | NCB | N/A | PS | Plan | 4/11/14 - 18/11/14 | 18/11/14 - 2/12/14 | N/A | 4/5/15 -15/6/15 | 15/6/15 | 29/6/15 | N/A | N/A | N/A | 6/7/15 | 27/7/15 | N/A | 24/8/15 | 24/8/15 | 31/8/15
Actual
2 | Renovation of FGN Airstrip Facilities at Langtang, Plateaeu State | FMA/SW/2015 | 2 | BOQ | NCB | N/A | PS | Plan | 4/11/14 - 18/11/14 | 18/11/14 - 2/12/14 | N/A | 4/5/15 -15/6/15 | 15/6/15 | 29/6/15 | N/A | N/A | N/A | 6/7/15 | 27/7/15 | N/A | 24/8/15 | 24/8/15 | 31/8/15
Actual
3 | Renovation of FGN Airstrip Facilities at Potiskum, Yobe State | FMA/SW/2015 | 3 | BOQ | NCB | N/A | PS | Plan | 4/11/14 - 18/11/14 | 18/11/14 - 2/12/14 | N/A | 4/5/15 -15/6/15 | 15/6/15 | 29/6/15 | N/A | N/A | N/A | 6/7/15 | 27/7/15 | N/A | 24/8/15 | 24/8/15 | 31/8/15
Actual
4 | Renovation of FGN Airstrip Facilities at Oshogbo, Osun State | FMA/SW/2015 | 4 | BOQ | NCB | N/A | PS | Plan | 4/11/14 - 18/11/14 | 18/11/14 - 2/12/14 | N/A | 4/5/15 -15/6/15 | 15/6/15 | 29/6/15 | N/A | N/A | N/A | 6/7/15 | 27/7/15 | N/A | 24/8/15 | 24/8/15 | 31/8/15
Actual
5 | Renovation of FGN Airstrip Facilities at Abeokuta, Ogun State | FMA/SW/2015 | 5 | BOQ | NCB | N/A | PS | Plan | 4/11/14 - 18/11/14 | 18/11/14 - 2/12/14 | N/A | 4/5/15 -15/6/15 | 15/6/15 | 29/6/15 | N/A | N/A | N/A | 6/7/15 | 27/7/15 | N/A | 24/8/15 | 24/8/15 | 31/8/15
Actual
6 | Renovation of FGN Airstrip Facilities at Obudu, Cross River State | FMA/SW/2015 | 6 | BOQ | NCB | N/A | PS | Plan | 4/11/14 - 18/11/14 | 18/11/14 - 2/12/14 | N/A | 4/5/15 -15/6/15 | 15/6/15 | 29/6/15 | N/A | N/A | N/A | 6/7/15 | 27/7/15 | N/A | 24/8/15 | 24/8/15 | 31/8/15
Actual

## Aviation Consultancy
| Ministry of Aviation Budgetary Year: 2015 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
| Desk Officer/ |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation | [5 empty] | Contract Implementation
| Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | MDA APPROVAL | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Inspection /Acceptance
| Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 4wks | 4-6 wks | 2 - 3 wks | 1 - 2 wks | Plan | 2 - 4 wk | 1 - 2 wks | 3 wks | 2WKS | 8WKS | 2WKS | 1WK
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
2015 (CONSULTANCY) PROJECTS
1 | Consultancy Services lnformation Technology (IT) Audit | CA1 | 1 | N/A | NCB | NO | MTB | Plan | 4/11/14-18/11/14 | 18/11/14-2/12/14 | N/A | 2/3/15-1/4/15 | 1/4/15 | 22/4/15 | N/A | Plan | N/A | 22/4/15-6/5/15 | 6/5/15-27/5/15 | 27//5/15-9/6/15 | 9/6/15-4/8/15 | 4/8/15-18/8/15 | 25/8/15
[8 empty] | Actual | [7 empty] | Actual
2 | Consultancy of Access Control Management system at the Airports | CA2 | 2 | N/A | NCB | NO | MTB | Plan | 4/11/14-18/11/14 | 18/11/14-2/12/14 | N/A | 2/3/15-1/4/15 | 1/4/15 | 22/4/15 | N/A | Plan | N/A | 22/4/15-6/5/15 | 6/5/15-27/5/15 | 27//5/15-9/6/15 | 9/6/15-4/8/15 | 4/8/15-18/8/15 | 25/8/15
Actual
3 | First quarter monitoring and evaluation of the Ministyrs Capital Projects | N/A | 3 | N/A | Selective tendering | N/A |  | Plan | April
Actual
4 | Second quarter monitoring and evaluation of the Ministyrs Capital Projects | N/A | 4 | N/A | Selective tendering | N/A |  | Plan | July |  |  | N/A | N/A | N/A | N/A
Actual
5 | Third quarter monitoring and evaluation of the Ministyrs Capital Projects | N/A | 5 | N/A | Selective tendering | N/A |  | Plan | October |  |  | N/A | N/A | N/A | N/A
Actual
6 | Fourth quarter monitoring and evaluation of the Ministyrs Capital Projects | N/A | 6 | N/A | Selective tendering | N/A |  | Plan | December
|  | N/A | [5 empty] | Actual
7 | Oversight monitoring of Capital Projects by Senate Committee on Aviation | N/A | 7 | N/A | Selective tendering | N/A |  | Plan | June
Actual
8 | Oversight monitoring of Capital Projects by Senate Committee on Aviation | N/A | 8 | N/A | Selective tendering | N/A |  | Plan | November
Actual
9 | Oversight monitoring of Capital Projects by House Committee on Aviation | N/A |  | N/A | Selective tendering | N/A |  | Plan | May |  |  | N/A | N/A | N/A | N/A
Actual
10 | Oversight monitoring of Capital Projects byHouse Committee on Aviation | N/A | 9 | N/A | Selective tendering | N/A |  | Plan | December
Actual
11 | Ministry officials accompanying NAS committees on oversight visits | N/A |  | N/A | Selective tendering | N/A |  | Plan
Actual
12 | collabotation with Special Duties office of the OSGF for the Monitoring and Evaluation of (FEC) approved projects | N/A |  | N/A | Selective tendering | N/A |  | Plan | June
13 | Consultancy Service for Security Enhancement Programme for International Airports in Nigeria | CA3 |  | N/A | Selective tendering | YES | FEC | Actual | 4/5/15-18/5/15 | 18/5/15-1/6/15 | 1/6/15-29/6/15 | N/A |  |  | 29/6/15-13/7/15 | PLAN | 13/7/15-3/8/15 | 3/8/15-17/8/15 | 17/8/15-14/9/15 | 14/9/15-28/9/15 | 28/9/15-23/11/15 | 23/11/15-7/12/115 | 7/12-15

## Mines & Steel Consultancy
Ministry OF MINES AND STEEL DEVELOPMENT
Budget Year: 2015
|  | Basic Data | [7 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [8 empty] | Contract Implementation - Consultancy
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 1 weeks | 2 - 4 weeks | 2 weeks | 2 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
PROCUREMENT OF EQUIPMENT TO UPGRADE AND UPDATE STEEL DATA BANK | Plan | MMSD/C//01 | LOT 1C | LUMPSUM | NCB | MTB | QCBS | Pre-Qualification | POST REVIEW | 26/1-6/2/15 | 9/2-13/2/15 | 16/2-2/3/15 | 2/3-6/3/15 | 9/3-6/4/15 | 6/4-10/4/15 | 13/4-27/4/15 | 27/4/15 | 28/4-12/5/15 | 13/5-22/5/15 | 25/5--29/5/15 | 1/6-12/6/15 | 15/6-19/6/15 | 22/6-3/7/15 | NA | 6/7-10/7/15 | 13/7 - 17/7/15 | 20/7-31/7/15 | 30/9/15 | 30/11/15
ESTABLISHMENT OF EXTENTION SERVICES TO PERFORMING ARTISINAL &SMALL SCALE MINERS OPERATION. | Plan | MMSD/C/O2 | LOT 2C | LUMPSUM | NCB | MTB | QCBS | Pre-Qualification | POST REVIEW | 26/1-6/2/15 | 9/2-13/2/15 | 16/2-2/3/15 | 2/3-6/3/15 | 9/3-6/4/15 | 6/4-10/4/15 | 13/4-27/4/15 | 27/4/15 | 28/4-12/5/15 | 13/5-22/5/15 | 25/5--29/5/15 | 1/6-12/6/15 | 15/6-19/6/15 | 22/6-3/7/15 | NA | 6/7-10/7/15 | 13/7 - 17/7/15 | 20/7-31/7/15 | 30/9/15 | 30/11/15
STIIMULATION & PROMOTION OF ACTIVITIES | [9 empty] | 26/1-6/2/15 | 9/2-13/2/15 | 16/2-2/3/15 | 2/3-6/3/15 | 9/3-6/4/15 | 6/4-10/4/15 | 13/4-27/4/15 | 27/4/15 | 28/4-12/5/15 | 13/5-22/5/15 | 25/5--29/5/15 | 1/6-12/6/15 | 15/6-19/6/15 | 22/6-3/7/15 |  | 6/7-10/7/15 | 13/7 - 17/7/15 | 20/7-31/7/15 | 30/9/15 | 30/11/15
ACTIVITIES OF INDUSTRY IN THE METALS INDUSTRY IN THE 6 GEO-POLITICAL ZONES IN NIGERIA | Plan | MMSD/C/03 | LOT 3C | LUMPSUM | NCB | MTB | QCBS | Pre-Qualification | POST -REVIEW | 26/1-6/2/15 | 9/2-13/2/15 | 16/2-2/3/15 | 2/3-6/3/15 | 9/3-6/4/15 | 6/4-10/4/15 | 13/4-27/4/15 | 27/4/15 | 28/4-12/5/15 | 13/5-22/5/15 | 25/5--29/5/15 | 1/6-12/6/15 | 15/6-19/6/15 | 22/6-3/7/15 | NA | 6/7-10/7/15 | 13/7 - 17/7/15 | 20/7-31/7/15 | 30/9/15 | 30/11/15
CONDUCT OF4TH NATIONAL STEEL SUMMIT ON STEEL DEVELOPMENT IN NIGERIA | Plan | MMSD/C/04 | LOT 4C | LUMPSUM | NCB | MTB | QCBS | Pre-Qualification | POST -REVIEW | 26/1-6/2/15 | 9/2-13/2/15 | 16/2-2/3/15 | 2/3-6/3/15 | 9/3-6/4/15 | 6/4-10/4/15 | 13/4-27/4/15 | 27/4/15 | 28/4-12/5/15 | 13/5-22/5/15 | 25/5--29/5/15 | 1/6-12/6/15 | 15/6-19/6/15 | 22/6-3/7/15 |  | 6/7-10/7/15 | 13/7 - 17/7/15 | 20/7-31/7/15 | 30/9/15 | 30/11/15
PRODUCTION OF METALLURGICAL ACT AND REGULATION | Plan | MMSD/C/05 | LOT5C | LUMPSUM | NCB | MTB | QCBS | Pre-Qualification | POST -REVIEW | 26/1-6/2/15 | 9/2-13/2/15 | 16/2-2/3/15 | 2/3-6/3/15 | 9/3-6/4/15 | 6/4-10/4/15 | 13/4-27/4/15 | 27/4/15 | 28/4-12/5/15 | 13/5-22/5/15 | 25/5--29/5/15 | 1/6-12/6/15 | 15/6-19/6/15 | 22/6-3/7/15 | NA | 6/7-10/7/15 | 13/7 - 17/7/15 | 20/7-31/7/15 | 30/9/15 | 30/11/15
TECHNO-ECONOMIC SURVEY OF RESOURCES AND TECHNOLOGIES FOR THE MANAGEMENT AND DEVELOPMENT OF THE METAL INDUSTRIES IN NIGERIA | Plan | MMSD/C/06 | LOT 6C | LUMPSUM | NCB | MTB | QCBS | Pre-Qualification | POST -REVIEW | 26/1-6/2/15 | 9/2-13/2/15 | 16/2-2/3/15 | 2/3-6/3/15 | 9/3-6/4/15 | 6/4-10/4/15 | 13/4-27/4/15 | 27/4/15 | 28/4-12/5/15 | 13/5-22/5/15 | 25/5--29/5/15 | 1/6-12/6/15 | 15/6-19/6/15 | 22/6-3/7/15 | NA | 6/7-10/7/15 | 13/7 - 17/7/15 | 20/7-31/7/15 | 30/9/15 | 30/11/15
INTERNATIONAL EXHIBITION OF NIGERIAN MINERALS | Plan | MMSD/C/07 | LOT 7C | LUMPSUM | NCB | MTB | QCBS | Pre-Qualification | POST -REVIEW | 26/1-6/2/15 | 9/2-13/2/15 | 16/2-2/3/15 | 2/3-6/3/15 | 9/3-6/4/15 | 6/4-10/4/15 | 13/4-27/4/15 | 27/4/15 | 28/4-12/5/15 | 13/5-22/5/15 | 25/5--29/5/15 | 1/6-12/6/15 | 15/6-19/6/15 | 22/6-3/7/15 | NA | 6/7-10/7/15 | 13/7 - 17/7/15 | 20/7-31/7/15 | 30/9/15 | 30/11/15
PRODUCTION OF ANNUAL JOURNAL ON MINERALS AND METALS | Plan | MMSD/C/08 | LOT8C | LUMPSUM | NCB | MTB | QCBS | Pre-Qualification | POST -REVIEW | 26/1-6/2/15 | 9/2-13/2/15 | 16/2-2/3/15 | 2/3-6/3/15 | 9/3-6/4/15 | 6/4-10/4/15 | 13/4-27/4/15 | 27/4/15 | 28/4-12/5/15 | 13/5-22/5/15 | 25/5--29/5/15 | 1/6-12/6/15 | 15/6-19/6/15 | 22/6-3/7/15 | NA | 6/7-10/7/15 | 13/7 - 17/7/15 | 20/7-31/7/15 | 30/9/15 | 30/11/15
SOURCING OF RAW MATERIALS;BAUXITE,FERRO-ALLOY,FLUXES,BINDERS | Plan | MMSD/C/09 | LOT9C | LUMPSUM | NCB | MTB | QCBS | Pre-Qualification | POST -REVIEW | 26/1-6/2/15 | 9/2-13/2/15 | 16/2-2/3/15 | 2/3-6/3/15 | 9/3-6/4/15 | 6/4-10/4/15 | 13/4-27/4/15 | 27/4/15 | 28/4-12/5/15 | 13/5-22/5/15 | 25/5--29/5/15 | 1/6-12/6/15 | 15/6-19/6/15 | 22/6-3/7/15 | NA | 6/7-10/7/15 | 13/7 - 17/7/15 | 20/7-31/7/15 | 30/9/15 | 30/11/15
GENERATION OF GEOSCIENCE DATA ON GOLD,BARITE,IRON-ORE,COAL,BAUXITE IN NW,NE,NC,SW,SS, BREAKDOWN:- 17a NW - 17b NE - 17C NC- 17d SW - 17e SS- | Plan | MMSD/C/10 | LOT 10C | LUMPSUM | NCB | MTB | QCBS | Pre-Qualification | POST -REVIEW | 26/1-6/2/15 | 9/2-13/2/15 | 16/2-2/3/15 | 2/3-6/3/15 | 9/3-6/4/15 | 6/4-10/4/15 | 13/4-27/4/15 | 27/4/15 | 28/4-12/5/15 | 13/5-22/5/15 | 25/5--29/5/15 | 1/6-12/6/15 | 15/6-19/6/15 | 22/6-3/7/15 | NA | 6/7-10/7/15 | 13/7 - 17/7/15 | 20/7-31/7/15 | 30/9/15 | 30/11/15
ANALYTICAL STUDIES OF STRATEGIC MINERALS | Plan | MMSD/C/11 | LOT 11C | LUMPSUM | NCB | MTB | QCBS | Pre-Qualification | POST -REVIEW | 26/1-6/2/15 | 9/2-13/2/15 | 16/2-2/3/15 | 2/3-6/3/15 | 9/3-6/4/15 | 6/4-10/4/15 | 13/4-27/4/15 | 27/4/15 | 28/4-12/5/15 | 13/5-22/5/15 | 25/5--29/5/15 | 1/6-12/6/15 | 15/6-19/6/15 | 22/6-3/7/15 | NA | 6/7-10/7/15 | 13/7 - 17/7/15 | 20/7-31/7/15 | 30/9/15 | 30/11/15
MONITORING OF STEEL AND ALLUMINIUM INDUSTRY | Plan | MMSD/C/12 | LOT 12 C | LUMPSUM | NCB | MTB | QCBS | Pre-Qualification | POST -REVIEW | 26/1-6/2/15 | 9/2-13/2/15 | 16/2-2/3/15 | 2/3-6/3/15 | 9/3-6/4/15 | 6/4-10/4/15 | 13/4-27/4/15 | 27/4/15 | 28/4-12/5/15 | 13/5-22/5/15 | 25/5--29/5/15 | 1/6-12/6/15 | 15/6-19/6/15 | 22/6-3/7/15 | NA | 6/7-10/7/15 | 13/7 - 17/7/15 | 20/7-31/7/15 | 30/9/15 | 30/11/15

## Mines & Steel Goods
Ministry Of Mines And Steel Dvelopment
Budgetary Year: 2015
|  | Basic Data | [7 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation - Goods
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pro-Qualification | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Arrival of Goods | Inspection/Final Acceptance
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
PROCUREMENT OF IDENTITY CARD MACHINE | Plan | MMSD/G/O1 | LOT 1A | LUMPSUM | NCB | PERM-SEC | LERB | Post-Qualification | POST REVIEW | 26/1-13/2/15 | 16/2-27/2/15 | 2/3-13/3/15 | 16/3-24/4/15 | 24/4/15 | 27/4-8/5/15 | 11/5-22/5/15 | NA | 25/5-29/5/15 | 1/6-5/6/15 | 8/6-19/6/15 | 31/8/15 | 30/9/15
PURCHASE OF 800KVA GENERATOR | Plan | MMSD/G/O2 | LOT 2A | LUMPSUM | NCB | MTB | LERB | Post-Qualification | POST REVIEW | 26/1-13/2/15 | 16/2-27/2/15 | 2/3-13/3/15 | 16/3-24/4/15 | 24/4/15 | 27/4-8/5/15 | 11/5-22/5/15 | NA | 25/5-29/5/15 | 1/6-5/6/15 | 8/6-19/6/15 | 31/8/15 | 30/9/15
PURCHASE OF SECURITY EQUIPMENT | Plan | MMS/G/03 | LOT 3A | LUMPSUM | NCB | MTB | LERB | Post-Qualification | POST REVIEW | 26/1-13/2/15 | 16/2-27/2/15 | 2/3-13/3/15 | 16/3-24/4/15 | 24/4/15 | 27/4-8/5/15 | 11/5-22/5/15 | NA | 25/5-29/5/15 | 1/6-5/6/15 | 8/6-19/6/15 | 31/8/15 | 30/9/15
Total Cost Plan | [7 empty] | Post-Qualification |  | 26/1-13/2/15 | 16/2-27/2/15 | 2/3-13/3/15 | 16/3-24/4/15 | 24/4/15 | 27/4-8/5/15 | 11/5-22/5/15 |  | 25/5-29/5/15 | 1/6-5/6/15 | 8/6-19/6/15 | 31/8/15 | 30/9/15
PURCHASE OF AUTOMATIC VEHICLE SECURITY SCANNER | Plan | MMSD/G/04 | LOT 4A | LUMPSUM | NCB | MTB | LERB | Post-Qualification | POST REVIEW | 26/1-13/2/15 | 16/2-27/2/15 | 2/3-13/3/15 | 16/3-24/4/15 | 24/4/15 | 27/4-8/5/15 | 11/5-22/5/15 | NA | 25/5-29/5/15 | 1/6-5/6/15 | 8/6-19/6/15 | 31/8/15 | 30/9/15
PROCUREMENT OF METALLURGICAL TESTING EQUIPMENT;(A) SULPHUR AND CARBON ANALYSER (5996)(B) UNIVERSAL TESTING MACHINE (1000KN)©PORTABLE ANALYSER (NEWTON XRF)(D)PORTABLE HARDNESS TESTER(HARTIP 3000) | Plan | MMSD/G/05 | LOT 5A | LUMPSUM | NCB | MTB | LERB | Post-Qualification | POST REVIEW | 26/1-13/2/15 | 16/2-27/2/15 | 2/3-13/3/15 | 16/3-24/4/15 | 24/4/15 | 27/4-8/5/15 | 11/5-22/5/15 | NA | 25/5-29/5/15 | 1/6-5/6/15 | 8/6-19/6/15 | 31/8/15 | 30/9/15
PROCUREMENT OF FIELD AND OFFICE EQUIPMENT - PROTECTION KITS HARMFUL WASTE,AFFLUENT AND TOXIC BYE PRODUCTS E.G. NOSE MASK,EYE GOGGLE, HAND GLOVES, SAFETY BOOTS ETC. | Plan | MMSD/G/06 | LOT6A | LUMPSUM | NCB | MTB | LERB | Post-Qualification | POST REVIEW | 26/1-13/2/15 | 16/2-27/2/15 | 2/3-13/3/15 | 16/3-24/4/15 | 24/4/15 | 27/4-8/5/15 | 11/5-22/5/15 | NA | 25/5-29/5/15 | 1/6-5/6/15 | 8/6-19/6/15 | 31/8/15 | 30/9/15

## Mines & Steels Works
Ministry Of Mines And Steel Development
Budget Year: 2015
|  | Basic Data | [7 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation - Works
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pro-Qualification | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 24 weeks
Plan vs Actual
RECLAMATION OF 100 HIGH RISK ABANDONED MINE SITES IN THE COUNTRY FROM Yr 2007 to 2015(3) | Plan | MMSD/W/O1 | LOT 1B | LUMPSUM | NCB | MTB | LERD | Post - Qualification | Post Review | 26/1-13/2/15 | 16/2-27/2/15 | 2/3-13/3/15 | 16/3-24/4/15 | 24/4/15 | 27/4-8/5/15 | 11/5-22/5/15 | NA | 25/5-29/5/15 | 1/6-5/6/15 | 8/6-19/6/15 | 30/10/15 | 30/11/15
PROCUREMENT OF ICT EQUIPMENT AND ESTABLISHMENT OF A WELL EQUIPPED AND STANDARD INFORMATION MANAGEMENT SYSTEM CENTRE | Plan | MMSD/W/02 | LOT2B | LUMPSUM | NCB | MTB | LERD | Post - Qualification | Post Review | 26/1-13/2/15 | 16/2-27/2/15 | 2/3-13/3/15 | 16/3-24/4/15 | 24/4/15 | 27/4-8/5/15 | 11/5-22/5/15 | NA | 25/5-29/5/15 | 1/6-5/6/15 | 8/6-19/6/15 | 30/10/15 | 30/11/15

## Police Affairs works
Ministry/Department/Agency:Ministry of Police Affairs
Budgetary Year: 2015 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Works
Desk Officer/Contact #: |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Pre-or Post Qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
i) Upgrading of Dei-Dei / Jabi Barracks and Provision of Infrastructures, Abuja FCT . | PSD/001/2015 | LOT A1 | Lumpsum | NCB | post | MTB | Plan | Jan 27 - Feb 17 | Feb 18 - Mar 4 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | May 12 - May 26 | Plan | NA | May 27 - June 9 | June 16 | June 16 - 30 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual
ii) Construction of a Central Amoury in Abuja for the Nigeria Police Force. | PSD/002/2015 | LOT A2 | Lumpsum | NCB | post | MTB | Plan | Jan 27 - Feb 17 | Feb 4 - 17 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | May 12 - May 26 | Plan | NA | May 27 - June 9 | June 16 | June 16 - 30 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual
iii) Renovation and Upgrading of Police Force Headquarters; renovation and completion of SPO'S quarters in Owerri. | PSD/003/2015 | LOTA 3 | Lumpsum | NCB | Post | MTB | Plan | jan 27 - Feb 17 | Feb 4 - 17 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | May 12 - May 26 | Plan | NA | May 27 - June 9 | June 16 | June 16 - 30 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual
iv)Construction of National Secretariat of the PCRC IN a Abuja. | PSD/004/2015 | LOT A4 | Lumpsum | NCB | Post | MTB | Plan | jan 27 - Feb 17 | Feb 4 - 17 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | May 12 - May 26 | Plan | NA | May 27 - June 9 | une 16 | June 16 - 30 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual
Perimeter fencing and renovation of Divisional Police Office at Irrua, Esan Central L.G.A, Edo State. | PSD/005/2015 | LOT A5 | Lumpsum | NCB | Post | MTB | Plan | jan 27 - Feb 17 | Feb 4 - 17 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | May 12 - May 26 | Plan | NA | May 27 - June 9 | une 16 | June 16 - 30 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual
Construction of 3N0. Block of 8 flats 4B/R Each at SPO's Quarters Asokoro | PSD/006/2015 | LOT A6 | Lumpsum | NCB | Post | MTB | Plan | jan 27 - Feb 17 | Feb 4 - 17 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | May 12 - May 26 | Plan | NA | May 27 - June 9 | May 19 - 26 | May 27-June 7 | Nov 30 | Dec 14
|  | + |  |  |  |  | Actual | [7 empty] | Actual
vii) Construction and Equiping of a Police Station in Odemu, Osun State. | PSD/007/2015 | LOT A7 | Lumpsum | NCB | Post | MTB | Plan | jan 27 - Feb 17 | Feb 4 - 17 | NA | Mar 9 - Apr 208 | Apr 20 | Apr 21- May 12 | May 12 - May 26 |  | NA | May 27 - June 9 | May 19 - 26 | May 27-June 7 | Nov 30 | Dec 14
Actual
Completin of the Rehabilitation of 5No. Blocks of SPO's Quarters, Maitama, Abuja. | PSD/008/2015 | LOTA 8 | Lumpsum | NCB | Post | MTB | Plan | jan 27 - Feb 17b 3 | Feb 4 - 17 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | Apr 21 -May 2 | Plan | NA | May 27 - June 9 | May 19 - 26 | May 27-June 7 | Nov 30 | Dec 14
Actual
Construction of Police Station in Ugbonla, Iiaje L.G.A Iiaje L.G.A, Ondo Stae. | PSD/009/2015 | LOT A9 | Lumpsum | NCB | Post | MTB |  | Jan 27 - Feb 17b 3 | Feb 4 - 17 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | Apr 21- May 12 | Plan | NA | May 27 - June 9 | May 19 - 26 | May 27-June 7 | Nov 30 | Dec 14
Actual
Construction of vault and Procurement of File Racks and shelves for Archival Storage of ProcurementDocument and Records |  | LOTA10 | Lumpsum | NCB | POST | MTB | Plan | Jan 27 - Feb 17 | Feb 4 - 14 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | Apr 21- May 12 | Plan | NA | May 27 - June 9 | May 19 - 26 | May 27-June 7 | Nov 30 | Dec 14

## Police Affairs Goods
Ministry/Department/Agency:Ministry of Police Affairs
Budgetary Year: 2015 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Goods
Desk Officer/Contact #: |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Pre-or Post Qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Provision of Library Service to Police Secondry Schools in Kano, Katsina,Zamfara, Minna, Rivers, Cross River, Akwa Ibom, Imo and Ondo at N5M per School.. | MPA003000157 | LOT B1 | Lumpsum |  | POST | MTB | Plan | Jan 27 - Feb 17 | Feb 4 - 17 | NA | FMar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | Apr 21- May 12 | Plan | NA | May 27 - June 9 | May 19 - 26 | May 27-June 7 | Nov 30 | Dec 14
|  |  |  | NCB |  |  | Actual | [7 empty] | Actual
Purchase of books on policing and security for Headquater Library. | MPA003000152 | LOT B2 | Lumpsum | NCB | POST | MTB | Plan | Jan 27 - Feb 17 | Feb 4 - 17 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | Apr 21- May 12 | Plan | NA | May 27 - June 9 | May 19 - 26 | May 27-June 7 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual
Completion of the purchase of Office Furniture and Equipment for Hqtrs and 36 States Offices and Abuja. | MPA001000146 | LOT B3 | Lumpsum | NCB | POST | MTB | Plan | Jan 27 - Feb 17 | Feb 4 - 14 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | Apr 21- May 12 | Plan | NA | May 27 - June 9 | June 10 - 24 | May 27-June 7 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual
Purchase of Security Equipment. | MPA004000160 | LOT B4 | Lumpsum | NCB | POST | MTB | Plan | Jan 27 - Feb 17 | Feb 4 - 14 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | Apr 21- May 12 | Plan | NA | May 27 - June 9 | June 10 - 24 | May 27-June 7 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual
Purchase of 2Nos Modern Hi-Tech Identity Card Machine with Security Features . | MPA001000148 | LOT B5 | Lumpsum | NCB | POST | MTB | Plan | [7 empty] | Plan | NA |  | June 10 - 24 | May 27-June 7 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual

## Police Affairs Consultancy
Ministry/Department/Agency:Ministry of Police Affairs
Budgetary Year: 2015 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Goods
Desk Officer/Contact #: |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Pre-or Post Qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Provision of Library Service to Police Secondry Schools in Kano, Katsina, Zamfara, Minna, Rivers, Cross River, Akwa Ibom, Imo and Ondo at N5M per School. | MPA003000157 | LOT C1 | Lumpsum |  | POST | MTB | Plan | Jan 27 - Feb 17b 3 | Feb 4 - 17 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | Apr 21- May 12 | Plan | NA | May 27 - June 9 | May 19 - 26 | May 27-June 7 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual
Certification and Protection of Police Properties Nationwide. | MPA005000189 | LOT C2 | Lumpsum | NCB | POST | MTB | Plan | Jan 27 - Feb 17b 3 | Feb 4 - 17 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | Apr 21- May 12 | Plan | NA | May 27 - June 9 | May 19 - 26 | May 27-June 7 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual
Development of National Policy on Public Security and Safety. | MPA006000213 | LOT C3 | Lumpsum | NCB | POST | MTB | Plan | Jan 27 - Feb 17b 3 | Feb 4 - 17 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | Apr 21- May 12 | Plan | NA | May 27 - June 9 | May 19 - 26 | May 27-June 7 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual
iii. Development of Policy Framework on Community Policing. | MPA006000230 | LOT C4 | Lumpsum | NCB | POST | MTB | Plan | Jan 27 - Feb 17 | Feb 4 - 14 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | Apr 21- May 12 | Plan | NA | May 27 - June 9 | June 10 - 24 | May 27-June 7 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual
iv. Bi- Annual Police Public Perception and performance Survey in 36 states of the Federation and FCT. | MPA006000233 | LOT C5 | Lumpsum | NCB | POST | MTB | Plan | Jan 27 - Feb 17 | Feb 4 - 14 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | Apr 21- May 12 | Plan | NA | May 27 - June 9 | June 10 - 24 | May 27-June 7 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual
v. Assessment of Police barracks Nationwide. | MPA006000238 | LOT C6 | Lumpsum | NCB | POST | MTB | Plan | Jan 27 - Feb 17 | Feb 4 - 14 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | Apr 21- May 12 | Plan | NA |  | June 10 - 24 | May 27-June 7 | Nov 30 | Dec 14
|  |  | Lumpsum |  |  |  | Actual | [7 empty] | Actual
iv. NPF Election Mornitoring in the Gubernatorial Presidental , Senatorial election and bye- election 2015 by the Ministry in States. | MPA008000266 | LOT C7 | Lumpsum | NCB | POST | MTB | Plan | Jan 27 - Feb 17 | Feb 4 - 14 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | Apr 21- May 12 | Plan | NA | May 27 - June 9 | May 19 - 26 | May 27-June 7 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual
Mornitoring and Evaluation of Police Capital Projects. | MPA008000256 | LOT C8 | Lumpsum | NCB | POST | MTB | Plan | Jan 27 - Feb 17b 3 | Feb 4 - 17 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | Apr 21- May 12 | Plan | NA | May 27 - June 9 | May 19 - 26 | May 27-June 7 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual
Research and Development ( Establishment of Data Base for Police Projects) | MPA006000219 | LOT C9 | Lumpsum | NCB | POST | MTB | Plan | Jan 27 - Feb 17b 3 | Feb 4 - 17 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | Apr 21- May 12 | Plan | NA | May 27 - June 9 | May 19 - 26 | May 27-June 7 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual
Mornitoring and Evaluation of 2015 Capital Budget , Recurrent Budget , Personnel Budget of the Nigeria Police in all police pay Offices, Internally Generated Revenue and 2015 Budget Preparation (MTSS/ Bilateral) and Budget Defence). | MPA008000260 | LOT C10 | Lumpsum | NCB | POST | MTB | Plan | Jan 27 - Feb 17b 3 | Feb 4 - 17 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | Apr 21- May 12 | Plan | NA | May 27 - June 9 | May 19 - 26 | May 27-June 7 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual
Regisration, Encoding and Automated Asset Inventory Management. | MPA007000251 | LOT C11 | Lumpsum | NCB | POST | MTB | Plan | Jan 27 - Feb 17b 3 | Feb 4 - 17 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | Apr 21- May 12 | Plan | NA | May 27 - June 9 | May 19 - 26 | May 27-June 7 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual
Advocacy, Awareness Creation and Enlighenment Campaign on Security, Anti-Corruption, SERVICOM and Legal Bill for Police Reform Trust Fund and Police Academy, Wudil, Kano. | MPA006000226 | LOT C12 | Lumpsum | NCB | POST | MTB | Plan | Jan 27 - Feb 17b 3 | Feb 4 - 17 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | Apr 21- May 12 | Plan | NA | May 27 - June 9 | May 19 - 26 | May 27-June 7 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual
Coordination of Bilateral and Multilateral relations with other Countries in relation with the Nigeria Police. |  | LOT C13 | Lumpsum | NCB | POST | MTB | Plan | Jan 27 - Feb 17b 3 | Feb 4 - 17 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | Apr 21- May 12 | Plan | NA | May 27 - June 9 | May 19 - 26 | May 27-June 7 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual
MPA ( Ministerial Press Briefing). |  | LOT C14 | Lumpsum | NCB | POST | MTB | Plan | Jan 27 - Feb 17b 3 | Feb 4 - 17 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | Apr 21- May 12 | Plan | NA | May 27 - June 9 | May 19 - 26 | May 27-June 7 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual
National Survey on KPIs for NPF in Collaboration with NBS. |  | LOT C15 | Lumpsum | NCB | POST | MTB | Plan | Jan 27 - Feb 17b 3 | Feb 4 - 17 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | Apr 21- May 12 | Plan | NA | May 27 - June 9 | May 19 - 26 | May 27-June 7 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual
PPP Investment and Collaboration Forum; Private Partnership Programme Facilitations, Mornitoring and Evaluation. |  | LOT C16 | Lumpsum | NCB | POST | MTB | Plan | Jan 27 - Feb 17b 3 | Feb 4 - 17 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | Apr 21- May 12 | Plan | NA | May 27 - June 9 | May 19 - 26 | May 27-June 7 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual
Consultancy for the Development of Public Private Partnership Infrastructure/ project Arrangement. |  | LOT C17 | Lumpsum | NCB | POST | MTB | Plan | Jan 27 - Feb 17b 3 | Feb 4 - 17 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | Apr 21- May 12 | Plan | NA | May 27 - June 9 | May 19 - 26 | May 27-June 7 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual
Police Reform Programmes. |  | LOT C18 | Lumpsum | NCB | POST | MTB | Plan | Jan 27 - Feb 17b 3 | Feb 4 - 17 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | Apr 21- May 12 | Plan | NA | May 27 - June 9 | May 19 - 26 | May 27-June 7 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual
Development of National Revenue Guildelines on Police Service . |  | LOT C19 | Lumpsum | NCB | POST | MTB | Plan | Jan 27 - Feb 17b 3 | Feb 4 - 17 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | Apr 21- May 12 | Plan | NA | May 27 - June 9 | May 19 - 26 | May 27-June 7 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual
Quarterly Market Survey and Price Inteligence Surveillance. |  | LOT C20 | Lumpsum | NCB | POST | MTB | Plan | Jan 27 - Feb 17b 3 | Feb 4 - 17 | NA | Mar 9 - Apr 20 | Apr 20 | Apr 21- May 12 | Apr 21- May 12 | Plan | NA | May 27 - June 9 | May 19 - 26 | May 27-June 7 | Nov 30 | Dec 14
[7 empty] | Actual | [7 empty] | Actual

## NCFMIDP
Ministry/Department/Agency: National Commission for Refugees, Migrants and Internally Displaced Persons
Budget Year: 2015
|  | Basic Data | [7 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation - Goods
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Arrival of Goods | Inspection/Final Acceptance
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
Plan vs Actual
PURCHASE OF HEALTH/MEDICAL EQUIPMENT FOR MOBILE CLINIC | Plan | 101 |  | Bills of Quantity | NS | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW
Actual
PROTECTION CARE AND MAINTENANCE/COMMUNITY SERVICES | Plan | 102 |  |  | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | [9 empty] | NA | 18/08/14 - 25/08/14 | 25/08/14 - 29/08/14

## NHRC Goods
NATIONAL HUMAN RIGHTS COMMISSION - 2015 PROCUREMENT PLAN-GOODS
S/N | PROJECT DESCRIPTION | LOT NO | LUMP SUM OR BOQ | PROCUREMENT METHOD | ADVERT FOR PRE-QUALIFICATION | BID INVITATION DATE | BID CLOSING DATE | BID EVALUATION | APPROVAL/ "NO OBJECTION" | AWARD FEC APPROVAL | CONTRACT SIGNING | CONTRACT DURATION
1 | Office equipment for Hqtrs, Zonal and State offices | 1 | BOQ | NCB | 2015-02-02 | 2015-07-13 | 2015-07-27 | 2015-08-06 | 2015-08-14 | NA | 2015-08-18 | 2 Weeks
2 | Office equipment for S/West Zonal Office | 2 | BOQ | PQ | 2015-02-02 | 2015-07-13 | 2015-07-27 | 2015-08-06 | 2015-08-14 | NA | 2015-08-18 | 2 Weeks
3 | Office equipment for S/South Zonal Office | 3 | BOQ | PQ | 2015-02-02 | 2015-07-13 | 2015-07-27 | 2015-08-06 | 2015-08-14 | NA | 2015-08-18 | 2 Weeks
4 | Office equipment for North West Zonal Office | 4 | BOQ | PQ | 2015-02-02 | 2015-07-13 | 2015-07-27 | 2015-08-06 | 2015-08-14 | NA | 2015-08-18 | 2 Weeks
5 | Office equipment for North Central Zonal Office | 5 | BOQ | PQ | 2015-02-02 | 2015-07-13 | 2015-07-27 | 2015-08-06 | 2015-08-14 | NA | 2015-08-18 | 2 Weeks
6 | Office equipment for State Offices | 6 | BOQ | NCB | 2015-02-02 | 2015-07-13 | 2015-07-27 | 2015-08-06 | 2015-08-14 | NA | 2015-08-18 | 2 Weeks
7 | Upgrade of ICT, Zonal Offices | 7 | BOQ | NCB | 2015-02-02 | 2015-04-16 | 2015-04-30 | 2015-05-12 | 2015-05-21 | NA | 2015-05-29 | 2 Weeks
8 | Supply of computers | 8 | BOQ | PQ | 2015-02-02 | 2015-04-16 | 2015-04-30 | 2015-05-12 | 2015-05-21 | NA | 2015-05-29 | 2 Weeks
9 | Installation of scanners, bomb detector and other security equipment to ensure safety and security of lives and property at Zonal Offices | 9 | BOQ | PQ | 2015-02-02 | 2015-04-16 | 2015-04-30 | 2015-05-12 | 2015-05-21 | NA | 2015-05-29 | 2 Weeks
10 | Security equipment for Field Offices | 10 | BOQ | PQ | 2015-02-02 | 2015-04-16 | 2015-04-30 | 2015-05-12 | 2015-05-21 | NA | 2015-05-29 | 2 Weeks

## NHRC Consultancy
NATIONAL HUMAN RIGHTS COMMISSION - 2015 PROCUREMENT PLAN-NON CONSULTANT AND CONSULTANCY SERVICES
S/N | PROJECT DESCRIPTION | LOT NO | LUMP SUM OR BOQ | PROCUREMENT METHOD | ADVERT FOR PRE-QUALIFICATION | BID INVITATION DATE | BID CLOSING DATE | BID EVALUATION | APPROVAL/ "NO OBJECTION" | AWARD FEC APPROVAL | CONTRACT AMOUNT | CONTRACT SIGNING | CONTRACT DURATION
1 | Audit of Public/Corporate buildings and institutions/organisations to determine level of access to persons with disabilities | 1 | LS | Complex Lump Sum | 2015-02-02
2 | Production of Human Rights Resource materials/documents | 2 | LS | Small Assignment LS | 2015-02-02
3 | Production of Newsletter | 3 | LS | PQ | 2015-02-02
4 | Production of Annual Reports | 4 | LS | PQ | 2015-02-02
5 | Production of Human Rights Journal and State of Human Rights in Nigeria Report | 5 | LS | PQ | 2015-02-02
6 | Documentation of the State of Human Rights in Nigeria | 6 | LS | PQ | 2015-02-02
7 | Production/ publication of Prison Audit Report | 7 | LS | PQ | 2015-02-02
8 | Security services Headquarters | 8 | BOQ | NCB | 2015-02-02
9 | Security services Zonal/State Offices | 9 | BOQ | NCB | 2015-02-02
10 | Cleaning services Headquarters | 10 | BOQ | NCB | 2015-02-02
11 | Cleaning services Zonal/State Offices | 11 | BOQ | NCB | 2015-02-02
12 | Cleaning services Headquarters Annex (AMO) | 12 | BOQ | PQ | 2015-02-02
13 | Non-Life Insurance Firm | 13 | BOQ | NCB | 2015-02-02
14 | Group Life Insurance | 14 |  | NCB | 2015-02-02

## NDBDA
Ministry/Department/Agency: | [8 empty] | NIGER DELTA BASIN DEVELOPMENT AUTHORITY, PH
Budgetary Year: 2015 | [9 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: ENGR O.M QUADRI/ 08056026971 |  |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation
Project Description* | Pack No. | Lot N0. | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mob. Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
UNDERGROUND WATER DEVELOPMENT |  |  |  |  | 50000000
Rehabilitation of Sapele Water project (headworks) |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 10000000 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 2500000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
WATER SUPPLY PROJECT AT FIMIE –AMA (TANK & RETICULATION) |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 10000000 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 500000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
WATER SUPPLY PROJECT AT FIMIE-AMA (HEADWORKS) |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 10486502 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 524325.1 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Construction of Treatment Plant at Diebu Town, Southern Ijaw Lga, Bayelsa State |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 12689000 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 2500000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Construction of Treatment Plant at Olugbobiri Town, Southern Ijaw LGA |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 12689000 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 2500000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Extension of Reticulation (750m) at Ojobo Community |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 6348900.1 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 2500000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Construction of Treatment Plant at Egbedi Town, Kolokuma/Opokuma Lga, Bayelsa State |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 12650000 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 4000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Construction of Mini Water Scheme at Ogwashi-Uku In Aniocha South Lga, Delta State |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 20170851.32 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 3000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Construction Of Solar Powered Water Scheme At Okpo-Ama With Reticulation And Treatment Plant |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 19000000 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 4000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Construction Of Solar Powered Water Borehole And Reticulation At Twon Brass Community, Brass Lga |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 18002334 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 4000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Construction of Treatment Plant at Sabagrea, Bayelsa State. |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 12689000 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 3000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Solar Powered Borehole At Ugbeku Community In Delta State |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 2, 312,908.50 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 1500000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Solar Power Borehole At Omoku Ogba Egbema Ndoni Lga, Rivers State |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 6, 500,200.00 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 1500000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Solar Powered Borehole At Oluasi In Nembe Lga Of Bayelsa State |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 12, 641,370.00 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 2000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Solar Power Borehole At Torugbene Town In Burutu Lga, Bayelsa State |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 4, 702,000.00 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 1500000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Provision Of Water Supply Scheme At Ndokwa/Ukuani Federal Constituency, Delta State |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 3502000.01 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 1500000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
MOTORIZED BOREHOLE AT REV. JOSEPH OSOLO'S COMPOUND, ERHIEKEVWE STREET, OFF NUMA CLOSE, EKIUGBO-UGHELLI, DELTA STATE |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 12258102.99 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 3000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
CONSTRUCTION OF 700FT DEEP BOREHOLE AT OLUK-AMA EGBOROMUNG ANDONI LGA IN RIVERS SOUTH EAST SENATORIAL DISTRICT, RIVERS STATE |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 15999999.73 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 3975674.9 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Additional Construction Work On Umuajuloke Water Scheme |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 16000000.8 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 3000000 | Engr Tonye David-West | Hon O.E Beredugo
DEEP BOREHOLE WATER PROJECT IN OPHORIGBALA, OMERWE, OTORIWHREKO, EDHEMOKO, OWRIDO, MEREJE, ENEWARI, IKEBIRI I, IKEBIRI II, OKPOTUWARI, AYAMA OGBIA, OTUOKPOTI |  |  |  |  | 50000000
Deep Borehole At Sampou |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 39522640.4 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 2000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Construction Of Deep Borehole Water Project At Ikebiri 1 Community, Bayelsa State |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 12, 060,745.20 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 7000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Construction of Deep Borehole at Egueama Community, Bayelsa State |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | 6/4/2015 | 18/5/2015 | 5/6/2015 | 12/6/2015 | Plan | 21000000 | N/A | 19/6/2015 | 26/6/2015 | YES | 1ST DEC 2015 | 31ST DEC 2015 | 21000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Construction of Deep Borehole in Amariari-Ama Community Rivers State |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | 6/4/2015 | 18/5/2015 | 5/6/2015 | 12/6/2015 | Plan | 20000000 | N/A | 19/6/2015 | 26/6/2015 | YES | 1ST DEC 2015 | 31ST DEC 2015 | 20000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Small Scale Irrigation Projects structures such as Bunds, Dykes, canals, etc at Isiokpo, Kpong, Egberu in Rivers State, Faudo Onopa, Anyama-Ogbia in Bayelsa State, Eghwu in Delta State, |  |  |  |  | 50000000
Secondary Clearing, Land Preparation and Cultivation of 5ha Pilot Vegetable Farm at Egberu |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 8945000 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 3000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Clearing, Sand Filling and Reclamation of the Site For Proposed Area Office at Fando Onopa, Bayelsa State |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 24711225 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 5000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Reactivation of Ovu Irrigation Project (Land Clearing and Construction of Bunds) Delta State |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 14850000 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 3000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Construction of Farm at Uhweru Irrigation Project |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 11350000 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 3000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Rehabilitation of Generator House and procurement/installation of Generating Set at Kpong Small Scale Irrigation Project |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | 6/4/2015 | 18/5/2015 | 5/6/2015 | 12/6/2015 | Plan | 8000000 | N/A | 19/6/2015 | 26/6/2015 | YES | 1ST DEC 2015 | 31ST DEC 2015 | 8000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Construction of Earth Road including 1 No culvert at Kpong Small Scale Irrigation Project |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | 6/4/2015 | 18/5/2015 | 5/6/2015 | 12/6/2015 | Plan | 6000000 | N/A | 19/6/2015 | 26/6/2015 | YES | 1ST DEC 2015 | 31ST DEC 2015 | 6000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Rehabilitation of poultry house and stocking of poultry farm at Kpong Small Scale Irrigation Project |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | 6/4/2015 | 18/5/2015 | 5/6/2015 | 12/6/2015 | Plan | 9000000 | N/A | 19/6/2015 | 26/6/2015 | YES | 1ST DEC 2015 | 31ST DEC 2015 | 9000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Land preparation and cultivation of Plantain farm at Otuokpoti community, Bayelsa State |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | 6/4/2015 | 18/5/2015 | 5/6/2015 | 12/6/2015 | Plan | 8000000 | N/A | 19/6/2015 | 26/6/2015 | YES | 1ST DEC 2015 | 31ST DEC 2015 | 8000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Rehabilitation of poultry house and stocking of poultry farm at Isiokpo, Rivers State |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | 6/4/2015 | 18/5/2015 | 5/6/2015 | 12/6/2015 | Plan | 5000000 | N/A | 19/6/2015 | 26/6/2015 | YES | 1ST DEC 2015 | 31ST DEC 2015 | 5000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
COMPLETION OF ONGOING REHABILITATION OF HEAD OFFICE BUILDING AT PORT HARCOURT, AREA OFFICE AT ISIOKOLO (DELTA STATE), ACQUISITIION OF SECURITY AND FIRE FIGHTING GADGETS |  |  |  |  | 30000000
Landscaping Of the Head Office Back Premises |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 8766420 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 1383210 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Renovation of Area Office at Isiokolo, Delta State |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 6501783.75 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 4000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Furnishing and Equipping of Head Office at Port Harcourt, Rivers State |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 10466820 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 3000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Furnishing and Equipping Of Area Office At Isiokolo, Delta State |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 5699000 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 2000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Furnishing and Equipping of Area Office at Yenegoa, Bayelsa State |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 5952840 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 2000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Rehabilitation of the Main Head Office Building Roofing Structures & Roof covering, Rivers State |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 30000000 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 10000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Land preparation and cultivation of Cassava/Plantain farm at Isiokolo Area Office, Delta State |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | 6/4/2015 | 18/5/2015 | 5/6/2015 | 12/6/2015 | Plan | 7616790 | N/A | 19/6/2015 | 26/6/2015 | YES | 1ST DEC 2015 | 31ST DEC 2015 | 7616790 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Constructi on of Flood and erosion Control and Drainage Structures at Elibrada, Rumuche, Mgbo-Osi Mission Road (Rivers State), Eteama (Bayelsa State) & Agbarho, Torugbene & Ode-Itsekiri Abonnema Reclamation (Studies) |  |  |  |  | 20000000
Construction of tertiary drainage at Rumuche |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 10082750 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 2000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Const of drainage at Airforce Base PH |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 12000000 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 2000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Study And Design Of And Erosion Control, Land Reclamation, Shore Protection,and Drainage Structures Behind Okirika Grammar School (Ogs) Okirika, Rivers State |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 3412500 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 2000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Study And Design Of And Erosion Control, Land Reclamation, Shore Protection And Drainage Structures At Dawes Island, Rivers State |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 3412500 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 2000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Completion of Agwara Drainage Construction, Rivers State |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 3884752.83 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 2000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Construction of 2km drainage at Eneka Community in Rivers State |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 21916630 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 5000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Construction of 1km Concrete Road at Elejiji in Rivers State |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 18532500 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 5000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
COMPLETION OF ONGOING CONSTRUCTION WORK IN THE LABORATORY BUILDING (ACQUISITION OF LAB EQUIPMENTS) |  |  |  |  | 10000000
Renovation of the Laboratory Building Block C |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 11889548.5 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 2000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
Procurement of Laboratory Reagents |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 7988000 | N/A | N/A | N/A | N/A | 1ST DEC 2015 | 31ST DEC 2015 | 2000000 | Engr Tonye David-West | Hon O.E Beredugo
Actual
Procurement of Laboratory Equipment/Reagents for the Laboratory at the Head office Complex, Port Harcourt |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | 6/4/2015 | 18/5/2015 | 5/6/2015 | 12/6/2015 | Plan | 6000000 | N/A | 19/6/2015 | 26/6/2015 | YES | 1ST DEC 2015 | 31ST DEC 2015 | 6000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
PROJECTS MONITORING/EVALUATION ACTIVITIES |  |  |  |  | 10000000
Project Monitoring/Evaluation Activities of the Authority |  |  | BOQ | OCB |  | N/A | PTB | Plan | N/A | N/A | N/A | 6/4/2015 | 18/5/2015 | 5/6/2015 | 12/6/2015 | Plan | 10000000 | N/A | 19/6/2015 | 26/6/2015 | YES | 1ST DEC 2015 | 31ST DEC 2015 | 10000000 | Engr Tonye David-West | Hon O.E Beredugo
[8 empty] | Actual | [7 empty] | Actual
TOTAL |  |  |  |  | 220000000 | [18 empty] | 220000000

## NCPC
Ministry/Department/Agency: NIGERIAN CHRISTIAN PILGRIMS COMMISSION (NCPC)
Budgetary Year: 2015 | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation | [6 empty] | Contract Implementation
Project Description* | Package Number | Lot Number | Procurement Method | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan | 2 wks | 1 - 2 wks | 3 wks
|  |  |  | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
BOMB JAMMER | NCPC 11004798 |  | NATIONAL COMPETITIVE BIDDING | 6 WKS | PTB | Plan | 2 WKS | 2 WKS | 6 WKS | N/A | 6 WKS | 2 WKS | 1 WK | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
1 UNIT IMPROVISED EXPLOSIVE DEVICE DETECTOR | NCPC 12004810 |  | NATIONAL COMPETITIVE BIDDING | 6 WKS | PTB | Plan | 2 WKS | 2 WKS | 6 WKS | N/A | 6 WKS | 2 WKS | 1 WK | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
CONST./PROVISION OF 5NO. SICK BAYS (PORTAKABINS) FOR MEDICAL SCREENING | NCPC 12004841 |  | NATIONAL COMPETITIVE BIDDING | 6 WKS | PTB | Plan | 2 WKS | 2 WKS | 6 WKS | N/A | 6 WKS | 2 WKS | 1 WK | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual
ADDITIONAL FURNITURE FOR THE HEAD AND ZONAL OFFICES | NCPC 3004712 |  | NATIONAL COMPETITIVE BIDDING | 6 WKS | PTB | Plan | 2 WKS | 2 WKS | 6 WKS | N/A | 6 WKS | 2 WKS | 1 WK | Plan | N/A | N/A | N/A | N/A | N/A | N/A
[6 empty] | Actual | [7 empty] | Actual

## NCPC Consultancy
Ministry/Department/Agency: NCPC
Budgetary Year: 2015 |  | If Post-Review, No-objection Dates are not needed |  |  |  |  | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report
Norm Duration of Proc Steps |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks | 4 wk |  | 3 wks | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
List of Contracts
TO SHOW THE IMPACT OF PILGRIMAGE ON INDIVIDUAL COMMUNITIES AND THE NATION OVER TIME THROUGH EMPIRICAL STUDIES NCPC 13004847 | FIXED BUDGET SELECTION (FBS) | LUMP SUM | PTB | PTB | PTB | PTB | PTB | PTB | PTB | PTB |  | 6 WKS | 6 WKS | 1 WK | N/A | 2 WKS | 1 WK | N/A |  | 2 WKS | N/A | 1 WK | 6 WKS | 1 WK
[6 empty] | Actual | [7 empty] | Actual

## NSCDC Goods
Ministry/Department/Agency: Nigeria Security and Civil Defence Corps
Budget Year: 2015
GOODS |  | Basic Data | [7 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation - Goods
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Arrival of Goods | Inspection/Final Acceptance
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
Plan vs Actual
MATERIAL AND SUPPLIES | Plan
Actual
PROCUREMENT OF 2 NOS OF AMBULLANCE WITH GADGETS FOR EMERGENCY AND DISASTER MANAGEMENT | Plan | GDS001 | 1 | Sch of Del | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 28/01/15 - 11/02/15 | 12/02/15 - 25/02/15 | 2015-02-03 | 16/03/2015 | NA | 20/04/15 | 21/05/15 | 22/05/15 - 05/06/15 | NA | NA | 6/07/15 - 20/07/15 | 22/07/15 - 03/08/15 | NA | 03/08/15- 17/08/15 | 18/08/15 - 31/08/15
| Actual | [8 empty] | NA | NA
PROCUREMENT OF 12Nos. Of PICK-UP VANS WITH GADGETS | Plan | GDS02 | 1 | Sch of Del | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 28/01/15 - 11/02/15 | 12/02/15 - 25/02/15 | 2015-02-03 | 16/03/2015 | NA | 20/04/15 | 21/05/15 | 22/05/15 - 05/06/15 | NA | NA | 6/07/15 - 20/07/15 | 22/07/15 - 03/08/15 | NA | 03/08/15- 17/08/15 | 18/08/15 - 31/08/15
Actual
Actual
PROCUREMENT OF ANTIVANDAL EQUIPMENT- 135 UNITS BINOCULAR DIGITAL CAMERA | Plan | GDS03 | 3 | Sch of Del | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 28/01/15 - 11/02/15 | 12/02/15 - 25/02/15 | 2015-02-03 | 16/03/2015 | NA | 20/04/15 | 21/05/15 | 22/05/15 - 05/06/15 | NA | NA | 6/07/15 - 20/07/15 | 22/07/15 - 03/08/15 | NA | 03/08/15- 17/08/15 | 18/08/15 - 31/08/15
Actual
PROCUREMENT OF ANTIVANDAL EQUIPMENT- 68 NOS MASTER STUN GUN | Plan | GDS003 | 3 | Sch of Del | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 28/01/15 - 11/02/15 | NA | 2015-02-03 | 16/03/2015 | NA | 20/04/15 | 21/05/15 | 22/05/15 - 05/06/15 | NA | NA | 6/07/15 - 20/07/15 | 22/07/15 - 03/08/15 | NA | 03/08/15- 17/08/15 | 18/08/15 - 31/08/15
| Actual | [8 empty] | 28/01/15 - 11/02/15
PROCUREMENT OF COMMUNICATION EQUIPMENT; SERVICE PROVIDER SEGMENTED COST | Plan | GDS004 | 4 | Sch of Del | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 28/01/15 - 11/02/15 | NA | 2015-02-03 | 16/03/2015 | NA | 20/04/15 | 21/05/15 | 22/05/15 - 05/06/15 | NA | NA | 6/07/15 - 20/07/15 | 22/07/15 - 03/08/15 | NA | 03/08/15- 17/08/15 | 18/08/15 - 31/08/15
| Actual | [8 empty] | 28/01/15 - 11/02/15
PROCUREMENT OF COMMUNICATION EQUIPMENT: CALL EQUIPMENT MANAGEMENT PROVIDER | Plan | GDS04 | 4 | Sch of Del | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 28/01/15 - 11/02/15 | 12/02/15 - 25/02/15 | 2015-02-03 | 16/03/2015 | NA | 20/04/15 | 21/05/15 | 22/05/15 - 05/06/15 | NA | NA | 6/07/15 - 20/07/15 | 22/07/15 - 03/08/15 | NA | 03/08/15- 17/08/15 | 18/08/15 - 31/08/15
Actual
PROCUREMENT OF COMMUNICATION EQUIPMENT: SUBSCRIPTION FEE FOR CALL PROGRAMMING PROVIDER | Plan | GDS04 | 4 | Sch of Del | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 28/01/15 - 11/02/15 | 12/02/15 - 25/02/15 | 2015-02-03 | 16/03/2015 | NA | 20/04/15 | 21/05/15 | 22/05/15 - 05/06/15 | NA | NA | 6/07/15 - 20/07/15 | 22/07/15 - 03/08/15 | NA | 03/08/15- 17/08/15 | 18/08/15 - 31/08/15
| Actual | [8 empty] | 28/01/15 - 11/02/15 | 12/02/15 - 25/02/15
PROCUREMENT OF DEFENCE EQUIPMENT : OPERATION EQUIPMENT: 36 NO INDIVIDUAL PROTECTIVE EQUIPMENT | Plan | GDS04 | 4 | Sch of Del | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 28/01/15 - 11/02/15 | 12/02/15 - 25/02/15 | 2015-02-03 | 16/03/2015 | NA | 20/04/15 | 21/05/15 | 22/05/15 - 05/06/15 | NA | NA | 6/07/15 - 20/07/15 | 22/07/15 - 03/08/15 | NA | 03/08/15- 17/08/15 | 18/08/15 - 31/08/15
| Actual | [8 empty] | 28/01/15 - 11/02/15 | 12/02/15 - 25/02/15
PROCUREMENT OF DEFENCE EQUIPMENT : OPERATION EQUIPMENT: 36 NO EXPLOSIVE DETONATOR | Plan | GDS04 | 4 | Sch of Del | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 28/01/15 - 11/02/15 | 12/02/15 - 25/02/15 | 2015-02-03 | 16/03/2015 | NA | 20/04/15 | 21/05/15 | 22/05/15 - 05/06/15 | NA | NA | 6/07/15 - 20/07/15 | 22/07/15 - 03/08/15 | NA | 03/08/15- 17/08/15 | 18/08/15 - 31/08/15
| Actual | [8 empty] | 28/01/15 - 11/02/15 | 12/02/15 - 25/02/15
PROCUREMENT OF DEFENCE EQUIPMENT : OPERATION EQUIPMENT: 1 NO HEDD HAND HELD EXPLOSIVE DEVICE | Plan | GDS04 | 4 | Sch of Del | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 28/01/15 - 11/02/15 | 12/02/15 - 25/02/15 | 2015-02-03 | 16/03/2015 | NA | 20/04/15 | 21/05/15 | 22/05/15 - 05/06/15 | NA | NA | 6/07/15 - 20/07/15 | 22/07/15 - 03/08/15 | NA | 03/08/15- 17/08/15 | 18/08/15 - 31/08/15
| Actual | [8 empty] | 28/01/15 - 11/02/15 | 12/02/15 - 25/02/15
PROCUREMENT OF ARMS AND AMMUNITIONS: 25 NOS AK 47 | Plan | GDS04 | 4 | Sch of Del | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 28/01/15 - 11/02/15 | 12/02/15 - 25/02/15 | NA | NA | NA | 20/04/15 | 21/05/15 | 22/05/15 - 05/06/15 | NA | NA | 6/07/15 - 20/07/15 | 22/07/15 - 03/08/15 | NA | 03/08/15- 17/08/15 | 18/08/15 - 31/08/15
| Actual | [8 empty] | 28/01/15 - 11/02/15 | 12/02/15 - 25/02/15
PROCUREMENT OF ARMS AND AMMUNITIONS: 83 NOS PISTOL | Plan | GDS04 | 4 | Sch of Del | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 28/01/15 - 11/02/15 | 12/02/15 - 25/02/15 | NA | NA | NA | 20/04/15 | 21/05/15 | 22/05/15 - 05/06/15 | NA | NA | 6/07/15 - 20/07/15 | 22/07/15 - 03/08/15 | NA | 03/08/15- 17/08/15 | 18/08/15 - 31/08/15
| Actual | [8 empty] | 28/01/15 - 11/02/15 | 12/02/15 - 25/02/15
PROCUREMENT OF ARMS AND AMMUNITIONS: 138 BOXES OF AMMUNITIONS | Plan | GDS005 | 1 | Sch of Del | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 28/01/15 - 11/02/15 | 12/02/15 - 25/02/15 | NA | NA | NA | 20/04/15 | 21/05/15 | 22/05/15 - 05/06/15 | NA | NA | 6/07/15 - 20/07/15 | 22/07/15 - 03/08/15 | NA | 03/08/15- 17/08/15 | 18/08/15 - 31/08/15
Actual

## NSCDC Works
Ministry/Department/Agency: Nigeria Security and Civil Defence Corps
Budget Year: 2015
WORKS |  | Basic Data | [7 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation - Works
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Plan vs Actual
COMPLETION OF 2 OUT OF 37 STATES COMMANDS HQ (ABEOKUTA AND KATSINA) | Plan | WKS002 | 1 | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 10/11/14 | 17/11/14
Actual
COMPLETION OF 8 NOS STANDARD CLASSROOMS BLOCKS OF 3 CLASSES EACH AT TRAINING SCHOOL LAND DONATED BY OGUN STATE GOVERNMENT. | Plan | WKS003 | 2 | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 10/11/14 | 17/11/14
Actual
COMPLETION OF PHASE 3 ADMINISTRATIVE BLOCK | Plan | WKS004 | 3 | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 10/11/14 | 17/11/14
Actual
COMPLETION OF 6 UNITS OF 3 BEDROOM FLATS OF 2 STOREY BUILDING | Plan | WKS005 | 5 | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 10/11/14 | 17/11/14
Actual
COMPLETION OF 4 UNITS OF 3 BEDROOM FLATS. | Plan | WKS006 | 6 | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 10/11/14 | 17/11/14
Actual
COMPLETION OF 20 UNITS OF 1 BEDROOM FLATS OF 5 STOREY BUIDLING AT SAUKA | Plan | WKS007 | 7 | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 10/11/14 | 17/11/14
Actual
CONTRUCTION/PROVISION OF DEFENCE EQUIPMENT: COMPLETION OF INDOOR SHOOTING RANGE WITH IN-BUILT ARMORY | Plan | WKS013 | 13 | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 10/11/14 | 17/11/14

## NAMA Works
Ministry/Department/Agency: Nigerian Airspace Management Agency
Budget Year: 2015
|  | Basic Data | [7 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation - Works
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Plan vs Actual
procurement and installation of Navigational Aids Equipments (ILS/DME,5CVOR/DME,Signal Analyzer,Tools Boxes and spear parts for benin,Ibadan and Owerri Airport. | Plan | NAMA/PROC/WKS/15 | 24 | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | 12/01/15 | 23/02/15 | 23/02/15 - 27/02/15 | 27/02/15 - 6/03/15 | NA | 6/03/15 - 20/03/15 | 20/03/15 - 24/03/15 | NA | 24/03/15 | 31/03/16
Actual
Rebuilding of additional two warehousees to modem office buildings in the lagos Headquarters Annex and renovation of operational offices | Plan | NAMA/PROC/WKS/15 | 25 | Bills of Quantity | NCB | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | 12/01/15 | 23/02/15 | 23/02/15 - 16/03/15 | 16/03/15 - 31/03/15 | NA | 31/03/15 - 14/04/15 | 14/04/15 - 28/04/15 | NA | NA | 29/04/16
Actual
Procurement and Mnstallation of media Converters ,Multiplexers for Intergration of NAMA PABX network in 10 airports. | Plan | NAMA/Proc/wks/14 | 23 | Bills of Quantity | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 6/01/15 - 27/01/15 | 27/01/15 - 30/01/15 | NA | NA | NA | NA | NA | 30/01/15 | 13/03/15 | 13/03/15 - 31/03/15 | 31/03/15 - 20/04/15 | NA | 20/04/15 - 4/05/15 | 4/05/15 - 18/05/15 | NA | NA | 31/05/16
Actual
Purchase,Installation and Commissioning of Long Distance Radio for Lagos and kano ACCs | Plan | NAMA/Proc/wks/14 | 7 | Bills of Quantity | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | 28/01/15 | 11/03/15 | 11/03/15 - 1/04/15 | 1/04/15 - 29/04/15 | NA | 29/04/15 - 13/05/15 | 13/05/15 - 27/05/15 | NA | NA | 31/05/16
Actual
Safe Tower Equipments | Plan | NAMA/Proc/wks/14 |  | Bills of Quantity | NCB | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | 22/01/15 | 5/03/15 | 5/03/15 - 24/03/15 | 24/03/15 - 21/04/15 | NA | 21/04/15 - 30/04/15 | 30/04/15 - 14/05/15 | NA | NA | 24/05/16
Actual
Purocurement of Spear Parts for Maintenance of Communication,Navigational and Survelance Equipments (CMS) in All Airports | Plan | NAMA/Proc/wks/15 |  | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA
Actual
Maintenance,Replacement and Upgrade of Air-Navigation Facilities in all the Airports (ongoing Project) | Plan | NAMA/Proc/wks/14 | 11 | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | 29/01/15 | 12/03/15 | 12/03/15 - 24/03/15 | 24/03/15 - 21/04/15 | NA | 21/04/15 - 5/05/15 | 5/05/15 - 19/05/15 | NA | NA | 28/08/15
Actual
Safe Tower Equipments (Ongoing Project) | Plan | NAMA/Proc/wks/14 |  | Bills of Quantity | NCB | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW
Actual
Purocurement of Spear Parts for Maintenance of Communication,Navigational and Survelance Equipments (CMS) in All Airports on-Going | Plan | NAMA/Proc/wks/14 |  | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | 22/01/15 | 5/03/15 | 5/03/15 - 24/03/15 | 24/03/15 - 16/04/15 | NA | 16/04/15 - 30/04/15 | 30/04/15 - 14/05/15 | NA | NA | 26/05/16
Actual
AIS/AFTN Automation and AIP/Chart/Map Production (with Redundant MF-TDMA VSAT Network) on Going | Plan | NAMA/Proc/wks/14 |  | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | 30/01/15 - 27/02/15 | 27/02/15 - 13/03/15 | 13/03/15 - 31/03/15 | 31/03/15 - 21/04/15 | 21/04/15 - 2/06/15 | 2/06/15 | 14/07/15 | 14/07/15 - 4/08/15 | 4/08/15 - 21/08/15 | NA | 21/08/15 - 4/09/15 | 4/09/15 - 18/09/15 | NA | NA | 30/09/16
Actual
Upgrade of Lagos,Kano,PHC and Abuja Safe Tower as Ongoing Projects for 2015 | Plan | NAMA/Proc/wks/14 |  | Bills of Quantity | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | 29/01/15 | 12/03/15 | 12/03/15 - 31/03/15 | 31/03/15 - 20/04/15 | NA | 20/04/15 - 4/05/15 | 4/05/15 - 18/05/15 | NA | NA | 24/05/16
Actual
Procurement and Installation of Facility Generators.On-Going 2015 project. | Plan | NAMA/PROC/WKS/15 |  | Bills of Quantity | NCB | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION |  | 21/05/14 - 4/06/14 | 4/06/14 - 18/06/14 | NA | NA | NA |  |  | 25/08/14 | 6/10/14 | 6/10/14 - 20/10/14 | 20/10/14 - 3/11/14 | NA | 3/11/14 - 17/11/14 | 17/11/14 - 28/11/14 | NA | NA | 30/11/15
Actual

## NAMA Goods
Ministry/Department/Agency: Nigerian Airspace Management Agency
Budget Year: 2015
|  | Basic Data | [7 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation - Goods
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Arrival of Goods | Inspection/Final Acceptance
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
Plan vs Actual
Procurement of Electrical,Elecronics and Mechanical Tools Boxes for Lagos,Abuja,PHC and Kano | Plan | NAMA/PROC/GDS/15 | 26 | Bills of Quantity | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | 30/01/15 | 13/03/15 | 13/03/15 - 23/03/15 | 23/03/15 - 31/03/15 | NA | 31/03/15 - 14/04/15 | 14/04/15 - 22/04/15 | NA | 22/04/15 - 29/04/16 | 29/04/16 - 13/05/16
Actual
Procurement of Refridgerators and Airconditioners | Plan | NNAMA/Proc/GDS/14 |  | Sch of Del | NCB | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | 6/01/15 | 17/02/15 | 17/02/15 - 10/03/15 | 10/03/15 - 18/03/15 | NA | 18/03/15 - 27/03/15 | 27/03/15 - 10/04/15 | NA | 10/04/15 - 22/04/16 | 22/04/16 - 6/05/16
Actual
Underground Cable Restructuring and underlay for Navaids and ILS | Plan | NNAMA/Proc/GDS/14 |  | Sch of Del | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION |  | NA | NA | NA | NA | NA | 6/01/15 | 17/02/15 | 17/02/15 - 26/02/15 | 26/02/15 - 6/03/15 | NA | 6/03/15 - 20/03/15 | 20/03/15 - 30/03/15 | NA | 30/03/15 - 31/03/16 | 31/03/16 - 8/04/16
Actual
Procurement of Hand-held Security Scanning Machines and Automated Biometric Access Contorl and Barriers for Enugu,Spkoto, Calabar,Maiduguri and Kaduna on Going Project | Plan | NAMA/Proc/wks/15 |  | Sch of Del | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 28/01/15 - 18/02/15 | 18/02/15 - 4/03/15 | NA | NA | NA | 4/03/15 | 15/04/15 | 15/04/15 - 30/04/15 | 30/04/15 - 19/05/15 | NA | 19/05/15 - 2/06/15 | 2/06/15 - 16/06/15 | NA | 16/06/15 - 23/06/16 | 23/06/16 - 7/07/16
Actual
Ground-Ground Radio for Coordination in Kano FIR. | Plan | nama/proc/Gds/15 |  | Sch of Del | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | 30/01/15 | 13/03/15 | 13/03/15 - 3/04/15 | 3/04/15 - 22/04/15 | NA | 22/04/15 - 6/05/15 | 6/05/15 - 20/05/15 | NA | 20/05/15 - 31/05/16 | 31/05/16 - 14/06/16
Actual
Upgrade of Lagos TRACON Crntre and procurement of Controllers Headset. | Plan | nama/proc/Gds/15 |  | Sch of Del | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | 28/01/15 | 11/03/15 | 11/03/15 - 1/04/15 | 1/04/15 - 29/04/15 | NA | 29/04/15 - 13/05/15 | 13/05/15 - 27/05/15 | NA | 27/05/15 - 31/05/16 | 31/05/16 - 14/06/16
Actual
Provision of Microsoft Enterprise Soft wares,LAN for 18 Airports including WAN integration and network Security and the Procurement of Computing Facilities and Data Centre Servers,Mornitoring and Control System. | Plan | nama/proc/gds/15 | 45 | Bills of Quantity | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 19/05/14 - 2/06/14 | 2/06/14 - 16/06/14 | 16/06/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 28/07/14 | 28/07/14 | 27/08/14 | 27/08/14 - 10/09/14 | 10/09/14 - 24/09/14 | 24/09/14 - 8/10/14 | 15/10/14 - 29/10/14 | 29/10/14 - 12/11/14 | 14/11/14 - 28/11/14
Actual
Procurement of Spare Parts and Accessories for Maintainance of Communication,Navigational and Surveillance Equipments (CNS) in all Airports | Plan | NNAMA/Proc/GDS/14 |  | Sch of Del | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | [6 empty] | 28/11/14 - 12/12/14 | 12/12/14 - 19/12/14 | 19/12/14 - 2/01/15
Actual

## NAMA Consultancy
Ministry/Department/Agency: Nigerian Airspace Management Agency
Budget Year: 2015
|  | Basic Data | [7 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  | Contract Implementation - Consultancy
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2.2 - 2 weeks | 3 weeks | 2 - 4 weeks | 2 weeks | 4 - 6 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
Human Capital Development On-Going Project for 2015 | Plan | nama/proc/con/15 |  | Time-Based | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | NA | POST REVIEW | 27/01/15 - 17/02/15 | 17/02/15 - 27/02/15 | 27/02/15 - 13/03/15 | 13/03/15 - 3/04/15 | 22/04/15 | 22/04/15 - 6/05/15 | 6/05/15 - 17/06/15 | NA | 17/06/15 - 1/07/15 | 1/07/15 - 15/07/15 | 15/07/15 - 29/07/15 | 29/07/15 - 12/08/15 | NA | 12/08/15 - 9/09/15 | NA | 9/09/15 - 23/09/15 | 23/09/15 - 7/10/15 | NA | 7/10/15 | 30/10/15
Actual

## NCAA
NIGERIAN CIVIL AVIATION AUTHORITY
Ministry/Department/Agency: NCAA |  | PROCUREMENT PLAN MAINLINE WITHIN NCAA/MTB THRESHOLD.(FGN) |  |  |  | THE TIME LINE IS TO BE COMPARED WITH THE COUNCILS APPROVAL | [14 empty] | uhtar
Budgetary Year: 2015 |  | IGR CAPITAL PROJECTS |  |  |  |  | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: | Page 1 of 3 | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot No. | Procurement Method | Pre-qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Plan vs. Actual | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  | If Prequalifica tion add 2wks |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 2 - 4 wks | Plan | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks |  | 2 wks
[6 empty] | Actual | [7 empty] | Actual
List of Contracts
Aeromedical Equipment | NA | 1 | NCB | N.A. | PTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
Computerisation: Web-based Video Conferencing/ Telepresence and ICT Upgrade | NA | 2 | NCB | 2 Weeks | MTB/BPP | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
Plant and Machinery | NA | 3 | NCB | 2 Weeks | MTB/BPP | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan |  | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
Office Furniture and Equipment | NA | 4 | NCB | 2 Weeks | MTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
Aircraft Tracking System: Upgrade and Expansion of Automated Realtimne Exceedence Reporting (A GPS based Flight Watch Program) | N.A | 5 | NCB | 2 Weeks | MTB/BPP | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
Performance Based Bnaviation (PBN) Project Support (Development of Geodetic Aerial Mapping and Imagery Data Capture of Obstacles and Obstructions in all the 4 International Airports and all Airports in Navigable Envelop Areas in the Niger Delta Region). | N.A | 6 | NCB | 2 Weeks | MTB/BPP | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
Computerisation of DAAS Operations | NA | 7 | NCB | N.A. | MTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
Server Upgrades | NA | 8 | NCB | N.A. | PTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
Renovation of NCAA Corporate Head Quarters Abuja | NA | 9 | NCB | N.A. | PTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
NCAA Corporate Headquarters, Abuja | NA | 10 | NCB | 2 Weeks | MTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
Professional Services for Financial, Technical, Operational & Human Resources Reviews and Periodic Assessment | NA | 11 | NCB | N.A. | MTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
Distance Explosive Detector Gadgets | NA | 12 | NCB | 2 Weeks | MTB/BPP | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
Aviation Family Centre | NA | 13 | NCB | 2 Weeks | MTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
Automation of Technical File Control Centre (TFCC) for DAWS | NA | 14 | NCB | 2 Weeks | MTB/BPP | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
NIGERIAN CIVIL AVIATION AUTHORITY
Ministry/Department/Agency: NCAA |  | PROCUREMENT PLAN MAINLINE WITHIN NCAA/MTB THRESHOLD.(FGN) |  |  |  | THE TIME LINE IS TO BE COMPARED WITH THE COUNCILS APPROVAL
Budgetary Year: 2015 |  | IGR CAPITAL PROJECTS |  |  |  |  | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: | Page 2 of 3 | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation | [6 empty] | Contract Implementation
Project Description* | Package Number | Lot No. | Procurement Method | Pre-qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Plan vs. Actual | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  | If Prequalifica tion add 2wks |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 2 - 4 wks | Plan | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks |  | 2 wks
[6 empty] | Actual | [7 empty] | Actual
List of Contracts
TOTAL B/FWD | [5 empty] | Plan | [7 empty] | Plan | N.A
[6 empty] | Actual | [7 empty] | Actual
NCAA Achiving System for all Directorates | NA | 15 | NCB | 2 Weeks | MTB/BPP | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan |  | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
Microsoft Enterprise Software License Agreement Plan. | NA | 16 | NCB | 2 Weeks | MTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
Upgrade of NCAA LAN from CAT-5 to CAT-6 | N.A | 17 | NCB | 2 Weeks | MTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
SharePoint 2010 Services across Lagos, Lagos Annex and Abuja | N.A | 18 | NCB | 2 Weeks | MTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
Symantec Backup Services, Network Attached Storage (NAS) Services and Redundant Array of Independent Disks (RAID) and SCSI drive for Servers. | NA | 19 | NCB | N.A. | MTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
Asphalt Overlay Resurfacing of NCAA Lagos Headquarters Lagos. | NA | 20 | NCB | N.A. | PTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
NCAA Archive Building | NA | 21 | NCB | N.A. | PTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
Construction of 2-Storey Building | NA | 22 | NCB | 2 Weeks | MTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
Front Office / Driver's Pool | NA | 23 | NCB | N.A. | MTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
Extention of DAAS Building | NA | 24 | NCB | 2 Weeks | MTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
Remodelling /Upgrade of Facilities at Regional Offices | NA | 25 | NCB | 2 Weeks | MTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
Borehold and Treatment Plants | NA | 26 | NCB | 2 Weeks | MTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
NIGERIAN CIVIL AVIATION AUTHORITY
Ministry/Department/Agency: NCAA |  | PROCUREMENT PLAN MAINLINE WITHIN NCAA/MTB THRESHOLD.(FGN) |  |  |  | THE TIME LINE IS TO BE COMPARED WITH THE COUNCILS APPROVAL
Budgetary Year: 2015 |  | IGR CAPITAL PROJECTS |  |  |  |  | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: | Page 3 of 3 | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation | [6 empty] | Contract Implementation
Project Description* | Package Number | Lot No. | Procurement Method | Pre-qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Plan vs. Actual | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  | If Prequalifica tion add 2wks |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 2 - 4 wks | Plan | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks |  | 2 wks
[6 empty] | Actual | [7 empty] | Actual
List of Contracts
TOTAL B/FWD | [5 empty] | Plan | [7 empty] | Plan | N.A
[6 empty] | Actual | [7 empty] | Actual
Furnishing & equipping of the Renovated Calibration Building (GAT). | NA | 27 | NCB | 2 Weeks | MTB/BPP | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan |  | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
Rehabilitation, Equipping and Furnishing of Office porter- cabin. | NA | 28 | NCB | 2 Weeks | MTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
Renovation of Port-Harcourt Guest House. | N.A | 29 | NCB | 2 Weeks | MTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
CCTV Surveillanne System | N.A | 30 | NCB | 2 Weeks | MTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
Automization of NCAA main Gates & security Gadgets in Lagos. | NA | 40 | NCB | N.A. | MTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
Performance Based Navigation System | NA | 41 | NCB | N.A. | PTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
Ancillary and all Directorates IT Automation | NA | 42 | NCB | N.A. | PTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
Renovation and Rehabilitation of Lagos and Annex Office Buildings | NA | 43 | NCB | 2 Weeks | MTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
Gymnasium Equipment | NA | 44 | NCB | N.A. | PTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
Office Stationeries and Consumables | NA | 45 | NCB | N.A. | PTB | Plan | 2/1/15 - 23/1/15 | 26/1 - 2/2/15 | 2 - 16/2/15 | 2/3/15 - 2/4/15 | 2/4/15 | 2 - 20/4/15 | 20/4/15 - 18/5/15 | Plan | N.A | 4/6-18/6/15 | 18/6-2/7/15 |  |  | 16/7/15
[6 empty] | Actual | [7 empty] | Actual
[6 empty] | Plan | [7 empty] | Plan
[6 empty] | Actual | [7 empty] | Actual
[6 empty] | Plan | [7 empty] | Plan
[6 empty] | Actual | [7 empty] | Actual

## NCAT Goods
Ministry/Department/Agency: Nigerian College of Aviation Technology Zaria | [5 empty] | THE TIME LINE IS TO BE COMPARED WITH THE COUNCILS APPROVAL
Budgetary Year: 2015 | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation | [7 empty] | Contract Implementation
Project Description* | Package Number | Lot Number | Procurement Method | Pre-qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Plan vs. Actual | FEC Approval | Date Contract Offer | Date Contract Signature |  | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks | Plan | 2 wks | 1 - 2 wks | 2 wks |  | 2 - 3 wks | T | 2 wks
|  |  |  | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Purchase of Simulator Spare Parts | NCAT/GDS/DC/2013/001 | LOT 1 | ICB | N/A | PTB | Plan | 22 FEB- 8 MAR-2013 | 8 MAR- 18 MAR 2013 | N/A | 22 MAR- 19 APR 2013 | 19 APR 2013 | 20 APR - 3 MAY | 3 MAY - 17 MAY 2013 | Plan | N/A | 19 MAY- 3 JUN 2013 | 3 JUN- 17 JUN 2013 |  | 18 JUN- 4 JULY 2013 | 27 OCTOBER 2013 | 31 OCTOBER 2013
[6 empty] | Actual | [7 empty] | Actual
Provision of VOR/DME for ILS Flight Training | NCAT/GDS/DC/2014/002 | LOT 1 | DC | N/A | BPP/FEC | Plan | 8-SEPT-2014 | 28 OCT 2014 | N/A | 31 SEPT 2014 | 29 OCT 2014 | 5 NOV 2014 | 12 NOV 2014 | Plan | 26 NOV 2014 | 3 DEC 2014 | 17 DEC 2014 |  | 24 - DEC-2014 | 27 MAY 2016 | 10- JUN 2016
[6 empty] | Actual | [7 empty] | Actual
|  |  | DC |  | MTB | Actual | 14- OCT- 2014 | [5 empty] | 14 NOV 2014 | Actual | 8-DEC-2014 | 9 DEC 2014 | 10 DEC 2014
Refleeting of College Aircraft- Phase I (Supply of 3 DA40 and 2 DA42 Aircrafts) | NCAT/GDS/DC/2013/003 | LOT 1 | DC | N/A | BPP/FEC | Plan | 22 FEB- 8 MAR-2014 | 8 MAR- 18 MAR 2014 | N/A | 22 MAR- 19 APR 2014 | 19 APR 2014 | 20 APR - 3 MAY | 3 MAY - 17 MAY 2014 | Plan | 29- OCT- 2014 | 12 NOV 2014 | 26-NOV-2014 |  | 27 - JAN-2014 | 30 DEC 2016 | 13 JAN 2017
|  |  | DC |  | FEC | Actual | 13- OCT- 2014 | [5 empty] | 29- OCT- 2014 | Actual | 17-DEC-2014 | 24 DEC 2014 | 13 JAN 2015
Provision of Nav Aids VOR/DME for Maintenance Training | NCAT/GDS/DC/2014/003 | LOT 1 | DC | N/A | BPP/FEC | Plan | 8-SEPT-2014 | 28 OCT 2014 | N/A | 31 SEPT 2014 | 29 OCT 2014 | 5 NOV 2014 | 12 NOV 2014 | Plan | 26 NOV 2014 | 3 DEC 2014 | 17 DEC 2014 |  | 28 - DEC-2014 | 27 MAY 2016 | 10- JUN 2016
|  |  | DC |  | MTB | Actual | 14- OCT- 2014 | [5 empty] | 14 NOV 2014 | Actual | 8-DEC-2014 | 9 DEC 2014 | 10 DEC 2014
Purchase and Installation of BOEING737 Simulator | NCAT/GDS/DC/2013/005 | LOT 1 | DC | N/A | BPP/ FEC | Plan | 22 FEB- 8 MAR-2013 | 8 MAR- 18 MAR 2013 | N/A | 22 MAR- 19 APR 2013 | 19 APR 2013 | 20 APR - 3 MAY 2013 | 17 MAY 2014 | Plan | 15 SEPT 2014 | 29 SEPT 2014 | 13 OCT 2014 |  | 5 JAN 2014 | 3 DEC 2016 | 17 DEC 2016
|  |  | DC |  | FEC | Actual | 16- JAN - 2013 | [5 empty] | 20-JAN- 2014 | Actual | 22- OCT- 2014 | 17-NOV-2014 | 17-DEC-2014
Aviation Gas | NCAT/GDS/DC/2014/007 | LOT 1 | DC | N/A | BPP/FEC | Plan | 22 FEB- 8 MAR-2014 | 8 MAR- 18 MAR 2014 | N/A | 22 MAR- 19 APR 2014 | 19 APR 2014 | 20 APR - 3 MAY | 3 MAY - 17 MAY 2014 | Plan | 17 - 31 MAY 2014 | 3 - 14 JUN 2014 | 14 - 28 JUN 2014 |  | 6 JAN 2015 | 4 APRIL 2015 | 18 APRIL 2015
|  |  | DC |  | FEC | Actual | 4- AUG- 2014 | [5 empty] | 03- OCT- 2014 | Actual | 17- DEC- 2014 | 17 DEC 2014 | 18 DEC 2014
Construction of College Perimeter Fence(on-going) | NCAT/WKS/NCB/2010/009 | LOT 5 | NCB | Pre-Qualification | MTB | Plan | 22 FEB - 10 MAR 2010 | N/A | N/A | 25 MAR- 7 MAY 2010 | 7 MAY 2010 | 8 MAY- 30 MAY 2010 |  | Plan | N/A | 7 - 14 FEB2011 | 14 - 21 FEB 2011 | 7 MAR 2011 | 6 JUL 2012 | 5 AUG 2012 | 31 OCTOBER 2013
[6 empty] | Actual |  |  | 29 OCT-12 NOV 2010 | 29 OCT- 26 NOV 2010 | 26 NOV 2010 | 10- DEC- 2010 | 12 JAN 2011 | Actual

## NCAT Works
Ministry/Department/Agency: Nigerian College of Aviation Technology, Zaria
Budgetary Year: 2015 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: |  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Pre-or Post Qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Plan vs. Actual | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
NCAT Annex Enugu,Lagos,Yola and Akwa Ibom | NCAT/WKS/NCB/2014/001 | LOT 1 | BOQ | NCB | Pre Qualification |  | Plan | 4 - 15 MAR 2014 | 18 - 29 MAR 2014 | 2-APR-2014 | 2 APR-14 MAY 2014 | 14 MAY 2014 | 28 MAY 2014 | N/A |  |  | 27 MAY - 7 JUN 2014 | 10 -14 JUN 2014 | 17 - 21 JUN 2014 | 30 OCT 2014 | 30 NOV 2014
[7 empty] | Actual |  |  | 6-DEC-2014
NCAT Flying School Campuses: Uyo, Lagos, Abuja and Enugu | NCAT/WKS/NCB/2014/002 | LOT 1 | BOQ | NCB | Pre Qualification |  | Plan | 4 - 15 MAR 2014 | 18 - 29 MAR 2014 | 2-APR-2014 | 2 APR-14 MAY 2014 | 14 MAY 2014 | 28 MAY 2014 | N/A |  |  | 27 MAY - 7 JUN 2014 | 10 -14 JUN 2014 | 17 - 21 JUN 2014 | 30 OCT 2014 | 30 NOV 2014
[7 empty] | Actual |  |  | 6-DEC-2014
NCAT Liaison ¦Offices: Abuja, Uyo, Lagos and Enugu | NCAT/WKS/NCB/2014/003 | LOT 1 | BOQ | NCB | Post Qualification |  | Plan | 4 - 15 MAR 2014 | 18 - 29 MAR 2014 | 2-APR-2014 | 2 APR-14 MAY 2014 | 14 MAY 2014 | 28 MAY 2014 | N/A |  |  | 27 MAY - 7 JUN 2014 | 10 -14 JUN 2014 | 17 - 21 JUN 2014 | 30 OCT 2014 | 30 NOV 2014
[7 empty] | Actual |  |  | 6-DEC-2014
Completion of Construction of College Perimeter Fence(on-going) | NCAT/WKS/NCB/2010/009 | LOT 5 |  | NCB | Pre-Qualification | MTB | Plan | 22 FEB - 10 MAR 2010 | N/A | N/A | 25 MAR- 7 MAY 2010 | 7 MAY 2010 | 8 MAY- 30 MAY 2010 |  | Plan | N/A | 7 - 14 FEB2011 | 14 - 21 FEB 2011 | 7 MAR 2011 | 6 JUL 2012 | 5 AUG 2012
[7 empty] | Actual |  |  | 29 OCT-12 NOV 2010 | 29 OCT- 26 NOV 2010 | 26 NOV 2010 | 10- DEC- 2010 | 12 JAN 2011 | Actual
Purchase and Installation of BOEING737 Simulator | NCAT/GDS/DC/2013/005 | LOT 1 | 1200000000 | DC |  | FEC | Plan | 22 FEB- 8 MAR-2014 | 8 MAR- 18 MAR 2014 | N/A | 22 MAR- 19 APR 2014 | 19 APR 2014 | 20 APR - 3 MAY 2014 | 3 MAY - 17 MAY 2014 | Plan | 17 - 31 MAY 2014 | 3 - 14 JUN 2014 | 14 - 28 JUN 2014 |  | 12 - JUL-2014 | 27 OCTOBER 2014
[7 empty] | Actual | [7 empty] | Actual
Construction of 250 capacity Cafeteria (On-Going) | NCAT/WKS/NCB/2013/009 | LOT 1 | BOQ | NCB | Post Qualification | PTB | Plan | 4 - 15 MAR 2013 | 18 - 29 MAR 2013 | N/A | 1 - 26 APR 2013 | 2013-04-26 | 29 Apr - 10 May 2013 | 13 - 24 May 2013 | Plan | N/A | 27 MAY - 7 JUN 2013 | 10 -14 JUN 2013 | 17 - 21 JUN 2013 | 30 OCT 2013 | 30 NOV 2013
[7 empty] | Actual | 8-JUL-2013 | 9-JUL-2013 |  | 11-JUL-2013 | 19-AUG-2013 |  | 23-SEPT-2013 | Actual |  | 24-SEPT-2013

## NCAT Consultancy
Budgetary Year: 2015 |  | If Post-Review, No-objection Dates are not needed |  |  |  |  | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | Plan vs. Actual | No-objection Date | FEC Approval | Contract Amount in Naira | Contract Offer | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report
Norm Duration of Proc Steps |  |  |  | Plan | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | Plan | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 1- 2 wk | 2 wks | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
List of Contracts
Consultancy Services for the Design and Supervision of the Resurfacing and Extension of Runway and Taxiway | QCBS | LUMP SUM | PTB | Plan | 3 - 15 FEB 2013 | 17 - 22 FEB 2013 | 25 FEB - 8 MAR 2013 | 11 -15 MAR 2013 | 22 MAR 2013 | 25 - 29 MAR 2013 | Plan | 1 -12 APR 2013 | 12 APR 2013 | 15 - 26 APR 2013 | 29 APR- 3 MAY 2013 | 6 - 10 MAY 2013 | 13 - 17 MAY 2013 | 20 - 24 MAY 2013 | Plan | 27 - 31 MAY 2013 | N/A | 25,000,000.00 | 3 - 7 JUN 2013 | 10 - 14 JUN 2013 | Plan | 17 - 21 JUN 2013 | 1 - 5 JUL 2013 | 31 DEC 2013
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Consultancy Services for the Supervision of Rehabilitation of 3rd Hangar | QCBS | LUMP SUM | FEC | Plan | 3 - 15 FEB 2013 | 17 - 22 FEB 2013 | 25 FEB - 8 MAR 2013 | 11 -15 MAR 2013 | 22 MAR 2013 | 25 - 29 MAR 2013 | Plan | 1 -12 APR 2013 | 12 APR 2013 | 15 - 26 APR 2013 | 29 APR- 3 MAY 2013 | 6 - 10 MAY 2013 | 13 - 17 MAY 2013 | 20 - 24 MAY 2013 | Plan | 27 - 31 MAY 2013 | N/A | 100000000 | 3 - 7 JUN 2013 | 10 - 14 JUN 2013 | Plan | 17 - 21 JUN 2013 | 1 - 5 JUL 2013 | 31 DEC 2013
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Consultancy for Complete Design and Preparation of BEME and Tender Documents on NCAT Flying School Campuses: Uyo,Lagos,Abuja and Enugu. | QCBS | LUMP SUM | NTB | Plan | 3 - 15 FEB 2014 | 17 - 22 FEB 2014 | 25 FEB - 8 MAR 2014 | 11 -15 MAR 2014 | 22 MAR 2014 | 25 - 29 MAR 2014 | Plan | 1 -12 APR 2014 | 12 APR 2014 | 15 - 26 APR 2014 | 29 APR- 3 MAY 2014 | 15 SEPT 2014 | 29 SEPT 2014 | 12 NOV 2014 | Plan | 26 NOV 2014 | 10 DEC 2014 |  | 24 DEC 2014 | 8 JAN 2015 | Plan | 17 JAN 2015 | 1 MAR 2015 | 31 JUN 2015
|  |  |  | Actual |  |  | 31 JUL- 1 AUG 2014 |  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
NCAT Flying School Campuses: Uyo, Lagos, Abuja and Enugu | QCBS | LUMP SUM | NTB | Plan | 3 - 15 FEB 2014 | 17 - 22 FEB 2014 | 25 FEB - 8 MAR 2014 | 11 -15 MAR 2014 | 22 MAR 2014 | 25 - 29 MAR 2014 | Plan | 1 -12 APR 2014 | 12 APR 2014 | 15 - 26 APR 2014 | 29 APR- 3 MAY 2014 | 6 - 10 MAY 2014 | 13 - 17 MAY 2014 | 20 - 24 MAY 2014 | Plan | 27 - 31 MAY 2014 | N/A |  | 3 - 7 JUN 2014 | 10 - 14 JUN 2014 | Plan | 17 - 21 JUN 2014 | 1 - 5 JUL 2014 | 31 DEC 2014
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
NCAT Liaison ¦Offices: Abuja, Uyo, Lagos and Enugu | QCBS | LUMP SUM | NTB | Plan | 3 - 15 FEB 2014 | 17 - 22 FEB 2014 | 25 FEB - 8 MAR 2014 | 11 -15 MAR 2014 | 22 MAR 2014 | 25 - 29 MAR 2014 | Plan | 1 -12 APR 2014 | 12 APR 2014 | 15 - 26 APR 2014 | 29 APR- 3 MAY 2014 | 6 - 10 MAY 2014 | 13 - 17 MAY 2014 | 20 - 24 MAY 2014 | Plan | 27 - 31 MAY 2014 | N/A |  | 3 - 7 JUN 2014 | 10 - 14 JUN 2014 | Plan | 17 - 21 JUN 2014 | 1 - 5 JUL 2014 | 31 DEC 2014
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
|  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
|  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual

## NMA
| Ministry/Department/Agency: Procurement | NIGERIAN METEOROLOGICAL AGENCY
| Budget Year: 2015 | 2015
| - |  | Basic Data | [7 empty] | Draft-Bid Documents |  | Plan vs Actual | Specific Procurement Notice/Advert | Two Stage Tendering |  | Prequalification Evaluation |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation - Works
| Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Plan vs Actual | Advertisement for Pre-Qualification | First Stage Bidding | Second Stage Bidding - Technical/Financial | MDA Approval/No Objection Date | Submission of Prequalification Evaluation Report | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance
S/N | Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks |  | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 2 - 4 weeks | 2 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
1 | Procurement and Installation of Wide Area Network for NiMet Weather Stations Nationwide |  | W-1 | W-001 | WORKS | ongoing | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Actual
2 | Provision of Zonal Synoptic Offices of Idah, Kano and Ibadan Metropolis to accommodate Rainfall, Climate, Flood, Air Quality/ Zonal and Desertification Monitoring Services |  | W-2 | W-002 | WORKS | OCB | PTB | LERB | NA | NA | 5/1/2015 - 26/1/2015 | 26/1/2015 - 9/2/2015 | Plan | NA | NA | NA | NA | NA | 6/4/2015- 18/5/2015 | 18/5/2015 | 18/5/2015 - 8/6/2015 | 2015-06-08 | NA | 15/6/2015 - 29/6/2015 | 29/6/2015 - 13/7/2015 | 13/7/2015 - 3/8/2015 | 30th Nov. 2015 | 2015-07-12

## OHCSF
Office of the Head of Civil Service of the Federation (OHCSF) Procurement Plan-Goods
Budgetary Year:2015 | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact: |  | BASIC DATA | [6 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Description* | Package Number | Lot Number | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | FEC Approval | Date Contract Offer | Date Contract Signature |  | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  | If Prequalification |  | Plan | 2- 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 -2 wks | Plan | 2 wks | 1-2wks | 3 wks
|  |  |  | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
PURCHASE OF OFFICE STATIONERIES/COMPUTER CONSUMABLE | HCSF/CSO/PROC/NCB/15/01 | 2 | NCB | Post | Post | Plan | 4 May,15 | N/A | N/A | 18 May, 15 | 15 June, 15 | 29 June, 15 | N/A | Plan | N/A | 13 July, 15 | 3 Aug, 15 | Plan | N/A | 17 Aug, 15 | 24 Aug, 15
|  |  |  | ' '' |  | Actual | [7 empty] | Actual |  |  |  | Actual
BOOKS | HCSF/CSO/PROC/NCB/15/02 | 1 | NCB | Post | Post | Plan | 4 May,15 | N/A | N/A | 18 May, 15 | 15 June, 15 | 29 June, 15 | N/A | Plan | N/A | 13 July, 15 | 3 Aug, 15 | Plan | N/A | 17 Aug, 15 | 24 Aug, 15
[6 empty] | Actual | [7 empty] | Actual |  |  |  | Actual
PRINTING OF NON SECURITY DOCUMENTS | HCSF/CSO/PROC/NCB/15/03 | 1 | NCB | Post | Post | Plan | 4 May,15 | N/A | N/A | 18 May, 15 | 15 June, 15 | 29 June, 15 | N/A | Plan | N/A | 13 July, 15 | 3 Aug, 15 | Plan | N/A | 17 Aug, 15 | 24 Aug, 15
[6 empty] | Actual | [7 empty] | Actual |  |  |  | Actual
PRINTING OF SECURITY DOCUMENTS | HCSF/CSO/PROC/NCB/15/04 | 1 | NCB | Post | Post | Plan | 4 May,15 | N/A | N/A | 18 May, 15 | 16 June, 15 | 30 June, 15 | N/A | Plan | N/A | 14 July, 15 | 4 Aug, 15 | Plan | N/A | 18 Aug, 15 | 25 Aug, 15
[6 empty] | Actual | [7 empty] | Actual |  |  |  | Actual
TEACHING AIDS/ INSTRUCTION MATERIALS | HCSF/CSO/PROC/NCB/15/05 | 1 | NCB | Post | Post | Plan | 4 May,15 | N/A | N/A | 18 May, 15 | 16 June, 15 | 30 June, 15 | N/A | Plan | N/A | 14 July, 15 | 4 Aug, 15 | Plan | N/A | 18 Aug, 15 | 25 Aug, 15
[6 empty] | Actual | [7 empty] | Actual |  |  |  | Actual
EMPLOYMENT OF CONTRACTORS FOR THE MAINTENANCE OF OFFICE BUILDING/RESIDENTIAL QUARTERS | HCSF/CSO/PROC/NCB/15/06 | 4 | NCB | Post | Post | Plan | 16 June, 15 | N/A | N/A | 30 June, 15 | 28 July, 15 | 11 Aug, 15 | N/A | Plan | N/A | 25 Aug, 15 | 15 Sept, 15 | Plan | N/A | 29 Sept, 15 | 6 Oct, 15
[6 empty] | Actual | [7 empty] | Actual |  |  |  | Actual
MAINTENANCE OF OFFICE/ IT EQUIPMENTS | HCSF/CSO/PROC/NCB/15/07 | 1 | NCB | Post | Post | Plan | 4 May,15 | N/A | N/A | 18 May, 15 | 16 June, 15 | 30 June, 15 | N/A | Plan | N/A | 14 July, 15 | 4 Aug, 15 | Plan | N/A | 18 Aug, 15 | 25 Aug, 15
[6 empty] | Actual | [7 empty] | Actual |  |  |  | Actual
MAINTENANCE OF PLANTS/GENERATORS | HCSF/CSO/PROC/NCB/15/08 | 1 | NCB | Post | Post | Plan | 16 June, 15 | N/A | N/A | 30 June, 15 | 28 July, 15 | 11 Aug, 15 | N/A | Plan | N/A | 25 Aug, 15 | 15 Sept, 15 | Plan | N/A | 29 Sept, 15 | 6 Oct, 15
[6 empty] | Actual | [7 empty] | Actual |  |  |  | Actual
EMPLOYMENT OF CONTRACTORS FOR THE MAINTENANCE OF ELEVATORS | HCSF/CSO/PROC/NCB/15/09 | 4 | NCB | Post | Post | Plan | 16 June, 15 | N/A | N/A | 30 June, 15 | 28 July, 15 | 11 Aug, 15 | N/A | Plan | N/A | 25 Aug, 15 | 15 Sept, 15 | Plan | N/A | 29 Sept, 15 | 6 Oct, 15
[6 empty] | Actual | [7 empty] | Actual |  |  |  | Actual
OTHER MAINTENANCE SERVICES | HCSF/CSO/PROC/NCB/15/10 | 1 | NCB | Post | Post | Plan | 7 July, 15 | N/A | N/A | 21 July, 15 | 18 Aug, 15 | 1 Sept, 15 | N/A | Plan | N/A | 15 Sept, 15 | 6 Oct, 15 | Plan | N/A | 20 Oct, 15 | 27 Oct, 15
[6 empty] | Actual | [7 empty] | Actual |  |  |  | Actual
PLANT/GENERATOR FUEL COST | HCSF/CSO/PROC/NCB/15/11 | 1 | NCB | Post | Post | Plan | 4 May,15 | N/A | N/A | 18 May, 15 | 15 June, 15 | 29 June, 15 | N/A | Plan | N/A | 13 July, 15 | 3 Aug, 15 | Plan | N/A | 17 Aug, 15 | 24 Aug, 15
[6 empty] | Actual | [7 empty] | Actual |  |  |  | Actual

## PSC Non Consultancy
Non Consultancy Services
Procurement plan for fiscal year 2015
SN | Title of Bid | Source of funds | Procurement method | Plan vs Actual | Terms of Reference |  | Request for Expression of interest (REOI) |  | Shortlist and Approval | Request for Proposal (RFP) |  |  |  | Evaluation Report |  | Notification and Contract signing | Contract Execution
[5 empty] | Preparation | Approval | Issuing Date | Submission Date |  | Preparation | Approval | Invitation | Proposal submission/opening | Preparation | Approval |  | Start | End
1 | Provision of Office Cleaning Services | Budgetary Allocation | National Competitive Bidding | Plan | 2015-03-05 | 2015-03-09 | 2015-03-13 | 2015-04-03 | 2015-04-13 | 2015-03-05 | 2015-03-09 | 2015-04-20 | 2015-05-11 | 2015-05-22 | 2015-05-29 | 2015-06-05 | 2015-06-11 | 2015-09-10
Actual
2 | Provision of Vehicles and Transport Maintenance Services | Budgetary Allocation | National Competitive Bidding | Plan | 2015-02-13 | 2015-02-17 | 2015-02-24 | 2015-03-16 | 2015-03-27 | 2015-02-13 | 2015-02-17 | 2015-04-03 | 2015-05-01 | 2015-05-11 | 2015-05-16 | 2015-05-25 | 2015-05-29 | 2015-06-29
Actual
3 | Provision of Generator Maintenance and Repair Services | Budgetary Allocation | National Competitive Bidding | Plan | 2015-02-06 | 2015-02-13 | 2015-02-20 | 2015-03-20 | 2015-03-30 | 2015-02-06 | 2015-02-13 | 2015-04-06 | 2015-05-04 | 2015-05-11 | 2015-05-18 | 2015-06-04 | 2015-06-11 | 2015-07-09
Actual
4 | Provision of Security Services | Budgetary Allocation | National Competitive Bidding | Plan | 2015-02-06 | 2015-02-13 | 2015-02-20 | 2015-03-20 | 2015-03-30 | 2015-02-06 | 2015-02-13 | 2015-04-06 | 2015-05-04 | 2015-05-11 | 2015-05-18 | 2015-06-04 | 2015-06-11 | 2015-07-09
Actual
4 | Provision of Office Furniture maintenance services | Budgetary Allocation | National Competitive Bidding | Plan | 2015-02-13 | 2015-02-17 | 2015-02-24 | 2015-03-16 | 2015-03-27 | 2015-02-13 | 2015-02-17 | 2015-04-03 | 2015-05-01 | 2015-05-11 | 2015-05-16 | 2015-05-25 | 2015-05-29 | 2015-06-29
Actual

## PSC Services
Consultancy Services
Procurement plan for fiscal year 2015
SN | Title of Bid | Source of funds | Procurement method | Plan vs Actual | Terms of Reference |  | Request for Expression of interest (REOI) |  | Shortlist and Approval | Request for Proposal (RFP) |  |  |  | Evaluation Report |  | Notification and Contract signature | Contract Execution
[5 empty] | Preparation | Approval | Issuing Date | Submission Date |  | Preparation | Approval | Invitation | Proposal submission/opening | Preparation | Approval |  | Start | End
1 | Financial Consulting | Budgetary Allocation | LSC | Plan | 2015-03-05 | 2015-03-09 | 2015-03-13 | 2015-04-03 | 2015-04-13 | 2015-03-05 | 2015-03-09 | 2015-04-20 | 2015-05-11 | 2015-05-22 | 2015-05-28 | 2015-06-05 | 2015-06-11 | 2015-09-10
Actual
2 | Legal Services | Budgetary Allocation | LSC | Plan | 2015-03-05 | 2015-03-09 | 2015-03-13 | 2015-04-03 | 2015-04-13 | 2015-03-05 | 2015-03-09 | 2015-04-20 | 2015-05-11 | 2015-05-22 | 2015-05-28 | 2015-06-05 | 2015-06-11 | 2015-09-10
Actual
3 | Engineering Services |  |  | Plan | 2015-03-05 | 2015-03-09 | 2015-03-13 | 2015-04-03 | 2015-04-13 | 2015-03-05 | 2015-03-09 | 2015-04-20 | 2015-05-11 | 2015-05-22 | 2015-05-28 | 2015-06-05 | 2015-06-11 | 2015-09-10
Actual
4 | ICT Consulting | Budgetary Allocation | LSC | Plan | 2015-02-13 | 2015-02-17 | 2015-02-24 | 2015-03-16 | 2015-03-27 | 2015-02-13 | 2015-02-17 | 2015-04-03 | 2015-05-01 | 2015-05-11 | 2015-05-15 | 2015-05-25 | 2015-05-29 | 2015-06-29
Actual

## PSC Goods
Goods/Supplies
Procurement plan for fiscal year 2015
SN | Title of tender |  | Qty | Source of funds | Procurement method | Plan vs Actual | Preparation of tender document |  | No' or approval on the tender document |  | Advertsement/ request for quotation | Bid submission/ opening | Bid evaluation | No objection/aproval on evaluation report |  | Notification and contract signing | Contract Execution
[7 empty] | Start | End | BPP | PSC |  |  |  | BPP | PSC |  | Start | End
| printing of Security Documents | 2ND QTR | LS |  | National Shopping | Plan | 2015-05-07 | 2015-05-09 | NA | 2015-05-11 | 2015-05-18 | 2015-06-01 | 2015-06-05 | NA | 2015-06-08 | 2015-06-11 | 2015-06-12 | 2015-06-29
Actual
|  | 4TH QTR |  |  | National Shopping | Plan | 2015-11-02 | 2015-11-03 | NA | 2015-11-06 | 2015-11-09 | 2015-11-23 | 2015-11-26 | NA | 2015-11-30 | 2015-12-03 | 2015-12-04 | 2015-12-17
Actual
| Printing of Non Security documents | 1 Half | LS | Budgetary Allocation | National Shopping | Plan | 2015-05-07 | 2015-05-11 | NA | 2015-05-11 | 2015-05-18 | 2015-06-01 | 2015-06-05 | NA | 2015-06-08 | 2015-06-11 | 2015-06-12 | 2015-06-29
Actual
2 |  | 2 Half | LS |  | National Shopping | Plan | 2015-07-02 | 2015-07-06 | NA | 2015-07-10 | 2015-07-17 | 2015-07-31 | 2015-08-07 | NA | 2015-08-10 | 2015-08-20 | 2015-08-20 | 2015-09-03
Actual
| Purchase of Computer consumables | 1 qtr |  |  | National Shopping | Plan | 2015-03-01 | 2015-03-04 | NA | 2015-03-05 | 2015-03-06 | 2015-03-19 | 2015-03-20 | NA | 2015-03-20 | 2015-03-23 | 2015-03-23 | 2015-04-06
Actual
|  | 2 qtr |  |  | National Shopping | Plan | 2015-06-01 | 2015-06-04 | NA | 2015-06-05 | 2015-06-08 | 2015-06-22 | 2015-06-25 | NA | 2015-06-26 | 2015-06-26 | 2015-06-29 | 2015-07-13
Actual
|  | 3 qtr |  |  | National Shopping | Plan | 2015-09-03 | 2015-09-04 | NA | 2015-09-07 | 2015-09-10 | 2015-09-24 | 2015-09-25 | NA | 2015-09-28 | 2015-09-28 | 2015-10-01 | 2015-10-15
Actual
|  | 4 qtr |  |  | National Shopping | Plan | 2015-12-03 | 2015-12-04 | NA | 2015-12-07 | 2015-12-06 | 2015-12-19 | 2015-12-21 | NA | 2015-12-21 | 2015-12-21 | 2015-12-24 | 2015-01-07
Actual
| Purchase of office Equipment (furniture & motor vehicles) | 1ST QTR |  | Budgetary Allocation | National Shopping | Plan | 2015-02-06 | 2015-02-09 | NA | 2015-02-09 | 2015-02-20 | 2015-03-05 | 2015-03-06 | NA | 2015-03-09 | 2015-03-13 | 2015-03-16 | 2015-03-30
Actual
|  | 2ND QTR |  |  | National Shopping | Plan | 2015-04-02 | 2015-04-09 | BPP | 2015-04-16 | 2015-04-23 | 2015-05-07 | 2015-05-14 | 2015-05-28 |  | 2015-06-01 | 2015-06-01 | 2015-08-31
Actual
|  | 3RD QTR |  |  | National Shopping | Plan | 2015-08-03 | 2015-08-06 | NA | 2015-08-06 | 2015-08-07 | 2015-08-22 | 2015-08-24 | NA | 2015-08-27 | 2015-08-28 | 2015-08-28 | 2015-09-13
Actual
|  | 4TH QTR |  |  | National Shopping | Plan | 2015-10-02 | 2015-10-05 | NA | 2015-10-05 | 2015-10-09 | 2015-10-23 | 2015-10-24 | NA | 2015-10-26 | 2015-10-29 | 2015-10-30 | 2015-11-16
Actual
| Purchase of Books |  | 1 |  | National Shopping | Plan | 2015-10-02 | 2015-10-05 | NA | 2015-10-05 | 2015-10-09 | 2015-10-23 | 2015-10-24 | NA | 2015-10-26 | 2015-10-29 | 2015-10-31 | 2015-11-13
4 | Purchase of office stationaries | 1ST QTR | LS | Budgetary Allocation | National Shopping | Plan | 2015-02-06 | 2015-02-09 | NA | 2015-02-09 | 2015-02-20 | 2015-03-05 | 2015-03-06 | NA | 2015-03-09 | 2015-03-13 | 2015-03-16 | 2015-03-30
Actual
|  | 2ND QTR |  |  | National Shopping | Plan | 2015-05-07 | 2015-05-08 | NA | 2015-05-11 | 2015-05-18 | 2015-06-01 | 2015-06-05 | NA | 2015-06-08 | 2015-06-11 | 2015-06-12 | 2015-06-29
Actual
|  | 3RD QTR |  |  | National Shopping | Plan | 2015-08-03 | 2015-08-06 | NA | 2015-08-06 | 2015-08-10 | 2015-08-22 | 2015-08-24 | NA | 2015-08-27 | 2015-08-28 | 2015-08-31 | 2015-09-13
Actual
|  | 4TH QTR |  |  | National Shopping | Plan | 2015-10-02 | 2015-10-05 | NA | 2015-10-05 | 2015-10-09 | 2015-10-23 | 2015-10-24 | NA | 2015-10-26 | 2015-10-29 | 2015-10-30 | 2015-11-16
Actual

## Science and Technology Works
Ministry/Department/Agency: Planning, Research and Policy Analysis
Budget Year: 2015
|  | Basic Data | [7 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation - Works
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Plan vs Actual
ESTABLISHMENT OF CENTRAL E-LIBARARY | Plan | FMST/PD/012 | 12 | Bills of Quantity | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 10/02/14 - 27/02/14 | 28/02/14 - 14/03/14 | NA | NA | NA | NA | NA | 14/04/14 | 19/05/14 | 20/05/14 - 6/06/14 | 9/06/14 - 27/06/14 | NA | 30/06/14 - 7/07/14 | 8/07/14 - 22/07/14 | 23/07/14 - 11/08/14 | 19/09/14 | 20/10/14
Actual
WARD BASED CLUSTER PROJECTS | Plan | FMST/PD/2015/005 | 5 | Bills of Quantity | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 7/01/13 - 28/01/13 | 29/01/13 - 12/02/13 | NA | NA | NA | NA | NA | 2/04/13 | 14/05/13 | 20/05/13 - 31/05/13 | 3/06/13 - 21/06/13 | NA | 24/06/13 - 8/07/13 | 9/07/13 - 23/07/13 | 23/07/13 - 31/07/13 | 31/10/13 | 15/11/13
Actual
DEVELOPMENT OF NATIONAL SCIENCE AND TECHNOLOGY MUSEUM | Plan | FMST/PD/001 | 1 | Bills of Quantity | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 10/02/14 - 27/02/14 | 28/02/14 - 14/03/14 | NA | NA | NA |  |  | 14/04/14 | 19/05/14 | 20/05/14 - 6/06/14 | 9/06/14 - 27/06/14 | NA | 30/06/14 - 7/07/14 | 8/07/14 - 22/07/14
Actual
KARSHI SOLAR TECHNOLOGY EXPERIMENT | Plan | FMST/PD/004 | 4 |  | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 10/02/14 - 27/02/14 | 28/02/14 - 14/03/14 | NA | NA | NA | NA | NA | 14/04/14 | 19/05/14 | 20/05/14 - 6/06/14 | 9/06/14 - 27/06/14 | NA | 30/06/14 - 7/07/14 | 8/07/14 - 22/07/14 | 23/07/14 - 11/08/14 | 19/09/14 | 20/10/14
Actual
ESTABLISHMENT OF FMST CALL CENTER ON GOVT SERVICE PORTAL | Plan | FMST/PD/008 | 8 |  | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 10/02/14 - 27/02/14 | 28/02/14 - 14/03/14 | NA | NA | NA | NA | NA | 14/04/14 | 19/05/14 | 20/05/14 - 6/06/14 | 9/06/14 - 27/06/14 | NA | 30/06/14 - 7/07/14 | 8/07/14 - 22/07/14 | 23/07/14 - 11/08/14 | 19/09/14 | 20/10/14
Actual
DEVELOPMENT OF SCIENCE AND TECHNOLOGY PARK (S & T PARKS) IN NIGERIA | Plan | 002 | 2 |  | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW
Actual
DEVELOPMENT OF DATABANK OF NIGERIA SCIENTIST, ENGINEERS & TECHNOLOGIST (LOCAL & DIASPORA) | Plan | FMST/2015/003 | 3 |  | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW
Actual
DEVELOPMENT OF INDIGENOUS SCIENCE LABORATORY FOR SECONDARY SCHOOLS | Plan | FMST/PD/2015/15 | 15 |  | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION |  | 21/05/14 - 4/06/14 | 4/06/14 - 18/06/14 | NA | NA | NA |  |  | 25/08/14 | 6/10/14 | 6/10/14 - 20/10/14 | 20/10/14 - 3/11/14 | NA | 3/11/14 - 10/11/14 | 10/11/14 - 24/11/14
Actual

## Science Non consultancy
Ministry/Department/Agency: Planning, Research and Policy Analysis
Budget Year: 2015
|  | Basic Data | [7 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  | Contract Implementation - Consultancy
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2.2 - 2 weeks | 3 weeks | 2 - 4 weeks | 2 weeks | 4 - 6 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
NATIONAL SCIENCE TECHNOLOGY WEEK | Plan | FMST/PD/10 | 10 |  | NCB | Ministerial Tenders Board | LC - Least Cost | POST-QUALIFICATION | POST REVIEW | 6/02/14 - 20/02/14 | 24/02/14 - 7/03/14 | 17/03/14 - 31/03/14 | 7/04/14 - 14/04/14 | 15/04/14 | 17/04/14 - 30/04/14 | 12/05/14 - 26/05/14 | 27/05/14 - 20/06/14 | 23/06/14 - 30/06/14 | 1/07/14 - 15/07/14 | 16/07/14 - 30/07/14 | 31/07/14 - 8/08/14 | 11/08/14 - 22/08/14 | 25/08/14 - 8/09/14 | NA | 15/09/14 - 19/09/14 | 22/09/14 - 6/10/14 | 6/10/14 - 17/10/14 | 31/10/14 | 7/11/14
Actual
INTERNARTIONAL JUNIOR SCIENCE OLYMPIAD (IJSO) EVENT | Plan | FMST/PD/11 | 11 | Time-Based | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 6/02/14 - 20/02/14 | 24/02/14 - 7/03/14 | 17/03/14 - 31/03/14 | 7/04/14 - 14/04/14 | 15/04/14 | 17/04/14 - 30/04/14 | 12/05/14 - 26/05/14 | 27/05/14 - 20/06/14 | 23/06/14 - 30/06/14 | 1/07/14 - 15/07/14 | 16/07/14 - 30/07/14 | 31/07/14 - 8/08/14 | 11/08/14 - 22/08/14 | 25/08/14 - 8/09/14 | NA | 15/09/14 - 19/09/14 | 22/09/14 - 6/10/14 | 6/10/14 - 17/10/14 | 31/10/14 | 7/11/14
Actual
PRESIDENTIAL STANDING COMMITTEE ON INNOVATION AND INVENTION(PSCII) | Plan | FMST/PD/13 | 13 | DL | NCB | Ministerial Tenders Board | LC - Least Cost | POST-QUALIFICATION | POST REVIEW | 6/02/14 - 20/02/14 | 24/02/14 - 7/03/14 | 17/03/14 - 31/03/14 | 7/04/14 - 14/04/14 | 15/04/14 | 17/04/14 - 30/04/14 | 12/05/14 - 26/05/14 | 27/05/14 - 20/06/14 | 23/06/14 - 30/06/14 | 1/07/14 - 15/07/14 | 16/07/14 - 30/07/14 | 31/07/14 - 8/08/14 | 11/08/14 - 22/08/14 | 25/08/14 - 8/09/14 | NA | 15/09/14 - 19/09/14 | 22/09/14 - 6/10/14 | 6/10/14 - 17/10/14 | 31/10/14 | 7/11/14
Actual
NATIONAL CONFERENCE ON SCIENCE AND TECHNOLOGY | Plan | FMST/PD/2015/14 | 14 |  | SSDC | Ministerial Tenders Board | LC - Least Cost | POST-QUALIFICATION | POST REVIEW | [14 empty] | 24/09/14 - 8/10/14 | 8/10/14 - 22/10/14 | 22/10/14 - 5/11/14
Actual
MONITORING AND SUPERVISION OF POST STEP B PROJECTS/ACTIVITIES | Plan | FMST/PD/2015/16 | 16 | DL |  | Ministerial Tenders Board | LC - Least Cost | POST-QUALIFICATION | POST REVIEW | [14 empty] | NA | 3/11/14 - 10/11/14 | 10/11/14 - 24/11/14

## Science Consultancy
Ministry/Department/Agency: Planning, Research and Policy Analysis
Budget Year: 2015
|  | Basic Data | [7 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  | Contract Implementation - Consultancy
Project Description |  | Package Number | Lot Number | Contract Type | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report
Normal duration of procurement Process | [7 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2.2 - 2 weeks | 3 weeks | 2 - 4 weeks | 2 weeks | 4 - 6 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
AUTOMATING OF SELECTED PROCESS AND ACTIVITIES OF FMST AND ITS OPERATION | Plan | FMST/PD/006 | 6 | Time-Based | NCB | Ministerial Tenders Board | LC - Least Cost | POST-QUALIFICATION | POST REVIEW | 6/02/14 - 19/02/14 | 24/02/14 - 7/03/14 | 17/03/14 - 31/03/14 | 7/04/14 - 14/04/14 | 15/04/14 | 17/04/14 - 30/04/14 | 12/05/14 - 26/05/14 | 27/05/14 - 20/06/14 | 23/06/14 - 30/06/14 | 1/07/14 - 15/07/14 | 16/07/14 - 30/07/14 | 31/07/14 - 8/08/14 | 11/08/14 - 22/08/14 | 25/08/14 - 8/09/14 | NA | 15/09/14 - 19/09/14 | 22/09/14 - 6/10/14 | 6/10/14 - 17/10/14 | 31/10/14 | 7/11/14
Actual
SURVEY FOR DETERMINATION OF LEVEL OF EXPROSE TO PESTICIDERSIDS IN FOOD | Plan | FMST/PD/007 | 7 | Time-Based | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 6/02/14 - 19/02/14 | 24/02/14 - 7/03/14 | 17/03/14 - 31/03/14 | 7/04/14 - 14/04/14 | 15/04/14 | 17/04/14 - 30/04/14 | 12/05/14 - 26/05/14 | 27/05/14 - 20/06/14 | 23/06/14 - 30/06/14 | 1/07/14 - 15/07/14 | 16/07/14 - 30/07/14 | 31/07/14 - 8/08/14 | 11/08/14 - 22/08/14 | 25/08/14 - 8/09/14 | NA | 15/09/14 - 19/09/14 | 22/09/14 - 6/10/14 | 6/10/14 - 17/10/14 | 31/10/14 | 7/11/14
Actual
TECHNOLOGY DIFFUSION AND TRANSFER(DTI) | Plan | FMST/PD/009 | 9 |  | NCB | Ministerial Tenders Board | LC - Least Cost | POST-QUALIFICATION | POST REVIEW | 5/02/14 - 19/02/14 | 24/02/14 - 7/03/14 | 17/03/14 - 31/03/14 | 7/04/14 - 14/04/14 | 15/04/14 | 17/04/14 - 30/04/14 | 12/05/14 - 26/05/14 | 27/05/14 - 20/06/14 | 23/06/14 - 30/06/14 | 1/07/14 - 15/07/14 | 16/07/14 - 30/07/14 | 31/07/14 - 8/08/14 | 11/08/14 - 22/08/14 | 25/08/14 - 8/09/14 | NA | 15/09/14 - 19/09/14 | 22/09/14 - 6/10/14 | 6/10/14 - 17/10/14 | 31/10/14 | 7/11/14

## FMF Works
Ministry/Department/Agency: Ministry Of Finance
Budget Year: 2015
|  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Works |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Plan vs Actual
Plan
Purchase of Security Equipment and Accessories (Ongoing - project) | Actual |  |  | Lump Sum | 160000000 | NCS | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | NIL | POST REVIEW |  |  | NIL | N/A | NIL | N/A | N/A | 10th June, 2014 | 5th August 2014 | 18th August, 2014 | Nil | 160000000 | N/A | 27th October, 2014 | 27th October, 2014 |  | 27th February, 2015 | 9th September, 2015 | 160000000 | AD (Capital) | D (Procurement)
| Plan | [9 empty] | 20th May, 2015
Rehabilitation/Repairs of office building - (New) | Actual |  |  | Lump Sum | 80000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | NIL | POST REVIEW | 28th May, 2015 | Not Yet | NIL | N/A | NIL | N/A | N/A | 28th August, 2015 | 8th October, 2015 | 15th October, 2015 | Nil | 80000000 | N/A | 30th October, 2015 | 30th October, 2015 |  | 10th October, 2016 | 1 week | 80000000 | AD (Capital) | D (Procurement)
Plan
Rehabilitation of Phase 1 complex (Ongoing - project) | Actual |  |  | Lump Sum | 80000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | NIL | POST REVIEW |  |  | NIL | N/A | NIL | N/A | N/A | 10th June, 2014 | 5th August 2014 | 18th August, 2014 | Nil | 80000000 | N/A |  |  |  | 7th August, 2015 |  | 80000000 | AD (Capital) | D (Procurement)
Plan
Supply and Installation of Perimeter Intrusion Management system and CCTV (Ongoing - project) | Actual |  |  | Lump Sum | 55000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  | POST REVIEW |  |  | NIL | N/A | NIL | N/A | N/A |  |  |  | Nil | 55000000 | N/A | 2nd December, 2013 | 2nd December, 2013 |  | March, 2014 | March, 2014 | 55000000 | AD (Capital) | D (Procurement)
Plan
Supply and Installation of Concrete Barriers/Boulders (Ongoing - project) | Actual |  |  | Bills of Quantity | 25000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  | POST REVIEW |  |  | NIL | N/A | NIL | N/A | N/A |  |  |  |  | 25000000 | N/A | 2nd December, 2013 | 2nd December, 2013 |  | March, 2014 | March, 2014 |  | AD (Capital) | D (Procurement)
Plan
Supply and Installation of motorised gate barrier, car park intrusion management & 2 nos full body scanner (on-going project) | Actual |  |  | Lump Sum | 60000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  | POST REVIEW |  |  | NIL | N/A | NIL | N/A | N/A | 10th June, 2014 | 5th August 2014 | 18th August, 2014 |  | 60000000 | N/A | 23rd October, 2014 | 2th October, 2014 |  |  | 27th February, 2015 |  | AD (Capital) | D (Procurement)
| Plan | [9 empty] | 20th May, 2015
Rehabilitation of Phase 1, i.e. the Fire Systems and Special Services (on-going project) | Actual |  |  | Lump Sum | 60000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  | POST REVIEW | 28th may, 2015 |  | NIL | N/A | NIL | N/A | N/A | 28th August, 2015 | 8th October, 2015 | 15th October, 2015 |  | 60000000 | N/A | 30th October, 2015 | 30th October, 2015 |  | 10th April, 2016 |  |  | AD (Capital) | D (Procurement)
| Plan | [9 empty] | 20th May, 2015
Total Cost Plan
Total Cost Actual |  |  |  |  | 520000000 | [16 empty] | 520000000

## FMF Consultancy
Ministry/Department/Agency: Ministry Of Finance
Budget Year: 2015
|  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2.2 - 2 weeks | 3 weeks | 2 - 4 weeks | 2 weeks | 4 - 6 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
| Plan | [9 empty] | 31st May, 2014 | 7th June, 2014 | 8th July, 2014 | 30th July, 2014 | 8th August, 2014 | 11th August, 2014 | 8th July, 2014 | 9th August, 2014 | 18th August, 2015 |  | 8th October, 2014 | 22nd October, 2014 | 5th November, 2014
Economic Reform Planning Management /Monitoring and Evaluation of FEC Approved Ministry Projects (on-going) | Actual |  | 1 | Lump Sum | 37405262 | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | N/A | POST REVIEW | 16tn May, 2014 | 10th June, 2015 | 10th June, 2014 | 7th August, 2014 | 5th August, 2014 | 25th August 2014 | 10th June, 2014 | 5th August, 2014 | 18th August, 2015 | 14th November, 2014 | 21st October, 2014 | 3rd November, 2014 | 18th November, 2014 | N/A | 37405262 | N/A | [6 empty] | AD (Capital) | D (Procurement)
| Plan | [9 empty] | 16th May, 2014 | 1st July, 2014 | 8th July, 2014 | 30th July, 2014 | 8th August, 2014 | 11th August, 2014 | 8th July, 2014 |  | 2nd October, 2014 | 23rd September, 2014 | 8th October, 2014 | 22nd October, 2014 | 5th November, 2014 |  |  |  | 3rd December, 2014 | 10th December, 2014
Economic Reform Planning Management /Cost-Benefit Analysis of Export Expansion (on-going) | Actual |  | 2 | Lump Sum | 15000000 | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | N/A | POST REVIEW | 31st May, 2014 | 7th June, 2014 | 10th June, 2014 | 7th July, 2014 | 5th August, 2014 | 25th Nov. 2014 | 10th June, 2014 | 5th August, 2014 | 18th August, 2014 | 14th November, 2014 | 21st October, 2014 | 3rd November, 2014 | 18th November, 2014 | N/A | 15000000 | N/A | 9th December, 2014 | 23rd December, 2014 |  |  |  |  | AD (Capital) | D (Procurement)
| Plan | [11 empty] | 8th July, 2014 | 30th July, 2014 | 8th August, 2014 |  | 8th July, 2014 |  |  |  | 8th October, 2014 | 22nd October, 2014 | 5th November, 2014
Economic Reform Planning Management /Assessment of Foreign Direct Investment Inflow (on-going) | Actual |  | 3 | Lump Sum | 18510669 | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | N/A | POST REVIEW | 19tn May, 2014 | 7th June, 2014 | 10th June, 2014 | 7th August, 2014 | 5th August, 2014 | 14th Nov. 2014 | 10th June, 2014 | 5th August, 2014 | 18th August, 2014 | 14th November, 2014 | 21st October, 2014 | 3rd November, 2014 | 18th November, 2014 | N/A | 18510669 | N/A | [6 empty] | AD (Capital) | D (Procurement)
| Plan |  |  |  | 18000000 | [19 empty] | 18000000 |  | 22nd July, 2015 | 30th July, 2015
Domestication of Macro Econometric Model for Revenue Forecasting (New) | Actual |  |  | Lump Sum | 17978500 | NCB | Ministerial Tenders Board | Selective Tendering BPP "No Objection Certificate" obtained. | N/A | POST REVIEW | 16tn May, 2014 | 6th June, 2014 | [11 empty] | 16th December, 2014 | 17978500 |  | 2nd September, 2015 | 10th September, 2015 |  |  |  |  | AD (Capital) | D (Procurement)
| Plan | [9 empty] | 16th May, 2014 | 1st July, 2014 |  |  |  |  | 26th August, 2014 | 9th September, 2014 | 2nd October, 2014
Unified Communication to FMF/Broadband Internet Connectivity Lot-2 Provision of Wifi Devices ETC (on-going) | Actual |  | 2 | Lump Sum | 9800000 | NCB | Ministerial Tenders Board | Least Cost Selection | N/A | POST REVIEW | 31st May, 2014 | 7th July, 2014 | 17th July, 2014 |  | 23rd July, 2014 | 30th July, 2014 | 8th September, 2014 | 22nd Seoptember, 2014 | 16th October, 2014 | 7th Novemeber, 2014 |  | 24th July, 2014 | N/A | N/A | 9800000 | N/A | 9th December, 2014 | 23rd December, 2104 |  |  |  |  | AD (Capital) | D (Procurement)
| Plan |  |  | Lump Sum | 7500000 | NCB |  |  |  |  | 16th May, 2014 | 1st July, 2014 |  |  |  |  | 26th August, 2014 | 9th September, 2014 | 2nd October, 2014
Unified Communication to FMF/Broadband Internet Connectivity Lot-3 Provision of bandwidth Monitoring Solution (on-going) | Actual |  | 3 | Lump Sum | 4800000 | NCB | Accounting Officer: Permanent Secretary | Least Cost Selection | N/A | POST REVIEW | 31st May, 2014 | 7th July, 2014 | 17th July, 2014 |  | 23rd July, 2014 | 30th July, 2014 | 8th September, 2014 | 22nd Seoptember, 2014 | 16th October, 2014 | 7th Novemeber, 2014 |  | 24th July, 2014 | N/A | N/A | 5000000 | N/A | 9th December, 2014 | 23rd December, 2104 |  |  |  |  | AD (Capital) | D (Procurement)
| Plan | [25 empty] | 9th December, 2014 | 23rd December, 2104
Comprehensive Power Protection Solution for FMF Server room (New) | Actual |  |  | Lump Sum | 10000000 | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | N/A | POST REVIEW | [12 empty] | N/A | N/A | 10000000 | N/A | [6 empty] | AD (Capital) | D (Procurement)
| Plan |  |  | Lump Sum | [6 empty] | 20th May, 2015
IFEMIS Content Management (New) | Actual |  |  | Lump Sum | 10000000 | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | N/A | POST REVIEW | 28th May, 2015 |  | 28th August, 2015 |  |  |  | 28th August, 2015 | 8th october,2015 | 15th October, 2015 |  | 23rd October, 2015 | 30th October, 2015 |  | N/A | 10000000 | N/A | 9th November, 2015 | 9th November, 2015 |  |  |  |  | AD (Capital) | D (Procurement)
| Plan |  |  |  | 5000000
Advocacy on Financial Literacy | Actual |  |  | Lump Sum | 4900000 | NCB | Accounting Officer: Permanent Secretary | Least Cost Selection | N/A | POST REVIEW |  |  | 10th Seotember, 2015 |  |  | 23rd September, 2015 |  |  | 16th September, 2015 | 24th September, 2015 |  |  | N/A | N/A | 5000000 | N/A | 30th September, 2015 | 30th September, 2015 |  |  |  |  | AD (Capital) | D (Procurement)
Total Cost Plan
Total Cost Actual