## V.O.N Goods
Ministry/Department/Agency: Voice Of Nigeria
Budget Year: 2014
|  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Goods |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Arrival of Goods | Inspection/Final Acceptance | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
Plan vs Actual
Supply/Installation and Upgrading of VON Information Technology Infrastructure, Supply of Computer hardware, LAN, WAN, VSAT, Computerization of Finance, Admin, Admin Records, Programmes, News and Zonal Offices. | Plan | fmi/von/po1 | 1 | Bills of Quantity | 65000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW
Actual
Provision of News Gathering and Recording Equipment for News, Programmes and Zonal Office | Plan | Fmi/Von/Po2 | 2 | Bills of Quantity | 97500000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW
Actual
Movement of Equipment and Provision of Operational Infrastructure | Plan | fmi/von/po3 | 3 | Bills of Quantity | 129500000 | NCB | BPP issues "No Objection" to award/FEC approves | LERB - LOWEST EVALUATED RESPONSIVE BID | PRE-QUALIFICATION | PRIOR REVIEW
Actual
Total Cost Plan |  |  |  |  | 292000000
Total Cost Actual

## V.O.N Works
Ministry/Department/Agency: Voice Of Nigeria
Budget Year: 2014
|  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Works |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Plan vs Actual
Rehabilitation and Refurbishing of VON Transmitting Station Ikorodu and Aerial Fields Lagos | Plan | fmi/von/po1 | 1 | Bills of Quantity | 142500000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW
Actual
Construction and Upgrading of Public Power supply to the Transmitting Station Abuja, Provision of Generator Set at all the Zonal Offices and Power Sub-station in Ikorodu Lagos | Plan | Fmi/Von/Po2 | 2 | Bills of Quantity | 65000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW
Actual
Construction of Broadcasting Houses/Studio Complex and Corporate Headquaters (On-going) | Plan | fmi/von/po3 | 3 | Bills of Quantity | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW
Actual
Provision of Spare Parts, Upgrading of Equipment, Rehabilitation of Building Infrastructures, Antenna Systems and General Facilities | Plan | fmi/von/po4 | 4 | Bills of Quantity | 65000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW
Actual
Total Cost Plan |  |  |  |  | 472500000
Total Cost Actual

## UPPER BENUE Works
Ministry/Department/Agency: Upper Benue River Basin Development Authority
Budget Year: 2014
|  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Works |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Plan vs Actual
Kiri dam and irrigation(rehabilitation of main canal and dam structure) | Plan | UBR/CAP/2014/1 | 1 | BEME | 0 | NS | Accounting Officer: Permanent Secretary | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW
Actual
YOLA IRRIGATION (Maintenance of irrigation pumps/procurement of irrigation requirements for FY2013 / 2014 dry seasn farming) | Plan | UBR/CAP/2014/3 | 3 | BEME | 41420054.03 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 41420054.03 | Jumai Adi - [Designation: ACAO] | Abubakar Muazu - [Designation: Executive Director Engieering]
| Actual | [24 empty] | NA | NA | NA | NA | NA | NA
KIRI DAM AND IRRIGATION (Rehabilitation of main canal and dam structures) | Plan | UBR/CAP/2014/1 | 1 |  | 829425374.41 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PRE-QUALIFICATION | POST REVIEW | [20 empty] | Abubakar Muazu - [Designation: Executive Director Engieering]
Actual
DUGWABA DAM AND IRRIGATION (Continuation of construction of dam embankment and spillway) | Plan | UBR/CAP/2014/2 | 2 |  | 753753009.4 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PRE-QUALIFICATION | POST REVIEW | [20 empty] | Abubakar Muazu - [Designation: Executive Director Engieering]
Actual
Total Cost Plan |  |  |  |  | 1624598437.84 | [23 empty] | 41420054.03
Total Cost Actual

## R.E.A
| Ministry/Department/Agency: Rural Electrification Agency | [6 empty] | THE TIME LINE IS TO BE COMPARED WITH THE COUNCILS APPROVAL
| Budgetary Year 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
| Desk Officer/Contact: Charles Emeka Ngene, 08033141907 and Bulus Daniel Maiyaki, 08033117757 |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation |  |  | Contract Implementation
| Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Plan vs. Actual | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
| Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 1wk | 2 - 3 wks | T | 2 wks | 2 - 3 wks | T | 2 wks
List of Contracts
1 | Electrification of Aba- Alfa, Araromi and Babaode in Ayiba LGA in Oyo State | REA/CP/14/01 | Lot 1 | 25690571 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
2 | Electrification of Ikere in Iseyin LGA, Oyo State | REA/CP/14/02 | Lot 2 | 41696000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
3 | Electrification of Akinwunmi / Osuogun in Iseyin LGA, Oyo State | REA/CP/14/03 | Lot 3 | 42455150 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
4 | Electrification of Ibaragun / Robinyan in Ifo LGA, Ogun State | REA/CP/14/04 | Lot 4 | 42700000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
5 | Electrification of Mbala / Umuaku/ Amuda / Ndiawa / Umuelen / Ihie / Lomara & Installation of 2 x 7.5MVA 33/11KV at Nkwoagu in Abia | REA/CP/14/05 | Lot 5 | 60000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
6 | Electrification of Umunevo Amagunze / Njiagu Ihuokpara in Enugu State | REA/CP/14/06 | Lot 6 | 37500000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
7 | Electrification improvement in Umuada, Obunaoru and other communities in Ngodoukwu in Abia State | REA/CP/14/07 | Lot 7 | 25000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
8 | Electrification of Ohuhu -Nsulu and Umugo in Isiala Ngwa North LGA in Abia | REA/CP/14/08 | Lot 8 | 25000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
9 | Electrification Project at Amagunze Extension 1 in Enugu State | REA/CP/14/09 | Lot 9 | 21285000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
10 | Electrification of Fota - Riji - Duwa - Yan - Dingam in Gombi LGA, Adamawa State | REA/CP/14/10 | Lot 10 | 30000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
11 | Tenah ITC/TDN in Gombi LGA, Adamawa State | REA/CP/14/11 | Lot 11 | 15000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
12 | Zigayirma, Kwaakah, Mullah & Jabba in Hong LGA, Adamawa State | REA/CP/14/12 | Lot 12 | 30000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
13 | Rehabilitation of Ngamdu - Gotala and Electrification of Dabira, Kaga LGA, Borno State | REA/CP/14/13 | Lot 13 | 35000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
14 | Electrification of Marguba, Kaga LGA, Borno State | REA/CP/14/14 | Lot 14 | 25000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
15 | Electrification of Malumeri, Damboa LGA, Borno State | REA/CP/14/15 | Lot 15 | 22500000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
16 | Electrification of Dongon, Gogadi & Kware Dauiel I Zaru LGA in Kebbi State | REA/CP/14/16 | Lot 16 | 30000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
17 | Electrification of Kunyai - Marsa - Rikawan Zangon Kataf LGA Kaduna State | REA/CP/14/17 | Lot 17 | 25000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
18 | Electrification of Kamantan - Lenak - tudun Wada - Kaform - Kagal - hurgyam - Angwan Laushi - nassarawa - Kar,men - Idung - Kanzir - Tapyeri - Hwukyan Zangon Kataf LGA Kaduna State | REA/CP/14/18 | Lot 18 | 35000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
19 | Electrification of Zonkwa - Kamantan Zangon Kataf LGA Kaduna State | REA/CP/14/19 | Lot 19 | 20000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
20 | Electrification of Ajoko Ipee Community in Oyun L.G.A, Kwara State | REA/CP/14/20 | Lot 20 | 30000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
21 | Electrification of Apata - Aje/Alagboa /Owode - Jankere Communities in asa LGA, Kwara state | REA/CP/14/21 | Lot 21 | 20000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
22 | Electrification of Oke - Ode / Aireke/ Igbo - Ote, Kereaje- Dikko / sani - Koro / Eleyele/ Igbaja -Ogele / magboa & Labaka Extension in Ifelodun LGA, Kwara State | REA/CP/14/22 | Lot 22 | 35000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
23 | Electrification of Alalubosa in Ilorin South LGA, Kwara State | REA/CP/14/23 | Lot 23 | 12500000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
24 | Electrification of Nassarawa Eggon - Mada station in Nassarawa State | REA/CP/14/24 | Lot 24 | 12500000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
25 | Electrification of Andaha - Rinza in Nassarawa | REA/CP/14/25 | Lot 25 | 15000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
26 | Electrification of Gbade - Nakare in Nassarawa State | REA/CP/14/26 | Lot 26 | 15000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
27 | Completion of Bachit Lwa - Shonong in Plateau State | REA/CP/14/27 | Lot 27 | 25000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
28 | Electrification of Fusa - maijuju - Zandi in Plateau State | REA/CP/14/28 | Lot 28 | 30000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
29 | Electrification of Hiktup - Kobwang - Mper in Plateau State | REA/CP/14/29 | Lot 29 | 15000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
30 | Electrification of Lungu in FCT | REA/CP/14/30 | Lot 30 | 25000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
31 | Electrification of Mpape in FCT | REA/CP/14/31 | Lot 31 | 25000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
32 | Electrification of Daki Biyu in FCT | REA/CP/14/32 | Lot 32 | 30000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual
33 | Extension of Electricity to some communities in Niger State | REA/CP/14/33 | Lot 33 | 60000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
34 | Electrification of Obagede/Kpake in Ajaokuta LGA, Kogi State | REA/CP/14/34 | Lot 34 | 22500000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  |  |  | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
35 | Electrification of Pupa Akin Community in Kwara State | REA/CP/14/35 | Lot 35 | 12500000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
36 | Electrification of Ogodo and Alata Communities in Oyun LGA, Kwara State | REA/CP/14/36 | Lot 36 | 19500000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  |  |  | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
37 | Electrification of Ojegbe village, Iyakom oboru community, Oju LGA, Benue State | REA/CP/14/37 | Lot 37 | 12500000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  |  |  | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
38 | Electrification of Harge - Shikaan in Katsina - Ala LGA, Benue State | REA/CP/14/38 | Lot 38 | 15000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
39 | Electrification of Kyado - Mbajir, Katsina Ala LGA, Benue State | REA/CP/14/39 | Lot 39 | 12500000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
40 | Electrification of Adikpo - Sati Mbabanu, Kwande LGA, Benue State | REA/CP/14/40 | Lot 40 | 10000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
41 | IKOT AKPAN SUNG Installation of Transformers and construction of (HT/LT) Lines in Akwa Ibom State | REA/CP/14/41 | Lot 41 | 10544727.088 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
42 | Electrification of Ikot Ide Apakpan in Akwa Ibom | REA/CP/14/42 | Lot 42 | 20000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
43 | Electrification of Mbiokporo 2 in Nsit Ibom LGA, Akwa Ibom | REA/CP/14/43 | Lot 43 | 20000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
44 | Electrification of Urohi - Oke Communities in Esan West LGA, Edo State | REA/CP/14/44 | Lot 44 | 26305753.71 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
45 | Electrification of Agi - Izekor Communities in Igueben LGA, Edo State | REA/CP/14/45 | Lot 45 | 21858637 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
46 | Electrification of rural communities in Esan Central Esan West and Igueben LGA (Oyomo Quarters, Okuemen, Oraede and Isibhelua village), Edo State | REA/CP/14/46 | Lot 46 | 25000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
47 | Electrification of Mkpara - Ndim village in Ikom LGA, Cross River State | REA/CP/14/47 | Lot 47 | 15000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
48 | Electrification of Okosure village in Ikom LGA in Cross River State | REA/CP/14/48 | Lot 48 | 20000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
49 | Rural electrification of Okoroba Ext. ijn Ogbia LGA Bayelsa state | REA/CP/14/49 | Lot 49 | 28264121.28 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual
50 | Rural Electrification of Eboh in Ogbia LGA Bayelsa state | REA/CP/14/50 | Lot 50 | 23645942.32 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
51 | Rehabilitation of Otoabagi-Oluokpokiti-Opune-Otungidi 33KV Line and installation of Distribution Transformers, Bayelsa state | REA/CP/14/51 | Lot 51 | 33470326.4 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
52 | Rural electrification of Elebele-Oruna-Emeya, Bayelsa state | REA/CP/14/52 | Lot 52 | 23208752 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
53 | Rural Electrification of Igwuruta Ali community in Rivers | REA/CP/14/53 | Lot 53 | 21829052 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
54 | Rural Electrification of Ogboza Amanator Autonomous community in Rivers | REA/CP/14/54 | Lot 54 | 23645888 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
55 | Radiation of 37km of 33KV line for power inprovement in Ika North East/South LGA in Delta state | REA/CP/14/55 | Lot 55 | 30315239.04 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
56 | Construction And Rehabilitation Of Angiama-Oporoma And Oporama Hospital-Onyoma-Ekowa North-Ekianbiri-Peremabiri And Peremabiri School. 48km 33kv Line in Bayelsa State | REA/CP/14/56 | Lot 56 | 66439386.3472 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
57 | CONSTRUCTION OF ANGIAMA OTUAN-UMBUGBENE-OGBONGUENE-EGBE PULUGBERE-AKETI-ONDEWARI-KOROKOSEI-IKEINYABIRI-OLUGBOBIRI-KEBIRI-AWIGBENE-OSIAMA-ISONI-AZIA-KASAMA. 38 KM 33KV ITC LINE IN BAYELSA STATE | REA/CP/14/57 | Lot 57 | 92125180.8568 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
58 | CONSTRUCTION AND REHABILITATION OFAGIAMA-ANGIAMA-LUDONU-AGIDIGBENE-ENIWARI-OFONIBIRI-OPUAMA-OPOLOBUGO-DIEBU-PEREMABIRI-BIO AGUABIRI-AGUABIRI-IGEBIRI-OBELELI-ANYAMA-OWEIKOROGHA-IKBIRI AMASOMA. 42KM 33KV ITC IN BAYELSA STATE | REA/CP/14/58 | Lot 58 | 101884463.0552 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
59 | Rural Electrification of Obulu Okiti Community, Delta State | REA/CP/14/59 | Lot 59 | 20588554.896 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
60 | Electrification of Abavo / Ahilagu /Oki / Boji Boji/ Agbor Obi / Emuhu/ Udumebah/ Otolokpo communities in Ika North East, LGA, Delta State | REA/CP/14/60 | Lot 60 | 60000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
61 | Provision and installation of Solar street light in 25 communities in Niger State | REA/CP/14/61 | Lot 61 | 100000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
62 | Provision and Installation of Solar street light in Akpuoga/Onuogba/Obinagu/Uguruoma/Nchotancha in Nike LGA, Enugu State | REA/CP/14/62 | Lot 62 | 30000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
63 | Provision and Installation of Solar street light in 5 rural communities in Onitsha North/ Onitsha South local Government Area, Anambra State. | REA/CP/14/63 | Lot 63 | 30000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
64 | Provision and Installation of 5No. 500KVA 33/.415kv Transformers at Onitsha North / Onitsha South Local Govt. Area, Anambra State | REA/CP/14/64 | Lot 64 | 30000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
65 | Electrification of Ogboji in Orumba North LGA, Anambra | REA/CP/14/65 | Lot 65 | 30000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | Dir. Proc.
66 | Provision and installation of solar street light in Udi Community in Udi LGA, Enugu State | REA/CP/14/66 | Lot 66 | 45000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual
67 | Provision and installation of solar street light in Umuabi community in Udi LGA | REA/CP/14/67 | Lot 67 | 20000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
68 | Provision and installation of solar street light in Nneke Ano/Ugwu Ogo Communities in Enugu East LGA, Enugu State | REA/CP/14/68 | Lot 68 | 25000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | Dir. Proc.
69 | Provision and installation of solar street light in ESUT communities in Agani, Enugu State | REA/CP/14/69 | Lot 69 | 30000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | Dir. Proc.
70 | Provision and installation of solar street light in Amaechi Awkunanaw in Enugu South LGA, Enugu State | REA/CP/14/70 | Lot 70 | 40000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | Dir. Proc.
71 | Provision and installation of solar street light in Oboroke, Okehi LGA, Kogi State | REA/CP/14/71 | Lot 71 | 15000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | Dir. Proc.
72 | Electrfication of township distribution network in Eniwari/Oporoma/Fonibiri/Kainyabiri/Opuama Communities | REA/CP/14/72 | Lot 72 | 40000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | Dir. Proc.
73 | Provision of solar street light at Akwuke/Akwuke Uwani / Isikwe Achi Communities | REA/CP/14/73 | Lot 73 | 15000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | Dir. Proc.
74 | Power Improvement of Umunakanu Owere in Ehime - Mbano LGA from Nkwo Okwe to Umuezeala Ihu with two transformers | REA/CP/14/74 | Lot 74 | 20000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | Dir. Proc.
75 | Power Improvement of Umuaka - Orlu Rural Electrification Project in Imo State | REA/CP/14/75 | Lot 75 | 28000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | Dir. Proc.
76 | Provision of solar street light at Ishiagu in Ebonyi State | REA/CP/14/76 | Lot 76 | 30000000 | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | Dir. Proc.
77 |  | REA/CP/14/77 | Lot 77 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | Dir. Proc.
78 |  | REA/CP/14/78 | Lot 78 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | Dir. Proc.
79 |  | REA/CP/14/79 | Lot 79 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | Dir. Proc.
80 |  | REA/CP/14/80 | Lot 80 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | Dir. Proc.
81 |  | REA/CP/14/81 | Lot 81 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | Dir. Proc.
82 |  | REA/CP/14/82 | Lot 82 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
83 |  | REA/CP/14/83 | Lot 83 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | Dir. Proc.
84 |  | REA/CP/14/84 | Lot 84 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | Dir. Proc.
85 |  | REA/CP/14/85 | Lot 85 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual
86 |  | REA/CP/14/86 | Lot 86 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14 |  |  | DD. Proc. | Dir. Proc.
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | Dir. Proc.
87 |  | REA/CP/14/87 | Lot 87 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | Dir. Proc.
88 |  | REA/CP/14/88 | Lot 88 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | Dir. Proc.
89 |  | REA/CP/14/89 | Lot 89 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | Dir. Proc.
90 |  | REA/CP/14/90 | Lot 90 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | Dir. Proc.
91 |  | REA/CP/14/91 | Lot 91 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | Dir. Proc.
92 |  | REA/CP/14/92 | Lot 92 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
93 |  | REA/CP/14/93 | Lot 93 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
94 |  | REA/CP/14/94 | Lot 94 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
95 |  | REA/CP/14/95 | Lot 95 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
96 |  | REA/CP/14/96 | Lot 96 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
97 |  | REA/CP/14/97 | Lot 97 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
98 |  | REA/CP/14/98 | Lot 98 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
99 |  | REA/CP/14/99 | Lot 99 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
100 |  | REA/CP/14/100 | Lot 100 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
101 |  | REA/CP/14/101 | Lot 101 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
102 |  | REA/CP/14/102 | Lot 102 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
103 |  | REA/CP/14/103 | Lot 103 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
104 |  | REA/CP/14/104 | Lot 104 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
105 |  | REA/CP/14/105 | Lot 105 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
106 |  | REA/CP/14/106 | Lot 106 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
107 |  | REA/CP/14/107 | Lot 107 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
108 |  | REA/CP/14/108 | Lot 108 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
109 |  | REA/CP/14/109 | Lot 109 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
110 |  | REA/CP/14/110 | Lot 110 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
111 |  | REA/CP/14/111 | Lot 111 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
112 |  | REA/CP/14/112 | Lot 112 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
113 |  | REA/CP/14/113 | Lot 113 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
114 |  | REA/CP/14/114 | Lot 114 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
115 |  | REA/CP/14/115 | Lot 115 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
116 |  | REA/CP/14/116 | Lot 116 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
117 |  | REA/CP/14/117 | Lot 117 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
118 |  | REA/CP/14/118 | Lot 118 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
119 |  | REA/CP/14/119 | Lot 119 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
120 |  | REA/CP/14/120 | Lot 120 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
121 |  | REA/CP/14/121 | Lot 121 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
122 |  | REA/CP/14/122 | Lot 122 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
123 |  | REA/CP/14/123 | Lot 123 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
124 |  | REA/CP/14/124 | Lot 124 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
125 |  | REA/CP/14/125 | Lot 125 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
126 |  | REA/CP/14/126 | Lot 126 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
127 |  | REA/CP/14/127 | Lot 127 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
128 |  | REA/CP/14/128 | Lot 128 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
129 |  | REA/CP/14/129 | Lot 129 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
130 |  | REA/CP/14/130 | Lot 130 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
131 |  | REA/CP/14/131 | Lot 131 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
132 |  | REA/CP/14/132 | Lot 132 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
133 |  | REA/CP/14/133 | Lot 133 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
134 |  | REA/CP/14/134 | Lot 134 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
135 |  | REA/CP/14/135 | Lot 135 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
136 |  | REA/CP/14/136 | Lot 136 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
137 |  | REA/CP/14/137 | Lot 137 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
138 |  | REA/CP/14/138 | Lot 138 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
139 |  | REA/CP/14/139 | Lot 139 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
140 |  | REA/CP/14/140 | Lot 140 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
141 |  | REA/CP/14/141 | Lot 141 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
142 |  | REA/CP/14/142 | Lot 142 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
143 |  | REA/CP/14/143 | Lot 143 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
144 |  | REA/CP/14/144 | Lot 144 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
145 |  | REA/CP/14/145 | Lot 145 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
146 |  | REA/CP/14/146 | Lot 146 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
147 |  | REA/CP/14/147 | Lot 147 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
148 |  | REA/CP/14/148 | Lot 148 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
149 |  | REA/CP/14/149 | Lot 149 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
150 |  | REA/CP/14/150 | Lot 150 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
151 |  | REA/CP/14/151 | Lot 151 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
152 |  | REA/CP/14/152 | Lot 152 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
153 |  | REA/CP/14/153 | Lot 153 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
154 |  | REA/CP/14/154 | Lot 154 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
155 |  | REA/CP/14/155 | Lot 155 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
156 |  | REA/CP/14/156 | Lot 156 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
157 |  | REA/CP/14/157 | Lot 157 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
158 |  | REA/CP/14/158 | Lot 158 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
159 |  | REA/CP/14/159 | Lot 159 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
160 |  | REA/CP/14/160 | Lot 160 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
161 |  | REA/CP/14/161 | Lot 161 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
162 |  | REA/CP/14/162 | Lot 162 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
163 |  | REA/CP/14/163 | Lot 163 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
164 |  | REA/CP/14/164 | Lot 164 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
165 |  | REA/CP/14/165 | Lot 165 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
166 |  | REA/CP/14/166 | Lot 166 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
167 |  | REA/CP/14/167 | Lot 167 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
168 |  | REA/CP/14/168 | Lot 168 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
169 |  | REA/CP/14/169 | Lot 169 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
170 |  | REA/CP/14/170 | Lot 170 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
171 |  | REA/CP/14/171 | Lot 171 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
172 |  | REA/CP/14/172 | Lot 172 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
173 |  | REA/CP/14/173 | Lot 173 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
174 |  | REA/CP/14/174 | Lot 174 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
175 |  | REA/CP/14/175 | Lot 175 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
176 |  | REA/CP/14/176 | Lot 176 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
177 |  | REA/CP/14/177 | Lot 177 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
178 |  | REA/CP/14/178 | Lot 178 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
179 |  | REA/CP/14/179 | Lot 179 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
180 |  | REA/CP/14/180 | Lot 180 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
181 |  | REA/CP/14/181 | Lot 181 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
182 |  | REA/CP/14/182 | Lot 182 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
183 |  | REA/CP/14/183 | Lot 183 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
184 |  | REA/CP/14/184 | Lot 184 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
185 |  | REA/CP/14/185 | Lot 185 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
186 |  | REA/CP/14/186 | Lot 186 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
187 |  | REA/CP/14/187 | Lot 187 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
188 |  | REA/CP/14/188 | Lot 188 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
189 |  | REA/CP/14/189 | Lot 189 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
190 |  | REA/CP/14/190 | Lot 190 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
191 |  | REA/CP/14/191 | Lot 191 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
192 |  | REA/CP/14/192 | Lot 192 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
193 |  | REA/CP/14/193 | Lot 193 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
194 |  | REA/CP/14/194 | Lot 194 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
195 |  | REA/CP/14/195 | Lot 195 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
196 |  | REA/CP/14/196 | Lot 196 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
197 |  | REA/CP/14/197 | Lot 197 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
198 |  | REA/CP/14/198 | Lot 198 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
199 |  | REA/CP/14/199 | Lot 199 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
200 |  | REA/CP/14/200 | Lot 200 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
201 |  | REA/CP/14/201 | Lot 201 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
202 |  | REA/CP/14/202 | Lot 202 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
203 |  | REA/CP/14/203 | Lot 203 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
204 |  | REA/CP/14/204 | Lot 204 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
205 |  | REA/CP/14/205 | Lot 205 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
206 |  | REA/CP/14/206 | Lot 206 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
207 |  | REA/CP/14/207 | Lot 207 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
208 |  | REA/CP/14/208 | Lot 208 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
209 |  | REA/CP/14/209 | Lot 209 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
210 |  | REA/CP/14/210 | Lot 210 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
211 |  | REA/CP/14/211 | Lot 211 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
212 |  | REA/CP/14/212 | Lot 212 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
213 |  | REA/CP/14/213 | Lot 213 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
214 |  | REA/CP/14/214 | Lot 214 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
215 |  | REA/CP/14/215 | Lot 215 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
216 |  | REA/CP/14/216 | Lot 216 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
217 |  | REA/CP/14/217 | Lot 217 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
218 |  | REA/CP/14/218 | Lot 218 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
219 |  | REA/CP/14/219 | Lot 219 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
220 |  | REA/CP/14/220 | Lot 220 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
221 |  | REA/CP/14/221 | Lot 221 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
222 |  | REA/CP/14/222 | Lot 222 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
223 |  | REA/CP/14/223 | Lot 223 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
224 |  | REA/CP/14/224 | Lot 224 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
225 |  | REA/CP/14/225 | Lot 225 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
226 |  | REA/CP/14/226 | Lot 226 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
227 |  | REA/CP/14/227 | Lot 227 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
228 |  | REA/CP/14/228 | Lot 228 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
229 |  | REA/CP/14/229 | Lot 229 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
230 |  | REA/CP/14/230 | Lot 230 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
231 |  | REA/CP/14/231 | Lot 231 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
232 |  | REA/CP/14/232 | Lot 232 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
233 |  | REA/CP/14/233 | Lot 233 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
234 |  | REA/CP/14/234 | Lot 234 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
235 |  | REA/CP/14/235 | Lot 235 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
236 |  | REA/CP/14/236 | Lot 236 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
237 |  | REA/CP/14/237 | Lot 237 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
238 |  | REA/CP/14/238 | Lot 238 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
239 |  | REA/CP/14/239 | Lot 239 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
240 |  | REA/CP/14/240 | Lot 240 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
241 |  | REA/CP/14/241 | Lot 241 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
242 |  | REA/CP/14/242 | Lot 242 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
243 |  | REA/CP/14/243 | Lot 243 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
244 |  | REA/CP/14/244 | Lot 244 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
245 |  | REA/CP/14/245 | Lot 245 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
246 |  | REA/CP/14/246 | Lot 246 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
247 |  | REA/CP/14/247 | Lot 247 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
248 |  | REA/CP/14/248 | Lot 248 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
249 |  | REA/CP/14/249 | Lot 249 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
250 |  | REA/CP/14/250 | Lot 250 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
251 |  | REA/CP/14/251 | Lot 251 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
252 |  | REA/CP/14/252 | Lot 252 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
253 |  | REA/CP/14/253 | Lot 253 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
254 |  | REA/CP/14/254 | Lot 254 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
255 |  | REA/CP/14/255 | Lot 255 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
256 |  | REA/CP/14/256 | Lot 256 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
257 |  | REA/CP/14/257 | Lot 257 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
258 |  | REA/CP/14/258 | Lot 258 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
259 |  | REA/CP/14/259 | Lot 259 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
260 |  | REA/CP/14/260 | Lot 260 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
261 |  | REA/CP/14/261 | Lot 261 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
262 |  | REA/CP/14/262 | Lot 262 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
263 |  | REA/CP/14/263 | Lot 263 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
264 |  | REA/CP/14/264 | Lot 264 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
265 |  | REA/CP/14/265 | Lot 265 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
266 |  | REA/CP/14/266 | Lot 266 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
267 |  | REA/CP/14/267 | Lot 267 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
268 |  | REA/CP/14/268 | Lot 268 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
269 |  | REA/CP/14/269 | Lot 269 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
270 |  | REA/CP/14/270 | Lot 270 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
271 |  | REA/CP/14/271 | Lot 271 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
272 |  | REA/CP/14/272 | Lot 272 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
273 |  | REA/CP/14/273 | Lot 273 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
274 |  | REA/CP/14/274 | Lot 274 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
275 |  | REA/CP/14/275 | Lot 275 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
276 |  | REA/CP/14/276 | Lot 276 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
277 |  | REA/CP/14/277 | Lot 277 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
278 |  | REA/CP/14/278 | Lot 278 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
279 |  | REA/CP/14/279 | Lot 279 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
280 |  | REA/CP/14/280 | Lot 280 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
281 |  | REA/CP/14/281 | Lot 281 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
282 |  | REA/CP/14/282 | Lot 282 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
283 |  | REA/CP/14/283 | Lot 283 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
284 |  | REA/CP/14/284 | Lot 284 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
285 |  | REA/CP/14/285 | Lot 285 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
286 |  | REA/CP/14/286 | Lot 286 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
287 |  | REA/CP/14/287 | Lot 287 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
288 |  | REA/CP/14/288 | Lot 288 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
289 |  | REA/CP/14/289 | Lot 289 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
290 |  | REA/CP/14/290 | Lot 290 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
291 |  | REA/CP/14/291 | Lot 291 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
292 |  | REA/CP/14/292 | Lot 292 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
293 |  | REA/CP/14/293 | Lot 293 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
294 |  | REA/CP/14/294 | Lot 294 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
295 |  | REA/CP/14/295 | Lot 295 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
296 |  | REA/CP/14/296 | Lot 296 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
297 |  | REA/CP/14/297 | Lot 297 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
298 |  | REA/CP/14/298 | Lot 298 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
299 |  | REA/CP/14/299 | Lot 299 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
300 |  | REA/CP/14/300 | Lot 300 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
301 |  | REA/CP/14/301 | Lot 301 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
302 |  | REA/CP/14/302 | Lot 302 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
303 |  | REA/CP/14/303 | Lot 303 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
304 |  | REA/CP/14/304 | Lot 304 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
305 |  | REA/CP/14/305 | Lot 305 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
306 |  | REA/CP/14/306 | Lot 306 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
307 |  | REA/CP/14/307 | Lot 307 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
308 |  | REA/CP/14/308 | Lot 308 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
309 |  | REA/CP/14/309 | Lot 309 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
310 |  | REA/CP/14/310 | Lot 310 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
311 |  | REA/CP/14/311 | Lot 311 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
312 |  | REA/CP/14/312 | Lot 312 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
313 |  | REA/CP/14/313 | Lot 313 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
314 |  | REA/CP/14/314 | Lot 314 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
315 |  | REA/CP/14/315 | Lot 315 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
316 |  | REA/CP/14/316 | Lot 316 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
317 |  | REA/CP/14/317 | Lot 317 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
318 |  | REA/CP/14/318 | Lot 318 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
319 |  | REA/CP/14/319 | Lot 319 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
320 |  | REA/CP/14/320 | Lot 320 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
321 |  | REA/CP/14/321 | Lot 321 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
322 |  | REA/CP/14/322 | Lot 322 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
323 |  | REA/CP/14/323 | Lot 323 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
324 |  | REA/CP/14/324 | Lot 324 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
325 |  | REA/CP/14/325 | Lot 325 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
326 |  | REA/CP/14/326 | Lot 326 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
327 |  | REA/CP/14/327 | Lot 327 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
328 |  | REA/CP/14/328 | Lot 328 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
329 |  | REA/CP/14/329 | Lot 329 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
330 |  | REA/CP/14/330 | Lot 330 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
331 |  | REA/CP/14/331 | Lot 331 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
332 |  | REA/CP/14/332 | Lot 332 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
333 |  | REA/CP/14/333 | Lot 333 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
334 |  | REA/CP/14/334 | Lot 334 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
335 |  | REA/CP/14/335 | Lot 335 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
336 |  | REA/CP/14/336 | Lot 336 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
337 |  | REA/CP/14/337 | Lot 337 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
338 |  | REA/CP/14/338 | Lot 338 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
339 |  | REA/CP/14/339 | Lot 339 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
340 |  | REA/CP/14/340 | Lot 340 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
341 |  | REA/CP/14/341 | Lot 341 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
342 |  | REA/CP/14/342 | Lot 342 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
343 |  | REA/CP/14/343 | Lot 343 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
344 |  | REA/CP/14/344 | Lot 344 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
345 |  | REA/CP/14/345 | Lot 345 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
346 |  | REA/CP/14/346 | Lot 346 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
347 |  | REA/CP/14/347 | Lot 347 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
348 |  | REA/CP/14/348 | Lot 348 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
349 |  | REA/CP/14/349 | Lot 349 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
350 |  | REA/CP/14/350 | Lot 350 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
351 |  | REA/CP/14/351 | Lot 351 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
352 |  | REA/CP/14/352 | Lot 352 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
353 |  | REA/CP/14/353 | Lot 353 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
354 |  | REA/CP/14/354 | Lot 354 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
355 |  | REA/CP/14/355 | Lot 355 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
356 |  | REA/CP/14/356 | Lot 356 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
357 |  | REA/CP/14/357 | Lot 357 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
358 |  | REA/CP/14/358 | Lot 358 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
359 |  | REA/CP/14/359 | Lot 359 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
360 |  | REA/CP/14/360 | Lot 360 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
361 |  | REA/CP/14/361 | Lot 361 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
362 |  | REA/CP/14/362 | Lot 362 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
363 |  | REA/CP/14/363 | Lot 363 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
364 |  | REA/CP/14/364 | Lot 364 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
365 |  | REA/CP/14/365 | Lot 365 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
366 |  | REA/CP/14/366 | Lot 366 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
367 |  | REA/CP/14/367 | Lot 367 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
368 |  | REA/CP/14/368 | Lot 368 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
369 |  | REA/CP/14/369 | Lot 369 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
370 |  | REA/CP/14/370 | Lot 370 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
371 |  | REA/CP/14/371 | Lot 371 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
372 |  | REA/CP/14/372 | Lot 372 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
373 |  | REA/CP/14/373 | Lot 373 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
374 |  | REA/CP/14/374 | Lot 374 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
375 |  | REA/CP/14/375 | Lot 375 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
376 |  | REA/CP/14/376 | Lot 376 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
377 |  | REA/CP/14/377 | Lot 377 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
378 |  | REA/CP/14/378 | Lot 378 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
379 |  | REA/CP/14/379 | Lot 379 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
380 |  | REA/CP/14/380 | Lot 380 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
381 |  | REA/CP/14/381 | Lot 381 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
382 |  | REA/CP/14/382 | Lot 382 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
383 |  | REA/CP/14/383 | Lot 383 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
384 |  | REA/CP/14/384 | Lot 384 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
385 |  | REA/CP/14/385 | Lot 385 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
386 |  | REA/CP/14/386 | Lot 386 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
387 |  | REA/CP/14/387 | Lot 387 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
388 |  | REA/CP/14/388 | Lot 388 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
389 |  | REA/CP/14/389 | Lot 389 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
390 |  | REA/CP/14/390 | Lot 390 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
391 |  | REA/CP/14/391 | Lot 391 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
392 |  | REA/CP/14/392 | Lot 392 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
393 |  | REA/CP/14/393 | Lot 393 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
394 |  | REA/CP/14/394 | Lot 394 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
395 |  | REA/CP/14/395 | Lot 395 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
396 |  | REA/CP/14/396 | Lot 396 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
397 |  | REA/CP/14/397 | Lot 397 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
398 |  | REA/CP/14/398 | Lot 398 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
399 |  | REA/CP/14/399 | Lot 399 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.
400 |  | REA/CP/14/400 | Lot 400 |  | NCB |  | PTB | Plan | 3/03/14 - 24/03/14 | 24/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | 21/04/14 - 19/05/14 | 19/05/14 - 30/06/14 | 30/06/14 - 14/07/14 | 14/07/14 - 21/07/14 | Plan |  | Not Applicable | Not Applicable | 21/07/14 - 28/07/14 | 28/07/14 - 18/08/14 |  |  | 18/08/14 - 8/09/14
[8 empty] | Actual | [7 empty] | Actual | [10 empty] | DD. Proc. | DD. Proc.

## O-O R. BASIN Consultancy
Ministry/Department/Agency: Ogun/Osun River Basin Development Authority
Budget Year: 2014
|  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 1 weeks | 2 - 4 weeks | 2 weeks | 2 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
PREVENTIVE HEALTH CARE: HIV/AIDS ADVOCACY | Plan | OORBDA/2014/PROC/INVT/NC5 |  | Time-Based | 930000 | NS | Accounting Officer: Director General/CEO | LC - Least Cost | POST-QUALIFICATION | POST REVIEW | 3/03/14 - 21/03/14 | 24/03/14 - 4/04/14 | 7/04/14 - 21/04/14 | NA | 30/04/14 | 30/04/14 - 9/05/14 | 9/05/14 - 20/05/14 | 20/05/14 - 20/05/14 | 20/05/14 - 30/05/14 | 2/06/14 - 6/06/14 | 1/07/14 - 1/07/14 | 1/07/14 - 15/07/14 | NA | 15/07/14 - 22/07/14 | NA | NA | 22/07/14 - 5/08/14 | 5/08/14 - 19/08/14 | 19/08/14 - 9/09/14 | NA | NA | NA
Actual
Total Cost Plan |  |  |  |  | 930000
Total Cost Actual

## O-O R. BASIN Works
Ministry/Department/Agency: Ogun/Osun River Basin Development Authority
Budget Year: 2014
|  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Works |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Plan vs Actual
OYAN RIVER DAM IRRIGATION | Plan |  | 1 | BEME | 0 | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW
Actual
OFIKI IRRIGATION SCHEME (Phase I) | Plan | OORBDA/2014/PROC/INVT/NC1 |  | BEME | 40500000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 3/03/14 - 21/03/14 | 24/03/14 - 4/04/14 | 7/04/14 - 5/05/14 | 6/05/14 - 20/05/14 | 20/05/14 - 17/06/14 | NA | NA | 17/06/14 | 1/07/14 | 1/07/14 - 15/07/14 | 15/07/14 - 22/07/14 | NA | NA | 22/07/14 - 5/08/14 | 5/08/14 - 19/08/14 | 19/08/14 - 9/09/14 | NA | NA | NA | Ezekiel FALOLA - [Designation: Chief Engineer Irrigation] | Olujimi SOKUNLE - [Designation: Executive Director Engineering]
| Actual | [20 empty] | NA | NA
OYAN RIVER DAM IRRIGATION PROJECT | Plan | OORBDA/2014/PROC/INVT/NC2 |  | BEME | 5105000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 3/03/14 - 21/03/14 | 24/03/14 - 4/04/14 | 7/04/14 - 5/05/14 | 6/05/14 - 20/05/14 | 20/05/14 - 17/06/14 | NA | NA | 17/06/14 | 1/07/14 | 1/07/14 - 15/07/14 | 15/07/14 - 22/07/14 | NA | NA | 22/07/14 - 5/08/14 | 5/08/14 - 19/08/14 | 19/08/14 - 9/09/14 | NA | NA | NA | Ezekiel FALOLA - [Designation: Chief Engineer Irrigation] | Olujimi SOKUNLE - [Designation: Executive Director Engineering]
| Actual | [20 empty] | NA | NA
ITOIKIN IRRIGATION PROJECT | Plan | OORBDA/2014/PROC/INVT/NC3 |  | BEME | 40502000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 3/03/14 - 21/03/14 | 24/03/14 - 4/04/14 | 7/04/14 - 5/05/14 | 6/05/14 - 20/05/14 | 20/05/14 - 17/06/14 | NA | NA | 17/06/14 | 1/07/14 | 1/07/14 - 15/07/14 | 15/07/14 - 22/07/14 | NA | NA | 22/07/14 - 5/08/14 | 5/08/14 - 19/08/14 | 19/08/14 - 9/09/14 | NA | NA | NA | Ezekiel FALOLA - [Designation: Chief Engineer Irrigation] | Olujimi SOKUNLE - [Designation: Executive Director Engineering]
Actual
REHABILITATION OF HQ OFFICE COMPLEX (INCLUDING REPLACEMENT OF OBSOLETE OFFICE FURNITURE, EQUIPMENT AND FITTINGS) | Plan | OORBDA/2014/PROC/INVT/NC4 |  | BEME | 19491104 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 3/03/14 - 21/03/14 | 24/03/14 - 4/04/14 | 7/04/14 - 5/05/14 | 6/05/14 - 20/05/14 | 20/05/14 - 17/06/14 | NA | NA | 17/06/14 | 1/07/14 | 1/07/14 - 15/07/14 | 15/07/14 - 22/07/14 | NA | NA | 22/07/14 - 5/08/14 | 5/08/14 - 19/08/14 | 19/08/14 - 9/09/14 | NA | NA | NA | Ezekiel FALOLA - [Designation: Chief Engineer Irrigation] | Olujimi SOKUNLE - [Designation: Executive Director Engineering]
Actual
Total Cost Plan |  |  |  |  | 105598104
Total Cost Actual

## SECRETARY Consultancy Services
Ministry/Department/Agency: OFFICE OF THE SECRETARY TO THE GOVERNMENT OF THE FEDERATION
Budget Year: 2014
|  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 1 weeks | 2 - 4 weeks | 2 weeks | 2 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
PRODUCTION OF COMPENDIUM OF LAWS /BILLS PASSED BY NATIONAL AND STATE ASSEMBLIES 1999 MAY TO 2012 AND PRODUCTION OF NIGERIA&#039;S FOREIGN POLICY UNDER CIVILIAN REGIME | Plan | 012 | 23 | Time-Based | 50000000 | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 - 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | 29/05/14 - 12/06/14 | 12/06/14 - 26/06/14 | 26/06/14 - 3/07/14 | 50000000 | NA | 3/07/14 - 17/07/14 | 17/07/14 - 31/07/14 | NA | 31/07/14 | 14/08/14 | 50000000 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
| Actual | [31 empty] | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
RESEARCH & CONSTITUTIONAL MATTERS | Plan | 013 | 24 | Time-Based | 50000000 | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | NA | POST REVIEW | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 - 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | 29/05/14 - 12/06/14 | 12/06/14 - 26/06/14 | 26/06/14 - 3/07/14 | 50000000 | NA | 3/07/14 - 17/07/14 | 17/07/14 - 31/07/14 | NA | 31/07/14 | 14/08/14 | 50000000 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
| Actual | [31 empty] | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
SETTLEMENT OF CONSULTANCY FEES FOR COMPLETION OF SHEHU SHAGARI COMPLEX | Plan | 015 | 26 | Lump Sum | 150000000 | NCB | BPP issues "No Objection" to award/FEC approves | CQ - Consultant&#039;s Qualification | NA | PRIOR REVIEW | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 - 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | 29/05/14 - 12/06/14 | 12/06/14 - 26/06/14 | 26/06/14 - 3/07/14 | 150000000 | NA | 3/07/14 - 17/07/14 | 17/07/14 - 31/07/14 | 31/07/14 - 14/08/14 | 14/08/14 | 28/08/14 | 150000000 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
| Actual | [31 empty] | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
Total Cost Plan |  |  |  |  | 250000000 | [19 empty] | 250000000 | [6 empty] | 250000000
Total Cost Actual

## SECRETARY Goods
Ministry/Department/Agency: OFFICE OF THE SECRETARY TO THE GOVERNMENT OF THE FEDERATION
Budget Year: 2014
|  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Goods |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Arrival of Goods | Inspection/Final Acceptance | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
Plan vs Actual
HP Scanners | Plan | 001 | 1 |  | 15000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID
Actual
UPS (BLUEGATE 1.5 KVA) 500 NOS | Plan | 001 | 2 | Bills of Quantity | 14350000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 14350000 | NA | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | NA | 29/05/14 - 19/06/14 | 19/06/14 - 3/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
| Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
PROCUREMENT OF OFFICE EQUIPMENTS FOR ADDITIONAL OFFICES | Plan | 001 | 3 | Bills of Quantity | 283000000 | NCB | BPP issues "No Objection" to award/FEC approves | LERB - LOWEST EVALUATED RESPONSIVE BID | PRE-QUALIFICATION |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 283000000 | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | 29/05/14 - 12/06/14 | 12/06/14 - 26/06/14 | 26/06/14 - 10/07/14 | 10/07/14 - 24/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
| Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
PROCUREMENT OF THERMOCOOL FRIDGE (150 N0) | Plan | 001 | 4 | Bills of Quantity | 12370000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 12370000 | NA | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | NA | 29/05/14 - 19/06/14 | 19/06/14 - 3/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
| Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
PROCUREMENT OF C-WAYS WATER DISPENSER (100 NO) | Plan | 001 | 5 | Bills of Quantity | 4950000 | NCB | Accounting Officer: Permanent Secretary | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 4950000 | NA | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | NA | 29/05/14 - 19/06/14 | 19/06/14 - 3/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
| Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
PROCUREMENTOF HP LAPTOP COMPUTER (2.6 GH2 DUAL (CORE, 3200 GB HDD, 2GB ) 150 N0 | Plan | 001 | 6 | Bills of Quantity | 25800000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 25800000 | NA | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | NA | 29/05/14 - 19/06/14 | 19/06/14 - 3/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
| Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
PROCUREMENT OF HP DESKTOP COMPUTER (150 NO) | Plan | 001 | 7 | Bills of Quantity | 27000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 27000000 | NA | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | 29/05/14 - 19/06/14 | 19/06/14 - 3/07/14 | 3/07/14 - 17/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
| Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
PROCUREMENT OF HP LASERJET PRINTER 2053 (200 NO ) | Plan | 001 | 8 | Bills of Quantity | 16500000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 16500000 | NA | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | NA | 29/05/14 - 19/06/14 | 19/06/14 - 3/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
| Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
PROCUREMENT OF PHOTOCOPYING MACHINES (50 NO ) | Plan | 001 | 9 | Bills of Quantity | 35000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 35000000 | NA | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | NA | 29/05/14 - 19/06/14 | 19/06/14 - 3/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
| Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
PROCUREMENT OF SHREDDING MACHINES (SANYO 650 )300 NO | Plan | 001 | 10 | Bills of Quantity | 5625000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 5625000 | NA | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | NA | 29/05/14 - 19/06/14 | 19/06/14 - 3/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
| Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
PROCUREMENT OF LIBRARY BOOKS & EQUIPMENT FOR SPECIALISED LIBRARIES IN OSGF | Plan | 002 | 11 | Bills of Quantity | 150000000 | NCB | BPP issues "No Objection" to award/FEC approves | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 150000000 | 1/05/14 - 7/05/14 | 7/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | 29/05/14 - 5/06/14 | 5/06/14 - 19/06/14 | 19/06/14 - 3/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
| Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
PROCUREMENT OF GYMNASIUM EQUIPMENT (BICYCLE, EGO TREAD MILL SET OF WEIGHTS) | Plan | 003 | 12 | Bills of Quantity | 50073420 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 50073420 | NA | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | NA | 29/05/14 - 19/06/14 | 19/06/14 - 3/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
| Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
PROCUREMENT OF SECURITY ITEMS (SUPPLY AND INSTALLATION OF UNDER VEHICLE INSPECTION SYSTEM, BOLLARDS, HAND-HELD SCANNERS | Plan | 004 | 13 | Bills of Quantity | 1161356582 | NCB | BPP issues "No Objection" to award/FEC approves | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | NA | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 1161356582 | 1/05/14 - 8/05/14 | 8/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | 29/05/14 - 5/06/14 | 5/06/14 - 19/06/14 | 19/06/14 - 26/06/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
| Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
PROCUREMENT OF MOTORCYCLES FOR DISPATCH (6 No.) | Plan | 005 | 14 | Bills of Quantity | 900000 | NS | Accounting Officer: Permanent Secretary | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 900000 | NA | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | NA | 29/05/14 - 19/06/14 | 19/06/14 - 3/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
| Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
PROCUREMENT OF POOL VEHICLES FOR USE OF ELDER STATE MEN WHEN IN ABUJA OFFICIAL (COASTER | Plan | 006 | 15 | Bills of Quantity | 70000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 70000000 | NA | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | NA | 29/05/14 - 19/06/14 | 19/06/14 - 3/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
| Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
PROCUREMENT OF COASTER BUSES (6 NO ) | Plan | 006 | 16 | Bills of Quantity | 78000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 13/03/14 | 13/03/14 - 27/03/14 | 27/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 78000000 | NA | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | NA | 29/05/14 - 19/06/14 | 19/06/14 - 3/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
| Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
PROCUREMENT OF TOYOTA BUSES ( HIGH ROOF ) FOR CABINET MEETINGS DISTRIBUTION & DISPATCHING | Plan | 006 | 17 | Bills of Quantity | 36000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 36000000 | NA | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | NA | 29/05/14 - 19/06/14 | 19/06/14 - 3/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
| Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
Total Cost Plan |  |  |  |  | 1985925002 | [14 empty] | 1970925002
Total Cost Actual

## SECRETARY Non-Consultancy
Ministry/Department/Agency: OFFICE OF THE SECRETARY TO THE GOVERNMENT OF THE FEDERATION
Budget Year: 2014
|  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 1 weeks | 2 - 4 weeks | 2 weeks | 2 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
Democracy Day and Independence Celeberations | Plan | 016 | 27 | Lump Sum | 250000000 | NCB | BPP issues "No Objection" to award/FEC approves | QCBS - Quality and Cost Based Selection | PRE-QUALIFICATION | PRIOR REVIEW | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 - 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | 29/05/14 - 12/06/14 | 12/06/14 - 26/06/14 | 26/06/14 - 3/07/14 | 250000000 | 3/07/14 - 17/07/14 | 17/07/14 - 31/07/14 | 31/07/14 - 14/08/14 | 14/08/14 - 28/08/14 | 9/09/14 | 23/09/14 | 250000000 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
| Actual | [31 empty] | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
Total Cost Plan |  |  |  |  | 250000000 | [19 empty] | 250000000 | [6 empty] | 250000000
Total Cost Actual

## O.O SURVEYOR GOODS
Ministry/Department/Agency: OFFICE OF THE SURVEYOR - GENERAL OF THE FEDERATION | [6 empty] | THE TIME LINE IS TO BE COMPARED WITH THE COUNCILS APPROVAL
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: Mr. E. O. Moses - 08064914125 |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization | [5 empty] | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Plan vs. Actual | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 2 wks | Plan | 2 - 3 wks | T | 2 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual |  |  |  |  | Actual
List of Contracts
High Definition Camera, Accessories and office utilities | 1 | 1 | N3, 000, 000.00 | NCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan | 3000000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | CPS | DDP
Actual
Production and distribution of OSGOF’S News Bulletin | 2 | 1 | 2, 500, 000.00 | NCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan | 2, 500, 000.00 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | CPS | DDP
Actual
Media Awareness Campaign on the Role of Surveying and mapping in achieving vision 20-20-20 | 3 | 1 | 1, 500, 000.00 | NCB | N/A | MTB | Actual | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May |  | 1, 500, 000.00 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | CPS | DDP
Procurement of Customized Stock Verification Completion Certificate with Security code Number | 4 | 1 | 1200000 | NCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan | 1200000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | H (SVU) | DDP
Actual
Acquisition of I.T. Equipments | [14 empty] | Plan
| 5 | 1 | 4000000 | Bidding | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Actual | 4000000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | DD (IA) | DDP
Actual
Procurement and Installation of Software for the Production of Due Diligence Data | 6 | 1 | 5000000 | NCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan | 5000000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | D. Boundaries | DPP
[7 empty] | Actual | [7 empty] | Actual
Procurement and Installation of Software for the Production of Due Diligence Data | 7 | 1 | 5000000 | NCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan | 5000000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | D. Boundaries | DDP
[7 empty] | Actual | [7 empty] | Actual
Production of Sensitization materials; handbills, Stickers, table planners, branded items, t-shirts with caps. | 8 | 1 | 1, 500, 000.00 | National Competitive Bidding | N/A |  | Plan Actual | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan Actual | N 1, 500, 000.00 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | Chairman (ACTU) | DDP
Procurement of investigative/Security materials: 3 No. Camcorder, 3 No. I-pad, 1 No. Mini I-pad (4G Network), 1 No. Sony Projector. | 9 | 2 | 2, 500, 000.00 | National Competitive Bidding | N/A |  | Plan Actual | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan Actual | N 2, 500, 000.00 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | Chairman (ACTU) | DDP
Production of quarterly Magazines | 10 | 1 | N 4,650,000.00 | National Competitive Bidding | N/A |  | Plan Actual | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan Actual | N 650, 000.00 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | Chairman (ACTU) | DDP
PROCUREMENT OF SPECIAL SURVEYS EQUIPMENT | [6 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
(i) Supply of 1 No. tide gauge. | 11 | 1 | 5327814.11 | NCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan | 5327814.11 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | D. Survey | DDP
[7 empty] | Actual | [7 empty] | Actual
(ii) Acquisition of (a) Digital Elevation Models (DEMs) coverage of Anambra State for comprehensive gully Erosion Monitoring. (b) High Resolution satellite imageries covering Sokoto, Kebbi and Zamfara States | 12 | 2 | 17759380.37 | NCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan | 17759380.37 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | D. Survey | DDP
[7 empty] | Actual | [7 empty] | Actual
(iii)Supply of Special Survey Work implements and camping equipments | 13 | 3 | 4162909.76 | NCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan | 4162909.76 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | D. Survey | DDP
[7 empty] | Actual | [7 empty] | Actual
(iv) Attendance of an International Hydrographic Conference/Training for 4No officers. | 14 | 4 | 7991721.17 | NCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan | 7991721.17 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | D. Survey | DDP
[7 empty] | Actual | [7 empty] | Actual
(v) Integrity Checks on Tidal/Special Survey Installations. | 15 | 5 | 5327814.11 | NCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan | 5327814.11 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | D. Survey | DDP
[7 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF GEODETIC EQUIPMENT | [6 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
(i) 2 No. GNSS/GPS Precision Receivers (Topcon, Sokkia & Trimble) | 16 | 1 | 15633860 | NCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan | 15633860 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | D. Survey | DDP
[7 empty] | Actual | [7 empty] | Actual
(ii) Total Station (1No.), Precision Digital Level (1No.) | 17 | 2 | 9500000 | NCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan | 9500000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | D. Survey | DDP
[7 empty] | Actual | [7 empty] | Actual
(iii)Precision GNSS/GPS Antenna, Data Logger, Battery etc. | 18 | 3 | 10655622.07 | NCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan | 10655622.07 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | D. Survey | DDP
[7 empty] | Actual | [7 empty] | Actual
Field & Survey Digital Equipments | [6 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
(i) Monumentation Accessories & implements | 19 | 1 | 3345400.38 | NCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan | 3345400.38 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | D. Survey | DDP
[7 empty] | Actual | [7 empty] | Actual
(ii) Transport Logistics & camping Equipments | 20 | 2 | 2000000 | NCB | N/A | PTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan | 2000000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | D. Survey | DDP
[7 empty] | Actual | [7 empty] | Actual
(iii) Construction Materials | 21 | 3 | 3500000 | NCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan | 3500000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | D. Survey | DDP
[7 empty] | Actual | [7 empty] | Actual
(iv) Field Inspection Services & Contingencies | 22 | 4 | 3000000 | NCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan | 3000000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | D. Survey | DDP
[7 empty] | Actual | [7 empty] | Actual
Acquisition of Materials for Budget Activities | 23 | 1 | 4000000 | National Competitive Bidding | N/A | MTB | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 4000000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | DFA | DDP
[7 empty] | Actual | [7 empty] | Actual
Replacement of Office Equipment e.g Computers, Printers, Toners and other Comsumables | 24 | 1 | 16000000 | National Competitve Bidding | N/A | MTB | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 16000000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | DFA | DPP
[7 empty] | Actual | [7 empty] | Actual
Procurement of the following office equipment for Hqts and Zonal offices:10No. Zinox Laptop, 10No.Zinox Desktop Computer, 2No. Set executive Leather Settees & 8No. Ex table & Chairs | 25 | 1 | 9800000 | National Competitive Bidding | N/A | MTB | Actual | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug |  | 9800000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | DHR | DDP
Procurement of equipment for e-Registry: No. Personnel Records management Software, Data Capturing and Storage Facilities, 5No.Zinox desktop Computer | 26 | 2 | 5900000 | National Competitive Bidding | N/A | MTB | Actual | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug |  | 5900000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | DHR | DDP
Actual
Procurement of Various office Furniture for for Hqts and Zonal office | 27 | 2 | 8200000 | National Competitive Bidding | N/A | MTB | Actual | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug |  | 8200000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | DHR | DDP
Actual
Procurement of Store Racks | 28 | 3 | 1000000 | National Competitive Bidding | N/A | Prior |  | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug |  | 1000000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | DHR | DDP
Actual
Actual
Procurement of Shelves at the central Store in Abuja | 29 | 1 | 1000000 | National Competitive Bidding | N/A | Prior |  | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug |  |  | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct
Capital Project Implementation, Monitorina and Evaluation | 30 | 1 | 10000000 | National Competitive Bidding | N/A | MTB | Actual | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug |  | 10000000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | AD (FA) | DDP
Procurement installation and update of customized software for the production of due diligence Data. | 31 | 1 | 3495000 | National Competitive Bidding | N/A | MTB | Actual | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug |  | 3495000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | DDP | SGOF
Provision of Utility Vehicle and Staff/Students Bus for each of the Engineering Training Schools at Ijora, Abeokuta and Kuje. | 32 | 2 | 15000000 | OCB | N/A | MTB | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 15000000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | DEMS | DPP
Actual
Purchase of Sporting Facilities at Engineering Training Schools, in Ijora, Abeokuta and Kuje | 33 | 1 | 2000000 | OCB | N/A | MTB | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 1990900 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | DEMS | DPP
Actual
Procurement of Digital Workstation and Other Accessories | 34 | 2 | 25000000 | National Competitive Bidding | N/A | MTB | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 25000000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | Director Survey Coordination | DD Procurement
Actual
Purchase of 2Nos. Of Hilux Utility Vehicles | 35 | 1 | 15000000 | National Competitive Bidding | N/A | MTB | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 15000000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | Director Survey Coordination | DD Procurement
Actual
Procurement of 4No 4M DEM for Benin, Gombe, Makurdi and Ilorin Township Mapping | 36 | 2 | 5600000 | NCB |  | MTB | Actual | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug |  | 5598000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | DLC | DDP
Actual
Procurement of Various survey data capturing and storing equipment for mapping. | 37 | 1 | 5740000 |  |  | MTB |  | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug |  | 5739000 | N/A | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | DDP
Actual
Procurement of High precision Dual frequency Survey equipments. | 38 | 1 | 29835000 |  |  | MTB | Actual | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug |  | 29830000 | N/A | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | DDP
AQUISITION OF DATABASE HIGH PERFORMANCE SERVER
Procurement of Server Plotter and Scanner | 39 | 1 | 9000000 | OCB | N/A | MTB | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 9000000 | N/A | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | DDPP
[7 empty] | Actual | [7 empty] | Actual
Acquisition of three (3) Work station and Laptops. | 40 | 2 | 4500000 | OCB | N/A | MTB | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 4500000 | N/A | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | DDPP
[7 empty] | Actual | [7 empty] | Actual
CREATION & MAINTENANCE OF NATIONAL GEOSPATIAL REPOSITORY OSGOF
Procurement of backup data storage for the Datacenter | 41 | 1 | 9000000 | OCB | N/A | MTB | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 9000000 | N/A | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | DDPP
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  |  | 283474521.97

## O.O SURVEYOR WORKS
Ministry/Department/Agency: |  | OFFICE OF THE SURVEYOR - GENERAL OF THE FEDERATION | [6 empty] | OSGOF | 2014 | [6 empty] | OSGOF |  |  | BOUNDARIES DEPARTMENT
Budgetary Year: | 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed | [5 empty] | 2014
Desk Officer/Contact #: Mr. E. O. Moses - 08064914125 |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Bauchi/Gombe ISB, Observation of Boundary beacons | 1 | 1 | BOQ | National Competitive Bidding | 8500000 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 8250000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 8,250,000.00 | D. Boundaries | DDP
[8 empty] | Actual | [7 empty] | Actual
Kaduna/Plateau ISB,Observation of boundary beacons | 2 | 1 | BOQ | National Competitive Bidding | 8000000 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 7812370 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 7812370 | D. Boundaries | DDP
[8 empty] | Actual | [7 empty] | Actual
Ogun/Oyo ISB,Observation of boundary beacons | 3 | 1 | BOQ | National Competitive Bidding | 8500000 | N/A |  | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 8150622 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 8150622 | D. Boundaries | DDP
[8 empty] | Actual | [7 empty] | Actual
Kaduna/Kano ISB, clearing of line & maintenance beacon | 4 | 1 | BOQ | National Competitive Bidding | 9000000 | N/A | PTB |  | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June |  | 8534000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 8,534,000.00 | D. Boundaries | DDP
Plateau/Taraba ISB clearing of Line and Maintenance ISB beacons | 5 | 1 | BOQ | National Competitive Bidding | 8800000 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 8620500 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 8,620,500.00 | D. Boundaries | DDP
[8 empty] | Actual | [7 empty] | Actual
Ekiti/Kwara ISB clearing of Line & Maintenance beacon | 6 | 1 | BOQ | National Competitive Bidding | 9500000 | N/A | PTB |  | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June |  | 9200650 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 9,200,650.00 | D. Boundaries | DDP
Oyo/Osun ISB Claaring of line and Maintenances ISB beacons | 7 | 1 | BOQ | National Competitive Bidding | 7800000 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 7781170 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 7,781,170.00 | D. Boundaries | DDP
[8 empty] | Actual | [7 empty] | Actual
Ekiti/Osun ISB, Emplacement of Beacons | 8 | 1 | BOQ | National Competitive Biddin | 9000000 | N/A | PTB |  | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June |  | 8620662 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 8,620,662.00 | D. Boundaries | DDP
Enugu/Ebonyi ISB, Emplacement Of boundary beacons | 9 | 1 | BOQ | National Competitive Bidding | 7680000 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 8250254 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 8,250,254.00 | D. Boundaries | DDP
[8 empty] | Actual | [7 empty] | Actual
Kwara/Kogi ISB,Emplacement of beacons | 10 | 1 | BOQ | National Competitive Biddin | 9000000 | N/A | PTB |  | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June |  | 8750000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 8,750,000.00 | D. Boundaries | DDP
Anambra/Kogi; Emplacement of beacons | 11 | 1 | BOQ | National Competitive Bidding | 9000000 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 8682572 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 8,682,572.00 | D. Boundaries | DDP
[8 empty] | Actual | [7 empty] | Actual
Edo/Delta ISB Field Tracing and Prov.Demarcation | 12 | 1 | BOQ | National Competitive Biddin | 7500000 | N/A | PTB |  | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June |  | 7069400 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 7,069,400.00 | D. Boundaries | DDP
Kano/Katsina ISB Field Tracing and Prov.Demarcation | 13 | 1 | BOQ | National Competitive Bidding | 7000000 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 6850120 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 6,850,120.00 | D. Boundaries | DDP
[8 empty] | Actual | [7 empty] | Actual
FCT/Niger ISB Field Tracing and Prov.Demarcation | 14 | 1 | BOQ | National Competitive Biddin | 7800000 | N/A | PTB |  | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June |  | 7680285 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 7,680,285.00 | D. Boundaries | DDP
Abia/Akwa-Ibom ISB Field Tracing and Prov.Demarcation | 15 | 1 | BOQ | National Competitive Bidding | 7500000 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 7250792 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 7,250,792.00 | D. Boundaries | DDP
[8 empty] | Actual | [7 empty] | Actual
Gombe/Yobe ISB Field Tracing and Prov.Demarcation | 16 | 1 | BOQ | National Competitive Bidding | 6500000 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 6496603 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 6,496,603.00 | D. Boundaries | DDP
[8 empty] | Actual | [7 empty] | Actual
Surveying and observation of Nigeria's international Boundaries: Nigeria-Niger | 17 | 1 | BOQ | National Competitive Bidding | 8320000 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 8320000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 8320000 | D. Boundaries | DDP
[8 empty] | Actual | [7 empty] | Actual
Surveying and Observation of Nigeria's International Boundaries: Nigeria-Benin/Cameroon | 18 | 1 | BOQ | National Competitive Bidding | 24960000 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 24800000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 24,800,000.00 | DB | DDP
[8 empty] | Actual | [7 empty] | Actual
Vista clearing of Nigeria/Benin International Boundary | 19 | 1 | BOQ | National Competitive Bidding | 4800000 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 3780000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 3,780,000.00 | DB | DDP
[8 empty] | Actual | [7 empty] | Actual
Vista clearing of Nigeria/Niger International Boundary | 20 | 1 | BOQ | National Competitive Bidding | 9960000 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 9860000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 9.860,000.00 | DB | DDP
[8 empty] | Actual | [7 empty] | Actual
Pillar construction of Nigeria/Benin International Boundary | 21 | 1 | BOQ | National Competitive Bidding | 7680000 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 7600000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 7,600,000.00 | DB | DDP
[8 empty] | Actual | [7 empty] | Actual
Pillar construction of Nigeria/Niger International Boundary | 22 | 1 | BOQ | National Competitive Bidding | 15360000 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 15,240.000.00 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 15,240,000.00 | DB | DDP
[8 empty] | Actual | [7 empty] | Actual
Maintenance of Int'l Boundary and Manag. | 23 | 1 | BOQ | National Competitive Bidding | 23040000 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 22890000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 22,890,000.00 | DB | DDP
[8 empty] | Actual | [7 empty] | Actual
Survey/Field Assessment of Boundary Corridor of Nigeria-Cameroon International Boundary located within Borno and Adamawa States in Nigeria/North and Extreme North Regions in Cameroon | 24 | 1 | BOQ | National Competitive Bidding | 20140000 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 20000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 20,000,000,00 | DB | DDP
[8 empty] | Actual | [7 empty] | Actual
Survey/Field Assessment of Boundary Corridor of Nigeria-Cameroon International Boundary located within Taraba, Benue and Cross River States in Nigeria/Adamawa and South West Regions in Cameroon | 25 | 1 | BOQ | National Competitive Bidding | 15700000 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 15580000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 15,580,000.00 | DB | DDP
[8 empty] | Actual | [7 empty] | Actual
Creation, Demarcation and Furnishing of Additional office spaces. | 26 | 1 | BOQ | National Competitive Bidding | 6500000 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 6500000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 6500000 | DDL | DDP
[8 empty] | Actual | [7 empty] | Actual
SURVEYS FOR GULLY EROSION CONTROL & DESERTIFICATION MONITORING | [7 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
(i). Contour generation and Processing of 2m High Resolution DEMs for gully erosion monitoring of sites in SE Nigeria | 27 | 1 | B. O. Q | NCB | 5879493.75 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 5879493.75 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 5879493.75 | D. Survey | DDP
[8 empty] | Actual | [7 empty] | Actual
SURVEY FOR COASTLINE ENCROACHMENT MONITORING | [7 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
(i). Establishment & Observation of 3D Special Controls/Benchmarks at any these Coastal Communities;- Eastern Obollo (Akwa Ibom State) & Badagry (Lagos State). | 28 | 1 | B. O. Q | NCB | 2939746.55 | N/A | CEO | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 2939746.55 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 2939746.55 | D. Survey | DDP
[8 empty] | Actual | [7 empty] | Actual
BUILDING AND DEMARCATION OF ROADS R-O-W NATIONWIDE | [7 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Processing of High Resolution Satellite Imageries (0.5m) R.O.W Surveys of 240km length of 3 Federal Highways | [7 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
85km | 29 | 1 | BOQ | NCB | 10709374.02 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 10709374.02 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 10709374.02 | D. Survey | DDP
[8 empty] | Actual | [7 empty] | Actual
85km | 30 | 2 | BOQ | NCB | 10709374.02 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 10709374.02 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 10709374.02 | D. Survey | DDP
[8 empty] | Actual | [7 empty] | Actual
70km | 31 | 3 | BOQ | NCB | 10709374.02 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 10709374.02 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 10709374.02 | D. Survey | DDP
[8 empty] | Actual | [7 empty] | Actual
Purchases | 32 | 4 | BOQ | NCB | 3148839.15 | N/A | CEO | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 3148839.15 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 3148839.15 | D. Survey | DDP
[8 empty] | Actual | [7 empty] | Actual
BUILDING AND DEMARCATION OF R-O-W RAIL ROADS NATIONWIDE | [7 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Processing of High Resolution Satellite Imageries (0.5m) for R.O.W Surveys of 150km length of 3 Railroad | [7 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
50km | 33 | 1 | BOQ | NCB | 7656078.46 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 7656078.46 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 7656078.46 | D. Survey | DDP
[8 empty] | Actual | [7 empty] | Actual
50km | 34 | 2 | BOQ | NCB | 7656078.46 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 7656078.46 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 7656078.46 | D. Survey | DDP
[8 empty] | Actual | [7 empty] | Actual
50km | 35 | 3 | BOQ | NCB | 7656078.46 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 7656078.46 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 7656078.46 | D. Survey | DDP
[8 empty] | Actual | [7 empty] | Actual
Purchases | 36 | 4 | BOQ | NCB | 2536428.17 | N/A | CEO | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 2536428.17 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 2536428.17 | D. Survey | DDP
[8 empty] | Actual | [7 empty] | Actual
GPS OBSERVATION OF CONTROLS NATION WIDE | [7 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 24402600 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 24402600 | D. Survey | DDP
(i). GPS observation of 75No. Primary Controls Nationwide | 37 | 1 | B. O. Q | NCB | 24402600 | N/A | PTB | Actual | [7 empty] | Actual
[8 empty] | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 5276752.15 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 5276752.15 | D. Survey | DDP
Project Safety materials-(Boots, Reflective jackets etc) | 38 | 2 | BOQ | NCB | 5276352.15 | N/A | PTB | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Plan | [7 empty] | Plan
DETERMINATION OF GEOIDAL UNDULATION IN VARIOUS PARTS OF TNIGERIA | [7 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 19522080 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 19522080 | D. Survey | DDP
(i). Observation of 60 No. Bench mark/ controls for vertical and horizontal values | 39 | 1 | B. O. Q | NCB | 19522080 | N/A | PTB | Actual | [7 empty] | Actual
[8 empty] | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 5360226.67 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 5360226.67 | D. Survey | DDP
(i) Procurement and training of Geoidal undulation Local software for data processing and analysis | 40 | 2 | BOQ | NCB | 5360226.67 | N/A | PTB | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Plan | [7 empty] | Plan
DIGITAL EQUIPMENT MAINTENANCE AND OVER HAUL | [7 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 2215144.88 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 2215144.88 | D. Survey | DDP
(i). Installation of 1No. A-3 color laser jet 9500N HP Printer and servicing of 3No. HP 6320 Printer | 41 | 1 | B. O. Q | NCB | 2215144.88 | N/A | CEO | Actual | [7 empty] | Actual
[8 empty] | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 4600000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 4600000 | D. Survey | DDP
(ii)Upgrading of Trimble R8 Data logger and replacement of internal Battery, power cable and other accessories | 42 | 2 | BOQ | NCB | 4600000 | N/A | PTB | Actual | [7 empty] | Actual
[8 empty] | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 3500000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 3500000 | D. Survey | DDP
(iii) Local Training on GNSS/GPS equipments and CORS | 43 | 2 | BOQ | NCB | 3500000 |  | CEO | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
CONSTRUCTION OF PRIMARY PILLARS (79 NOS) | [7 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 12500000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 12500000 | D. Survey | DDP
(i). Construction of Primary Pillars (NE & NC) | 55 | 1 | BOQ | NCB | 12500000 | N/A | PTB | Actual | [7 empty] | Actual
[8 empty] | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 12500000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 12500000 | D. Survey | DDP
(ii)Construction of Primary Pillars (NW) | 45 | 2 | BOQ | NCB | 12500000 | N/A | PTB | Actual | [7 empty] | Actual
[8 empty] | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 12500000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 12500000 | D. Survey | DDP
(iii) Construction of Primary Pillars (SE & SS) | 46 | 3 | BOQ | NCB | 12500000 |  | PTB | Actual | [7 empty] | Actual
[8 empty] | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 12475694.62 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 12475694.62 | D. Survey | DDP
(iv) Construction of Primary Pillars (SW & FCT) | 47 | 4 | BOQ | NCB | 12475694.62 |  | PTB | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
RECOVERY AND MAINTENANCE OF1ST & 2ND ORDER CONTROLS/SURVEY BEACONS | [7 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 6000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 6000000 | D. Survey | DDP
(i). Owerri - PHC Road (XTC Series) | 48 | 1 | BOQ | NCB | 6000000 | N/A | PTB | Actual | [7 empty] | Actual
[8 empty] | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 5796081.83 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 5796081.83 | D. Survey | DDP
(ii) Benin - Warri Road | 49 | 2 | BOQ | NCB | 5796081.83 | N/A | PTB | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
Creation, Demarcation and Furnishing of Additional office spaces. | 50 | 1 | BOQ | National Competitive Bidding | 6500000 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 6500000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 6500000 | DFA | DDP
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
HRM
Renovation and Partition of 8No. Office with aluminum coated frame and glass at OSGOF Hqts | 51 | 1 | BOQ | National Competitive Building | 5000000 | N/A | CEO | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 4950000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 3900000 | DHR | DDP
[8 empty] | Actual | [7 empty] | Actual
Maintenance and Renovation of two (2) OSGOF zonal Offices | 52 | 2 | BOQ | National Competitive Building | 30000000 |  | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 19000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 29850000 | DHR | DDP
Pilot Scheme Mapping at 1:25,000 |  | 1 | BOQ | National Competitive Building | 220163455.69 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 8849000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 8849000 | D(MAPPING) | DDP
[18 empty] | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014
[8 empty] | Actual | [7 empty] | Actual
Map Revision of 1:50,000 Topo Covering Nigeria | 53 | 1 | BOQ | National Competitive Building | 60596970 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 6300000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 6300000 | D(MAPPING) | DDP
[8 empty] | Actual | [7 empty] | Actual
Upgrading of the Converted 1:50,000 Topo Maps. | 54 | 1 | BOQ | National Competitive Building | 63393665 | N/A | PTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 5700000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 5700000 | D(MAPPING) | DDP
[8 empty] | Actual | [7 empty] | Actual
Topographical Mapping of Nigeria @ 1:100,000 & 1:250,000 | 55 | 1 | BOQ | National Competitive Building | 22925953.55 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 6000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 6000000 | D(MAPPING) | DDP
[8 empty] | Actual | [10 empty] | May | May
Electronic National Atlas | 56 | 2 | BOQ | National Competitive Building | 19693126.78 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 4500000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 4500000 | D(MAPPING) | DDP
Actual
Procurement and installation of Trimble Equipment at Minna | 57 | 3 | BOQ | NC Bidding | 12179838.1 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 12179838.1 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 12179838.1 | D(MAPPING) | DDP
Actual
Installation of Trimble Equipment at Ado-Ekiti | 58 | 1 | BOQ | NC Bidding | 11248338.5 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 11248338.5 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 11248338.5 | D(MAPPING) | DDP
[8 empty] | Actual | [7 empty] | Actual
Replacement and Upgrade of facilities at Gembu COR Station | 59 | 2 | Lump sum | N/A | 4931499.6 | N/A | CEO | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 4931499.6 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 4931499.6 | D(MAPPING) | DDP
[8 empty] | Actual | [7 empty] | Actual
Updating of Abuja Digital Street Guide & its Satellite Towns | 60 | 1 | Lump sum | NC Bidding | 12132258.93 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 12132258.93 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 12132258.93 | D(MAPPING) | DDP
[8 empty] | Actual | [7 empty] | Actual
Production of Street Guide Map of Uyo | 61 | 2 | Lump sum | NC Bidding | 9600230.18 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 9600230.18 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 9600230.18 | D(MAPPING) | DDP
[8 empty] | Actual | [7 empty] | Actual
Plan
Capacity Building, Local & International, AFREF,Training on GIS in South Africa & Professional Training in UK, USA | 62 | 1 | Lump sum | NC Bidding | 17340363.49 | N/A | PTB | Actual | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 17340363.49 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 17340363.49 | D(MAPPING) | DDP
Production of Street Guide Map of Dutse | 63 | 2 | Lump sum | NC Bidding | 9600102.43 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 9600102.43 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 9600102.43 | D(MAPPING) | DDP
[8 empty] | Actual | [7 empty] | Actual
Production of Street Guide Map of Osogbo | 64 | 3 | Lump sum | NC Bidding | 9573010.12 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 9573010.12 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 9573010.12 | D(MAPPING) | DDP
[8 empty] | Actual | [7 empty] | Actual
International Travel for FIG, AFREF etc., Meetings & Negotiations with Neighbouring Countries | 65 | 1 | Lump sum | NC Bidding | 15593857.38 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 15593857.38 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 15593857.38 | D(MAPPING) | DDP
Digitization of Survey Archives Maps and Plans | 66 | 2 | BOQ | Competitive Bidding | 15000000 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 15000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 15000000 | Director Survey Coordination | DD Procurement
[8 empty] | Actual | [7 empty] | Actual
Upgrading of Infrastructure of Map Depot in the Zonal Offices | 67 | 1 | BOQ | Competitive Bidding | 15000000 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 15000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 15000000 | Director Survey Coordination | DD Procurement
[8 empty] | Actual | [7 empty] | Actual
Township Mapping of State Capitals
(a) Township Mapping of Benin City, Edo State | 68 | 1 | BEME | OCB | 9970000 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 9968000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 9968000 | D (Cad/Legal) | DPP
[8 empty] | Actual | [7 empty] | Actual
(b)Township Mapping of Makurdi Benue State | 69 | 2 | BEME | OCB | 9750000 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 9749000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 9749000 | D (Cad/Legal) | DPP
[8 empty] | Actual | [7 empty] | Actual
©Township Mapping of Ilorin, Kwara State | 70 | 1 | BEME | OCB | 9580000 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 9577000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 9577000 | D (Cad/Legal) | DPP
[8 empty] | Actual | [7 empty] | Actual
(d) Township Mapping of Gombe, Gombe State | 71 | 1 | BEME | OCB | 9459000 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 9460000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 9460000 | D (Cad/Legal) | DPP
(1) Construction of 35 Nos of 2nd Order controls in Sokoto State | 72 | 2 | BEME | OCB | 8750000 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 8749000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 8749000 | D (Cad/Legal) | DPP
[8 empty] | Actual | [7 empty] | Actual
(2) Construction of 35 Nos of 2nd Order controls in Imo Satate | 73 | 1 | BEME | OCB | 8750000 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 8749000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 8749000 | D (Cad/Legal) | DPP
Construction of 2nd Order Cadastral Controls for | 74 | 1 | [5 empty] | Plan | [7 empty] | Plan
Township Mapping | [7 empty] | Actual | [7 empty] | Actual
(3) Construction of 35 Nos of 2nd Order controls in Kogi State | 75 | 2 | BEME | OCB | 8029000 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 8027500 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 8027500 | D (Cad/Legal) | DPP
[8 empty] | Actual | [7 empty] | Actual
Pilot Scheme Digital Cadastral Mapping of Nigeria. |  | 1 | [5 empty] | Plan | [7 empty] | Plan | [8 empty] | D (Cad/Legal) | DPP
[8 empty] | Actual | [7 empty] | Actual
(1)Standard Sheet 123, covering Kaduna, Kaduna State | 76 | 1 |  |  | 9959000 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 9959000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 9959000 | D (Cad/Legal) | DPP
[8 empty] | Actual | [7 empty] | Actual
(2) Standard Sheet 211, covering Jos, plateau State | 77 | 2 |  |  | 9948000 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 9948000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 9948000 | D (Cad/Legal) | DPP
[8 empty] | Actual | [7 empty] | Actual
(3) Standard Sheet 49, Birnin Kebbi, Kebbi State | 78 | 1 | BEME | OCB | 9940000 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 9935000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 9935000 | D (Cad/Legal) | DPP
[8 empty] | Actual | [7 empty] | Actual
(4). Standard Sheet 243, covering Osogbo, Osun State | 79 | 1 | BEME | OCB | 9949000 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 9948500 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 9948500 | D (Cad/Legal) | DPP
[8 empty] | Actual | [7 empty] | Actual
(3) Standard Sheet 327 Yenogoa Bayelsa State | 80 | 2 | BEME | OCB | 9955000 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 9954000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 9954000 | D (Cad/Legal) | DPP
[8 empty] | Actual | [7 empty] | Actual
(4). Standard Sheet 209 Warri Delta State | 81 | 1 | BEME | OCB | 9955000 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 9954000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 9954000 | D (Cad/Legal) | DPP
[8 empty] | Actual | [7 empty] | Actual
(b) Production of Cadastral Atlas of Oguta, Oguta L. G . A . Imo State | 82 | 1 | BEME | OCB | 9925000 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 9923000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 9923000 | D (Cad/Legal) | DPP
[8 empty] | Actual | [7 empty] | Actual
(b) Production of Cadastral Atlas of Minna, Nigerr State | 83 | 1 | BEME | OCB | 9934000 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 9938900 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 9938900 | D (Cad/Legal) | DPP
[8 empty] | Actual | [7 empty] | Actual
(c) Utility mapping of Awka, Anambra State | 84 | 2 | BEME | OCB | 7490000 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 7455000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 7455000 | D (Cad/Legal) | DPP
[8 empty] | Actual | [7 empty] | Actual
(b) Utility mapping of Asaba, Delta State | 85 | 1 | BEME | OCB | 7490000 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 74890000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 74890000 | D (Cad/Legal) | DPP
CREATION & MAINTENANCE OF NATIONAL GEOSPATIAL REPOSITORY OSGOF
Data Conversion of Analogue field survey data into digital equivalent | 86 | 1 | BOQ | OCB | 5000000 | N/A | CEO | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 5000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 5000000 | DPR&D | DDPP
[8 empty] | Actual | [7 empty] | Actual
Harmonization of Local Area Networks in the office | 87 | 2 | BOQ | OCB | 6500000 | N/A | PTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 6500000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 | 6500000 | DPR&D | DDPP
[8 empty] | Actual | [7 empty] | Actual
TOTAL |  |  |  |  | 1194594714.96

## CONSULTANCY
Ministry/Department/Agency: OFFICE OF THE SURVEYOR - GENERAL OF THE FEDERATION
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: Mr. E. O. Moses - 08064914125 |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | Plan vs. Actual | No-objection Date | FEC Approval | Contract Amount in Naira | Contract Offer | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | Plan | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | Plan | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 1- 2 wk | 2 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
List of Contracts
Developing of Stock Verification Data System for (6) Six Zonal Offices | NCB | Lumpsum | 2000000 | CEO | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 2,000,000.00 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26TH Aug- 2nd Sept | 3rd Sept- 10th Sept | 2,000,000.00 | H (SVU) | DDP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Electronic Stock Verification on Materials | NCB | Lumpsum | 800000 | CEO | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 8000000 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26TH Aug- 2nd Sept | 3rd Sept- 10th Sept | 8000000 | H (SVU) | DDP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Capital Project Monitoring Software | NCB | Lumpsum | 3200000 | PTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 3200000 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26TH Aug- 2nd Sept | 3rd Sept- 10th Sept | 3200000 | DD ( I Audit) | DDP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Prepayment Verification of Executed projects | NCB | Lumpsum | 4000000 | PTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 4000000 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26TH Aug- 2nd Sept | 3rd Sept- 10th Sept | 4000000 | DD (Audit) | DDP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Customized Audit Software in E-payment Enviroment | NCB | Lumpsum | 2400000 | CEO | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 2400000 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26TH Aug- 2nd Sept | 3rd Sept- 10th Sept | 2400000 | DD (Audit) | DDP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Technical support for verification of Survey projects | NCB | Lumpsum | 2400000 | CEO | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 2400000 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26TH Aug- 2nd Sept | 3rd Sept- 10th Sept | 2400000 | DD (Audit) | DDP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Sensitization on Prudent Budget Implementation | NCB | Lumpsum | 4000000 | PTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 4000000 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26TH Aug- 2nd Sept | 3rd Sept- 10th Sept | 4000000 | DD (Audit) | DDP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Consultancy Services for the Monitoring of On-Going Projects | RP | Lumpsum or Time-Based | 5000000 | PTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 5000000 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26TH Aug- 2nd Sept | 3rd Sept- 10th Sept | 5000000 | D. Boundaries | DPP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Advertisement of Capital Projects of N10m and Above in compliance with Due Process Guidelines | DP | Lumpsum | 10000000 | PTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 10000000 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26TH Aug- 2nd Sept | 3rd Sept- 10th Sept | 10000000 | D. Boundaries | DPP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Consultancy Services for the Monitoring of On-Going Projects | RP | Lumpsum or Time-Based | 5000000 | PTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 5000000 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26TH Aug- 2nd Sept | 3rd Sept- 10th Sept | 5000000 | D. Boundaries | DDP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Advertisement of Capital Projects of N10m and Above in compliance with Due Process Guidelines | DP | Lumpsum | 10000000 | PTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 10000000 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26TH Aug- 2nd Sept | 3rd Sept- 10th Sept | 10000000 | D. Boundaries | DDP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Legal Consultancy and Software Training | Open Competive Bidding | Lumpsum | 8000000 | PTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 8000000 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26TH Aug- 2nd Sept | 3rd Sept- 10th Sept | 8000000 | D. Boundaries | DDP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Capacity Building Programme - Training Programmes, Workshops Conferences, Seminars | National Competitive Bidding | Lumpsum | 4, 000, 000.00 | PTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 4, 000, 000.00 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26TH Aug- 2nd Sept | 3rd Sept- 10th Sept | 4, 000, 000.00 | Chairman (ACTU) | DDP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
(a)Sensitization/Inauguration of the field offices for Zonal and State Liaison Offices. (b)Joint Sensitization of ACTU Desk Officers of FMW/FERMA/OSGOF. | National Competitive Bidding | Lumpsum | 3, 000, 000.00 | PTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 3, 000, 000.00 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26TH Aug- 2nd Sept | 3rd Sept- 10th Sept | 3, 000, 000.00 | Chairman (ACTU) | DDP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Sensitization programme at the Headquarters in batches 1) Directorates cadre 2) GL 10 – 14 3) 3) GL 9 and below | National Competitive Bidding | Lumpsum | 1, 400, 000.00 | CEO | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 1, 400, 000.00 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26TH Aug- 2nd Sept | 3rd Sept- 10th Sept | 1, 400, 000.00 | Chairman (ACTU) | DDP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
(a)Sensitization/Inauguration of the field offices for Zonal and State Liaison Offices.(b)Joint Sensitization of ACTU Desk Officers of FMW/FERMA/OSGOF. | National Competitive Bidding | Lumpsum | 1, 100, 000.00 | CEO | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 1, 100, 000.00 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26TH Aug- 2nd Sept | 3rd Sept- 10th Sept | 1, 100, 000.00 | Chairman (ACTU) | DDP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
EXECUTION OF SPECIAL SURVEY PROJECTS |  |  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
(ii). Consultancy Services for Subsidence and Deformation of heavy Engineering structures to include Bridges, Dams and Oil Tank Farm. | NCB | Time Based | 9455263.72 | PTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 9455263.72 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26TH Aug- 2nd Sept | 3rd Sept- 10th Sept | 9455263.72 | D. Survey | DDP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
(iii). Stakeholders' Campaign on National Gravity Surveys | NCB | Lumpsum | 8317752.69 | PTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 8317752.69 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26TH Aug- 2nd Sept | 3rd Sept- 10th Sept | 8317752.69 | D. Survey | DDP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Capital Project Monitoring/Verification | Open Competive Bidding | Lumpsum | 12000000 | PTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 12000000 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26TH Aug- 2nd Sept | 3rd Sept- 10th Sept | 12000000 | DFA | DDP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Management Software for e-Payment Expenditure and other Returns | Open Competive Bidding | Lumpsum | 4000000 | PTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 4000000 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26TH Aug- 2nd Sept | 3rd Sept- 10th Sept | 4000000 | DFA | DDP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Manpower Development in Public Finance and Treasury Practices | Open Competive Bidding | Lumpsum | 8000000 | PTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 8000000 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26TH Aug- 2nd Sept | 3rd Sept- 10th Sept | 8000000 | DFA | DDP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Insurance of OSGOF Hqts. Building at Abuja including office equipment | National competitive building | Lumpsum | 10,000,000.0 | PTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 10,000,000.0 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26TH Aug- 2nd Sept | 3rd Sept- 10th Sept | 10,000,000.0 | DHR | DDP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Consultancy Services for the Evaluation of Technical Projects | National competitive building | Lumpsum | 10,000,000.00 | PTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 10,000,000.00 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26TH Aug- 2nd Sept | 3rd Sept- 10th Sept | 10,000,000.00 | AD (FA) | DDP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Consultancy Services for Monitoring of Ongoing Capital Project in OSGOF. | National competitive building | Lumpsum | 3,500,000.00 | PTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 3495000 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26TH Aug- 2nd Sept | 3rd Sept- 10th Sept | 3,500,000.00 | DDP | SGOF
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Advertisement of capital projects in the national dailies | National competitive building | Lumpsum | 18000000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 17950000 |  |  | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 18000000 | DDP | SGOF
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Actual
Actual
Consultancy Services for Seminars, Consultations and Meetings with different sectors on Survey Coordination issues | National Competitive Bidding | L/S | 5000000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 5000000 | Director Survey Coordination | DD Procurement
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Consultancy Services for Review/Updating of the Survey Coordination Act of 1962 and its Amendments | National Competitive Bidding | L/S | 10000000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 10000000 | Director Survey Coordination | DD Procurement
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Consultancy Services for Establishment of Registry of Stakeholders in Geospatial Data Acquisition | National Competitive Bidding | L/S | 5000000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 5000000 | Director Survey Coordination | DD Procurement
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Consultancy Services for Monitoring of the Projects of the Various Sectors such as Multinational Oil Companies, MDA's and Other Stakeholders for Compliance with the Provision of Survey Coordination Act Provision of Survey Coordination Act | National Competitive Bidding | L/S | 20000000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 20000000 | Director Survey Coordination | DD Procurement
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Consultancy Services for Maintenance of Survey Coordination and Advisory Board on Survey Training Conference | National Competitive Bidding | L/S | 25000000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 25000000 | Director Survey Coordination | DD Procurement
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Consultancy Services for Production and Upgrading of Technical Manual Specifications and Instructions | National Competitive Bidding | L/S | 5000000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 5000000 | Director Survey Coordination | DD Procurement
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Consultancy Services for Monitoring, Coordination and Supervision of all Field Operations of the Zones | National Competitive Bidding | L/S | 20000000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 20000000 | Director Survey Coordination | DD Procurement
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Consultancy Services for Relating and Interfacing with Ordinance Survey of UK and Other Relevant Survey Institutions | National Competitive Bidding | L/S | 15000000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 15000000 | Director Survey Coordination | DD Procurement
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Consultancy Services for Quality Control of Related Activities in the various Sectors of the Economy Affected by the Coordination Act | National Competitive Bidding | L/S | 10000000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 10000000 | Director Survey Coordination | DD Procurement
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Consultancy Services for Pooling of Surveyors in all MDA's in the Country | National Competitive Bidding | L/S | 5000000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 5000000 | Director Survey Coordination | DD Procurement
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Consultancy Services for Monuments (Passive and Active) in the Six Geo-Political Zones | National Competitive Bidding | L/S | 10000000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 10000000 | Director Survey Coordination | DD Procurement
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Optimizing Transformation Parameters | National Competitive Bidding | Lump sum | 8700000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 8700000 | DPR&D | DDPP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Rigorous Adjustment of zero order control Network. | National Competitive Bidding | Lump sum | 9000000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 9000000 | DPR&D | DDPP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Preparation of Policy on CORS | National Competitive Bidding | Lump sum | 2300000 | CEO | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 2300000 | DPR&D | DDPP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
CREATION & MAINTENANCE OF NATIONAL GEOSPATIAL REPOSITORY OSGOF
Uploading of geodata into the database. | National Competitive Bidding | Lump sum | 7000000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 7000000 | DPR&D | DDPP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Payment of Internet subscription | National Competitive Bidding | Lump sum | 4000000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 4000000 | DPR&D | DDPP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Payment of Office Portal Maintenance | National Competitive Bidding | Lump sum | 2500000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 2500000 | DPR&D | DDPP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Payment of subscription for software | National Competitive Bidding | Lump sum | 6000000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 6000000 | DPR&D | DDPP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
AQUISITION OF DATABASE HIGH PERFORMANCE SERVER
On-point Solution of e-commerce prepaid | National Competitive Bidding | Lump sum | 17000000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 17000000 | DPR&D | DDPP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Training on Database Software and Operations | National Competitive Bidding | Lump sum | 9500000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 9500000 | DPR&D | DDPP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Supports for the Database hard ware and Software | National Competitive Bidding | Lump sum | 7000000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 7000000 | DPR&D | DDPP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Network Security for Servers | National Competitive Bidding | Lump sum | 9000000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 9000000 | DPR&D | DDPP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Project Monitoring in NW | National Competitive Bidding | Lump sum | 2500000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 2500000 | DPR&D | DDPP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Project Monitoring in SW | National Competitive Bidding | Lump sum | 3000000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 3000000 | DPR&D | DDPP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Project Monitoring in NC | National Competitive Bidding | Lump sum | 2500000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 2500000 | DPR&D | DDPP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Project Monitoring in SE | National Competitive Bidding | Lump sum | 2500000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 2500000 | DPR&D | DDPP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Project Monitoring in NE | National Competitive Bidding | Lump sum | 2500000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 2500000 | DPR&D | DDPP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Project Monitoring in SS | National Competitive Bidding | Lump sum | 3000000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 3000000 | DPR&D | DDPP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
COLLABORATION ON SCIENTIFIC AND SKILL EXCHANGE PROGRAM
Collaboration with Ordinance Survey United Kingdom | National Competitive Bidding | Lump sum | 8000000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 8000000 | DPR&D | DDPP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Collaboration with Head of Service on restructuring the Office scheme of service for Optimum performance. | National Competitive Bidding | Lump sum | 8000000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 8000000 | DPR&D | DDPP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Collaboration with ESRI california, USA for Training in GIS and data management | National Competitive Bidding | Lump sum | 9000000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 5000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 9000000 | DPR&D | DDPP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Collaboration with National Emergency Management Agency, Nigeria. | National Competitive Bidding | Lump sum | 3000000 | PTB | Plan | 5th Mar- 21 Mar | 24th Mar- 31st Mar | 1st April- 15th April | 16th April- 23rd April | 24th April- 2nd May | 5th May- 12th May | Plan | 13th May- 11th June | 11th June | 12th June- 26th June | 27th June- 11th July | 14th July- 28th July | 29th July- 12th Aug | 13th Aug- 27th Aug | Plan | N/A | N/A | 3000000 | 28th Aug- 4th Sept | 5th Sept- 19th Sept | Plan | N/A | 22nd Sept- 29th Sept | 30th Sept- 7th Oct | 3000000 | DPR&D | DDPP
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
TOTAL |  |  | 372573016.41

## N EX. IM. BANK
APPENDIX I PROCUREMENT RECORDS
PROCURING ENTITY (MDA) : |  | NIGERIAN EXPORT-IMPORT BANK
MINISTRY : |  | FEDERAL MINISTRY OF FINANCE
FINANCIAL YEAR : |  | 2014
| BASIC DATA | [9 empty] | CONTRACT AWARD |  |  |  |  | CONTRACT IMPLEMENTATION
S/N | CONTRACT DESCRIPTION | DATE ADVERT PUBLISHED AND MEDIA | APPROVAL THRESHOLD | PROCUREMENT METHOD | BID OPENING DATE | BIDS EVALUATION REPORT DATE | BUDGETARY PROVISION (NGN) | DATE OF CERTIFICATE OF NO OBJECTION | APPROVAL DATE BY AO/MTB/FEC | AWARDED TO LEAST TENDERER | CONTRACTOR | DATE OF CONTRACT AWARD | CONTRACT VALUE (NGN) | CONTRACT PERIOD | DATE OF COMMENCEMENT (PHYSICAL MOBILIZATION) | AMOUNT PAID AS AT 31/12/2013 (NGN) | EXPECTED COMPLETION DATE | PROJECT STATUS | % OF COMPLETION AS AT 31/12/2013 | DATE OF VARIATION APPROVAL IF ANY | VARIATION AMOUNT (NGN) | REMARKS
1 | 14 nosOperational vehicles | _ | _ | Direct purchase | _ | _ | 169000000 | _ | _ | _ | Coscharis Motors& Elizade Nigeria Limited | _ | _ | _ | _ | _ | Upon receipt of award letter | _ | _ | _ | _ | On-going
2 | 1200 KVA Mantrac Generator (Caterpillar) | _ | _ | Direct purchase | _ | _ | 56000000 | 22/03/2012 | 2013-06-12 | _ | Mantrac Nigeria Limited | _ | _ | _ | _ | _ | Upon receipt of award letter | _ | _ | _ | _ | On-going
3 | Correction of structural defect/ Renovation of Head Office | 17/06/2013 | _ | Open bidding | _ | _ | 250000000 | _ | _ | Nil | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | On-going
4 | Information Technology | _ | _ | Open bidding | _ | _ | 232728804 | 26/03/2013 | _ | _ | Computer Warehouse Group | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | Awaiting Approval/On-going
5 | Archive Document Management toward paperless office | _ | _ | Open bidding | _ | _ | 35000000 | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | On-going

## NSCDC GOODS
|  | Ministry/Department/Agency: NIGERIA SECURITY AND CIVIL DEFENCE CORPS | [5 empty] | THE TIME LINE IS TO BE COMPARED WITH THE COUNCILS APPROVAL
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: ACG ABDULLAHI GANA MOH'D |  | BASIC DATA | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* MATERIAL AND SUPPLIES GENERAL (GOODS) | Package Number | Lot Number |  | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Plan vs. Actual | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
PURCHASE OF MOTOR VEHICLES | N/A | N/A |  | 29000000
Procurement of 3 nos. Ambulances with gadgets for emergency and disaster management | GDS.001 | 01 |  | 29000000 | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 29000000 | N/A | 2-3Wks | Date on Award Letter | N/A | 3wks after awards | Date of arrival | HOD Disaster Mgt Unit | ACG Procurement
ACTUAL
PURCHASE OF VANS | N/A | N/A |  | 73000000
Procurement of 10 nos. Operational Pick-up Van | GDS.002 | 02 |  | 73000000 | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 73000000 | N/A | 2-3Wks | Date on Award Letter | N/A | 3wks after awards | Date of arrival | DCG Operations | ACG Procurement
PURCHASE OF SECURITY EQUIPMENT | N/A | N/A |  | 69115386
Procurement of Disaster Mgt. Equipment. | GDS.003 | 03 |  | 30000000 | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 30000000 | N/A | 2-3Wks | Date on Award Letter | N/A | 3wks after awards | Date of arrival | DCG Operations | ACG Procurement
2 Nos Spreaders | GDS.003 | 03A | 5000000 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 0 | N/A | 2-3Wks | Date on Award Letter | N/A | 3wks after awards | Date of arrival | DCG Operations | ACG Procurement
10 Nos Cutter | GDS.003 | 03B | 25000000 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 0 | N/A | 2-3Wks | Date on Award Letter | N/A | 3wks after awards | Date of arrival | DCG Operations | ACG Procurement
Procurement of Anti-Vandal Equipment | GDS.004 | 04 |  | 14740386
100 Unit Fragmented Jacket | GDS.004 | 04A | 4800000 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 0 | N/A | 2-3Wks | Date on Award Letter | N/A | 3wks after awards | Date of arrival | HOD Anti Vandal Unit | ACG Procurement
300 Unit Binocular Digital Camera | GDS.004 | 04B | 2000000 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 0 | N/A | 2-3Wks | Date on Award Letter | N/A | 3wks after awards | Date of arrival | HOD Anti Vandal Unit | ACG Procurement
50 Nos Master Stun Gun (Police Stun Gun) | GDS.004 | 04C | 2665000 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 0 | N/A | 2-3Wks | Date on Award Letter | N/A | 3wks after awards | Date of arrival | HOD Anti Vandal Unit | ACG Procurement
120 Nos Binocular | GDS.004 | 04C | 5275386 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 0 | N/A | 2-3Wks | Date on Award Letter | N/A | 3wks after awards | Date of arrival | HOD Anti Vandal Unit | ACG Procurement
Communication Equipment | GDS.005 | 05 |  | 12375000
8 Nos Router | GDS.005 | 05A | 480000 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 0 | N/A | 2-3Wks | Date on Award Letter | N/A | 3wks after awards | Date of arrival | HOD Communication Unit | ACG Procurement
50 Nos Digital Camera | GDS.005 | 05B | 4750000 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 0 | N/A | 2-3Wks | Date on Award Letter | N/A | 3wks after awards | Date of arrival | HOD Communication Unit | ACG Procurement
2 Nos HP Server | GDS.005 | 05C | 810000 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 0 | N/A | 2-3Wks | Date on Award Letter | N/A | 3wks after awards | Date of arrival | HOD Communication Unit | ACG Procurement
30 Nos Thermal Sensor | GDS.005 | 05D | 1470000 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 0 | N/A | 2-3Wks | Date on Award Letter | N/A | 3wks after awards | Date of arrival | HOD Communication Unit | ACG Procurement
96 PCS Intwercom Intercom Telephone Boxes | GDS.005 | 05E | 1229000 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 0 | N/A | 2-3Wks | Date on Award Letter | N/A | 3wks after awards | Date of arrival | HOD Communication Unit | ACG Procurement
36 Nos Customized Wrist Watches Recorder and Reminder | GDS.005 | 05F | 3636000 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 0 | N/A | 2-3Wks | Date on Award Letter | N/A | 3wks after awards | Date of arrival | HOD Communication Unit | ACG Procurement
Procurement of Anti -Terrorism Equipment | GDS.006 | 06 |  | 12000000
26 Nos Telephone Inerception/ Cellular | GDS.006 | 06A | 8736000 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 0 | N/A | 2-3Wks | Date on Award Letter | N/A | 3wks after awards | Date of arrival | HOD Counter-terrorism Unit | ACG Procurement
20 Nos Viper (Police Stun Gun) | GDS.006 | 06B | 1066520 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 0 | N/A | 2-3Wks | Date on Award Letter | N/A | 3wks after awards | Date of arrival | HOD Counter-terrorism Unit | ACG Procurement
98 Nos Wall Penetrators (Wall has ear) | GDS.006 | 06C | 2197480 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 0 | N/A | 2-3Wks | Date on Award Letter | N/A | 3wks after awards | Date of arrival | HOD Counter-terrorism Unit | ACG Procurement
PURCHASE OF DEFENCE EQUIPMENT | GDS.007 | N/A |  | 162721500.22
Operational Equipment | GDS.007 | 07
700 Nos GOTA Handset with 300 F155 Set and 30 Cassette from NIGCOSAT | GDS.007 | 07A | 60000000 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 0 | N/A | 2-3Wks | Date on Award Letter | N/A | 3wks after awards | Date of arrival | DCG Operations | ACG Procurement
60 Nos Individual Protective Equipment (Flex Force Modular Hard Shell Crowd Control System FX-1) | GDS.007 | 07B | 5760000 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 0 | N/A | 2-3Wks | Date on Award Letter | N/A | 3wks after awards | Date of arrival | DCG Operations | ACG Procurement
90 Nos Explosive Detonator/ Distruptor | GDS.007 | 07C | 7240000 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 0 | N/A | 2-3Wks | Date on Award Letter | N/A | 3wks after awards | Date of arrival | DCG Operations | ACG Procurement
Procurement Of Arms and Ammunition | GDS.008 | 08
83 Nos Pistol | GDS.008 | 08A | 7428500 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 0 | N/A | 2-3Wks | Date on Award Letter | N/A | 3wks after awards | Date of arrival | HOD Armed Squad Unit | ACG Procurement
360 Boxes of Ammunition | GDS.008 | 08B | 12793000 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 0 | N/A | 2-3Wks | Date on Award Letter | N/A | 3wks after awards | Date of arrival | HOD Armed Squad Unit | ACG Procurement
100 Nos AK 47 Riffle | GDS.008 | 08C | 25000000 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 0 | N/A | 2-3Wks | Date on Award Letter | N/A | 3wks after awards | Date of arrival | HOD Armed Squad Unit | ACG Procurement
100 Nos G3 Riffle | GDS.008 | 08D | 20000000 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 0 | N/A | 2-3Wks | Date on Award Letter | N/A | 3wks after awards | Date of arrival | HOD Armed Squad Unit | ACG Procurement
100 Nos. Ballistic Bullet Proof | GDS.008 | 08E | 12000000 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 0 | N/A | 2-3Wks | Date on Award Letter | N/A | 3wks after awards | Date of arrival | HOD Armed Squad Unit | ACG Procurement
100 Nos Ballistic Helmet. | GDS.008 | 08F | 12500000.22 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 0 | N/A | 2-3Wks | Date on Award Letter | N/A | 3wks after awards | Date of arrival | HOD Armed Squad Unit | ACG Procurement
333836886.22
SUMMARY
GOODS |  |  |  | 333836886.22
WORKS |  |  |  | 501247113.78
TOTAL |  |  |  | 835084000
KEY
NCB |  | NATIONAL COMPETITIVE BIDDING
CDTB |  | CIVIL DEFENCE TENDER BOARD

## NSCDC WORKS
Ministry/Department/Agency: NIGERIA SECURITY AND CIVIL DEFENCE CORPS | [7 empty] | THE TIME LINE IS TO BE COMPARED WITH THE COUNCILS APPROVAL
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: ACG ABDULLAHI GANA MOH'D |  | BASIC DATA | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* MATERIAL AND SUPPLIES GENERAL(WORKS) | Package Number | Lot Number |  | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Plan vs. Actual | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment (15%) | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts | [6 empty] | w
CONSTRUCTION OF OFFICE BUILDING | WKS.001 |  |  | 327096830
ACTUAL
Construction & Completion of 2 out of 37 States Command HQ (Abeokuta and Katsina) | WKS.001 | 01A |  | 13081686 | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 13081686 | N/A | 2-3WKS | 4WKS | 1962252.9 | N/A | Based on Valuation Certificate | HOD Works & Logistics unit | ACG Procurement
Completion of 8 Nos Standard Classrooms blocks of 3 Classes each at training school land donated by Ogun State. | WKS.001 | 01B |  | 29308071 | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 29308071 | N/A | 2-3WKS | 4WKS | 4396210.65 | N/A | Based on Valuation Certificate | HOD Works & Logistics unit | ACG Procurement
Completion of NHQ Complex Abuja | WKS.001 | 01C |  | 284707072 | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 284707072 | N/A | 2-3WKS | 4WKS | 42706060.8 | N/A | Based on Valuation Certificate | HOD Works & Logistics unit | ACG Procurement
Construction of Phase 3 Admin Block | WKS.001 |  | 100273113 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 100273113 | N/A | 2-3WKS | 4WKS | 15040966.95 | N/A | Based on Valuation Certificate | HOD Works & Logistics unit | ACG Procurement
Completion of 6 Units of 3 Bedroom Flat of 2 Srorey Building | WKS.001 |  | 51283050 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 51283050 | N/A | 2-3WKS | 4WKS | 7692457.5 | N/A | Based on Valuation Certificate | HOD Works & Logistics unit | ACG Procurement
Completion of 4 Units of 3 Bedroom Flats, Football Field, In-door Sporting Complex at Sauka, | WKS.001 |  | 46489985.36 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 46489985.36 | N/A | 2-3WKS | 4WKS | 6973497.804 | N/A | Based on Valuation Certificate | HOD Works & Logistics unit | ACG Procurement
Completion of 20 Units of 1 Bedroom Flats of One Storey Buiding at Sauka | WKS.001 |  | 60602538.81 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 60602538.81 | N/A | 2-3WKS | 4WKS | 9090380.8215 | N/A | Based on Valuation Certificate | HOD Works & Logistics unit | ACG Procurement
Construction of Warehouse at Sauka | WKS.001 |  | 26058384.83 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 26058384.83 | N/A | 2-3WKS | 4WKS | 3908757.7245 | N/A | Based on Valuation Certificate | HOD Works & Logistics unit | ACG Procurement
CONSTRUCTION OF 2 OUT OF 8 BARRACKS FOR NSCDC | [7 empty] | PLAN
|  |  |  | 158929245 |  |  |  | ACTUAL
Completion of Block of 36 units of 1 bedroom at abeokuta. | WKS.002 |  | 24237052.48 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 24237052.48 | N/A | 2-3WKS | 4WKS | 3635557.872 | N/A | Based on Valuation Certificate | HOD Works & Logistics unit | ACG Procurement
Completion of Male Hostel at college of Security Mgt. abeokuta. | WKS.002 |  | 46519152.02 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 46519152.02 | N/A | 2-3WKS | 4WKS | 6977872.803 | N/A | Based on Valuation Certificate | HOD Works & Logistics unit | ACG Procurement
Completion of 4 units of 3 bedroom flats at college of security mgt. abeokuta. | WKS.002 |  | 35419860 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 35419860 | N/A | 2-3WKS | 4WKS | 5312979 | N/A | Based on Valuation Certificate | HOD Works & Logistics unit | ACG Procurement
Completion of male hostel at katsina training school. | WKS.002 |  | 46334757.23 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 46334757.23 | N/A | 2-3WKS | 4WKS | 6950213.5845 | N/A | Based on Valuation Certificate | HOD Works & Logistics unit | ACG Procurement
Completion of 36 units of 2 bedrooms flat at Katsina. | WKS.002 |  | 6418423.27 |  | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 6418423.27 | N/A | 2-3WKS | 4WKS | 962763.4905 | N/A | Based on Valuation Certificate | HOD Works & Logistics unit | ACG Procurement
ACTUAL
COMPLETION OF INDOOR SHOOTING RANGE | WKS.003 | 03A |  | 15221038.78 | NCB | N/A | CDTB | PLAN | Jan-Feb | Feb | Mar | Mar 21st | April 26th | May 2nd | N/A |  | 15221038.78 | N/A | 2-3WKS | 4WKS | 2283155.817 | N/A | Based on Valuation Certificate | HOD Works & Logistics unit | ACG Procurement
ACTUAL
TOTAL |  |  |  | 501247113.78

## NDIC Goods
Ministry/Department/Agency:NDIC
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #:S.Magaji |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
1.Supply of E3500 Hand Held Explosive Detector | N/A | LOT 1 | 14000000 | NCB | Post-Qualification |  | Plan |  |  |  | 21/04/2014 | 26/05/2014 | 9/06/2014 | N/A | Plan
[7 empty] | Actual | [7 empty] | Actual
date
2. Provision of Bollard System | N/A | LOT 2 | 14000000 | NCB | Post-Qualification |  | Plan |  |  |  | 21/04/2014 | 26/05/2014 | 9/06/2014 | N/A
[7 empty] | Actual | [7 empty] | 2 weeks
3. Provision of Desktop Computers and lasercolor printer | N/A | LOT 3 | 10678650 | NCB | Post-Qualification |  | Plan |  |  |  | 21/04/2014 | 26/05/2014 | 9/06/2014 | N/A | Plan
[7 empty] | Actual | [7 empty] | Actual
4.Provision of operational vehicles | N/A | LOT 1 | 505471695 | Direct Proc. | Post-Qualification |  | Plan |  |  |  | 12/05/2014 | 23/06/2014 | 7/07/2014 | N/A | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Plan
[7 empty] | Actual | [7 empty] | 2 weeks
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Plan
[7 empty] | Actual | [7 empty] | 2 weeks

## NDIC Works
Ministry/Department/Agency:NDIC
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #:S.Magaji |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
1.Replacement of ascoustic suspended ceiling |  |  | BOQ | NCB | 98481796 |  |  | Plan | N/A | N/A | N/A | 10/04/2014 | 22/05/2014 | 5/06/2014 | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
2.Upgrading of Direct Expansion Unit for ITD |  |  | BOQ | NCB | 25000000 |  |  | Plan | N/A | N/A | N/A | 10/04/2014 | 22/05/2014 | 5/06/2014 | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
3.Purchase of Land/Agency Fees for Ilorin zonal office |  |  | BOQ | NCB | 265650000 |  |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | 10/06/2014 | Plan
[8 empty] | Actual | [7 empty] | Actual
4.Renovation of Kano Zonal Office |  |  |  |  | 67000000 |  |  | Plan | N/A | N/A | N/A |  |  |  |  | Plan
|  |  | BOQ | NCB |  |  |  | Actual |  |  |  | 10/04/2014 | 22/05/2014 | 5/06/2014 | N/A | Actual
5.Flood Control at Benin Zonal office |  |  | BOQ | NCB | 10000000 |  |  | Plan | N/A | N/A | N/A | 1004/2014 | 22/05/2014 | 5/06/2014 | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
6. Repair of roof at Benin Zonal Office |  |  | BOQ | NCB | 10000000 |  |  | Plan | N/A | N/A | N/A | 5/05/2014 | 16/06/2014 | 30/06/2014 | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
7.Staff recreation & Gym facilities |  |  | BOQ | NCB | 1 19,600,000.00 |  |  | Plan | N/A | N/A | N/A | 5/05/2014 | 16/06/2014 | 30/06/2014 | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
8.Provision of Central Solar Energy for Central Ups |  |  | BOQ | NCB | 40000000 |  |  | Plan | N/A | N/A | N/A | 5/05/2014 | 16/06/2014 | 30/06/2014 | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
9.Upgrading of Rooptop Units for Conference hall. |  |  | BOQ | NCB | 17000000 |  |  | Plan | N/A | N/A | N/A | 5/05/2014 | 16/06/2014 | 30/06/2014 | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
10.Provision of step Hedge Profile at the Head Office building |  |  | BOQ | NCB | 11000000 |  |  | Plan | N/A | N/A | N/A | 5/05/2014 | 16/06/2014 | 30/06/2014 | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
11.Provision of lift Aesthetics |  |  | BOQ | NCB | 15,000,000.00 |  |  | Plan | N/A | N/A | N/A | 5/05/2014 | 16/06/2014 | 30/06/2014 | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
12.Upgrading driveway from ICPC gate to NDIC |  |  | BOQ | NCB | 10000000 |  |  | Plan | N/A | N/A | N/A | 3/06/2014 | 15/07/2014 | 29/07/2014 | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
13.Construction of perimeter fence/gate house at Ilorin Zonal Office |  |  | BOQ | NCB | 25000000 |  |  | Plan | N/A | N/A | N/A | 10/06/2014 | 22/07/2014 | 5/08/2014 | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
14.Construction of perimeter fence and gate house at Sokoto Zonal Office |  |  | BOQ | NCB | 40000000 |  |  | Plan | N/A | N/A | N/A | 10/06/2014 | 22/07/2014 | 5/08/2014 | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Actual | N/A | N/A | N/A | 10/06/2014 | 22/07/2014 | 5/08/2014 | N/A | Actual
15.Replacement of PVC tiles with granite floor tiles |  |  | BOQ | NCB | 258194440 |  |  | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
16. Mobilization to site and Construction of Portharcourt zonal Office |  |  | BOQ | NCB | 500000000 |  |  | Plan | N/A | N/A | N/A | 10/06/2014 | 22/07/2014 | 5/08/2014 | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
17.Mobilization to site and Construction of Sokoto Zonal Office |  |  |  | NCB | 500000000 |  |  | Plan | N/A | N/A | N/A | 10/06/2014 | 22/07/2014 | 5/08/2014 | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
18.Mobilization to site Construction and construction of Bauchi Zonal Office.. |  |  | BOQ | NCB | 500000000 |  |  | Plan | N/A | N/A | N/A | 10/06/2014 | 22/07/2014 | 5/08/2014 | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
19..Mobilzation to site and construction of Yola Zonal Office |  |  | BOQ | NCB | 50000000 |  |  | Plan | N/A | N/A | N/A | 10/06/2014 | 22/07/2014 | 5/08/2014 | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
20.Construction of perimeter fence and gate house at Sokoto Zonal Office |  |  | BOQ | NCB | 40000000 |  |  | Plan | N/A | N/A | N/A | 10/06/2014 | 22/07/2014 | 5/08/2014 | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 2368844440 |  |  | Plan | [7 empty] | Plan | #NAME? | [6 empty] | 0
[5 empty] | 2368844440 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## NDIC Consultancy
Ministry/Department/Agency:NDIC
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #:S.Magaji |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Prior/Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
Consultancy Service for the construction of Ilorin Zonal Office. | QCBS | Time-Based | 80000000 | Prior-review | Plan |  |  | 8/04/2014 | 29/04/2014 | 13/05/2014 | 20/05/2014 | Plan | 27/05/2014 | 8/07/2014 | 22/07/2014 | 19/08/2014 | 26/08/2014 | 9/09/2014 | 23/09/2014 | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
2. Consultancy Service for the construction of Sokoto Zonal Office. | QCBS | Time-Based | 80000000 | Prior-review | Plan |  |  | 8/04/2014 | 29/04/2014 | 13/05/2014 | 20/05/2014 | Plan | 27/05/2014 | 8/07/2014 | 22/07/2014 | 19/08/2014 | 26/08/2014 | 9/09/2014 | 23/09/2014 | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
3. Consultancy Services for the construction of Yola Zonal Office. | QCBS | Time-Based | 80000000 | Prior-review | Plan |  |  | 8/04/2014 | 29/04/2014 | 13/05/2014 | 20/05/2014 | Plan | 27/05/2014 | 8/07/2014 | 22/07/2014 | 19/08/2014 | 26/08/2014 | 9/09/2014 | 23/09/2014 | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
4. Consultancy Services for the construction of Bauchi Zonal Office | QCBS | Time-Based | 80000000 | Prior-review | Plan |  |  | 8/04/2014 | 29/04/2014 | 13/05/2014 | 20/05/2014 | Plan | 27/05/2014 | 8/07/2014 | 22/07/2014 | 19/08/2014 | 26/08/2014 | 9/09/2014 | 23/09/2014 | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
5.Training on Risk Management and Corporate financing | CQ | Time- Based | 36585000 | Prior-review | Plan |  |  | 5/05/2014 | 26/05/2014 | 09/06/2014 | 16/06/14 | Plan | 23/06/2014 | 4/08/2014 | 18/08/2014 | 15/09/2014 | 22/09/2014 | 6/10/2014 | 20/10/2014 | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
6.Training on Enterprise Risk Management & BASEL II/III | CQ | Time-Based | 41985175 | Prior-review | Plan |  |  | 5/05/2014 | 26/05/2014 | 09/06/2014 | 16/06/14 | Plan | 23/06/2014 | 4/08/2014 | 18/08/2014 | 15/09/2014 | 22/09/2014 | 6/10/2014 | 20/10/2014 | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
7. Training on Alternative dispute resolution(ADR) Techniques and options. | CQ | Time-Based | 18243243 | Prior-review | Plan |  |  | 5/05/2014 | 26/05/2014 | 09/06/2014 | 16/06/14 | Plan | 23/06/2014 | 4/08/2014 | 18/08/2014 | 15/09/2014 | 22/09/2014 | 6/10/2014 | 20/10/2014 | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
8. Capacity building on stratergic budgeting and cost control. | CQ | Time-based | 8991950 |  | Plan |  |  | 5/05/2014 | 26/05/2014 | 09/06/2014 | 16/06/14 | Plan | 23/06/2014 | 4/08/2014 | 18/08/2014 | 15/09/2014 | 22/09/2014 | 6/10/2014 | 20/10/2014 | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
9.Training on employee mentoring and counselling | CQ | Time-based | 15000000 |  | Plan |  |  | 5/05/2014 | 26/05/2014 | 09/06/2014 | 16/06/14 | Plan | 23/06/2014 | 4/08/2014 | 18/08/2014 | 15/09/2014 | 22/09/2014 | 6/10/2014 | 20/10/2014 | Plan | [6 empty] | Plan
Total Cost |  |  | 440805368 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 0 |  |  |  | Plan |  |  |  | 0
|  |  | #REF! |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | #REF! |  |  |  | Actual |  |  |  | #REF!
Fill gray cells only!

## NDIC Works (2)
Ministry/Department/Agency:NDIC
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #:S.Magaji |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
21.Supply and Installation of IP-CCTV |  |  | BOQ | NCB | 17820 |  |  | Plan | N/A | N/A | N/A | 10/04/2014 | 22/05/2014 | 5/06/2014 | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
22.Supply and Installation of Biometric Staff identification and Attendance(Abuja) |  |  | BOQ | NCB | 31185000 |  |  | Plan | N/A | N/A | N/A | 10/04/2014 | 22/05/2014 | 5/06/2014 | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
23.Suplly and Installation of Walkthrough Metal Detectors |  |  | BOQ | NCB | 14000000 |  |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
24.Supply and Installation of Door Access Control (Head Office) |  |  |  |  | 39000000 |  |  | Plan | [7 empty] | Plan
|  |  | BOQ | NCB |  |  |  | Actual | N/A | N/A | N/A | 10/04/2014 | 22/05/2014 | 5/06/2014 | N/A | Actual
25.Supply and Installation of Door Access Control (Lagos) |  |  | BOQ | NCB | 43768616 |  |  | Plan | N/A | N/A | N/A | 10/4/2014 | 22/05/2014 | 5/06/2014 | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
26.Supply and Installation of Staff Biometric Staff identification and attendance(Lagos Office) |  |  | BOQ | NCB | 18711000 |  |  | Plan | N/A | N/A | N/A | 5/05/2014 | 16/06/2014 | 30/06/2014 | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
27 Supply and Installation of Door Access Control (Zonal Offices) |  |  | BOQ | NCB | 65243144 |  |  | Plan | N/A | N/A | N/A | 5/05/2014 | 16/06/2014 | 30/06/2014 | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
28.Supply and Installation of LED Electronic Display Board (big) |  |  | BOQ | NCB | 40000000 |  |  | Plan | N/A | N/A | N/A | 5/05/2014 | 16/06/2014 | 30/06/2014 | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
29. Installation of Lift Operational Software |  |  | BOQ | NCB | 17000000 |  |  | Plan | N/A | N/A | N/A | 5/05/2014 | 16/06/2014 | 30/06/2014 | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Actual | [7 empty] | Actual
30.Construction of perimeter fence/gate house at Ilorin Zonal Office |  |  | BOQ | NCB | 25000000 |  |  | Plan | N/A | N/A | N/A | 10/06/2014 | 22/07/2014 | 5/08/2014 | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
31. Supply and Installation of Furniture items for the Head Office, Lagos Office and the Zonal Offices. |  |  | BOQ | NCB | 168700456 |  |  | Plan | N/A | N/A | N/A | 10/06/2014 | 22/07/2014 | 5/08/2014 | N/A | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 462608216 |  |  | Plan | [7 empty] | Plan | #NAME? | [6 empty] | 0
[5 empty] | 462608216 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## OIL SPILL Consultancy Services
Ministry/Department/Agency: National Oil Spill Detection and Responce Agency
Budget Year: 2014
|  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 1 weeks | 2 - 4 weeks | 2 weeks | 2 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
Updated and Execution of National Oil Spilll Contigency Plan (NOSCP) | Plan | NOSDRA/PPAR/65/VOL1/96 | 5 |  | 106520769 | NCB | BPP issues "No Objection" to award/FEC approves | QCBS - Quality and Cost Based Selection | NA | PRIOR REVIEW
Actual
Total Cost Plan |  |  |  |  | 106520769
Total Cost Actual

## OIL SPILL Works
Ministry/Department/Agency: National Oil Spill Detection and Responce Agency
Budget Year: 2014
|  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Works |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Plan vs Actual
construction of Lab. | Plan | NOS/PPAR/VOLI/208 | 3 |  | 3000000 | NCB | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 31/01/14 - 7/02/14 | 10/02/14 - 14/02/14 | NA | NA | NA | NA | NA | 14/02/14 | 21/03/14 | 21/03/14 - 4/04/14 | 7/04/14 - 21/04/14 | 3000000 | NA | 21/04/14 - 23/04/14 | 24/04/14 - 2/05/14 | 5/05/14 - 23/05/14 | 25/08/14 | 29/08/14 | 3000000 | Gidado Abiodun - [Designation: DD Procurement] | Peter Idabor - [Designation: Director General/Chief Executive Officer]
Actual
Construction of Laboratory & Warehouse | Plan | NOSDRA/PPAR/65/VOL1/96 | 1 | Bills of Quantity | 394003621 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PRE-QUALIFICATION | POST REVIEW
Actual
Total Cost Plan |  |  |  |  | 397003621 | [16 empty] | 3000000 | [6 empty] | 3000000
Total Cost Actual

## OIL SPILL Non-Consultancy
Ministry/Department/Agency: National Mathematical Centre, Abuja
Budget Year: 2014
|  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 1 weeks | 2 - 4 weeks | 2 weeks | 2 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
Establishment of Continous Professional Development Training Programme | Plan |  |  |  | 14000000 | NCB | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | POST-QUALIFICATION | POST REVIEW
Actual
Total Cost Plan |  |  |  |  | 14000000
Total Cost Actual

## NFVC Goods
Ministry/Department/Agency: National film and Video Censors Board
Budget Year: 2014
|  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Goods |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Arrival of Goods | Inspection/Final Acceptance | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
Plan vs Actual
Furnishing of North West Zone | Plan | FMI/NFVCB/01 | 2 | Sch of Del | 4637812 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | 10/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | NA | 21/04/14 | 2/06/14 | 2/06/14 - 23/06/14 | NA | 463781200 | NA | 23/06/14 - 7/07/14 | 7/07/14 - 21/07/14 | 21/07/14 - 11/08/14 | 11/08/14 - 29/08/14 | 29/08/14 - 12/09/14 | Helen Anakwenze - [Designation: Ag. Head (Procurement)] | NA
Actual
Furnishing of South West Zone | Plan | FMI/NFVCB/01 | 1 | Sch of Del | 4637812 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | 10/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | NA | 21/04/14 | 2/06/14 | 2/06/14 - 23/06/14 | NA | 463781200 | NA | 23/06/14 - 7/07/14 | 7/07/14 - 21/07/14 | 21/07/14 - 11/08/14 | 11/08/14 - 29/08/14 | 29/08/14 - 12/09/14 | Helen Anakwenze - [Designation: Ag. Head (Procurement)] | NA
Actual
Furnishing of South East Zone | Plan | FMI/NFVCB/01 | 3 | Sch of Del | 4637812 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | 10/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | NA | 21/04/14 | 2/06/14 | 2/06/14 - 23/06/14 | NA | 463781200 | NA | 23/06/14 - 7/07/14 | 7/07/14 - 21/07/14 | 21/07/14 - 11/08/14 | 11/08/14 - 29/08/14 | 29/08/14 - 12/09/14 | Helen Anakwenze - [Designation: Ag. Head (Procurement)] | NA
| Actual | [9 empty] | NA | NA
Furnishing of North Central Zone | Plan | FMI/NFVCB/01 | 5 | Sch of Del | 3478359 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | 10/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | NA | 21/04/14 | 2/06/14 | 2/06/14 - 23/06/14 | NA | 347835900 | NA | 23/06/14 - 7/07/14 | 7/07/14 - 21/07/14 | 21/07/14 - 11/08/14 | 11/08/14 - 29/08/14 | 29/08/14 - 12/09/14 | Helen Anakwenze - [Designation: Ag. Head (Procurement)] | NA
| Actual | [11 empty] | NA
Furnishing of North East Zone | Plan | FMI/NFVCB/01 | 4 | Sch of Del | 3014577 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | 10/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | NA | 21/04/14 | 2/06/14 | 2/06/14 - 23/06/14 | NA | 301457700 | NA | 23/06/14 - 7/07/14 | 7/07/14 - 21/07/14 | 21/07/14 - 11/08/14 | 11/08/14 - 29/08/14 | 29/08/14 - 12/09/14 | Helen Anakwenze - [Designation: Ag. Head (Procurement)] | NA
Actual
Furnishing of South South Zone | Plan | FMI/NFVCB/01 | 6 | Sch of Del | 2782687 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | 10/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | NA | 21/04/14 | 2/06/14 | 2/06/14 - 23/06/14 | NA | 278268700 | NA | 23/06/14 - 7/07/14 | 7/07/14 - 21/07/14 | 21/07/14 - 11/08/14 | 11/08/14 - 29/08/14 | 29/08/14 - 12/09/14 | Helen Anakwenze - [Designation: Ag. Head (Procurement)] | NA
Actual
BUSES | Plan | FMI/NFVCB/02 | 1 | Sch of Del | 15000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | 10/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | NA | 21/04/14 | 2/06/14 | 2/06/14 - 23/06/14 | NA | 15000000 | NA | 23/06/14 - 7/07/14 | 7/07/14 - 21/07/14 | 21/07/14 - 11/08/14 | 11/08/14 - 29/08/14 | 29/08/14 - 12/09/14 | Helen Anakwenze - [Designation: Ag. Head (Procurement)] | NA
| Actual | [9 empty] | NA | NA
RESEARCH AND DEVELOPMENT (Operational vehicles) | Plan | FMI/NFVCB/03 | 1 |  | 25000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW
Actual
Total Cost Plan |  |  |  |  | 63189059 | [14 empty] | 2333905900
Total Cost Actual

## NFVC Non-Consultancy Services
Ministry/Department/Agency: National film and Video Censors Board
Budget Year: 2014
|  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2.2 - 2 weeks | 3 weeks | 2 - 4 weeks | 2 weeks | 4 - 6 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
INTERNATIONAL CONFERENCE ON FILM CLASSIFICATION | Plan | FMI/NFVCB/03 | 2 | Lump Sum | 15000000 | NCB | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | POST-QUALIFICATION | POST REVIEW | NA | NA | 10/03/14 - 24/03/14 | 24/03/14 - 14/04/14 | 14/04/14 | NA | 14/04/14 - 26/05/14 | 26/05/14 - 26/05/14 | 26/05/14 - 9/06/14 | NA | 9/06/14 - 10/06/14 | 10/06/14 - 16/06/14 | NA | NA | 15000000 | NA | 16/06/14 - 20/06/14 | 20/06/14 - 25/06/14 | 25/06/14 - 4/07/14 | 9/07/14 | 8/08/14 | 15000000 | Helen Anakwenze - [Designation: Ag. Head (Procurement)] | Helen Anakwenze - [Designation: Ag. Head (Procurement)]
Actual
INTERNATIONAL ROAD SHOWS | Plan | FMI/NFVCB/03 | 5 | Lump Sum | 15000000 | NCB | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | POST-QUALIFICATION | POST REVIEW | NA | NA | 10/03/14 - 24/03/14 | 24/03/14 - 14/04/14 | 14/04/14 | NA | 14/04/14 - 26/05/14 | 26/05/14 - 26/05/14 | 26/05/14 - 9/06/14 | NA | 9/06/14 - 10/06/14 | 10/06/14 - 16/06/14 | NA | NA | 15000000 | NA | 16/06/14 - 20/06/14 | 20/06/14 - 30/06/14 | 30/06/14 - 11/07/14 | 11/07/14 | 25/07/14 | 15000000 | Helen Anakwenze - [Designation: Ag. Head (Procurement)] | NA
Actual
Actual
SURVEILLANCE AND DATA COLLECTION (4) | Plan | FMI/NFVCB/03 | 4 | Lump Sum | 20000000 | NCB | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | POST-QUALIFICATION | POST REVIEW | NA | NA | 10/03/14 - 24/03/14 | 24/03/14 - 14/04/14 | 14/04/14 | NA | 14/04/14 - 26/05/14 | 26/05/14 - 26/05/14 | 26/05/14 - 9/06/14 | NA | 9/06/14 - 10/06/14 | 10/06/14 - 16/06/14 | NA | NA | 5000000 | NA | 16/06/14 - 20/06/14 | 20/06/14 - 25/06/14 | 25/06/14 - 4/07/14 | 4/07/14 | 2/12/14 | 20000000 | Helen Anakwenze - [Designation: Ag. Head (Procurement)] | NA
Actual
Actual
TWO LOCAL ROAD SHOWS | Plan | FMI/NFVCB/03 | 3 | Lump Sum | 20000000 | NCB | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | POST-QUALIFICATION | POST REVIEW | NA | NA | 10/03/14 - 24/03/14 | 24/03/14 - 14/04/14 | 14/04/14 | NA | 14/04/14 - 26/05/14 | 26/05/14 - 26/05/14 | 26/05/14 - 9/06/14 | NA | 9/06/14 - 10/06/14 | 10/06/14 - 16/06/14 | NA | NA | 10000000 | NA | 16/06/14 - 20/06/14 | 20/06/14 - 25/06/14 | 25/06/14 - 4/07/14 | 9/07/14 | 8/08/14 | 20000000 | Helen Anakwenze - [Designation: Ag. Head (Procurement)] | NA
| Actual | [23 empty] | 45000000
Total Cost Plan |  |  |  |  | 70000000 | [19 empty] | 45000000 | [6 empty] | 70000000
Total Cost Actual

## NFVC Works
Ministry/Department/Agency: National film and Video Censors Board
Budget Year: 2014
|  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Works |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Plan vs Actual
REHABILITATION/REPAIRES OF OFFICE BUILDING (LAGOS ZONAL OFFICE BUILDING) | Plan | FMI/NFVCB/04 | 1 | Bills of Quantity | 34068408 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | 10/03/14 - 7/04/14 | 7/04/14 - 21/04/14 | NA | 21/04/14 - 30/04/14 | 30/04/14 - 23/05/14 | 23/05/14 | 4/07/14 | 4/07/14 - 18/07/14 | NA |  | NA | 18/07/14 - 31/07/14 | 31/07/14 - 6/08/14 | 6/08/14 - 22/08/14 | 22/08/14 | 31/12/14 | 34068408 | Helen Anakwenze - [Designation: Ag. Head (Procurement)] | NA
Actual
Total Cost Plan |  |  |  |  | 34068408 | [23 empty] | 34068408
Total Cost Actual

## FRMA2 Consultancy Services
Ministry/Department/Agency: Ferderal Roads Maintenance Agency
Budget Year: 2014
|  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2.2 - 2 weeks | 3 weeks | 2 - 4 weeks | 2 weeks | 4 - 6 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
LOCAL TRAVEL & TRANSPORT : TRAINING | Plan | FERMA/03 | 1 | Lump Sum | 150000000 | NCB | BPP issues "No Objection" to award/FEC approves | CQ - Consultant&#039;s Qualification | PRE-QUALIFICATION | PRIOR REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 150000000 | NA | NA | NA | NA | 13/10/14 | 24/11/14 | 150000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
LOCAL TRAVEL & TRANSPORT : OTHERS | Plan | FERMA/03 | 2 | Lump Sum | 100000000 | NCB | BPP issues "No Objection" to award/FEC approves | CQ - Consultant&#039;s Qualification | PRE-QUALIFICATION | PRIOR REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 100000000 | NA | NA | NA | NA | NA | NA | NA | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
INTERNATIONAL TRAVEL & TRANSPORT : TRIANING | Plan | FERMA/03 | 3 | Lump Sum | 150000000 | NCB | BPP issues "No Objection" to award/FEC approves | CQ - Consultant&#039;s Qualification | PRE-QUALIFICATION | PRIOR REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 150000000 | NA | NA | NA | NA | NA | NA | 150000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
INTERNATIONAL TRAVEL & TRANSPORT : OTHERS | Plan | FERMA/03 | 4 | Lump Sum | 150000000 | NCB | BPP issues "No Objection" to award/FEC approves | CQ - Consultant&#039;s Qualification | PRE-QUALIFICATION | PRIOR REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 150000000 | NA | NA | NA | NA | NA | NA | 150000000 | INI USORO - [Designation: GENERAL MANAGER] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
LOCAL TRAINING | Plan | FERMA/03 | 11 | Lump Sum | 100000000 | NCB | BPP issues "No Objection" to award/FEC approves | CQ - Consultant&#039;s Qualification | PRE-QUALIFICATION | PRIOR REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 100000000 | NA | NA | NA | NA | NA | NA | 100000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
INTERNATIONAL TRAINING | Plan | FERMA/03 | 12 | Lump Sum | 200000000 | NCB | BPP issues "No Objection" to award/FEC approves | CQ - Consultant&#039;s Qualification | PRE-QUALIFICATION | PRIOR REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 200000000 | NA | NA | NA | NA | NA | NA | 200000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
FINANCIAL CONSULTANTING | Plan | FERMA/03 | 16 |  | 25000000 | NCB | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 25000000 | NA | NA | NA | NA | NA | NA | 25000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
INFORMATION TECHNOLOGY CONSULTING | Plan | FERMA/03 | 17 | Lump Sum | 35000000 | NCB | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 35000000 | NA | NA | NA | NA | NA | NA | 35000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
LEGAL SERVICES | Plan | FERMA/03 | 18 | Time-Based | 25000000 | NCB | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 25000000 | NA | NA | NA | NA | NA | NA | 25000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
ENGINEERING SERVICES | Plan | FERMA/03 | 19 | Lump Sum | 30000000 | NCB | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 30000000 | NA | NA | NA | NA | NA | NA | 30000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
ARHITECTUAL SERVICES | Plan | FERMA/03 | 20 | Lump Sum | 15000000 | NCB | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | POST-QUALIFICATION | POST REVIEW | NA | NA |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 15000000 | NA | NA | NA | NA | NA | NA | 15000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
DIRECT TEACHING & LABORATORY COST | Plan | FERMA/03 | 36 | Lump Sum | 100000000 | NCB | BPP issues "No Objection" to award/FEC approves | CQ - Consultant&#039;s Qualification | PRE-QUALIFICATION | PRIOR REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 100000000 | NA | NA | NA | NA | NA | NA | 100000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
Total Cost Plan |  |  |  |  | 1080000000 | [19 empty] | 1080000000 | [6 empty] | 980000000
Total Cost Actual

## FRMA 2 Goods
Ministry/Department/Agency: Ferderal Roads Maintenance Agency
Budget Year: 2014
|  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Goods |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Arrival of Goods | Inspection/Final Acceptance | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
Plan vs Actual
BOOKS | Plan | FERMA/02 | 2 | Bills of Quantity | 20000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | NA | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 | 14/03/14 | 25/04/14 | 28/04/14 - 12/05/14 | 13/05/14 - 20/05/14 | 20000000 | NA | 21/05/14 - 4/06/14 | 5/06/14 - 12/06/14 | NA | 13/06/14 - 27/06/14 | 30/06/14 - 7/07/14 | INI USORO - [Designation: GENERAL MANAGER] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
NEWSPAPERS | Plan | FERMA/02 | 3 | Bills of Quantity | 1000000 | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | NA | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 | 14/03/14 | 25/04/14 | 28/04/14 - 12/05/14 | 13/05/14 - 20/05/14 | 1000000 | NA | 21/05/14 - 4/06/14 | 5/06/14 - 12/06/14 | NA | 13/06/14 - 27/06/14 | 30/06/14 - 7/07/14 | INI USORO - [Designation: GENERAL MANAGER] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
OFFICE STATIONARIES AND COMPUTER CONSUMABLES | Plan | FERMA/02 | 1 | Bills of Quantity | 50000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | NA | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 | 14/03/14 | 25/04/14 | 28/04/14 - 12/05/14 | 13/05/14 - 20/05/14 | 50000000 | NA | 21/05/14 - 4/06/14 | 5/06/14 - 12/06/14 | NA | 13/06/14 - 27/06/14 | 30/06/14 - 7/07/14 | INI USORO - [Designation: GENERAL MANAGER] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
PRINTING OF SECURITY DOCUMENTS | Plan | FERMA/02 | 6 | Bills of Quantity | 20000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | NA | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 | 14/03/14 | 25/04/14 | 28/04/14 - 12/05/14 | 13/05/14 - 20/05/14 | 20000000 | NA | 21/05/14 - 4/06/14 | 5/06/14 - 12/06/14 | NA | 13/06/14 - 27/06/14 | 30/06/14 - 7/07/14 | INI USORO - [Designation: GENERAL MANAGER] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
PRINTING OF NON SECURITY DOCUMENTS | Plan | FERMA/02 | 5 | Bills of Quantity | 10000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | NA | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 | 14/03/14 | 25/04/14 | 28/04/14 - 12/05/14 | 13/05/14 - 20/05/14 | 10000000 | NA | 21/05/14 - 4/06/14 | 5/06/14 - 12/06/14 | NA | 13/06/14 - 27/06/14 | 30/06/14 - 7/07/14 | INI USORO - [Designation: GENERAL MANAGER] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
MAGAZINES AND PERIDICALS | Plan | FERMA/02 | 4 | Bills of Quantity | 1000000 | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | NA | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 | 14/03/14 | 25/04/14 | 28/04/14 - 12/05/14 | 13/05/14 - 20/05/14 | 1000000 | NA | 21/05/14 - 4/06/14 | 5/06/14 - 12/06/14 | NA | 13/06/14 - 27/06/14 | 30/06/14 - 7/07/14 | INI USORO - [Designation: GENERAL MANAGER] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
TEACHING AIDS/INSTRUCTION MATERIALS | Plan | FERMA/02 | 10 |  | 50000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | NA | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 | 14/03/14 | 25/04/14 | 28/04/14 - 12/05/14 | 13/05/14 - 20/05/14 | 50000000 | NA | 21/05/14 - 4/06/14 | 5/06/14 - 12/06/14 | NA | 13/06/14 - 27/06/14 | 30/06/14 - 7/07/14 | INI USORO - [Designation: GENERAL MANAGER] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
UNIFORM AND OTHER CLOTHING | Plan | FERMA/02 | 9 |  | 10000000 | NCB | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | NA | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 | 14/03/14 | 25/04/14 | 28/04/14 - 12/05/14 | 13/05/14 - 20/05/14 | 10000000 | NA | 21/05/14 - 4/06/14 | 5/06/14 - 12/06/14 | NA | 13/06/14 - 27/06/14 | 30/06/14 - 7/07/14 | INI USORO - [Designation: GENERAL MANAGER] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
DRUGS AND MEDICAL SUPPLIES | Plan | FERMA/02 | 7 |  | 5000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | NA | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 | 14/03/14 | 25/04/14 | 28/04/14 - 12/05/14 | 13/05/14 - 20/05/14 | 5000000 | NA | 21/05/14 - 4/06/14 | 5/06/14 - 12/06/14 | NA | 13/06/14 - 27/06/14 | 30/06/14 - 7/07/14 | INI USORO - [Designation: GENERAL MANAGER] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
FIELD & CAMPING MATERIALS SUPPLIES | Plan | FERMA/02 | 8 |  | 165654022 | NCB | BPP issues "No Objection" to award/FEC approves | LERB - LOWEST EVALUATED RESPONSIVE BID | PRE-QUALIFICATION | PRIOR REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | NA | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 | 14/03/14 | 25/04/14 | 28/04/14 - 12/05/14 | 13/05/14 - 20/05/14 | 165654022 | NA | 21/05/14 - 4/06/14 | 5/06/14 - 12/06/14 | NA | 13/06/14 - 27/06/14 | 30/06/14 - 7/07/14 | INI USORO - [Designation: GENERAL MANAGER] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
FOOD STUFF/CATERING MATERIAL SUPPLIES | Plan | FERMA/02 | 11 | Bills of Quantity | 10000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | NA | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 | 14/03/14 | 25/04/14 | 28/04/14 - 12/05/14 | 13/05/14 - 20/05/14 | 10000000 | NA | 21/05/14 - 4/06/14 | 5/06/14 - 12/06/14 | NA | 13/06/14 - 27/06/14 | 30/06/14 - 7/07/14 | INI USORO - [Designation: GENERAL MANAGER] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
MAINTENANCE OF MOTOR VEHICLE/TRANSPORT EQUIPMENT | Plan | FERMA/02 | 12 | Bills of Quantity | 100000000 | NCB | BPP issues "No Objection" to award/FEC approves | LERB - LOWEST EVALUATED RESPONSIVE BID | PRE-QUALIFICATION | PRIOR REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | NA | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 | 14/03/14 | 25/04/14 | 28/04/14 - 12/05/14 | 13/05/14 - 20/05/14 | 100000000 | NA | 21/05/14 - 4/06/14 | 5/06/14 - 12/06/14 | NA | 13/06/14 - 27/06/14 | 30/06/14 - 7/07/14 | INI USORO - [Designation: GENERAL MANAGER] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
MAINTENANCE OF OFFICE FURNITURE | Plan | FERMA/02 | 13 | Bills of Quantity | 20000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | NA | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 | 14/03/14 | 25/04/14 | 28/04/14 - 12/05/14 | 13/05/14 - 20/05/14 | 20000000 | NA | 21/05/14 - 4/06/14 | 5/06/14 - 12/06/14 | NA | 13/06/14 - 27/06/14 | 30/06/14 - 7/07/14 | INI USORO - [Designation: GENERAL MANAGER] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
MAINTENANCE OF OFFICE BUILDING/RESIDENTIAL QTRS | Plan | FERMA/02 | 14 | Bills of Quantity | 1000000 | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | NA | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 | 14/03/14 | 25/04/14 | 28/04/14 - 12/05/14 | 13/05/14 - 20/05/14 | 1000000 | NA | 21/05/14 - 4/06/14 | 5/06/14 - 12/06/14 | NA | 13/06/14 - 27/06/14 | 30/06/14 - 7/07/14 | INI USORO - [Designation: GENERAL MANAGER] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
MAINTENANCE OF OFFICE/ IT EQUIPMENTS | Plan | FERMA/02 | 15 | Bills of Quantity | 500000000 | NCB | BPP issues "No Objection" to award/FEC approves |  | PRE-QUALIFICATION | PRIOR REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | NA | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 | 14/03/14 | 25/04/14 | 28/04/14 - 12/05/14 | 13/05/14 - 20/05/14 | 500000000 | NA | 21/05/14 - 4/06/14 | 5/06/14 - 12/06/14 | NA | 13/06/14 - 27/06/14 | 30/06/14 - 7/07/14 | INI USORO - [Designation: GENERAL MANAGER] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
MAINTENANCE OF PLANTS/GENERATOR | Plan | FERMA/02 | 16 | Bills of Quantity | 3000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | NA | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 | 14/03/14 | 25/04/14 | 28/04/14 - 12/05/14 | 13/05/14 - 20/05/14 | 3000000 | NA | 21/05/14 - 4/06/14 | 5/06/14 - 12/06/14 | NA | 13/06/14 - 27/06/14 | 30/06/14 - 7/07/14 | INI USORO - [Designation: GENERAL MANAGER] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
OTHER MAINTENACE SERVICES | Plan | FERMA/02 | 17 | Bills of Quantity | 8000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | NA | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 | 14/03/14 | 25/04/14 | 28/04/14 - 12/05/14 | 13/05/14 - 20/05/14 | 8000000 | NA | 21/05/14 - 4/06/14 | 5/06/14 - 12/06/14 | NA | 13/06/14 - 27/06/14 | 30/06/14 - 7/07/14 | INI USORO - [Designation: GENERAL MANAGER] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
MAINTENACE OF ROADS AND BRIDGES | Plan | FERMA/02 | 18 |  | 23500000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | NA | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 | 14/03/14 | 25/04/14 | 28/04/14 - 12/05/14 | 13/05/14 - 20/05/14 | 23500000 | NA | 21/05/14 - 4/06/14 | 5/06/14 - 12/06/14 | NA | 13/06/14 - 27/06/14 | 30/06/14 - 7/07/14 | INI USORO - [Designation: GENERAL MANAGER] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
Total Cost Plan |  |  |  |  | 998154022 | [14 empty] | 998154022
Total Cost Actual

## FRMA 2 Non-Consultancy Services
Ministry/Department/Agency: Ferderal Roads Maintenance Agency
Budget Year: 2014
|  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2.2 - 2 weeks | 3 weeks | 2 - 4 weeks | 2 weeks | 4 - 6 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
ELECTRICITY CHARGES | Plan | FERMA/03 | 5 | Lump Sum | 150000000 | NCB | BPP issues "No Objection" to award/FEC approves | QCBS - Quality and Cost Based Selection | PRE-QUALIFICATION | PRIOR REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 150000000 | NA | NA | NA | NA | NA | NA | 150000000 | INI USORO - [Designation: GENERAL MANAGER] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
TELEPHONE CHARGES | Plan | FERMA/03 | 6 | Lump Sum | 10000000 | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 10000000 | NA | NA | NA | NA | NA | NA | 10000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
INTERNET ACCESS CHARGES | Plan | FERMA/03 | 7 | Lump Sum | 100000000 | NCB | BPP issues "No Objection" to award/FEC approves | QCBS - Quality and Cost Based Selection | PRE-QUALIFICATION | PRIOR REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 100000000 | NA | NA | NA | NA | NA | NA | 100000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
SATELITE BROADCASTING ACCESS CHARGES | Plan | FERMA/03 | 8 | Lump Sum | 10000000 | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 10000000 | NA | NA | NA | NA | NA | NA | 10000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
WATER RATES | Plan | FERMA/03 | 9 | Lump Sum | 10000000 | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 10000000 | NA | NA | NA | NA | NA | NA | 10000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
SEWERAGE CHARGES | Plan | FERMA/03 | 10 | Lump Sum | 2500000 | NCB | Parastatals Tenders Board |  | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2500000 | NA | NA | NA | NA | NA | NA | 2500000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
SECURITY SERVICES | Plan | FERMA/03 | 13 | Lump Sum | 150000000 | NCB | BPP issues "No Objection" to award/FEC approves | QCBS - Quality and Cost Based Selection | PRE-QUALIFICATION | PRIOR REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 150000000 | NA | NA | NA | NA | NA | NA | 150000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
OFFICE RENT | Plan | FERMA/03 | 14 | Lump Sum | 100000000 | NCB | BPP issues "No Objection" to award/FEC approves | QCBS - Quality and Cost Based Selection | PRE-QUALIFICATION | PRIOR REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 100000000 | NA | NA | NA | NA | NA | NA | 100000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
CLEANING AND FUMIGATION SERVICES | Plan | FERMA/03 | 15 | Lump Sum | 50000000 | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 50000000 | NA | NA | NA | NA | NA | NA | 50000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
SURVEYING SERVICES | Plan | FERMA/03 | 21 | Lump Sum | 25000000 | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 25000000 | NA | NA | NA | NA | NA | NA | 25000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
MOTOR VEHICLE FUEL COST | Plan | FERMA/03 | 22 | Lump Sum | 15000000 | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 15000000 | NA | NA | NA | NA | NA | NA | 15000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
OTHER TRANSPORT EQUIPMENT FUEL COST | Plan | FERMA/03 | 23 | Lump Sum | 5000000 | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 5000000 | NA | NA | NA | NA | NA | NA | 5000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
PLANT/ GENERATOR COST | Plan | FERMA/03 | 24 | Lump Sum | 35000000 | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 35000000 | NA | NA | NA | NA | NA | NA | 35000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
BANK CHARGES ( OTHER THAN INTEREST) | Plan | FERMA/03 | 25 | Lump Sum | 2500000 | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2500000 | NA | NA | NA | NA | NA | NA | 2500000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
INSURANCE PREMIUM | Plan | FERMA/03 | 26 | Lump Sum | 15000000 | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 15000000 | NA | NA | NA | NA | NA | NA | 15000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
OTHER CRF BANK CHARGES | Plan | FERMA/03 | 27 | Lump Sum | 2500000 | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | NA | 12/02/14 - 19/02/14 | 24/02/14 | 25/02/14 - 4/03/14 | 5/03/14 - 19/03/14 | 20/03/14 - 3/04/14 | 4/04/14 - 18/04/14 | 21/04/14 - 28/04/14 | 29/04/14 - 13/05/14 | 14/05/14 - 28/05/14 | 29/05/14 - 12/06/14 | 13/06/14 - 20/06/14 | 2500000 | NA | 23/06/14 - 7/07/14 | 8/07/14 - 15/07/14 | NA | 16/07/14 | 23/07/14 | 2500000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
REFRESHMENTS AND MEALS | Plan | FERMA/03 | 28 | Lump Sum | 15000000 | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 15000000 | NA | NA | NA | NA | NA | NA | 15000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
HONORARIUM & SITTING ALLOWANCE | Plan | FERMA/03 | 29 | Lump Sum | 10000000 | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 10000000 | NA | NA | NA | NA | NA | NA | 10000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
PUBLICITY AND ADVERTISEMENT | Plan | FERMA/03 | 30 | Lump Sum | 15000000 | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 15000000 | NA | NA | NA | NA | NA | NA | 15000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
MEDICAL EXPENSES | Plan | FERMA/03 | 31 | Lump Sum | 15000000 | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 15000000 | NA | NA | NA | NA | NA | NA | 15000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
POSTAGE & COURIER SERVICES | Plan | FERMA/03 | 32 | Lump Sum | 1000000 | NS | Accounting Officer: Director General/CEO | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 1000000 | NA | NA | NA | NA | NA | NA | 1000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
WELFARE PACKAGES | Plan | FERMA/03 | 33 | Lump Sum | 5000000 | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 5000000 | NA | NA | NA | NA | NA | NA | 5000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
SUBSCRIPTION TP PROFESSIONALS BODIES | Plan | FERMA/03 | 34 | Lump Sum | 25000000 | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 25000000 | NA | NA | NA | NA | NA | NA | 25000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
SPORTING ACTIVITIES | Plan | FERMA/03 | 35 | Lump Sum | 5000000 | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 5000000 | NA | NA | NA | NA | NA | NA | 5000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
PROJECT MONITORING ACTIVITIES & FOLLOW UP | Plan | FERMA/03 | 37 | Lump Sum | 1500000 | NS | Accounting Officer: Director General/CEO | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 1500000 | NA | NA | NA | NA | NA | NA | 1500000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
Total Cost Plan |  |  |  |  | 775000000 | [19 empty] | 775000000 | [6 empty] | 775000000
Total Cost Actual

## FRMA 2 Works
Ministry/Department/Agency: Ferderal Roads Maintenance Agency
Budget Year: 2014
|  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Works |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Plan vs Actual
CONSTRUCTION OF KADUNA STATE FIELD HEADQUARTERS, KADUNA. | Plan | FERMA/01 | 10 | Bills of Quantity | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 150000000 | NA | 3/12/12 - 10/12/12 | 11/12/12 - 18/12/12 | NA | 2/12/14 | 3/12/14 | 150000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
CONSTRUCTION OF BAYELSA STATE FEILD HEADQUARTERS YENAGOA | Plan | FERMA/01 | 8 |  | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 150000000 | NA | 3/12/12 - 10/12/12 | 11/12/12 - 18/12/12 | NA | 2/12/14 | 3/12/14 | 150000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
CONSTRUCTION OD FIELD HEADQUARTERS, ENUGU, ENUGU STATE. | Plan | FERMA/01 | 9 | Bills of Quantity | 150000000 | NCB | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 150000000 | NA | 3/12/12 - 10/12/12 | 11/12/12 - 18/12/12 | NA | 2/12/14 | 3/12/14 | 150000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
SPECIAL MAINTENANCE/REHABILITATION REPAIRS OF KABBA-EGBE-OMUARAN | Plan | FERMA/01 | 1 | Bills of Quantity | 400000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PRE-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 | 14/03/14 - 21/03/14 | 24/03/14 - 31/03/14 | 1/04/14 - 8/04/14 | 9/04/14 | 21/05/14 | 22/05/14 - 5/06/14 | 6/06/14 - 20/06/14 | 400000000 | NA | 23/06/14 - 30/06/14 | 1/07/14 - 8/07/14 | 9/07/14 - 16/07/14 | 7/07/15 | 8/07/15 | 4000000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
SPECIAL MAINTENANCE/REHABILITATION REPAIRS OF KEFFI-KADUNA-JOS ROAD | Plan | FERMA/01 | 2 | Bills of Quantity | 300000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PRE-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 | 14/03/14 - 21/03/14 | 24/03/14 - 31/03/14 | 1/04/14 - 8/04/14 | 9/04/14 | 21/05/14 | 21/05/14 - 5/06/14 | 6/06/14 - 20/06/14 | 300000000 | NA | 23/06/14 - 30/06/14 | 1/07/14 - 8/07/14 | 9/07/14 - 16/07/14 | 7/07/15 | 8/07/15 | 300000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
SPECIAL MAINTENANCE/REHABILITATION REPAIRS OF BAUCHI-GOMBE ROAD. | Plan | FERMA/01 | 3 | Bills of Quantity | 500000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PRE-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 | 14/03/14 - 21/03/14 | 24/03/14 - 31/03/14 | 1/04/14 - 8/04/14 | 9/04/14 | 21/05/14 | 21/05/14 - 5/06/14 | 6/06/14 - 20/06/14 | 300000000 | NA | 23/06/14 - 30/06/14 | 1/07/14 - 8/07/14 | 9/07/14 - 16/07/14 | 7/07/15 | 8/07/15 | 500000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
SPECIAL MAINTENANCE/REHABILITATION OF EDO S/B-AGBOR SAPELE ROAD IN DELTA/EDO STATE | Plan | FERMA/01 | 4 | Bills of Quantity | 500000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PRE-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 | 14/03/14 - 21/03/14 | 24/03/14 - 31/03/14 | 1/04/14 - 8/04/14 | 9/04/14 | 21/05/14 | 21/05/14 - 5/06/14 | 6/06/14 - 20/06/14 | 500000000 | NA | 23/06/14 - 30/06/14 | 1/07/14 - 8/07/14 | 9/07/14 - 16/07/14 | 7/07/15 | 8/07/15 | 500000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
PURCHASE AND MAINTENANCE OF HEAVY EQUIPMENT/TRUCKS | Plan | FERMA/01 | 5 | Lump Sum | 200000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | NA | 27/02/14 - 13/03/14 | 14/03/14 - 21/03/14 | 24/03/14 - 31/03/14 | 1/04/14 - 8/04/14 | 9/04/14 | 21/05/14 | 21/05/14 - 5/06/14 | 6/06/14 - 20/06/14 | 200000000 | NA | 23/06/14 - 30/06/14 | 1/07/14 - 8/07/14 | NA | 7/07/15 | 8/07/15 | 200000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
CONSTRUCTION OF CORPORATE HEADQUARTERS/OFFICES | Plan | FERMA/01 | 6 | Bills of Quantity | 500000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | PRE-QUALIFICATION | POST REVIEW | 20/01/14 - 3/02/14 | 4/02/14 - 11/02/14 | 12/02/14 - 26/02/14 | 27/02/14 - 13/03/14 | 14/03/14 - 21/03/14 | 24/03/14 - 31/03/14 | 1/04/14 - 8/04/14 | 9/04/14 | 21/05/14 | 21/05/14 - 5/06/14 | 6/06/14 - 20/06/14 | 500000000 | NA | 23/06/14 - 30/06/14 | 1/07/14 - 8/07/14 | 9/07/14 - 16/07/14 | 7/07/15 | 8/07/15 | 500000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
CONSTRUCTION OF DELTA STATE FIELD HEADQUARTERS ASABA | Plan | FERMA/01 | 7 | BEME | 150000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 150000000 | NA | 3/12/12 - 10/12/12 | 11/12/12 - 18/12/12 | NA | 2/12/14 | 3/12/14 | 150000000 | MOHAMMED HASSAN - [Designation: EXECUTIVE DIRECTOR] | GABRIEL AMUCHI - [Designation: Managing Director]
Actual
Total Cost Plan |  |  |  |  | 3000000000 | [16 empty] | 2800000000 | [6 empty] | 6600000000
Total Cost Actual

## FRMA GOODS
Ministry/Department/Agency: WORKS - FERMA
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
|  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  | 2 - 3 wks | T | 2 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Office Stationatries and Computer Consumables | 1 | 1 | 50000000 | NCB | N/A | FERMA TB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 30th Apr- 14th May | 15th May - 26 May | Plan | 50000000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23July | 50000000 | ED | MD
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Books | 2 | 1 | 20000000 | NCB | N/A | FERMA TB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 30th Apr- 14th May | 15th May - 26 May | Plan | 20000000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23July | 20000000 | ED | MD
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Newspapers | 3 | 1 | 1000000 | NCB | N/A | MD | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 30th Apr- 14th May | 15th May - 26 May | Plan | 1,000,000,00 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23July | 1,000,000,00 | ED | MD
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Magazines and Periodicals | 4 | 1 | 1000000 | NCB | N/A | MD | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 30th Apr- 14th May | 15th May - 26 May | Plan | 1,000,000,00 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23July | 1,000,000,00 | ED | MD
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Printing of non security documents | 5 | 1 | 10000000 | NCB | N/A | FERMA TB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 30th Apr- 14th May | 15th May - 26 May | Plan | 10,000,000,00 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23July | 10,000,000,00 | ED | MD
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Printing of security Documents | 6 | 1 | 20000000 | NCB | N/A | FERMA TB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 30th Apr- 14th May | 15th May - 26 May | Plan | 20,000,000,00 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23July | 20,000,000,00 | ED | MD
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Drugs and Medical Supplies | 7 | 1 | 5000000 | NCB | N/A | FERMA TB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 30th Apr- 14th May | 15th May - 26 May | Plan | 5000000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23July | 5000000 | ED | MD
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Field & Camping Materials Supplies | 8 | 1 | 165654022 | NCB | N/A | FEC | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 30th Apr- 14th May | 15th May - 26 May | Plan | 165654022 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23July | 165654022 | ED | MD
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Uniforms and other clothing | 9 | 1 | 10000000 | NCB | N/A | FERMA TB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 30th Apr- 14th May | 15th May - 26 May | Plan | 10,000,000,00 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23July | 10,000,000,00 | ED | MD
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Teaching Aids/ Insruction Materials | 10 | 1 | 50000000 | NCB | N/A | FERMA TB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 30th Apr- 14th May | 15th May - 26 May | Plan | 50000000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23July | 50000000 | ED | MD
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Food Stufff/ Catering Materials Suppliies | 11 | 1 | 10000000 | NCB | N/A | FERMA TB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 30th Apr- 14th May | 15th May - 26 May | Plan | 10,000,000,00. | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23July | 10,000,000,00. | ED | MD
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual

## FRMA WORKS
Ministry/Department/Agency: WORKS - FERMA
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
|  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Special Maintenance/Rehabilitation Repairs of Kabba - Egbe - Omuaran Ilorin Road in Kwara State. | 1 | 1 | BOQ | NCB | 400000000 | Pre-Qua | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June |  | 400000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 | 400,000,000 | ED | MD/CEO
Special Maintenance/Rehabilatation Repairs of Keffi- Kaduna-Jos Road. | 1 | 2 | BOQ | NCB | 300000000 | Pre-Qua | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June |  | 300000000 | N/A | 03/07-17/07/14 | 18/07-25/07/14 | N/A | 26/07-25/05/15 | 25/05/15 | 300000000 | ED | MD/CEO
Special Maintenance/Rehabilaton Repairs of Bauchi-Gombe Road | 1 | 1 | BOQ | NCB | 500000000 | Pre-Qua | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June |  | 500000000 | N/A | 03/07-17/07/14 | 18/07-25/07/14 | N/A | 26/07-25/05/15 | 25/05/15 | 500000000 | ED | MD/CEO
Special Maintenance/Rehabilation Repairs of Edo S/B-Agbor-Sapele Road in Delta/Edo State | 2 | 2 | BOQ | NCB | 500000000 | Pre-Qua | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June |  | 500000000 | N/A | 03/07-17/07/14 | 18/07-25/07/14 | N/A | 26/07-25/05/15 | 25/05/15 | 500000000 | ED | MD/CEO
Purchase and Maintenance of Heavy Equipment/Trucks | 3 | 1 | BOQ | NCB | 200000000 | N/A | FERMMA TB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June |  | 200000000 | N/A | 03/07-17/07/14 | 18/07-25/07/14 | N/A | 26/07-25/05/15 | 25/05/15 | 200000000 | ED | MD/CEO
Construction of Corporate HeadQuarters/Offices | 4 | 1 | BOQ | NCB | 500000000 | ON GOING | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June |  | 500000000 | N/A | 03/07-17/07/14 | 18/07-25/07/14 | N/A | 26/07-25/05/15 | 25/05/15 | 500000000 | ED | MD/CEO
Construction of Delta State Field Headquaters Asaba | 5 | 1 | BOQ | N/A | 150000000 | ON GOING | FERMA TB |  | ON GOING | ON GOING | ON GOING | ON GOING | ON GOING | ON GOING | ON GOING |  | 150,000.000.00 | N/A | ON GOING | ON GOING | N/A | ON GOING | ON GOING | 150000000 | ED | MD/CEO
Construction of Bayelsa State Field Headquaters Yenagoa | 6 | 1 | BOQ | N/A | 150000000 | ON GOING | FERMA TB |  | ON GOING | ON GOING | ON GOING | ON GOING | ON GOING | ON GOING | ON GOING |  | 150,000,000,00 | N/A | ON GOING | ON GOING | N/A | ON GOING | ON GOING | 150000000 | ED | MD/CEO
Construction Of Field Headquaters Enugu, Enugu State. | 7 | 2 | BOQ | N/A | 150000000 | ON GOING | FERMA TB |  | ON GOING | ON GOING | ON GOING | ON GOING | ON GOING | ON GOING | ON GOING |  | 150,000,000,00 | N/A | ON GOING | ON GOING | N/A | ON GOING | ON GOING | 150000000 | ED | MD/CEO
Construction of Kaduna State Field Headquaters Kaduna | 8 | 1 | BOQ | N/A | 150000000 | ON GOING | FERMA TB |  | ON GOING | ON GOING | ON GOING | ON GOING | ON GOING | ON GOING | ON GOING |  | 150,000,000,00 | N/A | ON GOING | ON GOING | N/A | ON GOING | ON GOING | 150000000 | ED | MD/CEO
Maintenance of Motor Vehicle/Transport Equipment | 9 | 2 | BOQ | NCB | 100,000,000,00 | N/A | FERMA TB |  | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 100,000,000,00 | N/A | 03/07-17/07/14 | 18/07-25/07/14 | N/A | 26/07-25/05/15 | 25/05/15 | 100,000,000,00 | ED | MD
Actual
9
Maintenace of Office Funiture | 10 | 1 | BOQ | NCB | 20,000,000,00 | N/A | FERMA TB |  | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 20,000,000,00 | N/A | 03/07-17/07/14 | 18/07-25/07/14 | N/A | 26/07-25/05/15 | 25/05/15 | 20,000,000,00 | ED | MD
Actual
Maintenance of Office Building / Residential QTRS | 11 | 1 | BOQ | NCB | 1,000,000,00 | N/A | MD |  | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 1,000,000,00 | N/A | 03/07-17/07/14 | 18/07-25/07/14 | N/A | 26/07-25/05/15 | 25/05/15 | 1,000,000,00 | ED | MD
Actual
Maintenance of Office/ IT Equipments | 12 | 2 | BOQ | NCB | 500,000,000,00 | Pre-Qua | FEC |  | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 500,000,000,00 | N/A | 03/07-17/07/14 | 18/07-25/07/14 | N/A | 26/07-25/05/15 | 25/05/15 | 500,000,000,00 | ED | MD
Actual
Maintenance of Plants/ Generators | 13 | 1 | BOQ | NCB | 3,000,000,00 | N/A | MD |  | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 3,000,000,00 | N/A | 03/07-17/07/14 | 18/07-25/07/14 | N/A | 26/07-25/05/15 | 25/05/15 | 3,000,000,00 | ED | MD
Actual
Other Maintenance Services | 14 | 1 | BOQ | NCB | 8,000,000,00 | N/A | MD |  | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 8,000,000,00 | N/A | 03/07-17/07/14 | 18/07-25/07/14 | N/A | 26/07-25/05/15 | 25/05/15 | 8,000,000,00 | ED | MD
Actual
Maintenance OF Roads and Bridges | 15 | 1 | BOQ | NCB | 23500000 | N/A | FERMA TB |  | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 235000000 | N/A | 03/07-17/07/14 | 18/07-25/07/14 | N/A | 26/07-25/05/15 | 25/05/15 | 235000000 | ED | MD
Actual

## FRMA CONSULTANCY
Ministry/Department/Agency:
Budgetary Year: |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval |  | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/ Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | Plan vs. Actual | No-objection Date | FEC Approval | Contract Amount in Naira | Contract Offer | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | Plan | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | Plan | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 1- 2 wk | 2 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
List of Contracts
Local Travel & Transport: Training | NA | LUMP SUM | 150000000 | FERMA TB | Plan | NA | NA | N/A | NA | NA | N/A | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | 15/10/2014 | 24/11/2014 | 150000000 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Local Travel & Transport : Others | NA | LUMP SUM | 100000000 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 100000000 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
International Travel & Transport : Training | NA | LUMP SUM | 150000000 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 150000000 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
International Travel & Transport : Others | NA | LUMP SUM | 150000000 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 150000000 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Electricity Charges | NA | LUMP SUM | 150,000,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 150,000,000,00 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Telephone Charges | NA | LUMP SUM | 10,000,000,00 | FERMA TB |  | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA |  | NA | NA | NA | 10,000,000,00 | ED | MD/CEO
Internet Access Charges | NA |  | 100,000,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 100,000,000,00 | ED | MD/CEO
|  | LUMP SUM |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Satellite Broadcasting Access Charges | NA | LUMP SUM | 10,000,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 10,000,000,00 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Water Rates | NA | LUMP SUM | 10,000,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 10,000,000,00 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Sewerage Charges | NA | LUMP SUM | 2500000 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 2500000 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Local Training | NA | LUMP SUM | 100,000,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 100,000,000,00 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
International Training | NA | LUMP SUM | 200,000,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 200,000,000,00 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Security Services | NA | LUMP SUM | 150,000,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 150,000,000,00 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Office Rent | NA | LUMP SUM | 100,000,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 100,000,000,00 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Cleaning and Fumigation Services | NCB | LUMP SUM | 50000000 | FERMA TB | Plan | 03/2-24/2/14 | 25/2-11/03/14 | NA | NA | NA | NA | Plan | 20/5/2014 | 20/5-4/7/14 | 7/7-18/7/14 | 22/7 -1/8/14 | 5/8 -15/8/14 | NA | 18/8 -29/8/14 | Plan | NA | NA | 50000000 | 1/09-12/09/14 | 16/09 -26/9/14 | Plan | NA | 9/09/2015 | 30/09/2015 | 50000000 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Financial Consultanting | NA | LUMP SUM | 25,000,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 25,000,000,00 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Information Technology Consulting | NA | LUMP SUM | 35,000,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 35,000,000,00 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Legal Services | NA | TIME BASED | 25,000,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 25,000,000,00 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Engineering Services | NA | LUMP SUM | 30,000,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 30,000,000,00 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Architectual Services | NA | LUMP SUM | 15,000,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 15,000,000,00 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Surveying Services | NA | LUMP SUM | 25,000,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 25,000,000,00 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Motor Vehicle Fuel Cost | NA | LUMP SUM | 15,000,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 15,000,000,00 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Other Transport Equipment Fuel Cost | NA | LUMP SUM | 5,000,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 5,000,000,00 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Plant / Generator Cost | NA | LUMP SUM | 35,000,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 35,000,000,00 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Bank Charges ( Other Than Interest) | NA | LUMP SUM | 2,500,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 2,500,000,00 | ED | MD/CEO
[5 empty] | Actual | [14 empty] | Actual | [5 empty] | Actual
Insurance Premium | NA | LUMP SUM | 15,000,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 15,000,000,00 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Other CRF Bank Charges | NA | LUMP SUM | 2,500,000,00 | FERMA TB | Plan | 03/02-24/02/14 | 25/02-11/03/14 | N/A | 12/03-14/03/14 | 19/03/14 | 20/03-03/04/14 | Plan | 07/04-21/04/14 | 22/04-20/05/14 | 21/05-04/06/14 | 05/06-13/06/14 | 23/06-07/07/14 | 08/07-22/07/14 | 23/07-06/08/14 | Plan | 07/08-21/08/14 | NA | 2,500,000,00 | 25/08-08/09/14 | 09/09-23/09/14 | Plan | NA | 9/09/2015 | 30/09/2015 | 2,500,000,00 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Refreshment & Meals | NA | LUMP SUM | 15,000,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 15,000,000,00 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Honorarium & Sitting Allowance | NA | LUMP SUM | 10,000,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 10,000,000,00 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Publicity & Advertisement | NA | LUMP SUM | 15,000,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 15,000,000,00 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Medical Expenses | NA | LUMP SUM | 15,000,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 15,000,000,00 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Postage & Courier Services | NA | LUMP SUM | 1,000,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 1,000,000,00 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Welfare Packages | NA | LUMP SUM | 5,000,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 5,000,000,00 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Subscription to Professional Bodies | NA | LUMP SUM | 25,000,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 25,000,000,00 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Sporting Acttivities | NA | LUMP SUM | 5,000,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 5,000,000,00 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Direct Teaching & Laboratory Cost | NA | LUMP SUM | 100,000,000,00 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 100,000,000,00 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Project Monitoring Activities & Follow Up | NA | LUMP SUM | 15000000 | FERMA TB | Plan | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | Plan | NA | NA | NA | 15000000 | ED | MD/CEO
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
TOTAL COST |  |  | 617500000

## FMW Goods
Ministry/Department/Agency: WORKS -
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
|  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Plan vs. Actual | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 2 wks | Plan | 2 - 3 wks | T | 2 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual |  |  |  |  | Actual
List of Contracts
Installation of e-Law Library and Training of Staff. | 1 | 1 | 10000000 | OCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 30th Apr- 14th May | 15th May - 26 May | Plan | 10000000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23July | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Purchase of Laws of the Federation of Nigeria (25 sets) and Purchase of Law Books, Statutes and Periodics Law Reports and Law Journals | 2 | 1 | 5000000 | OCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May- 14th May | 15th May - 26 May | Plan | 5000000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23July | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Purchase of Office Furnitures for Legal Officers (11 Officers) | 3 | 2 | 2500000 | OCB | N/A | PS | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May- 14th May | 15th May - 26 May | Plan | 2500000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23July | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Procurement of Stationeries, Computer sets, HP Laserjet Printers, Toners, Ink, UPS and Other Accessories | 4 | 1 | 6000000 | OCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May- 14th May | 15th May - 26 May | Plan | 6000000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23July | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Purchase and Installation of 45 Nos Laptops/Samsung Tablet 10.1 for Directorate Cadre Staff and Heads of Units in the Headquaters. | 5 | 1 | 7000000 | OCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May- 14th May | 15th May - 26 May | Plan | 7000000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Upgrade of Existing Computer Systems and Accessories in the Ministry, Replacement of Existing Nos. 385 Computer System, Printers and UPS. | 6 | 1 | 5000000 | OCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan | 5000000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Purshace and Installation of HP 45 Computer Systems, HP 45 Printers and 45 UPS in the New Office Building of the Ministry. | 7 | 1 | 7000000 | OCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan | 7000000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Primary Internet 8GB Subscription to Galaxy Backbone. | 8 | 1 | 18000000 | OCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan | 18000000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Upgrade and Hosting of Interactive Web Portal for the Ministry | 9 | 1 | 5000000 | OCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan | 5000000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Purchase and Installation of Network Anti - Virus Software for Hqtrs, Building. | 19 | 1 | 5000000 | OCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan | 5000000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Upgrade of the Ministry's Data Centre with Servers, Computer Systems and Accessories for Networking. | 11 | 1 | 5000000 | OCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan | 5000000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
ICT Project Management Office - Upgrade | 12 | 1 | 5000000 | OCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan | 5000000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Secondary Internet 5MB Subscription to Phase 3.Com | 13 | 2 | 8000000 | OCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan | 8000000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Renewal of Microsoft 250 Volume Licence for the Ministry Server. | 14 | 1 | 10000000 | OCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May | Plan | 10000000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Provision of Monitoring and Evaluation Equipments (i)2 Nos Digital Camera with Accessories (ii)2 Nos Progectors Sreeen with Accessories (iii)2 Nos Cam Coder | 15 | 1 | 2500000 | OCB |  | PS | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May |  | 2500000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Purchase of Library Books Equipments for Headquarter and Field Headquarter. | 16 | 1 | 2500000 | OCB |  | PS | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May - 14th May | 15th May - 26th May |  | 2500000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23rd July | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Establishment and Equipping of E-Learing Centre | 17 | 1 | 10000000 | OCB | N/A | MTB | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 10000000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual
Supply and Installation of Automated Physical files Storage & Retrival System (Vertical Carousel) | 18 | Lot 2 | 10000000 | OCB | N/A | MTB | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 10000000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual
Installation of an Automated clock in pass | 19 | Lot 1 | 18000000 | OCB | N/A | MTB | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 18000000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual
Drugs and Medical Supplies | 20 | Lot 2 | 5825962 | OCB | N/A | MTB | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 5825962 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual
Maintenance of IPPIS Installations and Equipment | 21 | Lot 1 | 7000000 | OCB | N/A | MTB | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 7000000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual
Sports Equipment/Physical Fitness Facilities | 22 | Lot 2 | 22011649 | OCB | N/A | MTB | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 22011649 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual
Fill gray cells only!
Procurement of Modern Workshop Tools/Teaching Aids for Engineering Training School at Abeokuta. | 23 | 1 | 5000000 | OCB | N/A | MTB | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 4990800 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Procurement of Modern Workshop Tools/Teaching Aids for Engineering Development Centre at Ijora. | 24 | 2 | 5000000 | OCB | N/A | MTB | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 4978000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Purchase of Tools and Equipment for Teaching at Engineering Training School, Kuje. | 25 | 1 | 5000000 | OCB | N/A | MTB | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 4980900 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | Diretor Procurement | Permanent Secretary
Actual
Provision of Utility Vehicle and Staff/Students Bus for each of the Engineering Training Schools at Ijora, Abeokuta and Kuje. | 26 | 1 | 15000000 | OCB | N/A | MTB | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 15000000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | Diretor Procurement | Permanent Secretary
Actual
Purchase of Sporting Facilities at Engineering Training Schools, in Ijora, Abeokuta and Kuje | 27 | 1 | 2000000 | OCB | N/A | PS | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 1990900 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | Diretor Procurement | Permanent Secretary
Actual
Provision and Installation of 12Nos Foundry Machine tools & Equipments at Ijora Central Workshop and zonal workshops. | 28 | 1 | 30000000 | OCB | N/A | MTB | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 30000000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Provision and Installation of Engineering material Testing equipments at Ijora Central Workshop and zonal workshops. | 29 | 2 | 15000000 | OCB | N/A | MTB | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 15000000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Provision and Installation of Machine Tools and Equipments at Ijora Central Workshop. | 30 | 3 | 30000000 | OCB | N/A | MTB | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 30000000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Provision of 25 No. Material Handling Equipment and fourwheel drive vehicle for Streetlighting and Weigh Bridge Operations in the Six Geopolitical zone. | 31 | 4 | 20000000 | OCB | N/A | MTB | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 20000000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Provision of Design Equipment and Software for Mechanical Services. | 32 | 5 | 10000000 | OCB | N/A | MTB | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 10000000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Procurement and Installation of safety equipment for Headquarters building and key Assets and Personnel of the Ministry. 1. Surveillance Cameras with Remote Control Centres at entry and exit of major towns 2. High Security Vapour detector Equipment 3. IED Containment Equipment 4. Under vehicle inspection system with remote control sensing | 33 | 6 | 10000000 | OCB | N/A | MTB | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 10000000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Provision of 1No Standby Generator - 350KVA for Mechanical Workshop, Ijora | 34 | 7 | 17000000 | OCB | N/A | MTB | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 17000000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | Diretor Procurement | Permanent Secretary
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Actual
Procurement of Internal Audit Security working materials. | 35 | 1 | 4800000 | OCB | N/A | PS | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 4800000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | Diretor Procurement | Permanent Secretary
Actual
Procurement of Laptops, Desktops and Printers. | 36 | 2 | 4900000 | OCB | N/A | PS | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 4900000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | Diretor Procurement | Permanent Secretary
Actual
Procurement of Photocopiers. | 37 | 1 | 2000000 | OCB | N/A | PS | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 1800000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | Diretor Procurement | Permanent Secretary
Actual
Procurement of 2Nos of Hilux Internal Audit Inspection of Capital Project Veh. | 38 | 2 | 12350000 | OCB | N/A | MTB | Plan | 2nd May - 19th May | 20th May - 30th May | N/A | 2nd June - 15th July, | 15th July | 15th July- 30th July | 31st July- 8th Aug | Plan | 12200000 | N/A | 11 Aug- 20th Aug | 21st Aug- 5 Sept | Plan | N/A | 8th Sept- 22nd Sept | 23rd Sept- 8th Oct | Diretor Procurement | Permanent Secretary
Printing of Tender Document and Evaluation of Tender for Capital Projects | 39 | 1 | 7000000 | OCB | N/A | MTB | Plan | 14th Feb- 5th March | 8th March - 17th March | N/A | 18th Mar- 30th April | 30th April | 30th Apr- 14th May | 15th May - 26 May | Plan | 7000000 | N/A | 27th May- 6th June | 9th June- 23rd June | Plan | N/A | 24th June- 8th July | 9th July- 23July | Diretor Procurement | Permanent Secretary
Total Cost |  |  | 371387611

## FMW Works
Ministry/Department/Agency: WORKS
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
|  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of contracts
Upgrading of Water supply and treatment Plant at the Federal Ministry of Works Heaquarters, Abuja. | 1 | 1 | Bill of Quantities | OCB | 10000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 10000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Completion of on-going Construction of Mechanical Welding Workshop for Production of Streetlighting poles in Kuje: landscapping, Drainage & Horticultural Works | 2 | 1 | Bill of Quantities | OCB | 20000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 20000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Completion of on-going construction of 350m internal roads and landscaping at engineering Centre, Kuje. | 3 | 2 | Bill of Quantities | OCB | 10000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 10000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Road Furnitures - Manhole Covers - Maintenance / Rehabilitation; Road Traffic Sign - Maintenance / Rehabilitation; Bridge Railings - Maintenance/Rehabilitations | 4 | 1 | Bill of Quantities | OCB | 10000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 10000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Water system Development at Engineering centre Kuje: Water Treatment, Reticulation & Storage Facilities | 5 | 1 | BEME | OCB | 5000000 | N/A | PS | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 5000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Rehabiliation of existing fire fighting and early warning systems at the Headquarters and key zonal installations • Fire Alarm, Smoke detector system • Fire hose reel • Servicing of extinguishers | 6 | 1 | Bill of Quantities | OCB | 10000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 10000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Supply, Installation and Maintenance of Weigh Bridges | 7 | 1 | BEME | OCB | 5000000 | N/A | PS | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 5000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Installation of Airconditioners and Refregerators for the Headquaters and Field Offices | 8 | 1 | Bill of Quantities | OCB | 5000000 | N/A | PS | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 5000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Reclaimation of Sinking Part of Ijora Workshop | 9 | 1 | Bill of Quantities | OCB | 43000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 43000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Provision and Installation of 12Nos Foundry Machine tools & Equipments at Ijora Central Workshop and zonal workshops. | 10 | 1 | Bill of Quantities | OCB | 30000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 30000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Provision and Installation of Engineering material Testing equipments at Ijora Central Workshop and zonal workshops. | 11 | 2 | Bill of Quantities | OCB | 15000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 15000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Provision and Installation of Machine Tools and Equipments at Ijora Central Workshop. | 12 | 3 | Bill of Quantities | OCB | 30000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 30000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Provision and Installation of 25 No. Material Handling Equipment and fourwheel drive vehicle for Streetlighting and Weigh Bridge Operations in the Six Geopolitical zone. | 13 | 1 | Bill of Quantities | OCB | 20000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 20000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Provision and Installation of Design Equipment and Software for Mechanical Services. | 14 | 2 | Bill of Quantities | OCB | 10000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 10000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Procurement and Installation of safety equipment for Headquarters building and key Assets and Personnel of the Ministry. 1. Surveillance Cameras with Remote Control Centres at entry and exit of major towns 2. High Security Vapour detector Equipment 3. IED Containment Equipment 4. Under vehicle inspection system with remote control sensing | 15 | 1 | Bill of Quantities | OCB | 10000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 10000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Provision and Installation of 1No Standby Generator - 350KVA for Mechanical Workshop, Ijora | 16 | 2 | Bill of Quantities | OCB | 17000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 17000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Actual
SOUTH EAST ZONE
INSTALLATION OF STREET LIGHTS ON OWERRI - ONITSHA EXPRESSWAY, OWERRI END | 17 | 1 | Bill of Quantities | OCB | 87000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
INSTALLATION OF STREET LIGHTS ON ENUGU - PORT-HARCOURT EXPRESSWAY, (FOUR-CORNER JUNCTION) | 18 | 2 | Bill of Quantities | OCB | 88000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
REHABILITATION/SUSTENANCE OF STREETLIGHTS ON NSUKKA - ENUGU, 9TH MILE NBL BREWERIES (ENUGU) | 19 | 3 | Bill of Quantities | OCB | 40000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
REHABILITATION/SUSTENANCE OF STREETLIGHTS ON ABAKILIKI - OGOJA ROAD, ABAKILIKI END | 20 | 4 | Bill of Quantities | OCB | 40000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
SOUTH WEST ZONE
INSTALLATION OF STREET LIGHTS ON IBADAN - OGBOMOSHO - ILORIN EXPRESSWAY, OGBOMOSO INTERCHANGE, SECTION II | 21 | 1 | Bill of Quantities | OCB | 87000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
INSTALLATION OF STREET LIGHTS ON AKURE - OWO ROAD, AKURE END | 22 | 2 | Bill of Quantities | OCB | 88000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
REHABILITATION/SUSTENANCE OF STREETLIGHTS ON IBADAN - IFE, IFE END | 23 | 3 | Bill of Quantities | OCB | 45000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
REHABILITATION/SUSTENANCE OF STREETLIGHTS ON IBADAN - OYO, NEW ALIGNMENT (IBADAN END) | 24 | 4 | Bill of Quantities | OCB | 40000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
SOUTH SOUTH ZONE
INSTALLATION OF STREET LIGHTS ON AGBOR - ASABA EXPRESSWAY, SECTION II, UMUNEDE, DELTA STATE | 25 | 1 | Bill of Quantities | OCB | 90000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
INSTALLATION OF STREET LIGHTS ON BENIN - WARRI EXPRESSWAY, WARRI END | 26 | 2 | Bill of Quantities | OCB | 80000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
REHABILITATION/SUSTENANCE OF STREETLIGHTS ON NIGER BRIDGE | 27 | 3 | Bill of Quantities | OCB | 45000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
REHABILITATION/SUSTENANCE OF STREETLIGHTS ON SAPELE - BENIN INTERCHANGE, BENIN BYPASS, EDO STATE | 28 | 4 | Bill of Quantities | OCB | 40000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
NORTH WEST ZONE
INSTALLATION OF STREET LIGHTS ON SANNI - ABACHA ROAD, BIRNIN KEBBI, KEBBI STATE | 29 | 1 | Bill of Quantities | OCB | 87000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
INSTALLATION OF STREET LIGHTS ON KADUNA WESTERN BYPASS, KADUNA | 30 | 2 | Bill of Quantities | OCB | 88000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
REHABILITATION/SUSTENANCE OF STREETLIGHTS ON FUNTUA BYPASS, KATSINA | 31 | 3 | Bill of Quantities | OCB | 42000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
REHABILITATION/SUSTENANCE OF STREETLIGHTS ON GUSAU - SOKOTO ROAD, GUSAU END | 32 | 4 | Bill of Quantities | OCB | 38000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
NORTH CENTRAL ZONE
INSTALLATION OF STREET LIGHTS ON ABUJA - LOKOJA EXPRESSWAY, GIRI INTERCHANGE, SECTION II | 33 | 1 | Bill of Quantities | OCB | 110000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
INSTALLATION OF STREET LIGHTS ON MAKURDI - LAFIA ROAD, MAKURDI END, SECTION II | 34 | 2 | Bill of Quantities | OCB | 90000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
REHABILITATION/SUSTENANCE OF STREETLIGHTS ON IBADAN - ILORIN EXPRESSWAY, ILORIN END | 35 | 3 | Bill of Quantities | OCB | 35000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
REHABILITATION/SUSTENANCE OF STREETLIGHTS ON LOKOJA - AYINGBA ROAD, AJAOKUTA BRIDGE | 36 | 4 | Bill of Quantities | OCB | 35000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
REHABILITATION/SUSTENANCE OF STREETLIGHTS ON ABUJA - KEFFI EXPRESSWAY, ABACHA BARRACKS - KUGBO AND MARARABA | 37 | 5 | Bill of Quantities | OCB | 50000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
NORTH EAST ZONE
INSTALLATION OF STREET LIGHTS ON BAUCHI - GOMBE ROAD, GOMBE END, SECTION II | 38 | 1 | Bill of Quantities | OCB | 87000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
INSTALLATION OF STREET LIGHTS ON YOLA - JALINGO ROAD, JALINGO END | 39 | 2 | Bill of Quantities | OCB | 88000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
REHABILITATION/SUSTENANCE OF STREETLIGHTS ON NUMAN BRIDGE, ADAMAWA | 40 | 3 | Bill of Quantities | OCB | 40000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
REHABILITATION/SUSTENANCE OF STREETLIGHTS ON MAIDUGURI - BIU ROAD, MAIDUGURI END | 41 | 4 | Bill of Quantities | OCB | 40000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
NORTH CENTRAL (HEADQUARTERS)
PROCUREMENT AND INSTALLATION OF 1MVA, 11/0.415KV TRANSFORMER AND ASSOCIATED EQUIPMENT AT FEDERAL MINISTRY OF WORKS HQTRS, MABUSHI, ABUJA. | 42 | 1 | Bill of Quantities | OCB | 40000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
PROVISION OF ILLUMINATED ROAD SAFETY SIGNS ON ABUJA - KEFFI RD, FCT/NASSARAWA STATE | 43 | 2 | Bill of Quantities | OCB | 40000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
UPGRADING OF POWER SUPPLY CABLES AT FEDERAL MINISTRY OF WORKS HQTRS, MABUSHI, ABUJA. | 44 | 3 | Bill of Quantities | OCB | 20000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
MAINTENANCE OF LIFT IN MINISTER'S BLOCK, FEDERAL MINISTRY OF WORKS, HQTRS, MABUSHI, ABUJA. | 45 | 4 | Bill of Quantities | OCB | 10000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
GENERAL MAINTENANCE OF ELECTRICAL INSTALLATIONS AT FEDERAL MINISTRY OF WORKS, HQTRS, MABUSHI, ABUJA. | 46 | 5 | Bill of Quantities | OCB | 40000000 | N/A | MTB | Plan | 5th Mar- 14th Mar | 17th Mar- 25th Mar | 26th Mar- 9th Apr | 10th Apr- 23rd May | 23rd May | 26th May- 10th Jun | 11th Jun- 20th Jun | Plan | 87000000 | N/A | 23rd Jun- 30th Jun | 1st Jul- 8th Jul | N/A | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Water system Development at Engineering Trainning School, Abeokuta . | 47 | 1 | BEME | OCB | 5000000 | N/A | PS | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 4990000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Construction Services for 1 No. 32 Bedroom Storey Hostel at Engineering Training School, Abeokuta. | 48 | 1 | BEME | OCB | 50000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 50000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Construction of Engineering Training School Library at Ijora. | 49 | 2 | BEME | OCB | 10000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 9979800 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Construction Services for 1 No. 32 Bedroom Storey Hostel of the Building at Engineering Training School, Kuje. | 50 | 1 | BEME | OCB | 50000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 50000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Completion of Workshop building at the Engineering Training School, Kuje. | 51 | 2 | BEME | OCB | 10000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 9890000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Infrastructural Development of Federal Ministry of Works Headquarters and Construction of Zonal Headquarters offices in the six Geopolitical zones | 52 | 1 | BEME | OCB | 560000000 | PRE-QUAL | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 560000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Remodification of the old plant and vehicle Workshop building at the new Automobile Training centre, Ijora. | 53 | 1 | BEME | OCB | 48000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 48000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Rehabilitation of existing Hostel/Classrooms at Elect./Mech. Engineering Training School., Abeokuta. | 54 | 1 | BEME | OCB | 5000000 | N/A | PS | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 4989000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Rehabilitation of existing Hostel/Classrooms at Engineering Development Centre,Ijora. | 55 | 2 | BEME | OCB | 5000000 | N/A | PS | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 4989700 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Construction of ICT centre at Elect./Mech. Engineering Training School, Abeokuta. | 56 | 1 | BEME | OCB | 5000000 | N/A | PS | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 4999800 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
EMSD In -House Monitoring and Evaluation of Projects | 57 | 1 | BEME | OCB | 5000000 | N/A | PS | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 4890000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Equipping of Engineering Departments Design Office at FMW Headquarters | 58 | 1 | BEME | OCB | 5000000 | N/A | PS | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 4900900 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Capacity Building for Engineers,Technicians, Technologist,craftsmen in the Engineering Services departments of Federal Ministry of Works | 59 | 1 | BEME | OCB | 5000000 | N/A | PS | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 4998560 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Provision of Solar Street Light at the premises of the Elect./Mech. Engineering Training School, Kuje. | 60 | 1 | BEME | OCB | 5000000 | N/A | PS | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 4900000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
REHABILITATION AND MAINTENANCE OF 3RD MAINLAND BRIDGE INCLUDING UNDER WATER PROTECTION WORKS | 61 | 1 | BEME | OCB | 1000000000 | Pre-Qua | FEC | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 9000000000 | 4th June - 20th June | 23rd June- 30th June | 1st Jul- 8th Jul |  | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
COUNTERPART FUNDING FOR REPLACEMENT OF DILAPIDATED BAILEY BRIDGES | 62 | 1 | BEME | OCB | 1000000000 | Pre-Qua | FEC | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 4600000000 | 4th June - 20th June | 23rd June- 30th June | 1st Jul- 8th Jul |  | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
CONSTRUCTION OF IKOM BRIDGE | 63 | 1 | BEME | OCB | 1000000000 | Pre-Qua | FEC | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 5600000000 | 4th June - 20th June | 23rd June- 30th June | 1st Jul- 8th Jul |  | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
UP GRADING OF HIGHWAYS MANAGEMENT INFORMATION SYSTEM(MIS) FOR FEDERAL HIGHWAYS(DATA BASE/AUTO/CIVILCAD) | 64 | 1 | BEME | OCB | 40000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 40000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
SUBSCRIPTION TO AND PARTICIPATION IN INTERNATIONAL BODIES(TRANS-SAHARAN ,TRANS-AFRICAN HIGHWAY, IRF, TRANS - SAHEL ETC) | 65 | 1 | BEME | OCB | 50000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 50000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
UPGRADING OF FACILITIES AND PROCUREMENT OF TEACHING AIDS FOR HIGHWAY TRAINING CENTRES AT KADUNA,BADAGRY & UGONEKI | 66 | 2 | BEME | OCB | 60000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 60000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
HIGHWAYS TRAFFIC EVALUATION INCLUDING : EQUIPMENT,TRAFFIC CENSUS AND OPERATIONS | 67 | 1 | BEME | OCB | 50000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 50000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
PROVISION OF FACILITIES (HAEDWARE AND SOFTWARE ) FOR ESTABLISHMENT OF ROAD ASSET MANAGEMENT SYSTEM | 68 | 1 | BEME | OCB | 30000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 30000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
PROCUREMENT OF WEIGHBRIDGE EQUIPMENT/PARTS AND OPERATIONS INCLUDING ANCILIARY WORKS(ALONG MAJOR HIGHWAYS);COMPLETION OF ON - GOING PROJECTS | 69 | 1 | BEME | OCB | 255000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 255000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
MANAGING AN INDEPENDENT FIELD CONTROL UNIT TO MONITOR PROGRESS AND ACTIVITIES ON SITE | 70 | 1 | BEME | OCB | 40000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 40000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
SURVEY AND GAZETTING OF RIGHT OF WAY ON THE FEDERAL ROAD NETWORK | 71 | 1 | BEME | OCB | 75000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 75000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Equipping of Internal Audit Departments Offices at FMW Headquarters | 72 | 1 | BEME | OCB | 5000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 4900000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Capacity Building for Internal Auditors of Federal Ministry of Works | 73 | 1 | BEME | OCB | 5000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 4998000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Dualization of Sapele-Ewu road, Section 1: Sapele-Agbor in Delta State | 74 | 1 | BEME | OCB | 1500000000 | N/A | FEC | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 1500000000 | 4th June - 20th June | 23rd June- 30th June | 1st Jul- 8th Jul |  | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Dualization of Sapele-Ewu road, Section 1: Sapele-Agbor in Delta State | 75 | 2 | BEME | OCB | 1500000000 | N/A | FEC | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 1500000000 | 4th June - 20th June | 23rd June- 30th June | 1st Jul- 8th Jul |  | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Dualization of Yenegoa-Road junction - Kolo-Otuoke-Bayelsa Palm (20km) | 76 | 3 | BEME | OCB | 1500000000 | N/A | FEC | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 1500000000 | 4th June - 20th June | 23rd June- 30th June | 1st Jul- 8th Jul |  | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Rehabilitation of Enugu - PortHarcourt Expressway, Section III | 77 | 1 | BEME | OCB | 1000000000 | N/A | FEC | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 1000000000 | 4th June - 20th June | 23rd June- 30th June | 1st Jul- 8th Jul |  | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Dualization of Keffi-Makurdi-9th mile enugu road section i(keffi-makurdi) | 78 | 1 | BEME | OCB | 1000000000 | N/A | FEC | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 1000000000 | 4th June - 20th June | 23rd June- 30th June | 1st Jul- 8th Jul |  | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
pavement Strenghtening and asphalt overlay of Ajebandele -Ijebu Ode-Shagamu road in Ogun State | 79 | 1 | BEME | OCB | 1000000000 | N/A | FEC | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 1000000000 | 4th June - 20th June | 23rd June- 30th June | 1st Jul- 8th Jul |  | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Completion of Otukpo-Oweto (Oweto -Ogboko section) in Benue State | 80 | 1 | BEME | OCB | 500000000 | N/A | FEC | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 500000000 | 4th June - 20th June | 23rd June- 30th June | 1st Jul- 8th Jul |  | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Construction of Koro-Nimbo-Shiagi-Echi Wada road road in Kwara State | 81 | 1 | BEME | OCB | 600000000 | N/A | FEC | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 600000000 | 4th June - 20th June | 23rd June- 30th June | 1st Jul- 8th Jul |  | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Completion of Akpanya-Ofobo road in Kogi State | 82 | 1 | BEME | OCB | 400000000 | N/A | FEC | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 400000000 | 4th June - 20th June | 23rd June- 30th June | 1st Jul- 8th Jul |  | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Rehabilitation of Damaturu -Biu road in Yobe State/ Borno State | 83 | 1 | BEME | OCB | 500000000 | N/A | FEC | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 500000000 | 4th June - 20th June | 23rd June- 30th June | 1st Jul- 8th Jul |  | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Construction of Birni Gwari-Dan Gulbi road in kaduna/ Zamfara States | 84 | 1 | BEME | OCB | 650000000 | N/A | FEC | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 650000000 | 4th June - 20th June | 23rd June- 30th June | 1st Jul- 8th Jul |  | July 2014 | Dec 2014 |  | Diretor Procurement | Permanent Secretary
[8 empty] | Actual | [7 empty] | Actual
Upgrading of Procurement documents and Establishment of Procurement Registry Unit. | 85 | 1 | BEME | OCB | 35000000 | N/A | MTB | Plan | 14th Feb- 7th March | 10th March - 21st March | N/A | 24th Mar - 6th May | 6th May | 7th May- 23rd May | 26th May - 3rd June | Plan | 35000000 | N/A | 4th june- 13th June | 16th June- 23rd June | N/A | June 2014 | December 2014 |  | Diretor Procurement | Permanent Secretary
TOTAL |  |  |  |  | 16563000000

## FMW Consultant
Ministry/Department/Agency:WORKS
Budgetary Year: 2013 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
|  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/ Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | Plan vs. Actual | No-objection Date | FEC Approval | Contract Amount in Naira | Contract Offer | Contract Signature | Plan vs. Actual | Mobilisation Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | Plan | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | Plan | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 1- 2 wk | 2 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
List of Contracts
ENGINEERING DESIGN OF A BRIDGE ACROSS BADAGRY CREEK TO LINK TONGEJI ISLAND WITH WEKAN ALONG NIGERIA-BENIN INTERNATIONAL BOUNDARY | OCB | L/S | 60000000 | MTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 60000000 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26th Aug- 2nd Sept | 3ed Sept- 10th Sept | 60000000 | Diretor Procurement | Perm. Sec.
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Capacity building/Career Development | OCB | L/S | 35000000 | MTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 35000000 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26th Aug- 2nd Sept | 3ed Sept- 10th Sept | 35000000 | Diretor Procurement | Perm. Sec.
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Mainstreaming of HIV/AIDs in the Workplace for the Staff of the Ministry and Field Offices | OCB | L/S | 5000000 | MTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 5000000 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26th Aug- 2nd Sept | 3ed Sept- 10th Sept | 5000000 | Diretor Procurement | Perm. Sec.
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Fill gray cells only!
DESIGN FOR THE OF A ROAD LINKING ARAROMI SEASIDE (ONDO STATE)-ODE (OGUNS STATE) | OCB | L/S | 17416546 | MTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 15000000 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26th Aug- 2nd Sept | 3ed Sept- 10th Sept | 15000000 | Diretor Procurement | Perm. Sec.
[5 empty] | Actual | [6 empty] | Actual | [13 empty] | Actual
ENGINEERING DESIGN OF IJEBU ODE-EPE ROAD IN OGUN/LAGOS STATES | OCB | L/S | 8708273 | MTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 10000000 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26th Aug- 2nd Sept | 3ed Sept- 10th Sept | 10000000 | Diretor Procurement | Perm. Sec.
[5 empty] | Actual | [6 empty] | Actual | [13 empty] | Actual
DESIGN FOR THE REHAB OF UKHUNUMWA-IGBASUWA | OCB | L/S | 8708273 | MTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 10000000 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26th Aug- 2nd Sept | 3ed Sept- 10th Sept | 10000000 | Diretor Procurement | Perm. Sec.
[5 empty] | Actual | [6 empty] | Actual | [13 empty] | Actual
DESIGN FOR THE REHABILITATION OF SILLUKO-IGBASUWA OKADA-OGBESE ROAD | OCB | L/S | 8708273 | MTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 10000000 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26th Aug- 2nd Sept | 3ed Sept- 10th Sept | 10000000 | Diretor Procurement | Perm. Sec.
[5 empty] | Actual | [6 empty] | Actual | [13 empty] | Actual
DESIGN OF AWO-IDEMILI-UMUDURU ROAD | OCB | L/S | 3483309 | MTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 15000000 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26th Aug- 2nd Sept | 3ed Sept- 10th Sept | 15000000 | Diretor Procurement | Perm. Sec.
[5 empty] | Actual | [6 empty] | Actual | [13 empty] | Actual
ENGINEERING DESIGN FOR THE DUALIZATION OF KULENDE JUNCTION - NNPC DEPOT OKE OYI IN KWARA STATE | OCB | L/S | 8708273 | MTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 15000000 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26th Aug- 2nd Sept | 3ed Sept- 10th Sept | 15000000 | Diretor Procurement | Perm. Sec.
[5 empty] | Actual | [6 empty] | Actual | [13 empty] | Actual
ENGINEERING DESIGN OF AZARE-BARKEJI-MADARA ROAD IN BAUCHI STATE | OCB | L/S | 8708273 | MTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 15000000 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26th Aug- 2nd Sept | 3ed Sept- 10th Sept | 15000000 | Diretor Procurement | Perm. Sec.
[5 empty] | Actual | [6 empty] | Actual | [13 empty] | Actual
ENGINEERING DESIGN FOR THE CONSTRUCTION OF GEIDAM-DAMASAK ROAD IN YOBE/BORNO STATE | OCB | L/S | 12000000 | MTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 15000000 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26th Aug- 2nd Sept | 3ed Sept- 10th Sept | 15000000 | Diretor Procurement | Perm. Sec.
[5 empty] | Actual | [6 empty] | Actual | [13 empty] | Actual
ENGINEERING DESIGN FOR THE CONSTRUCTION OF GURI-GOGARAM-GASHUA ROAD IN YOBE STATE | OCB | L/S | 12000000 | MTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | N/A | N/A | 15000000 | 1st Aug- 8th Aug | 11th Aug- 25th Aug | Plan | N/A | 26th Aug- 2nd Sept | 3ed Sept- 10th Sept | 15000000 | Diretor Procurement | Perm. Sec.
[5 empty] | Actual | [6 empty] | Actual | [13 empty] | Actual
ENGINEERING DESIGN FOR THE REHAB OF DAMATURU-BIU ROAD IN YOBE STATE | OCB | L/S | 500000000 | FEC | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | 4th Aug- 18th Aug | 19th Aug- 2nd Sept | 15000000 | 3rd Sept- 10th Sept | 11th Sept- 25th Sept | Plan | N/A | 26th Aug- 2nd Sept | 3ed Sept- 10th Sept | 15000000 | Diretor Procurement | Perm. Sec.
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Procurement Monitoring Compliance and Evaluation of Road Projects in the 36 States and FCT | NA | LUMP SUM | 8000000 | MTB | Plan | NA | NA | N/A | NA | NA | N/A |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA |  | NA | NA | NA | 8000000 | DDP | Perm Sec.
Placement of Advertisement in National Dailies and Tender Journal | NA | LUMP SUM | 5000000 | MTB | Plan | NA | NA | N/A | NA | NA | N/A |  | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA |  | NA | NA | NA | 5000000 | DDP | Perm Sec.
Capacity Building for Procurement Officers | NA | LUMP SUM | 20000000 | MTB | Plan | 14th Feb - 28th Feb | 3rd Mar - 10th Mar | 11th Mar- 24th Mar | 25th Mar- 1st Apr | 2nd Apr- 9th Apr | 10th Apr- 17th Apr | Plan | 18th Apr- 16th May | 16th May | 19th May - 2nd June | 3rd Jun- 17th Jun | 18th Jun- 2nd Jul | 3rd Jul- 17th Jul | 18th Jul- 1st Aug | Plan | 4th Aug- 18th Aug | 19th Aug- 2nd Sept | 20000000 | 3rd Sept- 10th Sept | 11th Sept- 25th Sept | Plan | N/A | 26th Aug- 2nd Sept | 3ed Sept- 10th Sept | 20000000 | Diretor Procurement | Perm. Sec.
[12 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual

## PRPA Consultancy Services
Ministry/Department/Agency: Planning, Research and Policy Analysis
Budget Year: 2014
|  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2.2 - 2 weeks | 3 weeks | 2 - 4 weeks | 2 weeks | 4 - 6 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
DEVELOPMENT OF DATABANK OF NIGERIA SCIENTIST, ENGINEERS$ TECHNOLOGIST(LOCAL AND IN DIASPORA | Plan | FMST/PD/003 | 3 | Time-Based | 60000000 | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 5/02/14 - 19/02/14 | 24/02/14 - 7/03/14 | 17/03/14 - 31/03/14 | 7/04/14 - 14/04/14 | 15/04/14 | 17/04/14 - 30/04/14 | 12/05/14 - 26/05/14 | 27/05/14 - 20/06/14 | 23/06/14 - 30/06/14 | 1/07/14 - 15/07/14 | 16/07/14 - 30/07/14 | 31/07/14 - 8/08/14 | 11/08/14 - 22/08/14 | 25/08/14 - 8/09/14 | 60000000 | NA | 15/09/14 - 19/09/14 | 22/09/14 - 6/10/14 | 6/10/14 - 17/10/14 | 31/10/14 | 7/11/14 | 60000000 | PO Emeana - [Designation: CPO] | ABBA TUJA - [Designation: DD Procurement]
Actual
AUTOMATING OF SELECTED PROCESS AND ACTIVITIES OF FMST AND ITS OPERATION | Plan | FMST/PD/006 | 6 |  | 30000000 | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 6/02/14 - 19/02/14 | 24/02/14 - 7/03/14 | 17/03/14 - 31/03/14 | 7/04/14 - 14/04/14 | 15/04/14 | 17/04/14 - 30/04/14 | 12/05/14 - 26/05/14 | 27/05/14 - 20/06/14 | 23/06/14 - 30/06/14 | 1/07/14 - 15/07/14 | 16/07/14 - 30/07/14 | 31/07/14 - 8/08/14 | 11/08/14 - 22/08/14 | 25/08/14 - 8/09/14 | 30000000 | NA | 15/09/14 - 19/09/14 | 22/09/14 - 6/10/14 | 6/10/14 - 17/10/14 | 31/10/14 | 7/11/14 | 30000000 | ISA MSHELTANGE - [Designation: PPO] | ABBA TUJA - [Designation: DD Procurement]
Actual
SURVEY FOR DETERMINATION OF LEVEL OF EXPROSE TO PESTICIDERSIDS IN FOOD | Plan | FMST/PD/007 | 7 | Time-Based | 8000000 | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 6/02/14 - 19/02/14 | 24/02/14 - 7/03/14 | 17/03/14 - 31/03/14 | 7/04/14 - 14/04/14 | 15/04/14 | 17/04/14 - 30/04/14 | 12/05/14 - 26/05/14 | 27/05/14 - 20/06/14 | 23/06/14 - 30/06/14 | 1/07/14 - 15/07/14 | 16/07/14 - 30/07/14 | 31/07/14 - 8/08/14 | 11/08/14 - 22/08/14 | 25/08/14 - 8/09/14 | 8000000 | NA | 15/09/14 - 19/09/14 | 22/09/14 - 6/10/14 | 6/10/14 - 17/10/14 | 31/10/14 | 7/11/14 | 8000000 | Alabi Kolawole - [Designation: PPO] | PO Emeana - [Designation: CPO]
Actual
TECHNOLOGY DIFFUSION AND TRANSFER(DTI) | Plan | FMST/PD/009 | 9 | Lump Sum | 10000000 | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 5/02/14 - 19/02/14 | 24/02/14 - 7/03/14 | 17/03/14 - 31/03/14 | 7/04/14 - 14/04/14 | 15/04/14 | 17/04/14 - 30/04/14 | 12/05/14 - 26/05/14 | 27/05/14 - 20/06/14 | 23/06/14 - 30/06/14 | 1/07/14 - 15/07/14 | 16/07/14 - 30/07/14 | 31/07/14 - 8/08/14 | 11/08/14 - 22/08/14 | 25/08/14 - 8/09/14 | 10000000 | NA | 15/09/14 - 19/09/14 | 22/09/14 - 6/10/14 | 6/10/14 - 17/10/14 | 31/10/14 | 7/11/14 | 10000000 | Peter Aribo - [Designation: CPO] | ABBA TUJA - [Designation: DD Procurement]
Actual
Total Cost Plan |  |  |  |  | 108000000 | [19 empty] | 108000000 | [6 empty] | 108000000
Total Cost Actual

## PRPA Goods
Ministry/Department/Agency: Planning, Research and Policy Analysis
Budget Year: 2014
|  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Goods |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Arrival of Goods | Inspection/Final Acceptance | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
Plan vs Actual
DEVELOPMENT AND EQUIPING OF NATIONAL SCIENCE AND TECHNOLOGY MUSEUM | Plan | FMST/PD/001 | 1 | Sch of Del | 30000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 10/02/14 - 27/02/14 | 28/02/14 - 14/03/14 | NA | NA | NA | 14/04/14 | 19/05/14 | 20/05/14 - 6/06/14 | 9/06/14 - 27/06/14 | 30000000 | NA | 30/06/14 - 7/07/14 | 8/07/14 - 22/07/14 | 23/07/14 - 11/08/14 | 15/09/14 - 26/09/14 | 6/10/14 - 20/10/14 | Peter Aribo - [Designation: CPO] | ABBA TUJA - [Designation: DD Procurement]
Actual
Total Cost Plan |  |  |  |  | 30000000 | [14 empty] | 30000000
Total Cost Actual

## PRPA Non-Consultancy Services
Ministry/Department/Agency: Planning, Research and Policy Analysis
Budget Year: 2014
|  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2.2 - 2 weeks | 3 weeks | 2 - 4 weeks | 2 weeks | 4 - 6 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
NATIONAL SCIENCE TECHNOLOGY WEEK | Plan | FMST/PD/10 | 10 | Time-Based | 10000000 | NS | Ministerial Tenders Board | CQ - Consultant&#039;s Qualification | POST-QUALIFICATION | POST REVIEW | 6/02/14 - 20/02/14 | 24/02/14 - 7/03/14 | 17/03/14 - 31/03/14 | 7/04/14 - 14/04/14 | 15/04/14 | 17/04/14 - 30/04/14 | 12/05/14 - 26/05/14 | 27/05/14 - 20/06/14 | 23/06/14 - 30/06/14 | 1/07/14 - 15/07/14 | 16/07/14 - 30/07/14 | 31/07/14 - 8/08/14 | 11/08/14 - 22/08/14 | 25/08/14 - 8/09/14 | 10000000 | NA | 15/09/14 - 19/09/14 | 22/09/14 - 6/10/14 | 6/10/14 - 17/10/14 | 31/10/14 | 7/11/14 | 10000000 | ISA MSHELTANGA - [Designation: PPO] | PO Emeana - [Designation: CPO]
Actual
INTERNARTIONAL JUNIOR SCIENCE OLYMPIAD (IJSO) EVENT | Plan | FMST/PD/11 | 11 | Time-Based | 20000000 | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 6/02/14 - 20/02/14 | 24/02/14 - 7/03/14 | 17/03/14 - 31/03/14 | 7/04/14 - 14/04/14 | 15/04/14 | 17/04/14 - 30/04/14 | 12/05/14 - 26/05/14 | 27/05/14 - 20/06/14 | 23/06/14 - 30/06/14 | 1/07/14 - 15/07/14 | 16/07/14 - 30/07/14 | 31/07/14 - 8/08/14 | 11/08/14 - 22/08/14 | 25/08/14 - 8/09/14 | 20000000 | NA | 15/09/14 - 19/09/14 | 22/09/14 - 6/10/14 | 6/10/14 - 17/10/14 | 31/10/14 | 7/11/14 | 20000000 | Alabi Kolawole - [Designation: PPO] | Peter Aribo - [Designation: CPO]
Actual
PRESIDENTIAL STANDING COMMITTEE ON INNOVATION AND INVENTION(PSCII) | Plan | FMST/PD/13 | 13 | Lump Sum | 80000000 | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 6/02/14 - 20/02/14 | 24/02/14 - 7/03/14 | 17/03/14 - 31/03/14 | 7/04/14 - 14/04/14 | 15/04/14 | 17/04/14 - 30/04/14 | 12/05/14 - 26/05/14 | 27/05/14 - 20/06/14 | 23/06/14 - 30/06/14 | 1/07/14 - 15/07/14 | 16/07/14 - 30/07/14 | 31/07/14 - 8/08/14 | 11/08/14 - 22/08/14 | 25/08/14 - 8/09/14 | 80000000 | NA | 15/09/14 - 19/09/14 | 22/09/14 - 6/10/14 | 6/10/14 - 17/10/14 | 31/10/14 | 7/11/14 | 80000000 | Peter Aribo - [Designation: CPO] | ABBA TUJA - [Designation: DD Procurement]
Actual
Total Cost Plan |  |  |  |  | 110000000 | [19 empty] | 110000000 | [6 empty] | 110000000
Total Cost Actual

## PRPA Works
Ministry/Department/Agency: Planning, Research and Policy Analysis
Budget Year: 2014
|  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Works |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Plan vs Actual
Establishment of Central E-Library | Plan | FMST/PD/012 | 12 | Lump Sum | 30624570 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 10/02/14 - 27/02/14 | 28/02/14 - 14/03/14 | NA | NA | NA | NA | NA | 14/04/14 | 19/05/14 | 20/05/14 - 6/06/14 | 9/06/14 - 27/06/14 | 30624570 | NA | 30/06/14 - 7/07/14 | 8/07/14 - 22/07/14 | 23/07/14 - 11/08/14 | 19/09/14 | 20/10/14 | 30624570 | ISA MSHELTANGA - [Designation: PPO] | ABBA TUJA - [Designation: DD Procurement]
Actual
DEVELOPMENT OF SCIENCE AND TECHNOLOGY PARK(S$TPARKS)IN NIGERIA | Plan | FMST/PD/002 | 2 | Lump Sum | 80000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 10/02/14 - 27/02/14 | 28/02/14 - 14/03/14 | NA | NA | NA | NA | NA | 14/04/14 | 19/05/14 | 20/05/14 - 6/06/14 | 9/06/14 - 27/06/14 | 80000000 | NA | 30/06/14 - 7/07/14 | 8/07/14 - 22/07/14 | 23/07/14 - 11/08/14 | 19/09/14 | 20/10/14 | 80000000 | Agwai Cyril - [Designation: Chief Procurement Officer] | ABBA TUJA - [Designation: DD Procurement]
Actual
KARSHI SOLAR TECHNOLOGY EXPERIMENT | Plan | FMST/PD/004 | 4 | Lump Sum | 20000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 10/02/14 - 27/02/14 | 28/02/14 - 14/03/14 | NA | NA | NA | NA | NA | 14/04/14 | 19/05/14 | 20/05/14 - 6/06/14 | 9/06/14 - 27/06/14 | 20000000 | NA | 30/06/14 - 7/07/14 | 8/07/14 - 22/07/14 | 23/07/14 - 11/08/14 | 19/09/14 | 20/10/14 | 20000000 | ANTHONY MBIBI - [Designation: ACPO] | ABBA TUJA - [Designation: DD Procurement]
Actual
WARD BASED CLUSTER PROJECT | Plan | FMST/PD/005 | 5 | Lump Sum | 20000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 10/02/14 - 27/02/14 | 28/02/14 - 14/03/14 | NA | NA | NA | NA | NA | 14/04/14 | 19/05/14 | 20/05/14 - 6/06/14 | 9/06/14 - 27/06/14 | 20000000 | NA | 30/06/14 - 7/07/14 | 8/07/14 - 22/07/14 | 23/07/14 - 11/08/14 | 19/09/14 | 20/10/14 | 20000000 | Alabi Kolawole - [Designation: PPO] | ABBA TUJA - [Designation: DD Procurement]
Actual
ESTABLISHMENT OF FMST CALL CENTER ON GOVT SERVICE PORTAL | Plan | FMST/PD/008 | 8 | Lump Sum | 7000000 | NCB | Accounting Officer: Permanent Secretary | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 10/02/14 - 27/02/14 | 28/02/14 - 14/03/14 | NA | NA | NA | NA | NA | 14/04/14 | 19/05/14 | 20/05/14 - 6/06/14 | 9/06/14 - 27/06/14 | 7000000 | NA | 30/06/14 - 7/07/14 | 8/07/14 - 22/07/14 | 23/07/14 - 11/08/14 | 19/09/14 | 20/10/14 | 7000000 | ANTHONY MBIBI - [Designation: ACPO] | Agwai Cyril - [Designation: Chief Procurement Officer]
Actual
Total Cost Plan |  |  |  |  | 157624570 | [16 empty] | 157624570 | [6 empty] | 157624570
Total Cost Actual

## EHOR 2 Consultancy Services
Ministry/Department/Agency: Environmental Health Officers Registration Council Of Nigeria
Budget Year: 2014
|  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 1 weeks | 2 - 4 weeks | 2 weeks | 2 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
CONSTRUCTION OF TWO DIFFERENT TYPE OF DOMESTIC BIOMASS DIGESTERS IN EVERONMENTAL HEALTH TRANNING INSTITUTION | Plan | EHOROE004005255 | 1 | Lump Sum | 27000000 | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 17/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 - 3/04/14 | 3/04/14 - 10/04/14 | 24/04/14 | 24/04/14 - 8/05/14 | 8/05/14 - 22/05/14 | 22/05/14 - 22/05/14 | 22/05/14 - 5/06/14 | 5/06/14 - 19/06/14 | 19/06/14 - 3/07/14 | 3/07/14 - 17/07/14 | 17/07/14 - 31/07/14 | 31/07/14 - 28/08/14 | 27000000 | NA | 28/08/14 - 11/09/14 | 11/09/14 - 25/09/14 | NA | 23/10/14 | 6/11/14 | NA | CHINWEOKW COLLINS - [Designation: Procurement Officer] | ABONYI DOMINC - [Designation: CHIEF ENVIRONMENTAL HEALTH OFFICER]
Actual
STRENGTENING OF ENVIRONMENTAL HEALTH OFFICERS CAPACITY TO ENFORCE IMPROVED SANITATION STANDARD AND OTHER LOGISTICS. | Plan | EHORE003005246 | 2 | Lump Sum | 29500000 | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 17/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 - 3/04/14 | 3/04/14 - 10/04/14 | 24/04/14 | 24/04/14 - 8/05/14 | 8/05/14 - 22/05/14 | 22/05/14 - 22/05/14 | 22/05/14 - 5/06/14 | 5/06/14 - 19/06/14 | 19/06/14 - 3/07/14 | 3/07/14 - 17/07/14 | 17/07/14 - 31/07/14 | 31/07/14 - 28/08/14 | 29500000 | NA | 28/08/14 - 11/09/14 | 11/09/14 - 25/09/14 | NA | 23/10/14 | 6/11/14 | NA | ABIODUN FUNMILAYO - [Designation: SENIOR ADMIN OFFICER] | BABA MOHAMMED - [Designation: CHIEF ENVIRONMENTAL HEALTH OFFICER]
Actual
DEVELOPMENT OF MINIMUM PROFESSIONAL PRACTICE REFERENCE STANDARD AND ENVIRONMENTAL HEALTH EDUCATION AND AWARENESS NATIONWIDE WITH ASSOCIATED. | Plan | EHORE0030052 | 3 | Lump Sum | 32070000 | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 17/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 - 3/04/14 | 3/04/14 - 10/04/14 | 24/04/14 | 24/04/14 - 8/05/14 | 8/05/14 - 22/05/14 | 22/05/14 - 22/05/14 | 22/05/14 - 5/06/14 | 5/06/14 - 19/06/14 | 19/06/14 - 3/07/14 | 3/07/14 - 17/07/14 | 17/07/14 - 31/07/14 | 31/07/14 - 28/08/14 | 32070000 | NA | 28/08/14 - 11/09/14 | 11/09/14 - 25/09/14 | NA | 23/10/14 | 6/11/14 | NA | ANDY UKAH - [Designation: CHIEF ENVIRONMENTAL HEALTH OFFICER] | ABONYI DOMINC - [Designation: CHIEF ENVIRONMENTAL HEALTH OFFICER]
Actual
DEVELOPMENT OF ENVIRONMENTAL HEALTH INFORMATION SYSTEM/IHRIS SOFTWARE AND CAPACITY BUILDING DEVELOPMENT FOR EHORECON STAFF TO IMPROVED DATA MANAGEMENT | Plan | EHORE004004255 | 4 | Lump Sum | 48000000 | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Actual
Total Cost Plan |  |  |  |  | 136570000 | [19 empty] | 88570000
Total Cost Actual

## EHOR 2 Goods
Ministry/Department/Agency: Environmental Health Officers Registration Council Of Nigeria
Budget Year: 2014
|  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Goods |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Arrival of Goods | Inspection/Final Acceptance | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
Plan vs Actual
PROCUREMENT OF EQUIPMENT AND MATERIALS TO STRENTHING ENVIRONMENTAL HEALTH PROGRAMMES IN SELECTED UNIVERSITIES | Plan | EHORE001005232 | 1 | Sch of Del | 41430000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 17/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | NA | NA | NA | 20/03/14 | 1/05/14 | 1/05/14 - 22/05/14 | 22/05/14 - 19/06/14 | 41430000 | NA | 19/06/14 - 3/07/14 | 3/07/14 - 17/07/14 | NA | 17/07/14 - 15/08/14 | 15/08/14 - 29/08/14 | CHINWEOKW COLLINS - [Designation: Procurement Officer] | ANDY UKAH - [Designation: CHIEF ENVIRONMENTAL HEALTH OFFICER]
Actual
PROCUREMENT OF OFFICE EQUIPMENT AND OTHER LOGISTICS | Plan | EHORE004004255 | 2 | Sch of Del | 48000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 17/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | NA | NA | NA | 20/03/14 | 1/05/14 | 1/05/14 - 22/05/14 | 22/05/14 - 19/06/14 | 48000000 | NA | 19/06/14 - 3/07/14 | 3/07/14 - 17/07/14 | NA | 17/07/14 - 15/08/14 | 15/08/14 - 29/08/14 | ADIKWU LILIAN - [Designation: PRINCIPAL ACCOUNTANT] | MBA VICTOR - [Designation: ASSISTANT CHIEF ADMIN OFFICER]
Actual
Total Cost Plan |  |  |  |  | 89430000 | [14 empty] | 89430000
Total Cost Actual

## E.H.O.R Consultancy Services
Ministry/Department/Agency: Environmental Health Officers Registration Council Of Nigeria
Budget Year: 2014
|  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2.2 - 2 weeks | 3 weeks | 2 - 4 weeks | 2 weeks | 4 - 6 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
CONSTRUCTION OF TWO DIFFERENT TYPE OF DOMESTIC BIOMASS DIGESTERS IN EVERONMENTAL HEALTH TRANNING INSTITUTION | Plan | EHOROE004005255 | 1 | Lump Sum | 27000000 | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 17/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 - 3/04/14 | 3/04/14 - 10/04/14 | 24/04/14 | 24/04/14 - 8/05/14 | 8/05/14 - 4/06/14 | 4/06/14 - 4/06/14 | 4/06/14 - 18/06/14 | 18/06/14 - 2/07/14 | 2/07/14 - 16/07/14 | 16/07/14 - 30/07/14 | 30/07/14 - 13/08/14 | 13/08/14 - 10/09/14 | 27000000 | NA | 10/09/14 - 24/09/14 | 24/09/14 - 8/10/14 | NA | 18/11/14 | 16/12/14 | NA | CHINWEOKW COLLINS - [Designation: Procurement Officer] | ABONYI DOMINC - [Designation: CHIEF ENVIRONMENTAL HEALTH OFFICER]
Actual
STRENGTENING OF ENVIRONMENTAL HEALTH OFFICERS CAPACITY TO ENFORCE IMPROVED SANITATION STANDARD AND OTHER LOGISTICS. | Plan | EHORE003005246 | 2 | Lump Sum | 29500000 | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 17/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 - 3/04/14 | 3/04/14 - 10/04/14 | 24/04/14 | 24/04/14 - 8/05/14 | 8/05/14 - 4/06/14 | 4/06/14 - 4/06/14 | 4/06/14 - 18/06/14 | 18/06/14 - 2/07/14 | 2/07/14 - 16/07/14 | 16/07/14 - 30/07/14 | 30/07/14 - 13/08/14 | 13/08/14 - 10/09/14 | 29500000 | NA | 10/09/14 - 24/09/14 | 24/09/14 - 8/10/14 | NA | 19/11/14 | 17/12/14 | NA | ABIODUN FUNMILAYO - [Designation: SENIOR ADMIN OFFICER] | BABA MOHAMMED - [Designation: CHIEF ENVIRONMENTAL HEALTH OFFICER]
Actual
DEVELOPMENT OF MINIMUM PROFESSIONAL PRACTICE REFERENCE STANDARD AND ENVIRONMENTAL HEALTH EDUCATION AND AWARENESS NATIONWIDE WITH ASSOCIATED. | Plan | EHORE0030052 | 3 | Lump Sum | 32070000 | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 17/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 - 3/04/14 | 3/04/14 - 10/04/14 | 24/04/14 | 24/04/14 - 8/05/14 | 8/05/14 - 4/06/14 | 4/06/14 - 4/06/14 | 4/06/14 - 18/06/14 | 18/06/14 - 2/07/14 | 2/07/14 - 16/07/14 | 16/07/14 - 30/07/14 | 30/07/14 - 13/08/14 | 13/08/14 - 10/09/14 | 32070000 | NA | 10/09/14 - 24/09/14 | 24/09/14 - 8/10/14 | NA | 19/11/14 | 17/12/14 | NA | ANDY UKAH - [Designation: CHIEF ENVIRONMENTAL HEALTH OFFICER] | ABONYI DOMINC - [Designation: CHIEF ENVIRONMENTAL HEALTH OFFICER]
Actual
DEVELOPMENT OF ENVIRONMENTAL HEALTH INFORMATION SYSTEM/IHRIS SOFTWARE AND CAPACITY BUILDING DEVELOPMENT FOR EHORECON STAFF TO IMPROVED DATA MANAGEMENT | Plan | EHORE004004255 | 4 | Lump Sum | 48000000 | NCB | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Actual
Total Cost Plan |  |  |  |  | 88570000 | [19 empty] | 88570000
Total Cost Actual

## EHOR Goods
Ministry/Department/Agency: Environmental Health Officers Registration Council Of Nigeria
Budget Year: 2014
|  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Goods |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Arrival of Goods | Inspection/Final Acceptance | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
Plan vs Actual
PROCUREMENT OF EQUIPMENT AND MATERIALS TO STRENTHING ENVIRONMENTAL HEALTH PROGRAMMES IN SELECTED UNIVERSITIES | Plan | EHORE001005232 | 1 | Sch of Del | 41430000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 17/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | NA | NA | NA | 20/03/14 | 1/05/14 | 1/05/14 - 22/05/14 | 22/05/14 - 19/06/14 | 41430000 | NA | 19/06/14 - 3/07/14 | 3/07/14 - 17/07/14 | NA | 17/07/14 - 15/08/14 | 15/08/14 - 29/08/14 | CHINWEOKW COLLINS - [Designation: Procurement Officer] | ANDY UKAH - [Designation: CHIEF ENVIRONMENTAL HEALTH OFFICER]
Actual
PROCUREMENT OF OFFICE EQUIPMENT AND OTHER LOGISTICS | Plan | EHORE004004255 | 2 | Sch of Del | 48000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 17/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | NA | NA | NA | 20/03/14 | 1/05/14 | 1/05/14 - 22/05/14 | 22/05/14 - 19/06/14 | 48000000 | NA | 19/06/14 - 3/07/14 | 3/07/14 - 17/07/14 | NA | 17/07/14 - 15/08/14 | 15/08/14 - 29/08/14 | ADIKWU LILIAN - [Designation: PRINCIPAL ACCOUNTANT] | MBA VICTOR - [Designation: ASSISTANT CHIEF ADMIN OFFICER]
Actual
Total Cost Plan |  |  |  |  | 89430000 | [14 empty] | 89430000
Total Cost Actual

## EHOR Works
Ministry/Department/Agency: Environmental Health Officers Registration Council Of Nigeria
Budget Year:
|  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Works |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Plan vs Actual
Total Cost Plan
Total Cost Actual

## E.H.O.R Goods
Ministry/Department/Agency: Environmental Health Officers Registration Council Of Nigeria
Budget Year: 2014 |  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Goods |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Arrival of Goods | Inspection/Final Acceptance | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
Plan vs Actual
PROCUREMENT OF EQUIPMENT AND MATERIALS TO STRENTHING ENVIRONMENTAL HEALTH PROGRAMMES IN SELECTED UNIVERSITIES | Plan | EHORE001005232 | 1 | Sch of Del | 41430000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 17/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | NA | NA | NA | 20/03/14 | 1/05/14 | 1/05/14 - 22/05/14 | 22/05/14 - 19/06/14 | 41430000 | NA | 19/06/14 - 3/07/14 | 3/07/14 - 17/07/14 | NA | 17/07/14 - 15/08/14 | 15/08/14 - 29/08/14 | CHINWEOKW COLLINS - [Designation: Procurement Officer] | ANDY UKAH - [Designation: CHIEF ENVIRONMENTAL HEALTH OFFICER]
Actual
. | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | .
.
Total Cost Plan |  |  |  |  | 41430000 | [14 empty] | 41430000
Total Cost Actual

## D.M.O
PROCUREMENT PLAN 2014
Debt Management Office
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
ABUBAKAR S. K. NO. 08036914999 |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Acquisition of Computer Systems | N/A | 1 | 4932580 | National Competitive Bidding | N/A | N/A | Plan | 25/08/14 - 09/09/14 | N/A | N/A | 5/08/14 | 16/09/14 | 16/09/14 -30/09/14 | N/A | Plan | 4932580 | N/A | 24/10/14 | 24/10/14 | - | 14/11/14 | 14/11/14
[7 empty] | Actual | [7 empty] | Actual
Computer Software Acquisition | N/A | 2 | 11609801 | National Competitive Bidding | N/A | N/A | Plan | 25/08/14 - 09/09/14 | N/A | N/A | 5/08/14 | 16/09/14 | 16/09/14 -30/09/14 | N/A | Plan | 11609801 | N/A | 24/10/14 | 24/10/14 | - | 14/11/14 | 14/11/14
[7 empty] | Actual | [7 empty] | Actual
Office Furniture | N/A | 3 | 8460000 | National Competitive Bidding | N/A | N/A | Plan | 25/08/14 - 09/09/14 | N/A | N/A | 5/08/14 | 16/09/14 | 16/09/14 -30/09/14 | N/A | Plan | 8460000 | N/A | 24/10/14 | 24/10/14 | - | 14/11/14 | 14/11/14
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  | 6 | 25002381 |  |  |  | Plan | [7 empty] | Plan | 25002381
|  | 0 | 0 |  |  |  | Actual | [7 empty] | Actual | 0
Fill gray cells only!

## COREN GOODS
Ministry/Department/Agency: WORKS - COREN
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
|  | Basic Data | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks | Plan |  | 2wks | 1 - 2 wks | 1 wks | Plan | 2 -3 wks | T | 2 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual |  |  |  |  | Actual
List of Contracts
Procurement of Project Vehicle (Toyota Hilux) - for Makurdi Zonal Office, Benue State | 1 | 1 | 5878000 | OCB | Post- Qual | CTB | Plan | 14th Feb-7th March, 2014 | 10th March-17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May- 16th May | 19th May- 26th May | Plan | 5878000 | N/A | 27th May- 3rd June | 4th june - 18th June | Plan | N/A | 19th June- 3rd July | 4th July- 17th July | COREN REGISTRAR | COREN PRESIDENT
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Procurement of Project Vehicle for Kano Zonal Office (KIA Cerato) | 2 | 2 | 5061000 | OCB | Post- Qual | CTB | Plan | 14th Feb-7th March, 2014 | 10th March-17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May- 16th May | 19th May- 26th May | Plan | 5061000 | N/A | 27th May- 3rd June | 4th june - 18th June | Plan | N/A | 19th June- 3rd July | 4th July- 17th July | COREN REGISTRAR | COREN PRESIDENT
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Procurement of Project Vehicle for Enugu Zonal Office (KIA Cerato), Enugu State | 3 | 1 | 5061000 | OCB | Post- Qual | CTB | Plan | 14th Feb-7th March, 2014 | 10th March-17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May- 16th May | 19th May- 26th May | Plan | 5061000 | N/A | 27th May- 3rd June | 4th june - 18th June | Plan | N/A | 19th June- 3rd July | 4th July- 17th July | COREN REGISTRAR | COREN PRESIDENT
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Procurement of Laptop for Management Staff. | 4 | 1 | 4760000 | OCB | Post- Qual | C/President | Plan | 14th Feb-7th March, 2014 | 10th March-17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May- 16th May | 19th May- 26th May | Plan | 4760000 | N/A | 27th May- 3rd June | 4th june - 18th June | Plan | N/A | 19th June- 3rd July | 4th July- 17th July | COREN REGISTRAR | COREN PRESIDENT
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Procurement of Desktop for Staff at Head office | 5 | 2 | 1260000 | OCB | Post- Qual | C/Registrar | Plan | 14th Feb-7th March, 2014 | 10th March-17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May- 16th May | 19th May- 26th May | Plan | 1260000 | N/A | 27th May- 3rd June | 4th june - 18th June | Plan | N/A | 19th June- 3rd July | 4th July- 17th July | COREN REGISTRAR | COREN PRESIDENT
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Purchase of Printers | 6 | 1 | 750000 | OCB | Post- Qual | C/Registrar | Plan | 14th Feb-7th March, 2014 | 10th March-17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May- 16th May | 19th May- 26th May | Plan | 750000 | N/A | 27th May- 3rd June | 4th june - 18th June | Plan | N/A | 19th June- 3rd July | 4th July- 17th July | COREN REGISTRAR | COREN PRESIDENT
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Purchase of Photocopier Machines | 7 | 2 | 1230000 | OCB | Post- Qual | C/Registrar | Plan | 14th Feb-7th March, 2014 | 10th March-17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May- 16th May | 19th May- 26th May | Plan | 1230000 | N/A | 27th May- 3rd June | 4th june - 18th June | Plan | N/A | 19th June- 3rd July | 4th July- 17th July | COREN REGISTRAR | COREN PRESIDENT
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Provision of Conference table (2 units) and Chairs (at least 34 units) at Council Chamber, Head Office, Abuja | 8 | 1 | 3500000 |  | Post- Qual | C/President | Plan | 14th Feb-7th March, 2014 | 10th March-17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May- 16th May | 19th May- 26th May | Plan | 3500000 | N/A | 27th May- 3rd June | 4th june - 18th June | Plan | N/A | 19th June- 3rd July | 4th July- 17th July | COREN REGISTRAR | COREN PRESIDENT
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Plan
Actual
Provision of Furniture @ COREN Head office with File cabinet Design Equipment and Software for Mechanical Services | 9 | 1 | 3500000 |  | MTB | C/President | Plan | 14th Feb-7th March, 2014 | 10th March-17th March | N/A | 18th Mar- 30th April | 30th April | 2nd May- 16th May | 19th May- 26th May | Plan | 3500000 | N/A | 27th May- 3rd June | 4th june - 18th June | Plan | N/A | 19th June- 3rd July | 4th July- 17th July | COREN REGISTRAR | COREN PRESIDENT
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Total Cost |  |  | 15000000 | [12 empty] | 15000000

## COREN WORKS (2)
Ministry/Department/Agency: WORKS - COREN
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
|  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Construction of Kano Zonal Office, Kano State. | 1 | 1 | BEME | OCB | 53000000 | N/A | MTB | Plan | 28th Feb- 20th March | 21st March-27th March | N/A | 28th Mar- 9th May | 9th May | 12th May- 27th May | 28th May- 4th June | Plan | 53000000 | N/A | 5th June- 12th June | 13th June- 20th June | N/A | June 2014 | Dec 2014 | COREN REGISTRAR | COREN PRESIDENT
[8 empty] | Actual | [7 empty] | Actual
Construction of Makurdi Zonal Office, Makurdi, Benue State | 2 | 1 | BEME | OCB | 53000000 | N/A | MTB | Plan | 28th Feb- 20th March | 21st March-27th March | N/A | 28th Mar- 9th May | 9th May | 12th May- 27th May | 28th May- 4th June | Plan | 53000000 | N/A | 5th June- 12th June | 13th June- 20th June | N/A | June 2014 | Dec 2014 | COREN REGISTRAR | COREN PRESIDENT
[8 empty] | Actual | [7 empty] | Actual
Completion of Enugu Zonal Office, Enugu State | 3 | 1 | BEME | OCB | 23000000 | N/A | MTB | Plan | 28th Feb- 20th March | 21st March-27th March | N/A | 28th Mar- 9th May | 9th May | 12th May- 27th May | 28th May- 4th June | Plan | 23000000 | N/A | 5th June- 12th June | 13th June- 20th June | N/A | June 2014 | Dec 2014 | COREN REGISTRAR | COREN PRESIDENT
Actual
TOTAL COST |  |  |  |  | 129000000

## O.O.S Consultancy Services
Ministry/Department/Agency: OFFICE OF THE SECRETARY TO THE GOVERNMENT OF THE FEDERATION
Budget Year: 2014
|  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 1 weeks | 2 - 4 weeks | 2 weeks | 2 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
PRODUCTION OF COMPENDIUM OF LAWS /BILLS PASSED BY NATIONAL AND STATE ASSEMBLIES 1999 MAY TO 2012 AND PRODUCTION OF NIGERIA&#039;S FOREIGN POLICY UNDER CIVILIAN REGIME | Plan | 012 | 23 | Time-Based | 50000000 | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 - 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | 29/05/14 - 12/06/14 | 12/06/14 - 26/06/14 | 26/06/14 - 3/07/14 | 50000000 | NA | 3/07/14 - 17/07/14 | 17/07/14 - 31/07/14 | NA | 31/07/14 | 14/08/14 | 50000000 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
| Actual | [31 empty] | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
RESEARCH & CONSTITUTIONAL MATTERS | Plan | 013 | 24 | Time-Based | 50000000 | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | NA | POST REVIEW | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 - 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | 29/05/14 - 12/06/14 | 12/06/14 - 26/06/14 | 26/06/14 - 3/07/14 | 50000000 | NA | 3/07/14 - 17/07/14 | 17/07/14 - 31/07/14 | NA | 31/07/14 | 14/08/14 | 50000000 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
| Actual | [31 empty] | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
SETTLEMENT OF CONSULTANCY FEES FOR COMPLETION OF SHEHU SHAGARI COMPLEX | Plan | 015 | 26 | Lump Sum | 150000000 | NCB | BPP issues "No Objection" to award/FEC approves | CQ - Consultant&#039;s Qualification | NA | PRIOR REVIEW | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 - 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | 29/05/14 - 12/06/14 | 12/06/14 - 26/06/14 | 26/06/14 - 3/07/14 | 150000000 | NA | 3/07/14 - 17/07/14 | 17/07/14 - 31/07/14 | 31/07/14 - 14/08/14 | 14/08/14 | 28/08/14 | 150000000 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
| Actual | [31 empty] | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
Total Cost Plan |  |  |  |  | 250000000 | [19 empty] | 250000000 | [6 empty] | 250000000
Total Cost Actual

## O.O.S Goods
Ministry/Department/Agency: OFFICE OF THE SECRETARY TO THE GOVERNMENT OF THE FEDERATION
Budget Year: 2014
|  |  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Goods |  |  | Action Party | Champion
S/N | Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Arrival of Goods | Inspection/Final Acceptance | Name/Designation | Name/Designation
| Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
Plan vs Actual
1 | HP Scanners | Plan | 001 | 1 |  | 15000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID
Actual
2 | GOODS WORKS AND SERVICES | Plan | 001 | 1 | Bills of Quantity | 15000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 15000000 | NA | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | NA | 29/05/14 - 19/06/14 | 19/06/14 - 3/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
|  | Actual | [9 empty] | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
3 | UPS (BLUEGATE 1.5 KVA) 500 NOS | Plan | 001 | 2 | Bills of Quantity | 14350000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 14350000 | NA | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | NA | 29/05/14 - 19/06/14 | 19/06/14 - 3/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
|  | Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
4 | PROCUREMENT OF OFFICE EQUIPMENTS FOR ADDITIONAL OFFICES | Plan | 001 | 3 | Bills of Quantity | 283000000 | NCB | BPP issues "No Objection" to award/FEC approves | LERB - LOWEST EVALUATED RESPONSIVE BID | PRE-QUALIFICATION |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 283000000 | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | 29/05/14 - 12/06/14 | 12/06/14 - 26/06/14 | 26/06/14 - 10/07/14 | 10/07/14 - 24/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
|  | Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
5 | PROCUREMENT OF THERMOCOOL FRIDGE (150 N0) | Plan | 001 | 4 | Bills of Quantity | 12370000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 12370000 | NA | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | NA | 29/05/14 - 19/06/14 | 19/06/14 - 3/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
|  | Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
6 | PROCUREMENT OF C-WAYS WATER DISPENSER (100 NO) | Plan | 001 | 5 | Bills of Quantity | 4950000 | NS | Accounting Officer: Permanent Secretary | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 4950000 | NA | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | NA | 29/05/14 - 19/06/14 | 19/06/14 - 3/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
|  | Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
7 | PROCUREMENTOF HP LAPTOP COMPUTER (2.6 GH2 DUAL (CORE, 3200 GB HDD, 2GB ) 150 N0 | Plan | 001 | 6 | Bills of Quantity | 25800000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 25800000 | NA | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | NA | 29/05/14 - 19/06/14 | 19/06/14 - 3/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
|  | Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
8 | PROCUREMENT OF HP DESKTOP COMPUTER (150 NO) | Plan | 001 | 7 | Bills of Quantity | 27000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 27000000 | NA | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | 29/05/14 - 19/06/14 | 19/06/14 - 3/07/14 | 3/07/14 - 17/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
|  | Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
9 | PROCUREMENT OF HP LASERJET PRINTER 2053 (200 NO ) | Plan | 001 | 8 | Bills of Quantity | 16500000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 16500000 | NA | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | NA | 29/05/14 - 19/06/14 | 19/06/14 - 3/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
|  | Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
10 | PROCUREMENT OF PHOTOCOPYING MACHINES (50 NO ) | Plan | 001 | 9 | Bills of Quantity | 35000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 35000000 | NA | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | NA | 29/05/14 - 19/06/14 | 19/06/14 - 3/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
|  | Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
11 | PROCUREMENT OF SHREDDING MACHINES (SANYO 650 )300 NO | Plan | 001 | 10 | Bills of Quantity | 5625000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 5625000 | NA | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | NA | 29/05/14 - 19/06/14 | 19/06/14 - 3/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
|  | Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
12 | PROCUREMENT OF LIBRARY BOOKS & EQUIPMENT FOR SPECIALISED LIBRARIES IN OSGF | Plan | 002 | 11 | Bills of Quantity | 150000000 | NCB | BPP issues "No Objection" to award/FEC approves | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 150000000 | 1/05/14 - 7/05/14 | 7/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | 29/05/14 - 5/06/14 | 5/06/14 - 19/06/14 | 19/06/14 - 3/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
|  | Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
13 | PROCUREMENT OF GYMNASIUM EQUIPMENT (BICYCLE, EGO TREAD MILL SET OF WEIGHTS) | Plan | 003 | 12 | Bills of Quantity | 50073420 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 50073420 | NA | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | NA | 29/05/14 - 19/06/14 | 19/06/14 - 3/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
|  | Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
14 | PROCUREMENT OF SECURITY ITEMS (SUPPLY AND INSTALLATION OF UNDER VEHICLE INSPECTION SYSTEM, BOLLARDS, HAND-HELD SCANNERS | Plan | 004 | 13 | Bills of Quantity | 1161356582 | NCB | BPP issues "No Objection" to award/FEC approves | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | NA | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 1161356582 | 1/05/14 - 8/05/14 | 8/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | 29/05/14 - 5/06/14 | 5/06/14 - 19/06/14 | 19/06/14 - 26/06/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
|  | Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
15 | PROCUREMENT OF MOTORCYCLES FOR DISPATCH (6 No.) | Plan | 005 | 14 | Bills of Quantity | 900000 | NS | Accounting Officer: Permanent Secretary | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 900000 | NA | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | NA | 29/05/14 - 19/06/14 | 19/06/14 - 3/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
|  | Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
16 | PROCUREMENT OF POOL VEHICLES FOR USE OF ELDER STATE MEN WHEN IN ABUJA OFFICIAL (COASTER | Plan | 006 | 15 | Bills of Quantity | 70000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 70000000 | NA | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | NA | 29/05/14 - 19/06/14 | 19/06/14 - 3/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
|  | Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
17 | PROCUREMENT OF COASTER BUSES (6 NO ) | Plan | 006 | 16 | Bills of Quantity | 78000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 13/03/14 | 13/03/14 - 27/03/14 | 27/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 78000000 | NA | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | NA | 29/05/14 - 19/06/14 | 19/06/14 - 3/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
|  | Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
18 | PROCUREMENT OF TOYOTA BUSES ( HIGH ROOF ) FOR CABINET MEETINGS DISTRIBUTION & DISPATCHING | Plan | 006 | 17 | Bills of Quantity | 36000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID |  |  | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 | 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 36000000 | NA | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | NA | 29/05/14 - 19/06/14 | 19/06/14 - 3/07/14 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
|  | Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
| Total Cost Plan |  |  |  |  | 2000925002 | [14 empty] | 1985925002
Total Cost Actual

## O.O.S Non-Consultancy Services
Ministry/Department/Agency: OFFICE OF THE SECRETARY TO THE GOVERNMENT OF THE FEDERATION
Budget Year: 2014
|  |  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
S/N | Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/Designation | Name/Designation
| Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 1 weeks | 2 - 4 weeks | 2 weeks | 2 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
1 | Democracy Day and Independence Celeberations | Plan | 016 | 27 | Lump Sum | 250000000 | NCB | BPP issues "No Objection" to award/FEC approves | QCBS - Quality and Cost Based Selection | PRE-QUALIFICATION | PRIOR REVIEW | 9/01/14 - 30/01/14 | 30/01/14 - 13/02/14 | 13/02/14 - 27/02/14 | 27/02/14 - 6/03/14 | 6/03/14 | 6/03/14 - 20/03/14 | 20/03/14 - 3/04/14 | 3/04/14 - 17/04/14 | 17/04/14 - 1/05/14 | 1/05/14 - 15/05/14 | 15/05/14 - 29/05/14 | 29/05/14 - 12/06/14 | 12/06/14 - 26/06/14 | 26/06/14 - 3/07/14 | 250000000 | 3/07/14 - 17/07/14 | 17/07/14 - 31/07/14 | 31/07/14 - 14/08/14 | 14/08/14 - 28/08/14 | 9/09/14 | 23/09/14 | 250000000 | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
|  | Actual | [31 empty] | FUNKE ONIPEDE - [Designation: Chief Procurement Officer] | IBRAHIM BADEIRI - [Designation: DD Procurement]
| Total Cost Plan |  |  |  |  | 250000000 | [19 empty] | 250000000 | [6 empty] | 250000000
Total Cost Actual

## A.R.M.I Consultancy Services
Ministry/Department/Agency: Agricultural & Rural Management Training Institute (ARMTI)
Budget Year: 2014
|  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 1 weeks | 2 - 4 weeks | 2 weeks | 2 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
UPGRADING OF ABUJA REGIONAL TRAINING CENTRE-SUPERVISION & CONSTRUCTION(ON-GOING) | Plan | ARMTI/2012/02 | 2 |  | 3000000 |  | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 3000000 | NA | 2/05/12 - 16/05/12 | 22/05/12 - 25/05/12 | NA | 6/10/14 | 20/10/14 | 3000000 | Owolabi Olajide - [Designation: Chief Proc. Officer] | John Iyilade - [Designation: CE (Works)]
Actual
YOUTH & WOMEN EMPOWERMENT SCHEME (ADAVI, KOGI STATE) (ON-GOING) | Plan | ARMTI/2012/13 | 13 |  | 5687177 | NCB | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 5867177 | NA | NA | NA | NA | 6/10/14 | 20/10/14 | 5687177 | Owolabi Olajide - [Designation: Chief Proc. Officer] | Anthony Njoku - [Designation: Director]
Actual
RESEARCH & CURRICULUM DEV(IMPACT ASSESSMENT EVALUATION OF ARMTI (ON-GOING) | Plan | ARMTI/2012/12 | 12 |  | 7838145 | NCB | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 7838145 | NA | NA | NA | NA | NA | NA | 7838145 | Owolabi Olajide - [Designation: Chief Proc. Officer] | Anthony Njoku - [Designation: Director]
Actual
YOUTH & WOMEN EMPOWERMENT SCHEME, EHUDA, RIVERS STATE (ON-GOING) | Plan | ARMTI/2012/15 | 15 |  | 5687178 | NCB |  | CQ - Consultant&#039;s Qualification | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 5687178 | NA | NA | NA | NA | 6/10/14 | 20/10/14 | 5687178 | Owolabi Olajide - [Designation: Chief Proc. Officer] | Anthony Njoku - [Designation: Director]
Actual
Total Cost Plan |  |  |  |  | 22212500 | [19 empty] | 22392500 | [6 empty] | 22212500
Total Cost Actual

## A.R.M.INon-Consultancy Services
Ministry/Department/Agency: Agricultural & Rural Management Training Institute (ARMTI)
Budget Year: 2014
|  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 1 weeks | 2 - 4 weeks | 2 weeks | 2 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
TRAINING EXTENSION FOR YOUTH,WOMEN,FARMERS & CHANGING AGENTS & OFF CAMPUS TRAINING {ON-GOING) | Plan | ARMTI/2013/07 | 7 |  | 50000000 |  | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 50000000 | NA | NA | NA | NA | 6/10/14 | 20/10/14 | 50000000 | Owolabi Olajide - [Designation: Chief Proc. Officer] | Anthony Njoku - [Designation: Director]
Actual
VILLAGE ALIVE DEVELOPMENT INITIATIVE (ON-GOING) | Plan | ARMTI/2012/08 | 8 |  | 10000000 |  | Parastatals Tenders Board | LC - Least Cost | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 10000000 | NA | NA | NA | NA | NA | NA | 10000000 | Owolabi Olajide - [Designation: Chief Proc. Officer] | Anthony Njoku - [Designation: Director]
Actual
MAMAGEMENT CAPACITY DEVELOPMENT FOR AGRICULTURAL TRANSFORMATION AGENDA (ON-GOING) | Plan | ARMTI/2013/09 | 9 |  | 30000000 |  | Parastatals Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 30000000 | NA | NA | NA | NA | 6/10/14 | 20/10/14 | 30000000 | Owolabi Olajide - [Designation: Chief Proc. Officer] | Anthony Njoku - [Designation: Director]
Actual
NATIONAL TRAINING OF TRAINERS (ON-GOING) | Plan | ARMTI/2013/10 | 10 |  | 10000000 |  | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 10000000 | NA | NA | NA | NA | 6/10/14 | 20/10/14 | 10000000 | Owolabi Olajide - [Designation: Chief Proc. Officer] | Anthony Njoku - [Designation: Director]
Actual
YOUTH EMPOWERMENT SKILL FOR AGRIC BUSINESS (ON-GOING) | Plan | ARMTI/2013/11 | 11 |  | 20000000 |  | Parastatals Tenders Board | LC - Least Cost | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 20000000 | NA | NA | NA | NA | 6/10/14 | 20/10/14 | 20000000 | Owolabi Olajide - [Designation: Chief Proc. Officer] | Anthony Njoku - [Designation: Director]
Actual
TRAINING OF YOUTH & WOMEN/PROCUREMENT OF CASSAVA PROCESSING MACHINE (ON-GOING) | Plan | ARMTI/2013/14 | 14 |  | 20000000 |  | Parastatals Tenders Board | CQ - Consultant&#039;s Qualification | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 20000000 | NA | NA | NA | NA | 6/10/14 | 20/10/14 | 20000000 | Owolabi Olajide - [Designation: Chief Proc. Officer] | Anthony Njoku - [Designation: Director]
Actual
Total Cost Plan |  |  |  |  | 140000000 | [19 empty] | 140000000 | [6 empty] | 140000000
Total Cost Actual

## A.R.M.T.I Works
Ministry/Department/Agency: Agricultural & Rural Management Training Institute (ARMTI)
Budget Year: 2014
|  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Works |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Plan vs Actual
UPGRADING OF ABUJA REGIONAL TRAINING CENTRE (ON-GOING) | Plan | ARMTI/2012/01 | 1 |  | 51700000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 51700000 | NA | 22/11/12 - 27/11/12 | 10/12/12 - 10/12/12 | 25/08/14 - 12/09/14 | 24/10/14 | 14/11/14 | 51700000 | Owolabi Olajide - [Designation: Chief Proc. Officer] | John Iyilade - [Designation: CE (Works)]
Actual
CONSTRUCTION OF OFFICE AND HOSTELS (NEW) | Plan | ARMTI/2014/03 | 3 |  | 4162713 | NCB | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 24/02/14 - 17/03/14 | 17/03/14 - 31/03/14 | 31/03/14 - 28/04/14 | NA | NA | 28/04/14 - 28/04/14 | 28/04/14 - 28/04/14 | NA | NA | 12/05/14 - 16/05/14 | 19/05/14 - 30/05/14 | 4162713 | NA | 4/08/14 - 18/08/14 | 18/08/14 - 22/08/14 | 25/08/14 - 12/09/14 | 24/10/14 | 31/10/14 | 4162713 | Owolabi Olajide - [Designation: Chief Proc. Officer] | John Iyilade - [Designation: CE (Works)]
Actual
REHABILITATION OF CAMPUS BUILDINGS (NEW) | Plan | ARMTI/2014/04 | 4 |  | 5000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 24/02/14 - 17/03/14 | 17/03/14 - 31/03/14 | 31/03/14 - 28/04/14 | NA | NA | 28/04/14 - 28/04/14 | 28/04/14 - 28/04/14 | NA | NA | 12/05/14 - 16/05/14 | 19/05/14 - 30/05/14 | 5000000 | NA | 4/08/14 - 18/08/14 | 18/08/14 - 22/08/14 | 25/08/14 - 12/09/14 | 24/10/14 | 14/11/14 | 5000000 | Owolabi Olajide - [Designation: Chief Proc. Officer] | John Iyilade - [Designation: CE (Works)]
Actual
INDUSTRIAL BOREHOLE AND RETICULATION (NEW) | Plan | ARMTI/2014/05 | 5 |  | 25000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 24/02/14 - 17/03/14 | 17/03/14 - 31/03/14 | 31/03/14 - 28/04/14 | NA | NA | 28/04/14 - 28/04/14 | 28/04/14 - 28/04/14 | NA | NA | 12/05/14 - 16/05/14 | 19/05/14 - 30/05/14 | 25000000 | NA | 4/08/14 - 18/08/14 | 18/08/14 - 22/08/14 | 25/08/14 - 12/09/14 | 24/10/14 | 14/11/14 | 25000000 | Owolabi Olajide - [Designation: Chief Proc. Officer] | John Iyilade - [Designation: CE (Works)]
Actual
CONSTRUCTION AND PROVISION OF ROADS/DRAINAGES (NEW) | Plan | ARMTI/2014/06 | 6 |  | 2000000 | NS | Accounting Officer: Director General/CEO | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 24/02/14 - 17/03/14 | 17/03/14 - 31/03/14 | 31/03/14 - 28/04/14 | NA | NA | 28/04/14 - 28/04/14 | 28/04/14 - 28/04/14 | NA | NA | 12/05/14 - 16/05/14 | 19/05/14 - 30/05/14 | 2000000 | NA | 4/08/14 - 18/08/14 | 18/08/14 - 22/08/14 | 25/08/14 - 12/09/14 | 24/10/14 | 14/11/14 | 2000000 | Owolabi Olajide - [Designation: Chief Proc. Officer] | John Iyilade - [Designation: CE (Works)]
Actual
Total Cost Plan |  |  |  |  | 87862713 | [16 empty] | 87862713 | [6 empty] | 87862713
Total Cost Actual

## M.C.T Consultancy Services
Ministry/Department/Agency: Main Ministry
Budget Year: 2014
|  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 weeks | 1 weeks | 2 - 4 weeks | 2 weeks | 2 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
OUTSOURCING CONTRACT FOR GOVERNMENT CONTACT CENTRE ABUJA | Plan | FMCT/PROC/GCC/14/1 | 7 |  | 100000000 | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | NA | PRIOR REVIEW | 6/02/14 - 20/02/14 | 20/02/14 - 28/02/14 | 28/02/14 - 14/03/14 | NA | 14/04/14 | 14/04/14 - 28/04/14 | 29/04/14 - 13/05/14 | 3/06/14 - 3/06/14 | 3/06/14 - 17/06/14 | 17/06/14 - 23/06/14 | 24/06/14 - 24/06/14 | 24/06/14 - 30/06/14 | 3/07/14 - 4/07/14 | 7/07/14 - 11/07/14 | 95000000 | NA | 15/07/14 - 18/07/14 | 18/07/14 - 21/07/14 | 21/07/14 - 31/07/14 | 29/08/14 | 30/09/14 | 95000000 | Jibril Mohammed - [Designation: Chief Proc. Officer] | Ogochuku Ufoegbune - [Designation: DD Procurement]
Actual
E-GOVERNMENT IMPLEMENTATION (DIGITIZATION OF GOVERNMENT DATA AND SWITCH TO .gov.ng) | Plan | FMCT/E-GOV/14/002 | 8 | Lump Sum | 95000000 | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 6/02/14 - 20/02/14 | 20/02/14 - 28/02/14 | 28/02/14 - 14/03/14 | NA | 14/04/14 | 14/04/14 - 28/04/14 | 29/04/14 - 13/05/14 | 3/06/14 - 3/06/14 | 3/06/14 - 17/06/14 | 17/06/14 - 23/06/14 | 24/06/14 - 24/06/14 | 24/06/14 - 30/06/14 | 3/07/14 - 4/07/14 | 7/07/14 - 11/07/14 | 95000000 | NA | 15/07/14 - 18/07/14 | 18/07/14 - 21/07/14 | 21/07/14 - 31/07/14 | 29/08/14 | 30/09/14 | 95000000 | Jibril Mohammed - [Designation: Chief Proc. Officer] | Ogochuku Ufoegbune - [Designation: DD Procurement]
Actual
DEPLOYMENT OF ICT TOOLS FOR ICT PROFESSIONAL CADRE | Plan | FMCT/E-GOV/14/003 | 9 | Lump Sum | 95000000 | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 6/02/14 - 20/02/14 | 20/02/14 - 28/02/14 | 28/02/14 - 14/03/14 | NA | 14/04/14 | 14/04/14 - 28/04/14 | 29/04/14 - 13/05/14 | 3/06/14 - 3/06/14 | 3/06/14 - 17/06/14 | 17/06/14 - 23/06/14 | 24/06/14 - 24/06/14 | 24/06/14 - 30/06/14 | 3/07/14 - 4/07/14 | 7/07/14 - 11/07/14 | 95000000 | NA | 15/07/14 - 18/07/14 | 18/07/14 - 21/07/14 | 21/07/14 - 31/07/14 | 29/08/14 | 30/09/14 | 95000000 | Jibril Mohammed - [Designation: Chief Proc. Officer] | Ogochuku Ufoegbune - [Designation: DD Procurement]
Actual
ESTABLISHMENT OF INTEGRATED DOCUMENT MANAGEMENT INFORMATION SYSTEM | Plan | FMCT/E-GOV/14/004 | 9 | Lump Sum | 40000000 | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 6/02/14 - 20/02/14 | 20/02/14 - 28/02/14 | 28/02/14 - 14/03/14 | NA | 14/04/14 | 14/04/14 - 28/04/14 | 29/04/14 - 13/05/14 | 3/06/14 - 3/06/14 | 3/06/14 - 17/06/14 | 17/06/14 - 23/06/14 | 24/06/14 - 24/06/14 | 24/06/14 - 30/06/14 | 3/07/14 - 4/07/14 | 7/07/14 - 11/07/14 | 95000000 | NA | 15/07/14 - 18/07/14 | 18/07/14 - 21/07/14 | 21/07/14 - 31/07/14 | 29/08/14 | 30/09/14 | 95000000 | Jibril Mohammed - [Designation: Chief Proc. Officer] | Ogochuku Ufoegbune - [Designation: DD Procurement]
Actual
EXTENSION OF GOVERNMENT SERVICES PORTAL | Plan | FMCT/E-GOV/14/05 | 10 | Lump Sum | 95000000 | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 6/02/14 - 20/02/14 | 20/02/14 - 28/02/14 | 28/02/14 - 14/03/14 | NA | 14/04/14 | 14/04/14 - 28/04/14 | 29/04/14 - 13/05/14 | 3/06/14 - 3/06/14 | 3/06/14 - 17/06/14 | 17/06/14 - 23/06/14 | 24/06/14 - 24/06/14 | 24/06/14 - 30/06/14 | 3/07/14 - 4/07/14 | 7/07/14 - 11/07/14 | 150000000 | 14/07/14 - 28/07/14 | 31/07/14 - 31/07/14 | 4/08/14 - 8/08/14 | 21/08/14 - 29/08/14 | 30/09/14 | 15/10/14 | 150000000 | Jibril Mohammed - [Designation: Chief Proc. Officer] | Ogochuku Ufoegbune - [Designation: DD Procurement]
Actual
IMPLEMENTATION OF NATIONAL BROADBAND STRATEGY AND ROADMAP | Plan | 006 | 14 | Lump Sum | 180000000 | NCB | BPP issues "No Objection" to award/FEC approves | QCBS - Quality and Cost Based Selection | NA | PRIOR REVIEW | 17/02/14 - 3/03/14 | 17/03/14 - 21/03/14 | 24/03/14 - 4/04/14 | 4/04/14 - 11/04/14 | 24/04/14 | 30/04/14 - 14/05/14 | 14/05/14 - 27/05/14 | 27/05/14 - 27/05/14 | 27/05/14 - 10/06/14 | 10/06/14 - 16/06/14 | 16/06/14 - 23/06/14 | 30/06/14 - 4/07/14 | 14/07/14 - 21/07/14 | 25/07/14 - 8/08/14 | 150000000 | 13/08/14 - 20/08/14 | 25/08/14 - 29/08/14 | 29/08/14 - 29/08/14 | 9/09/14 - 16/09/14 | 17/10/14 | 24/10/14 | 150000000 | Jibril Mohammed - [Designation: Chief Proc. Officer] | Ogochuku Ufoegbune - [Designation: DD Procurement]
Actual
NIGERIA-NIGER JOINT COMMISSION(NNJC):DIGITIZATION OF MARADI (NIGER) TO KATSINA (NIGERIA) MICROWAVE TRANSMISSION LINK. | Plan | 006 | 15 | Lump Sum | 97143787 | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 17/02/14 - 28/02/14 | 28/02/14 - 7/03/14 | 7/03/14 - 21/03/14 | 21/03/14 - 28/03/14 | 24/04/14 | 30/04/14 - 14/05/14 | 14/05/14 - 27/05/14 | 27/05/14 - 27/05/14 | 27/05/14 - 10/06/14 | 10/06/14 - 16/06/14 | 23/06/14 - 23/06/14 | 30/06/14 - 4/07/14 | 14/07/14 - 21/07/14 | 25/07/14 - 8/08/14 | 85000000 | 13/08/14 - 20/08/14 | 25/08/14 - 25/08/14 | 25/08/14 - 29/08/14 | 9/09/14 - 16/09/14 | 20/10/14 | 27/10/14 | 85000000 | Jibril Mohammed - [Designation: Chief Proc. Officer] | Ogochuku Ufoegbune - [Designation: DD Procurement]
Actual
TERRESTERIAL BROADBAND BACKBONE: ABUJA (NIGERIA), ZINDAR (NIGER), ALGIERS (ALGERIS). | Plan | 006 | 16 | Lump Sum | 76170453 | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 17/02/14 - 21/02/14 | 21/02/14 - 28/02/14 | 7/03/14 - 21/03/14 | 21/04/14 - 24/04/14 | 24/04/14 | 30/04/14 - 14/05/14 | 14/05/14 - 27/05/14 | 27/05/14 - 27/05/14 | 27/05/14 - 10/06/14 | 10/06/14 - 16/06/14 | 23/06/14 - 23/06/14 | 30/06/14 - 4/07/14 | 14/07/14 - 21/07/14 | NA | 84000000 | NA | 28/07/14 - 31/07/14 | 31/07/14 - 4/08/14 | 4/08/14 - 15/08/14 | 20/10/14 | 24/10/14 | 84000000 | Jibril Mohammed - [Designation: Chief Proc. Officer] | Ogochuku Ufoegbune - [Designation: DD Procurement]
Actual
CREATION OF DATA BASE MANAGEMENT SYSTEM AND INSTALLATION OF ITU DEVELOPED SPECTRUM MANAGEMENT TOOLS | Plan | 006 | 16 | Lump Sum | 50000000 | NCB | Ministerial Tenders Board | QCBS - Quality and Cost Based Selection | POST-QUALIFICATION | POST REVIEW | 17/02/14 - 24/02/14 | 24/02/14 - 28/02/14 | 7/03/14 - 21/03/14 | 21/04/14 - 24/04/14 | 24/04/14 | 30/04/14 - 14/05/14 | 14/05/14 - 27/05/14 | 27/05/14 - 27/05/14 | 27/05/14 - 10/06/14 | 10/06/14 - 16/06/14 | 23/06/14 - 23/06/14 | 30/06/14 - 4/07/14 | 14/07/14 - 21/07/14 | NA | 48000000 | NA | 25/07/14 - 31/07/14 | 31/07/14 - 1/08/14 | 11/08/14 - 25/08/14 | 25/08/14 | 8/09/14 | 48000000 | Jibril Mohammed - [Designation: Chief Proc. Officer] | Ogochuku Ufoegbune - [Designation: DD Procurement]
Actual
Total Cost Plan |  |  |  |  | 828314240 | [19 empty] | 897000000 | [6 empty] | 897000000
Total Cost Actual

## M.C.T Works
Ministry/Department/Agency: Main Ministry
Budget Year: 2014
|  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Works |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Plan vs Actual
Outsourcing Contract for Government Contact Centre, Abuja | Plan | FMCT/PROC/GCC/14/1 | 1 | Bills of Quantity | 100000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/01/14 - 16/01/14 | 16/01/14 - 17/01/14 | NA | NA | NA | NA | NA | 14/02/14 | 28/03/14 | 14/04/14 - 18/04/14 | 21/04/14 - 22/04/14 | 100000000 | NA | 30/04/14 - 1/05/14 | 5/05/14 - 9/05/14 | 16/05/14 - 23/05/14 | 3/07/14 | 26/09/14 | 100000000 | Jibril Mohammed - [Designation: Chief Proc. Officer] | Ogochuku Ufoegbune - [Designation: DD Procurement]
Actual
ESTABLISHEMENT OF CITIZENS INFORMATION CENTER AND PORTAL ENUGU | Plan | FMCT001 | 1 |  | 285000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/01/14 - 16/01/14 | 16/01/14 - 23/01/14 | NA | NA | 23/01/14 - 20/02/14 | NA | NA | NA | NA | NA | 20/03/14 - 4/04/14 | 250000000 | NA | 14/04/14 - 28/04/14 | 2/05/14 - 5/05/14 | 19/05/14 - 26/05/14 | 30/07/14 | 29/08/14 | 250000000 | Jibril Mohammed - [Designation: Chief Proc. Officer] | Ogochuku Ufoegbune - [Designation: DD Procurement]
Actual
ESTABLISHMENT OF CITIZENS INFORMATION CENTER AND PORTAL LAGOS | Plan | FMCT002 | 2 |  | 185000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 2/01/14 - 16/01/14 | 16/01/14 - 23/01/14 | NA | NA | 23/01/14 - 20/02/14 | NA | NA | NA | NA | NA | 20/02/14 - 21/02/14 | 150000000 | NA | 14/04/14 - 28/04/14 | 2/05/14 - 5/05/14 | 19/05/14 - 26/05/14 | 30/07/14 | 29/08/14 | 150000000 | Jibril Mohammed - [Designation: Chief Proc. Officer] | Ogochuku Ufoegbune - [Designation: DD Procurement]
Actual
REHABILITATION OF COMMUNITY CENTER AT AZARE | Plan | 004 | 4 |  | 15250000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW
Actual
REHABILITATION OF COMMUNITY CENTER AZARE | Plan | 004 | 4 | Bills of Quantity | 15250000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 5/02/14 - 19/02/14 | 19/02/14 - 27/02/14 | 27/02/14 - 13/03/14 | NA | 13/03/14 - 20/03/14 | NA | NA | 20/03/14 | 30/04/14 | 14/05/14 - 15/05/14 | 15/05/14 - 5/06/14 | 13000000 | NA | 30/06/14 - 30/06/14 | 30/06/14 - 4/07/14 | 4/07/14 - 25/07/14 | 30/09/14 | 10/10/14 | 13000000 | Jibril Mohammed - [Designation: Chief Proc. Officer] | Ogochuku Ufoegbune - [Designation: DD Procurement]
Actual
REHABILITATION OF COMMUNITY CENTER GUSAU | Plan | 004 | 5 | Bills of Quantity | 15250000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 5/02/14 - 19/02/14 | 19/02/14 - 27/02/14 | 27/02/14 - 13/03/14 | NA | 13/03/14 - 20/03/14 | NA | NA | 20/03/14 | 30/04/14 | 14/05/14 - 15/05/14 | 15/05/14 - 30/05/14 | 13500000 | NA | 30/06/14 - 30/06/14 | 30/06/14 - 4/07/14 |  | 30/09/14 | 3/10/14 | 13500000 | Jibril Mohammed - [Designation: Chief Proc. Officer] | Ogochuku Ufoegbune - [Designation: DD Procurement]
Actual
REHABILITATION OF COMMUNITY CENTER IPAJA | Plan | 004 | 6 | Bills of Quantity | 15250000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 5/02/14 - 19/02/14 | 19/02/14 - 27/02/14 | 27/02/14 - 13/03/14 | NA | 13/03/14 - 20/03/14 | NA | NA | 20/03/14 | 30/04/14 | 14/05/14 - 15/05/14 | 15/05/14 - 30/05/14 | 13500000 | NA | 30/06/14 - 30/06/14 | 30/06/14 - 4/07/14 | 4/07/14 - 17/07/14 | 30/09/14 | 10/10/14 | 13500000 | Jibril Mohammed - [Designation: Chief Proc. Officer] | Ogochuku Ufoegbune - [Designation: DD Procurement]
Actual
REHABILITATION OF WUSE II ANNEX OFFICE ABUJA | Plan | FMCT/SM/14/01 | 10 | Bills of Quantity | 40000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 6/02/14 - 19/02/14 | 19/02/14 - 27/02/14 | 27/02/14 - 13/03/14 | NA | 13/03/14 - 20/03/14 | NA | NA | 20/03/14 | 30/04/14 | 14/05/14 - 15/05/14 | 15/05/14 - 30/05/14 | 36000000 | NA | 30/06/14 - 30/06/14 | 30/06/14 - 4/07/14 | 4/07/14 - 14/07/14 | 15/08/14 | 20/08/14 | 36000000 | Jibril Mohammed - [Designation: Chief Proc. Officer] | Ogochuku Ufoegbune - [Designation: DD Procurement]
Actual
E-GOVERNMENT IMPLEMENTATION AND INSTALLATION (DIGITIZATION OF GOVERNMENT DATA AND SWITCH TO .gov.ng) | Plan | FMCT/E-GOV/14/004 | 11 | Bills of Quantity | 180000000 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 6/02/14 - 19/02/14 | 19/02/14 - 27/02/14 | 27/02/14 - 13/03/14 | NA | 14/04/14 - 21/04/14 | NA | NA | 21/04/14 | 30/05/14 | 16/06/14 - 30/06/14 | 30/06/14 - 4/07/14 | 180000000 | NA | 7/07/14 - 11/07/14 | 11/07/14 - 14/07/14 | 14/07/14 - 25/07/14 | 15/08/14 | 29/08/14 | 180000000 | Jibril Mohammed - [Designation: Chief Proc. Officer] | Ogochuku Ufoegbune - [Designation: DD Procurement]
Actual
CONSTRUCTION OF 1 No COMMUNITY CENTRE AT IRMS OGOJA | Plan | 006 | 17 | Bills of Quantity | 82340907 | NCB | Ministerial Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 17/02/14 - 24/02/14 | 24/02/14 - 28/02/14 | NA | NA | NA | NA | NA | NA | NA | NA | NA | 82000000 | NA | NA | NA | NA | 30/06/14 | 15/07/14 | 82000000 | Jibril Mohammed - [Designation: Chief Proc. Officer] | Ogochuku Ufoegbune - [Designation: DD Procurement]
Actual
Total Cost Plan |  |  |  |  | 933340907 | [16 empty] | 838000000 | [6 empty] | 838000000
Total Cost Actual

## H.R.M Goods
Ministry/Department/Agency:
Budgetary Year: | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
date
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  | 0 | 0 |  |  |  | Plan | [7 empty] | Plan | 0
|  | 0 | 0 |  |  |  | Actual | [7 empty] | Actual | 0
Fill gray cells only!

## H.R.M Works
Ministry/Department/Agency:
Budgetary Year: | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 0 |  |  | Plan | [7 empty] | Plan | 0 | [6 empty] | 0
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## H.R.M Consultants
Ministry/Department/Agency: Human Resources Management
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: D.B. Sule |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Prior/Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
Human Capital Development for Staff | NCB | Lumpsum | 80900000 | Post | Plan | 3/2 - 25/2/14 | 26/2 - 3/3/14 | NA | NA | NA | NA | Plan | 4/3 - 2014 - | - 1/4/2014 | 2/4 - 21/4/2014 | 22/4 - 28/4/2014 | 29/4 - 9/5/2014 | 12/5 - 26/5/2014 | 27/5 - 2/6/2014 | Plan | 3/6 - 16/6/2014 | 17/6 - 23/6/2014 | 80900000 | 24/6 - 30/6/2014 | NA | 1/7 - 7/7/2014 | Plan | 12,135,000.00 | 15/9/2014 | 29/11/2014 | 80,900,000.00
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 80900000 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 80900000 |  |  |  | Plan |  |  |  | 80900000
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!

## F.M.I PROCUREMENT Goods
Ministry/Department/Agency:
Budgetary Year: | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
date
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  | 0 | 0 |  |  |  | Plan | [7 empty] | Plan | 0
|  | 0 | 0 |  |  |  | Actual | [7 empty] | Actual | 0
Fill gray cells only!

## F.M.I PROCUREMENT Works
Ministry/Department/Agency: Procurement Department
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: R.O. Omoniyi |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Digitization of Procurement Department using Hardware and Software Application | FMI/PROC/I | LOT 1 | Bill of Quantity | NCB | 3000000 | Pre-or Post Qualification | Post Review | Plan | 3/2 - 25/2/2014 | NA | 4/3/2014 - | 4/3/2014 - | - 14/4/2014 | 15/4 - 5/5/2014 | 6/5 - 13/5/2014 | Plan | 3000000 | NA | 14/5 - 23/5/2014 | 26/5 - 9/6/14 | NA | 31/10/2014 | 29/11/2014 | 3,000,000.00
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 3000000 |  |  | Plan | [7 empty] | Plan | 3000000 | [6 empty] | 3000000
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## F.M.I PROCUREMENT Consultants
Ministry/Department/Agency:
Budgetary Year: |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Prior/Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 0 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 0 |  |  |  | Plan |  |  |  | 0
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!

## F.M.I P.R Goods
Ministry/Department/Agency:
Budgetary Year: | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
date
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  | 0 | 0 |  |  |  | Plan | [7 empty] | Plan | 0
|  | 0 | 0 |  |  |  | Actual | [7 empty] | Actual | 0
Fill gray cells only!

## F.M.I P.R Works
Ministry/Department/Agency:
Budgetary Year: | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 0 |  |  | Plan | [7 empty] | Plan | 0 | [6 empty] | 0
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## F.M.I P.R Consultants
Ministry/Department/Agency: PR & P Department
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: Peter Dama |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Prior/Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
Promotion of Made-in-Nigeria Products & Related Activities | NCB | Lumpsum | N10m | Post | Plan | 3/2 - 25/2/14 | 26/2 /3/3/14 | NA | NA | NA | NA | Plan | 4/3/2014 - | - 1/4/2014 | 2/4 - 21/4/2014 | 22/4 - 28/4/2014 | 29/4 - 9/5/2014 | 12/5 - 26/5/2014 | 27/5 - 2/6/2014 | Plan | 3/6 - 16/6/2014 | 17/6 - 23/6/2014 | N10m | 24/6 - 30/6/2014 | NA | 1/7 - 7/7/2014 | Plan | 1,500,000.00 | 15/9/2014 | 29/11/2014 | 10,000,000.00
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Nationwide Media Tour of Federal Government Projects and Hosting of Town Hall Meetings | NCB | Lumpsum | N241m | Post | Plan | 3/2 - 25/2/14 | 26/2 /3/3/14 | NA | NA | NA | NA | Plan | 4/3/2014 - | - 1/4/2014 | 2/4 - 21/4/2014 | 22/4 - 28/4/2014 | 29/4 - 9/5/2014 | 12/5 - 26/5/2014 | 27/5 - 2/6/2014 | Plan | 3/6 - 16/6/2014 | 17/6 - 23/6/2014 | N241m | 24/6 - 30/6/2014 | NA | 1/7 - 7/7/2014 | Plan | 36,150,000.00 | 15/9/2014 | 29/11/2014 | 241,000,000.00
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | #VALUE! |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | #VALUE! |  |  |  | Plan |  |  |  | 251000000
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!

## F.M.I I.T Goods
Ministry/Department/Agency:
Budgetary Year: | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
date
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  | 0 | 0 |  |  |  | Plan | [7 empty] | Plan | 0
|  | 0 | 0 |  |  |  | Actual | [7 empty] | Actual | 0
Fill gray cells only!

## F.M.I I.T Works
Ministry/Department/Agency: Information Technology Department
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: A.O.M |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
LAN/INTERNET/IPPIS MANAGEMENT WITH AUTOMATION OF THE MINISTRY'S WORK PROCESS | FMI/IT/I | LOT 2 | BQ | SHOOPING | 2000000 | Pre-or Post Qualification | Post Review | Plan | 3/2 - 25/2/2014 | 26/2 - 3/3/2014 | 4/3/2014 - | 4/3/2014 - | - 14/4/2014 | 15/4 - 5/52014 | NA | Plan | 2000000 | NA | 14/5 - 23/5/2014 | 26/5 - 9/6/14 | - | 4/11/2013 | 29/11/2014 | 2,000,000.00
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 2000000 |  |  | Plan | [7 empty] | Plan | 2000000 | [6 empty] | 2000000
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## F.M.I I.T Consultants
Ministry/Department/Agency: Information Technology Department
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: A.O.M |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Prior/Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
Hosting and Management of the National Web Portal www.nigeria.gov.ng including purchase of relevant devices for remote content Management | NCB | Lumpsum | 7000000 |  | Plan | 3/2 - 25/2/14 | 26/2 - 3/3/14 | NA | NA | NA | NA | Plan | 4/3/2014 - | - 1/4/2014 | 2/4 - 21/4/2014 | 22/4 - 28/4/2014 | 29/4 9/5/2014 | 12/5 - 26/5/2014 | 27/5 - 2/6/2014 | Plan | 3/6 - 16/6/2014 | 17/6 - 23/6/2014 | 7000000 | 24/6 - 30/6/2014 | NA | 1/7 - 7/7/2014 | Plan | - | 15/9/2014 | 29/11/2014 | 7,000,000.00
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
LAN/INTERNET/IPPIS MANAGEMENT AND VIDEO CONFERENCING, MANAGEMENT AND INTEGRATION OF SOCIAL MEDIA PALTFORM COLLABORAION INCLUDING SECURED WAN WITH VPN OPTIMIZATION | NCB | Lumpsum | 7000000 |  | Plan | 3/2 - 25/2/14 | 26/2 - 3/3/14 | NA | NA | NA | NA | Plan | 4/3/2014 - | - 1/4/2014 | 2/4 - 21/4/2014 | 22/4 - 28/4/2014 | 29/4 9/5/2014 | 12/5 - 26/5/2014 | 27/5 - 2/6/2014 | Plan | 3/6 - 16/6/2014 | 17/6 - 23/6/2014 | 7000000 | 24/6 - 30/6/2014 | NA | 1/7 - 7/7/2014 | Plan | - | 15/9/2014 | 29/11/2014 | 7,000,000.00
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 14000000 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 14000000 |  |  |  | Plan |  |  |  | 14000000
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!

## F.M.I F.G.P Goods
Ministry/Department/Agency: FGP
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: O.O Oshunbiyi |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Production of Government Publications for Sale to the Public |  | LOT 1 | 30000000 | NCB | POST | POST | Plan | 3/2 - 25/2/2014 | 26/2 - 3/3/2014 | 4/3/2014 - | 4/3/2014 - | - 14/4/2014 | 15/4 - 5/5/2014 | 6/5 - 13/5/2014 | Plan | 30000000 | NA | 14/5 - 23/5/2014 | 23/5 - 9/6/2014 | NA | 9/7/2014 | 16/7/2014
[7 empty] | Actual | [7 empty] | Actual
date
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  | #VALUE! | 30000000 |  |  |  | Plan | [7 empty] | Plan | 30000000
|  | 0 | 0 |  |  |  | Actual | [7 empty] | Actual | 0
Fill gray cells only!

## F.M.I F.G.P Works
Ministry/Department/Agency: FGP
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: O.O Oshunbiyi |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Purchase of Digital Machines and Other Equipments | FMI/FGP/01 | LOT1 | BOQ | NCB | 5000000 | POST | POST | Plan | 4/2 - 25/2/2014 | 26/2 - 3/3/2014 | 4/3/2014 - | 4/3/2014 - | - 14/4/2014 | 15/4 - 5/5/2014 | 6/5 - 13/5/2014 | Plan | 51000000 | NA | 14/5 - 23/5/2014 | 26/5 - 9/6/14 | 7,650,000.00 | 31/10/2014 | 29/11/2014 | 51,000,000.00
[8 empty] | Actual | [7 empty] | Actual
Rehabilitation of Printing Equipment at FGP, Lagos | FMI/FGP/02 | LOT2 | BOQ | NCB | 20000000 | POST | POST | Plan | 4/2 - 25/2/2014 | 26/2 - 3/3/2014 | 4/3/2014 - | 4/3/2014 - | - 14/4/2014 | 15/4 - 5/5/2014 | 6/5 - 13/5/2014 | Plan | 20000000 | NA | 14/5 - 23/5/2014 | 26/5 - 9/6/14 | 3,000,000.00 | 31/10/2014 | 29/11/2014 | 20,000,000.00
[8 empty] | Actual | [7 empty] | Actual
Rehabilitations of Structure at FGP, Lagos, Access Road to FGP Abuja. | FMI/FGP/03 | LOT3 | BOQ | NCB | 20000000 | POST | POST | Plan | 4/2 - 25/2/2014 | 26/2 - 3/3/2014 | 4/3/2014 - | 4/3/2014 - | - 14/4/2014 | 15/4 - 5/5/2014 | 6/5 - 13/5/2014 | Plan | 20000000 | NA | 14/5 - 23/5/2014 | 26/5 - 9/6/14 | 3,000,000.00 | 31/10/2014 | 29/11/2014 | 20,000,000.00
[8 empty] | Actual | [7 empty] | Actual
Supply of Office Machines to New FGP, Abuja | FMI/FGP/04 | LOT4 | BOQ | NCB | 10000000 | POST | POST | Plan | 4/2 - 25/2/2014 | 26/2 - 3/3/2014 | 4/3/2014 - | 4/3/2014 - | - 14/4/2014 | 15/4 - 5/5/2014 | 6/5 - 13/5/2014 | Plan | 10000000 | NA | 14/5 - 23/5/2014 | 26/5 - 9/6/14 | - | 31/10/2014 | 29/11/2014 | 10,000,000.00
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 55000000 |  |  | Plan | [7 empty] | Plan | 101000000 | [6 empty] | 101000000
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## F.M.I F.G.P Consultants
Ministry/Department/Agency:
Budgetary Year: |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Prior/Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 0 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 0 |  |  |  | Plan |  |  |  | 0
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!

## F.M.I N.A Goods
Ministry/Department/Agency: National Archives of Nigeria
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: Umar Abdulyekin |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Repository Equpment | FMI/01/ARCH | [5 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
date
Sharp Photocopying Machine and Archive Steel Shelves |  | Lot 1 | N2m | SHOPPING | POST | POST | Plan | 3/2 - 25/2/2014 | 26/2 - 3/3/2014 | 4/3/2014 - | 4/3/2014 - | - 14/4/2014 | 15/4 - 5/5/2014 | 6/5 - 13/5/2014 | Plan | N2m | NA | 14/5 - 23/5/2014 | 23/5 - 9/6/2014 | NA | 9/7/2014 | 16/7/2014
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  | #VALUE! | #VALUE! |  |  |  | Plan | [7 empty] | Plan | #VALUE!
|  | 0 | 0 |  |  |  | Actual | [7 empty] | Actual | 0
Fill gray cells only!

## F.M.I N.A Works
Ministry/Department/Agency: National Archives of Nigeria
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: Umar Abdulyekin |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Renovation of Archives: Enugu, Ibadan, Jos, Maiduguri, Benin & Kaduna | FMI/01/ARCH | LOT 1 | BOQ | NCB | N5m | POST | POST | Plan | 4/2 - 25/2/2014 | 26/2 - 3/3/2014 | 4/3/2014 - | 4/3/2014 - | - 14/4/2014 | 15/4 - 5/52014 | 6/5 - 13/5/2014 | Plan |  | NA | 14/5 - 23/5/2014 | 26/5 - 9/6/14 | - | 31/11/2014
[8 empty] | Actual | [7 empty] | Actual
Purchase and Repairs of Technical Equipment | FMI/02/ARCH | LOT 2 | BOQ | NCB | N10m | POST | POST | Plan | 4/2 - 25/2/2014 | 26/2 - 3/3/2014 | 4/3/2014 - | 4/3/2014 - | - 14/4/2014 | 15/4 - 5/52014 | 6/5 - 13/5/2014 | Plan |  | NA | 14/5 - 23/5/2014 | 26/5 - 9/6/14 | - | 31/11/2014
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | #VALUE! |  |  | Plan | [7 empty] | Plan | 0 | [6 empty] | 0
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## F.M.I N.A Consultants
Ministry/Department/Agency: National Archives of Nigeria
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: Umar Abdulyekin |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Prior/Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
Digitization of Archives | NCB |  | N5m | Post | Plan | 3/2 - 25/2/14 | 26/2 - 3/3/14 | NA | NA | NA | NA | Plan | 4/3/2014 - | - 1/4/2014 | 2/4 - 21/4/2014 | 22/4 - 28/4/14 | 29/4 - 9/5/2014 | 12/5 - 26/5/2014 | 27/5 - 2/6/2014 | Plan | 3/6 - 16/6/2014 | 17/6 -23/6/2014 | 5000000 | 24/6 - 30/6/2014 | NA | 1/7 - 7/7/2014 | Plan | - | 15/9/2014 | 29/11/2014 | 5,000,000.00
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | #VALUE! |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 5000000 |  |  |  | Plan |  |  |  | 5000000
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!

## F.M.I P.P.D Goods
Ministry/Department/Agency: Production, Publication & Documentation
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: Dom Onyechi |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Procurement of HD and Celluloid 16mm Camera and Equipment for Video & Photo section | FMI/01/PPD | LOT 1 | 3000000 | NCB | POST | POST | Plan | 3/2 - 25/2/2014 | 26/2 - 3/3/2014 | 4/3/2014 - | 4/3/2014 - | - 14/4/2014 | 15/4 - 5/5/2014 | 6/5 - 13/5/2014 | Plan | 3000000 | NA | 14/5 - 23/55/2014 | 23/5 - 9/6/2014 | NA | 9/9/2014 | 16/7/2014
[7 empty] | Actual | [7 empty] | Actual
date
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  | #VALUE! | 3000000 |  |  |  | Plan | [7 empty] | Plan | 3000000
|  | 0 | 0 |  |  |  | Actual | [7 empty] | Actual | 0
Fill gray cells only!

## F.M.I P.P.D Works
Ministry/Department/Agency: Production, Publication & Documentation
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: Dom Onyechi |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Continuation of the Construction of the Abandoned Male Hostel at NIPI, Kaduna | FMI/PPD/2 | LOT 1 | BQ | NCB | 6000000 | Pre-or Post Qualification | Post Review | Plan | 3/2 - 25/2/2014 | 26/2 - 3/3/2014 | 4/3/2014 - | 4/3/2014 - | - 14/4/2014 | 15/4 - 5/5/2014 | 6/5 - 13/5/2014 | Plan | 6000000 | NA | 14/5 - 23/5/2014 | 26/5 - 9/6/14 | -- | 21/10/2014 | 29/11/2014 | 6000000
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 6000000 |  |  | Plan | [7 empty] | Plan | 6000000 | [6 empty] | 6000000
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## F.M.I P.P.D Consultants
Ministry/Department/Agency: | PPD
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: Dom Onyechi |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Prior/Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
1. PUBLICATIONS | NCB | Lumpsum | N65m | Post | Plan | 3/2 - 25/2/14 | 26/2 - 3/3/14 | N/A | N/A | N/A | N/A | Plan | 4/3/2014 - | - 1/4/2014 | 2/4 - 21/4/2014 | 22/4 - 28/4/2014 | 29/4 - 9/5/2014 | 12/5 - 26/5/2014 | 27/5 - 2/6/2014 | Plan | 3/6 - 16/6/2014 | 17/6 - 23/6/2014 | N65m | 24/6 - 30/6/2014 | NA | 1/7 - 7/7/2014 | Plan | 9,750,000.00 | 15/9/2014 | 29/11/2014 | 65,000,000.00
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
(a) Government Today |  |  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
(b) Production of Nigeria Monthly |  |  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
© Sectorial Booklets |  |  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
(d) Pictorial on the National Good Governance Tour - 5,000 Copies |  |  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
2. PRODUCTION OF CALENDARS AND DIARIES | NCB | Lumpsum | N200m | Post | Plan | 3/2 - 25/2/14 | 26/2 - 3/3/14 | N/A | N/A | N/A | N/A | Plan | 4/3/2014 - | - 1/4/2014 | 2/4 - 21/4/2014 | 22/4 - 28/4/2014 | 29/4 - 9/5/2014 | 12/5 - 26/5/2014 | 27/5 - 2/6/2014 | Plan | 3/6 - 16/6/2014 | 17/6 - 23/6/2014 | N200m | 24/6 - 30/6/2014 | NA | 1/7 - 7/7/2014 | Plan | 30,000,000.00 | 15/9/2014 | 29/11/2014 | 200,000,000.00
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
3. FILM & DOCUMENTARIES | NCB | Lumpsum | N25m | Post | Plan | 3/2 - 25/2/14 | 26/2 - 3/3/14 | N/A | N/A | N/A | N/A | Plan | 4/3/2014 - | - 1/4/2014 | 2/4 - 21/4/2014 | 22/4 - 28/4/2014 | 29/4 - 9/5/2014 | 12/5 - 26/5/2014 | 27/5 - 2/6/2014 | Plan | 3/6 - 16/6/2014 | 17/6 - 23/6/2014 | N25m | 24/6 - 30/6/2014 | NA | 1/7 - 7/7/2014 | Plan | 3,750,000.00 | 15/9/2014 | 29/11/2014 | 25,000,000.00
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
(a) Production of Documentaries on Transformation Agenda |  |  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
(b) Production of Jingles on Various Government Policies. (c) Airing of Jingles |  |  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
Actual
Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | #VALUE! |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | #VALUE! |  |  |  | Plan |  |  |  | 290000000
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!

## F.M.I F.A Goods
Ministry/Department/Agency:
Budgetary Year: | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
date
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  | 0 | 0 |  |  |  | Plan | [7 empty] | Plan | 0
|  | 0 | 0 |  |  |  | Actual | [7 empty] | Actual | 0
Fill gray cells only!

## F.M.I F.A Works
Ministry/Department/Agency:
Budgetary Year: | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 0 |  |  | Plan | [7 empty] | Plan | 0 | [6 empty] | 0
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## F.M.I F.AConsultants
Ministry/Department/Agency: Finance and Accounts Department
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: Umaru Sule |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Prior/Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
Capacity Building on Budget Monitoring of Projects and Evaluation and Financial Management in line with Transformation Agenda | NCB | Lumpsum | 30500000 | POST | Plan | 3/2 - 25/2/14 | NA | NA | NA | NA | NA | Plan | 3/3/2014 | - 14/4/2014 | 15/4 - 28/4/2014 | NA | 28/4 - 12/5/2014 | 13/5 - 26/5/2014 | 27/5 - 3/6/2014 | Plan | 4/6 -16/6/2014 | 30/6/2014 | 30500000 | 1/7 - 14/7/2014 | NA | 15/7 - 28/7/2014 | Plan | 4,575,000.00 | 15/9/2014 | 14/11/2014 | 30,500,000.00
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Advance Computer Training in Excel and Finance Software Application for Staff of the Department | NCB | Lumpsum | 10000000 | POST | Plan | 3/2 - 25/2/14 | NA | NA | NA | NA | NA | Plan | 3/3/2014 | - 14/4/2014 | 15/4 - 28/4/2014 | NA | 28/4 - 12/5/2014 | 13/5 - 26/5/2014 | 27/5 - 3/6/2014 | Plan | 4/6 -16/6/2014 | 30/6/2014 | 10000000 | 1/7 - 14/7/2014 | NA |  | Plan | - | 15/9/2014 | 14/11/2014 | 10,000,000.00
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 40500000 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 40500000 |  |  |  | Plan |  |  |  | 40500000
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!

## F.M.I P.C Goods
Ministry/Department/Agency:
Budgetary Year: | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
date
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  | 0 | 0 |  |  |  | Plan | [7 empty] | Plan | 0
|  | 0 | 0 |  |  |  | Actual | [7 empty] | Actual | 0
Fill gray cells only!

## F.M.I P.C Works
Ministry/Department/Agency: | Public Communication
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: E.N Agbegir |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Rehabilitation of National Press Center, Abuja | FMI/PC/1 | Lot 1 | BQ | NCB | 7000000 | Post Qualification | Post Review | Plan | 4/2 - 25/2/2014 | 26/2 - 3/3/2014 | 4/3/2014 - | 4/3/2014 - | - 14/4/2014 | 15/4 - 5/5/2014 | 6/5 - 13/5/2014 | Plan | 7000000 | NA | 14/5 - 23/5/2014 | 26/5 - 9/6/14 | - | 31/10/2014 | 29/11/2014 | 7,000,000.00
[8 empty] | Actual | [7 empty] | Actual
Development of Social Media Platforms & Networking with other Platforms | FMI/PC/1 | Lot 2 | BQ | NCB | 50000000 | Post Qualification | Post Review | Plan | 4/2 - 25/2/2014 | 26/2 - 3/3/2014 | 4/3/2014 - | 4/3/2014 - | - 14/4/2014 | 15/4 - 5/5/2014 | 6/5 - 13/5/2014 | Plan | 50000000 | NA | 14/5 - 23/5/2014 | 26/5 - 9/6/14 | 7,500,000.00 | 31/10/2014 | 29/11/2014 | 50,000,000.00
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 57000000 |  |  | Plan | [7 empty] | Plan | 57000000 | [6 empty] | 57000000
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## F.M.I P.C Consultants
Ministry/Department/Agency:
Budgetary Year: |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Prior/Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
Publicity of Government Development Programmes & Activities/Organizing Ministerial | NCB | Lumpsum | 130000000 | Post | Plan | 3/2 - 25/2/14 | 26/2/ - 3/3/14 | NA | NA | NA | NA | Plan | 4/3/2014 - | - 1/4/2014 | 2/4 - 21/4/14 | 22/4 - 28/4/14 | 29/5 - 9/5/14 | 12/5 - 26/5/14 | 27/5 - 2/6/14 | Plan | 3/6 - 16/6/2014 | 17/6 - 23/6/2014 | 130000000 | 24/6 - 30/6/2014 | NA | 1/7 - 7/7/2014 | Plan | 19,500,000.00 | 15/9/2014 | 29/11/2014 | 130,000,000.00
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Grassroot publicity of governmnet Policies & Programmes by FICs | NCB | Lumpsum | 30000000 | Post | Plan | 3/2 - 25/2/14 | 26/2/ - 3/3/14 | NA | NA | NA | NA | Plan | 4/3/2014 - | - 1/4/2014 | 2/4 - 21/4/14 | 22/4 - 28/4/14 | 29/5 - 9/5/14 | 12/5 - 26/5/14 | 27/5 - 2/6/14 | Plan | 3/6 - 16/6/2014 | 17/6 - 23/6/2014 | 30000000 | 24/6 - 30/6/2014 | NA | 1/7 - 7/7/2014 | Plan | 4,500,000.00 | 15/9/2014 | 29/11/2014 | 30,000,000.00
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Publicity of NV20:2020 | NCB | Lumpsum | 55000000 | Post | Plan | 3/2 - 25/2/14 | 26/2/ - 3/3/14 | NA | NA | NA | NA | Plan | 4/3/2014 - | - 1/4/2014 | 2/4 - 21/4/14 | 22/4 - 28/4/14 | 29/5 - 9/5/14 | 12/5 - 26/5/14 | 27/5 - 2/6/14 | Plan | 3/6 - 16/6/2014 | 17/6 - 23/6/2014 | 55000000 | 24/6 - 30/6/2014 | NA | 1/7 - 7/7/2014 | Plan | 8,250,000.00 | 15/9/2014 | 29/11/2014 | 55,000,000.00
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
External Publicity/Media Insertions in Foreign Media:Print Media, Electronic Media, Media Forum in selected cities abroad. Engagement with Foreign News Agencies,Production of Specialized Publicity materials for External Audience | NCB | Lumpsum | 300000000 | Post | Plan | 3/2 - 25/2/14 | 26/2/ - 3/3/14 | NA | NA | NA | NA | Plan | 4/3/2014 - | - 1/4/2014 | 2/4 - 21/4/14 | 22/4 - 28/4/14 | 29/5 - 9/5/14 | 12/5 - 26/5/14 | 27/5 - 2/6/14 | Plan | 3/6 - 16/6/2014 | 17/6 - 23/6/2014 | 300000000 | 24/6 - 30/6/2014 | NA | 1/7 - 7/7/2014 | Plan | 45,000,000.00 | 15/9/2014 | 29/11/2014 | 300,000,000.00
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 515000000 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 515000000 |  |  |  | Plan |  |  |  | 515000000
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!

## SGR Goods
Ministry/Department/Agency: FEDERAL MINISTRY OF AGRICULTURE: STRATEGIC GRAINS RESERVE DEPARTMENT (SGR)
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact N.A.Kilishi 08035916885 |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization | [5 empty] | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Plan vs. Actual | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 2 wks | Plan | 2 - 3 wks | T | 2 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual |  |  |  |  | Actual
List of Contracts
PROCUREMENT OF ASSORTED GRAINS | [6 empty] | Plan | [7 empty] | Plan |  |  |  |  | Plan
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Procurement of 1000mt of maize |  |  | 90000000 | NCB | NA | MTB | Plan | Apr 24 - June 6 | June 9 - June 16 | NA | July 7 - Aug 4 | Sept 15 | Sept 22 - Oct 3 | 0ct 6 - 0ct 20 | Plan |  | NA | Nov 3 - Nov 17 | Nov 21 - Dec 5 | Plan | Dec 8 - Dec 18 | Dec 22 - Jan 3 | Jan 5 - Jan 19
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Procurement of 500mt of sorghum |  |  | 42500000 | NCB | NA | MTB | Plan | Apr 24 - June 6 | June 9 - June 16 | NA | July 7 - Aug 4 | Sept 15 | Sept 22 - Oct 3 | 0ct 6 - 0ct 20 | Plan |  | NA | Nov 3 - Nov 17 | Nov 21 - Dec 5 | Plan | Dec 8 - Dec 18 | Dec 22 - Jan 3 | Jan 5 - Jan 19
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Procurement of 500mt of Millet |  |  | 50000000 | NCB | NA | MTB | Plan | Apr 24 - June 6 | June 9 - June 16 | NA | July 7 - Aug 4 | Sept 15 | Sept 22 - Oct 3 | 0ct 6 - 0ct 20 | Plan |  | NA | Nov 3 - Nov 17 | Nov 21 - Dec 5 | Plan | Dec 8 - Dec 18 | Dec 22 - Jan 3 | Jan 5 - Jan 19
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Procurement of 200mt of Garri |  |  | 24000000 | NCB | NA | MTB | Plan | Apr 24 - June 6 | June 9 - June 16 | NA | July 7 - Aug 4 | Sept 15 | Sept 22 - Oct 3 | 0ct 6 - 0ct 20 | Plan |  | NA | Nov 3 - Nov 17 | Nov 21 - Dec 5 | Plan | Dec 8 - Dec 18 | Dec 22 - Jan 3 | Jan 5 - Jan 19
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Procurement of 100mt of Soyabeans |  |  | 11500000 | NCB | NA | MTB | Plan | Apr 24 - June 6 | June 9 - June 16 | NA | July 7 - Aug 4 | Sept 15 | Sept 22 - Oct 3 | 0ct 6 - 0ct 20 | Plan |  | NA | Nov 3 - Nov 17 | Nov 21 - Dec 5 | Plan | Dec 8 - Dec 18 | Dec 22 - Jan 3 | Jan 5 - Jan 19
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Procurement of 500mt of Paddy Rice |  |  | 62500000 | NCB | NA | MTB | Plan | Apr 24 - June 6 | June 9 - June 16 | NA | July 7 - Aug 4 | Sept 15 | Sept 22 - Oct 3 | 0ct 6 - 0ct 20 | Plan |  | NA | Nov 3 - Nov 17 | Nov 21 - Dec 5 | Plan | Dec 8 - Dec 18 | Dec 22 - Jan 3 | Jan 5 - Jan 19
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Procurement of 300mt of HQCF |  |  | 37500000 | NCB | NA | MTB | Plan | [7 empty] | Plan |  | NA | Nov 3 - Nov 17 | Nov 21 - Dec 5 | Plan | Dec 8 - Dec 18 | Dec 22 - Jan 3 | Jan 5 - Jan 19
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Procurement of Handling Equipment | [6 empty] | Plan | Apr 24 - June 6 | June 9 - June 16 | NA | July 7 - Aug 4 | Sept 15 | Sept 22 - Oct 3 | 0ct 6 - 0ct 20 | Plan |  | NA | Nov 3 - Nov 17 | Apr 15- 26 | Plan | Dec 8 - Dec 18 | Dec 22 - Jan 3 | Jan 5 - Jan 19
|  |  | 18000000 | NCB | NA | MTB | Actual | [7 empty] | Actual |  |  |  |  | Actual
Procurement of Environmental Chemicals |  |  | 10000000 | NCB | NA | MTB | Plan | Jan 7 -18 | June 9 - June 16 | NA | July 7 - Aug 4 | Sept 15 | Sept 22 - Oct 3 | 0ct 6 - 0ct 20 | Plan |  | NA | Nov 3 - Nov 17 | Nov 21 - Dec 5 | Plan | Dec 8 - Dec 18 | Dec 22 - Jan 3 | Jan 5 - Jan 19
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
Procurement of Storage Chemicals |  |  | 15000000 | NCB | NA | MTB | Plan | Jan 7 -18 | Jan 21-25 | NA | Jan 28 - Feb8 | Sept 15 | Sept 22 - Oct 3 | 0ct 6 - 0ct 20 | Plan |  | NA | Nov 3 - Nov 17 | Nov 21 - Dec 5 | Plan | Dec 8 - Dec 18 | Dec 22 - Jan 3 | Jan 5 - Jan 19
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual
[7 empty] | Plan | [7 empty] | Plan |  |  |  |  | Plan
[7 empty] | Actual | [7 empty] | Actual |  |  |  |  | Actual

## SGR Works
Ministry/Department/Agency: SGR
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Rehabilitation of Hotoro Grain Depot, Provision of Avery Scales, Pallets and Fumigation sheets |  |  |  | NCB | 7,500,000.00 |  | MTB | Plan | Apr 24 - June 6 | June 9 - June 16 | NA | July 7 - Aug 4 | Sept 15 | Sept. 22 - Oct 3 | Oct 6 - Oct 20 | Plan |  | NA | Nov 3 - Nov 17 | Nov 21 - 30 | Dec 8 Dec 18
[8 empty] | Actual | [7 empty] | Actual
Rehabilitation of Specialised Community warehouses |  |  |  | NCB | 35000000 |  | MTB | Plan | Apr 24 - June 6 | June 9 - June 16 | NA | July 7 - Aug 4 | Sept 15 | Sept. 22 - Oct 3 | Oct 6 - Oct 20 | Plan |  | NA | Nov 3 - Nov 17 | Nov 21 - 30 | Dec 8 Dec 18
[8 empty] | Actual | [7 empty] | Actual
Digitalization of Weighbridges in Functional Silo Complexes |  |  |  | NCB | 40000000 |  | MTB | Plan | Apr 24 - June 6 | June 9 - June 16 | NA | July 7 - Aug 4 | Sept 15 | Sept. 22 - Oct 3 | Oct 6 - Oct 20 | Plan |  | NA | Nov 3 - Nov 17 | Nov 21 - 30 | Dec 8 Dec 18
Rehabilitation of SGR Ibadan Silo Complex Road Network |  |  |  | NCB | 12500000 |  | MTB | Plan | Apr 24 - June 6 | June 9 - June 16 | NA | July 7 - Aug 4 | Sept 15 | Sept. 22 - Oct 3 | Oct 6 - Oct 20 | Plan |  | NA | Nov 3 - Nov 17 | Nov 21 - 30 | Dec 8 Dec 18
Installation Sweep Augers at SGR Silo Complex |  |  |  | NCB | 50,000.000.00 |  | MTB | Plan | Apr 24 - June 6 | June 9 - June 16 | NA | July 7 - Aug 4 | Sept 15 | Sept. 22 - Oct 3 | Oct 6 - Oct 20 | Plan |  | NA | Nov 3 - Nov 17 | Nov 21 - 30 | Dec 8 Dec 18
Provision of Access Scaffold |  |  |  | NCB | 35,000.000.00 |  | MTB | Plan | Apr 24 - June 6 | June 9 - June 16 | NA | July 7 - Aug 4 | Sept 15 | Sept. 22 - Oct 3 | Oct 6 - Oct 20 | Plan |  | NA | Nov 3 - Nov 17 | Nov 21 - 30 | Dec 8 Dec 18
[8 empty] | Actual | [7 empty] | Actual
Provision of Grains Cleaners |  |  |  | NCB | 27000000 |  | MTB | Plan | Apr 24 - June 6 | June 9 - June 16 | NA | July 7 - Aug 4 | Sept 15 | Sept. 22 - Oct 3 | Oct 6 - Oct 20 | Plan |  | NA | Nov 3 - Nov 17 | Nov 21 - 30 | Dec 8 Dec 18
[8 empty] | Actual | [7 empty] | Actual
Provision of 350KVA Generators |  |  |  | NCB | 25000000 |  | MTB | Plan | Apr 24 - June 6 | June 9 - June 16 | NA | July 7 - Aug 4 | Sept 15 | Sept. 22 - Oct 3 | Oct 6 - Oct 20 | Plan |  | NA | Nov 3 - Nov 17 | Nov 21 - 30 | Dec 8 Dec 18
[8 empty] | Actual | [7 empty] | Actual
Rehabilitation of Leakages |  |  |  | NCB | 5000000 |  | MTB | Plan | Apr 24 - June 6 | June 9 - June 16 | NA | July 7 - Aug 4 | Sept 15 | Sept. 22 - Oct 3 | Oct 6 - Oct 20 | Plan |  | NA | Nov 3 - Nov 17 | Nov 21 - 30 | Dec 8 Dec 18
[8 empty] | Actual | [7 empty] | Actual
Provision of Industrial Stiching Machines |  |  |  | NCB | 15000000 |  | MTB | Plan | Apr 24 - June 6 | June 9 - June 16 | NA | July 7 - Aug 4 | Sept 15 | Sept. 22 - Oct 3 | Oct 6 - Oct 20 | Plan |  | NA | Nov 3 - Nov 17 | Nov 21 - 30 | Dec 8 Dec 18
[8 empty] | Actual | [7 empty] | Actual
Rehabilitation of Grain Dryers |  |  |  | NCB | 40000000 |  | MTB | Plan | Apr 24 - June 6 | June 9 - June 16 | NA | July 7 - Aug 4 | Sept 15 | Sept. 22 - Oct 3 | Oct 6 - Oct 20 | Plan |  | NA | Nov 3 - Nov 17 | Nov 21 - 30 | Dec 8 Dec 18
[8 empty] | Actual | [7 empty] | Actual
Provision of Tractor Mounted Slashers and Lawnmowers |  |  |  | NCB | 15000000 |  | MTB | Plan | Apr 24 - June 6 | June 9 - June 16 | NA | July 7 - Aug 4 | Sept 15 | Sept. 22 - Oct 3 | Oct 6 - Oct 20 | Plan |  | NA | Nov 3 - Nov 17 | Nov 21 - 30 | Dec 8 Dec 18
[8 empty] | Actual | [7 empty] | Actual
Replacement of Bagging Plants |  |  |  | NCB | 20000000 |  | MTB | Plan | Apr 24 - June 6 | June 9 - June 16 | NA | July 7 - Aug 4 | Sept 15 | Sept. 22 - Oct 3 | Oct 6 - Oct 20 | Plan |  | NA | Nov 3 - Nov 17 | Nov 21 - 30 | Dec 8 Dec 18
[8 empty] | Actual | [7 empty] | Actual
Provision of Centrifuga type (10) Nos. Aerations Fans |  |  |  | NCB | 12000000 |  | MTB | Plan | Apr 24 - June 6 | June 9 - June 16 | NA | July 7 - Aug 4 | Sept 15 | Sept. 22 - Oct 3 | Oct 6 - Oct 20 | Plan |  | NA | Nov 3 - Nov 17 | Nov 21 - 30 | Dec 8 Dec 18
[8 empty] | Actual | [7 empty] | Actual
Provision of Dust Houses |  |  |  | NCB | 10000000 |  | MTB | Plan | Apr 24 - June 6 | June 9 - June 16 | NA | July 7 - Aug 4 | Sept 15 | Sept. 22 - Oct 3 | Oct 6 - Oct 20 | Plan |  | NA | Nov 3 - Nov 17 | Nov 21 - 30 | Dec 8 Dec 18
[8 empty] | Actual | [7 empty] | Actual
Procurement of 10 Nos Batteries for Inverters |  |  |  | NCB | 1000000 |  | MTB | Plan | Apr 24 - June 6 | June 9 - June 16 | NA | July 7 - Aug 4 | Sept 15 | Sept. 22 - Oct 3 | Oct 6 - Oct 20 | Plan |  | NA | Nov 3 - Nov 17 | Nov 21 - 30 | Dec 8 Dec 18
[8 empty] | Actual | [7 empty] | Actual

## SGR Consultants
Ministry/Department/Agency: FEDERAL MINISTRY OF AGRICULTURE: STRATEGIC GRAINS RESERVE DEPARTMENT (SGR)
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Destk Officer/Contact: 08035916885 |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | Plan vs. Actual | No-objection Date | FEC Approval | Contract Amount in Naira | Contract Offer | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | Plan | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | Plan | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 1- 2 wk | 2 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
List of Contracts
Training/Meetings/Conferneces/supervisory visits |  |  | 40,000.000.00 |  | Plan | Apr 24 - June 6 | June 9 - June 16 |  |  |  |  | Plan | July 7 - Aug 4 | Sept 15 - Sept 22 | Sept 22 - Oct 3 | Oct 6 - Oct 20 | Oct 20 - Nov 3 | Nov 4 - Nov 18 |  | Plan |  |  |  | Nov 12 - Nov 30 | Dec 1 - Dec 14 | Plan |  | Dec 15 - Dec 22
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Total Cost |  |  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | #REF! |  |  | Plan |  |  |  | #REF!
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | #REF! |  |  | Actual |  |  |  | #REF!
Fill gray cells only!

## RURAL Works
MINISTRY/DEPT/AGENCY: AGRICULTURE AND RURAL DEVELOPMENT | PROCUREMENT-PLAN WORKS
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: OLUSHIYAN F M |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No Objections | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No Objections | Plan vs. Actual | Contract Amount Certified in Naira | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2-6wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 1wk
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Upscaling and linkage support for 8 Nos.existing enclave project sites and farm resettlement site centres | Package 1 | Lot 1 | BOQ | NCB | 83075000 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 83075000 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 83075000
TOTAL |  |  |  |  | 83075000 | [18 empty] | 83075000
| Package 1 | Lot 5 | BOQ | NCB | 77,116,716.00 | Post qualification | MTB | Plan | 30th July- 20th Aug,2013 | 23rd -24th Aug,2013 | Not Required | 27th Aug-24th Sept,2013 | 24th Sept,2013 | 24th- 28th Sept,2013 | 2nd -8th Sept,2013 | Plan | 77,116,716.00 | Not Required | 8th - 15th Oct,2013 | 15th - 22nd Oct, 2013 | 22nd -31st Oct,2013 | 15th Oct,2013 - 10th Dec,2013(8th week) | 10th-31st ,2013(12th week) | 77,116,716.00
[8 empty] | Actual | [7 empty] | Actual
| Package 1 | Lot 6 | BOQ | NCB | 63,000,000.00 | Post qualification | MTB | Plan | 30th July- 20th Aug,2013 | 23rd -24th Aug,2013 | Not Required | 27th Aug-24th Sept,2013 | 24th Sept,2013 | 24th- 28th Sept,2013 | 2nd -8th Sept,2013 | Plan | 63,000,000.00 | Not Required | 8th - 15th Oct,2013 | 15th - 22nd Oct, 2013 | 22nd -31st Oct,2013 | 15th Oct,2013 - 10th Dec,2013(8th week) | 10th-31st ,2013(12th week) | 63,000,000.00
[8 empty] | Actual | [7 empty] | Actual
Provision of 25 Units motorized boreholes for rural communities | Package 2 | Lot 2 | BOQ | NCB | 184363776.4 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 184363776.4 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 184363776.4
TOTAL |  |  |  |  | 184363776.4 | [11 empty] | 184363776.4 | [6 empty] | 184363776.4
| Package 1 | Lot 8 | BOQ | NCB | 76,907,151.00 | Post qualification | MTB | Plan | 30th July- 20th Aug,2013 | 23rd -24th Aug,2013 | Not Required | 27th Aug-24th Sept,2013 | 24th Sept,2013 | 24th- 28th Sept,2013 | 2nd -8th Sept,2013 | Plan | 76,907,151.00 | Not Required | 8th - 15th Oct,2013 | 15th - 22nd Oct, 2013 | 22nd -31st Oct,2013 | 15th Oct,2013 - 10th Dec,2013(8th week) | 10th-31st ,2013(12th week) | 76,907,151.00
[8 empty] | Actual | [7 empty] | Actual
| Package 1 | Lot 9 | BOQ | NCB | 76,612,151.00 | Post qualification | MTB | Plan | 30th July- 20th Aug,2013 | 23rd -24th Aug,2013 | Not Required | 27th Aug-24th Sept,2013 | 24th Sept,2013 | 24th- 28th Sept,2013 | 2nd -8th Sept,2013 | Plan | 76,612,151.00 | Not Required | 8th - 15th Oct,2013 | 15th - 22nd Oct, 2013 | 22nd -31st Oct,2013 | 15th Oct,2013 - 10th Dec,2013(8th week) | 10th-31st ,2013(12th week) | 76,612,151.00
[8 empty] | Actual | [7 empty] | Actual
Provision of 86 Units hand pump equipped boreholes for rural communities | Package 3 | Lot 3 | BOQ | NCB |  | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan |  | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week)
Actual
TOTAL
| Package 1 | Lot 11 | BOQ | NCB | 76,500,716.00 | Post qualification | MTB | Plan | 30th July- 20th Aug,2013 | 23rd -24th Aug,2013 | Not Required | 27th Aug-24th Sept,2013 | 24th Sept,2013 | 24th- 28th Sept,2013 | 2nd -8th Sept,2013 | Plan | 76,500,716.00 | Not Required | 8th - 15th Oct,2013 | 15th - 22nd Oct, 2013 | 22nd -31st Oct,2013 | 15th Oct,2013 - 10th Dec,2013(8th week) | 10th-31st ,2013(12th week) | 76,500,716.00
[8 empty] | Actual | [7 empty] | Actual
| Package 1 | Lot 12 | BOQ | NCB | 76,541,205.00 | Post qualification | MTB | Plan | 30th July- 20th Aug,2013 | 23rd -24th Aug,2013 | Not Required | 27th Aug-24th Sept,2013 | 24th Sept,2013 | 24th- 28th Sept,2013 | 2nd -8th Sept,2013 | Plan | 76,541,205.00 | Not Required | 8th - 15th Oct,2013 | 15th - 22nd Oct, 2013 | 22nd -31st Oct,2013 | 15th Oct,2013 - 10th Dec,2013(8th week) | 10th-31st ,2013(12th week) | 76,541,205.00
[8 empty] | Actual | [7 empty] | Actual
Promotion of 43 Units homestead/backyard irrigation crop production activities | Package 4 | Lot 4 | BOQ | NCB | 106256074.26 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 106256074.26 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June,2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 106256074.26
TOTAL |  |  |  |  | 106256074.26 | [10 empty] | Actual | 106256074.26 | [6 empty] | 106256074.26
Construction/Consolidation of Constituency rural roads
| Package 1 | Lot 15 | BOQ | NCB | 40,500,000.00 | Post qualification | MTB | Plan | 30th July- 20th Aug,2013 | 23rd -24th Aug,2013 | Not Required | 27th Aug-24th Sept,2013 | 24th Sept,2013 | 24th- 28th Sept,2013 | 2nd -8th Sept,2013 | Plan | 40,500,000.00 | Not Required | 8th - 15th Oct,2013 | 15th - 22nd Oct, 2013 | 22nd -31st Oct,2013 | 15th Oct,2013 - 10th Dec,2013(8th week) | 10th-31st ,2013(12th week) | 40,500,000.00
[8 empty] | Actual | [7 empty] | Actual
| Package 1 | Lot 17 | BOQ | NCB | 18,000,000.00 | Post qualification | MTB | Plan | 30th July- 20th Aug,2013 | 23rd -24th Aug,2013 | Not Required | 27th Aug-24th Sept,2013 | 24th Sept,2013 | 24th- 28th Sept,2013 | 2nd -8th Sept,2013 | Plan | 18,000,000.00 | Not Required | 8th - 15th Oct,2013 | 15th - 22nd Oct, 2013 | 22nd -31st Oct,2013 | 15th Oct,2013 - 10th Dec,2013(8th week) | 10th-31st ,2013(12th week) | 18,000,000.00
[8 empty] | Actual | [7 empty] | Actual
|  |  | BOQ | NCB | 738,000,000.00 | Post qualification | MTB | Plan | 30th July- 20th Aug,2013 | 23rd -24th Aug,2013 | Not Required | 27th Aug-24th Sept,2013 | 24th Sept,2013 | 24th- 28th Sept,2013 | 2nd -8th Sept,2013 | Plan | 738,000,000.00 | Not Required | 8th - 15th Oct,2013 | 15th - 22nd Oct, 2013 | 22nd -31st Oct,2013 | 15th Oct,2013 - 10th Dec,2013(8th week) | 10th-31st ,2013(12th week) | 738,000,000.00
[8 empty] | Actual | [7 empty] | Actual
Construction/Consolidation of 1 KM Ibom Baraki-Obinkita-Asanga-Amuvi consituency Road, Abia State | package 5 | Lot 5 | BOQ | NCB | 18381541.5 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 18381541.5 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 18381541.5
Construction/Consolidation of 4.2Km Gbokutaru-Ajebandele constituency Road, Ijebu.Ogun State | package 5 | Lot 6 | BOQ | NCB | 83710068 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 83710068 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 83710068
Construction/Consolidation of 7Km Ikere/Ijan constituency Road, Ekiti South, Ekiti State | package 5 | Lot 7 | BOQ | NCB | 74717637.75 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 74717637.75 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 74717637.75
Construction/Consolidation of 8Km Amaguwa-Gidan constituency Road, Ringim LGA, Jigawa State | package 5 | Lot 8 | BOQ | NCB | 65820117.61 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 65820117.61 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 65820117.61
Construction/Consolidation of 3Km Ekoli-Edda-Okagwe Ohafia constituency Road, Afikpo South LGA, Ebonyi State | package 5 | Lot 9 | BOQ | NCB | 69937087 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 69937087 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 -21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 69937087
Construction/Consolidation of 4Km Amba-Bassa/Yelwa, constituency Road Kokona LGA, Nasarawa State | package 5 | Lot 10 | BOQ | NCB | 66820000 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 66820000 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 66820000
Construction/Consolidation of 9Km Gwarzo-,Mazoji constituency Road,Matazu LGA, Katsina State | package 5 | Lot 11 | BOQ | NCB | 79328866.05 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 79328866.05 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 79328866.05
Construction/Consolidation of 3.2 Km Kaltungo-Banguji constituency Road Gombe State | package 5 | Lot 12 | BOQ | NCB | 69601387.3 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 69601387.3 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 69601387.3
Construction/Consolidation of 3.3Km Ovwodemo Farm constituency Road Delta State | package 5 | Lot 13 | BOQ | NCB | 63183834 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 63183834 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 63183834
Construction/Consolidation of 3KM Rural Road in Kwara State | package 5 | Lot 14 | BOQ | NCB | 62728170.75 | Post qualification | MTB | Plan | 17th March- 1st April,2014 | 3rd -4th April ,2014 | Not Required | 7th April -5th May ,2014 | 5th May ,2014 | 6th- 9th May,2014 | 12th -15th May,2014 | Plan | 62728170.75 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 62728170.75
Construction/Consolidation of3KM Rural Road in Edo South Senatorial District, Edo State | package 5 | Lot 15 | BOQ | NCB | 60493293 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 60493293 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 60493293
Construction/Consolidation of 4.3 KM Rural Road in Tambuwal LGA, Sokoto, Sokoto State | package 5 | Lot 16 | BOQ | NCB | 77889420 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 77889420 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 77889420
Construction/Consolidation of 2.6KM Rural Road in Ogbomosho LGA, Oyo State | package 5 | Lot 17 | BOQ | NCB | 45049252.5 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 45049252.5 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 45049252.5
Construction/Consolidation of 1KM Rural Road from Danwarari-Saaadam in Ailero, Kebbi State | package 5 | Lot 18 | BOQ | NCB | 21500955 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 21500955 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 21500955
Construction/Consolidation of 1.5 KM Rural Road Yar Wutsiya Kungurmi Wanke, Bugudu LGA, Zamfara State | package 5 | Lot 19 | BOQ | NCB | 26412592 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 26412592 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 26412592
Construction/Consolidation of 1.5 KM Furore-Ribadu constituency Road,Adamawa State | package 5 | Lot 20 | BOQ | NCB | 24318948 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 24318948 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 24318948
Construction/Consolidation of 5KM Agbokinm Water falls-Abia constituency Road, Etung LGA, Cross River State | package 5 | Lot 21 | BOQ | NCB | 30937803.75 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 30937803.75 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June,2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 30937803.75
Construction/Consolidation of 8.7KM Gwaram Federal constituency Road, Jigawa State | package 5 | Lot 22 | BOQ | NCB | 105250162.05 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 105250162.05 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 105250162.05
Construction/Consolidation of1KM Danmarke Rural road, Kankara LGA, Katsina State | package 5 | Lot 23 | BOQ | NCB | 19783921.5 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 19783921.5 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 19783921.5
Construction/Consolidation of1. 5Km Akpagher - Ikpeger Road, Benue State | package 5 | Lot 24 | BOQ | NCB | 24625722.5 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 24625722.5 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 24625722.5
Construction/Consolidation of 14Km Rural road from Enagi-Dikko-Gbodoji-Guzan-Kpata-Tsuworo, Edaji LGA, Niger south Senatorial District, Niger State | package 5 | Lot 25 | BOQ | NCB | 83271825 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 83271825 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 83271825
Construction/Consolidation of 9.4 Ajido -Apodo constituency Road | package 5 | Lot 26 | BOQ | NCB | 42730184.7 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 42730184.7 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 42730184.7
TOTAL |  |  |  |  | 1216492789.96 | [11 empty] | 1216492789.96 | [6 empty] | 1216492789.96
Solar Rural Electrification in 3 Rural communities in Emure/Gboyin and Ekiti East LGAs, Ekiti State | Package 6 | Lot 27 |  | NCB | 14432187 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 14432187 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 14432187
Provision of 25Nos. Hand Pump Equipped Borehole at various Rural communities and LGAs in Ekiti State. | Package 7 | Lot 28 | BOQ | NCB | 31007543.25 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 31007543.25 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 31007543.25
Provision of Cassava processing integrated industry at Akpoha in Afikpo North LGA, Ebonyi State | Package 8 | Lot 29 | BOQ | NCB | 18030364.8 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 18030364.8 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 18030364.8
TOTAL |  |  |  |  | 63470095.05 | [11 empty] | 63470095.05 | [6 empty] | 63470095.05
PAYMENT OF OUTSTANDING DEBTS
[5 empty] | 300000000 | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan | 300000000 | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week) | 300000000
Payment of outstanding liabilities for certified 2006 and 2012 rural roads, MDG projects |  |  | BOQ | NCB |  | Post qualification | MTB | Plan | 17th March- 1st April, 2014 | 3rd -4th April, 2014 | Not Required | 7th April -5th May, 2014 | 5th May, 2014 | 6th- 9th May, 2014 | 12th -15th May, 2014 | Plan |  | Not Required | 19th May - 2nd June, 2014 | 2nd - 9th June, 2014 | 9th -16th June, 2014 | 2nd June, 2014 - 21st July, 2014(8th week) | 21st July-11th August, 2014(12th week)

## RURAL Consultants
MINISTRY/DEPT/AGENCY: AGRICULTURE AND RURAL DEVELOPMENT/RURAL DEVELOPMENT/RAMP | [7 empty] | CONSULTANCY
Budgetary Year: 2012 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/Evaluation of Financial Proposals | Submission Eval Report (T) (F) | Negotiations if any (N) | Plan vs. Actual | No-Objection Date | FEC Approval | Contract Amount in Naira | Contract offer | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | Plan | 2-3wks | 1-2wks | 2 wks | 1wk |  | 1-2wks | Plan | 2wks | 2-4wks | 2wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 1-2wks | 2wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
List of Contracts
Design, Preparation of Bidding Documents and the supervision of the Rehabilitation of 7Adoka – Umogidi – Opaha Rd, Otukpo LGA, Benue State (Extension) (Double surface dressing). | CQS | Lumpsum | 10000000 | MTB | Plan | 31st May-14th June,2012 | 14th -18th June, 2012 | Not Required | Not Required | Not Required | Not required | Plan | 18th June- 2nd July, 2012 | 18th June- 2nd July, 2012 | 2nd-9th Jul,2012 | 9th - 13th Jul,2012 | 13th-20th July,2012 | 20th - 25th July,2012 | Not Required | Plan | Not Required | Not required | 10000000 | 25th -31st July, 2012 | 1st-7th Aug,2012 | Plan | Not Required | 1st-14th Aug, 2012 | 14th-21st Aug2012 | 10000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Design, Preparation of Bidding Documents and the supervision of the Rehabilitation of 7km Igunmale – Ulayi – Jigban Road, Ado LGA, Benue State (Extension) (Double surface dressing). | CQS | Lumpsum | 10000000 | MTB | Plan | 31st May-14th June,2012 | 14th -18th June, 2012 | Not Required | Not Required | Not Required | Not required | Plan | 18th July- 2nd Aug, 2012 | 18th July- 2nd Aug, 2012 | 2nd-9th Jul,2012 | 9th - 13th Jul,2012 | 13th-20th July,2012 | 20th - 25th July,2012 | Not Required | Plan | Not Required | Not required | 10000000 | 25th -31st July, 2012 | 1st-7th Aug,2012 | Plan | Not Required | 1st-14th Aug, 2012 | 14th-21st Aug2012 | 10000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Design, Preparation of Bidding Documents and the supervision of the Rehabilitation of 8km Ugbokpo – Edikwu – Opaha Rd, Apa LGA, Benue State (Extension) (Double Surface dressing). | CQS | Lumpsum | 12500000 | MTB | Plan | 31st May-14th June,2012 | 14th -18th June, 2012 | Not Required | Not Required | Not Required | Not required | Plan | 18th July- 2nd Aug, 2012 | 18th July- 2nd Aug, 2012 | 2nd-9th Jul,2012 | 9th - 13th Jul,2012 | 13th-20th July,2012 | 20th - 25th July,2012 | Not Required | Plan | Not Required | Not required | 12500000 | 25th -31st July, 2012 | 1st-7th Aug,2012 | Plan | Not Required | 1st-14th Aug, 2012 | 14th-21st Aug2012 | 12500000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Design, Preparation of Bidding Documents and the supervision of the Rehabilitation of 13km Ochobo – Agadagba – Onyagede Rd, Ohimini LGA, Benue State (Extension) (Double Surface dressing). | CQS | Lumpsum | 20000000 | MTB | Plan | 31st May-14th June,2012 | 14th -18th June, 2012 | Not Required | Not Required | Not Required | Not required | Plan | 18th July- 2nd Aug, 2012 | 18th July- 2nd Aug, 2012 | 2nd-9th Jul,2012 | 9th - 13th Jul,2012 | 13th-20th July,2012 | 20th - 25th July,2012 | Not Required | Plan | Not Required | Not required | 20000000 | 25th -31st July, 2012 | 1st-7th Aug,2012 | Plan | Not Required | 1st-14th Aug, 2012 | 14th-21st Aug2012 | 20000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Design, Preparation of Bidding Documents and the supervision of the Rehabilitation of 6km Ubokpo - Ijantle - Okobi Road, Apa LGA, Benue State (Double Surface dressing) | CQS | Lumpsum | 8500000 | MTB | Plan | 31st May-14th June,2012 | 14th -18th June, 2012 | Not Required | Not Required | Not Required | Not required | Plan | 18th July- 2nd Aug, 2012 | 18th July- 2nd Aug, 2012 | 2nd-9th Jul,2012 | 9th - 13th Jul,2012 | 13th-20th July,2012 | 20th - 25th July,2012 | Not Required | Plan | Not Required | Not required | 8500000 | 25th -31st July, 2012 | 1st-7th Aug,2012 | Plan | Not Required | 1st-14th Aug, 2012 | 14th-21st Aug2012 | 8500000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Design, Preparation of Bidding Documents and the supervision of the Rehabilitation of 5km Ogoli - Ipolo - Ipum/Cho Road, Otukpo LGA, Benue State (Double Surface dressing) | CQS | Lumpsum | 7000000 | MTB | Plan | 31st May-14th June,2012 | 14th -18th June, 2012 | Not Required | Not Required | Not Required | Not required | Plan | 18th July- 2nd Aug, 2012 | 18th July- 2nd Aug, 2012 | 2nd-9th Jul,2012 | 9th - 13th Jul,2012 | 13th-20th July,2012 | 20th - 25th July,2012 | Not Required | Plan | Not Required | Not required | 7000000 | 25th -31st July, 2012 | 1st-7th Aug,2012 | Plan | Not Required | 1st-14th Aug, 2012 | 14th-21st Aug2012 | 7000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Design, Preparation of Bidding Documents and the supervision of the Rehabilitation of 6km Awulema - Ajegaji - Ogene - Alaglanu Road, Ohimini LGA, Benue State (Double Surface dressing). | CQS | Lumpsum | 8500000 | MTB | Plan | 31st May-14th June,2012 | 14th -21st June, 2012 | Not Required | Not Required | Not Required | Not required | Plan | 18th July- 2nd Aug, 2012 | 18th July- 2nd Aug, 2012 | 2nd-9th Jul,2012 | 9th - 13th Jul,2012 | 13th-20th July,2012 | 20th - 25th July,2012 | Not Required | Plan | Not Required | Not required | 8500000 | 25th -31st July, 2012 | 1st-7th Aug,2012 | Plan | Not Required | 1st-14th Aug, 2012 | 14th-21st Aug2012 | 8500000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Design, Preparation of Bidding Documents and the supervision of the Rehabilitation of 6km Efoyo - Ikpogo - Omadewu - Ebya Road, Okpokwu LGA, Benue State (Double Surface dressing). | CQS | Lumpsum | 8500000 | MTB | Plan | 31st May-14th June,2012 | 14th -21st June, 2012 | Not Required | Not Required | Not Required | Not required | Plan | 18th July- 2nd Aug, 2012 | 18th July- 2nd Aug, 2012 | 2nd-9th Jul,2012 | 9th - 13th Jul,2012 | 13th-20th July,2012 | 20th - 25th July,2012 | Not Required | Plan | Not Required | Not required | 8500000 | 25th -31st July, 2012 | 1st-7th Aug,2012 | Plan | Not Required | 1st-14th Aug, 2012 | 14th-21st Aug2012 | 8500000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Design, Preparation of Bidding Documents and the supervision of the Rehabilitation of 6km Adum East - Adiko - Okwutungbe, Obi LGA, Benue State (Double Surface dressing). | CQS | Lumpsum | 8500000 | MTB | Plan | 31st May-14th June,2012 | 14th -21st June, 2012 | Not Required | Not Required | Not Required | Not required | Plan | 18th July- 2nd Aug, 2012 | 18th July- 2nd Aug, 2012 | 2nd-9th Jul,2012 | 9th - 13th Jul,2012 | 13th-20th July,2012 | 20th - 25th July,2012 | Not Required | Plan | Not Required | Not required | 8500000 | 25th -31st July, 2012 | 1st-7th Aug,2012 | Plan | Not Required | 1st-14th Aug, 2012 | 14th-21st Aug2012 | 8500000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Design, Preparation of Bidding Documents and the supervision of the Rehabilitation of 6km Otada - Emichi - Okpamaju - Odudaje Road, Otukpo LGA, Benue State (Double Surface dressing). | CQS | Lumpsum | 9000000 | MTB | Plan | 31st May-14th June,2012 | 14th -21st June, 2012 | Not Required | Not Required | Not Required | Not required | Plan | 18th July- 2nd Aug, 2012 | 18th July- 2nd Aug, 2012 | 2nd-9th Jul,2012 | 9th - 13th Jul,2012 | 13th-20th July,2012 | 20th - 25th July,2012 | Not Required | Plan | Not Required | Not required | 9000000 | 25th -31st July, 2012 | 1st-7th Aug,2012 | Plan | Not Required | 1st-14th Aug, 2012 | 14th-21st Aug2012 | 9000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Design, Preparation of Bidding Documents and the supervision of the Rehabilitation of 6km Otobi - Ujume - Edumoga - Ohuma Road, Oju LGA, Benue State (Double Surface dressing). | CQS | Lumpsum | 8500000 | MTB | Plan | 31st May-14th June,2012 | 14th -21st June, 2012 | Not Required | Not Required | Not Required | Not required | Plan | 18th July- 2nd Aug, 2012 | 18th July- 2nd Aug, 2012 | 2nd-9th Jul,2012 | 9th - 13th Jul,2012 | 13th-20th July,2012 | 20th - 25th July,2012 | Not Required | Plan | Not Required | Not required | 8500000 | 25th -31st July, 2012 | 1st-7th Aug,2012 | Plan | Not Required | 1st-14th Aug, 2012 | 14th-21st Aug2012 | 8500000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Design, Preparation of Bidding Documents and the supervision of the Rehabilitation of 6km Oju - Ujume - Edumoga - Ohuma, Oju LGA, Benue State (Double Surface dressing). | CQS | Lumpsum | 8500000 | MTB | Plan | 31st May-14th June,2012 | 14th -21st June, 2012 | Not Required | Not Required | Not Required | Not required | Plan | 18th July- 2nd Aug, 2012 | 18th July- 2nd Aug, 2012 | 2nd-9th Jul,2012 | 9th - 13th Jul,2012 | 13th-20th July,2012 | 20th - 25th July,2012 | Not Required | Plan | Not Required | Not required | 8500000 | 25th -31st July, 2012 | 1st-7th Aug,2012 | Plan | Not Required | 1st-14th Aug, 2012 | 14th-21st Aug2012 | 8500000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Design, Preparation of Bidding Documents and the supervision of the Rehabilitation of 4km Onobi - Icho - Ajobe - Otukpo, Otukpo LGA, Benue State (Double Surface dressing). | CQS | Lumpsum | 6000000 | MTB | Plan | 31st May-14th June,2012 | 14th -21st June, 2012 | Not Required | Not Required | Not Required | Not required | Plan | 18th July- 2nd Aug, 2012 | 18th July- 2nd Aug, 2012 | 2nd-9th Jul,2012 | 9th - 13th Jul,2012 | 13th-20th July,2012 | 20th - 25th July,2012 | Not Required | Plan | Not Required | Not required | 6000000 | 25th -31st July, 2012 | 1st-7th Aug,2012 | Plan | Not Required | 1st-14th Aug, 2012 | 14th-21st Aug2012 | 6000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Design, Preparation of Bidding Documents and the supervision of the Rehabilitation of 10km Rim Junction - Jol, Riyom, Plateau State (Double Surface dressing). | CQS | Lumpsum | 15000000 | MTB | Plan | 31st May-14th June,2012 | 14th -21st June, 2012 | Not Required | Not Required | Not Required | Not required | Plan | 18th July- 2nd Aug, 2012 | 18th July- 2nd Aug, 2012 | 2nd-9th Jul,2012 | 9th - 13th Jul,2012 | 13th-20th July,2012 | 20th - 25th July,2012 | Not Required | Plan | Not Required | Not required | 15000000 | 25th -31st July, 2012 | 1st-7th Aug,2012 | Plan | Not Required | 1st-14th Aug, 2012 | 14th-21st Aug2012 | 15000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Design, Preparation of Bidding Documents and the supervision of the Rehabilitation of 3km Road Network at Apata Kekere Village in Oke Orogun that links Ojoo - Iwo Road Express way, Akinyele, Oyo State (Double Surface dressing). | CQS | Lumpsum | 4500000 | PS | Plan | 31st May-14th June,2012 | 14th -21st June, 2012 | Not Required | Not Required | Not Required | Not required | Plan | 18th July- 2nd Aug, 2012 | 18th July- 2nd Aug, 2012 | 2nd-9th Jul,2012 | 9th - 13th Jul,2012 | 13th-20th July,2012 | 20th - 25th July,2012 | Not Required | Plan | Not Required | Not required | 4500000 | 25th -31st July, 2012 | 1st-7th Aug,2012 | Plan | Not Required | 1st-14th Aug, 2012 | 14th-21st Aug2012 | 4500000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Design, Preparation of Bidding Documents and the supervision of the Rehabilitation of 3km Agba - Esha, Igweledeoha/Ndeoke - Ededeagu Road, Ebonyi & Ohaukwu, Ebonyi State (Double Surface dressing) | CQS | Lumpsum | 5000000 | MTB | Plan | 31st May-14th June,2012 | 14th -21st June, 2012 | Not Required | Not Required | Not Required | Not required | Plan | 18th July- 2nd Aug, 2012 | 18th July- 2nd Aug, 2012 | 2nd-9th Jul,2012 | 9th - 13th Jul,2012 | 13th-20th July,2012 | 20th - 25th July,2012 | Not Required | Plan | Not Required | Not required | 5000000 | 25th -31st July, 2012 | 1st-7th Aug,2012 | Plan | Not Required | 1st-14th Aug, 2012 | 14th-21st Aug2012 | 5000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Design, Preparation of Bidding Documents and the supervision of the Rehabilitation of 1km Ikun Ekiti, Moba LGA, Ekiti State (Double Surface dressing). | CQS | Lumpsum | 2000000 | PS | Plan | 31st May-14th June,2012 | 14th -21st June, 2012 | Not Required | Not Required | Not Required | Not required | Plan | 18th July- 2nd Aug, 2012 | 18th July- 2nd Aug, 2012 | 2nd-9th Jul,2012 | 9th - 13th Jul,2012 | 13th-20th July,2012 | 20th - 25th July,2012 | Not Required | Plan | Not Required | Not required | 2000000 | 25th -31st July, 2012 | 1st-7th Aug,2012 | Plan | Not Required | 1st-14th Aug, 2012 | 14th-21st Aug2012 | 2000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Actual
Design, Preparation of Bidding Documents and the supervision of the Rehabilitation of 15km Access Road to each of the six staple crop processing zones in the Country (Double Surface dressing). | CQS | Lumpsum | 82000000 | MTB | Plan | 31st May-14th June,2012 | 14th -21st June, 2012 | Not Required | Not Required | Not Required | Not required | Plan | 18th July- 2nd Aug, 2012 | 18th July- 2nd Aug, 2012 | 2nd-9th Jul,2012 | 9th - 13th Jul,2012 | 13th-20th July,2012 | 20th - 25th July,2012 | Not Required | Plan | Not Required | Not required | 82000000 | 25th -31st July, 2012 | 1st-7th Aug,2012 | Plan | Not Required | 1st-14th Aug, 2012 | 14th-21st Aug2012 | 82000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Design, Preparation of Bidding Documents and the supervision of the Rehabilitation of 200km existing Rural Feeder Roads (Earth Roads) | CQS | Lumpsum | 60000000 | MTB | Plan | 31st May-14th June,2012 | 14th -21st June, 2012 | Not Required | Not Required | Not Required | Not required | Plan | 18th July- 2nd Aug, 2012 | 18th July- 2nd Aug, 2012 | 2nd-9th Jul,2012 | 9th - 13th Jul,2012 | 13th-20th July,2012 | 20th - 25th July,2012 | Not Required | Plan | Not Required | Not required | 60000000 | 25th -31st July, 2012 | 1st-7th Aug,2012 | Plan | Not Required | 1st-14th Aug, 2012 | 14th-21st Aug2012 | 60000000
Actual
Total Cost |  |  | 349,500,000.00 | [8 empty] | Actual | [7 empty] | Actual |  |  | 349,500,000.00 |  |  | Actual |  |  |  | 349,500,000.00
FOOTNOTE
The Locations of some of the Access Roads to the staple crop processing zones and the Feeder Roads are yet to be determined

## LIVESTOCK Goods
Ministry/Department/Agency: | FEDERAL DEPARTMENT OF LIVESTOCK | [5 empty] | THE TIME LINE IS TO BE COMPARED WITH THE COUNCILS APPROVAL
Budgetary Year: 2014 | 2014 | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: | DR. G.M. MSHELBWALA | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Plan vs. Actual | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Supply of feeds requirement for targeted dairy animals @2kg/cow/day in the 11 implementing States: Nasarawa, Niger, Oyo, Kaduna, Adamawa, FCT, Kano, Kwara, Taraba, Plateau and Ekiti States (6 bags of 50kg/farmer of dairy feeds to 4,400 dairy farmers) | A.1 | A.1.1 | 46200000 | GES | N/A | MTB | Plan | Jan,14 - Jan,25 | Jan, 25 - Feb, 8th | Feb,18 | Feb,18 - March, 11th | March,25 | April, 8 | N/A | Plan | 46200000 | N/A | April, 15 | April, 29 | May, 2014 | June,2014 | August,2014
[7 empty] | Actual | [7 empty] | Actual
Supply of Salt lick for the targeted dairy animals in 11 implementing States: Nasarawa, Niger, Oyo, Kaduna, Adamawa, FCT, Kano, Kwara, Taraba, Plateau and Ekiti States (1block of 10kg/ farmer to 4,400 dairy farmers) | A.1 | A.1.2 | 3080000 | GES | N/A | MTB | Plan | Jan,14 - Jan,25 | Jan, 25 - Feb, 8th | Feb,18 | Feb,18 - March, 11th | March,25 | April, 8 | N/A | Plan | 3080000 | N/A | April, 15 | April, 29 | May, 2014 | June, 2014 | August,2014
[7 empty] | Actual | [7 empty] | Actual
Provision of 500 units of Brahma Breeding semen, | B.1 | B.1.1 | 6500000 | DP | N/A | PS | Plan | Jan,14 - Jan,25 | Jan, 25 - Feb, 8th | Feb,18 | Feb,18 - March, 11th | March,25 | April, 8 | N/A | Plan | 6500000 | N/A | April, 15 | April, 29 | May, 2014 | June,2014 | August,2014
[7 empty] | Actual | [7 empty] | Actual
Provision of 46,800(25kg) bags of fattening concentrate and 3,600 Blocks of Salt licks to 1,800 beef farmers in 18 States | B.1 | B.1.5 | 51300000 | GES | N/A | MTB | Plan | Jan,14 - Jan,25 | Jan, 25 - Feb, 8th | Feb,18 | Feb,18 - March, 11th | March,25 | April, 8 | N/A | Plan | 51300000 | N/A | April, 15 | April, 29 | May, 2014 | June,2014 | August,2014
[7 empty] | Actual | [7 empty] | Actual
Provision of feeds and Salt Block to 4 Cattle Breeding Centres | B.1 | B.1.6 | 6000000 | DP | N/A | PS | Plan | Jan,14 - Jan,25 | Jan, 25 - Feb, 8th | Feb,18 | Feb,18 - March, 11th | March,25 | April, 8 | N/A | Plan | 6000000 | N/A | April, 15 | April, 29 | May, 2014 | June,2014 | August,2014
[7 empty] | Actual | [7 empty] | Actual
Provision of 18 zero fly screens to 18 States under GES @100% | B.1 | B.1.7 | 6270000 | DP | N/A | PS | Plan | Jan,14 - Jan,25 | Jan, 25 - Feb, 8th | Feb,18 | Feb,18 - March, 11th | March,25 | April, 8 | N/A | Plan | 6270000 | N/A | April, 15 | April, 29 | May, 2014 | June,2014 | August,2014
[7 empty] | Actual | [7 empty] | Actual
 Provision of 29,900 (25kg) bags of concentrate ruminant feeds/dewormer/ acaricide and salt block for 5,980 sheep & goats farmers in 30 States | C.1 | C.1.1 | 34684000 | GES | N/A | MTB | Plan | Jan,14 - Jan,25 | Jan, 25 - Feb, 8th | Feb,18 | Feb,18 - March, 11th | March,25 | April, 8 | N/A | Plan | 34684000 | N/A | April, 15 | April, 29 | May, 2014 | June,2014 | August,2014
[7 empty] | Actual | [7 empty] | Actual
 Provision of feeds/ water reticulation for 4 sheep & goats multiplication centres (Ladanawa, Tuma, Shaki & Zugu) | C.1 | C.1.6 | 4600000 | DP | N/A | PS | Plan | Jan,14 - Jan,25 | Jan, 25 - Feb, 8th | Feb,18 | Feb,18 - March, 11th | March,25 | April, 8 | N/A | Plan | 4600000 | N/A | April, 15 | April, 29 | May, 2014 | June,2014 | August,2014
[7 empty] | Actual | [7 empty] | Actual
 Provision of 1,200 pure breeds of pig to 400 pig farmers in 8 States: Ogun, Benue, Anambra, Nasarawa, Delta, Imo and Osun State | D.1 | D.1.4 | 12000000 | GES | N/A | MTB | Plan | Jan,14 - Jan,25 | Jan, 25 - Feb, 8th | Feb,18 | Feb,18 - March, 11th | March,25 | April, 8 | N/A | Plan | 12000000 | N/A | April, 15 | April, 29 | May, 2014 | June.2014 | August,2014
[7 empty] | Actual | [7 empty] | Actual
Provision of 20 bags (25kg) pig grower/gestation feeds and 5ml of disinfectant to 400 pig farmers as GES | D. 1 | D.1.5 | 11000000 | GES | NA | MTB | Plan | Jan,14 - Jan,25 | Jan, 25 - Feb, 8th | Feb,18 | Feb,18 - March, 11th | March,25 | April, 8 | NA | Plan | 11000000 | NA | April, 15 | April, 29 | May, 2014 | June,2014 | August,2014
[7 empty] | Actual | [7 empty] | Actual
Supply of feed/water reticulation at 2 pig multiplication centres | D. 1 | D.1.7 | 4000000 | DP | NA | PS | Plan | Jan,14 - Jan,25 | Jan, 25 - Feb, 8th | Feb,18 | Feb,18 - March, 11th | March,25 | April, 8 | NA | Plan | 4000000 | NA | April, 15 | April, 29 | May, 2014 | June,2014 | August,2014
[7 empty] | Actual | [7 empty] | Actual
Provision of 30,000 bags (50kg) of industrial salts to 6,000 skin buyers in 12 States: SO, ZF, KT, KN, BA, JG, NA, KB, GB, AD, KD & TR | E.1 | E.1.1 | 42000000 | GES | N/A | MTB | Actual | Jan,14 - Jan,25 | Jan, 25 - Feb, 8th | Feb,18 | Feb,18 - March, 11th | March,25 | April, 8 | N/A | Plan | 42000000 | NA | April, 15 | April, 29 | May, 2014 | June,2014 | August,2014
[7 empty] | Actual | [7 empty] | Actual
 Provision of 270,000 Shika Brown DOC to 2,700 poultry farmers | F.1 | F.1.1 | 32400000 | GES | NA | MTB | Plan | Jan,14 - Jan,25 | Jan, 25 - Feb, 8th | Feb,18 | Feb,18 - March, 11th | March,25 | April, 8 |  | Plan | 32400000 | NA | April, 15 | April, 29 | May, 2014 | June,2014 | August,2014
[7 empty] | Actual | [7 empty] | Actual
Provision of 202, 500kg of poultry feeds to 2,700 poultry farmers | F.1 | F.1.2 | 20250000 | GES | N/A | MTB | Plan | Jan,14 - Jan,25 | Jan, 25 - Feb, 8th | Feb,18 | Feb,18 - March, 11th | March,25 | April, 8 | N/A | Plan | 20250000 | N/A | April, 15 | April, 29 | May, 2014 | June,2014 | August,2014
[7 empty] | Actual | [7 empty] | Actual
Provision of 2,080,000 Doses of NCDV to 5,200 poultry farmers | F.1 | F.1.3 | 16200000 | GES | NA | MTB | Plan | Jan,14 - Jan,25 | Jan, 25 - Feb, 8th | Feb,18 | Feb,18 - March, 11th | March,25 | April, 8 | NA | Plan | 16200000 | NA | April, 15 | April, 29 | May, 2014 | June,2014 | August,2014
[7 empty] | Actual | [7 empty] | Actual
Provision of 540,000 Doses of poultry drugs to 2,700 poultry farmers | F.1 | F.1.4 | 8100000 | GES | NA | MTB | Plan | Jan,14 - Jan,25 | Jan, 25 - Feb, 8th | Feb,18 | Feb,18 - March, 11th | March,25 | April, 8 | NA | Plan | 8100000 | NA | April, 15 | April, 29 | May, 2014 | June,2014 | August,2014
[7 empty] | Actual | [7 empty] | Actual
Procurement of 1 Operational Vehicles (Toyota Hillux) (Animal Health) | G.1 | G.1.2 | 6500000 | DP | NA | MTB | Plan | Jan,14 - Jan,25 | Jan, 25 - Feb, 8th | Feb,18 | Feb,18 - March, 11th | March,25 | April, 8 | NA | Plan | 6500000 | NA | April, 15 | April, 29 | May, 2014 | June,2014 | August,2014
[7 empty] | Actual | [7 empty] | Actual
Procurement of 3 Hilux (Petrol Engine) to facilitate task force and coordinate field activity (Halal Value Chain) | J.1 | J.1.1 | 20000000 | DP | NA | MTB | Plan | Jan,14 - Jan,25 | Jan, 25 - Feb, 8th | Feb,18 | Feb,18 - March, 11th | March,25 | April, 8 | NA | Plan | 20000000 | NA | April, 15 | April, 29 | May, 2014 | June,2014 | August,2014
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  |  | 331084000 | [12 empty] | 331084000

## LIVESTOCK Works
Ministry/Department/Agency: | FEDERAL DEPARTMENT OF LIVESTOCK
Budgetary Year: 2014 | 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: | DR. G.M. MSHELBWALA | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Upgrading/Maintenance of Pesticide laboratory and School to operational state | H.1 | H.1.17 | Bill of Quantities | NCB | 20000000 | NA | MTB | Plan | Jan,14 -Jan, 25 | Jan,25 - Feb,8 | Feb, 18 | Feb, 18 -March,11 | March,25 | April, 8 | April, 11 | Plan | 20000000 | NA | April, 15 | April, 29 | May,2014 | June,2014 | August,2014 | 20000000
[8 empty] | Actual | [7 empty] | Actual
Construction of 2no. Micro Earthdam at Lata Grazing Reserve, Kwara State | I.1 | I.1.1 | Bill of Quantities | Direct Labour | 31071000 | NA | MTB | Plan | Jan,14 -Jan, 25 | Jan,25 - Feb,8 | Feb, 18 | Feb, 18 -March,11 | March,25 | April, 8 | April, 11 | Plan | 31071000 | NA | April, 15 | April, 29 | May,2014 | June,2014 | August,2014 | 31071000
[8 empty] | Actual | [7 empty] | Actual
Construction of 3no. Solar Boreholes at Wasimi Grazing Reserve, Oyo State | I.1 | I.1.2 | Bill of Quantities | Direct Labour | 24200000 | NA | MTB | Plan | Jan,14 -Jan, 25 | Jan,25 - Feb,8 | Feb, 18 | Feb, 18 -March,11 | March,25 | April, 8 | April, 11 | Plan | 24200000 | NA | April, 15 | April, 29 | May,2014 | June,2014 | August,2014 | 24200000
[8 empty] | Actual | [7 empty] | Actual
Construction of Cattle Resting Point consisting of Admin block, Boreholes, Vet Clinc, Milk Collection Centre at Keana, Nasarawa State | I.1 | I.1.6 | Biil of Quantities | NCB | 31000000 | NA | MTB | Plan | Jan,14 -Jan, 25 | Jan,25 - Feb,8 | Feb, 18 | Feb, 18 -March,11 | March,25 | April, 8 | April, 11 | Plan | 31000000 | NA | April, 15 | April, 29 | May,2014 | June,2014 | August,2014 | 31000000
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 106271000 | [11 empty] | 106271000 | [6 empty] | 106271000
Fill gray cells only!

## LIVESTOCK Consultants
Ministry/Department/Agency: | FEDERAL DEPARTMENT OF LIVESTOCK
Budgetary Year: 2014 | 2014 | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: | DR. G.M. MSHELBWALA | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | Plan vs. Actual | No-objection Date | FEC Approval | Contract Amount in Naira | Contract Offer | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | Plan | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | Plan | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 1- 2 wk | 2 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
List of Contracts
 Consultancy Services to conduct Artificial Insemination and Cross Breeding ( Pastoral and Community AI of 4,000 cattle in 5 States): FCT, Nasarawa, Niger, Kwara & Oyo State | SSS | lumpsum | 15800000 | NCB | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 15800000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 15800000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
 Development Development Programme (DDP) Collaboration with WAMCO | SSS | lumpsum | 4100000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 4100000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 4100000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
 Capacity Building for all stakeholders (farmers groups, Inseminators, extension workers and policy makers) on dairy production and management | SSS | lumpsum | 7500000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 7500000 | April,26 | May,2014 | Plan | June, 2014 | August.2014 | Sept.2014 | 7500000
[5 empty] | Actual |  | Jan,25 - Feb, 8 |  |  |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
Farmers mobilization and Clustering around the MCCs at Oyo, Kaduna, Kano & FCT | SSS | lumpsum | 6060000 | PS |  |  | Jan,25 - Feb, 8 | Feb, 18 | Feb, 18 - March, 11 | March,13 | NA |  | NA | March, 25 | March, 29 | March, 25 - April , 2 | March, 25 - April , 2 | April, 19 | NA |  | NA | NA | 6060000 | April, 26 | May, 2014 | Plan | June, 2014 | August, 2014 | Sept, 2014 | 6060000
Actual
Measurement of Herd Productivity in the Field | SSS | lumpsum | 8600000 | PS |  |  | Jan,25 - Feb, 8 | Feb, 18 | Feb, 18 - March, 11 | March,14 | NA |  | NA | March, 25 | March, 29 | March, 25 - April , 2 | March, 25 - April , 2 | April, 19 | NA |  | NA | NA | 8600000 | April, 26 | May,2014 | Plan | June, 2014 | August, 2014 | Sept, 2014 | 8600000
Actual
 Linkages of local dairy farmers group to private processors and marketers | SSS | lumpsum | 3170000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,14 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 3170000 | April,26 | May,2014 | Plan | June, 2014 | August, 2014 | Sept.2014 | 3170000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
 Development of Dairy Association of Nigeria/ meeting with CEO of Dairy Service Providers | In- House Activity | lumpsum | 3740000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,14 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 3740000 | April,26 | May,2014 | Plan | June, 2014 | August, 2014 | Sept.2014 | 3740000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
 Linkage of 1800 farmers with Halal Processors under SmallHolders Fattening Scheme (SHFS) | In- House Activity | lumpsum | 4700000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 4700000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 4700000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Sensitization and Supervision of Projects | In- House Activity | lumpsum | 5700000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 5700000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 5700000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Study tour to Bostwana, Desk Officer and 3 Other | In- House Activity | lumpsum | 4800000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 4800000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 4800000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
On- farm demonstration of feeds and feeding to 18 Trainers and Cattle Management in the 18 States where cattle has comparative advantage | In- House Activity | lumpsum | 4560000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 4560000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 4560000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Collaborative visits to DFID/GEMS, NAPRI, FUNAAB, Private Farmers & M/E of field activities in 30 States | In- House Activity | lumpsum | 2205000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 2205000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 2205000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Sensitization and Town Hall meetings in Sheep and Goats Stakeholders in 20 States | In- House Activity | lumpsum | 4111000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 4111000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 4111000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Training of 48 State Personnels and Sheep and Goats 80 farmers | In- House Activity | lumpsum | 4000000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 4000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 4000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Study tour to South Africa or Morocco by Team Leaders, Desk Officers and Five Others | In- House Activity | lumpsum | 4500000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 4500000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 4500000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Baseline Study of Stakeholders and Existing infrastructures in 6 States ( Anambra and Nasarawa, Delta, Akwa - Ibom, Imo and Osun States | In-House Activity | lumpsum | 3000000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 3000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 3000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Registration of farmers in 8 States: Ogun, Benue, Anambra, Nasarawa, Delta, Akwa - Ibom, Imo and Osun State | In- House Activity | lumpsum | 3900000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 3900000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 3900000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Sensitization of pig farmers, facilities, input suppliers and animal health service providers | In- House Activity | lumpsum | 1600000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 1600000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 1600000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Training the trainers of 34 pigs farmers at 2 locations | In- House Activity | lumpsum | 3150000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 3150000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 3150000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Field and Operational visits in 8 States | In- House Activity | lumpsum | 3000000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 3000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 3000000
[5 empty] | Actual | Jan. 14 - Jan. 25 | [5 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Study Tour to Netherlands | In- House Activity | lumpsum | 3250000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 3250000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 3250000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Capacity building for Stakeholders (butchers, flayers, abattoir attendants and trades) in 12 States: SO, ZF, KT, KN, BA, JG, NA, KB, GB, AD, KD & TR | In- House Activity | lumpsum | 6000000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 6000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 6000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Registration of skin collectors, leather works and dealers in 12 States: SO, ZF, KT, KN, BA, JG, NA, KB, GB, AD, KD & TR | In- House Activity | lumpsum | 3140000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 3140000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 3140000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Support for the establishment of 2 collection centres in 2 locations | In- House Activity | lumpsum | 4500000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 4500000 | April,26 | May,2013 | Plan | June, 2014 | August. 2014 | Sept.2014 | 4500000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Pre -roll out Sensitisation and training of Skin Buyers in 6 new States on skin preservation using Industrial Salt | In- House Activity | lumpsum | 4500000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 4500000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 4500000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Support for popularisation of made in Nigeria leather | In- House Activity | lumpsum | 4090000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 4090000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 4090000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Data Collection and Field Verification Visits | In- House Activity | lumpsum | 2000000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 2000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 2000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Linkage of Skin Buyers Association to Tanneries and local skin processors as well as other stakeholders in the Industry | In- House Activity | lumpsum | 1770000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 1770000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 1770000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Pilot Study on hides and skin standardisation and grading in Nigeria | In- House Activity | lumpsum | 3000000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | N/A | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 3000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 3000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Market testing of SBL to determine its acceptability by poultry farmers | In- House Activity | lumpsum | 2000000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 2000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 2000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Stakeholders calibration of standards for poultry industry | In- House Activity | lumpsum | 3000000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 3000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 3000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Reassessment of FGCG, BDG, VCBM & RCBM as alternatives to maize and soya beans | In- House Activity | lumpsum | 2000000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 2000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 2000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Training of stakeholders in the auditing of farms and hatcheries and implementation of industry standard | In-House Activity | lumpsum | 5000000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 5000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 5000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Advocacy/ Sensitization visits to participating States | In - House Activity | lumpsum | 2000000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 2000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 2000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Supervision of field activities/ Attendance of National and International meetings | In - House Activity | lumpsum | 9050000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 9050000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 9050000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Technical Sessions/ Sensitization workshop on protocol for Import/Export certification of Animals and Animal Products as well as single window platform for stakeholders + Field Officers in 36 States and FCT | In - House Activity | lumpsum | 15800000 | MTB | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 15800000 | April,26 | May,2013 | Plan | June, 2014 | August. 2014 | Sept.2014 | 15800000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Monitoring of CBPP and PPR vaccination exercise nationwide + Survey of Rinderpest viral containing materials | In-House Activity | lumpsum | 5000000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 5000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 5000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Study tours to Department of Agriculture (US, and South Africa) to understudy their import/export producedures | In-House Activity | lumpsum | 4000000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 4000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 4000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Provision for Trace back and forward of outbreaks of Transboundary Animal Disease (TADs) | In- House Activity | lumpsum | 5200000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 5200000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 5200000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Risk Assessment and Disease Investigation Skills Enhancement for Epidemiology | In- House Activity | lumpsum | 5000000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | NA | Plan | N/A | N/A | 5000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 5000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Risk based targeted surveillance of H7N9 virus in domestic/wildbirds at LBMs in 9 States: Kano, Kaduna, Lagos, Oyo, Ogun, Enugu, Plateau, Niger and Jigawa State/ Influenza A in Pigs | In- House Activity | lumpsum | 7300000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 7300000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 7300000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Strengthening of disease Surveillance network/Disease reporting and consultative meeting with Directors of Veterinary Services in 36 States + FCT | In- House Activity | lumpsum | 7200000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 7200000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 7200000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Preparation of Contigency Plan and Control of Peste des Petits Ruminants (PPR) | In- House Activity | lumpsum | 5800000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 5800000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 5800000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Support to compliment the pilot project on data capturing methodology and instrument by the AU-IBAR VetGov program in 6 States | In- House Activity | lumpsum | 8000000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 8000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 8000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Capacity building/meeting for the Livestock Policy Hub (LPH) members | In- House Activity | lumpsum | 3000000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 3000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 3000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Advocacy/Animal Disease Communication Surveillance | In- House Activity | lumpsum | 5000000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 5000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 5000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Wildlife Disease surveillance in 10 States: Yobe, Adamawa, Bauchi, Kaduna, Kano, Taraba, Ogun, Cross River and Plateau States | In- House Activity | lumpsum | 5000000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 5000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 5000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Programme and Training of FELTP Candidates on field epidemiology with Federal Ministry of Health and USA'S Centre for Disease control Department to support 4nos. Staff | In- House Activity | lumpsum | 10000000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 10000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 10000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Participation at statutory international meetings of OIE, ECOWAS, AU/IBAR as well as contribution to OIE | In- House Activity | lumpsum | 12000000 | MTB | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | NA | Plan | N/A | N/A | 12000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 12000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Preparation of Guildeline/ Draft document for Animal Welfare in Nigeria | In- House Activity | lumpsum | 3000000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 3000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 3000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Collaboration with State on abattoir and meat hygiene and training on HACCP guidelines | In- House Activity | lumpsum | 8700000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | N/A | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 8700000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 8700000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Study to determine the prevelence of Bovine Tuberculosis at 6 selected municipal abattoirs nationwide | In- House Activity | lumpsum | 8500000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 8500000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 8500000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Baseline Survey of the Veterinary infrastructures in the States and FCT | In- House Activity | lumpsum | 15000000 | MTB | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 15000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 15000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Consultancy Services on the site selection and Architectural design of prototype FVMC | In- House Activity | lumpsum | 10000000 | MTB |  | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A |  | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A |  | N/A | N/A | 10000000 | April,26 | May,2014 |  | June, 2014 | August, 2014 | Sept.2014 | 10000000
Tsetse fly control Survey, Control and Mapping | In- House Activity | lumpsum | 15000000 | MTB | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 15000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 15000000
[5 empty] | Actual | Jan. 14 - Jan. 25 | [5 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Hosting and Participation at NNJC meetings | In- House Activity | lumpsum | 12000000 | MTB | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 12000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 12000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Participation at International meetings (SAICM, PATTEC, WAAPP) | In- House Activity | lumpsum | 3000000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 3000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 3000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Field Visits and Monitoring | In- House Activity | lumpsum | 5000000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 5000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 5000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Conduct of grasshopper egg- pod survey in selected states representative of geographical zones | In- House Activity | lumpsum | 27500000 | MTB | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 27500000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 27500000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Recruitment of a Consultant for the designs, preparation of bills and technical supervision of the bores and resting points | In-House Activity | lumpsum | 10000000 | MTB | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A |  | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A |  | N/A | N/A | 10000000 | April,26 | May,2014 | Plan | June, 2014 | August,2014 | Sept.2014 | 10000000
Actual
Monitoring and Evaluation of Projects | In-House Activity | lumpsum | 3859000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A |  | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A |  | N/A | N/A | 3859000 | April,26 | May,2014 | Plan | June, 2014 | August,2014 | Sept.2014 | 3859000
[5 empty] | Actual | [20 empty] | Actual
Support toward commissioning of 1st Halal meat factory in FCT; through water reticulation, provision of cold chain facilities as well as linkage to market and access to credit financing | NCB/In-House Activity | lumpsum | 50000000 | MTB | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A |  | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A |  | N/A | N/A | 50000000 | April,26 | May,2014 | Plan | June, 2014 | August,2014 | Sept.2014 | 50000000
[5 empty] | Actual | [20 empty] | Actual
Implementation of Key Recommendations of the study report on "Transformation of the meat industry"/Development of Brands Registry | In-House Activity | lumpsum | 50000000 | MTB | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A |  | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A |  | N/A | N/A | 50000000 | April,26 | May,2014 | Plan | June, 2014 | August,2014 | Sept.2014 | 50000000
[5 empty] | Actual | [20 empty] | Actual
Registration of Large Scale Commercial Livestock Producers and Association nationwide | In-House Activity | lumpsum | 10000000 | MTB | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A |  | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A |  | N/A | N/A | 10000000 | April,26 | May,2014 | Plan | June, 2014 | August,2014 | Sept.2014 | 10000000
[5 empty] | Actual | [20 empty] | Actual
Sensitizing investors and attracting major investors in Meat Industry towards investing in Nigeria's meat industry | In-House Activity | lumpsum | 20000000 | MTB | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A |  | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A |  | N/A | N/A | 20000000 | April,26 | May,2014 | Plan | June, 2014 | August,2014 | Sept.2014 | 20000000
[5 empty] | Actual | [20 empty] | Actual
Study Tours to Countries with developed Halal meat industry | In-House Activity | lumpsum | 10000000 | MTB | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A |  | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A |  | N/A | N/A | 10000000 | April,26 | May,2014 | Plan | June, 2014 | August,2014 | Sept.2014 | 10000000
[5 empty] | Actual | [20 empty] | Actual
Basic Training for cattle producers in feedlot operations | In-House Activity | lumpsum | 15000000 | MTB | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A |  | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A |  | N/A | N/A | 15000000 | April,26 | May,2014 | Plan | June, 2014 | August,2014 | Sept.2014 | 15000000
[5 empty] | Actual | [20 empty] | Actual
Improving the policy and Business Environment to facilitate the development of Halal Meat Centres | In-House Activity | lumpsum | 15000000 | MTB | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A |  | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A |  | N/A | N/A | 15000000 | April,26 | May,2014 | Plan | June, 2014 | August,2014 | Sept.2014 | 15000000
[5 empty] | Actual | [20 empty] | Actual
Field Monitoring, Consultation with Stakeholders | In-House Activity | lumpsum | 10000000 | MTB | Plan | Jan. 14 - Jan. 25 | Jan,25 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A |  | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A |  | N/A | N/A | 10000000 | April,26 | May,2014 | Plan | June, 2014 | August,2014 | Sept.2014 | 10000000
[5 empty] | Actual | [20 empty] | Actual
Total Cost |  |  | 553355000 | [19 empty] | 553355000 | [6 empty] | 553355000
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual
Fill gray cells only!

## FERTILIZER Goods
Ministry/Department/Agency: |  |  | Federal Fertilizer Department |  |  |  | THE TIME LINE IS TO BE COMPARED WITH THE COUNCILS APPROVAL
Budgetary Year: 2010 | 2014 | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: |  | Mr A. O. Osho: 08065488780 | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Plan vs. Actual | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Inorganic Fertilizer |  |  | 2399248750 | Subsidy component of GES |  |  | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 2399248750 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14 | FFD | FMA&RD
[7 empty] | Actual | [7 empty] | Actual
Organic Fertililizer |  |  | 474113500 | Subsidy component of GES |  |  | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 474113500 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
Soil amendment micronutrient |  |  | 336950000 | Subsidy component of GES |  |  | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 336950000 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
PHCN ABJ PHCN KADUNA |  |  | 210000 | Settlement of bills |  |  | Plan | [7 empty] | Plan
|  |  | 150000 | Settlement of bills |  |  | Actual | [7 empty] | Actual
Water ABJ Water Kaduna |  |  | 150000 | Settlement of bills |  |  | Plan | [7 empty] | Plan
|  |  | 120000 | Settlement of bills |  |  | Actual | [7 empty] | Actual
Environmental Bill |  |  | 100000 | Settlement of bills |  |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Fire Extinguished |  |  | 320000 | LCB |  |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Subscription for Fertilizer Market Bulletin |  |  | 2000000 | Data gatheringat international level |  |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Capacity building by IFDC and MARKETS |  |  | 18000000 | capacity building |  |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
National and International Conferences |  |  | 4, 025,400.00 | Enhancement of technical staff
Workshop for Validation of Inspection and Analysis Manual |  |  | 4,500,000.00 | Coordination and participation in the workshop
Collection of fertilizer samples from ports, mnufacturers, blenders and dealesr |  |  | 6,500,000.00 | sample collection
Analysis of fertilizer samples |  |  | 15,000,000.00 | analysis
Zonal training of persons involved in GES (South) |  |  | 10,466,000.00
Zonal training of persons involved in GES (North) |  |  | 11,830,000.00
Collection of samples from rdemption centres |  |  | 5,000,000.00
Analysis of samples (Dry Season)
Printing and binding of fertilizer law in booklet form |  |  | 3,500,000.00 | facilitate and organize
General Staff training on computer and Management skills |  |  | 5,000,000.00 | facilitate and organize
Purchase of diesel for Generator |  |  | 1,000,000.00
purchase of office equipment( tables, chairs, computer,etc) |  |  | 1,000,000.00 | purchase of needed equipment
TOTAL |  |  | 3231362250

## FERTILIZER Works
Ministry/Department/Agency:
Budgetary Year: 2010 | 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: |  | Basic Data:Mr A. O. Osho 08065488780 | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 0 |  |  | Plan | [7 empty] | Plan | 0 | [6 empty] | 0
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## FERTILIZER Consultants
Ministry/Department/Agency: | FEDERAL DEPT. OF FERTILIZER
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: | Mr A. O. Osho: 08065488780 | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | Plan vs. Actual | No-objection Date | FEC Approval | Contract Amount in Naira | Contract Offer | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | Plan | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | Plan | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 1- 2 wk | 2 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
List of Contracts
Supply Chain Management |  |  | 375000000 |  | Plan |  |  | Roll over from 2013 |  |  |  | Plan | [7 empty] | Plan | [5 empty] | Plan
|  | Time based |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Africa Fertilizer FinancingFacilities |  | Time based | 320000000 |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Technology platform Management/deployment |  | Time based | 450,000,00.00 |  | Plan |  |  | Roll over from 2013 |  |  |  | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Review of National PolicyFertilizer |  | Time based | 19250000 |  |  |  |  | Roll over from 2013 |  |  |  | Plan | [7 empty] | Plan | [5 empty] | Plan
[12 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Crop/soil specific multidimentional trial of fertilizers by research Institutes |  | Time based | 32000000 |  |  | 3wks |  | 4wks |  |  | 2wks | Plan | [7 empty] | Plan | [5 empty] | Plan
[12 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Total Cost |  |  | #VALUE! |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | #REF! |  |  | Plan |  |  |  | #REF!
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | #REF! |  |  | Actual |  |  |  | #REF!

## FCC ORJI Goods
Ministry/Department/Agency: FMA&RD FEDERAL COOPERATIVE COLLEGE, OJI RIVER. | [6 empty] | THE TIME LINE IS TO BE COMPARED WITH THE COUNCILS APPROVAL
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: OGBONNA C. U. 08033600629 |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Plan vs. Actual | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Raising of Sheep and Goat | FCCO 01 | FCCO 01 | 900000 | Direct Application | N/A | Provost | Plan | March 13 | 31st March - 13th July | N/A | N/A | N/A | N/A | April 2013 | Plan | 900000 | N/A | N/A | N/A | N/A | 30 May, 2013 | June 2013 | FCCO | FMA&RD
[7 empty] | Actual | [7 empty] | Actual
Raising of Broilers and Layers | FCCO 02 | FCCO 02 | 500000 | Direct Application | N/A | Provost | Plan | March 13 | 31st March - 13th July | N/A | N/A | N/A | N/A | April 2013 | Plan | 500000 | N/A | N/A | N/A | N/A | 30 May, 2013 | June 2013 | FCCO | FMA&RD
[7 empty] | Actual | [7 empty] | Actual
Furnishing of College Auditorium | FCC 03 | FCC 03 | 7500000 | NTB | N/A | MTB | Plan | March. 2013 | 31st March, 2013 | April 2013 | 30th April, 2013 | May 2013 | 30th May, 2013 | June 2013 | Plan | 7500000 | N/A | June 2013 | 30th June, '13 | July 2013 | August 2013 | 15th Sept. 2013 | FCCO | FMA&RD
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  |  | 8900000 |  |  |  | Plan | [7 empty] | Plan | 8900000
|  |  | 0 |  |  |  | Actual | [7 empty] | Actual | 0
Fill gray cells only!

## FCC ORJI Works
Ministry/Department/Agency: FMA & RD FEDERAL COOPERATIVE COLLEGE, OJI RIVER.
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: OGBONNA C. U. 08033600629 |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Completion of College Internal Road Network | FCCO 01 | FCCO 01 | Bill of Quantities | Contract | 17285480 | Feb. 2013 | Minister | Plan | March. 2013 | 31st March, 2013 | April 2013 | 30th April, 2013 | May 2013 | 30th May, 2013 | June 2013 | Plan | 17285480 | N/A | June 2013 | 30th June, '13 | July 2013 | Dec. 2013 | Dec. 2013 | 17285480 | FCCO | FMA & RD
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 17285480 |  |  | Plan | [7 empty] | Plan | 17285480 | [6 empty] | 17285480
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## FCC ORJI Consultants
Ministry/Department/Agency: FMA & RD, FEDERAL COOPERATIVE COLLEGE, OJI RIVER.
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: OGBONNA C. U. 08033600629 |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | Plan vs. Actual | No-objection Date | FEC Approval | Contract Amount in Naira | Contract Offer | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | Plan | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | Plan | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 1- 2 wk | 2 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
List of Contracts
Promotion and Training of Cooperative Societies | NCB | Time Based | 2500000 | MTB | Plan | Jan. 2013 | Jan. 2013 | Feb. 2013 | Feb. 2013 | Feb. 2013 | March 2013 | Plan | March 2013 | April 2013 | April 2013 | April 2013 | May 2013 | May 2013 | May 2013 | Plan | June 2013 | N/A | 2,500,000 | June 2013 | June 2013 | Plan | June 2013 | June 2013 | Dec. 2013 | 2,500,000 | FCCO | FMA&RD
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Total Cost |  |  |  |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | #REF! |  |  | Plan |  |  |  | #REF!
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | #REF! |  |  | Actual |  |  |  | #REF!
Fill gray cells only!

## FCC IBADAN Goods
Ministry/Department/Agency: FEDERAL COOPERATIVE COLLEGE, ELEYELE IBADAN
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: FCC, IBADAN |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Purchase & Installation of modern bakery equipments using cassava flour |  |  | 8500000 | NCB | NA | PTB | Plan | 01/04/14-18/04/14 | 21/04/14-09/05/14 | 12/05/14-30/05/14 | 02/06/14-223/06/14 | 23/06/14 | 27/06/14-11/07/14 | NA |  | 8500000 | NA | 21/07/14-08/08/14 | 11/08/14-22/08/14 | 29/08/14-05/09/14 | 14/11/14-21/11/14 | 28/11/14-05/12/14
[7 empty] | Actual | [7 empty] | Actual
date
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  | 0 | 8500000 |  |  |  | Plan | [7 empty] | Plan | 8500000
|  | 0 | 0 |  |  |  | Actual | [7 empty] | Actual | 0
Fill gray cells only!

## FCC IBADAN Works
Ministry/Department/Agency: FEDERAL COOPERATIVE COLLEGE, IBADAN
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: FCC, IBADAN |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Construction of access Road for easy accessibility |  |  |  |  | 4115099.63 |  |  | Plan | [7 empty] | Plan | 4115099.63 |  |  |  | N/A | N/A | N/A | N/A
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 4115099.63 |  |  | Plan | [7 empty] | Plan | 4115099.63 | [6 empty] | #VALUE!
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## FCC IBADAN Consultants
Ministry/Department/Agency: FCC IBADAN
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #:FCC, IBADAN |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
Training and Empowerment of Rural Women, Youths and Farmers |  |  | 2259900.37 |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 2259900.37 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 0 |  |  |  | Plan |  |  |  | 0
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!

## EXT. SERV. Goods
Ministry/Department/Agency: |  |  | EXTENSION SERVICES |  |  |  | THE TIME LINE IS TO BE COMPARED WITH THE COUNCILS APPROVAL
Budgetary Year: 2014 | 2014 | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: |  | Mr A. O. Osho: 08065488780 | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Plan vs. Actual | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Inorganic Fertilizer |  |  | 2399248750 | Subsidy component of GES |  |  | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 2399248750 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
Organic Fertililizer |  |  | 474113500 | Subsidy component of GES |  |  | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 474113500 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
Soil amendment micronutrient |  |  | 336950000 | Subsidy component of GES |  |  | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 336950000 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
PHCN ABJ PHCN KADUNA |  |  | 210000 | Settlement of bills |  |  | Plan | [7 empty] | Plan
|  |  | 150000 | Settlement of bills |  |  | Actual | [7 empty] | Actual
Water ABJ Water Kaduna |  |  | 150000 | Settlement of bills |  |  | Plan | [7 empty] | Plan
|  |  | 120000 | Settlement of bills |  |  | Actual | [7 empty] | Actual
Environmental Bill |  |  | 100000 | Settlement of bills |  |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Fire Extinguished |  |  | 320000 | LCB |  |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Subscription for Fertilizer Market Bulletin |  |  | 2000000 | Data gatheringat international level |  |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Capacity building by IFDC and MARKETS |  |  | 18000000 | capacity building |  |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
National and International Conferences |  |  | 4, 025,400.00 | Enhancement of technical staff
Workshop for Validation of Inspection and Analysis Manual |  |  | 4,500,000.00 | Coordination and participation in the workshop
Collection of fertilizer samples from ports, mnufacturers, blenders and dealesr |  |  | 6,500,000.00 | sample collection
Analysis of fertilizer samples |  |  | 15,000,000.00 | analysis
Zonal training of persons involved in GES (South) |  |  | 10,466,000.00
Zonal training of persons involved in GES (North) |  |  | 11,830,000.00
Collection of samples from rdemption centres |  |  | 5,000,000.00
Analysis of samples (Dry Season)
Printing and binding of fertilizer law in booklet form |  |  | 3,500,000.00 | facilitate and organize
General Staff training on computer and Management skills |  |  | 5,000,000.00 | facilitate and organize
Purchase of diesel for Generator |  |  | 1,000,000.00
purchase of office equipment( tables, chairs, computer,etc) |  |  | 1,000,000.00 | purchase of needed equipment
TOTAL |  |  | 3231362250

## EXT. SERV. Works
Ministry/Department/Agency:
Budgetary Year: 2010 | 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: |  | Basic Data:Mr A. O. Osho 08065488780 | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 0 |  |  | Plan | [7 empty] | Plan | 0 | [6 empty] | 0
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## EXT. SERV. Consultants
Ministry/Department/Agency: | EXTENSION SERVICES
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: | Mr A. O. Osho: 08065488780 | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | Plan vs. Actual | No-objection Date | FEC Approval | Contract Amount in Naira | Contract Offer | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | Plan | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | Plan | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 1- 2 wk | 2 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
List of Contracts
Supply Chain Management |  |  | 375000000 |  | Plan |  |  | Roll over from 2013 |  |  |  | Plan | [7 empty] | Plan | [5 empty] | Plan
|  | Time based |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Africa Fertilizer FinancingFacilities |  | Time based | 320000000 |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Technology platform Management/deployment |  | Time based | 450,000,00.00 |  | Plan |  |  | Roll over from 2013 |  |  |  | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Review of National PolicyFertilizer |  | Time based | 19250000 |  |  |  |  | Roll over from 2013 |  |  |  | Plan | [7 empty] | Plan | [5 empty] | Plan
[12 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Crop/soil specific multidimentional trial of fertilizers by research Institutes |  | Time based | 32000000 |  |  | 3wks |  | 4wks |  |  | 2wks | Plan | [7 empty] | Plan | [5 empty] | Plan
[12 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Total Cost |  |  | #VALUE! |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | #REF! |  |  | Plan |  |  |  | #REF!
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | #REF! |  |  | Actual |  |  |  | #REF!

## FMA CO-OPS Goods
Ministry/Department/Agency:
Budgetary Year: | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
date
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  | 0 | 0 |  |  |  | Plan | [7 empty] | Plan | 0
|  | 0 | 0 |  |  |  | Actual | [7 empty] | Actual | 0
Fill gray cells only!

## CO-OPS Works
Ministry/Department/Agency:
Budgetary Year: | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 0 |  |  | Plan | [7 empty] | Plan | 0 | [6 empty] | 0
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## FMA CO-OPS Consultants
Ministry/Department/Agency: FMAWR/FEDERAL DEPARTMENT OF COOPERATIVES
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Prior/Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
Publication and Communication | NCB | Lumpsum | 20000000 | Prior | Plan | Feb. '10 | Feb. '10 | 2 /2 / '10 | 16 / 2 / '10 | 19 / 2 / '10 | 2 / 3 / '10 | Plan | 15 / 3 / '10 | 5 / 4 / '10 | 19 / 4 / '10 | 30 / 4 / '10 | 6 / 5 / '10 | 17 / 5 / '10 | 20 /5 / '10 | Plan | 28 / 5 / '10 | 8 / 6 / '10 | 20000000 | 23 / 6 / '10 |  | 25 / 6 / '10 | Plan | 30 / 6 / '10 | 20 / 7 / '10 | 30 / 7 / '10 | 20000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Cooperative Census and recertification. | NCB | Lumpsum | 20000000 | Prior | Plan | Feb. '10 | Feb. '10 | 2 /2 / '10 | 16 / 2 / '10 | 19 / 2 / '10 | 2 / 3 / '10 | Plan | 15 / 3 / '10 | 5 / 4 / '10 | 19 / 4 / '10 | 30 / 4 / '10 | 6 / 5 / '10 | 17 / 5 / '10 | 20 /5 / '10 | Plan | 28 / 5 / '10 | 8 / 6 / '10 | 20000000 | 23 / 6 / '10 |  | 25 / 6 / '10 | Plan | 30 / 6 / '10 | 20 / 7 / '10 | 30 / 7 / '10 | 20000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Cooperative Policy and Law Review. | NCB | Lumpsum | 140000000 | Prior | Plan | Feb. '10 | Feb. '10 | 2 /2 / '10 | 16 / 2 / '10 | 19 / 2 / '10 | 2 / 3 / '10 | Plan | 16 / 3 / '10 | 12 / 4 / '10 | 26 / 4 / '10 | 4 / 5 / '10 | 12 / 5 / '10 | 21 / 5 / '10 | 1 / 6 / '10 | Plan | 10 / 6 / '10 | 18 / 6 / '10 | 140000000 | 8 / 7 / '10 |  | 23 / 7 / '10 | Plan | 27/ 7 / '10 | 25 / 8 / '10 | 31 / 8 / '10 | 140000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Development of Cooperative regulatory framework. | NCB | Lumpsum | 5000000 | Prior | Plan | Feb. '10 | Jan. '10 | 15 / 1 / '10 | 29 / 1 / '10 | 5 / 2 / '10 | 18 / 2 / '10 | Plan | 3 / 3 / '10 | 29 / 3 / '10 | 12 / 4 / '10 | 21 / 4 / '10 | 31 / 4 / '10 | 12 / 5 / '10 | 21 / 5 / '10 | Plan | 3 / 6 / '10 | 15 / 6 / '10 | 5000000 | 5 / 7 / '10 |  | 20 / 7 / '10 | Plan | 23 / 7 / '10 | 24 / 8 / '10 | 31 / 8 / '10 | 5000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Cooperative Institutional Capacity and good governance / Launching of WOCCU PEARLS. | NCB | Lumpsum | 10000000 | Post | Plan | Feb. '10 | Jan. '10 | 15 / 1 / '10 | 29 / 1 / '10 | 5 / 2 / '10 | 18 / 2 / '10 | Plan | 8 / 3 / '10 | 30 / 3 / '10 | 13 / 4 / '10 | 23 / 4 / '10 | 5 / 5 / '10 | 14 / 5 / '10 | 26 /5 / '10 | Plan | 8 / 6 / '10 | 18 / 6 / '10 | 10000000 | 9 / 7 / '10 |  | 26 / 7 / '10 | Plan | 29 / 7 / '10 | 19/ 8 / '10 | 26 / 8 / '10 | 10000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Conduct Training Needs Analysis (TNA) and Training of Trainers (TOT) | NCB | Lumpsum | 10000000 | Post | Plan | Feb. '10 | Jan. '10 | 15 / 1 / '10 | 29 / 1 / '10 | 5 / 2 / '10 | 18 / 2 / '10 | Plan | 12 / 3 / '10 | 8 / 4 / '10 | 26 / 4 / '10 | 5 / 5 / '10 | 14 / 5 /'10 | 26 / 5 / '10 | 9 / 6 / '10 | Plan | 18 / 6 / '10 | 29 / 6 / '10 | 10000000 | 16 / 7 / '10 |  | 2 / 8 / '10 | Plan | 12 / 8 / '10 | 20 / 9 / '10 | 30 / 9 / '10 | 10000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Cooperative Management Training. | NCB | Lumpsum | 200000000 | Post | Plan | Feb. '10 | Jan. '10 | 5 / 1 / '10 | 18/ 1 / '10 | 2 / 2 / '10 | 15 / 2 / '10 | Plan | 8 / 3 / '10 | 6 / 4 / '10 | 23 / 4 / '10 | 3 / 5 / '10 | 14 / 5 / '10 | 27 / 5 / '10 | 10 / 6 / '10 | Plan | 23 / 6 / '10 | 5 / 7 / '10 | 200000000 | 23 / 7 / '10 |  | 11 / 8 / '10 | Plan | 17 / 8 / '10 | 12 / 10 / '10 | 29 / 10 / '10 | 200000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Strenghtening of Cooperative Inspectorate Services. | NCB | Lumpsum | 50000000 | Post | Plan | Feb. '10 | 27 / 1 / '10 | 9 / 2 / '10 | 10 / 2 / '10 | 19 / 2 / '10 | 2 / 3 / '10 | Plan | 25 / 3 / '10 | 19 / 4 / '10 | 3 / 5 / '10 | 14 / 5 / '10 | 25 / 5 / '10 | 2 / 6 / '10 | 11/ /6 / '10 | Plan | 24 / 6 / '10 | 7 / 7 / '10 | 50000000 | 26 / 7 / '10 |  | 10 / 8 / '10 | Plan | 18 / 8 / '10 | 11 / 10 / '10 | 28 / 10 / '10 | 50000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Monitoring and Evaluation / Development of Monitoring Indicators. | NCB | Lumpsum | 50000000 | Post | Plan | Feb. '10 | 27 / 1 / '10 | 9 / 2 / '10 | 10 / 2 / '10 | 19 / 2 / '10 | 2 / 3 / '10 | Plan | 18 / 3 / '10 | 8 / 4 / '10 | 21 / 4 / '10 | 4 / 5 / '10 | 14 / 5 / '10 | 25 / 5 / '10 | 3 / 6 / '10 | Plan | 15 / 6 / '10 | 25 / 6 / '10 | 50000000 | 19 / 7 / '10 |  | 3 / 8 / '10 | Plan | 10 / 8 / '10 | 28 / 10 / '10 | 30 / 11 / '10 | 50000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 505000000 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 505000000 |  |  |  | Plan |  |  |  | 505000000
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!

## CODEX Consultants
Ministry/Department/Agency: | MINISTERIAL CODEX COMMITTEE
Budgetary Year: 2014 | 2014 | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | Plan vs. Actual | No-objection Date | FEC Approval | Contract Amount in Naira | Contract Offer | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | Plan | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | Plan | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 1- 2 wk | 2 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
List of Contracts
Participation at International Codex Committee meeting | In - House | lumpsum | 28600000 | MTB | Plan | Jan. 14 - Jan. 25 | Jan,28 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 28600000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 28600000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
 Participation at National Codex Committee (NCC) Quartely Meetings | In - House | lumpsum | 800000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,28 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 800000 | April,26 | May,2014 | Plan | June, 2014 | August.,2014 | Sept.2014 | 800000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Participation at NCC Technical Sub-Committee Meeting | In-House | lumpsum | 400000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,28 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 400000 | April,26 | May,2014 | Plan | June, 2014 | August, 2014 | Sept.2014 | 400000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Hosting of Animal and Animal Products Technical Committee meeting | In-House | lumpsum | 2000000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,28 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 2000000 | April,26 | May,2014 | Plan | June, 2013 | August, 2014 | Sept.2014 | 2000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
 Hosting of Plants and Plant Products Technical Committee meeting | In-House | lumpsum | 1000000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,28 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 1000000 | April,26 | May,2014 | Plan | June, 2014 | August, 2014 | Sept.2014 | 1000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Hosting of e- Secreteriat for electronic Working Groups | In-House | lumpsum | 200000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,28 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 200000 | April,26 | May,2014 | Plan | June, 2014 | August, 2014 | Sept.2014 | 200000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Hosting of Ministerial Committee meetings | In-House | lumpsum | 600000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,28 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 600000 | April,26 | May,2014 | Plan | June, 2014 | August, 2014 | Sept.2014 | 600000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
 Study on Contaminants (arsenic) in Rice in Nigeria | NCB | lumpsum | 10000000 | MTB | Plan | Jan. 14 - Jan. 25 | Jan,28 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 10000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 10000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Training of Codex Officers in Departments and Parastatals on Codex Standard Setting Process | In-House | lumpsum | 2200000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,28 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 2200000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 2200000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Sensitization of Key Experts in Universities and Research Institutes on Codex Standard Setting process | In-House | lumpsum | 2200000 | PS | Plan | Jan. 14 - Jan. 25 | Jan,28 - Feb, 8 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 2200000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 2200000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Support for NCC Codex Activities | In - House | lumpsum | 2000000 | PS | Plan | Jan. 14 - Jan. 25 | March, 2013 | Feb, 18 | Feb,18 - March, 11 | March,13 | N/A | Plan | N/A | March,25 | March,29 | March, 25 - April 2 | April, 2 -April,16 | April,19 | N/A | Plan | N/A | N/A | 2000000 | April,26 | May,2014 | Plan | June, 2014 | August. 2014 | Sept.2014 | 2000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Actual
Total Cost |  |  | 50000000 | [19 empty] | 50000000 | [6 empty] | 50000000
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual
Fill gray cells only!

## APM Goods
Ministry/Department/Agency: APM | [6 empty] | THE TIME LINE IS TO BE COMPARED WITH THE COUNCILS APPROVAL
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: Engr. I. U. Nwankwo (08033904125) |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval/BPP "No Objection" | Plan vs. Actual | Certifiable Amount per Contract | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 4 wks | 6 wks | 2 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 2 wks | 2 - 3 wks | T | 2 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Procurement of 37 units of small Rice processing equipment |  |  | 370000000 | competitive bidding | 3rd - 17th Feb. | MTB | Plan | 18th Feb. -7th Mar | 10th - 21st Mar | 24th Mar - 4th Apr | 7thApril-2nd May | 5th May-13th Jun | 16th Jun.-27th Jun | 30th Jun -11th Jul | Plan | 10,000,000.00 | NA | 14th-25th Jul | 28th Jul -8th Aug | 11th -22nd Aug | 26th Sep. | 29thSep-10th Oct | Engr. Ogumbiyi | Engr. Jatto
[7 empty] | Actual | [7 empty] | Actual
Procurement of 37 units of Rice Destoners |  |  | 25900000 | competitive bidding | 3rd - 17th Feb. | MTB | Plan | 18th Feb. -7th Mar | 10th - 21st Mar | 24th Mar - 4th Apr | 7thApril-2nd May | 5th May-13th Jun | 16th Jun.-27th Jun | 30th Jun -11th Jul | Plan | 700,000.00 | NA | 14th-25th Jul | 28th Jul -8th Aug | 11th -22nd Aug | 26th Sep. | 29thSep-10th Oct | Engr. Ogumbiyi | Engr. Jatto
[7 empty] | Actual | [7 empty] | Actual
Procurement 37unit of Rice Mini Harvesters |  |  | 55000000 | competitive bidding | 3rd - 17th Feb. | MTB | Plan | 18th Feb. -7th Mar | 10th - 21st Mar | 24th Mar - 4th Apr | 7thApril-2nd May | 5th May-13th Jun | 16th Jun.-27th Jun | 30th Jun -11th Jul | Plan | 1,500,000.00 | NA | 14th-25th Jul | 28th Jul -8th Aug | 11th -22nd Aug | 26th Sep. | 29thSep-10th Oct | Engr. Gagare | Engr. Jatto
[7 empty] | Actual | [7 empty] | Actual
Procurement of 37 units of Rice Reapers |  |  | 22200000 | competitive bidding | 3rd - 17th Feb. | MTB | Plan | 18th Feb. -7th Mar | 10th - 21st Mar | 24th Mar - 4th Apr | 7thApril-2nd May | 5th May-13th Jun | 16th Jun.-27th Jun | 30th Jun -11th Jul | Plan | 600,000.00 | NA | 14th-25th Jul | 28th Jul -8th Aug | 11th -22nd Aug | 26th Sep. | 29thSep-10th Oct | Engr. Gagare | Engr. Jatto
[7 empty] | Actual | [7 empty] | Actual
Procurement 37units of RiceParboilers |  |  | 92500000 | competitive bidding | 3rd - 17th Feb. | MTB | Plan | 18th Feb. -7th Mar | 10th - 21st Mar | 24th Mar - 4th Apr | 7thApril-2nd May | 5th May-13th Jun | 16th Jun.-27th Jun | 30th Jun -11th Jul | Plan | 2,500,000.00 | NA | 14th-25th Jul | 28th Jul -8th Aug | 11th -22nd Aug | 26th Sep. | 29thSep-10th Oct | Engr. Gagare | Engr. Jatto
[7 empty] | Actual | [7 empty] | Actual
Procurement of 37units of Rice Bagging Machine |  |  | 5550000000 | competitive bidding | 3rd - 17th Feb. | MTB | Plan | 18th Feb. -7th Mar | 10th - 21st Mar | 24th Mar - 4th Apr | 7thApril-2nd May | 5th May-13th Jun | 16th Jun.-27th Jun | 30th Jun -11th Jul | Plan | 150,000,000.00 | NA | 14th-25th Jul | 28th Jul -8th Aug | 11th -22nd Aug | 26th Sep. | 29thSep-10th Oct | Engr. Isah | Engr. Jatto
[7 empty] | Actual | [7 empty] | Actual
Procurement of 37units Flat weighing scale |  |  | 14800000 | competitive bidding | 3rd - 17th Feb. | MTB | Plan | 18th Feb. -7th Mar | 10th - 21st Mar | 24th Mar - 4th Apr | 7thApril-2nd May | 5th May-13th Jun | 16th Jun.-27th Jun | 30th Jun -11th Jul | Plan | 400,000.00 | NA | 14th-25th Jul | 28th Jul -8th Aug | 11th -22nd Aug | 26th Sep. | 29thSep-10th Oct | Engr. Isah | Engr. Jatto
[7 empty] | Actual | [7 empty] | Actual
Procurement of 130unit of Multipurpose Sorghum grain treshers |  |  | 130000000 | competitive bidding | 3rd - 17th Feb. | MTB | Plan | 18th Feb. -7th Mar | 10th - 21st Mar | 24th Mar - 4th Apr | 7thApril-2nd May | 5th May-13th Jun | 16th Jun.-27th Jun | 30th Jun -11th Jul | Plan | 1,000,000.00 | NA | 14th-25th Jul | 28th Jul -8th Aug | 11th -22nd Aug | 26th Sep. | 29thSep-10th Oct | Engr. Okuwobi | Engr. Jatto
[7 empty] | Actual | [7 empty] | Actual
Purchase of 24units of Cassava chipping machine for farmers Cooperatives |  |  | 8400000 | competitive bidding | 3rd - 17th Feb. | MTB | Plan | 18th Feb. -7th Mar | 10th - 21st Mar | 24th Mar - 4th Apr | 7thApril-2nd May | 5th May-13th Jun | 16th Jun.-27th Jun | 30th Jun -11th Jul | Plan | 350,000.00 | NA | 14th-25th Jul | 28th Jul -8th Aug | 11th -22nd Aug | 26th Sep. | 29thSep-10th Oct | Engr. Adebiyi | Engr. Jatto
[7 empty] | Actual | [7 empty] | Actual
Procurement of 100units of oilpalm small processing equipment |  |  | 100000000 | competitive bidding | 3rd - 17th Feb. | MTB | Plan | 18th Feb. -7th Mar | 10th - 21st Mar | 24th Mar - 4th Apr | 7thApril-2nd May | 5th May-13th Jun | 16th Jun.-27th Jun | 30th Jun -11th Jul | Plan | 1,000,000.00 | NA | 14th-25th Jul | 28th Jul -8th Aug | 11th -22nd Aug | 26th Sep. | 29thSep-10th Oct | Engr. Malami | Engr. Jatto
[7 empty] | Actual | [7 empty] | Actual
Purchase of 1 no cashew processing equipment |  |  | 2000000 | National shopping | 3rd - 17th Feb. | PS | Plan | 18th Feb. -7th Mar | 10th - 21st Mar | 24th Mar - 4th Apr | 7thApril-2nd May | 5th May-13th Jun | 16th Jun.-27th Jun | 30th Jun -11th Jul | Plan | 2,000,000.00 | NA | 14th-25th Jul | 28th Jul -8th Aug | 11th -22nd Aug | 26th Sep. | 29thSep-10th Oct | Engr. Bello | Engr. Jatto
[7 empty] | Actual | [7 empty] | Actual
AGRIBUSINESS & INVESTMENT:
Support for participation in international Agribusiness and Investment Organisation |  |  | 20000000 |  | 3rd - 17th Feb. |  | Plan | 18th Feb. -7th Mar | 10th - 21st Mar | 24th Mar - 4th Apr | 7thApril-2nd May | 5th May-13th Jun | 16th Jun.-27th Jun | 30th Jun -11th Jul | Plan | 20,000,000.00 | NA | 14th-25th Jul | 28th Jul -8th Aug | 11th -22nd Aug | 26th Sep. | 29thSep-10th Oct | Engr. Udo | Engr. Jatto
[7 empty] | Actual | [7 empty] | Actual
Hosting of European Market Research Council (EMRC) Agribusiness forum |  |  | 80000000 |  | 3rd - 17th Feb. |  | Plan | 18th Feb. -7th Mar | 10th - 21st Mar | 24th Mar - 4th Apr | 7thApril-2nd May | 5th May-13th Jun | 16th Jun.-27th Jun | 30th Jun -11th Jul | Plan | 80,000,000.00 | NA | 14th-25th Jul | 28th Jul -8th Aug | 11th -22nd Aug | 26th Sep. | 29thSep-10th Oct | Engr. Udo | Engr. Jatto
[7 empty] | Actual | [7 empty] | Actual
Market Research, Test Market and consumer insight for commercialization |  |  | 20000000 |  | 3rd - 17th Feb. |  | Plan | 18th Feb. -7th Mar | 10th - 21st Mar | 24th Mar - 4th Apr | 7thApril-2nd May | 5th May-13th Jun | 16th Jun.-27th Jun | 30th Jun -11th Jul | Plan | 20,000,000.00 | NA | 14th-25th Jul | 28th Jul -8th Aug | 11th -22nd Aug | 26th Sep. | 29thSep-10th Oct | Engr. Gagare | Engr. Jatto
[7 empty] | Actual | [7 empty] | Actual
Agribusiness and Investment bulletins on value chains |  |  | 10000000 |  | 3rd - 17th Feb. |  | Plan | 18th Feb. -7th Mar | 10th - 21st Mar | 24th Mar - 4th Apr | 7thApril-2nd May | 5th May-13th Jun | 16th Jun.-27th Jun | 30th Jun -11th Jul | Plan | 10,000,000.00 | NA | 14th-25th Jul | 28th Jul -8th Aug | 11th -22nd Aug | 26th Sep. | 29thSep-10th Oct | Engr. Malami | Engr. Jatto
[7 empty] | Actual | [7 empty] | Actual
Private Sector Investment Drive |  |  | 10000000 |  | 3rd - 17th Feb. |  | Plan | 18th Feb. -7th Mar | 10th - 21st Mar | 24th Mar - 4th Apr | 7thApril-2nd May | 5th May-13th Jun | 16th Jun.-27th Jun | 30th Jun -11th Jul | Plan | 10,000,000.00 | NA | 14th-25th Jul | 28th Jul -8th Aug | 11th -22nd Aug | 26th Sep. | 29thSep-10th Oct | Engr. Malami | Engr. Jatto
[7 empty] | Actual | [7 empty] | Actual
SCPZs Monitiring and Evaluation |  |  | 55000000 |  | 3rd - 17th Feb. |  | Plan | 18th Feb. -7th Mar | 10th - 21st Mar | 24th Mar - 4th Apr | 7thApril-2nd May | 5th May-13th Jun | 16th Jun.-27th Jun | 30th Jun -11th Jul | Plan | 55000000 | NA | 14th-25th Jul | 28th Jul -8th Aug | 11th -22nd Aug | 26th Sep. | 29thSep-10th Oct | Engr. Fadah | Engr. Jatto
[7 empty] | Actual | [7 empty] | Actual
Purchase of 4Nos. Project Vehicles |  |  | 50000000 | competitive bidding | 3rd - 17th Feb. | MTB | Plan | 18th Feb. -7th Mar | 10th - 21st Mar | 24th Mar - 4th Apr | 7thApril-2nd May | 5th May-13th Jun | 16th Jun.-27th Jun | 30th Jun -11th Jul | Plan | 50000000 | NA | 14th-25th Jul | 28th Jul -8th Aug | 11th -22nd Aug | 26th Sep. | 29thSep-10th Oct | Engr. Malami | Engr. Jatto
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  |  | 6615800000 |  |  |  | Plan | [7 empty] | Plan | 105000000
|  |  | 0 |  |  |  | Actual | [7 empty] | Actual
Fill gray cells only!

## AMP Works
Ministry/Department/Agency: APM
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Within MDAs Thresholds, No-objection Dates not required
Desk Officer/Contact #: Mr. Okuwobi (08027103742) |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | MDA Approval | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Action Party | Champion
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 - 6 wks | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 1 wks |  |  | 6 Months
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Construction of 20units of primary cottage Sorghum processing plants |  |  | BOQ | Competitive Bidding | 2000000000 | 3rd - 17th Feb. | MTB | Plan | 18th Feb. -7th Mar | 10th - 21st Mar | 24th Mar - 4th Apr | 7thApril-2nd May | 5th May-13th Jun | 16th Jun.-27th Jun | 30th Jun -11th Jul | Plan | 200000000 | NA | 14th-25th Jul | 28th Jul -8th Aug | 11th -22nd Aug | 26th Sep. | 29thSep-10th Oct | 200000000 | Engr. Makinde | Engr. Jatto
[8 empty] | Actual | [7 empty] | Actual
Construction of 13units drying slabs for cassava chips for export |  |  | BOQ | Competitive Bidding | 65000000 | 3rd - 17th Feb. | MTB | Plan | 18th Feb. -7th Mar | 10th - 21st Mar | 24th Mar - 4th Apr | 7thApril-2nd May | 5th May-13th Jun | 16th Jun.-27th Jun | 30th Jun -11th Jul | Plan | 65000000 | NA | 14th-25th Jul | 28th Jul -8th Aug | 11th -22nd Aug | 26th Sep. | 29thSep-10th Oct | 65000000 | Engr Okuwobi | Engr. Jatto
[8 empty] | Actual | [7 empty] | Actual
construction of 6units of cashew processing plant |  |  | BOQ | Competitive Bidding | 96000000 | 3rd - 17th Feb. | MTB | Plan | 18th Feb. -7th Mar | 10th - 21st Mar | 24th Mar - 4th Apr | 7thApril-2nd May | 5th May-13th Jun | 16th Jun.-27th Jun | 30th Jun -11th Jul | Plan | 96000000 | NA | 14th-25th Jul | 28th Jul -8th Aug | 11th -22nd Aug | 26th Sep. | 29thSep-10th Oct | 96000000 | Engr. Adebiyi | Engr. Jatto
[8 empty] | Actual | [7 empty] | Actual
Staple Crop Processing Zones (SCPZS)
Land clearing for SCPZs new sites |  |  | BOQ | Competitive Bidding | 210000000 | 3rd - 17th Feb. | MTB | Plan | 18th Feb. -7th Mar | 10th - 21st Mar | 24th Mar - 4th Apr | 7thApril-2nd May | 5th May-13th Jun | 16th Jun.-27th Jun | 30th Jun -11th Jul |  | 210000000 | NA | 14th-25th Jul | 28th Jul -8th Aug | 11th -22nd Aug | 26th Sep. | 29thSep-10th Oct | 210000000 | Engr. Afowowe | Engr. Jatto
[8 empty] | Actual | [7 empty] | Actual
TOTAL = |  |  |  |  | 2371000000 | [11 empty] | 571000000 | [6 empty] | 571000000
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual

## AMP Consultants
Ministry/Department/Agency: APM (SCPZ)
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: Engr. A. O. Afowowe |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Thresholds | Plan vs. Actual | Prep & Submission by MDAs | MDA Approval | Advertisement | Lead-time before shortlist | Submission Date | MDA Approval | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | MDA Approval | Opening/Evaluation Financial Proposals | Submission Eval Report (T) (F) | Negotiations if Any (N) | Plan vs. Actual | No-objection Date | FEC Approval | Contract Amount in Naira | Contract Offer | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion
Norm Duration of Proc Steps |  |  |  |  | Plan | 2 -3 wks | 1 - 2 wks | 2 wks | 1 wks |  | 1 - 2 wks | Plan | 2 wks | 2-4 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 1- 2 wk | 2 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
List of Contracts
Staple Crop Processing Zones (SCPZs) Studies |  |  | 190000000 | BPP NO OBJECTION | Plan | 18th Feb. -7th Mar | 10th - 21st Mar | 24th Mar - 4th Apr | 7th -14th April | 15th - 18th April | 21stApril - 2nd May | Plan | 5th - 16th May | 19thMay- 13th Jun | 16th -27th Jun | 3oJun -11th Jul | 14th - 25th Jul | 28thJul - 8th Aug | 11th - 22nd Aug | Plan | 25th Aug - 5th Sep | NA | 190,000,000.00 | 8th - 19th Sep | 22ndSep-3rdOct | Plan | NA | 3rd -7th Nov. | 8th -12th Dec | 200,000,000.00 | Engr. Afowowe | Engr. Jatto
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
SCPZs Workshop | QCB | Time-Based | 60000000 | MTB | Plan | 3rd-17th Feb | 18th Feb-7th Mar | 10th-21st Mar | 24th-31st Mar | 1st-7th April | 8th-22nd April | Plan | 23rd April-5th May | 6th-28th May | 2nd-16th June | 17th June-1st July | 2nd-15th July | 18th-31st July | 4th-18th August | Plan | NA | NA | 60,000,000.00 | 25th Aug-8th Sept | 9th-22nd Sept | Plan | NA | 20th Oct-3rd Nov | 15th-22nd Dec | 60,000,000.00 | Engr. Afowowe | Engr. Jatto
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
SCPZs Training | QCB | Time-Based | 35000000 | MTB | Plan | 3rd-17th Feb | 18th Feb-7th Mar | 10th-21st Mar | 24th-31st Mar | 1st-7th April | 8th-22nd April | Plan | 23rd April-5th May | 6th-28th May | 2nd-16th June | 17th June-1st July | 2nd-15th July | 18th-31st July | 4th-18th August | Plan | NA | NA | 35,000,000.00 | 25th Aug-8th Sept | 9th-22nd Sept | Plan | NA | 20th Oct-3rd Nov | 15th-22nd Dec | 35,000,000.00 | Engr. Afowowe | Engr. Jatto
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [5 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Total Cost |  |  | 190000000 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 190000000 |  |  | Plan |  |  |  | 190000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
Fill gray cells only!

## ALR Goods
Ministry/Department/Agency: Dept. of Agric Lands Resources
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
i). Procrement of Medium Infra Red (MIR) Dry Chemistry Soil Testing Equipment | ALR | LOT 1 | 40000000 | Competitive Bidding | Jan 1 - Jan 14 | MTB | Plan | Jan 14 - Feb 4 | Feb 4 - Feb 18 | Feb 18- Mar 4 | Mar 4 - Apr 1 | Apr 15 | Apr 15 - Apr 29 | Apr 29 - May 13 | Plan | 40000000 | My 27 | May 27 - Jun 10 | Jun 24 | Jun 24 - Jul 15 | Aug 12 | Sep 9
[7 empty] | Actual | [7 empty] | Actual
date
ii). Production and Supply of Soil Extension Manuals | ALR | LOT 2 | 18283851 | Competitive Bidding | Jan 1 - Jan 14 | MTB | Plan | Jan 14 - Feb 4 | Feb 4 - Feb 18 | Feb 18- Mar 4 | Mar 4 - Apr 1 | Apr 15 | Apr 15 - Apr 29 | Apr 29 - May 13 | Plan | 18283851 | My 27 | May 27 - Jun 10 | Jun 24 | Jun 24 - Jul 15 | Aug 12 | Sep 9
[7 empty] | Actual | [7 empty] | Actual
iii). Procurement of Soil Laboratory in-a-box /Reagents | ALR | LOT 3 | 30000000 | Competitive Bidding | Jan 1 - Jan 14 | MTB | Plan | Jan 14 - Feb 4 | Feb 4 - Feb 18 | Feb 18- Mar 4 | Mar 4 - Apr 1 | Apr 15 | Apr 15 - Apr 29 | Apr 29 - May 13 | Plan | 30000000 | My 27 | May 27 - Jun 10 | Jun 24 | Jun 24 - Jul 15 | Aug 12 | Sep 9
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  | #VALUE! | 88283851 |  |  |  | Plan | [7 empty] | Plan | 88283851
|  | 0 | 0 |  |  |  | Actual | [7 empty] | Actual | 0
Fill gray cells only!

## ALR Works
Ministry/Department/Agency: Dept. of Agric Lands Resources
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
i). Construction of On-farm Water Harvesting Structure | ALR | LOT 1 | Lumpsum | Competitive Bidding | 22000000 | Jan 1 - Jan 14 | MTB | Plan | Jan 14 - Feb 4 | Feb 4 - Feb 18 | Feb 18- Mar 4 | Mar 4 - Apr 15 | Apr 15 | Apr 15 - May 6 | May 6 - May 20 | Plan | 22000000 | May 20 - Jun 17 | Jun 17 - Jul 1 | Jul 8 | 15% | Nov 8 | Dec 8 | 22000000
[8 empty] | Actual | [7 empty] | Actual
ii). Contruction of On-farm Erosion Control Measures | ALR | LOT 2 | Lumpsum | Competitive Bidding | 13,600,00.00 | Jan 1 - Jan 14 | MTB | Plan | Jan 14 - Feb 4 | Feb 4 - Feb 18 | Feb 18- Mar 4 | Mar 4 - Apr 15 | Apr 15 | Apr 15 - May 6 | May 6 - May 20 | Plan | 13,600,00.00 | May 20 - Jun 17 | Jun 17 - Jul 1 | Jul 8 | 15% | Nov 8 | Dec 8 | 13,600,00.00
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | #VALUE! |  |  | Plan | [7 empty] | Plan | #VALUE! | [6 empty] | #VALUE!
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## ALR Consultants
Ministry/Department/Agency: | Dept. of Agric Lands Resources
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Prior/Post Review | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
i) Establishment of an Agricultural Land Resources information platform that would serve as a vehicle to provide It infrastructure for efficient and effective land use planning and mamgement (collaboration with Nasarawa State Government) | MOU with PROGIS | Lumpsum | 50000000 | MTB | Plan | Jan 14 - Feb 4 | Feb 4 - Feb 11 | Feb 11- Feb 25 | Feb 25 - Mar 4 | Mar 4 | Mar 4 - Mar 18 | Plan | Mar 18 | Mar 18 - Apr 15 | Apr 15 - Apr 29 | May 13 | May 27 | Jun 10 | Jun 10 - Jun 24 | Plan | Jun 24 | Jun 24 - Jul 8 | 50000000 | Jul 8 - Jul 22 | Jul 22 - Aug 5 | Aug 19 | Plan | 15% | Sep 9 | Sep 30 | 50000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
ii) Establishment of a practical, timely and cost effective soil health surveillance serve to map soil condition, and set a baseline for monitoring the ecosystem | Competitive Bidding | Lumpsum | 40000000 | MTB | Plan | Jan 14 - Feb 4 | Feb 4 - Feb 11 | Feb 11- Feb 25 | Feb 25 - Mar 4 | Mar 4 | Mar 4 - Mar 18 | Plan | Mar 18 | Mar 18 - Apr 15 | Apr 15 - Apr 29 | May 13 | May 27 | Jun 10 | Jun 10 - Jun 24 | Plan | Jun 24 | Jun 24 - Jul 8 | 40000000 | Jul 8 - Jul 22 | Jul 22 - Aug 5 | Aug 19 | Plan | 15% | Sep 9 | Sep 30 | 40000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
iii) Establishment and Maintenance of Agro-Forestry (AF); Farmers Managed Natural Regeneration (FMNR); Conservation Agriculture (CA); Integrated Soil Fertility Management (ISFM) Technologies. | Competitive Bidding | Lumpsum | 40000000 | MTB | Plan | Jan 14 - Feb 4 | Feb 4 - Feb 11 | Feb 11- Feb 25 | Feb 25 - Mar 4 | Mar 4 | Mar 4 - Mar 18 | Plan | Mar 18 | Mar 18 - Apr 15 | Apr 15 - Apr 29 | May 13 | May 27 | Jun 10 | Jun 10 - Jun 24 | Plan | Jun 24 | Jun 24 - Jul 8 | 40000000 | Jul 8 - Jul 22 | Jul 22 - Aug 5 | Aug 19 | Plan | 15% | Sep 9 | Sep 30 | 40000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
iv) Conduct Training for Extension Officers, ADP Officers, large Scale farmers and farmers cooperative societies on the Use of Lab-in-Box for on the spot assessment of soil nutrients. | Competitive Bidding | Lumpsum | 10000000 | MTB | Plan | Jan 14 - Feb 4 | Feb 4 - Feb 11 | Feb 11- Feb 25 | Feb 25 - Mar 4 | Mar 4 | Mar 4 - Mar 18 | Plan | Mar 18 | Mar 18 - Apr 15 | Apr 15 - Apr 29 | May 13 | May 27 | Jun 10 | Jun 10 - Jun 24 | Plan | Jun 24 | Jun 24 - Jul 8 | 10000000 | Jul 8 - Jul 22 | Jul 22 - Aug 5 | Aug 19 | Plan | 15% | Sep 9 | Sep 30 | 10000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
v). Sensitization Training Workshop on Watershed Management | Competitive Bidding | Lumpsum | 4400000 | PS | Plan | Jan 14 - Feb 4 | Feb 4 - Feb 11 | Feb 11- Feb 25 | Feb 25 - Mar 4 | Mar 4 | Mar 4 - Mar 18 | Plan | Mar 18 | Mar 18 - Apr 15 | Apr 15 - Apr 29 | May 13 | May 27 | Jun 10 | Jun 10 - Jun 24 | Plan | Jun 24 | Jun 24 - Jul 8 | 10000000 | Jul 8 - Jul 22 | Jul 22 - Aug 5 | Aug 19 | Plan | 15% | Sep 9 | Sep 30 | 10000000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | #REF! |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | #REF! |  |  |  | Plan |  |  |  | #REF!
|  |  | #REF! |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | #REF! |  |  |  | Actual |  |  |  | #REF!
Fill gray cells only!

## FDA WHEAT Goods
Ministry/Department/Agency: FDA
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #:WHEAT |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Buyback of 32mt Breeder seeds produced by the reseach Institutes (IAR-ABU and LCRI) for ATA |  |  |  | MoU | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
date
Buyback of 160mt certified seed produced by 2 seed companies- Maina and Premier seed Nig. Ltd for ATA |  |  |  | MoU | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Buyback of 6,475mt of certified seed produced by wheat farmers in the wheat producing states through GES plus transportation |  |  |  | GES | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Procuurement of 71,637 bags (3,581mt) fertilizer: NPK 15:15:15 |  |  |  | GES | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Procurement of 1,334 cartons of micro-nutrients (Agrolyser-10 bottles/ctn) for distribution to farmers. |  |  |  | GES | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Procurement of 8,000 litres of post emergence herbicides @2,000/litre for distribution |  |  |  | GES | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Input distribution to farmers to reflet their requirements from their designated state |  |  |  | GES | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
3,000 water pumps 1,500 knapsack sprayers |  |  |  | MTB | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Procurement of small scale groundnut processing machine |  |  |  | MTB | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
36 nos med sized milling machines 200,000 (100kg) jute bags |  |  |  | MTB | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
identification of the existing medium/large scale processing mills/ establishment of additional processing mills in 11 core states |  |  |  | MTB | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
identification of the existing medium/large scale processing mills/ establishment of additional facilities mills in 11 core states |  |  |  | MTB | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  | #REF! | #REF! |  |  |  | Plan | [7 empty] | Plan | #REF!
|  | #REF! | #REF! |  |  |  | Actual | [7 empty] | Actual | #REF!
Fill gray cells only!

## FDA WHEAT Works
Ministry/Department/Agency:
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 0 |  |  | Plan | [7 empty] | Plan | 0 | [6 empty] | 0
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## FDA WHEAT Consultants
Ministry/Department/Agency:
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 0 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 0 |  |  |  | Plan |  |  |  | 0
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!

## FDA S.POTATOGoods
Ministry/Department/Agency: FDA (POTATO VALUE CHAIN)
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: SWEET POTATO |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Establisment of foundation stock |  |  | 30000000 | MoU | Pre-Qualification | MTB | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
date
Establishment and Installations of 3 nos. of screen House Tunnels in six states by NCRI |  |  | 20000000 | MoU | Pre-Qualification | MTB | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Diversified product Value Chain |  |  | 16000000 | MoU | Pre-Qualification | MTB | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Distribution of planting materials |  |  | 10000000 | MoU | Pre-Qualification | MTB | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Nutrition Value & Demend creation: Nutirtion awareness, food demostrations and distribution of OFSP vine through community infant Young child feeding support group in 3 state |  |  | 3000000 | MoU | Pre-Qualification | PS | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Engaging HPZC and NRCRI on production of improved variety |  |  | 47119600 | MoU | Pre-Qualification | MTB | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Train the trainer on all what you what to know about sweet potato |  |  | 2000000 | MoU | Pre-Qualification | PS | Plan | [7 empty] | Plan
Actual
Study tour on processing and utilization of OFSP Rwanda & Mozambique |  |  | 5000000 | MoU |  | PS | Plan
Actual
Irish Potato Development in Plateau, Taraba and CrossRiver |  |  | 75500000 | MoU |  | MTB | Plan
Actual
Research and Development |  |  | 16880400 | MoU |  | MTB | Plan
Actual
GES intervention, distribution of Irish seed to farmers |  |  | 1500000 | GES |  |  | Plan
Actual
Total Cost |  | #REF! | 227000000 |  |  |  | Plan | [7 empty] | Plan | #REF!
|  | #REF! | #REF! |  |  |  | Actual | [7 empty] | Actual | #REF!
Fill gray cells only!

## FDA S.POTATO Works
Ministry/Department/Agency:
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 0 |  |  | Plan | [7 empty] | Plan | 0 | [6 empty] | 0
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## FDA S.POTATO Consultants
Ministry/Department/Agency:
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 0 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 0 |  |  |  | Plan |  |  |  | 0
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!

## FDA SUGARCANE Goods
Ministry/Department/Agency: FDA (SUGARCANE VALUE CHAIN)
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #:SUGARCANE |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Multiplication & Distribution of industrial sugarcane to another 3,500 farmers in 14 state |  |  | 47000000 | MoU | Pre-Qualification | MTB | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
date
Supply of inorganic fertilizer to another 3,500 farmers in 14 state |  |  | 1361250 | GES | Pre-Qualification | Program | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Supply of organic fertilizer to another 3,500 farmers in 14 state |  |  | 1400000 | GES | Pre-Qualification | program | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
supply soil ammender/ Micro nutrient to another 3,000 farmers in 14 state |  |  | 1200000 | GES | Pre-Qualification | program | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
support to Expansion & Upgrading of 6 existing cottage sugarcane mill |  |  | 6000000 | NCB | Pre-Qualification | MTB | Plan | 01/04/14-1804/14 | 21/04/14-09/05/14 | 12/05/14-30/05/14 | 02/06/14-23/06/14 | 23/06/14 | 27/06/14-11/07/14 | NA | Plan | 6000000 | NA | 21/07/14-08/08/14 | 11/08/14-22/08/14 | 29/08/14-05/09/14 | 14/11/14-21/11/14 | 28/11/14-05/12/14
[7 empty] | Actual | [7 empty] | Actual
Support to 3 new farmers groups investor to establish cottage sugarcane milling/ethanol plants |  |  | 29000000 | NCB | Pre-Qualification | MTB | Plan | 01/04/14-1804/14 | 21/04/14-09/05/14 | 12/05/14-30/05/14 | 02/06/14-23/06/14 | 23/06/14 | 27/06/14-11/07/14 | NA | Plan | 29000000 | NA | 21/07/14-08/08/14 | 11/08/14-22/08/14 | 29/08/14-05/09/14 | 14/11/14-21/11/14 | 28/11/14-05/12/14
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  | #REF! | 85961250 |  |  |  | Plan | [7 empty] | Plan | #REF!
|  | #REF! | #REF! |  |  |  | Actual | [7 empty] | Actual | #REF!
Fill gray cells only!

## FDA SUGARCANE Works
Ministry/Department/Agency:
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 0 |  |  | Plan | [7 empty] | Plan | 0 | [6 empty] | 0
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## FDA SUGARCANE Consultants
Ministry/Department/Agency:
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 0 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 0 |  |  |  | Plan |  |  |  | 0
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!

## FDA SOYBEAN Goods
Ministry/Department/Agency: FDA
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: SOYBEAN |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Production of genetic materials (5mt of foundation seeds) |  |  | 2500000 | MoU | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
date
Production of genetic materials (100mt of foundation seeds) Breeder seeds |  |  | 30000000 | MoU | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Distribution of 2,000mt of improved soybean certified seeds to farmers by selected seed companies through GES |  |  | 106000000 | GES | Pre-Qualification |  | Plan | [7 empty] | Plan
Actual
Distribution of single superphospate (SSP) fertilizers to soybean farmers through GES |  |  | 80000000 | GES |  |  | Plan
Actual
Distribution of Herbicides (Pendimenthalin & Fusilade/Butachlor |  |  | 50000000 | GES |  |  | Plan
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  | #REF! | 138500000 |  |  |  | Plan | [7 empty] | Plan | #REF!
|  | #REF! | #REF! |  |  |  | Actual | [7 empty] | Actual | #REF!
Fill gray cells only!

## FDA SOYBEAN Works
Ministry/Department/Agency:
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 0 |  |  | Plan | [7 empty] | Plan | 0 | [6 empty] | 0
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## FDA SOYBEAN Consultants
Ministry/Department/Agency:
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 0 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 0 |  |  |  | Plan |  |  |  | 0
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!

## FDA SORGHUM Goods
Ministry/Department/Agency: FDA (SORGHUM VALUE CHAIN)
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #:SORGHUM |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Procurement of 25 Threshers |  |  | 6250000 | NCB | Pre-Qualification | MTB | Plan | 01/04/14-1804/14 | 21/04/14-09/05/14 | 12/05/14-30/05/14 | 02/06/14-23/06/14 | 23/06/14 | 27/06/14-11/07/14 | NA | Plan | 6250000 | NA | 21/07/14-08/08/14 | 11/08/14-22/08/14 | 29/08/14-05/09/14 | 14/11/14-21/11/14 | 28/11/14-05/12/14
[7 empty] | Actual | [7 empty] | Actual
date
Procurement of 1250MT of seed of seeds |  |  | 275000000 | GES | Pre-Qualification | Program | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Procurement of primary Sorghum milling machine |  |  | 12500000 | NCB | Pre-Qualification | MTB | Plan | 01/04/14-1804/14 | 21/04/14-09/05/14 | 12/05/14-30/05/14 | 02/06/14-23/06/14 | 23/06/14 | 27/06/14-11/07/14 | NA | Plan | 12500000 | NA | 21/07/14-08/08/14 | 11/08/14-22/08/14 | 29/08/14-05/09/14 | 14/11/14-21/11/14 | 28/11/14-05/12/14
[7 empty] | Actual | [7 empty] | Actual
Conduct baseline survey and market analysis for STVC |  |  | 24132000 | NCB | Pre-Qualification | MTB | Plan | 01/04/14-1804/14 | 21/04/14-09/05/14 | 12/05/14-30/05/14 | 02/06/14-23/06/14 | 23/06/14 | 27/06/14-11/07/14 | NA | Plan | 24132000 | NA | 21/07/14-08/08/14 | 11/08/14-22/08/14 | 29/08/14-05/09/14 | 14/11/14-21/11/14 | 28/11/14-05/12/14
[7 empty] | Actual | [7 empty] | Actual
Procurement of 25,000MT of fertilizer |  |  | 375000000 | GES | Pre-Qualification | Program | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Collaboration with ICRISAT for boosting the production, Utilization and commercialization of sorghum in Nigeria |  |  | 96000000 | MoU | Pre-Qualification | Program | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Train farmers on the operations and maintenance of sorghum Threshers and cottage milling equipment |  |  | 5000000 | MoU | Pre-Qualification | PS | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  | #REF! | 793882000 |  |  |  | Plan | [7 empty] | Plan | #REF!
|  | #REF! | #REF! |  |  |  | Actual | [7 empty] | Actual | #REF!
Fill gray cells only!

## FDA SORGHUM Works
Ministry/Department/Agency:
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 0 |  |  | Plan | [7 empty] | Plan | 0 | [6 empty] | 0
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## FDA SORGHUM Consultants
Ministry/Department/Agency:
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 0 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 0 |  |  |  | Plan |  |  |  | 0
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!

## FDA RUBBER Goods
Ministry/Department/Agency: FDA
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: RUBBER |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Procurement of 450,000 budded Rubber stump |  |  | 67500000 | MoU | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
date
Establishment of Rubber based cropping system demostration plots two/state in the 15 Rubber producing State |  |  | 15000000 | MoU | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Establishment of 5 unit sheeting battery processing equipment in 5 selected Rubber producing state |  |  | 25000000 | MoU | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Procurement of 15,000 bags of inorganic Fertilizer, organic and soil Amender/ Micro Nutrient |  |  | 200000000 | GES | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
procurement of 45,000 litre of Glyphosate |  |  | 88000000 | GES | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  | #REF! | 395500000 |  |  |  | Plan | [7 empty] | Plan | #REF!
|  | #REF! | #REF! |  |  |  | Actual | [7 empty] | Actual | #REF!
Fill gray cells only!

## FDA RUBBER Works
Ministry/Department/Agency:
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 0 |  |  | Plan | [7 empty] | Plan | 0 | [6 empty] | 0
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## FDA RUBBER Consultants
Ministry/Department/Agency:
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 0 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 0 |  |  |  | Plan |  |  |  | 0
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!

## FDA RICE Goods
Ministry/Department/Agency: FDA
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #:RICE |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Procurement and distribution of improved rice seed |  |  | 1270000000 | GES | Pre-Qualification | NA | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 13158688.3 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
Procurement of Fertilizer |  |  | 770000000 | GES | Pre-Qualification | NA | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 13158688.3 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
Procurement of Agrochemical |  |  | 140000000 | NCB | Pre-Qualification | MTB | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Procurement of irrigation pumps and pipe |  |  | 164000000 | NCB | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Procurement of Destoner |  |  | 15000000 | NCB | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Procurement of parboilers |  |  | 3000000 | NS | Pre-Qualification | PS | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Fabrication and Manufacturing of Dryer |  |  | 70000000 | MoU | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Procurement of Reapers |  |  | 30960000 | NCB | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Procurement of Knapsack sprayer |  |  | 10000000 | NCB | Pre-Qualification |  | Plan
Actual
Establishment of Sawah Eco-technology farm |  |  | 50000000 | MoU | Pre-Qualification |  | Plan
Actual
Fabrication and manufacture of ATAT thresher |  |  | 50000000 | MoU | Pre-Qualification |  | Plan
Actual
MoU with AfricaRice for capacity building in seed production and post harvest seed handling |  |  | 10000000 | MoU | Pre-Qualification |  | Plan
Actual
Development of Market information system in rice value chain |  |  | 18179250 | MoU | Pre-Qualification |  | Plan
Actual
Hybrid Rice Development |  |  | 11000000 | MoU | Pre-Qualification |  | Plan
Actual
Total Cost |  | #REF! | 2662139250 |  |  |  | Plan | [7 empty] | Plan | #REF!
|  | #REF! | #REF! |  |  |  | Actual | [7 empty] | Actual | #REF!
Fill gray cells only!

## FDA RICE Works
Ministry/Department/Agency:
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 0 |  |  | Plan | [7 empty] | Plan | 0 | [6 empty] | 0
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## FDA RICE Consultants
Ministry/Department/Agency:
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 0 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 0 |  |  |  | Plan |  |  |  | 0
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!

## FDA SESAME Goods
Ministry/Department/Agency: FDA (SESAME VALUE CHAIN)
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: SESAME |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
provision of Organic fertilizer, herbicide, fungicide, insecticide and inorganic |  |  | 26250000 | GES | Pre-Qualification | program | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 13158688.3 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
date
Provision of cleaning and sorting machine |  |  | 12000000 | NCB | Pre-Qualification | MTB | Plan | 01/04/14-1804/14 | 21/04/14-09/05/14 | 12/05/14-30/05/14 | 02/06/14-23/06/14 | 23/06/14 | 27/06/14-11/07/14 | NA | Plan | 12000000 | NA | 21/07/14-08/08/14 | 11/08/14-22/08/14 | 29/08/14-05/09/14 | 14/11/14-21/11/14 | 28/11/14-05/12/14
[7 empty] | Actual | [7 empty] | Actual
Provision for project Vehicle |  |  | 5000000 | NCB | Pre-Qualification | Direct procurement | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | 5000000 | NA | NA | NA | NA | NA | NA
[7 empty] | Actual | [7 empty] | Actual
Production of 2mt of breeder seed |  |  | 4000000 | MoU | Pre-Qualification | PS | Plan | NA | NA | NA | NA | NA | NA | NA | Plan | 4000000 | NA | NA | NA | NA | NA | NA
[7 empty] | Actual | [7 empty] | Actual
Procurement of foundation seed |  |  | 7000000 | MoU | Pre-Qualification | MTB | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Procurement of certified seed |  |  | 26000000 | MoU | Pre-Qualification | MTB | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Production of Acha Certifieds |  |  | 5000000 | MoU | Pre-Qualification | PS | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  | #REF! | 85250000 |  |  |  | Plan | [7 empty] | Plan | #REF!
|  | #REF! | #REF! |  |  |  | Actual | [7 empty] | Actual | #REF!
Fill gray cells only!

## FDA SESAME Works
Ministry/Department/Agency:
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 0 |  |  | Plan | [7 empty] | Plan | 0 | [6 empty] | 0
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## FDA SESAME Consultants
Ministry/Department/Agency:
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 0 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 0 |  |  |  | Plan |  |  |  | 0
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!

## FDA MAIZE Goods
Ministry/Department/Agency: FDA (MAIZE VALUE CHAIN)
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: MAIZE |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Production of foundation seeds of released improved stress tolerant maize varieties to seed companies for use in generating certified seeds for farmers |  |  | 50000000 | MoU | Pre-Qualification | MTB | Plan | NA | NA | NA | N A | NA | NA | NA | Plan | 50000000 | NA | NA | NA | NA | NA | NA
[7 empty] | Actual | [7 empty] | Actual
Generate adequate growth as of inbed lines and parents of single and top cross hybrids respectively for generating newer hybrids by seed companies |  |  | 25000000 | MoU | Pre-Qualification | MTB | Plan | NA | NA | NA | N A | NA | NA | NA | Plan | 25000000 | NA | NA | NA | NA | NA | NA
[7 empty] | Actual | [7 empty] | Actual
GES of seeds to plant about 1,200,000ha for Herbicides (7.2million litres) and Seed dresser (12million kg) |  |  | 334000000 | GES | Pre-Qualification | program | Plan | NA | NA | NA | N A | NA | NA | NA | Plan | 334000000 | NA | NA | NA | NA | NA | NA
[7 empty] | Actual | [7 empty] | Actual
GES on Fertilizer to farmers i. NPK: 27-13-13 (200,000bags) ii. Urea (200,000 bags) iii. Micronutrient |  |  | 399000000 | GES | Pre-Qualification | program | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  | #REF! | 808000000 |  |  |  | Plan | [7 empty] | Plan | #REF!
|  | #REF! | 0 |  |  |  | Actual | [7 empty] | Actual | #REF!
Fill gray cells only!

## FDA MAIZE Works
Ministry/Department/Agency:
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 0 |  |  | Plan | [7 empty] | Plan | 0 | [6 empty] | 0
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## FDA MAIZE Consultants
Ministry/Department/Agency:
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 0 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 0 |  |  |  | Plan |  |  |  | 0
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!

## FDA HORT. Goods
Ministry/Department/Agency: FDA (HORTICULTURE VALUE CHAIN)
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #:HORTICULTURE |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Procurement of 0.75mt UC&2B hybrid tomato seeds |  |  | 22500000 | NCB | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
date
Procurement of 0.75mt Roma VF Hybrid tomato seeds |  |  | 22500000 | NCB | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Procurement of 1.5mt Okra seeds |  |  | 33750000 | NCB | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Procurement of 1.0mt Onion (red Creole) seeds |  |  | 45000000 | NCB | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Procurement of 27.5mt Ugu seeds |  |  | 44000000 | NCB | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Project Vehicle |  |  | 5500000 | Direct procurement | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Procurement of 30mt Z-Force (Fungicide) |  |  | 45000000 | NCB | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Procurement of 11,200 litres Polythrin and Karate (Incsecticide) |  |  | 42000000 | NCB | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Procurement of 11,200 litres Gramozone supper and touchdown |  |  | 42000000 | NCB | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Legal framework on fresh produce production for export |  |  | 20000000 | Consultancy | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
support for the establishmentof a centre of Excellence (Competant Authority) |  |  | 70000000 | Consultancy | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Support to 3 Nos Universities of Agriculture to carry out adaptability and yield potential trials on new varieties vegetables seed |  |  | 12000000 | MoU | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Establ;ishment of a horticultural crops marketing platform to facilitate marketing of fresh produce both local and international |  |  | 30000000 | Consultancy | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Development of working document on Pineapple TCP with FAO for the South west Region |  |  | 1500000 | Consultancy | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
fabrication of 1no on-farm small scale processing equipment in collaboration with wilbahi investment and National Research Institute for chemical technology |  |  | 8000000 | PPP | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Production of 52,000 Citrus and 50,000 Mango seedlings improved varieties by college of Agric. Ibadan and NIHORT, Ibadan |  |  | 51000000 | MoU | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Support to NIHORT plan for young Breeders initiation horticultural crops (Tomato and Telfairia- Ugu) production |  |  | 6000000 | MoU | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  | #REF! | 550750000 |  |  |  | Plan | [7 empty] | Plan | #REF!
|  | #REF! | 0 |  |  |  | Actual | [7 empty] | Actual | #REF!
Fill gray cells only!

## FDA HORT. Works
Ministry/Department/Agency:
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 0 |  |  | Plan | [7 empty] | Plan | 0 | [6 empty] | 0
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## FDA HORT. Consultants
Ministry/Department/Agency:
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 0 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 0 |  |  |  | Plan |  |  |  | 0
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!

## FDA GINGER Goods
Ministry/Department/Agency: FDA (GINGER VALUE CHAIN)
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #:GINGER |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Production of 12mt Breeder ginger seed (yellow variety) |  |  | 5760000 | MoU | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
date
Production of 20mt of foundation ginger seed (yellow variety) |  |  | 6000000 | MoU | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Provision of 1000 bags of NPK 15:15:17-2 and 1000 bags of Urea |  |  | 6000000 | GES | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Production and distribution of 180mt certified seeds (yellow variety) |  |  | 6000000 | MoU | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
MoU with food crop production Technology transfer station (FCPTTS) to produce & distribute 55mt certified Ginger seed (yellow) |  |  | 11000000 | MoU | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Procurement and distribution of 3,000 ltrs of Diupop and 3000 litres Gramazone |  |  | 4500000 | MTB | Pre-Qualification |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  | #REF! | 39260000 |  |  |  | Plan | [7 empty] | Plan | #REF!
|  | #REF! | #REF! |  |  |  | Actual | [7 empty] | Actual | #REF!
Fill gray cells only!

## FDA GINGER Works
Ministry/Department/Agency:
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 0 |  |  | Plan | [7 empty] | Plan | 0 | [6 empty] | 0
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## FDA GINGER Consultants
Ministry/Department/Agency:
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 0 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 0 |  |  |  | Plan |  |  |  | 0
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!

## FDA G.NUT Goods
Ministry/Department/Agency: FDA (GROUNDNUT VALUE CHAIN)
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: G.NUT |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Procurement of 1200mt of Certified seed, 750mt of foundation and 400mt of breeder seed for farmers |  |  | 13158688.3 | GES | Pre-Qualification | program | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 13158688.3 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
date
Procurement of single Superphosphate fertilizer for farmers |  |  | 60422549.36 | GES | Pre-Qualification | program | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 60422549.36 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
Procurement of 1850kg of fungicide for farmers |  |  | 7049297.42 | GES | Pre-Qualification | program | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 7049297.42 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
Procuurement of 1500 ltrs of insecticide for farmers |  |  | 14098594.85 | GES | Pre-Qualification | program | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 14098594.85 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
Procurement of 25000 ltrs of herbicides for farmers |  |  | 56394379.4 | GES | Pre-Qualification | program | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 8118209.62 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
Base line studies to provide benchmark for project impact assessment |  |  | 8118209.62 | MoU | Pre-Qualification | MTB | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
conducting participatory varietal selection (PVS) trials |  |  | 2621945.6 | MoU | Pre-Qualification | PS | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Identify and disseminate improved technologies for village level cottage (groundnut oil extraction and other by product) |  |  | 4192306.75 | MoU | Pre-Qualification | PS | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Procurement of small scale groundnut processingmachine |  |  | 11250000 | NCB | Pre-Qualification | MTB | Plan | 01/04/14-18/04/14 | 21/04/14-09/05/14 | 12/05/14-30/05/14 | 02/06/14-223/06/14 | 23/06/14 | 27/06/14-11/07/14 | NA |  | 11250000 | NA | 21/07/14-08/08/14 | 11/08/14-22/08/14 | 29/08/14-05/09/14 | 14/11/14-21/11/14 | 28/11/14-05/12/14
Actual
[5 empty] | Pre-Qualification |  | Plan
Actual
[5 empty] | Pre-Qualification |  | Plan
Actual
[5 empty] | Pre-Qualification |  | Plan
Actual
[5 empty] | Pre-Qualification |  | Plan
Actual
[5 empty] | Pre-Qualification |  | Plan
Actual
[5 empty] | Pre-Qualification |  | Plan
Actual
[5 empty] | Pre-Qualification |  | Plan
Actual
Pre-Qualification
Pre-Qualification
Total Cost |  | #REF! | #REF! |  |  |  | Plan | [7 empty] | Plan | #REF!
|  | #REF! | #REF! |  |  |  | Actual | [7 empty] | Actual | #REF!
Fill gray cells only!

## FDA G.NUT Works
Ministry/Department/Agency:
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 0 |  |  | Plan | [7 empty] | Plan | 0 | [6 empty] | 0
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## FDA G.NUT Consultants
Ministry/Department/Agency:
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 0 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 0 |  |  |  | Plan |  |  |  | 0
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!

## FDA COTTON Goods
Ministry/Department/Agency: FDA (COTTON VALUE CHAIN)
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #:COTTON |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
GES on 1,650mt certified seed to support 82,500 farmers |  |  | 198000000 | GES | Pre-Qualification | program | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 198000000 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
Provission of Agrochemicals 257,000 litres of insecticide and 257,000 of herbicides to support 128,500 farmers |  |  | 257000000 | GES | Pre-Qualification | program | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 257000000 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
provision of 10,432 bags of NPK and 10,432 bags of urea |  |  | 114750000 | GES | Pre-Qualification | program | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 114750000 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
Provision of 10,000litre of biostimulant to support 10,000 farmers |  |  | 30000000 | GES | Pre-Qualification | program | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 30000000 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
Procurement of 339,167 units of Cotton harvest sack to support 28,264 farmers at 12 units per farmer |  |  | 122100000 | NCB | Pre-Qualification | MTB | Plan | 01/04/14-18/04/14 | 21/04/14-09/05/14 | 12/05/14-30/05/14 | 02/06/14-223/06/14 | 23/06/14 | 27/06/14-11/07/14 | NA |  | 122100000 | NA | 21/07/14-08/08/14 | 11/08/14-22/08/14 | 29/08/14-05/09/14 | 14/11/14-21/11/14 | 28/11/14-05/12/14
Actual
Payment to Institute for Agricultural Research, Ahmadu Bello University for the turn over of all available Breeder and foundation seeds |  |  | 129970000 | MoU |  | FEC
Actual
Total Cost |  | #REF! | 721850000 |  |  |  | Plan | [7 empty] | Plan | #REF!
|  | #REF! | #REF! |  |  |  | Actual | [7 empty] | Actual | #REF!
Fill gray cells only!

## FDA COTTON Works
Ministry/Department/Agency:
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 0 |  |  | Plan | [7 empty] | Plan | 0 | [6 empty] | 0
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## FDA COTTON Consultants
Ministry/Department/Agency:
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 0 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 0 |  |  |  | Plan |  |  |  | 0
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!

## FDA COCOA Goods
Ministry/Department/Agency: FDA (COCOA VALUE CHAIN)
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: COCOA |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Seedlings (1,125,600) million pods |  |  | 29040000 | GES | Pre-Qualification | Program | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
date
Production of hybride pods- WACRI II 375,000 no @ N60.00 by Ondo Tree Crops |  |  |  | on-going |  |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
date
Production of 30% payment for production of hybrids Cocoa pods WACRI II 300,000 no by Osun State |  |  |  | on-going |  |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
date
Provission of 30% payment for production of hybrides Cocoa pods WACRI II 450,600 no by CRIN (2014) |  |  |  | on-going |  |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
date
Provission of 30% payment for production of hybrides Cocoa pods WACRI II by Ekiti State CRIN (2014) |  |  |  | on-going |  |  | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
date
Fungicide (100,000 farmers receive 100 sachets each at 50% support) | [6 empty] | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
date
Ridomil Gold Plus 2million saachets |  |  | 260000000 | GES | Pre-Qualification | program | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 260000000 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
Funguran-Oh 2million sachets |  |  | 260000000 | GES | Pre-Qualification | program | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 260000000 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
Ultimax Plus 2million sachets |  |  | 200000000 | GES | Pre-Qualification | program | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 200000000 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
Cham DP 2million sachets |  |  | 160000000 | GES | Pre-Qualification | program | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 160000000 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
Kocide 2000 2million sachets |  |  | 180000000 | GES | Pre-Qualification | program | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 180000000 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
Actara 1.25million sachets |  |  | 75000000 | GES | Pre-Qualification | program | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 75000000 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
Proteus-170, 100,000packs |  |  | 65000000 | GES | Pre-Qualification | program | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 65000000 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
Teractive Cocoa |  |  | 175000000 | GES | Pre-Qualification | program | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 175000000 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
Cocoa Boost fertilizer 500bags |  |  | 175000000 | GES | Pre-Qualification | program | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 175000000 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
Procurement of 1,289 bale of hydrocabon free jute bags (300 pieces/bale) |  |  | 122455000 | NCB | Pre-Qualification | FEC | Plan | 01/04/14-18/04/14 | 21/04/14-09/05/14 | 12/05/14-30/05/14 | 02/06/14-223/06/14 | 23/06/14 | 27/06/14-11/07/14 | 14/07/14-21/07/14 |  | 122455000 | 14/07/14-21/07/14 | 21/07/14-08/08/14 | 11/08/14-22/08/14 | 29/08/14-05/09/14 | 14/11/14-21/11/14 | 28/11/14-05/12/14
[7 empty] | Actual | [7 empty] | Actual
Procurement of 1,500 units of Spraying equipment: solo pump (England) |  |  | 15000000 | NCB | Pre-Qualification | MTB | Plan | 01/04/14-18/04/14 | 21/04/14-09/05/14 | 12/05/14-30/05/14 | 02/06/14-223/06/14 | 23/06/14 | 27/06/14-11/07/14 | NA |  | 50390750 | NA | 21/07/14-08/08/14 | 11/08/14-22/08/14 | 29/08/14-05/09/14 | 14/11/14-21/11/14 | 28/11/14-05/12/14
[7 empty] | Actual | [7 empty] | Actual
Procurement of 14,100,833 polythen bags |  |  | 42302500 | NCB | Pre-Qualification | MTB | Plan | 01/04/14-18/04/14 | 21/04/14-09/05/14 | 12/05/14-30/05/14 | 02/06/14-223/06/14 | 23/06/14 | 27/06/14-11/07/14 | NA |  | 50390750 | NA | 21/07/14-08/08/14 | 11/08/14-22/08/14 | 29/08/14-05/09/14 | 14/11/14-21/11/14 | 28/11/14-05/12/14
[7 empty] | Actual | [7 empty] | Actual
Procurement and Installation of small and medium scale cottage Chocolate making plant (Cacao Cucuna, FL, USA) 5 No. in partnership with interested investor at 50% cost |  |  | 120000000 | NCB | Pre-Qualification | FEC | Plan | 01/04/14-18/04/14 | 21/04/14-09/05/14 | 12/05/14-30/05/14 | 02/06/14-223/06/14 | 23/06/14 | 27/06/14-11/07/14 | NA |  | 50390750 | NA | 21/07/14-08/08/14 | 11/08/14-22/08/14 | 29/08/14-05/09/14 | 14/11/14-21/11/14 | 28/11/14-05/12/14
[7 empty] | Actual | [7 empty] | Actual
Tissue culture testing of selected cocoa clones in Nigeria (CocTA/Univ of Ibadan) |  |  | 35000000 | MoU | Pre-Qualification | MTB | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Research for selection of adapted high yielding clones for generation of cocoa plantations and establishment of clonal plation in Nigeria (CocTA/CRIN) |  |  | 50390750 | MoU | Pre-Qualification | MTB | Plan
[7 empty] | Actual | [7 empty] | Actual
community level budwood/seed garden in 10 states |  |  | 72184250 | MoU | Pre-Qualification | MTB | [8 empty] | Plan
Actual
Four wheel drive Hilux Pick up |  |  | 8000000 | MTB | Pre-Qualification | MTB
Actual
Total Cost |  | #REF! | 2219372500 |  |  |  | Plan | [7 empty] | Plan | #REF!
|  | #REF! | #REF! |  |  |  | Actual | [7 empty] | Actual | #REF!
Fill gray cells only!

## FDA COCOA Works
Ministry/Department/Agency:
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 0 |  |  | Plan | [7 empty] | Plan | 0 | [6 empty] | 0
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## FDA COCOA Consultants
Ministry/Department/Agency:
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 0 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 0 |  |  |  | Plan |  |  |  | 0
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!

## FDA CASSAVA Goods
Ministry/Department/Agency: FDA (CASSAVA VALUE CHAIN)
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: CASSAVA |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Establishment of 163 ha of high starch yielding varieties |  |  | 25200000 | MoU | Pre-Qualification | MTB | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
date
172,045 bundle to be supplied by NRCRI |  |  | 94624750 | MoU | Pre-Qualification | MTB | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
344,091 bundles to be supplied RTEB |  |  | 189250000 | MoU | Pre-Qualification | FEC | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
172,045 bundles to be supplied by IITA |  |  | 94624750 | MoU | Pre-Qualification | MTB | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
supply of 13,091 Cassava specific fertilizer (12-12-17+2MgO) |  |  | 18000000 | MoU | Pre-Qualification | MTB | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Organic fertilizer |  |  | 1400000 | MoU | Pre-Qualification | PS | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Soil Amender/ micronutrients |  |  | 1200000 | MoU | Pre-Qualification | PS | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
Agro Processing facilicities |  |  | 74400000 | NCB | Pre-Qualification | MTB | Plan | 01/04/14-1804/14 | 21/04/14-09/05/14 | 12/05/14-30/05/14 | 02/06/14-23/06/14 | 23/06/14 | 27/06/14-11/07/14 | NA | Plan | 74400000 | NA | 21/07/14-08/08/14 | 11/08/14-22/08/14 | 29/08/14-05/09/14 | 14/11/14-21/11/14 | 28/11/14-05/12/14
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  | #REF! | 472299500 |  |  |  | Plan | [7 empty] | Plan | #REF!
|  | #REF! | #REF! |  |  |  | Actual | [7 empty] | Actual | #REF!
Fill gray cells only!

## FDA CASSAVA Works
Ministry/Department/Agency:
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 0 |  |  | Plan | [7 empty] | Plan | 0 | [6 empty] | 0
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## FDA CASSAVA Consultants
Ministry/Department/Agency:
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 0 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 0 |  |  |  | Plan |  |  |  | 0
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!

## fda cashew Goods
Ministry/Department/Agency: FDA (CASHEW VALUE CHAIN)
Budgetary Year: 2014 | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: CASHEW |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Estimated Amount in Naira | Procurement Method | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date Contract Offer | Date Contract Signature | Mobilization Advance Payment | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 wks | 1 - 2 wks | 3 wks
[5 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
Procurement of 20,000kg Brazilian jumbo variety of cashew seed @ N1000/kg from CRIN |  |  | 20000000 | MoU | Pre-Qualification | MTB | Plan | [7 empty] | Plan
[7 empty] | Actual | [7 empty] | Actual
date
Procurement of 1,833 Bags of fertilizer@ N6,000/bag |  |  | 11000000 | GES | Pre-Qualification | MTB | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 11000000 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
Procurement of 10,000 litres of agrochemical (Glyphosate) @N1,000/litre |  |  | 10000000 | GES | Pre-Qualification | Program | Plan | 06/01/14-20/01/14 | NA | 30/01/14-17/02/14 | 30/01/14 | 17/01/14 | 24/02/14-10/03/14 | NA | Plan | 11000000 | NA | 28/03/14 | 31/03/14-11/04/14 | NA | 14/04/14-25/04/14 | 30/04/14
[7 empty] | Actual | [7 empty] | Actual
Establishment of Two 2 unit of Cashew small scale processing equipment @N20m each |  |  | 40000000 | NCB | Pre-Qualification | MTB | Plan | 01/04/14-1804/14 | 21/04/14-09/05/14 | 12/05/14-30/05/14 | 02/06/14-23/06/14 | 23/06/14 | 27/06/14-11/07/14 | NA | Plan | 40000000 | NA | 21/07/14-08/08/14 | 11/08/14-22/08/14 | 29/08/14-05/09/14 | 14/11/14-21/11/14 | 28/11/14-05/12/14
[7 empty] | Actual | [7 empty] | Actual
Procurement of 70 bales of carbon free jute bags for raw cashew nuts (RCN) seed storage |  |  | 7000000 | NCB | Pre-Qualification | MTB | Plan | 01/04/14-1804/14 | 21/04/14-09/05/14 | 12/05/14-30/05/14 | 02/06/14-23/06/14 | 23/06/14 | 27/06/14-11/07/14 | NA | Plan | 7000000 | NA | 21/07/14-08/08/14 | 11/08/14-22/08/14 | 29/08/14-05/09/14 | 14/11/14-21/11/14 | 28/11/14-05/12/14
[7 empty] | Actual | [7 empty] | Actual
Procurement of 60 Unit Solo pumps (England) @100,00/pump |  |  | 6000000 | NCB | Pre-Qualification | MTB | Plan | 01/04/14-1804/14 | 21/04/14-09/05/14 | 12/05/14-30/05/14 | 02/06/14-23/06/14 | 23/06/14 | 27/06/14-11/07/14 | NA | Plan | 6000000 | NA | 21/07/14-08/08/14 | 11/08/14-22/08/14 | 29/08/14-05/09/14 | 14/11/14-21/11/14 | 28/11/14-05/12/14
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  | #REF! | 94000000 |  |  |  | Plan | [7 empty] | Plan | #REF!
|  | #REF! | 0 |  |  |  | Actual | [7 empty] | Actual | #REF!
Fill gray cells only!

## fda cashew Works
Ministry/Department/Agency:
Budgetary Year: 2014 | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Desk Officer/Contact #: |  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Project Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Budgetary Amount in Naira | Pre-or Post Qualification | Approval Threshold | Plan vs. Actual | Prep & Submission by MDAs | No-objection Date | Advertisement for Pre-Qualification | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount Certified in N | FEC Approval | Date of Contract Offer | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 2 - 3 wks | 1 - 2 wks | 2 wks | 2 to | 6 wks | 2 - 3 wks | 1 - 2 wks | Plan |  | 2 - 4 wk | 1 - 2 wks | 3 wks
[6 empty] | add 2 wks |  | Actual | [7 empty] | Actual
List of Contracts
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | [7 empty] | Plan
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 0 |  |  | Plan | [7 empty] | Plan | 0 | [6 empty] | 0
[5 empty] | 0 |  |  | Actual | [7 empty] | Actual | 0 | [6 empty] | 0
Fill gray cells only!

## fda cashew Consultants
Ministry/Department/Agency:
Budgetary Year: 2014 |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for Expression of Interest (when required)
Desk Officer/Contact #: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiation (N) | [7 empty] | Contract Finalization |  |  |  |  | Contract Implementation
Project Description* | Selection Method | Lumpsum or Time-Based | Budgetary Amount in Naira | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Approval Threshold | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in Naira | Contract ward | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 4 wks | 2 wks | 2 wks | 2 wks |  | 2 wks | Plan | 4 to | 8 wks | 3 wks | 2 wks | 2 wks | 2 wks | 2 wks | Plan | 2 wks | 2 wks |  | 4 wk |  | 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
[5 empty] | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 0 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | 0 |  |  |  | Plan |  |  |  | 0
|  |  | 0 |  | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  | 0 |  |  |  | Actual |  |  |  | 0
Fill gray cells only!